Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	March 2018

Title: Food and Agriculture Organization (FAO): Core Assessed Contribution 2016-17
Programme Code: 204147-101	Start Date: January 2016	End Date: December 2017
If programme was closed >1 month early please describe in a few words why.	N/A

Summary of Programme

Year	2016	2017
Programme Score	A	A
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review
The last Annual Review for the UK core assessed contribution to FAO in the 2016-2017 biennium was completed in May 2017. This reviewed progress during 2016 and concluded that it met expectations (and scored A). This project completion review (PCR) considers FAO’s progress for the entire biennium, (2016 and 2017) and draws on FAO reporting to its governing bodies, the deliberations of those bodies as well as informal meetings with FAO, and feedback from colleagues working with FAO from across DFID.

Global increases in the numbers of people facing food insecurity during 2016 and 2017 suggest that the impact indicator (the prevalence of food insecurity) for the UK core contribution to FAO deteriorated in 2016 and 2017. At the time of writing this report, FAO is still working on the outcome assessment and cannot yet provide a definitive calculation of the percentage of corporate outcomes achieved in 2016 and 2017. The final achievement against the target of 80% outcomes achieved will be reported in FAO’s Programme Implementation Report (PIR) to be published in April 2018. It is possible that this target may not have been met.  However, at output level, FAO is expected to exceed many of its targets and this PCR considers that FAO has met expectations (and scored A). The potential divergence between FAO’s output targets which have been exceeded and its outcome target which may be missed illustrates the importance of articulating the links between outputs and outcomes. Where these links are not clearly visible, this limits the opportunities to consider how progress in delivering outputs  is linked to FAO’s desired outcomes. The review makes a number of recommendations for DFID (UKREP’s) work with FAO over the 2018-2019 biennium which are set out below.

DFID’s Multilateral Development Review (MDR) was published in 2016 and made a number of suggestions to improve FAO performance and FAO has made progress with these. Key highlights include, FAO’s publication of data to the International Aid Transparency Initiative (IATI) in May 2017 and is the agreement of FAO’s Climate Change Strategy in June 2017 and an action plan to implement it.

Recommendations from the last Annual Review for the UK’s core assessed contribution to FAO are set out below with progress updates in bold:

1. DFID and FAO should agree indicators and targets for improvements in the agreed priority areas and include these in a finalised performance agreement for the 2017 to 2020 period. Ongoing. DFID and FAO discussed potential indicators which are included in a draft performance agreement that will be finalised in May 2018.
2. DFID should review and update this annual review once FAO’s MTR report is available. Completed in May 2017.
3. DFID should review FAO’s revised strategic results framework when it is presented to FAO’s Programme Committee to ensure that it includes improved results targets in priority areas. Completed. DFID has done this with mixed success: FAO will use more specific indicators to monitor audit recommendation implementaton but has not included specific targets for progress with AMR in its strategic results framework. Nonetheless, FAO did include AMR as a new priority its Programme of Work and Budget (PWB) allocating core (assessed) resources for three new posts to focus on AMR starting in 2018.
4. DFID should consider aligning our annual review process with FAO’s results reporting timetable for the next biennium (2018-19). Ongoing. DFID will do this so that the first annual review for the 2018-2019 biennium will be due in May 2019, once the mid-term review for the biennium is available.
5. The implementation of the Performance Management System (PEMS) is welcome. FAO should continue to monitor its implementation and report on this to its Finance Committee. FAO could consider setting performance targets for the PEMS. Ongoing. As reported in the Progress Report on Implementation of the External Auditor's Recommendations submitted to the Finance Committee, quality assurance mechanisms were established in 2017 for the Performance Evaluation and Management System (PEMS). (FC 169/11; see recommendations 5 and 6)
6. FAO should consider how to increase the transparency of its reporting on Human Resources (HR) management performance. No progress. In November 2017, FAO’s Finance Committee (FC) found that there was insufficient data and information in the HR management report to substantiate FAO’s analysis of progress (CL 158/7 para 23).
7. The Finance Committee (November 2016) recommended that FAO further improve communications between management and staff representative bodies. DFID should monitor the follow up to this recommendation. No progress. Staff representative bodies have the opportunity to address FAO Council. Their interventions suggest that communications and transparency continues to need improvement.
8. DFID and FAO to include FAO’s commitment to publish its disbursement information with IATI by April 2017 in our performance agreement. DFID (UKREP) to urge FAO to include this commitment in its revised results framework and monitor progress with this. Ongoing, good progress. FAO published disbursement information with IATI in early May 2017. DFID used European interventions at the March 2017 Programme Committee to ask FAO to include the commitment and a KPI in its results framework. Although this was not taken forward as a KPI, FAO remains committed to publishing expenditure information with IATI.
9. DFID (UKREP) to continue to encourage FAO to enhance efficiency through its programmes, continuing to report on savings made and train staff to “embed a culture of value for money”. Ongoing. UKREP has used EU and Member State and national statements at FAO governing body meetings to call for more focus across the organisation on Value for Money. FAO has delivered savings as agreed in the programme of work and budget (PWB) for 2016 - 2017 and identified further administrative savings in the PWB for 2018 – 2019 which will fund 59 additional technical specialist posts.
10. DFID (UKREP) to monitor FAO progress in improving project management and procurement and use meetings of the governing bodies to press for progress. Ongoing. UKRep pressed FAO management to include a KPI target for programme management in the November 2017 Programme Committee (PC). The PC supported measures to monitor FAO programmes and projects with the aim of improving their quality (see CL158/5 para 4i)
11. DFID (UKREP) should continue to monitor the implementation of FAO’s Enterprise Risk Management (ERM) and its corporate risk log when this is published; DFID (UKREP) should review and update its own risk assessment when the corporate risk log is published. DFID and FAO should consider including key progress milestones in a performance agreement with FAO e.g. completion of FAO’s statement of internal control by end 2017. Ongoing. UKRep Rome updated its own risk register in November 2017 and discussed FAO’s progress at the strategic dialogue meeting in January 2018. FAO’s statement of internal control will be completed in April 2018 and any follow up actions should be included as progress milestones in the UK FAO performance agreement.
12. DFID (UKREP) to monitor the implementation of the recommendations from FAO’s evaluation of its evaluation function and use meetings of the governing bodies to press for progress. Ongoing. UKRep raised this issue with the November 2017 Programme Committee (PC) and FAO has agreed to prepare an update on progress with these recommendations for discussion with the Programme Committee (CL158/5 footnote 4).
13. DFID (UKREP) should review the annual reviews prepared by the DFID country offices providing voluntary / bilateral funding to FAO. DFID (UKREP) should offer them the opportunity to provide feedback for inclusion in both the next review of DFID’s assessed contribution to FAO and our next annual strategic dialogue meeting with FAO. Completed January 2018. While all these projects were meeting expectations, many involved FAO and other partners so progress could not be attributed to FAO specifically. Feedback from their senior responsible owners did provide useful background for the UK FAO strategic dialogue meeting in January 2018.

Financial Position

Original Programme Value	£35,000,000.00
Extensions/ amendments	N/A
Log-frame revisions (with dates)	N/A
Total programme spend	£37,191,215.27

Follow up actions required following closure

PCR Recommendation 1: DFID (UKREP) should continue to encourage FAO to strengthen the links between the activities it invests in, their outputs and the outcomes that FAO expects to achieve. A key issue which DFID UKREP should raise with FAO’s Programme Committee is how FAO’s programmes will adapt to take account of conflict-driven growing food insecurity.

PCR Recommendation 2: DFID (UKREP) should monitor FAO’s implementation of recommendations from internal, external auditors and the Finance Committee for improvements to FAO’s HR management and include indicators of progress with this in the UK FAO performance agreement.

PCR Recommendation 3: DFID (UKREP) should continue to work with other member states to encourage FAO to strengthen the measures it has in place to prevent and respond to sexual harassement (e.g. of staff) as well as sexual exploitation and abuse (e.g. of beneficiaries) including encouraging staff and others to report their concerns.

PCR Recommendation 4. As recommended in the last Annual Review, DFID and FAO to include FAO’s commitment to publish its disbursement information with IATI in the UK FAO performance agreement to be agreed in May 2018.

PCR Recommendation 5: DFID should scrutinise FAO’s Statement of Internal Control and Anti-Fraud action plan when they are published in 2018 and identify specific actions to be included in the UK FAO performance agreement

PCR Recommendation 6: DFID should also include FAO’s KPI on implementing audit recommendations in the UK FAO performance agreement and continue to encourage FAO to strengthen its internal controls and risk management.

PCR Recommendation 7: DFID should consider a focus on FAO’s work to increase the resilience of livelihoods to threats and crises when updating the theory of change and logical framework for the UK core assessed contribution to FAO for 2018-2019.

A. Introduction and Context (1 page)

DevTracker Link to concept note:	https://devtracker.dfid.gov.uk/projects/GB-1-204147/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204147/documents

Outline of programme and what it has achieved
The Food and Agriculture Organisation (FAO) is a United Nations specialised agency and has a global leadership role in food and agriculture setting norms and standards and agreeing international treaties. The UK has been a member of FAO since its inauguration in 1945. FAO provides technical assistance and policy advice to governements to help to support the most vulnerable. It aims to eliminate food and hunger, including malnutrition, in line with the SDGs.

FAO contributes to DFID objectives through its focus on SDGs 1 and 2 to end poverty and hunger. Its work also contributes to 14 of the 17 other SDGs including on climate, gender, jobs, life on land, and below water. FAO is also the custodian of 21 SDG indicators. There is no system-wide agreement on funding the monitoring of the SDGs and FAO is working now to develop the means to support countries in gathering data and monitoring progress. FAO works on issues relating to land tenure and responsible agricultural investment, including through its policy support to the Committee on World Food Security (CFS).

Beyond the SDGs, FAO co-leads (with the UN World Food Programme, WFP) the humanitarian food security cluster, helping people rebuild their livelihoods following emergencies and natural disasters and is a signatory to the Grand Bargain for humanitarian reform. FAO also has a key role to play, with WHO and OIE, in delivering Global Health Security through its work to promote and implement a one health approach in developing countries; and through its work to support the development and agreement of global food safety and plant health standards through the CODEX Alimentarius Commission.

This Project Completion Review (PCR) covers the UK’s core assessed contribution to FAO for the 2016-2017 biennium of £37,191,215.27 million (£17.7m in 2016 and £19.5m in 2017). This represents 5.18% of the core budget funded by all Member States. The core assessed budget is about 40% of FAO’s total budget as set out in its Programme of Work and Budget (PWB) for the biennium. With its core budget, FAO sets standards and supports international treaties in critical areas for the UK, including food standards, forestry, fisheries and climate change. It monitors global food availability and prices, and its agricultural programmes help increase supply for the poorest. FAO also has an important role in leading the global response to Anti-Microbial Resistance (AMR), as well as to the 2017 outbreak of Fall Armyworm - both key UK priorities. The assessed budget also covers central administrative functions, such as Human Resources, Information Technology and security.

The remaining 60% of the budget is composed of voluntary extra-budgetary contributions from member states (including the UK and DFID) and other partners. Implementation of country-level projects is largely funded from FAO’s voluntary budget. Therefore, the totality of what the UK and other member states obtain from FAO in return for their funding reflects a combination of assessed and voluntary contributions. Although this PCR does not include these additional voluntary contributions, which are covered by separate business cases and reviews, it should be noted that both core and voluntarily funded activities are included in FAO’s vision, overarching goals, objectives, cross-cutting themes and functional objectives which are set out on the next page. FAO’s results framework sets targets at global and country level that depend on (core-funded) tools and expertise and (voluntarily-funded) implementation and inputs by FAO staff and partners. It is not possible to attribute all the results FAO reports to its core funding alone which is necessary but not sufficient to achieve FAO’s wider results.

In September 2017, FAO (and IFAD, UNICEF, WFP and WHO) launched the UN report on the State of Food Security and Nutrition in the World. After a decade of improvement, this shows that the number of hungry people rose by more than 40 million in 2016. It estimates that the number of chronically undernourished people in the world increased to 815 million in 2016, up from 777 million in 2015 (although still less than the 900 million reported in 2000). The most serious deteriorations have been observed in conflict situations and where conflict is combined with droughts or floods. Hunger and undernutrition are even worse where conflicts have been prolonged.

While comparable data on the state of food security and nutrition are not yet available for 2017, the Global Food Crisis Report, published in March 2018 reports that in 2017 almost 124 million people across 51 countries faced crisis level of acute food insecurity or worse – up 16 million from 2016. This suggests that the impact indicator on the prevalence of food insecurity for the UK core contribution to FAO will have deterioated in 2016 and 2017 (data on the rural poverty headcount ratio for the 2016-2017 period, the other impact indicator for this project, is not yet available). This deterioration is widely attributed to an increase in conflict rather anything FAO has or hasn’t done. FAO’s theory of change is clear that it can only ever contribute to the achievement of eradicating hunger, food insecurity and malnutrition and these figures underline that.

While FAO (and others’) ability to eradicate hunger in conflicted affected areas is limited, it has a valuable role in preventing conflict over natural resource use, in building resilience, and in humanitarian situations where it helps to protect and rebuild rebuilding livelihoods in the transition from emergency to longer-term development response, reducing dependence on, and the cost of, humanitarian aid. This is reflected in DFID’s voluntary funding to FAO (circa £77 million in the biennium 2016 - 2017) which is increasingly comprised of humanitarian aid projects. Following the launch of DFID’s Humanitarian Policy, UKRep Rome has been developing a partnership approach with FAO for work in emergencies. This is aimed at framing strategic discussions in countries around common objectives, especially around FAO’s role in achieving the Grand Bargain commitments.

Results Achieved
Examples of core-funded technical work and tools that have been produced during the 2016-2017 biennium, and to which the UK’s assessed contribution is therefore contributing, are:

- Food and agriculture statistical norms and standards, and the compilation, validation, analysis and dissemination of data through FAOSTAT (Corporate Database for Substantive Statistical Data) and related databases such as GLOBEFISH - http://www.fao.org/faostat/en/#home
- Information System on Food and Nutrition Security (with WFP)
- Global Information and Early Warning System - http://www.fao.org/giews/background/en/
- Desert Locust Information System
- Animal Health Information System platform
- State of the World publications on Agriculture (annual), Food Insecurity (annual), Fisheries and Aquaculture (biennial), and Forestry (biennial).
- http://www.fao.org/publications/sofa/the-state-of-food-and-agriculture/en/
- http://www.fao.org/state-of-food-security-nutrition/en/FAO food price index
- Global Forest Resources Assessment, and annual yearbooks on forest products, pulp and paper capacity - http://www.fao.org/forest-resources-assessment/en/
- Internationally agreed standards for plant health, through the IPPC. A significant tool supporting standard setting is the International Phytosanitary Portal
- Food safety and quality standards, through the Codex Alimentarius Commission (with WHO). This includes scientific advice provided through joint expert meetings on pesticide residues; food additives; and microbiological risk assessment
- OECD-FAO Agricultural Outlook (jointly with OECD).

Link to list of databases available	http://www.fao.org/statistics/databases/en/

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

FAO’s work in 2016 and 2017 was guided by the Programme of Work and Budget 2016-17 approved by the Conference in July 2015 and by FAO’s strategic results framework (SRF). The SRF includes the outcomes needed to achieve each Strategic Objective, and the outputs needed to attain each outcome. The framework includes indicators that measure progress at each level of the results chain. Performance targets (results) are determined by priorities at national and regional level. These provide the basis for assessing and reporting how FAO’s actions contribute to changes at national, regional and global level. This Project Completion Review (PCR) review assesses progress with a subset of these outputs which have been selected from FAO’s strategic results framework on the basis of UK priorities and included in the logical framework for the UK’s assessed contribution to FAO.

This PCR has been produced by DFID UK Rep Rome in March 2018. FAO’s reporting cycle does not coincide with DFID programme cycle, so this PCR anticipates the results that will be included in FAO’s Programme Implementation Report (PIR) for the 2016-2017 biennium that will be published in April 2018. The PIR will report on FAO’s performance with both its outcome and output level indicators for 2016 and 2017. This review also relies on: the documents FAO management has presented to its governing bodies; the deliberations of those bodies; on external evaluations and assessments; and on informal exchanges with FAO management.

Overall Outcome Assessment
OUTCOME	Outcome Indicator 1		Baseline	Milestone 1 (2015)	Milestone 2	Target (2017)
FAO supports countries to achieve food security and sustainable agricultural development	Percentage of FAO's corporate outcomes that are reported as achieved	Planned	76%	78%		80%
		Achieved				not yet available
			Source: FAO Programme of Work and Budget (PWB) 2016-17 and FAO Programme Implementation Report, April 2018

At outcome level, the DFID core (assessed) funding for FAO aims to support its effective delivery of high-quality services to developing countries in support of their plans to achieve food security and sustainable agricultural development. Like other normative UN agencies, FAO’s outcome-level objectives focus largely on changes at government level, and FAO’s results framework makes clear that responsibility for delivery falls both to governments and to FAO.

At the time of the writing of this report, FAO is still calculating the percentage of corporate outcomes achieved in 2016 and 2017 against the target of 80% that is anticipated for this biennium. The increased conflict in the Middle East, South Sudan, Northern Nigeria and DRC, and its impact on the deterioration in global food security during 2016 and 2017 (as reported above) may have impacted this measurement. Thus FAO may not meet its outcome target for 2016 and 2017 which this review attributes to factors outside FAO’s control.

Overall output score and description
FAO monitors progress with outputs on an annual basis using indicators and targets published in the Strategic Results Framework. At the end of 2016, 43 (86%) of the 50 Output targets for 2016 were fully achieved (thus “on track”), while 7 (14%) were partially achieved. In 2016, FAO’s achievement with its 2017 targets was already well advanced with 32 (64%) indicators showing at least 50% achievement against 2017 targets. Provisional results for the output indicators monitored in DFID’s logical framework suggest that FAO’s progress at output level has been good overall.

Output Number	Output title	Output Score	Output Impact weighting (%)
1	FAO delivers at country level, in line with DFID strategic priorities	A+	50%
2	Continued HR Reform	B	20%
3	Accountability and transparency to governing bodies	A	20%
4	Value for money	A	10%

Lessons
DFID’s Multilateral Development Review (MDR) was completed in 2015 and published in 2016. It recognised FAO’s progress since 2011 and assessed that FAO should be removed from special measures. The MDR made a number of suggestions to improve FAO performance and FAO has made progress with these during the the 2016 and 2017 biennium. Key highlights include FAO’s publication of data to the International Aid Transparency Initiative (IATI) in May 2017 and is the agreement of FAO’s Climate Change Strategy in June 2017 and an action plan to implement it.

Two key areas of progress since 2011 that the MDR recognised were the introduction of FAO’s strategic results framework and the reforms initiated to improve FAO’s internal controls and risk management. FAO has continued to make progress in both areas. Nonetheless further progress is still needed and the following lessons should support that.

Lesson 1: The links between the activities that FAO invests in, their outputs and the outcomes that FAO expects to achieve are not clearly visibile and this hinders the ability of FAO’s member states to discuss and understand why progress in delivering outputs may not result in FAO’s desired outcomes.

During 2016 and 2017, FAO has made progress in shaping its programme of work and budget to reflect its strategic results framework. In November 2016, FAO proposed revisions to its strategic results framework to align it more closely with the Sustainable Development Goals. These were agreed by the FAO Conference in July 2017 and are reflected in FAO’s Programme of Work and Budget (PWB) for the 2018-2019 bienneium. This will support FAO to implement the reforms to the UN Development system that the UN Secretary General has proposed. Nonetheless ‎the strategic results framework compiles the results of FAO’s work at a high (general) level and it remains difficult to see the outputs and outcomes of FAO’s specific work within it. The potential divergence between FAO’s output targets which have been exceeded and its outcome target which may be missed illustrates the importance of articulating the theory of change between outputs and outcomes. A more specific example of this is FAO’s work to combat antimicrobial resistance. FAO has responded to UK (and other EU MS) requests to prioritise this and allocated a specific proportion of its core budget for the 2018 2019 biennium to this work (e.g. by reallocating core funding to recruiting additional technical specialists to work on AMR) however, the strategic results framework does not specify what outputs this work is expected to achieve. The UK has drawn attention to this as a member of FAO’s Programme Committee (PC) and secured FAO Council support for further elaboration of this at the meeting of the PC in May 2018.

Lesson 2: Strengthening internal controls and risk management require organisational reforms which are underway but they also require a culture change in the way FAO staff work.

The quality of FAO’s risk management has improved over the life of the programme (2016 to 2017) however internal and external audit findings demonstrate that risk management needs to improve further. The 2016 MDR reported that FAO had made progress in strengthening risk management, including through the introduction of Enterprise Risk Management (ERM) to ensure that risk management is applied systematically. The approval by FAO’s Finance Committee of its Internal Controls Framework (ICF) was an important achievement in 2016 and work is undeway to complete FAO’s first ever Statement of Internal Control (SIC) for 2017. Nonetheless, implementation of the ERM is work in progress and FAO’s completion of the SIC, expected to be published in May 2018, will be a key milestone. External audit recommendations highlight the need for an increase in staff awareness about FAO’s internal control framework and what is expected of them. Building this awareness takes time and resources which are increasingly scarce as FAO continues to make administrative cost savings to address the programmatic priorities that member states have requested.

Lesson 3. Growing concerns about the underreporting of sexual harassement, exploitation and abuse in the UN system underline the need for a culture change in FAO which increases the awareness and application of FAO’s system of internal controls to prevent and respond to sexual harassement, exploitation and abuse.

Lesson 4. While the two of the three HR targets monitored in DFID’s logical framework have been met, this does not reflect the increasing concerns voiced at FAO’s finance committee about the lack of information to assess whether FAO’s HR policies are being adhered to, the use of consultants (‘non-staff human resources’) to undertake FAO’s core work; and the complains made by FAO’s staff representative bodies.

Lesson 5: Leaders have a key role to play in changing the culture of an organisation, how its staff work and how they collaborate with others.

The MDR also recommended FAO to strengthen its collaboration with other UN organisations, and particularly with IFAD and WFP which are also based in Rome. Following a written request in May 2016 from the UK and other member states and growing concerns voiced from the entire membership of their governing body meetings in 2016, the three Rome Based Agencies (RBAs), FAO, IFAD and WFP, issued a joint paper on collaboration in November 2016. The widespread concern of the membership shaped both the election process for a new IFAD president in February 2017 and the appointment of WFP’s new Exeuctive Director in April 2017. Since their appointments, there has been a notable increase in efforts of all three agencies to improve their collaboration.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	FAO delivers results at country level, in line with DFID strategic priorities
Output number per LF		1	Output Score	A+
Risk:		Low	Impact weighting (%):	50
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
1.1 Food Security and Nutrition: Number of countries with improved governance and coordination mechanisms for eradicating hunger, food insecurity and malnutrition (FAO Indicator 1.2.A)	The target is 24 by 2017. FAO reported that 25 countries had achieved this indicator in 2016	65 countries
1.2 Climate Change: Number of countries supported by FAO that report progress in mainstreaming food security and agriculture into Climate Change policies and processes.(FAO’s KPI 6.6.A)	FAO MTR -Target is 30 by 2017 / FAO reported that 20 countries had achieved this indicator in 2016	36 countries now report mainstreaming food security and agriculture into climate change policies and processes (at end of 2017)
1.3 Gender: Number of the gender mainstreaming minimum standards and women-specific targeted interventions adopted (FAO KPI 6.3.A)	The target is 10 by 2017 and FAO reported that 12 minimum standards had been achieved in 2016	12 out of 15 stahdards achieved
1.4 Work in fragile states: Number of countries that have improved their commitment and capacity for disaster and crisis risk management for agriculture, food and nutrition in the form of policies, legislation and institutional systems. (FAO Output 5.1.A)	The target is16 by 2017 and FAO reported that 27 countries had achieved this indicator by 2016	99 countries
1.5 Economic Empowerment: Number of countries with an improved set of policies, institutions and interventions aiming to generate decent rural employment, including for women and the youth (FAO Outcome 3.2.A)	The target is 18 by 2017. FAO reported that it was on track in 2016 with 6 countries achieving this indicator.	86 Countries

Key Points
Progress with the indicators for this outcome has exceeded the targets set for end 2017. This assessment was based on a preview of the results that FAO will publish in the Programme Implementation Report to be published in April 2018.

Although MTR reports that it has exceeded its gender target (indicator 1.3), it is worth noting that FAO has 15 minimum standards for gender equality and only 12 of these have been met so far. FAO’s Office of Evaluation will release an evaluation of FAO’s work on gender for consideration by the Conference in 2019.

Summary of responses to issues raised in previous annual reviews (where relevant)
The 2017 Annual Review of progress (in 2016) made the following recommendations. Progress with these is summarised below:

1. DFID should review and update this annual review once FAO’s MTR report is available. Completed in May 2017.
2. DFID should review FAO’s revised strategic results framework when it is presented to the programme committee to ensure that it includes improved results targets in priority areas. Completed. DFID has done this with mixed success: FAO will use more specific indicators to monitor audit recommendation implementaton but has not included specific targets for progress with AMR in its strategic results framework. Nonetheless, FAO did include AMR as a new priority its Programme of Work and Budget (PWB) allocating core (assessed) resources for three new posts to focus on AMR, following requests from the UK and other EU member states.
3. DFID should consider aligning the annual review process with FAO’s results reporting timetable for the next biennium (2018-19). Ongoing. DFID will do this so that the first annual review for the 2018-2019 biennium will be due in May 2019, once the mid-term review for the biennium is available.

Recommendations for future programmes
‎The output results reported here are based on the targets set in FAO’s SRF. As noted above, although FAO’s output targets have been exceeded, its outcome target which may be missed. The SRF compiles the results of FAO’s work at a high level and this makes it difficult to see the outputs and outcomes of FAO’s specific work within it. Neither are the links between the activities that FAO invests in, their outputs and outcomes that FAO expects to achieve clearly visibile. This hinders the ability of FAO staff and stakeholders to discuss and understand why good progress in delivering outputs may not result in FAO’s desired outcomes. The UK has drawn attention to this as a member of FAO’s Programme Committee (PC) and secured FAO Council support for further elaboration of this at the meeting of the PC in May 2018.

PCR Recommendation 1: DFID (UKREP) should continue to encourage FAO to strengthen the links between the activities it invests in, their outputs and the outcomes that FAO expects to achieve. A key issue which DFID UKREP should raise with FAO’s Programme Committee is how FAO’s programmes will adapt to take account of conflict-driven growing food insecurity.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Continued HR Reform
Output number per LF		2	Output Score	B
Risk:		Medium	Impact weighting (%):	20
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
2.1The Performance Management Policy and System (PEMS) is implemented and rolled out	The target was for the performance evaluation and management system to be implemented by 2017. FAO reported that it had launched PEMS in February 2016	Output met expectations. PEMS implemented throughout the organisation
2.2Time required to recruit staff (FAO’s KPI 11.1.A)	The target is to have reduced this to 120 days by 2017. FAO reported that it had met this target in 2016.	Output met expectations. 120 days target achieved
2.3Vacancy rates drop in technical and non technical areas	The baseline was 21% in 2015. FAO reported that the VR was 17.4% in 2016.	Output moderately did not meet expectations. The overall Professional Vacancy Rate as of November 2017 is 15.2 percent

Key Points

FAO reports on Human Resources Management to its Finance Committee (FC). These reports (FC 164/7 and FC 169/9); the FC deliberations; and informal reporting from FAO senior management have been used to assess this output. Although we cannot independently verify FAO reporting, the member states that sit on the Finance Committee scrutinise it carefully. FAO has met two of the three expectations for this output. However, this does not reflect the increasing concerns voiced at the FC about the lack of information to assess whether FAO’s HR policies are being adhered to, the use of consultants (‘non-staff human resources’) to undertake FAO’s core work and the complains made by FAO’s staff representative bodies. Thus this output is scored B overall.

2.1. FAO’s HR Management Report (November 2016) noted that FAO’s performance management system (PEMS) had been simplified and improved in 2016. FAO management have subsequently confirmed that the PEMS has been implemented throughout FAO in 2017. FAO’s Progress Report on Implementation of the External Auditor's Recommendations submitted to the Finance Committee in November 2017 (FC 169/11), states that quality assurance mechanisms were established in 2017 for the Performance Evaluation and Management System (PEMS).

2.2 The November 2016 and 2017 HR Management Reports do not report on the time taken to recruit staff so we asked FAO management to provide a progress update. This confirmed that the 120 day target had been met. FAO’s Office of the Inspector General (OIG) planned to undertake an internal audit of FAO’s recruitment and when completed, will provide an independent opinion on FAO’s recruitment policies.

2.3 Outputs moderately did not meet expectations for ouput target 2.3. FAO management said to the FC in November 2016 that they were aiming for a 15% vacancy rate and reported to the FC in November 2017 that vacancy rate for professional positions had decreased to 15.2 percent in 2017. In November 2017, the HR report noted FAO management continues to consider it essential to maintain flexibility in the vacancy rate for professional positions and that the vacancy rate is expected to be between 15% and 20% over the coming biennium. The FC noted that the current vacancy rate was still over the agreed target of 15 percent.

In November 2016, FAO management explained that their relatively high target vacancy rate is a cost saving strategy as vacant posts enable the organization to retain a more flexible use of resources. This has led to a significant increase in the use of consultants (‘Non Staff Human Resources’) and the November 2016 Finance Committee suggested that FAO use non-staff human resources more efficiently. Since then, however, the introduction of new procedures (the requirement for all FAO consultants to demonstrate they can speak two UN languages) for hiring consultants or renewing their contracts have caused delays. The November 2017 meeting of the FC encouraged FAO “to ensure that the technical expertise provided by consultants was not weakened by requiring additional languages for all positions and consider potential adjustments to the new guidelines to avoid disruptive effects on programme delivery” (CL 158/7 para 23c)

In considering FAO’s overall report on its management of human resources (FC 169/9), the November 2017 meeting of FAO's Finance Committee (FC) found that there was insufficient data and information in the HR management report to substantiate FAO’s analysis of progress (CL 158/7 para 23). This highlights the limited progress made with the recommendation in the 2017 annual review to improve HR transparency which remains outstanding.

Summary of responses to issues raised in previous annual reviews (where relevant)

2017 Recommendations and progress updates (in bold)

1. The implementation of the Performance Management System (PEMS) is welcome. FAO should continue to monitor its implementation and report on this to its Finance Committee. FAO could consider setting performance targets for the PEMS. Ongoing. As reported in the Progress Report on Implementation of the External Auditor's Recommendations submitted to the Finance Committee, quality assurance mechanisms were established in 2017 for the Performance Evaluation and Management System (PEMS). The quality control exercise included work plans, the year-end appraisal, and analysis of rating distribution and written comments. This continues to be work in progress.
2. FAO should consider how to increase the transparency of its reporting on Human Resources (HR) management performance. No progress. In November 2017, FAO’s Finance Committee (FC) found that there was insufficient data and information in the HR management report to substantiate FAO’s analysis of progress (CL 158/7 para 23).
3. The Finance Committee (November 2016) recommended that FAO further improve communications between management and staff representative bodies. DFID should monitor the follow up to this recommendation. No progress. Staff representative bodies have the opportunity to address FAO Council. Their interventions suggest that communications and transparency continues to need improvement.

Recommendations for future programmes
A number of factors suggest that FAO’s human resource management reforms are not progressing smoothly. These include limited progress with increasing transparency of HR management performance despite the repeated requests from FAO’s Finance Committee (FC) for more information; the concerns voiced by thte FC about FAO’s use of consulttants; the consistent complaints made by staff representatitve bodies in their statements to FAO Council; and a number of external audit recommendations.

FAO’s HR management report of November 2017 notes a number of areas for improvement and the Finance Committee encouraged the ongoing efforts to increase efficiency in human resources procedures and processes. A number of recommendations are also likely to be made in the internal audit of FAO’s recruitment proceedures during 2017.

PCR Recommendation 2: DFID (UKREP) should monitor FAO’s implementation of recommendations from internal, external auditors and the Finance Committee for improvements to FAO’s HR management and include indicators of progress with this in the UK FAO performance agreement.

Recent media reports have also highlighted the challenge of sexual exploitation, abuse and harassement across the UN. Addressing and preventing SEAH in the UN and across the international development sector is a priority for the UK and for many other member states. FAO’s Inspector General reports that there were two complaints of sexual exploitation during 2016. This is likely to underestimate the challenge in FAO.

FAO’s Director-General has assigned a FAO staff member to the United Nations System Chief Executive Board (CEB) Task Force on Addressing Sexual Harassment. The task force will examine the policies of UN organisations to address sexual harassment wih the aim of developing a common approach across the entire UN system to create a workplace free from sexual discrimination, harassment and abuse.

PCR Recommendation 3: DFID (UKREP) should continue to work with other member states to encourage FAO to strengthen the measures it has in place to prevent and respond to sexual harassement (e.g. of staff) as well as sexual exploitation and abuse (e.g. of beneficiaries) including encouraging staff and others to report their concnerns.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Accountability and transparency to governing bodies
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	20
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
3.1Implementation of governing body decisions within prescribed deadlines (FAO’s KPI 10.1.B)	The target is 90% by 2017. FAO reported that it had met this target in 2016.	Output moderately exceded expectations. 100% of governing body decisions implemented within prescribed deadline.
3.2 Percentage of recommendations where the agreed management response has been completed by the due date (FAO’s KPI 10.2.A)	The target is 95% by 2017. FAO reported it was off track with 84% completed in 2016	Output moderately did not meet expectations. 86% of recommendations have agreed management response completed by due date.

Key Points
Overall FAO has met expectations for this output. It moderately exceeded expectations for target 3.1 and moderately did not meet expectations for target 3.2. To assess this output, we anticipated the results that FAO management will report in their Programme Implemetation Report (PIR) for the 2016-2017 biennium due to be published in April 2018.

We have also considered FAO’s success in publishing disbursement information with IATI for the first time ever in early May 2017. This was a key recommendation in the 2016 MDR and the 2017 AR.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendations made in 2017 AR

DFID and FAO to include FAO’s commitment to publish its disbursement information with IATI by April 2017 in our performance agreement. DFID (UKREP) to urge FAO to include this commitment in its revised results framework and monitor progress with this. Ongoing, good progress. FAO published disbursement information with IATI in early May 2017. DFID used European interventions at the March 2017 Programme Committee to ask FAO to include the commitment and a KPI in its results framework. Although this was not taken forward as a KPI, FAO remains committed to publishing expenditure information with IATI.

Recommendations for future programmes

PCR Recommendation 4. As recommended in the last Annual Review, DFID and FAO to include FAO’s commitment to publish its disbursement information with IATI in the UK FAO performance agreement to be agreed in May 2018.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Value for Money
Output number per LF		4	Output Score
Risk:		Medium	Impact weighting (%):	10
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
4.1 Per cent of savings and efficiency gains planned in the 2016/2017 PWB	100% by 2017. FAO reported that it had achieved this in 2016.	100%

Key Points

This output target has been met as reported in the 2017 Annual Review. FAO management confirmed that 100% of efficiency savings planned in the 2016/2017 Programme of Work and Budget (PWB) have been achieved and that USD 14.2 million have been reallocated to eight higher priority areas of work.
- FAO is active in reducing staff costs where possible by limiting expenses in relation to duty travel and maintaining a high vacancy rate. As discussed under output 2 above, FAO’s Finance Committee have raised concerns about FAO’s high vacancy rate and the strategy of employing consultants as a cost saving measure.
- A broader review of FAO’s value for money is provided in the next section

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendationsfrom 2017 Annual Review

1. DFID (UKREP) to continue to encourage FAO to enhance efficiency through its programmes, continuing to report on savings made and train staff to “embed a culture of value for money”. Ongoing. UKREP has used EU and Member State and national statements at FAO governing body meetings to call for more focus across the organisation on Value for Money. FAO has delivered savings as agreed in the programme of work and budget (PWB) for 2016 - 2017 and identified further administrative savings in the PWB for 2018 – 2019 which will fund 59 additional technical specialist posts.
2. DFID (UKREP) to monitor FAO progress in improving project management and procurement and use meetings of the governing bodies to press for progress. Ongoing. UKRep pressed FAO management to include a KPI target for programme management in the November 2017 Programme Committee (PC). The PC supported measures to monitor FAO programmes and projects with the aim of improving their quality (see CL158/5 para 4i)

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
FAO’s key cost driver and main asset is its staff, which accounts for 75% of the FAO 2016-17 net appropriation budget (as reported in FAO’s Programme of Work and Budget (PWB) 2016-17). FAO staff costs are linked to those agreed in the UN common system and FAO management has limited options for controlling them. The most significant components are salaries, medical costs and benefits, such as education grants and home leave. 70% of cost increases in FAO’s Programme of Work and Budget for 2016/2017 are accounted for by increases in these costs (as reported in an information note for the 2015 FAO Conference). FAO management has used a number of strategies to contain these costs which include the use of consultants who are cheaper to employ because they are not entitled to staff benefits; and maintaining a relatively high vacancy rate. Only limited data on FAO’s human resources (both staff and consultants) has been made available and FAO’s Finance Committee has not been able to consider these strategies fully. Improving the transparency of FAO’s HR data is an ongoing challenge.

Exchange rates are another key cost driver. FAO requires that its member states make their assessed contributions in both US Dollars (USD) and Euros (EUR) to minimise financial risks to FAO from exchange rate fluctuations. Nevertheless, FAO still faces the risk of unfavourable exchange rates increasing the costs of its operations in countries which do not use USD or EUR and for operations which are funded from voluntary contributions in other currencies.

VfM performance compared to the original VfM proposition in the business case
The assessed contribution to FAO is exempt from the requirement for a business case because the contribution is a requirement for the UK membership of FAO. The percentage of the UK contribution of FAO’s core budget for the 2016/17 biennium is 5.18%. The percentage that each country is required to pay is determined by the UN centrally on the basis of the size of each country’s economy. The percentage of the UK contribution of FAO’s core budget for the 2018/19 biennium is 4.64%, £40 million.

Assessment of whether the programme represented value for money
The requirement to pay the UK assessed contribution in USD and EUR means that the cost of this in GBP varies and is increasing because of weakening of the GBP:USD and GPB:EUR exchange rates. The 2016 forecast amount for the UK contribution was £16.5 million but when paid the actual UK contribution was £17,681,203.16. Similarly for the UK contribution in 2017, the forecast amount was £16.5m, however it cost c £19.5 million.

FAO’s Programme of Work and Budget (PWB) for 2016-2017 noted the Director-General’s commitment to delivering best value for money and FAO has implemented almost the entirety of this PWB within the zero growth budget level agreed by member states. As reported under output 4, FAO’s Programme of Work and Budget (PWB) for 2016-17 planned efficiency gains and savings of US$14.2 million which FAO reports that it has achieved. Achieving this was facilitated by: benefits from previous investments in information technologies; and de-emphasising and realigning of work. e.g. FAO’s Programme of Work and Budget for 2018/19 notes that in 2016-2017:

USD 5 million was reallocated from the Capital Expenditure Facility to high-priority technical areas of work, arising from less costly investment in information technology infrastructure and systems; and

A reduction in staff costs was achieved due to a downward adjustment in personnel costs (freeze on remuneration, reductions in after-service medical cost)

Despite the increasing cost (to the UK), the value for money of this programme is likely to have been maintained or increased because of recent improvements in the economy and efficiency of FAO. However, it is not possible to assess whether FAO has improved its effectiveness. As mentioned above, FAO may not meet its outcome target for 2016 and 2017 which this review attributes to factors outside FAO’s control: the conflicts which have increased food insecurity.

Quality of financial management during programme
FAO’s financial management has ensured that FAO completed its PWB for the 2016-2017 biennium with zero nominal growth since 2014-2015 (with a relatively small forecasted underspend of USD5 million) as agreed by FAO’s member states. As noted above, FAO achieved planned efficiency gains and savings of US$14.2 million which enabled reprioritisation of FAO work while preventing growth in FAO’s Regular Budget.

Narrative and financial reporting requirments have been adhered to. The last report on the financial position of the organisation was considered by the November 2017 meeting of FAO’s Finance Committee (FC). The report noted that FAO had made the foreign exchange gains on the Euro portions of the assessed contributions from member states. These have helped to offset declines in assessed and voluntary contributions from member states. The FC noted that FAO’s prudent, low risk investment style. The FC also highlighted two key financial challenges facing FAO:

That although FAO’s current liquidity position was stable, FAO’s on-going cash flow health was dependent on the timely payment of assessed contributions by member states. The FC and FAO’s December 2017 Council subsequently encouraged to make timely payments.

A forecasted deficit of USD 900 million forecasted for FAO’s General Fund at 31 December 2017 (USD 907.1 million as at 31 December 2016), due principally to shortfalls in funding to offset charges for the After Service Medical Coverage Scheme and the Terminal Payments Fund.

The inability to bridge the funding gap of the After Service Medical Coverage (ASMC) liability has been an ongoing issue with the United Nations system. FAO has taken action to address this issue by investing in long-term assests that correspond with long term liabilities and amending staff eligibility crtierain to contain costs and reduce future liabilities, nonetheless the issue must be addressed across the UN System.

Auditing requirements have also been met. The most recent audit report is November 2017 report of the external auditor which includes both FAO’s audited accounts for 2016 (C2019 5A) and an audit of FAO’s performance (C2019 5B). The report issued an unmodified audit opinion that confirms that FAO’s financial statements are prepared, in all material aspects, in accordance with its financial reporting framework. The performance audit report highlighted concerns about FAO’s employee benefit oblications and in particular ASMC as outlined above. The report also highlights the dependency of FAO’s risk management on its internal controls and makes a number of recommendations to improve internal control awareness across FAO, risk management; and fraud risk management. These are discussed in the following section on risk management.

DFID (UKREP) has pressed FAO management to measure the percentage of all external audit recommendations (rather than just long outstanding recommendations) where the agreed management response has been completed by the due date. This will be included as a Key Performance Indicator in FAO’s results framework and DFID will continue to press FAO management for action to address these recommendations and the risks highlighted by the external auditor.

Date of last narrative financial report	http://www.fao.org/3/a-mu318e.pdf / November 2017
Date of last audited annual statement	http://www.fao.org/3/a-mu131e.pdf / November 2017 – Covering 2016 accounts

E: RISK (½ page)

Quality of risk management over the life of the programme
The quality of FAO’s risk management has improved over the life of the programme (2016 to 2017) however internal and external audit findings demonstrate that risk management needs to improve further. The 2016 MDR reported that FAO had made progress in strengthening risk management, including through the introduction of Enterprise Risk Management (ERM) to ensure that risk management is applied systematically. The approval by FAO’s Finance Committee of its Internal Controls Framework (ICF) was an important achievement in 2016 and work is underway to complete FAO’s first ever Statement of Internal Control (SIC) for 2017. Nonetheless, implementation of the ERM is work in progress and FAO’s completion of the SIC, expected to be published in May 2018, will be a key milestone.

As part of FAO’s internal controls, annual reports from the Inspector General and the Audit Committee are published and scrutinised by FAO’s Finance Committee (FC). The FC considered the most recent (2016) Annual Report of the IG (FC 166/12) in March 2017 and the most recent external auditor’s report (C2019 5B which appended to FAO’s audited accounts for 2016) in November 2017. Both raised ongoing concerns about FAO’s risk management.

The IG report included a summary of FAO Internal Audit Report AUD 0716: High Level Review of Management of Risks of Financial Fraud and other Corrupt Practices in FAO. The review’s objective was to synthesize the results of the recent reviews performed by Office of FAO’s Inspector General (OIG), the UN Joint Inspection Unit (JIU) and other external parties. The review concluded that FAO’s approach to fraud risk management is fragmentary and that there is insufficient evidence to form a view on the effectiveness of existing controls. Thus FAO may be at major risk of fraud exposure. The review also noted that FAO Management has communicated their vision of zero-tolerance to fraud and there is a solid regulatory framework to support this, starting with FAO's policy against fraud and other corrupt practices. The IG suggested FAO management develop a fraud management strategy.

DFID (UKRep) has met with FAO management to press FAO for a response to the 2016 JIU report on fraud across the UN. The JIU report recommends that UN organisations should  ‘conduct a comprehensive corporate fraud risk assessment’ and  ‘develop organization-specific comprehensive anti-fraud strategies and action plans’. UKREP working with other FAO Council members, secured Management’s commitment to developing an anti-fraud action plan based on the risk assessment that will follow from the SIC. The Report of the FAO Council meeting in December 2017:

“looked forward to the Secretariat reporting completion of the two outstanding recommendations contained in the Joint Inspection Report (JIU) on Fraud Prevention, Detection and Response in United Nations System Organizations and noted that this matter would be addressed at the November 2018 session of the Finance Committee”

PCR Recommendation 5: DFID should scrutinise FAO’s Statement of Internal Control and Anti-Fraud action plan when they are published and identify specific actions to be included in the UK FAO performance agreement

FAO’s most recent external auditor’s report (C2019 5B) recommends that FAO management revisits its risk management framework, ensures that fraud vulnerabilities are properly managed and strengthens its fraud risk governance. The external auditor also found a lack of awareness of FAO’s monitoring and supervisory controls and a need to improve them. DFID (UKREP) has pressed FAO management to measure the percentage of all external audit recommendations (rather than just long outstanding recommendations) where the agreed management response has been completed by the due date. This will be included as a Key Performance Indicator in FAO’s results framework.

PCR Recommendation 6: DFID should also include FAO’s KPI on audit recommendation implementation in the UK FAO performance agreement and continue to encourage FAO to strengthen its internal controls and risk management.

While DFID’s net risk rating ‘medium’ for our core contribution to FAO has not changed during 2016 and 2017, these audit findings and emerging risks suggest that DFID reconsiders our risk rating during the 2018-2019 bienneium. Emerging risks include the likelihood that growing awareness and discontent with sexual harassment, exploitation and abuse (SHEA) will reveal flaws in FAO’s systems for addressing and preventing it. It is likely that the two complaints of sexual exploitation received by FAO’s IG in 2016 underrepresent the prevalence of the challenge in FAO. DFID (UKREP) is working with other member states to press FAO to strengthen the measures it has in place to prevent and address SHEA and will continue to do so.

DFID (UKREP) will also strengthen efforts to mitigate risks arising from the UK exit from coordination of policy positions with other EUMS; and the possibility that the incoming DG whom FAO MS will elect in June 2019 will not pursue or ideally accelerate the reforms that are essential to improving FAO’s effectiveness and its risk management.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
At the time of the 2017 AR, FAO was on track to deliver its output targets and is likely to have exceeded output targets expected at the end of the 2016 2017 bienneium

Performance of partnership(s)
As this is a review of the UK assessed contribution to FAO, it is not governed by a formal contract or agreement but rather by the basic texts (rules) of FAO which the UK is a member of. This section reviews FAO’s partnership with other UN agencies and with its other stakeholders as well as with DFID.

The 2016 MDR notes that FAO generally develops strong partnerships and works in a participatory manner with partners, particularly at country level. The MDR also recommended FAO to strengthen its collaboration with other UN organisations, particularly with IFAD and WFP, both based in Rome. Following a written request in May 2016 from the UK (and other member states) and the growing concerns of the entire membership of their governing bodies, the three Rome Based Agencies (RBAs), FAO, IFAD and WFP, issued a joint paper on collaboration in November 2016. The widespread concern of the membership shaped both the election process for a new IFAD president in February 2017 and the appointment of WFP’s new Exeuctive Director in April 2017. Since their appointments, there has been a notable increase in efforts of all three agencies to improve their collaboration. This has included a joint visit of the three principals to Ethiopia in September 2017, wide ranging commitments to improve joint working further and the first ever joint informal governing body meeting later that month. Member states of all three agencies welcomed these efforts to improve collaboration and have called for annual joint progress reports to their governing bodies.

An updated Progress Report on RBA Collaboration was presented to the FAO Council in December 2017. This noted that the strengthening of RBA collaboration is in line with the United Nations system-wide ongoing efforts to increase efficiency, effectiveness, and accountability. The UN reform process initiated by the Secretary-General of the United Nations calls for robust collaboration and tearing down silos, underscoring the purpose of the 2030 Agenda as comprehensive and integrated, where UN entities work closely together and pool expertise, advancing integrated approaches to capacity building.

The RBA report also notes various areas of increased collaboration that the RBAs are embarking on at headquarters level (e.g. consistent approaches to protocol, interpretation and the organisation of governing body meetings). While these initiatives are welcome, the priority for the UK (and others) are the UNSG proposals for reform to the UN Devleopment System focusing on what happens at country level.

FAO’s Office of Evaluation’s 2017 Programme Evaluation Report (PER)[1] examines FAO’s decentralisation process and finds that FAO has strengthened coordination with partners at country level, especially government authorities, and developed diverse partnerships with other stakeholders. It finds that FAO’s collaboration with other agencies in humanitarian crisis, particularly with WFP and UNICEF, was considered effective (e.g. the Central African Republic and South Sudan).
[1] See Office of Evaluation biannual 2017 Programme Evaluation Report, submitted to FAO Conference in July 2017 at: http://www.fao.org/3/a-mt142e.pdf

UK partnership with FAO
UKRep Rome has continued to work closely together with FAO and other member states at its Rome headquarters focusing on priority areas, including FAO’s work to: combat Antimicrobial Resistance; address the spread of Fall Armyworm in Africa; strengthen internal controls and risk management; and implement Grand Bargain commitments to humanitarian reform. UKRep has organised a number events with FAO to raise the profile of these issues and press FAO and stakeholders for progress. Highlights include the visit of Prince Charles in April 2017 which raised the profile of FAO’s work to respond to the threat of famine in the Horn of Africa; and the UK chaired event in the margins of FAO’s 2017 Conference which brought together Agriculture Ministers from Ghana, South Africa, and Zimbabwe to call for action to support their response to Fall Armyworm.

DFID (and Defra) held our annual Strategic Dialogue meeting with FAO at the end of January 2018 which reviewed FAO’s progress with the 2016 MDR recommendations and agreed to build on links at technical working levels between HMG (DFID and Defra) and FAO. UKRep Rome has also strengthening communications with other HMG partners working with FAO across DFID and Defra. In January 2018, UKREP sought feedback from DFID stakeholders managing voluntary funded projects with FAO. This elicited feedback from 8 DFID country teams on their humanitarian and/or resilience projects with FAO. The total value of these projects is approximately US$150 million. In general the feedback is positive, with FAO delivering well in the areas of focus (technical capacity around livelihoods and support to agriculture). Some DFID country offices suggested FAO could improve collaboration on the ground so that it matched the good collaboration between FAO and WFP at HO level that can be seen in their joint briefings to the donors and board members. Suggestions also includeed improving risk management mechanisms and reporting at country level.

DFID is strengthening its partnership with FAO in humanitarian contexts, including through the development of a DFID-FAO Strategic Partnership Paper which aims to set out what DFID can expect from FAO when working in partnership in emergencies. This will be an item on the agenda for the next Strategic Dialogue meeting and an opportunity to assess FAO’s progress against the Grand Bargain commitments, including working in partnership and conducting effective joint assessments.

The DFID also works closely with FAO in the area of climate change, including in developing the organisational strategy and implementation plan as well as through discussions on a more strtageic, focussed approach to working through the Green Climate Fund (GCF).

Asset disposal and value obtained by DFID
This PCR is reporting on the completion of FAO’s programme of work and budget (PWB) for the 2016-2017 biennium. FAO will continue its work to implement the PWB for the 2018-2019 biennium thus asset disposal associated with the closure of this DFID project is not anticipated.

The Office of FAO’s Inspector General (OIG) undertook a review (AUD 2816) of FAO’s Fixed Assets management in 2016. This is summarised in the OIG’s Annual Report (FC166/2). It identifies several weaknesses in FAO’s internal controls. It concluces that FAO’s Asset Management is unsatisfactory, and that processes for all asset disposal types are ineffective and expose FAO to the risk of fraud. The report includes 22 actions agreed with FAO management to address their OIG findings. This highlights the importance of recommendation 5, above, that:

PCR Reccomendation 5: DFID should scrutinise FAO’s Statement of Internal Control and Anti-Fraud action plan when they are published and identify specific actions to be included in the UK FAO performance agreement

G: CONDITIONALITY (½ page)

Partnership principles assessment - Not applicable

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
FAO’s Office of Evaluation is independent and reports to the membership through FAO’s Programme Committee as well as to FAO management. Evaluations in FAO assess activities, projects, programmes, strategies and policies and are published in the Office of Evaluation website. Thematic and strategic evaluations are submitted to the Programme and other Committees and to FAO’s Council. Evaluations are often conducted in response to requests by the Programme Committee and the results are presented systematically to FAO governing bodies. In total, 39 Evaluations were published in 2016 and 24 in 2017. Management responses are submitted to the Programme Committee, together with reports on implementation of recommendations.

A 2016 evaluation of FAO’s evaluation function reported that FAO’s Office of Evaluation (OED) had made significant progress during the last biennium but that there remains scope for improvement both in learning and accountability. The timing of OED’s evaluations and recommendations limit their overall utility. The evaluation notes that in some cases evaluations were done too early or too late; there have been delays in the evaluation process (e.g. time taken to agree on the ToRs, timing of interactions with concerned parties, and with reporting). These issues limit FAO’s access to an important source of learning and improvement. Following DFID’s (UKREP) request to the Programme Committee in November 2017, FAO management has agreed to report on how it has followed up these recommendations (see update on AR recommendation 13).

Separately from these independent evaluations, part of FAO’s core work is to collect information and establish evidence as a global public good. In September 2017, FAO (and IFAD, UNICEF, WFP and WHO) launched the UN report on the State of Food Security and Nutrition in the World. After a decade of improvement, this shows that the number of hungry people rose by more than 40 million in 2016. It estimates that the number of chronically undernourished people in the world increased to 815 million in 2016, up from 777 million in 2015 (although still less than the 900 million reported in 2000). The most serious deteriorations have been observed in conflict situations and where conflict is combined with droughts or floods. Hunger and undernutrition are even worse where conflicts have been prolonged.

While comparable data on the state of food security and nutrition are not yet available for 2017, the Global Food Crisis Report, published in March 2018 reports that in 2017 almost 124 million people across 51 countries faced crisis level of acute food insecurity or worse – up 16 million from 2016. This suggests that the impact indicator on the prevalence of food insecurity for the UK core contribution to FAO will have deterioated in 2016 and 2017 (data on the rural poverty headcount ratio for the 2016-2017 period, the other impact indicator for this project, is not yet available). This deterioration is widely attributed to an increase in conflict rather anything FAO has or hasn’t done. FAO’s theory of change is clear that it can only ever contribute to the achievement of eradicating hunger, food insecurity and malnutrition and these figures underline that. Nonetheless, this evidence suggests that reviewing the theory of change that underpins FAO’s work in in conflicted affected areas would be useful.

PCR Recommendation 7: DFID should consider a focus on FAO’s work to increase the resilience of livelihoods to threats and crises when updating the theory of change and logical framework for the UK core assessed contribution to FAO for 2018-2019.

Monitoring progress throughout the review period
UKRep Rome monitors FAO’s performance through scrutiny of FAO management reporting. UK Rep Rome uses UK and EU interventions in FAO governing bodies to discuss and press for further progress. UK Rep Rome also meets with FAO’s senior staff overseeing policy, administration, finance and human resources on a regular basis and uses these meetings to monitor and discuss progress.

An Annual Review was completed by DFID UK Rep Rome in May 2017, following the publication of FAO’s Mid-Term Review of progress in 2016. This relied on: the MTR and other documents FAO management has presented to its governing bodies; the deliberations of those bodies; on external evaluations and assessments; and on informal exchanges with FAO management.

UKRep also engages with DFID country offices and policy staff at headquarters, raising policy and administrative issues with FAO management on their behalf. These exchanges contribute to UKRep’s overview of FAO’s performance at country level and were supplemented with systematic feedback from all DFID owners of voluntarily funded projects with FAO in January 2018. This information has been incorporated in this PCR and was discussed with FAO senior management at the Strategic Dialogue meeting in January 2018 as recommended by the Annual Review (Recommendation 12)

Sources
- Reviewed Strategic Framework 2017/7
- Progress Report on RBA Collaboration December 2017 CL 158/9
- Programme of Work and Budget 2016/17
- Human Resources Management FC 169/7;
- Financial highlights paper to FC
- Report on Financial Position of Organization November 2017
- Reports of Finance Committee, November 2016 and 2017
- Report of the Programme Committee, November 2017
- FAO Council Report, December 2017
- Progamme and Budgetry Transfers 2016/17 FC 169/7
- External Auditors Report C2019 5A and 5B
- DFID 2017 Annual Review of FAO progress in 2016
- DFID Multilateral Development Review 2016
- Independent assessment of FAO’s technical capacity 2017/26
- Office of Evaluation biannual 2017 Programme Evaluation Report, submitted to FAO Conference in July 2017 at: http://www.fao.org/3/a-mt142e.pdf
- Office of Inspector General Annual Reports 2016 and 2017
- Progress Report on Implementation of the External Auditor's Recommendations (169/11), Finance Committee, November 2017

Smart Guide
The Programme Completion Review is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions / Early closure is likely to be summed up by issues such as ‘poor performance by partners’ and/or ‘major changes in operating environment’
A: Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Output Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on AMPas part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Minor/Moderate/Major/Severe / Enter: Minor, Moderate, Major or Severe / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on AMP as part of loading the Annual Review for approval). / Where the Risk for this Output has been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section E Risk
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D: Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme / If programme was closed >1 month early please describe in a few words why, what savings were made, as well as what money was spent.
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management during programme / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E: Risk
Quality of risk management over the life of the programme. / How were risks managed, the degree to which they were realised and/or mitigated? / Did any risks materialised throught the duration of the programme which were not forseen? What where they and how was this managed? / What lessons have been learned?
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
G: Conditionality
Partnership principles assessment / For programmes where we have decided to use the PPs for management and monitoring, PCRs should generally include an assessment of commitment to the PPs, including any concerns that have occurred over the year, the partner government’s response, and details of any response by us. Teams should refer to the DFID guidance on reviewing projects.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review and PCR process