## HPF2 extension Logframe
PROJECT TITLE | Health Pooled Fund Phase 2
IMPACT | Impact Indicator 1 |  | Baseline (2015) | Milestone 1 (2017) April 2016 - March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018) | Explanatory notes for previos target (March 2018) | Explanatory notes for Extension Period Targets (Apr-Sept 2018)
Government led health systems that save lives | Under five mortality rate (per 1000 live births) | Planned | 99 / 93 |  |  |  | 89 | 89 | For impact indicators, surveys are done every 5 years, hence BL is 2015 and Target is estimated base on that for the next 3 years. Again this will depend on availability of data which could be 2018 or 2020 | Targets for the April-September 2018 period are based on achievement during the same period in 2017. The extension period falls in the rainy season, which affects progress to some of the indicators. In addition insecurity may affect access to health facilities.
|  | Achieved |  | N/A
Source
South Sudan Household Survey (SHHS) or Model Surveys. Baseline 99 UNICEF (2015), 93 World Bank (2015)
| Impact Indicator 2 |  | Baseline 2015 | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 |  | Target Sept 2018 (April 2016-Sept 2018)
| Maternal mortality ratio (per 100,000 live births) | Planned | 789 |  |  |  | 710 | 710
|  | Achieved |  | N/A
Source
SHHS, Maternal Mortality Survey or Model Surveys. Baseline 789 WHO (2015), (http://apps.who.int/gho/data/node.country.country-SSD)
| Impact Indicator 3 |  | Baseline 2015 | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Infant mortality ratio (per 100,000 live births) | Planned | 88 |  |  |  | 79 | 79
|  | Achieved |  | N/A
Source
SHHS, Maternal Mortality Survey or Model Surveys. Baseline 88 UNICEF, 2015 (https://data.unicef.org/topic/child-survival/neonatal-mortality/),
| Impact Indicator 4 |  | Baseline Jul 2015/June 2016 DHIS Data (after conversion factor) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Couple Years Protection (CYP) | Planned | 8680 |  |  |  | NA | 29155
|  | Achieved |  | 10672 | 13590 | 25966
Source
Baseline, July 2015 to June 2016 DHIS data and Target Projection for 6 months (April 2018 to Sept 2018). Conversion factor is the USAID endorsed conversion factor found on the their website. Male Condom was excluded.
| Impact Indicator 5 |  | Baseline Jul 2015/June 2016 DHIS Data (after conversion factor) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Disability Adjusted Life Years (DALY) averted | Planned |  |  |  |  | 2039792 | 2759718
Achieved
Source
HPF DALY calculator
OUTCOME | Outcome Indicator 1 |  | Baseline (March 2016) | Milestone 1 April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018) |  |  | Assumptions
Increased access to quality health services, in particular by children, pregnant women and other vulnerable groups. | Percentage of one-year olds vaccinated with the third dose of Pentavalent (DTP-HepB-Hib 3rd dose) vaccine | Planned | 46.8% (206,268) |  |  |  | 44% | 42% (414,592) | Target is below the baseline because of population migration and inaccessibility which affects both utilisation and access. Also cold chain support and vaccine supply is not under HPF control. |  | • Vaccines supplies remain available, and UNICEF continue to provide cold chain support • Government health workers continue to be paid • Availability of qualified midwives and other skilled professionals does not decrease • Large scale violence does not occur • Stability and access to health facilities is possible, conflict remains small scale and localised
|  | Achieved |  | 41.8% (175,320) | 39.5% (210,706) | 41.8% (366,938) |  |  | BL- HPF 1 Period (Oct 2013 to March 216), M1- 15 months (April 2016 to June 017), M3- 24 months (April 2016 to March 2018 ) and Targets from April 2016 to Sept 2018 (30 months).
Source
*Note: Achievement (%) is calculated using DHIS 8 States population of < 1 years old as the denominator
MoH HMIS/DHIS - Baseline 6 States, Target is previous Milestone 3 (April 16-Sept 2017) plus 6 months projection (April to Sept 2017)
| Outcome Indicator 2 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Proportion of children under five with fever in the last two weeks who were taken to a health facility within 24 hours of onset of fever | Planned | 64% |  |  |  | 70% | 70% | BL - 2015 survey, see data source below the milestone. Target is from South Sudan Health Sector Development, for year 2015. LQAS surveys are conducted every 2 yrs. By 2015 only 64% was achieved from BL of 32% in 2010 (Note BL of 32% was from Household Survey). Hence, we maintained the same target (70%), looking at the trend and the fact it was not achieved. Note this is national average. Assumption is that by 2017/2018 next survey will be done.
|  | Achieved |  | N/A
Source
Baseline - MoH Community LQAS 2015 National Average, Target Health Sector Development Plan 2012
| Outcome Indicator 3 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Contraceptive Prevalence Rate | Planned | 5% |  |  |  | 6.5% | 6.5% | BL - 2015 survey, see data source below the milestone. Target is based on South Sudan commitment to FP 2020. It was 8% but was reduced to 6.5% looking at trends and challenges in FP | Assumption is that UNFPA will provide contraceptives every quarter and the contraceptives are distributed together with the drugs to Counties/hospitals
|  | Achieved |  | N/A
Source
LQAS 2015. Note: 5% is the national average. Target is from SSFP 2020 commitment
| Outcome Indicator 4 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Percentage of births attended by skilled health personnel | Planned | 10.1% (39,012) |  |  |  | 11% | 11% (121,785) | BL- HPF 1 Period (Oct 2013 to March 216), M1- (April 2016 to June 2017) 15 months, M3- (April 2016 to March 2018) 24 months and Targets from April 2016 to Sept 2018 (30 months).
|  | Achieved |  | 10.9% (47,377) | 10.6% (57,670) | 11.1% (97,928)
Source
MoH HMIS/DHIS - Baseline 6 States, milestone 8 states, pop DHIS, M3 is manual calculation using DHIS population for 8 states, Target is modest because it is no cost extension coupled with insecurity hence no much change expected.
| Outcome Indicator 5 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Percentage of children 0-5 months receiving exclusive breastfeeding | Planned | 45% |  |  |  | 50% | 50% | See data source below, Household surveys are conducted every 5 years but none was done in 2015 and is not clear if there will be one in 2018, so we maintain Health Sector Development Plan Target
|  | Achieved |  | N/A
Source
Baseline - South Sudan Household Survey 2010, Target from HSDP
INPUTS (£) | DFID (£) |  | Got (£) | Other (£)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (Cumulative data HPF1 Start date - March 2016) | Milestone 1 (2017) Cumulative data (April 2016 to March 2017) | Milestone 2 (2017) Cumulative data (April 2016 to June 2017) | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018) |  |  | Assumptions
Strengthened delivery of health services, particularly responsive to the needs of women and children | Under five years outpatient consultations: (total 1 + 2) | Planned | 4239126 |  |  |  | 4953157 | 8252350 | BL- HPF 1 Period (Oct 2013 to March 216), M1- 12 months (April 2016 to March 2017), M2 - 15 months (April 2016 to June 2017), M3- 24 months (April 2016 to March 2018) and Targets from April 2016 to Sept 2018 (30 months). Note this is cumulative. |  | • MoH is able to pay for the BHI health workers • Availability of commodities from critical sources (e.g. UNFPA and family planning commodities) • Ability to work with the new administrative system, in a manner that allows the structures established in HPF1 to continue (community, county and state) • Other partners are able to provide top-up/emergency drugs if there are outbreaks or disease burden increases (e.g. WHO or UNICEF) • Emergency/ humanitarian partners continue to support the famine/high levels of malnutrition • Other programs from development partners continue without breakage (e.g. ICCM) • Government health workers continue to be paid • Large scale violence does not occur • Stability and access to health facilities is possible, conflict remains small scale and localised • Availability of qualified midwives and other skilled professionals does not decrease • ORS is available in facilities
| 1. curative consultations |  | 2901179 |  |  |  | 3481415 | 5607015
| 2. preventive/ promotive services |  | 1337947 |  |  |  | 1471742 | 2645335
|  | Achieved | Total | 3393819 | 4233077 | 7058302
|  |  | Curative | 2319909 | 2881310 | 4807770
|  |  | Preventive/Promotive | 1073910 | 1351767 | 2250532
Source
MoH HMIS/DHIS. Baseline 6 States, milestone 8 states
Gender disaggregation is not possible at the moment due to the revised HMIS tools for the Ministry, However, a 50% gender disaggregation formula can be applied to the results until the HMIS tools are revised in the further.
| Output Indicator 1.2 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Percentage of children under five years with diarrhoea who receive ORT | Planned | 86.2% |  |  |  | 91% | 91% | BL- HPF 1 Period (Oct 2013 to March 216), M1- 12 months (April 2016 to March 2017), M3- 21 months (April 2016 to Dec 2017) and Targets from April 2016 to March 2018 (24 months). Note the percentage is average not cumulative (DHIS calculates automatically)
|  | Achieved |  | 90.7% | 90.7% | 90%
Source
MoH HMIS/DHIS. Baseline 6 States, milestone 8 states
Calculation Number of under-five who are diagnosed with Diarrhoea and give ORT treatment (722019) divided by the Total number of under-five diagnosed with Diarrhoea (800229).
| Output Indicator 1.3 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Percentage of women who attended at least four times or more for antenatal care during pregnancy | Planned | 27.9% (110,248) |  |  |  | 28% | 27% (290,065) | To avoid confusion we shall leave as a percentage but the denominator will be determined using the DHIS population for the specific period.
|  | Achieved | 925918 | 26.8% (117,585) | 26.7% (147,212) | 26.96% (249,502) |  |  | BL- HPF 1 Period (Oct 2013 to March 216), M1- 12 months (April 2016 to March 2017), M2 - 15 months (April 2016 to June 2017), M3- 21 months (April 2016 to March 2018) and Targets from April 2016 to Sept 2018 (30months).
Source
MoH HMIS/DHIS. Baseline 6 States, milestones 8 States
Numerator is cumulative Data from April 2016 to March 2018, Denominator = Expected population/12*Number Months Covered during the project Implementation.
| Output Indicator 1.4 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Number of facilities with capacity to offer Emergency Obstetric care (disaggregate BEmONC and CEmONC) | Planned | CEmONC = 20 |  |  |  | 25 | 26 | BL - HPF 1, M3 is as of Oct to Dec quarter (used latest information). QTPR was used in conjuction with DHIS for data
|  |  | BEmONC = 34 |  |  |  | 37 | 44
|  | Achieved | CEmONC |  | 23 | 26
|  |  | BEmONC |  | 37 | 44
Source
HPF Health Facility Register
| Output Indicator 1.5 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Percentage of ANC attendees who received IPT2 and more | Planned | 51% |  |  |  | 52% | 52% | BL- HPF 1 Period (Oct 2013 to March 216), M1- 12 months (April 2016 to March 2017), M2 - 15 months (April 2016 to Juen 2017), M3- 24 months (April 2016 to March 2018) and Targets from April 2016 to Sept 2018 (30months). Note the percentage is average not cumulative (DHIS calculates automatically). Target below average because it is no cost extesion coupled with inaccessibility during rainy season and insecurity.
|  | Achieved |  | 52.1% | 50.7% | 52%
Source
MoH HMIS/DHIS - Baseline 6 States, target is 8 states
| Output Indicator 1.6 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Proportion of women 15-49 years using any modern family planning method | Planned | 5% |  |  |  | 6% | 6% | BL - 2015 survey, see data source below the milestone. Target is based on South Sudan commitment to FP 2020. It was 8% but was reduced to 6% looking at trends and challenges in FP
|  | Achieved |  | N/A
Source
Baseline - MoH Community LQAS 2015 National Average, Target based on SS FP 2020 commitment
| Output Indicator 1.7 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Percentage of counties where bulk consignments of medical drugs are distributed at Hospital and CHD level | Planned | NA |  |  |  | 98% | 98% | New Indicator, No BL - Period is taken from Planned consignment, M3 is distribution as of Oct 2017, target is also based on planned distribution. All counties and hospitals should be reached but usually due to insecurity there are some delays.
|  | Achieved |  |  | 98% | 98%
Source
Drug Distribution system - New indicator
| Output Indicator 1.8 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Number of health facilities providing family planning services with a minimum stock of three modern family planning methods including male condoms. | Planned | 86 |  |  |  | 338 | 200 | Commodities initially were distributed by UNFPA | Male condoms included, however, MOH does not list male condoms in the FP methods distributed. The changes in M1 and 2 could be due to a range of things: reporting, stock outs, and conflict. FP commodities are included in HPF supply chain distirbution plan, but the next distribution will be in October 2018.
|  | Achieved |  | 59 | 63 | 86
Source: DHIS -M1 - Jan-March 2017, M2 - April-June 2017, M3 - Jan- March 2018.
Milestone data from DHIS (latest period), Count of facilities that have reported atleast 3 modern methods within last 3 months period. Note that this method relies on monthly report submission, the number would flactuate from quarter to quarter depending on timeliness and completeness of reports i.e all health facilities submit reports on time. Also this will depend on utilisation of FP by clients as well as availability of data collection tools. This method will change once the IPs begin to use a checklist for availbility of methods rather than utilisation.
| Output Indicator 1.9 |  | Baseline (Cumulative data for 8 states in 2015) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Number of Antenatal client given Ferrous Sulphate + Folic Acid supplementation | Planned | 13453 |  |  |  | 320617 | 489031 | BL is from HMIS data Jan to Dec 2015, the indicator was no longer in the DHIS and hence from 2016 data is from QTPR. M1 is 12 months, m2 15 months, and M3 is 24 months. Data is cumulative. Target will be 30months.
|  | Achieved |  |  | 195622 | 447970 |  |  | Indicator 3.4 shifted to output 1
Source
QTPR HPF 2
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018) |  |  | Assumptions
Strengthened health systems at State and County level with detailed focusing on | Number of HPF Steering Committee meetings co-chaired by GRSS (cumulative) | Planned | 15 |  |  |  | 19 | 19 | BL - HP 1 period, M1 12 months, M2 - 15 months, M3 24 Months and target 30 months, note this is cumulative and include HPF 1 meetings. Data reportd quarter.
• Policy |  | Achieved |  | 15 | 17 | 18
• Human resources for Health |  |  | Source
• Health Financing including strengthening of payroll |  |  | Meeting minutes
• Health Information | Output Indicator 2.2 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
• Leadership and governance | Number of State Oversight Committee meetings held (cumulative) | Planned | 34 |  |  |  |  | 60 | Meetings started late due to delay in State Support Funds, the creation of new states and the disruption in 2016 due to the multiple bridging contracts Assumption is that there will be at least 1 meeting in each state for the remaining period
|  | Achieved |  | 36 | 44 | 52 | 53 |  | BL - HP 1 period, M1 12 months, M 2- 15 months, M3 24 Months and target 30 months, note this is cumulative and include HPF 1 meetings. Activity reported quarterly.
Source
Meeting minutes
| Output Indicator 2.3 |  | Baseline (March 2016) | Milestone 1 (2017) | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Number of counties with one comprehensive health plan + budget (government and all partners info combined) | Planned | 100% (39) |  |  |  | 100% (55/55) | NA (No Annual Plans During Extension) | BL for 6 states and used county system. M3 completed 23 lots in August 2017. Assumption is that HPF lots planning workshop provides the bases for counties to develop comprehensive workplans which includes other sources of fund.
|  | Achieved |  | 0 | 0 | 100%
Source
The baseline was 6 states, the target is counties in eight states (55 Counties)
County Plans/ Ips Lots Work plan)
| Output Indicator 2.4 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Number of counties in which HRIS is implemented | Planned | 92% (36/39) |  |  |  | 96% (53/55) | 94% (50/53) | Due to conflict Mayendit and Leer counties were not accessible at the time. A new wave of violence erupted in September 2017 | In addition to Mayendit and Leer, also Yei, Lainya, Morobo and Kajo Keji have been inaccessible to roll out the HRIS to date. We are not anticipating access between Apr and Sep 2018 unless situation improves.
|  | Achieved |  | 74% (39/53) | 83% (44/53) | 94% (50/53)
Source
HRIS Database
Baseline was counties in 6 states (Out of 39 Counties, 36 counties has HRIS implemented) Target is counties in 8 states
| Output Indicator 2.5 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Percentage of functional health facilities with quarterly integrated supportive supervision visits conducted by county health department using the QSC tool | Planned | 72% |  |  | 2499 | 60% | 60% | Target below the baseline because of insecurity. In Western Equatoria and CES facilities which are operational cannot be visited because either the area is under opposition control or the road is too risky for the staff members to travel. | Due to accessibility during the rain season couple with insecurity some of the facilities will not be supervised each quarter, which is why the target is below the baseline.
|  | Achieved |  |  | 52.2% | 51.48%
Source
|  |  | DHIS - Baseline 6 States, reporting on the indicator ended in March 2016, from April 2016 to Nov 2016 No data (bridging phase) | [5 empty] | See notes below data source, targeting at least 1 supervision per facility per quarter
Milestone is Calculated as Cumulative number of QSC reports in DHIS /Total Number of HFP supported facilities (PHCUs+PHCCs Functional) * Number of Quarters (Nov 2016 March 2018)
| Output Indicator 2.6 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Percentage of functional health facilities submitting HMIS reports through the DHIS timely (according to the data flow policy) | Planned | 88% |  |  |  | 85% | 83% | Formation of new counties impacts on reporting greatly as additional budget is required to bring the new counties up to the same standard as the established counties and these funds are not allocated. Inaccessibility due to insecurity (some reports either received very late or not at all). | Currently 83% of the health facilities are functioning. The denominator for this indicator is the total number of health facilities (functioning and non-functioning) so a target of 83% indicates that all the functioning facilities are submitting their reports.
|  | Achieved |  | 84.55% (10309/12,192) | 83.16% (12,674/15,240) | 81% |  |  | BL - HPF 1 period, M1 12 months, m2 15 months, M3 24 Months and target 30 months, note this is cumulative, see more notes below data source. (Note: Denominator = 1032 HF*xmonths)
Source
MoH HMIS/DHIS - Bassline 6 States, target 8 states (Milestone 1 - 12 months reports, Milestone 2 - 15 months reports, M3 - 24 months reports)
Baseline is high due to the overachievement in HPF 1 target in the 6 states, intended to maintain the target as M3 to as access to some health facility is likely to be affected due to insecurity and rains.
Number of HPF support Facilities {Numerator ( cumulative number of submitted reports) = Denominator expected reports (Number of HF * No of Months)}
| Output Indicator 2.7 |  | Baseline (March 2016) | Milestone 1 (2017) | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Number and percentage of functional health facilities with a health committee in place for communities to give feedback regarding health services | Planned | 60% (405/671) |  |  |  | 95% (768/809) | 95% | BL HPF1, M1 12 months,M2 15 months, M3, 24 Months and Target 30 months. Note this is latest information (on quarterly bases) not average or cumulative. Note that these are voluntary organisations and functionality keep changing.
|  | Achieved |  | 66% (651/986) | 92% (743/809) | 96.29%
Source
QTPR - non cumulative (latest value) - Baseline for 6 States. Measures only HPF supported Health Functional facilities, Target 8 States (809 - PHCCS+PHCUs)
| Output Indicator 2.8 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Percentage of functional health facilities which have documented joint meetings held with the health committee and health facility and either CHD or IP (i.e a quorum of 3 with the health committee and health facility being the main parties. CHD and/or IP will be present) | Planned | 49.6% |  |  |  | 30% | 50% | Insecurity prevailing in former WES, CES, Unity State, parts of Lakes State and part of EES, makes convening these meetings very difficult for all 4 parties at a health facility experiencing insecurity. | The meetings will depend on the availability of HC and health facility members. Asumpiton is that either CHD or IP will jion these meetings. That means a quorum of 3 is acceptable.
|  | Achieved |  |  | 29.48% | 27.12%
Source
QTPR - Baseline for 6 States, reporting ended in March 2016, Between April to Nov 2016 no data (bridging phase)
|  |  | Milestone is Calculated Cumulative number of Meetings reported in the QTPR/Total Number of HFP supported facilities functional* Number of Quarters, Quarter Nov-Dec 2016 excluded from the Denominator | [5 empty] | See notes below data source, BL HPF1, M1 12 months, M3 24 months and Target 24 months, cumulative number of meetings will be the numerator and denominator is no of HPF supported HF that are functional
| Output Indicator 2.9 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Percentage of health committee representatives that are women | Planned | 38% |  |  |  | 33% | 33% | In the two new added states there was less emphasis on women representation in the health committee, which has brought the percentage down, and changing membership is a gradual process | 35% is the government's affirmative action toincrease female representation. But because health committees are organisations where membership is voluntary with no incentive, HPF kept a modest target of 33%.
|  | Achieved |  | 29.91% | 33.29% | 31.66%
|  |  | Source | [7 empty] | RISK RATING
QTPR - Non Cumulative, report latest value
|  |  | Baseline was achievement for HPF1 in 6 states. The Milestone is calculated based on the latest information as reported in the QTPR for 8 states, In the two new added states there was less emphasis on women representation in the health committee, changing of membership is a gradual process, in addtion these are voluntary organisations | [5 empty] | Uses latest information per quarter, not cumulative or average | Last mile delivery to the health facilities in the rainy season from Jun-Sep 2018 is expected to be challenging. Stock outs are expected to be lower than the Mar-Jun 2017 (52%) but higher than Jun-Mar 2018 (38%)
| Output Indicator 2.10 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018) | BL- is March 2016, M1- 12 months (April 2016 to March 2017), M2 - 15 months April 16 to June 2017 M3- latest data (Jan-March 2018) and Targets from April 2016 to Sept 2018 (30months). Note the percentage is average not cumulative.
IMPACT WEIGHTING (%) | Percentage of health facilities with reported stock outs of all 4 tracer drugs supplied through HPF | Planned | 50% |  |  |  | 45% | 35% | Indicator 1.8 shifted to 2.10 based on SAB discussions
|  | Achieved |  | 55% | 52% | 38%
Source
E-monthly Reports, reporting latest quarter; Target below M3 because of rainy season and insecurity Amoxycillin 250mg caps/tabs, Artesunate+Amodiaquine Adult (6 tabs), Artesunate+Amodiaquine Todler (3 tabs) and ORS
INPUTS (£) |  |  | Govt (£) | Other (£)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018) |  |  | Assumptions
Increased access to nutrition services particularly for pregnant women and young children | Number of children under five weighed and measured as part of preventative or curative consultations (total) | Planned | 212543 |  |  |  | 835434 | 1449656 | BL- data for 6 states for 2016 (Jan-Dec 2016), note this is cumulative, M1 is 12 months,M2 - 15 months, M3 is 24 months and target will be 30 months |  | • Availability of commodities from critical sources (e.g. UNICEF) • Emergency/ humanitarian partners continue to support the famine/high levels of malnutrition • Stability and access to health facilities is possible, conflict remains small scale and localised • Other programs from development partners continue without breakage (e.g. ICCM, Nutrition Cluster) • Government health workers continue to be paid • Large scale violence does not occur
|  | Achieved |  | 507703 | 660884 | 1234799
Source
DHIS - Baseline 6 States
Achievement is cumulative data from April 2016 to March 2018
Data disaggregation no possible due to the Revised HMIS Tools
| Output Indicator 3.2 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Number of health workers trained on CMAM and MIYCN (disaggregated by gender) | Planned | 0 |  |  |  | 1285 | 2847
|  | Achieved |  | 689 (Female 208 i.e. 29.8%) | 1249 (Female 378 i.e. 30.26%) | 2,711 (Female 1007 i.e. 37%) |  |  | New indicator, no BL, M1 is 12 months data, M2 15 months and M3 is 24 months and target is 30 months. Note this is cumulative, reported quarterly.
Source
QTPR - New indicator, Hence no Baseline
| Output Indicator 3.3 |  | Baseline (March 2016) | Milestone 1 (2017) April 2016 to March 2017 | Milestone 2 (2017) April 2016 - June 2017 | Milestone 3 April 2016 - Mar 2018 | Target March 2018 (April 2016 -March 2018) | Target Sept 2018 (April 2016-Sept 2018)
| Number of children nutrition outpatient discharged cured six to 59 months (total) | Planned | 4726 |  |  |  | 73031 | 116557 | BL 6 States (Jan-Dec 2016), M1- 12 months, M2 - 15 months and M3-24 Months and target will be 30 months. Note this is cumulative.
|  | Achieved |  | 45518 | 55124 | 103042
|  |  | Source | [7 empty] | RISK RATING
DHIS - Baseline 6 States
Cumulative data reported monthly through the DHIS in 8 states
IMPACT WEIGHTING (%)
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£)
INPUTS (HR) | DFID (FTEs)

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.