Annual Review

Title: Business in the Community: Private Sector Engagement Programme
Programme Value £ (full life): £755,000		Review Date: 14th July 2018
Programme Code: 203417	Start Date: 15th July 2013	End Date: 15th July 2018

Summary of Programme Performance
Year	2014	2015	2016	2017	2018
Programme Score	A	A+	A+	A+	A
Risk Rating	Low	Low	Minor	Minor	Minor

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Log Frame

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

The UK is providing £755,000 over a five year period (2013 – 2018) to Business in the Community (BITC) to help improve the coordination and effectiveness of the UK private sector’s response to humanitarian emergencies. A three month no cost extension has been approved in principle, pending successful clearance of DFID’s enhanced safeguarding due diligence procedures.

At the time of the original business case, there had been a growing sense within the humanitarian sector that, beyond monetary donations, there was insufficient guidance, support, and regulation to guarantee quality humanitarian support from businesses. Moreover, a lack of mutual understanding and communication between humanitarian and commercial actors meant that access to the opportunities which humanitarian-business partnerships represent had been inhibited. This project was designed to help address this problem, and through it BITC have produced guidance and provided training to business in the delivery of humanitarian and emergency aid. They use their extensive networks and convening power to deliver this work and bring business and non-government organisations (NGO) together.

Through the project, BITC also arrange and deliver the International Disaster Relief and Resilience Award category at the annual Responsible Business Awards which showcases the best efforts of business in humanitarian response over the year, and works to continually promote business engagement.

Summary supporting narrative for the overall score in this review (1/2 page)

The overall score for the programme this year is an A.

Output 1’s major milestone was the increase in submissions for the Disaster Relief Awards. This year saw a considerable reduction in entries. Other indicators under output 1 were largely met, either slightly exceeding or missing milestones. The overall score for output 1 is a B.

On output 2, a major milestone was the use of a ‘matching tool’, called the Hub, to match businesses and NGOs. While development and launch of the Hub was successful, and considerable effort was put in by BITC to encourage its use, it was discovered early on after its launch that it was not going to deliver planned matches between businesses and NGOs. However, research is indicating that the work BITC has put in to bring together business and NGOs is achieving the building of partnerships – which is the wider goal of the Hub. BITC have also demonstrated that their influencing capacity is helping push the programme’s agenda beyond events that BITC organise. The overall score for this output is a B.

The milestone for output 3, 200 senior practitioners and business leaders engaged in seminars, simulations and training by July 2018 has been significantly exceeded and reflects the particular strength of convening and influencing groups that BITC bring to this agenda. The score for output 3 is an A+.

Recommendations for the year ahead (1/2 page)

DFID and BITC have agreed a 3 month no-cost, time only, extension to this programme - pending successful completion of DFID’s recently introduced enhanced due diligence procedures. The extension will allow BITC to produce a further research paper, ‘Business’s Unique Contribution III’ (BUC III). This piece of research will focus on evaluating the activities of the DFID grant and gain a better understanding of how long-term partnerships with business have been created through the grant. This will help BITC think about sustainability beyond the DFID grant. BITC will also use the currently unallocated budget to continue with awareness raising activities around business’s role in disaster relief.

As the Hub has not had the desired uptake of engagement with business and NGOs as originally planned, BITC will also use the additional time to explore options for getting best value out of the Hub to ensure that the efforts made to develop it do not go to waste. BITC is already in discussions with the United Nations Office for the Coordination of Humanitarian Affairs (UNOCHA) Connecting Business Initiative about possibilities for collaboration using the Hub platform.

BITC are also interested in focussing on how partnerships move from the relief stage to more strategic partnerships to help build resilient communities, including a focus on preparedness rather than just disaster response.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Increased insight and understanding for business on how they can best assist during humanitarian emergencies
Output number per LF		1	Output Score	B
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Development and delivery of annual BITC International Disaster Relief Award as part of the BITC International Disaster Relief programme (IDRP).	International Disaster Relief Awards held annually and show a 15% increase in submissions between 2014-2018.	3 Award entries for 2018, down from 11 last year.
Numbers of best practice case studies identified	50 case studies available: June 2018	Currently there 52 case studies have been identified. BITC are working on some additional data from their last research which they plan to convert into further case studies.
Publications referencing the business case for business engagement in disaster relief.	10% increase in the number of site visits to publications, research and insight papers by June 2018	From the baseline there has been an estimated 56% growth in the number of times BITC reports have been downloaded.
Online guidance for business on engagement with humanitarian community on BITC website.	15% increase users accessing online guidance by May 2018, against 2014 figures.	BITC’s latest guidance has been downloaded by 51 users against a 2014 baseline of 48, but see caveat below.

Provide supporting narrative for the output

By the time the call for entries for the International Disaster Relief and Resilience award process closed, 11 businesses had started the application form and 3 award entries had been made. The quantity of entries has decreased this year, but not the quality. BITC organised rounds of assessments to judge the entries, and following the assessments BITC prepared feedback for all companies who entered, based on the scores and comments of the assessors. DFID staff took part in the assessment and judging panels. To promote a good level and range of entries BITC actively reached out to target companies during the call to entry period, and publicised the award through external networks. The announcement of 2017 winners was made in July 2017 as planned.

Given the strong field of entries in previous years, BITC reported that some businesses did not believe that their disaster relief work was strong enough to win an award, so declined to enter. The disaster relief award category is less broad than other award categories, and BITC suggested that some businesses may have opted to submit an entry that could have been for the disaster award category under a different award.

This year 9 new case studies have been added to the website as part of the 2017 and 2018 Awards. In total, over the years of the programme, BITC has published over 50 case studies, slightly exceeding the target for the programme. In the first and second edition of BITC’s research 'Business Unique Contribution' a total of 21 case studies were included. Another 22 appeared in BITC’s guidance for business 'Addressing International Disaster Relief and Resilience'. There will be more to come in this year's edition of 'Business Unique Contribution' which is due to launch in September, pending the three month extension.

Since the baseline year, the number of downloads for BITC’s 2 research documents (Business Unique Contribution I and Business Unique Contribution II) has grown by 56%. There have been some changes to BITC’s data storage system which has meant moving where the research documents are located on the website. This has meant that BITC have not been able to report on the total number of page views. However, if these were considered it is likely that the growth of access to the documents would be higher. Similarly, online guidance has been downloaded a total of 51 times but access is anticipated to be higher. Also, BITC send guidance and research by email as a soft copy and distribute hard copies at events. Apart from the guidance and the different editions of the research over the last 5 years, BITC’s online presence has also grown by posting blogs and tweets on disaster relief. The latest one took place earlier on the year when a blog was published on the BITC website in partnership with the gender campaign at BITC calling for business to help NGOs implement better safeguarding policies by sharing their skills, expertise and experience. The blog can be accessed here.

While output 1.1 has shown a significant drop off from previous years, outputs 1.2 and 1.3 have been slightly over-achieved and 1.4 slightly under-achieved. Progress on developing and enabling access to programme relevant guidance and information has been good. On average, therefore, this output scores a B.

Lessons identified this year, and recommendations for the year ahead linked to this output
Previous annual reviews have recommended that BITC keep a watching brief on opportunities to explore and identify case studies and award entries from private sector engagement in conflict affected settings, while acknowledging that this is a particularly challenging area. This year there were some entries relating to this, including a programme developing an education system that will help children in extreme mobility circumstances to continue with their education. This programme is an example of the trend identified through initial findings in BITC’s latest research whereby businesses are working in ways that don’t just help improve the current situation of affected people, but also their future lives. The research suggests that many businesses have gone from responding to disasters to helping build resilient communities.

In previous years submissions for entry in the Disaster Relief and Resilience Award category at the annual Responsible Business Awards has been steadily increasing. This year saw a significant drop off in entries. The reason for this should be further understood, including whether it is an indicator of this agenda having a reduced focus for businesses.

Output Title	Partnerships between NGOs and businesses are created
Output number per LF		2	Output Score	B
Impact weighting (%):		40%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Number of new partnerships between NGOs and business established facilitated by BITC and supported by the Global Relief and Resilience Hub (the Hub)	15 new partnerships by May 2018	No ‘matches’ have been made to date using the Hub. In BITC’s last survey, out of 43 businesses 11 have said that they have found the overall programme useful to develop their partnerships. 4 NGOs out of 11 have reported that the programme has been useful to develop partnerships.
Number of forums and increase in dialogue around importance of engagement and partnerships between NGOs and business.	Increased corporate engagement and commitment to humanitarian forums and non BITC organised dialogue: May 2018	This reporting year BITC has organised 3 events for the International Disaster Relief and Resilience programme: the Hub launch, a collaboration roundtable, and a CEO dinner. / The Hub was also presented at the DEC Leadership Team Meetings and at a stand at the ‘Flood Expo’ event.

Briefly describe the output and provide supporting narrative for the output

The key part of output 2.1 throughout this programme has been the development of a ‘matching tool’, the Hub, which would enable the matching of offers from business with needs of NGOs in any given emergency situation. The development, awareness and testing of the Hub, facilitated by BITC throughout the programme has been consistently positive. However, the final target of achieving 15 matches through the Hub has not been successful, and no matches have been made to date.

BITC did put effort after the launch of the Hub to encourage uptake. For example, following the 3 weeks of hurricanes in the Caribbean and US, earthquake in Mexico and flooding in South Asia, the team was active in contacting BITC members to use the Hub to demonstrate their offers. While specific matches weren’t made using The Hub, BITC did report that BITC members were active in disaster relief activities: providing flights to assessment teams, providing cash donations and using logistics expertise.

BITC were quick to inform DFID of the low uptake of the Hub after it went live, and a project refocus was agreed. For the remainder of the programme, BITC will continue to monitor the Hub and manage the back-end for any new registrations and potential activity, however, they will place more focus on understanding how partnerships have been forged over the lifespan of the 5-year programme. This will primarily be achieved through the research evaluation which will inform Business Unique Contribution III.

During the last 5 years BITC has organised numerous fora and workshops bringing together business and NGOs. These have included ‘speed dating’ exercises which facilitated Business and NGOs to meet one another and simulation exercises to enable business to understand how their business could help when a disaster hits a community. Overall, a strength of BITC, recognised through previous annual reviews and day to day engagement, has been its ability to convene business and NGOs around the disaster relief agenda. From BITC’s last research on business engagement (BUC II) in International Disaster Relief and Resilience it has been shown that 11 businesses and 4 NGOs have found the programme useful to develop their partnerships with each other.

The previous annual review had a milestone to organise a collaboration roundtable on strategic responses to disasters. This was delayed due to the launch of The Hub. The event was organised for September in this reporting year. It included a full day of discussion on how to enhance, rethink and break down barriers of collaboration between the private sector and humanitarian organisations. There were 20 delegates, with an equal balance of business and humanitarian representation. The day focused on what could be done more effectively in business and NGO partnerships to address disaster relief and resilience, and how business can make more meaningful contributions to disaster relief. Feedback from the event showed that 75% found the event very useful and 25% found it useful.

Apart from events organised themselves, BITC have presented the programme at events organised by other organisations to expand the footprint of the programme and bring more people on board. During the International Disaster Relief and Resilience Dinner in May, a representative from an academic institution agreed to host a workshop on business engagement in disaster management in September. This is a demonstration of BITC’s networking and influencing capacity.

While the Hub, under output 2.1, has not had the success anticipated, the research is indicating that the work BITC put in to bring business and NGOs together is achieving the building of partnerships, though maybe not on the scale initially envisaged. BITC have also demonstrated that their influencing capacity is helping push the programme’s agenda beyond events that BITC organise. The overall score for this output is a B.

Lessons identified this year, and recommendations for the year ahead linked to this output
Following the launch of the Hub this year it has become evident that an online platform might not be the best place to create partnerships. Rather, these need a level of common understanding difficult to reach through an online platform, but possibly better facilitated through BITC’s series of events which seem to have shown more promise in achieving the programme’s desired partnership building between business and NGOs.

While the DFID grant with BITC is in its final stages, BITC are showing interest in continuing with this agenda through its core business including how they can support existing partnerships to grow with a focus in the whole disaster management cycle rather than just the immediate relief stage.

During recent months BITC have been in touch with the UN. In 2017 UNOCHA launched the Connecting Business Initiative, a demand driven multi-stakeholder initiative transforming the way the private sector engages before, during and after crises to create more resilient communities, increase local capacity and alleviate human suffering. BITC will remain in conversation with them to understand how they can better collaborate together in the future.

Output Title	Raised awareness amongst business and NGOs of the importance and effectiveness of the private sector in humanitarian response
Output number per LF		3	Output Score	A+
Impact weighting (%):		30	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Capacity building for business to identify their unique contribution and better understand how it can be used.	200 senior practitioners and business leaders engaged in seminars, simulations and training by July 2018	During the last 5 years BITC has had 575 senior practitioners and business leaders attending seminar, simulations and trainings.

Provide supporting narrative for the output
Over the last 5 years BITC has organised multiple events from webinars and workshops, breakfast and launch events, to smaller events in which they have brought together key players from the private and humanitarian sector to discuss opportunities and challenges when responding to disasters together. 575 senior practitioners have attended these events. As well as events organised by BITC, senior practitioners have also engaged with BITC during other events where BITC have presented on the work of the programme.

As part of BITC’s series of publications, ‘Business Unique Contribution’, case studies have been collected and presented in events for senior practitioners to reflect on how their own business can do something similar and incorporate international disaster relief into their core business strategy.

Evidence to demonstrate how BITC members have increased their involvement in this agenda has been conducted through a random search that BITC made on references to support for international disaster relief in companies’ external communications. A 16% growth was seen since 2014 in the number of business reporting on this, and it was also observed that businesses have moved from cash contributions to sharing skills and expertise as their preferred method of contributing.

BITC have performed very well against this output, over doubling the expected target. As such, this output scores at an A+

Lessons identified this year, and recommendations for the year ahead linked to this output
BITC plan to continue working in this area and are interested in focussing on how partnerships move from the relief stage to more strategic partnerships to help build resilient communities, including a focus on preparedness rather than just disaster response.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year
The causal chain in the Business Case suggests that the creation of guidance for business, development of a matching tool to link businesses and NGOs, and the establishment of the disaster relief award category will lead to the following outputs:
- Increased insight and understanding for business on how they can best assist during humanitarian emergencies
- Formal partnerships between NGOs and businesses
- Raised awareness amongst business and NGOs of the importance and effectiveness of the private sector in humanitarian response.

The outcome of the programme is that the UK private sector demonstrates stronger engagement in disaster response at a corporate level. The higher level impact of the programme is a private sector that is harnessed to reduce suffering in humanitarian disasters.

The assumption underpinning the causal chain is that increased awareness amongst NGOs and businesses of the case for action and how to do it, as well as practical support and brokering, will scale up the level of private sector engagement.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead
The recent evidence collected under output 3 indicates that the assumption under the causal chain is on the right track, highlighting that a 16% growth was seen since 2014 in the number of business reporting on disaster relief and that businesses have moved from cash contributions to sharing skills and expertise as their preferred method of contributing.

The major change over the past year to the logic of the theory of change is that it became evident that the Hub matching tool was not an effective vehicle for partnering NGOs and businesses. That aside, the programme has enabled effective partnering between NGOs and businesses through BITC’s core business activities. BITC is in discussions with UNOCHA’s connecting Business Initiative about possibilities for collaboration using the Hub platform.

In the remaining time left on the programme, including the proposed no cost extension, BITC will produce a further research paper, ‘Business’s Unique Contribution III’. This piece of research will focus on evaluating the activities of the DFID grant and gaining a better understanding how long-term partnerships with business have been created through the grant. This will help BITC think about sustainability beyond the DFID grant.

In previous years, submissions for entry in the Disaster Relief and Resilience Award category at the annual Responsible Business Awards has been steadily increasing. This year saw a significant drop off in entries. The reason for this should be further understood.

Explain major changes to the logframe in the past year
There have been no major changes to the logframe over the reporting year. Outcome indicator 3.2 relating the World Humanitarian Summit was removed as it was completed last year.

Describe any planned changes to the logframe as a result of this review
This review draws to a close the current output milestones on the logframe. A new logframe will be developed at the output level for the remaining time on the programme. This will be completed depending on the outcome of the proposed no-cost extension.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year
The value for money proposition in the original business case highlights BITC’s strategic position as a central source of advice and guidance for the private sector. Its wide network of members was noted as providing an opportunity to effect sector-wide change in humanitarian response, improving the private sector’s coordination during humanitarian emergencies and offering the potential to improve the quality and effectiveness of their responses. Making funding agencies and NGOs more aware of private sector resources was also highlighted as something that would enable smarter funding decisions.

BITC has continued to deliver against these VFM objectives. BITC uses a well-established and maintained database of over 800 business members. BITC continues to update the database through discussions with existing and target business, and uses this data to target guidance, research and events relating to emergency response.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

In addition to the value for money proposition in the original business case, BITC presents good economic VFM through its ability to use pro-bono support from its members (including venue hire, printing costs, and the development of the Hub).

The use of BITC’s database of business and its capacity to convene business around the programme’s agenda highlights the efficiency with which using an organisation such as BITC offers this programme. Despite the lack of uptake in the use of the Hub, through its core business activities BITC have demonstrated good ability to convene business to push the programme’s agenda.

The effectiveness of working with BITC is demonstrated by the research that BITC have undertaken which has shown a 16% growth rate seen since 2014 in the number of business reporting on disaster relief, and also that businesses have moved from cash contributions to sharing skills and expertise as their preferred method of contributing.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

The risk, identified in the business case, of there being insufficient interest and commitment among business and humanitarian agencies to pursue this agenda has remained low. However, the recent reduction in business interest in submitting applications to the International Disaster Relief and Resilience Award category at the annual Responsible Business Awards and limited uptake in use of the Hub may indicate that this risk is being realised.

That said, business engagement in disaster relief has been reported as occurring through other areas, such as the 16% growth rate of business reporting on the agenda since 2014 and businesses moving from cash contributions to sharing skills and expertise as their preferred method of contributing; and also, as noted under output 2, reporting of BITC members being active in disaster relief activities: providing flights to assessment teams, providing cash donations and using logistics expertise.

Through BUC III BITC will look at the lessons learnt over the grant period, including the Hub, and assess the strengths and weaknesses of the programme with a view to future engagement.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues

The programme is projecting a £40,595 underspend, most of which will be reallocated under the proposed no-cost extension.

While the spend has been lower than anticipated across most budget lines, the majority of the underspend can be directly attributed to costs that had been budgeted against The Hub, a) since it was built pro-bono by PwC and b) because it has not had the traction anticipated since its launch and therefore minimal time and resource have been allocated against it. Also, a restructuring in BITC has led to the merger of teams which is now overseen by a seconded member of staff who does not incur any costs to the programme budget.

As mentioned above, BITC’s ability to leverage pro-bono support against this programme for things such as venue hire, publications and the Hub has been a strong driver in keeping project costs to a minimum.

Date of last narrative financial report(s)	25/04/2018
Date of last audited annual statement (s)	09/11/2017

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

As the programme comes to an end, pending the time extension to the project, BITC plans on carrying out a research evaluation of the impact of BITC’s international disaster relief and resilience campaign over the last four and a half years, including the development of private sector international disaster management policies and processes and the progression of relationships with humanitarian NGOs.

The research, BUC III, will complement and build on two previous research publications of the same name. The research for ‘Business Unique Contribution I’ was carried out in spring 2014, at the beginning of the programme, to establish the level of business engagement in international disaster relief and resilience as well as expectations from both the business and NGO communities. The second iteration of research, ‘Business Unique Contribution II’ provided a midpoint review of the progression of business engagement in international disaster relief and resilience. The aim of the 2018 research will be to capture the evolution of this engagement since 2014 and will further act as an evaluation of the programme.

Progress on recommendations from previous reviews (1/2 page)

The previous review had 3 main recommendations:

DFID should think about options for continued business engagement in humanitarian and disaster relief beyond this project’s grant period
Under the proposed no cost extension, BITC will be using BUC III to help identify how the agenda can be sustained post-DFID funding.

Before the 2018 awards cycle begins BITC plan to do an internal and external review of the process, marketing and engagement, in order to drive and improve the awards process.
In 2018 the BITC awards team have made the application process easier for business and BITC by integrating the process in an online platform. The assessment phase has also been simplified by having an online phase in which assessors can read the entries in their own time, rather than bring the assessors together for a full day in a venue reading entries.

Now that the Hub has been launched, thought should be given to ensuring that it is fully utilised, maintained, and continually improved.
BITC are currently in discussions with UNOCHA’s Connecting Business Initiative about possibilities for collaboration. The Connecting Business Initiative carried out a mapping exercise to understand what private sector collaboration platforms were already in existence and decided not to build their own, when they learned that BITC was building a platform with this purpose in mind.

Smart Guide

The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (e.g. first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the output
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided