African Health Markets for Equity (AHME)
Business Case

June 2012
Table of Contents

List of Abbreviations

ACT	Artemisinin-Based Combination Therapy
AHME	African Health Markets for Equity
AIDS	Acquired Immune Deficiency Syndrome
ARI	Acute Respiratory Infection
AusAID	The Australian Government Overseas Aid Programme
BCC	Behaviour Change Communication
BMGF	Bill and Melinda Gates Foundation
CCT	Conditional Cash Transfers
CHW	Community Health Worker
COC	Combined Oral Contraceptive
COHSASA	Council for Health Service Accreditation of Southern Africa
DALY	Disability Adjusted Life Year
DFID	United Kingdom Department For International Development
DHS	Demographic and Health Survey
DSF	Demand Side Financing
EC	Emergency Contraceptive
FP	Family Planning
GBV	Gender Based Violence
GF	Grameen Foundation
GFATM	Global Fund to fight AIDS, Tuberculosis and Malaria
GIZ	Gesellschaft für Internationale Zusammenarbeit
HANSHEP	Harnessing Non-State Actors for Better Health for the Poor
HCT	HIV Counselling and Testing
HIA	Health in Africa, International Finance Corporation
HIFI	High Impact Framework for Integration
HIV	Human Immunodeficiency Virus
HMO	Health Maintenance Organisation
ICT	Information and Communications Technology
IFC	International Finance Corporation
ISO	International Organisation for Standardization
ISQua	International Society for Quality in Health Care
KfW	Kreditanstalt für Wiederaufbau
K-MET	Kisumu Medical and Education Trust
LLIN	Long Lasting Insecticidal Net
MCF	Medical Credit Fund
MDG	Millennium Development Goals
mHealth	Mobile health
MIP	Medical Insurance Provider
MIS	Management Information Systems
MMR	Maternal Mortality Ratio
MNCH	Maternal, Neonatal and Child Health
MOH	Ministry of Health
MOTECH	Mobile Technology for Community Health programme
MSA	Medical Savings Account
MSI	Marie Stopes International
NGO	Non-Governmental Organisation
NHIS (Ghana)	National Health Insurance Scheme
NHIF (Kenya)	National Hospital Insurance Fund
NHIS (Nigeria)	National Health Insurance Scheme
OOP	Out of Pocket Payments
ORT	Oral Rehydration Therapy
PAC	Post Abortion Care
PAFP	Post Abortion Family Planning
PEPFAR	President's Emergency Plan for AIDS Relief
PharmAccess	PharmAccess International
PMTCT	Prevention of Mother to Child Transmission
PPMV	Proprietary Patent Medicine Vendor
PPN	Private Provider Network
PPP	Public Private Partnership
PSI	Population Services International
SFH	Society for Family Health Nigeria
SME	Small and Medium sized Enterprises
SMS	Short Message Service
SP Prophylaxis	Sulfadoxine and Pyrimethamine Prophylaxis
SSA	Sub Saharan Africa
STI	Sexually Transmitted Infection
STD	Sexually Transmitted Disease
TA	Technical Assistance programme - part of MCF
TAP	Technical Advisory Panel
TB	Tuberculosis
UCSF	University of California San Francisco
UNICEF	United Nations Children’s Fund
USAID	United States Agency for International Development
VMMC	Voluntary Male Medical Circumcision
WHO	World Health Organisation

Intervention Summary
## Title: African Health Markets for Equity

What support will the UK provide?
DFID will provide £22 million (US$33.5m) over 5 years from 2012 to 2017 for high quality health care delivered through the private sector and targeted at the poor in Ghana, Nigeria and Kenya. DFID funding will be matched by the Bill and Melinda Gates Foundation (BMGF). All support will be channelled through the group for Harnessing Non-state Actors for Better Health for the Poor (www.hanshep.org).

Why is UK support required?
What need are we trying to address? / Diseases such as malaria, HIV/AIDS, tuberculosis (TB) and conditions such as childhood pneumonia and diarrhoea are rife in Sub-Saharan Africa (SSA). Services such as skilled delivery of babies and family planning are under-provided and underused. Half of health expenditure is paid from personal funds, often further impoverishing the poor and reducing their likelihood to seek care. Poor women and children suffer most. / To improve access to and quality of health care, public and private health care providers and patients must be involved. DFID already provides significant support to provide essential health services in the public sector in many countries. But the non-state sector, both commercial for profit and not-for-profit (for simplicity termed the “private sector” among health specialists), plays a critical role in the provision of health care and, in many countries, is larger than the public sector. However, private healthcare providers are disorganised, unregulated and (like many public providers) often provide poor quality services. / To improve the access of the poor to private health providers in SSA, supply and demand-side constraints must be tackled together. Supply-side interventions should improve the quality, scale, and scope of health services available, and demand-side interventions must give purchasing power to poor clients to improve the affordability of privately provided services.. To date, supply and demand-side interventions have tended to be implemented separately. While it is plausible in theory to expect that implementing them together might increase the results that can be achieved for a given level of investment (i.e. the value for money), there is little evidence available to show whether or not this is true in practice. / What will we do to tackle this problem and who will implement the support we provide? / DFID will fund a programme to improve the responsiveness of the healthcare market to the health care needs of poor men, women and children in Sub-Saharan Africa, starting with a focus on Kenya, Nigeria and Ghana. On the supply-side, the programme will increase the number of franchised health service providers (largely clinics) offering a range of high quality health services covering reproductive, maternal and neo-natal health, as well as malaria, acute respiratory infection, and TB/HIV. It will also stimulate and support demand with financing for poor people to pay for services. This will be supported by efforts at national policy reform as well as information and communications (ICT) technology to recruit, train, support and monitor health providers. / This work will be implemented by the African Health Markets for Equity partnership, led by Marie Stopes International (MSI), and comprising six of the leading organisations in their fields – MSI, Population Services International (PSI), Society for Family Health (SFH), Grameen Foundation (GF), PharmAccess International (PharmAccess) and the World Bank/International Finance Corporation Health in Africa Initiative (HIA).

What are the expected results?
What will change as a result of our support? / There will be improved health, measured in disability adjusted life years (DALYs) averted, and fewer / deaths amongst mothers giving birth (maternal deaths) and children under 5 years old, for poor people (in the bottom two income quintiles) in Nigeria, Kenya and Ghana. This impact will be achieved through increased provision and uptake of good quality essential health services by the poor. Health markets will better serve the poor, who will have increased access to improved quality, affordable health care. / What are the planned Outputs attributable to UK support? / Results attributable to UK support will include: / 208,920 DALYs averted in the programme period; / £37 GBP ($58 USD) average cost per DALY averted (US$1: £0.63); / New evidence about the additional benefits and costs of supporting demand- and supply-side interventions simultaneously. / The AHME programme as a whole, including support from BMGF and other sources, is estimated to lead to: / Over 1.7 million additional DALYs averted over 5 years / Over 12,000 additional maternal deaths and over 31,000 additional under five deaths averted / These results will be achieved by: / Expanding the scale of private sector service delivery working with 2,734 private providers in Nigeria, Kenya and Ghana / Expanding the scope of services offered by private providers to cover high burden conditions and high impact services focusing on poor women and children / Increasing access to and use of services by providing appropriate financing for poor clients / Efficiency and cost improvements to service provision over time / Supporting locally led changes to regulations and/or policies to strengthen health market systems. / How will we determine whether the expected results have been achieved? / The BMGF and DFID will support a concurrent independent impact evaluation of the programme, which will quantify benefits from the programme based on a set of key outcome and impact indicators and will also provide qualitative evidence on broader health systems implications of the programme. Additionally there will be mid-term and annual reviews and the AHME partnership will use their own monitoring systems to report to DFID and BMGF against the results framework on an annual basis.

Strategic Case

Context and need for a DFID intervention / DFID’s Business Plan 2011-2015 commits us to lead international action to improve maternal health and access to family planning. The UK Framework for Results for Improving Reproductive, Maternal and Newborn Health (RMNH) commits DFID to remove barriers that prevent access to good quality services, particularly for the poorest and most at risk. It also commits DFID to “expand the supply of quality services, delivering cost effective interventions for family planning, safe abortion, antenatal care, safe delivery and emergency obstetric care, postnatal and new-born care - through stronger health systems with public and private providers.” Further, the UK Framework for Results for Malaria commits DFID to “support approaches to ensure all men, women and children are able to access responsive malaria and related health services irrespective of where they live or their ability to pay.” / Life expectancy is lower in SSA than any other region of the world.[1] While the region accounts for 11% of the world’s population, it contains 24% of the global disease burden and commands less than 1% of global health expenditure.[2] Contributing to a high disease burden are high levels of infectious diseases, such as malaria, TB and HIV. The SSA region also has the highest maternal mortality ratio in the world, estimated at an average of 640 per 100,000.[3] SSA countries have made uneven progress on the health-related MDGs. In some instances, health indicators have actually worsened over the past decade. / Health systems across Africa are in urgent need of improvement. DFID already provides significant support to the systems that provide health services through the public sector in many countries. But the reality is that the public sector alone cannot shoulder the burden or directly provide the needed services. Private providers already play a significant role in the health sector in Africa (See Figure 1). Rich and poor alike seek care from private providers, though the poor have much lower access to formal providersthan do the better off. Initial analyses (Annexes 3a, b and c) of the health market systems in Ghana, Kenya and Nigeria show there are many constraints to the markets serving the needs of the poor. These include lack of regulation, lack of investment capital, low consumer knowledge and impoverishing health costs, among others. / The problems of inefficient health markets in SSA have numerous consequences relevant to DFID priorities in the region. First, the inadequacy of existing health markets hinders progress on the health-related MDGs. As a result, the poor health of populations, as evidenced by inadequate health MDG progress against set targets, stymies economic and political progress. Additionally, weak governance of health markets, including private markets, contributes to increasing the difficulty in strengthening health systems to respond effectively to the health needs of populations, especially when facing natural and other disasters requiring a coordinated response. Weak governance in health funding means current systems lack accountability and transparency and are thus vulnerable to low quality service, fraud and abuse. Finally, weak health markets disproportionately affect women and girls who rely on health care providers for reproductive and maternal health care. / A number of current, often fragmented efforts exist to address the systemic barriers to non-state health care provision and utilisation by the poor. To address poor service delivery, social franchising has applied the principles of commercial franchising to promote social benefits rather than financial profit. By organising small independent providers into larger chains, social franchises can yield returns to scale in investment in physical capital, supply chains, advertising, and worker training and supervision. Additionally, social franchises can offer the ability to: faster scale up programmes, decrease transaction costs, provide standardised services to a broad market, collectively negotiate financial reimbursement mechanisms, and replicate best practice services among a large group. Franchisees can also cross-subsidise less profitable services with the more profitable ones supported by the franchisor. The use of brand advertising makes social franchising compatible with social marketing efforts to build awareness of products, and community health workers often provide critical links to low-income consumers. / Figure 1: Source of Healthcare by Asset Quintile, SSA (Montagu and Visconti 2010) / To be able to pay for private health services, the poor need financial help. Subsidised health insurance schemes and vouchers that can be redeemed in exchange for services are two examples of demand side financing (DSF) that make privately provided services more affordable for poor people and so give them the choice and the financial ability to buy services. An essential part of DSF strategies is targeting the intervention to those most in need of services, typically poor women and children. Additionally, social media campaigns and other communications strategies work to raise awareness of the importance of specific health care interventions, such as immunisation and skilled birth attendance, and can thus raise the demand for these services. / Effective policy engagement also strengthens health markets. This involves those engaged in health care regulation, such as Ministries of Health and health professional organisations, to establish and implement regulatory frameworks, policies, and standards. It can also involve working with the private sector to align market incentives to ensure high quality and equitable health care. / Most countries in SSA have a clear need for health market improvement, but initial DFID support should be trialled in a few countries. Country selection criteria could include: / Number and size of existing private healthcare providers and existing demand side financing, e.g. insurance or voucher schemes, so these can be leveraged by the programme to increase value for money and impact; / Need in terms of health problems and high level of spending by the poor on healthcare; and / The political, policy, legal and regulatory environment, and existing examples of government and private sector partnership in healthcare.
Intended impacts in selected countries would be improved health, measured in contribution to disability adjusted life years (DALYs) averted, for poor people (in the bottom two income quintiles). This impact would be achieved through increased provision and affordability of good quality health services and increased utilisation of these services by the poor. There would be increased better quality essential services provided through organised private provider networks; consumers would be more able and willing to pay for services; and governments would more effectively regulate, supervise, support and engage the private sector. This would support the theory that the greater the interaction and synergy between supply-side support, demand-side support and support to regulatory functions, the greater will be their individual and aggregate impact. / Three groups of interest to DFID would benefit: / Low-income health care consumers in the bottom two economic quintiles whose use of health services would increase relative to prior unmet need, and whose out of pocket (OOP) expenditures would reduce. / Private health care providers, who will become more financially stable and viable due to improvements and transparency in quality, increase in client flow, increased access to credit, and better regulation of the health care market. / Health care regulators, such as Ministries of Health, who will manage improvements in regulation and capacity to respond to the health needs of the population. / Partnership with the Bill and Melinda Gates Foundation (BMGF) / 11. BMGF has provisionally allocated $33.5 million to the proposed African Health Markets for Equity project. The BMGF focus is on strengthening social franchising. DFID believes supply side interventions (social franchising) need to be supported by demand side financing to help the poor access health services. If DFID partners with BMGF, demand-side financing would need to be included in an intervention. There is strong agreement between DFID and BMGF on all other elements of potential support, and close joint working on project and evaluation design. DFID will allocate $33.5 million to match the BMGF funding. AHME is one of the projects funded by DFID and Gates through the HANSHEP group.
[1] Unicef, available from: http://www.unicef.org/sowc06/pdfs/regional_stat_sum_s21_ssa.pdf, and World Health Statistics, World Health Organisation 2008
[2] International Finance Corporation, The Business of Health in Africa: partnering with the private sector to improve people’s lives, IFC/World Bank Group 2011
[3] World Health Organisation, Trends in maternal mortality: 1990 to 2008, WHO 2010

2. Appraisal Case

What are the feasible options that address the need set out in the Strategic case? / The options to strengthen private health markets are detailed in Table 2 below: / Option Description / 1. Supply and demand side interventions to strengthen healthcare markets DFID provides $30m to African Health Markets for Equity programme in 3 countries, alongside an additional $30 million from BMGF. The programme supports supply, demand and support function work streams (i.e. workstreams 1-6). An additional $3.5m each is committed by DFID and BMGF for programme evaluation. / 2. Supply side only– support for private provider networks (social franchising) DFID provides $30m investment in supply side interventions only through DFID’s reproductive health framework agreement in 3 countries, alongside an additional $30m from BMGF. Complementary demand side interventions are not supported by DFID or BMGF (i.e. this option includes workstreams 1-3, and relevant elements of support functions in workstreams 5 and 6.) An additional $3.5m each is committed by DFID and BMGF for programme evaluation / 3. Do nothing No additional DFID investment in supply and demand side interventions in the three countries. BMGF invests $33.5m. This is the counterfactual. / Both feasible options involve pre-selected implementing partners. These partners were selected by BMGF in May 2011 after months of research and discussions with organisations operating in this field. / The pre-selection followed the following logic: / To strengthen African health markets, a range of competencies is required including experience working in the health sector on i.e. provider networking, quality improvement, provider finance, DSF, policy and regulation, and ICT; / A programme would appropriately be implemented by Africa-based mission-driven organisations that had demonstrated a commitment to these issues before the grant and could be expected to continue to pursue them after the grant, and that had a track record of attracting funding (for leverage and sustainability); and / Cost effectiveness and value for money: (a) Organisations already well-established in Africa would have lower staff and travel costs (and thus offer better value for money) than organisations operating primarily from Europe or the US. (b) A key determinant of cost-effectiveness is scale, for which it is essential to hit the ground running, so organisations with existing similar activities in country were selected. (c) Replication and adaptation of the AHME approaches are key to the ultimate value proposition, so we needed organizations that have similar activities in other countries to which these approaches could spread. No other potential implementing organisations met these criteria. / Once a strong consortium had been assembled, DFID and BMGF worked with the partners to design a programme that brings the greatest impact for the lowest cost. This has involved a reduction in the budget from an initial $80m to $60m, and significant increases in the targets for impact. The latest revision of the proposal represents a 9% increase in impact (in terms of number of DALYs averted) alone. / PSI and MSI are the umbrella organisations for most of the emerging franchise networks, operating 19 of the 28 social franchise networks for health in Africa in 2010. BMGF decided these organisations were sufficiently decentralised to meet the “Africa-based” criterion, having spent several months looking for wholly African organisations with these competencies without success. BMGF’s only preferred country was Nigeria (due to burden of disease and strength of private markets), hence SFH. BMGF had already been funding IFC under the Health in Africa programme and was confident IFC had unique capabilities for policymaker engagement and finance. Grameen Foundation was selected based on a review of their concept by mhealth specialists in BMGF and their excellent track record, including their work in Ghana for BMGF. For the demand-side financing, BMGF found no Africa-based organisations with a comparable track record to PharmAccess, and selected PharmAccess because they had initiated innovative work with considerable support from the Dutch government and had already begun to establish links with MSI and PSI. / In June 2011, BMGF called together these organisations for discussions in Nairobi and it was agreed that such a partnership should be trialled. The partners came together to progress programme design with BMGF and agreed broad operating principles, and DFID was later invited to join. Joining this programme, rather than going out to tender for implementing partners, will promote donor and implementer alignment. Shared oversight of the work between two donors is likely to improve quality and cost-effectiveness (to each individual donor) of oversight as BMGF and DFID will draw on a pool of internal experts (e.g. health, PSD, legal, procurement, evaluation), rather than each donor having to mobilise these experts for separate and possibly parallel programmes. BMGF is a significant player in this field and will bring expertise and alliances from other programmes which can be applied to this intervention. / The capacities and experience of each member of the partnership is described below. / Marie Stopes International (MSI): MSI will serve as the lead for the AHME partnership and will focus on service delivery through private provider networks. MSI is a global non-profit, non-governmental organisation providing high-quality voluntary family planning, comprehensive abortion care, maternal and child health, and HIV/AIDS services to millions of low income and underserved people across the globe each year. Since 2004, MSI has complemented its centres and outreach team with its Blue Star social franchises. These comprise more than 1,500 clinical health care providers in eleven countries across Africa and Asia. In several countries including: Ethiopia, Kenya, Malawi, Madagascar, Ghana, Sierra Leone, South Africa, and Mali. Internationally, MSI has successfully integrated DSF, such as vouchers and insurance, into its service delivery models. / Population Services International (PSI): Through its social marketing and social franchising programmes in over 60 countries, PSI raises awareness about, generates informed demand for, and distributes affordable, accessible, and attractive health products and services. PSI has more than 13 years of experience implementing social franchise programmes. With more than 16,000 franchise sites in 22 countries in Africa (including Kenya), Asia, and Latin America, PSI has developed several models to deliver high quality services in HIV counselling and testing, male circumcision, STI diagnosis and treatment, TB diagnosis and treatment, FP, maternal and child health, and post abortion care. PSI often incorporates performance based funding, such as voucher schemes, into its social franchise programmes to improve quality, equity and cost-effectiveness. / Society for Family Health (SFH): SFH is a public health non-governmental organisation in Nigeria. SFH health programmes in HIV, FP, malaria, and diarrhoeal disease are implemented in more than 200 communities in 33 states throughout the country. Through social franchising, SFH currently works with 276 private sector health facilities in 23 States of Nigeria to provide long term family planning methods as well as Post Partum Haemorrhage and Post Abortion Care. Through social marketing, SFH has trained over 37,000 proprietary patent medicine vendors (PPMV drug stores) and 2,000 pharmacies on family planning through USAID funding. Through support from the Global Fund for AIDS, Tuberculosis, and Malaria (GFATM), SFH supports over 2,000 clinics and 10,000 PPMVs and Pharmacies on the management and treatment of malaria. / PharmAccess International (PharmAccess): PharmAccess will manage quality improvement of the franchisees, as well as the Medical Credit Fund (MCF) to provide affordable loans and clinical and business technical assistance to clinics. The MCF was started in 2010 and is the first fund ever in Africa to address the financing needs of the lower-tier healthcare providers. PharmAccess has contracted three implementing TA partners and three banks for its operations in Tanzania, Kenya and Ghana respectively, and has nearly completed agreements with partners in Nigeria. PharmAccess also hosts the SafeCare Initiative, using International Society for Quality in Health Care (ISQua) approved quality standards, to support step-wise quality improvement and recognition of healthcare providers in resource-restricted settings. The SafeCare Initiative combines the knowledge, expertise and experience of three organisations: PharmAccess, Council for Health Service Accreditation of Southern Africa (COHSASA), and Joint Commission International (JCI). SafeCare also works with national governments to help develop national certification and accreditation programmes based on the SafeCare standards and methodology. / Grameen Foundation (GF): GF helps the world’s poorest, especially women, improve their lives and pull themselves out of poverty through financial services, critical information, and income-generating activities designed for the poor. More and more, these services are being delivered through mobile phones, enabling GF and partners to reach poorer and poorer people who have been unreached by traditional services. / International Finance Corporation/World Bank Health in Africa Initiative (HIA): HIA was established by the World Bank Group in partnership with the BMGF in 2009. The mission of HIA is to catalyse sustained improvements among the poor and underserved in Africa through two mechanisms: 1) increasing access to quality health-related goods and services and; 2) providing financial protection against the impoverishing effects of illness. HIA is working towards the improved access to quality health services delivered by the private sector through the following technical assistance and advisory activities. / Workstreams involved in feasible options are detailed below. / Workstream 1: Improving supply through Private Provider Networks (PPN) / The delivery of essential health services would be done through private providers including larger health facilities, clinics, pharmacies and drug shops. It would build on established country and global level networks, and systems. The scope of services offered by private health providers, as well as the number of delivery outlets would be increased. Network providers would be trained and supported on critical aspects of MNCH focusing on attended delivery, antenatal and post natal care, as well as service packages for children, adolescence and adults. This would include effective HIV/AIDS, TB and sexually transmitted diseases (STD) prevention and management. When integrated effectively, greater health impact is achieved and target audiences are reached more cost-effectively than through a single health area. Community health workers, as part of community outreach, would be trained to provide complementary information on supported interventions as well as referral for case management. Health franchise networks in each country would also use local mass media to generate demand. / The provider networks would be managed as delivery channels integral to a larger health system, with referral pathways into and out of provider networks being developed in order to better serve clients. This will also be supported by the inclusion of different levels of providers within PPNs as well as through the establishment of referral linkages with the public sector. To achieve sustainable market change, the partnership will work towards a mixed model of funding (user fees and government financing) for future phases of work, and encourage competition among providers. There would be a strong focus on affordability of services to the poorest two quintiles of society, and this would also be a focus of Workstreams 2 (Quality improvement and certification) and 4 (Demand side financing). / Workstream 2: Quality Improvement and Certification / The goal of the provider networks is to improve the quality of the franchised services delivered by the providers. To ensure the quality of the services, the provider networks would put in place quality assurance systems that: 1) ensure that the needs of the client are met; 2) ensure the ability of the provider to meet the needs of the client; 3) ensure that the provider delivers services at a set standard of quality; 4) ensure continuous improvement in quality; and 5) ensure affordability to the poorest two quintiles. These quality standards would be put in place by setting clinical and business standards as documented in the operations manual, competency based training, making appropriate equipment available, ensuring commodity security, and providing regular supportive supervision. Internal quality audits, client exit interviews and mystery clients are all conducted on a regular basis in all provider networks to measure the quality and affordability of service delivery. The branding of the provider network– Happy Mothers Network, BlueStar Ghana, Tunza, Amua – is used as a signal to clients that improved quality services are available at the branded provider. Demand generation activities by the provider networks reinforce this message. The quality assurance systems put in place by the provider networks would be complemented by the SafeCare Initiative. Providers in the network accessing credit through the Medical Credit Fund would participate in SafeCare’s stepwise certification, to track, acknowledge and certify incremental quality improvements up to the level required for formal international accreditation. / Workstream 3: Provider Credit / The Medical Credit Fund (MCF) would provide performance-based loans in combination with technical support to eligible private primary healthcare providers. The MCF TA programme focuses on two areas: quality improvement and technical support on business planning. The quality improvement part is designed along the lines of the standards and systems developed by the SafeCare Initiative. These standards enable healthcare facilities to measure and improve the quality, safety and efficiency of their services. The incremental approach of the loan is linked to quality improvement: at first a small loan is disbursed and repaid, and a follow-up loan is conditional on the achievement of quality performance indicators that have been formulated in a quality upgrade plan. This approach precludes providers using the loan for purposes other than improving the quality of health service delivery. / The MCF partners with local banks to provide loans, based on a risk sharing agreement that shifts the majority of the risk from the MCF to the local bank over time. The loans are offered at affordable terms and conditions. Lending through microfinance organisations, in addition to the MCF’s current banking partners, would also be explored, and appropriate arrangements with these partners made. In addition, a loan package for pharmacies will be developed, concurrent with the development within the AHME partnership of a specific quality assessment tool and quality control mechanisms. Over the lifetime of the project, the amount of risk taken on by local banks and microfinance organisations will increase as the project’s own loan funds are phased out to promote a self-sustaining loan market. / Technical support on business planning would be provided by the organisation providing the credit and the demand side-financing outlined below (PharmAcess). This would strengthen the healthcare providers’ financial management capabilities and help prepare the business case for the bank. Technical assistance would be implemented by MSI, PSI and SFH private provider networks. They would be responsible for selecting, training, monitoring, and evaluating providers in the MCF programme. The MCF would build technical capacity for this within the networks by providing training, tools and support. / Workstream 4: Demand-Side Financing (DSF) / DSF mechanisms seek to manage and reduce the consumer costs of accessing health services, so making good quality services more affordable for poor people. The healthcare financing environment in each of the 3 countries is different, and demand side financing would need to be tailed to the particular environment. Detailed analysis of country specific health DSF options and design of interventions, including using DFID’s Making Markets work for the Poor (M4P) framework, will be carried out during the first year of project implementation. This will inform the type of demand-side financing to be used in the specific context. / AHME partners recognise that for sustainability, it will be essential to coordinate the AHME DSF approaches with on-going public sector efforts in this area, in particular national health insurance schemes that are in different stages of development in Ghana, Kenya and Nigeria. As such DSF mechanisms to be considered would be: social and community-based health insurance, medical savings accounts, conditional cash transfers and vouchers for healthcare services. Hybrid models that include a blend of mechanisms would be considered as well (e.g. vouchers covering uninsurable risks or specific health conditions in national insurance schemes). The impact on DALYs averted and therefore the effect of different models on specific disease areas would be carefully taken into consideration. As significant in-country work is required prior to designing DSF, this workstream will become operational in year 2 of the project. / Workstream 5: Policy and Regulation / Policy and regulation work would focus on ensuring that provider networks and DSF interventions would be aligned with national priorities and fully integrated into national service delivery, health financing and disease prevention strategies. IFC Health in Africa will expand its policy and regulatory advisory work in Ghana, Kenya and Nigeria. The aim of the policy and regulation work would be to improve engagement between government and provider networks regarding national health priorities to address the constraints to better private sector contributions, including private sector delivery, procurement and commercial issues. Areas of focus would include building dialogue between governments and the private sector (including smaller providers, supply chain and larger market players) regarding regulation, health financing, delivery, procurement and commercial issues, information channels such as health management information systems, registration of private providers, and to ensure public planning takes account of private providers. Chambers of commerce and other representative bodies of the private sector (e.g. pharmaceuticals) will be consulted and involved where appropriate. / Workstream 6: Information and Communication Technology (ICT) / ICT can support the linkage between interventions, while also helping provider networks to more effectively reach and engage poor populations with critical information. Technologies can collect data that can improve quality of service, efficiency of operations, and ability to respond to needs in real-time. A challenge would be to identify which ICT interventions would have the greatest impact and how to allocate partnership resources toward those highest return-on-investment ICT solutions. Work in the 3 countries would begin with user-centred needs assessments (to determine a strategy and a roadmap for ICT investment). This draws on the process used to design the Grameen Foundation’s BMGF- funded Mobile Technology for Community Health (MOTECH) project in Ghana, and the early lessons learned from the programme[4]. / After completing the needs assessment, GF would guide the AHME partnership members in identifying opportunities where ICT solutions can accelerate the DALY-averting work of the AHME partnership. These might include ICT solutions for: / Provider Behaviour Change – Providers would need to master treatment of a number of new diseases as part of the intervention. ICT solutions can deliver information on those diseases (e.g., symptoms, treatment) as well as tips on how to better run the provider’s business. / Client Health Education – Mobile phone-based tools can deliver health tips on the targeted diseases, reminders to continue a course of care or visit a clinic, and provider referrals delivered by voice or SMS. / Data Collection and Analysis – The partnership would need to collect data directly from providers and other partners to use to monitor and evaluate the partnership’s impact as well as build the case for the potential of the overall intervention. / Commodity and Drug Supply Chains – PPNs move commodities and drugs to their providers on a regular basis but lack an automated system to track these movements, and to ensure quality control of medicines and medical devices. ICT solutions exist that could meet these needs. / Demand-Side Financing – The mature mobile money transfer system (MPesa) in Kenya and nascent mobile money networks in Nigeria and Ghana offer the potential to integrate mobile money transfers into DSF programmes, particularly around the pre-payment of health expenses. / Accountability – such as using mobile phones to allow providers to report on the quality of healthcare received. / Following decisions by the AHME Steering Committee, GF would first develop and pilot the selected ICT solutions in Ghana, as GF’s presence there is strongest with a strong base of programme staff, software developers and partner relationships. Successful solutions could then be rolled out to Kenya and Nigeria, with appropriate testing and modifications.
Assessing the strength of the evidence base for each feasible option / Social franchising interventions are common to both options 1 and 2. The literature on social franchising is generally encouraging[5] and early results suggest that social franchising could “rapidly expand health coverage to the poor, capture economies of scale and reduce the information asymmetries that often adversely affect quality of care”[6] . Systematic reviews of the evidence on social franchising have found that there have not yet been enough rigorous evaluations to allow strong conclusions to be drawn. A 2009 Cochrane review5 did not find any rigorous evidence to demonstrate the effect of social franchising on access to and quality of care in low- and middle-income countries” and concluded that “Governments, non-government organizations and international donor organizations should implement social franchises for LMICs with integral evaluations in order to learn whether and how they affect access to and quality of health services”. Similarly, a 2011 systematic review[7] found that “no rigorous evidence existed as to the effect of social franchising on access to and quality of health services in low- and middle-income countries” and recommended more rigorous evaluations. The evidence for option 2 and for the supply-side component of option 1 must therefore be classed as limited. The evaluation components of these options would, however, make an important contribution to increasing the evidence base for future interventions, as recommended by the systematic reviews. Both the results and the unintended consequences of the social franchising element would be measured. / The most significant difference between options 1 and 2 is the addition of the demand-side financing element in option 1 to increase affordable access to franchised and other services by poor people. It is not yet clear what form the demand-side intervention in each country would take; this would be determined during a one-year inception phase. But the most likely candidates are vouchers and the expansion of national health insurance schemes to cover networked providers. Demand-side financing would increase patient choice, allowing patients to access whichever services they prefer, within or outside the franchised networks. / There is a growing evidence base for demand-side financing interventions. Voucher schemes are increasingly being used to raise use of specific services provided in the private sector. Systematic reviews of voucher schemes have concluded that so far there is robust evidence that vouchers increase service utilisation and modest evidence that they improve service quality and can be effectively targeted to specific populations such as the poor or women. Bellows[8] et al. reviewed fifteen evaluation studies of seven sexual and reproductive health voucher programmes in Asia, Africa, and Latin America, finding promising quantitative evidence that the programmes increase women’s use of reproductive health services and improve quality of care and population health outcomes. Although the studies were primarily “cross-sectional or before-and-after without controls and thus not considered particularly strong study designs,” the authors contend that the “potential for reproductive health voucher [programmes] appears positive.” Similarly, Meyer et al[9] reviewed 24 studies evaluating 16 different health voucher programmes (mainly covering insecticide-treated bed nets or reproductive health services) and concluded that “The evidence indicates that health voucher programmes have been successful in increasing utilisation of health goods/services, targeting specific populations, and improving the quality of services.” / The evidence on the scope to increase utilisation of essential health services by the poor by incorporating networked private providers into national health insurance schemes is currently much more limited. Countries such as Rwanda and Ghana have recently expanded health insurance schemes to include the poor, using subsidies financed through tax revenues and donor funding. These schemes cover care provided by non-state providers. There is some evidence that they have increased utilisation of services[10] [11], but it is not clear what contribution including private providers has made to access by the poor. / There is also only limited evidence that combining demand-side and supply-side interventions offers better results (in terms of quality, utilisation and equity) and value for money than doing either in isolation. One of the objectives of this programme is to help answer this question and so contribute to building a stronger evidence base. But some of the evidence from other programmes points in this direction. A recent review of performance-based incentives for maternal health[12] points out that “Improving the supply of services, though important, is rarely enough to make a significant impact on maternal health. Demand for and access to services can remain constrained by the high cost of accessing services; imperfect knowledge of the long-term benefits of investing in antenatal care, facility births, and family planning; lack of prioritisation of such things in families; and social exclusion.” An impact evaluation of the performance based funding scheme for health centres in Rwanda[13] suggested that utilisation of some services (particularly preventive services such as antenatal care) may be more responsive to demand side than supply-side incentives. And in a case-study evaluation of the Bangladeshi government Maternal Health Voucher Scheme[14], Ahmed and Khan concluded that although the vouchers did increase purchasing power among poorer women and expanded utilisation, districts must ensure the health system is ready to meet increased demand. This suggests that related supply-side improvements are required to maximise the impact of demand-side financing interventions, which is consistent with studies of other demand-side interventions such as conditional cash transfers[15]. / In Table 3 below the quality of evidence for each option is rated as either Strong, Medium or Limited / Table 3: Strength of evidence rating / Option Evidence rating / 1 Medium/ Limited / 2 Limited / Do nothing Medium/ Limited / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Table 4: Ratings for climate change and environment / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C C / 2 C C / Do nothing C C
[4] Foundation and Motech, Mobile Technology for Community Health in Ghana: What it is and What Grameen Foundation Has Learned So Far, available from: http://www.grameenfoundation.org/sites/default/files/MOTECH-Early-Lessons-Learned-March-2011-FINAL.pdf
[5] Koehlmoos TP, Gazi R, Hossain SS, Zaman K. The effect of social franchising on access to and quality of health services in low- and middle-income countries. Cochrane Database of Systematic Reviews 2009, Issue 1. Art. No.: CD007136. DOI:10.1002/14651858.CD007136.pub2
[6] Ruster J. Franchising in health: emerging models, experiences, and challenges in primary care. Public Policy for the Private Sector Note No. 263. The World Bank Group Private Sector and Infrastructure Network, 2003.
[7] Koehlmoos T, Gazi R, Hossain S, Rashid M (2011) Social franchising evaluations: a scoping review. London: EPPI-Centre, Social Science Research Unit, Institute of Education, University of London.
[8] Bellows et al., Tropical Medicine and International Health 2011: The Use of Vouchers for Reproductive Health Services in Developing Countries: A Systematic Review
[9] Meyer C, Bellows N, Campbell M, Potts M (2011) The Impact of Vouchers on the Use and Quality of Health Goods and Services in Developing Countries: A systematic review. London: EPPI-Centre, Social Science Research Unit, Institute of Education, University of London
[10] Saksena P, et al. Mutual health insurance in Rwanda: Evidence on access to care and financial risk protection. Health Policy (2010), doi:10.1016/j.healthpol.2010.09.009
[11] Something old or something new? Social health insurance in Ghana, Sophie Witter and Bertha Garshong, BMC International Health and Human Rights 2009, 9:20 doi:10.1186/1472-698X-9-20
[12] Morgan, Lindsay, Alix Beith, and Rena Eichler. November 2011. Performance-Based Incentives for Maternal Health: Taking Stock of Current Programmes and Future Potentials Bethesda, MD: Health Systems 20/20 project, Abt Associates Inc.
[13] Basinga, Paulin, Paul J. Gertler, Agnes Binagwaho, Agnes L.B. Soucat, Jennifer Sturdy, and Cristel M.J. Vermeersch. 2011. “Effect on maternal and child health services in Rwanda of payment to primary health-care providers for performance: an impact evaluation.” The Lancet 377: 1421–28.
[14] Ahmed and Khan, Health Policy and Planning, 2011: A Maternal Health Voucher Scheme: What Have We Learned From the Demand-Side Financing Scheme in Bangladesh?
[15] Lagarde M, Haines A, Palmer N. The impact of conditional cash transfers on health outcomes and use of health services in low and middle income countries. Cochrane Database of Systematic Reviews 2009, Issue 4. Art. No.: CD008137. DOI:10.1002/14651858.CD008137

What are the costs and benefits of each feasible option? / Option 1 / The total donor contribution for option 1 will be $60.2m (£37.8m) over 5 years. This does not include the cost of the evaluation, which has a fixed cost and does not affect the value for money analysis. Each donor will bear 50% of the costs, so the total investment (minus the evaluation) by DFID is £18.9m. The breakdown of donor costs by activity and provider is shown in the table below: / Table 5: Costs of Option 1 (US$) / Agent Activity Budget $m $m DFID share / % of total DFID / MSI (and Partners) Overall management unit 5 2.5 9% / Grameen ICT 2.3 1.15 4% / IFC Policy and regulation 3.2 1.6 5% / MSI, PSI, SFH Scale up and increase in scope of health provider network 23.1 11.55 39% / PharmAccess Accreditation (quality improvements) 4.1 2.05 7% / Provider credit (quality improvements) 4.9 2.45 8% / PharmAccess Demand side financing 17.3 8.65 29% / TOTAL 60 30 100%

NB. BMGF and DFID will each allocate an additional $3.5m for independent evaluation.

Benefits of Option 1 / Each of the workstreams described above for option 1 can be expected to have benefits, but only some of these can be quantified. Where possible, benefits measured in disability-adjusted life years (DALYs) averted have been estimated. / Social Franchising / The direct benefits of AHME social franchising activities are expected to include a reduction in the burden of preventable, neonatal, maternal and child deaths and reductions in the burden of ill-health from respiratory diseases, nutritional deficiencies, HIV/AIDS, TB and pneumonia. These outcomes are likely to be achieved due to the greater scale and scope of service provision at higher quality levels due to the value added by the social franchising quality control and branding. / 5 shows the total expected impacts of the social franchising component (based on total service provision costs rather than just the donor subsidy) in terms of numbers of DALYs averted by health area. These estimates are based on modelling work by PSI[16]. / Figure 5: Impact of the programme in DALYs averted by Health Area / The additional DALYs averted as a result of the additional donor investment will be lower than those shown here. Since the donor contribution will account on average for 34% of the total service costs of social franchising, 34% of the total expected DALYs averted are attributed to this funding. Of these, only 80% are taken to be due to new and additional users and so included as additional benefits. But to take account of the fact that existing service users can also be expected to benefit from the improved quality of service provision, an increase of 30% in their DALYs is included. / It has not been possible to quantify the benefits of the other elements of the programme. The following benefits are expected to be produced but are not included in the model, meaning that the DALYs for option 1 (and in some cases also for options 2 and 3) are underestimated: / Impacts of demand side financing / Impacts of the Safecare quality assurance scheme and provider credit on the additional DALYs generated / Direct and indirect benefits of the policy and regulatory work. / Synergies associated with combining demand and supply side activities / Potential replication and leverage benefits within other countries and the global health community; / Healthcare cost savings accruing to households, donors and public sector; / Household income effects from demand side financing – investment gains and knock on effects resulting from demand side vouchers and subsidies. / In the case of demand side financing, it is not possible to quantify the benefits because it is not yet clear which mechanism or combination of mechanisms will be funded in each country. However, the types of benefits that DSF might be expected to generate include: / Reduction in impoverishment due to catastrophic expenditure by the poor on healthcare; / Increased uptake of services by poor people; / Increased ability of patients to hold providers to account; / Increased ability of patients to choose, thus driving competition and its benefits; and consequently / Improved health outcomes for the poor. / In the case of the other supply-side interventions, there is not yet enough empirical evidence on which to base estimates of the size of the benefits (see evidence section above). The evaluation of this programme will contribute to increasing the evidence base for future investment decisions. / Distribution of benefits / The benefits are likely to accrue primarily to rural low-income health care consumers due to the intended geographic targeting of the activities and the targeting of DSF. The immediate beneficiaries of the donor subsidy will also include private health care providers who have been operating in fragmented and unregulated. / Health care regulators and those responsible for health service delivery, such as Ministries of Health, will also benefit from the AHME partnership through the development of better regulation and capacity to respond to the health needs of the population. The policy and regulatory technical assistance will give rise to be wider benefits to society from a better health policy environment, leading to stronger supply chains and health market mechanisms. This will in turn allow other provider networks and provision to improve, thus creating spill over and indirect benefits to more vulnerable people. The impact of policy technical assistance on the private sector supply chains is likely to have a greater sustainability effect, compared to the social franchising activities and demand side activities. The impacts of policy changes should, in theory last much longer than the duration of the programme. / Balance of costs and social franchising benefits for Option 1 / Given that, as described above, it is not possible to quantify the full benefits of option 1, it is not possible to carry out a full comparison of costs and benefits. Error! Reference source not found.9 below summarises the results of a partial cost-effectiveness analysis, in which only the benefits from social franchising are quantified. The results are based on DALYs that are directly attributable to AHME funding[17]. / Table 9: Partial cost-effectiveness analysis of Option 1 / Budget and Impacts / Discounted budget (3% social discount rate) $56.7m / Discounted social franchising budget (including PMU) $26.2m / Impact: Number of DALYS attributable to Gates and DFID funding 417,840 / Cost effectiveness / Discounted cost per DALY from social franchising, based on total budget $136 / Discounted cost per DALY from social franchising, based on social franchising budget + PMU $63 / Un-quantified benefits / DALYs, equity gains and household income effects from DSF / DALYs from Safecare quality assurance and provider credit / Efficiency gains from ICT / Externalities and efficiency improvements from policy and regulatory impacts / Household level healthcare cost savings and illness prevented / Synergies from combining demand and supply side activities / As can be seen from Table 9 the cost per DALY ranges from $63 to $136 (£40 to £86), depending on which elements of costs are included. The lower figure includes only the costs that can be attributed to social franchising activities, while the higher figure spreads the whole budget over the DALYs averted through social franchising. The higher figure can be seen as corresponding to a worst- case scenario in which demand side financing, ICT, Policy and regulation and quality assurance and credit access have zero benefits. / To benchmark these figures, the WHO guidance indicates that interventions are highly cost effective if a DALY can be averted for less than the GNI per capita (Atlas method) of the country in question. The lowest GNI per capita figure for the three countries is $790 (Kenya).[18] Thus by this standard Option 1 is deemed a highly cost effective way of reducing morbidity and mortality (and would remain so even if the DALY estimates, which are based on assumptions about the growth of services delivery, turned out to be over-optimistic). / These overall cost per DALY figures mask considerable variation by country. PSI estimates suggest that the cost per DALY based on social franchising and PMU costs is highest in Ghana ($97), followed by Nigeria ($89) and Kenya ($21). For the most part, cost per DALY in a given country is influenced by 4 factors: the cost of doing business in country, the existing size of the franchise, the existing scope of services offered through the franchise, and the disease burden in country. The cost per DALY in Ghana is heavily influenced by the cost of doing business in Ghana, the relatively small size of the franchise (only 90 providers currently), and the limited existing scope of services included in franchise. Due to the low prevalence of HIV and TB, BlueStar Ghana will not franchise screening or treatment for these services, which boost DALY estimates in Nigeria and Kenya. The cost per DALY in Nigeria is influenced by MSI’s franchise, which is new and will be rural and so will not produce the same volume of DALYs as SFH’s franchise in the first few years. The cost per DALY in Kenya is the lowest as the MSI and PSI franchises are well established and well funded. To add the services under AHME will be slightly more cost effective. Franchisors expect that the cost per DALY decreases with the increased size and scope of the franchise. This reflects the increased efficiencies of the franchises to produce DALY. Nigeria projects a 300% decrease over the 5 years. Kenya projects a 200% decrease in cost per CYP, while Ghana projects a 78% decrease. / Option 2 / The difference between Option 1 and Option 2 is that under Option 2 the whole budget of $60m is invested in supply-side interventions. The costs of the management unit remain the same, but for the purposes of this appraisal it is assumed that the remaining costs are spread across supply-side activities in the same proportions as under Option 1. / Table 10: Costs of Option 2 (Supply side activities) / Agent Activity Budget $m DFID share $m % Of total / MSI (and Partners) Overall management unit 5.4 2.8 8 / Grameen ICT 3.6 1.8 6 / IFC Policy and regulation 4.6 2.3 8 / MSI, PSI, SFH Scale up and increase in scope of health provider network 33.8 16.9 56 / PharmAccess Accreditation (quality improvements) 5.9 2.95 10 / Provider credit (quality improvements) 7.1 3.55 12 / Total 60.2 30.2 100 / Option 2 still has benefits that cannot be quantified before the programme is implemented, but given that a larger proportion of the budget is allocated to social franchising, the unquantified benefits account for a smaller proportion of the total under option 2. The estimates presented here assume that increasing the availability of franchised services in rural areas proportionately increases the DALYs gained through those services; this may be an over-estimate if people living in those areas are unable to access the services due to financial or other constraints. / Table 11: Partial cost-effectiveness analysis of Option 2 / Budget and Impacts / Discounted budget (3% social discount rate) $56.7m / Discounted social franchising budget (including PMU) $36.8m / Impact: Number of DALYS attributable to Gates and DFID funding 610,816 / Cost effectiveness / Discounted cost per DALY from social franchising based on total budget $93 / Discounted cost per DALY from social franchising based on social franchising budget + PMU $60 / Unquantified benefits / DALYs from Safecare quality assurance and provider credit / Efficiency gains from ICT / Externalities and efficiency improvements from policy and regulatory impacts / Household level healthcare cost savings and illness prevented / In this case the cost per DALY ranges from $60 to $93 (£38 to £59), depending on which elements of costs are included. The lower figure (based on the social franchising budget + PMU costs) is of course very similar to that for option 1, since both options only quantify social franchising benefits. The figure based on the whole budget ($93 per DALY) is lower for option 2 than for option 1. The difference masks the unquantified benefits resulting from the 30% of budget in option 1 that is allocated to DSF. It also masks any equity benefits resulting from the DSF activities in option 1 and assumes that availability translates into accessibility as noted above. / DFID’s objective is to increase the use of good quality essential health services by poor people, but not all of the additional DALYs from SF will go to the poor. The objective of including the DSF component in option 1 is to make good quality services more affordable for poor people and so to increase the proportion of the total additional DALYs averted that benefit the poor. Option 2 would avert additional DALYs by investing more of the budget in SF, but it is expected that fewer of them would benefit poor people. Since DFID (at least implicitly) values DALYs averted for poor people more highly than those averted for richer people, it is possible that option 1 could generate greater benefits than option 2, even if the total number of DALYs averted were smaller. / Option 3: the counterfactual / This option refers to the baseline situation where DFID makes no additional investment. The Gates Foundation has indicated that they would go ahead with funding 50% of the AHME partnership ($30m) in the absence of DFID funding. They would not, however, fund the accreditation and access to credit activities. Thus the $30m is assumed to be spread pro rata on the other activities. The profile and distribution of benefits would be slightly different, as it is unclear whether all the benefits would be spread across the three countries in the same way. For ease of analysis it is assumed they are. The quantified benefits would be slightly less than 50% of Option 1 because the fixed cost of the PMU would be spread across less outputs, thus scale effects would not be realised. / Table 12: Costs of Option 3: Counterfactual / Agent Activity Budget $m % Of total / MSI (and Partners) Overall management unit 5.2 17 / Grameen ICT 1.2 4 / IFC Policy and regulation 1.7 6 / MSI, PSI, SFH Scale up and increase in scope of health provider network 12.5 42 / PharmAccess Demand Side Financing 9.4 31 / Total 30 100 / As the PMU costs are fixed costs, they now account for twice as large a proportion of the total budget compared to options 1 and 2. These fixed costs are spread across fewer units of output, raising the cost per DALY. / Table 13: Partial cost-effectiveness analysis of option 3 / Budget and Impacts / Discounted budget (3% social discount rate) $28m / Impact: Number of DALYS attributable to Gates funding 226,078 / Cost effectiveness / Discounted cost per SF DALY based on total budget $125 / Discounted cost per SF DALY based on social franchising budget + PMU $75 / Un-quantified benefits / DALYs, equity gains and household income effects from DSF / Efficiency gains from ICT / Externalities and efficiency improvements from policy and regulatory impacts / Household level healthcare cost savings / Synergies from combining demand and supply side activities (likely to be smaller at this scale) / 14 compares all the VFM metrics for all the options. It is not a straightforward comparison, because several elements of the intervention combinations give rise to unquantifiable benefits, and their magnitudes vary with the options. / Table 14: VFM comparison of options / 1 AHME programme 2: Supply side activities only 3: Counterfactual (no DFID spend) / Total programme budget $60.2m $60.2m $30m / DFID Budget outlay $30.2m $30.2m 0 / Number DFID attributable quantified DALYs 208,920 305,408 0 / Estimated discounted Cost per DALY range $63 to $136 $60 to $93 $75 to $132 / Non quantifiable benefits / DALYs, equity gains and household income effects from DSF achieved Yes No Yes / Extra DALYs from Safecare quality assurance and provider credit Yes Yes No / Synergies from combining demand and supply side activities Yes No Yes / Unquantified benefits to all options Efficiency gains from ICT / Externalities and efficiency improvements from policy and regulatory impacts / Household level healthcare cost savings / Increased accessibility to quality services for poorer people / D. What measures can be used to assess Value for Money for the intervention? / Impact level VfM indicators / To measure value for money, AHME will measure: / Incremental Cost per DALY (additional DALYs gained per pound of DFID money invested) / Incremental Societal Cost per DALY (system costs and out of pocket expenditure for patients); / Maternal deaths averted; and / Deaths in children under the age of 5 averted. / AHME will track the distribution of beneficiaries in terms of age, gender and income quintile, which will contribute to an assessment of equity gains, a good measure of VFM at the outcome level. The planned evaluation will isolate the impacts of the different activities (social franchising, accreditation, credit and DSF) on DALY generation, including costs per DALY. / VfM at the outcome level / To measure value for money, AHME will again measure improved equity in terms of those accessing the healthcare provided. Measures will include the percentage of clients using health services in the bottom two income quintiles. Outcome indicators will be taken from the DFID results frameworks for reproductive health and malaria and include, but not be limited to: / Numbers of women using modern methods of family planning calculated from Contraceptive Prevalence Rate (CPR) / Number of unintended pregnancies prevented modelled from couple years of protection (CYP) of family planning / Percentage of women receiving at least 4 antenatal care contacts during pregnancy / % of women who received at least two doses of IPTp during ANC visits during their last pregnancy / Percentage of infants exclusively breastfed for up to 6 months / % children under 5 years who received appropriate antimalarial treatment (including ACTs) within 24 hours of onset of fever in the last two weeks / VFM at the output level - increased scale and scope of private provider networks and demand side financing in the 3 countries. / Value for money at this level will depend upon minimisation of input costs, including in relations to costs incurred by other projects undertaking similar interventions in the 3 countries or other developing countries. This will be monitored by AHME partners on an ongoing basis, and investigated during the independent evaluation. Secondly, cost ratios, in particularly administration-to-programme cost ratios, will be kept at reasonable levels and monitored. The balance of programme spending on administrative functions compared with ‘client’ focused activities will be kept under scrutiny for the whole programme as well as for discrete packages of activities. Overhead costs will be minimised and, where possible, semi-fixed costs (such as accommodation costs) will be subject to regular challenge and review.
The additional DALYs averted as a result of the additional donor investment will be lower than those shown here. Since the donor contribution will account on average for 34% of the total service costs of social franchising, 34% of the total expected DALYs averted are attributed to this funding. Of these, only 80% are taken to be due to new and additional users and so included as additional benefits. But to take account of the fact that existing service users can also be expected to benefit from the improved quality of service provision, an increase of 30% in their DALYs is included. / It has not been possible to quantify the benefits of the other elements of the programme. The following benefits are expected to be produced but are not included in the model, meaning that the DALYs for option 1 (and in some cases also for options 2 and 3) are underestimated: / Impacts of demand side financing / Impacts of the Safecare quality assurance scheme and provider credit on the additional DALYs generated / Direct and indirect benefits of the policy and regulatory work. / Synergies associated with combining demand and supply side activities / Potential replication and leverage benefits within other countries and the global health community; / Healthcare cost savings accruing to households, donors and public sector; / Household income effects from demand side financing – investment gains and knock on effects resulting from demand side vouchers and subsidies. / In the case of demand side financing, it is not possible to quantify the benefits because it is not yet clear which mechanism or combination of mechanisms will be funded in each country. However, the types of benefits that DSF might be expected to generate include: / Reduction in impoverishment due to catastrophic expenditure by the poor on healthcare; / Increased uptake of services by poor people; / Increased ability of patients to hold providers to account; / Increased ability of patients to choose, thus driving competition and its benefits; and consequently / Improved health outcomes for the poor. / In the case of the other supply-side interventions, there is not yet enough empirical evidence on which to base estimates of the size of the benefits (see evidence section above). The evaluation of this programme will contribute to increasing the evidence base for future investment decisions. / Distribution of benefits / The benefits are likely to accrue primarily to rural low-income health care consumers due to the intended geographic targeting of the activities and the targeting of DSF. The immediate beneficiaries of the donor subsidy will also include private health care providers who have been operating in fragmented and unregulated. / Health care regulators and those responsible for health service delivery, such as Ministries of Health, will also benefit from the AHME partnership through the development of better regulation and capacity to respond to the health needs of the population. The policy and regulatory technical assistance will give rise to be wider benefits to society from a better health policy environment, leading to stronger supply chains and health market mechanisms. This will in turn allow other provider networks and provision to improve, thus creating spill over and indirect benefits to more vulnerable people. The impact of policy technical assistance on the private sector supply chains is likely to have a greater sustainability effect, compared to the social franchising activities and demand side activities. The impacts of policy changes should, in theory last much longer than the duration of the programme. / Balance of costs and social franchising benefits for Option 1 / Given that, as described above, it is not possible to quantify the full benefits of option 1, it is not possible to carry out a full comparison of costs and benefits. Table 6 below summarises the results of a partial cost-effectiveness analysis, in which only the benefits from social franchising are quantified. The results are based on DALYs that are directly attributable to AHME funding[19]. / Table 6: Partial cost-effectiveness analysis of Option 1 / Budget and Impacts / Discounted budget (3% social discount rate) $56.7m / Discounted social franchising budget (including PMU) $26.2m / Impact: Number of DALYS attributable to Gates and DFID funding 417,840 / Cost effectiveness / Discounted cost per DALY from social franchising, based on total budget $136 / Discounted cost per DALY from social franchising, based on social franchising budget + PMU $63 / Un-quantified benefits / DALYs, equity gains and household income effects from DSF / DALYs from Safecare quality assurance and provider credit / Efficiency gains from ICT / Externalities and efficiency improvements from policy and regulatory impacts / Household level healthcare cost savings and illness prevented / Synergies from combining demand and supply side activities / As can be seen from Table 9 the cost per DALY ranges from $63 to $136 (£40 to £86), depending on which elements of costs are included. The lower figure includes only the costs that can be attributed to social franchising activities, while the higher figure spreads the whole budget over the DALYs averted through social franchising. The higher figure can be seen as corresponding to a worst- case scenario in which demand side financing, ICT, Policy and regulation and quality assurance and credit access have zero benefits. / To benchmark these figures, the WHO guidance indicates that interventions are highly cost effective if a DALY can be averted for less than the GNI per capita (Atlas method) of the country in question. The lowest GNI per capita figure for the three countries is $790 (Kenya).[20] Thus by this standard Option 1 is deemed a highly cost effective way of reducing morbidity and mortality (and would remain so even if the DALY estimates, which are based on assumptions about the growth of services delivery, turned out to be over-optimistic). / These overall cost per DALY figures mask considerable variation by country. PSI estimates suggest that the cost per DALY based on social franchising and PMU costs is highest in Ghana ($97), followed by Nigeria ($89) and Kenya ($21). For the most part, cost per DALY in a given country is influenced by 4 factors: the cost of doing business in country, the existing size of the franchise, the existing scope of services offered through the franchise, and the disease burden in country. The cost per DALY in Ghana is heavily influenced by the cost of doing business in Ghana, the relatively small size of the franchise (only 90 providers currently), and the limited existing scope of services included in franchise. Due to the low prevalence of HIV and TB, BlueStar Ghana will not franchise screening or treatment for these services, which boost DALY estimates in Nigeria and Kenya. The cost per DALY in Nigeria is influenced by MSI’s franchise, which is new and will be rural and so will not produce the same volume of DALYs as SFH’s franchise in the first few years. The cost per DALY in Kenya is the lowest as the MSI and PSI franchises are well established and well funded. To add the services under AHME will be slightly more cost effective. Franchisors expect that the cost per DALY decreases with the increased size and scope of the franchise. This reflects the increased efficiencies of the franchises to produce DALY. Nigeria projects a 300% decrease over the 5 years. Kenya projects a 200% decrease in cost per CYP, while Ghana projects a 78% decrease. / Option 2 / The difference between Option 1 and Option 2 is that under Option 2 the whole budget of $60m is invested in supply-side interventions. The costs of the management unit remain the same, but for the purposes of this appraisal it is assumed that the remaining costs are spread across supply-side activities in the same proportions as under Option 1. / Table 7: Costs of Option 2 (Supply side activities) / Agent Activity Budget $m DFID share $m % Of total / MSI (and Partners) Overall management unit 5.4 2.8 8 / Grameen ICT 3.6 1.8 6 / IFC Policy and regulation 4.6 2.3 8 / MSI, PSI, SFH Scale up and increase in scope of health provider network 33.8 16.9 56 / PharmAccess Accreditation (quality improvements) 5.9 2.95 10 / Provider credit (quality improvements) 7.1 3.55 12 / Total 60.2 30.2 100 / Option 2 still has benefits that cannot be quantified before the programme is implemented, but given that a larger proportion of the budget is allocated to social franchising, the unquantified benefits account for a smaller proportion of the total under option 2. The estimates presented here assume that increasing the availability of franchised services in rural areas proportionately increases the DALYs gained through those services; this may be an over-estimate if people living in those areas are unable to access the services due to financial or other constraints. / Table 8: Partial cost-effectiveness analysis of Option 2 / Budget and Impacts / Discounted budget (3% social discount rate) $56.7m / Discounted social franchising budget (including PMU) $36.8m / Impact: Number of DALYS attributable to Gates and DFID funding 610,816 / Cost effectiveness / Discounted cost per DALY from social franchising based on total budget $93 / Discounted cost per DALY from social franchising based on social franchising budget + PMU $60 / Unquantified benefits / DALYs from Safecare quality assurance and provider credit / Efficiency gains from ICT / Externalities and efficiency improvements from policy and regulatory impacts / Household level healthcare cost savings and illness prevented / In this case the cost per DALY ranges from $60 to $93 (£38 to £59), depending on which elements of costs are included. The lower figure (based on the social franchising budget + PMU costs) is of course very similar to that for option 1, since both options only quantify social franchising benefits. The figure based on the whole budget ($93 per DALY) is lower for option 2 than for option 1. The difference masks the unquantified benefits resulting from the 30% of budget in option 1 that is allocated to DSF. It also masks any equity benefits resulting from the DSF activities in option 1 and assumes that availability translates into accessibility as noted above. / DFID’s objective is to increase the use of good quality essential health services by poor people, but not all of the additional DALYs from SF will go to the poor. The objective of including the DSF component in option 1 is to make good quality services more affordable for poor people and so to increase the proportion of the total additional DALYs averted that benefit the poor. Option 2 would avert additional DALYs by investing more of the budget in SF, but it is expected that fewer of them would benefit poor people. Since DFID (at least implicitly) values DALYs averted for poor people more highly than those averted for richer people, it is possible that option 1 could generate greater benefits than option 2, even if the total number of DALYs averted were smaller. / Option 3: the counterfactual / This option refers to the baseline situation where DFID makes no additional investment. The Gates Foundation has indicated that they would go ahead with funding 50% of the AHME partnership ($30m) in the absence of DFID funding. They would not, however, fund the accreditation and access to credit activities. Thus the $30m is assumed to be spread pro rata on the other activities. The profile and distribution of benefits would be slightly different, as it is unclear whether all the benefits would be spread across the three countries in the same way. For ease of analysis it is assumed they are. The quantified benefits would be slightly less than 50% of Option 1 because the fixed cost of the PMU would be spread across less outputs, thus scale effects would not be realised. / Table 9: Costs of Option 3: Counterfactual / Agent Activity Budget $m % Of total / MSI (and Partners) Overall management unit 5.2 17 / Grameen ICT 1.2 4 / IFC Policy and regulation 1.7 6 / MSI, PSI, SFH Scale up and increase in scope of health provider network 12.5 42 / PharmAccess Demand Side Financing 9.4 31 / Total 30 100 / As the PMU costs are fixed costs, they now account for twice as large a proportion of the total budget compared to options 1 and 2. These fixed costs are spread across fewer units of output, raising the cost per DALY. / Table 10: Partial cost-effectiveness analysis of option 3 / Budget and Impacts / Discounted budget (3% social discount rate) $28m / Impact: Number of DALYS attributable to Gates funding 226,078 / Cost effectiveness / Discounted cost per SF DALY based on total budget $125 / Discounted cost per SF DALY based on social franchising budget + PMU $75 / Un-quantified benefits / DALYs, equity gains and household income effects from DSF / Efficiency gains from ICT / Externalities and efficiency improvements from policy and regulatory impacts / Household level healthcare cost savings / Synergies from combining demand and supply side activities (likely to be smaller at this scale) / Table 11 compares all the VFM metrics for all the options. It is not a straightforward comparison, because several elements of the intervention combinations give rise to unquantifiable benefits, and their magnitudes vary with the options. / Table 11: VFM comparison of options / 1 AHME programme 2: Supply side activities only 3: Counterfactual (no DFID spend) / Total programme budget $60.2m $60.2m $30m / DFID Budget outlay $30.2m $30.2m 0 / Number DFID attributable quantified DALYs 208,920 305,408 0 / Estimated discounted Cost per DALY range $63 to $136 $60 to $93 $75 to $132 / Non quantifiable benefits / DALYs, equity gains and household income effects from DSF achieved Yes No Yes / Extra DALYs from Safecare quality assurance and provider credit Yes Yes No / Synergies from combining demand and supply side activities Yes No Yes / Unquantified benefits to all options Efficiency gains from ICT / Externalities and efficiency improvements from policy and regulatory impacts / Household level healthcare cost savings / Increased accessibility to quality services for poorer people / d. What measures can be used to assess Value for Money for the intervention? / Impact level VfM indicators / To measure value for money, AHME will measure: / Incremental Cost per DALY (additional DALYs gained per pound of DFID money invested) / Incremental Societal Cost per DALY (system costs and out of pocket expenditure for patients); / Maternal deaths averted; and / Deaths in children under the age of 5 averted. / AHME will track the distribution of beneficiaries in terms of age, gender and income quintile, which will contribute to an assessment of equity gains, a good measure of VFM at the outcome level. The planned evaluation will isolate the impacts of the different activities (social franchising, accreditation, credit and DSF) on DALY generation, including costs per DALY. / VfM at the outcome level / To measure value for money, AHME will again measure improved equity in terms of those accessing the healthcare provided. Measures will include the percentage of clients using health services in the bottom two income quintiles. Outcome indicators will be taken from the DFID results frameworks for reproductive health and malaria and include, but not be limited to: / Numbers of women using modern methods of family planning calculated from Contraceptive Prevalence Rate (CPR) / Number of unintended pregnancies prevented modelled from couple years of protection (CYP) of family planning / Percentage of women receiving at least 4 antenatal care contacts during pregnancy / % of women who received at least two doses of IPTp during ANC visits during their last pregnancy / Percentage of infants exclusively breastfed for up to 6 months / % children under 5 years who received appropriate antimalarial treatment (including ACTs) within 24 hours of onset of fever in the last two weeks / VFM at the output level - increased scale and scope of private provider networks and demand side financing in the 3 countries. / Value for money at this level will depend upon minimisation of input costs, including in relations to costs incurred by other projects undertaking similar interventions in the 3 countries or other developing countries. This will be monitored by AHME partners on an ongoing basis, and investigated during the independent evaluation. Secondly, cost ratios, in particularly administration-to-programme cost ratios, will be kept at reasonable levels and monitored. The balance of programme spending on administrative functions compared with ‘client’ focused activities will be kept under scrutiny for the whole programme as well as for discrete packages of activities. Overhead costs will be minimised and, where possible, semi-fixed costs (such as accommodation costs) will be subject to regular challenge and review. / Summary Value for Money Statement for the preferred option / Option 1 is the preferred option. The economic appraisal suggests that if it is assumed that there are no benefits from the demand side financing component of the programme, and no synergies from combining demand and supply side activities, option 2 is likely to have lower cost per additional DALY ($60-$93 per DALY) than option 1 ($63-$136 per DALY) and the counterfactual ($75 to $132 per DALY). But while it is not yet possible to estimate the unquantified benefits with accuracy, they are crucial to achieving DFID’s objective of increasing use of good quality essential health services by poor people. As explained, the benefits from demand-side financing will include reduction in impoverishment due to catastrophic expenditure by the poor on healthcare, increased ability of patients to hold providers to account and increased ability of patients to choose between providers, in addition to the improved utilisation of services and improved health outcomes for the poor that are reflected in DALYs. In order for option 1 to be as cost-effective as option 2, the addition of demand side financing would have to increase the total benefits by 46%. The evaluation will measure the additional benefits and provide new evidence on the impact of adding demand-side financing to the social franchising programme.
[17] The numbers of DALYs shown here are smaller than those in the logframe, which reflect all AHME programme results rather than just the part attributable to BMGF and DFID funding. The costs per DALY are also different.
[18] Source: World Bank
[19] The numbers of DALYs shown here are smaller than those in the logframe, which reflect all AHME programme results rather than just the part attributable to BMGF and DFID funding. The costs per DALY are also different.
[20] Source: World Bank

Commercial Case

a. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner?

DFID will fund the acquisition of goods and services for AHME through indirect procurement. DFID will sign an MoU with BMGF through which all funding for AHME implementation and evaluation will be channelled. BMGF will sign a Grant Arrangement with MSI. As DFID and BMGF will each take a 50% share of funding, this will simplify MSI’s responsibilities in terms of budgeting, forecasting and narrative and financial reporting. An existing DFID/BMGF MoU for strategic collaboration for sustainable intensification of agriculture provides a useful precedent.

b. Value for money through procurement

Implementation requires collaboration between several organisations as no one body has the technical expertise or reach to deliver the programme in its entirety. In order to achieve coherence, maximise synergies and potential economies of scale, and minimise transaction costs for DFID and BMGF, the programme will be contracted to a consortium, the lead agecy of which will manage all subcomponents.

Value for money will be achieved through local procurement as far as possible, as shown in the project budgets. MSI will recruit a dedicated Finance Officer for AHME, who will work out of MSI’s Nairobi office. The Finance Officer will be supported by MSI’s Finance Team in London.

Financial Case / a. What are the costs, how are they profiled and how will you ensure accurate forecasting? / Financial forecasts will be reviewed by all AHME partners on a quarterly basis and reported to BMGF who will share with DFID. This will promote accurate forecasting of cash requirements. / Table 12: Breakdown of Total Project Budget by Country and Organisation (US$m) / Country MSI PSI SFH PAI IFC GF Unallocated Total % / Nigeria 3,219,386 5,465,067 4,150,280 1,592,931 141,209 5,008,374 19,577,246 33 / Kenya 4,826,380 4,422,263 2,808,999 639,073 130,324 5,008,373 17,835,411 30 / Ghana 3,055,065 2,054,353 774,879 123,450 5,008,373 11,016,120 18 / Project Manage-ment 3,237,079 502,920 230,180 - 207,210 7,965 4,185,354 7 / Indirect * 2,549,086 738,777 550,091 1,081,636 160,705 60,442 2,245,132 7,385,869 12 / 16,886,996 5,663,960 6,245,338 10,095,267 3,374,799 463,389 17,270,251 60,000,000 100 / Total 28% 9% 10% 17% 6% 1% 29% 100% / % 3,219,386 5,465,067 4,150,280 1,592,931 141,209 5,008,374 19,577,246 33 / * Indirect shows the indirect rates charged by each of the organizations: MSI 15%, PSI 15%, SFH 10%, PAI 15%, IFC 5%, GF 15%. Within the budget there is ring fenced sum of US$17.4m of unallocated grants mainly for demand side financing (89%) and information, communications and technology (ICT) (11%). For the purposes of cost modelling, it has been assumed that this sum will be allocated across the line items in a similar way to the rest of the budget. This allows us to estimate the break down of the total budget by key cost drivers, which are personnel, travel, consultancy, supplies. Supplies category includes a multitude of items, such as commodities, rent for office space, utilities. The full allocation of sub-awards between partners is not yet known and will depend on analysis done in year 1, partly related to demand side financing. Hence, the 12% overhead figure is an average and includes overheads on unallocated funds. / Table 13: Total Project Budget by Workstream and Organisation (US$m) / Workstream MSI PSI SFH PAI IFC GF Unallocated Total % / PPN 13,649,917 5,161,041 6,015,158 - 24,826,116 41 / DSF 1,170,789 950,276 15,430,251 17,551,315 29 / MCF 4,860,788 4,860,788 8 / Safecare 4,063,691 4,063,691 7 / ICT 455,424 1,840,000 2,295,424 4 / Policy 2,217,312 2,217,312 4 / Project Management 3,237,079 502,920 230,180 - 207,210 7,965 - 4,185,354 7 / Total 16,886,996 5,663,961 6,245,338 10,095,267 3,374,798 463,389 17,270,251 60,000,000 100 / Table 14: Budget showing profile of spend over lifetime of project, by country (US$) / Country Year 1 Year 2 Year 3 Year 4 Year 5 Total % / 1: Nigeria 3,499,375 3,771,638 4,166,101 4,116,809 4,023,322 19,577,245 33 / 2: Kenya 2,991,792 3,772,063 3,814,661 3,599,982 3,656,913 17,835,411 30 / 3: Ghana 1,698,202 2,322,319 2,435,979 2,280,621 2,278,999 11,016,120 18 / PM 1,060,131 785,723 769,703 766,611 803,188 4,185,355 7 / Indirect (subcontract) 676,388 990,814 1,070,237 1,035,292 1,064,052 4,836,783 8 / Indirect (primary) 517,958 540,124 520,905 493,671 476,428 2,549,086 4 / Total 10,443,846 12,182,681 12,777,586 12,292,986 12,302,902 60,000,000 100 / Percentage 17% 20% 21% 20% 21% 100% / Table 15: Budget showing profile of spend over lifetime of project, by Workstream (US$) / Workstream Year 1 Year 2 Year 3 Year 4 Year 5 Total % / PPN 5,507,121 4,922,650 5,141,094 4,566,464 4,688,788 24,826,117 41% / DSF 1,363,715 4,053,363 4,057,026 4,060,227 4,016,983 17,551,315 29% / MCF 778,010 902,760 1,043,808 1,078,809 1,057,400 4,860,788 8% / Safecare 829,283 601,317 840,539 887,991 904,562 4,063,691 7% / ICT 455,424 460,000 460,000 460,000 460,000 2,295,424 4% / Policy 450,162 456,868 465,416 472,882 371,982 2,217,310 4% / Project Management 1,060,131 785,723 769,703 766,611 803,188 4,185,355 7% / Total 10,443,846 12,182,681 12,777,586 12,292,984 12,302,904 60,000,000 100% / Table 16: Breakdown of key cost drivers by budget line item / Cost category Nigeria Kenya Ghana Project Mgt Total Percentage / Personnel 8,386,386 4,868,263 2,778,525 1,926,729 17,959,903 30% / Travel 1,674,782 2,187,186 1,011,460 846,126 5,719,554 10% / Consultancy 748,710 642,126 670,830 360,000 2,421,666 4% / Supplies (broad category including commodities, rent, utilities) 3,504,653 5,045,462 1,476,933 1,022,501 11,049,549 18% / Indirect overheads 2,152,685 2,341,372 1,602,595 854,217 6,950,869 12% / Sub grants (unallocated funds) 5,008,373 5,008,373 5,008,374 - 15,025,119 25% / Allowable MSI indirect overheads on partners 108,750 108,750 108,750 108,750 435,000 1% / Equipment 254,340 84,000 70,000 30,000 438,340 1% / Total 21,838,678 20,285,533 12,727,466 5,148,323 60,000,000 100% / Personnel costs are expected to be high, given that a large proportion of activities are human resource heavy – technical assistance, training, and coordination roles. / Table 17: Allocated indirect overhead rates for Option 1, by consortium partner / Partner Indirect overhead charged (% rate on direct costs) Actual cost $ / Marie Stopes International 15% 2,549,086 / Population Services International 15% 738,777 / Society for Family Health in Nigeria 10% 550,091 / PharmAccess International 12% 1,081,636 / IFC 5% 160,705 / Grameen Foundation 15% 60,442 / Unallocated costs for DSF and ICT 13% 2,245,132 / Total 12% 7,385,869 / As can be seen from Table 18 the overhead rates range from 5% to 15%. Overall AHME requires a 12% administration fee. BMGF will not charge DFID for services provided to DFID under the MoU. / As lead partner, MSI requires a 15% administrative fee on MSI total direct costs, minus equipment--with a 1% administrative fee on sub awards to be applied to the first $100,000 of each sub award per organisation per year. This standard fee structure is taken directly from the Indirect-Cost Guidelines issued by the Bill & Melinda Gates Foundation and is used by MSI globally to ensure consistent treatment of cost recovery. The MSI indirect cost rate includes: accounting and financial management; human resources services for London and international staff; contracts management; information technology and systems support; quality assurance by MSI's research and metrics department; London and Nairobi facility costs; and other services such as the executive office, a portion of the management and administration of technical and programmatic departments, the preparation of bids and proposals, and public affairs. These charges are monitored closely and audited annually by an external auditor. / Society for Family Health – 10% / SFH indirect costs include all costs not easily attributable to any specific project, including the field offices, human resources management, procurement, external relations/communication, new business development, head office field coordination, internal audit, accounting, information technology and office of the chief executive. / Health in Africa, International Finance Corporation – 5% / The standard administrative fee for IFC-managed trust funds is five percent (5%) of the contributions. This is used to cover the costs of administering the trust fund. / PharmAccess International – 12% / Indirect costs for PharmAccess (including the demand side financing, MCF and SafeCare activities) are 12%. These costs cover the organisation’s running costs in Amsterdam including; the finance department; office management costs; office rent and supplies; senior management costs; IT support; communication; contract preparation and management. PharmAccess will be developing new products for AHME under its MCF and SafeCare initiatives, and costs of overheads will go some way to cover related management support. / Grameen Foundation – 15% / GF applies an indirect rate of 15%. In reality, the GF indirect rate was 22% for fiscal year 2010 (most recent audited financial report). It is calculated by expressing the cost of management and general expenses as a percentage of GF total programme services expenses. It includes the costs of: Operations, Finance, Development, Contract Management, Office of the President, Strategy and Research Departments. These expenses are pooled and allocated to direct programme activities at the end of each month. GF indirect rates are independently audited on an annual basis. / Population Services International – 15% / PSI charges a 15% administrative fee on total direct costs, minus equipment - with a 15% administrative fee on sub awards to be applied to the first $100,000 of each sub award per organization per year. This standard fee structure is taken directly from the Indirect-Cost Guidelines issued by the Bill & Melinda Gates Foundation and is used by PSI globally to ensure consistent treatment of cost recovery. The administrative fees include: accounting and financial management; employment services for Washington and international staff; contracts management; information technologies and systems support; quality assurance; Washington facilities costs; the Executive Office; a portion of the management and administration of technical and programmatic departments; the preparation of bids and proposals; public affairs and other administrative costs. These costs are monitored closely and audited annually by an external auditor. / b. How will it be funded: capital/programme/admin? / Table 18: Total donor financial contributions, millions (US$1: £0.63) / US$ GB£ / BMGF 33.5 21.1 / DFID Private Sector Department 15.4 9.7 / DFID Ghana 8 5 / DFID Kenya 0 0* / DFID Nigeria 8 5 / DFID Human Development Dept 2.1 1.3** / TOTAL DFID 33.5 21.1 / TOTAL 67 42.2 / * DFID Kenya is not committing funds at this point, so the costs of the Kenya work will be shared among PSD and BMGF. It is writing a business case to gain an understanding of Kenyan health markets for the poor (M4P) with a view to designing a larger private sector business case in 2014. One of the options appraised in the business case is AHME, but it is not the preferred one. / ** The AIDS and Reproductive Health Team in HDD has indicated a wish to fund £650,000 per year for years 2 and 3 of the project. This is being reviewed as a part of the current challenge to PD to cut commitments that do not yet have an approved business case. If there is a shortfall of funding from HDD, PSD will cover this amount to avoid jeopardising AHME. / Approval for co-funding from DFID Country Offices will be sought on the basis of this single umbrella Business Case, appending results expected to be delivered in each country. DFID Country Offices will allocate the agreed amount of co-funding for the programme on ARIES to the Private Sector Department (PSD). PSD in turn will provide funding to AHME. / DFID funds will come from programme resources. / Table 19: AHME spend profile by donor over project lifetime, US$ million (US$1: £0.63) / Year 1 Year 2 Year 3 Year 4 Year 5 Total / BMGF 5.2 6.1 6.4 6.15 6.15 30 / DFID Private Sector Department 0.95 1.85 3.2 2.95 2.95 15.6 / DFID Ghana 1.6 1.6 1.6 1.6 1.6 8 / DFID Nigeria 1.6 1.6 1.6 1.6 1.6 8 / DFID Human Development Dept 1.05* 1.05* 0 0 0 2.1 / TOTAL DFID 5.2 6.1 6.4 6.15 6.15 30 / TOTAL 10.5 12.2 12.8 12.3 12.3 60
In the event Human Development Department is unable to secure funds, PSD will cover these costs to avoid jeopardising the programme. / Until the Evaluation Protocol has been written, a spend profile for the independent evaluation is unavailable. DFID (PSD) and BMGF will fund equal shares of the evaluation. / c. How will funds be paid out? / Programme funds will be disbursed via an MoU between DFID and BMGF. Payments will be disbursed quarterly, following DFID receipt and review of a statement from BMGF of how the previous quarter’s funding has been used (received versus committed and/or disbursed) and a forecast for the coming quarter. As MSI will submit one claim for all implementing partners, BMGF will ensure MSI has reviewed claims by partner organisations before requesting further funding. Such checks will be built into BMGF’s due diligence checks. / There will be stringent tracking of unit costs and inputs to outputs to ensure funds remain secure and provide value for money. PSD will be responsible for monitoring all payments to BMGF for AHME and monitoring progress of results against intended targets, including Country Office specific targets. / For the evaluation, the same principles and process will apply.
c. What is the assessment of financial risk and fraud? / Prior to signing of the MoU, DFID will conduct due diligence of BMGF, including ensuring BMGF has in place satisfactory due diligence procedures for its grantees. The process for this will be agreed between PSD, FCPD and BMGF. It will be led by PSD with support from FCPD. / BMGF will be responsible for due diligence of MSI and the Evaluation Team. In turn, MSI will be responsible for due diligence of all AHME implementing partners, including through the application of its due diligence checklist drawn up as a response to the KPMG Due Diligence Report. / A due diligence assessment of Marie Stopes International was conducted by KPMG on behalf of DFID in March 2011, in advance of DFID granting a Programme Partnership Arrangement. MSI has satisfactorily addressed all critical and high priority findings of this assessment. / MSI regularly assesses risks, and undertakes activities to manage and mitigate financial risks and fraud. The Marie Stopes International risk management system has been developed to provide reasonable assurance to the Trustees and donors that there are adequate procedures in place and that their effective operation is evaluated. Marie Stopes internal audit team reports to the Steering Committee and will visit 23 partner countries, including Ghana, Kenya and Nigeria, in 2012 to assess risks and review operational and financial controls. MSI has a whistle-blowing policy in place that addressed administrative (as well as clinical) malpractice. This includes but not limited to: misuse of company assets, theft, siphoning of funds, awarding contracts unfairly and tax irregularities Demand-side financing will not include social cash transfers due to the very high level of fiduciary risk associated with these. Value for money in procurement will be promoted through local procurement in the 3 focus countries. / MSI will review partner financial policies and systems in order to ensure that financial risks are minimised and that procedures are in place to mitigate fraud. This will be undertaken at contract stage. The additional complexity of managing the high value 6 Partner project will have the effect of raising the risk profile of the project in the MSI Internal Audit planning documentation resulting in a significantly increased focus and allocation of resources to the internal control reviews in Ghana, Kenya and Nigeria throughout the life of the project. Typically these Programmes would receive an annual internal audit of 2-3 man weeks by qualified, audit trained, Team Members. However, it is intended that the frequency of internal audits will be increased and the time spent on verification and testing will be extended in order to provide assurance to the Board of MSI that the controls necessary to mitigate against fraud are in place and effective. This will include collaboration with partner organisations when reviewing documents supporting expenditure covered by the contract. / There is likely to be a significant administrative burden for the implementing partners in tracking country inputs. This will be managed using existing management systems. / If the programme is terminated early, through no fault of the implementing partners, DFID will reimburse, through BMGF, the suppliers for any costs that have already been incurred, or that will be necessarily incurred and the supplier cannot be expected to avoid or recover (including reasonable costs associated with programme run down).
d. How will expenditure be monitored, reported, and accounted for? / Financial and brief supporting narrative reports will be submitted by BMGF to DFID on a quarterly basis in accordance with procedures agreed under the MoU. These reports will support DFID’s quarterly in advance financial disbursements to BMGF. BMGF will also submit to DFID detailed annual technical and financial reports of AHME and the independent evaluation. / Assuming the MoU follows the agreement reached for the existing DFID/BMGF agricultural research MoU, the following process and principles will be applied. / BMGF will use its standard processes and procedures to oversee each grantee’s compliance with the terms and conditions of the applicable Grant Arrangement and the conduct of the relevant activities. Each Grantee will have sole responsibility for the use of DFID funds disbursed to them by the Foundation. / The Foundation will provide DFID with: / Written confirmation of receipt of each transfer of DFID funds; / A fully executed copy of each Grant Arrangement; / Written confirmation of the date and amount of any disbursement of DFID funds made by BMGF to a Grantee; / A copy of any financial statement BMGF receives from any Grantee during the term of the relevant grant; / An annual letter from BMGF’s Chief Financial Officer which summarises when and to which Grantee DFID funds were disbursed for that year. / BMGF will promptly transmit to DFID via email all requests from a Grantee for: (a) a Joint Project budget cost category change of more than 10%; 9b) a change to any joint project milestone; and (c) BMGF’s recommended response to such a request/s. / Each Grant Arrangement will require the Grantee to maintain records sufficient to enable DFID to determine how the DFID funds were spent, and to make such records available to DFID or its designee for inspection at reasonable times. Each Grant Arrangement will also provide DFID with standard and customary entitlement to visit Joint Project sites and otherwise communicate with project managers.

Management Case

What are the Management Arrangements for implementing the intervention? / The intervention will be jointly funded by BMGF and DFID. However, as DFID funding will flow through BMGF, BMGF will ultimately be responsible for reporting to DFID on use of DFID funds. DFID’s direct management involvement in AHME will be limited to its position on the AHME Steering Committee (see Figure 20). / Annual reviews of AHME will be included in DFID’s annual reviews for HANSHEP, along with all other HANSHEP programmes. These annual reviews will be coordinated by the Team Leader, Health and Education, Private Sector Department with input from DFID colleagues and relevant external stakeholders. / Many of the AHME partners were working together on a smaller scale before the AHME partnership. The scale of integration and collaboration proposed under the AHME partnership, however, requires a defined coordination, management and decision making structure (See Figure 21). This structure should ensure that the AHME partnership maintains contractual and contextual responsiveness. Given the complexity of a multi country, multi intervention programme, the proposed management and staffing plan for AHME will be flexible and subject to change during the programme based on experience. / Figure 20: Proposed management structure / Marie Stopes International will lead the AHME partnership and programme and will set up and oversee all management arrangements detailed below. / The AHME Steering Committee, with senior representatives of each organisation, from the two funders and the HANSHEP Secretariat, will review progress on a quarterly basis. The Steering Committee’s main purpose will be strategic oversight and resource allocation, and the participants will have the authority to address performance problems within their own organisations if needed. The Steering Committee will review results and hold management and individual partners accountable for their activities and results. Since annual resource allocations will be fungible between work streams and activities, the Steering Committee will be able to redirect funds from unallocated resources to the most effective activities. The Team Leader, Human Development in Private Sector Department and the Senior Health Economist, Health Services Team will represent DFID on the Steering Committee. They will represent views of their own Departments, the 3 relevant DFID country offices; and an Evaluation Adviser. Precise Terms of Reference for the Steering Committee, and DFID’s role on it, will be detailed after funding approval, and will be agreed by those responsible for Risk and Assurance in FCPD. / A Technical Advisory Panel (TAP) comprised of two independent experts from each of the three countries will meet every 6 months to ensure external perspectives are brought to bear. . Membership of the TAP will consist of government representatives, experts in private sector health care delivery, health financing and innovative technology. It will meet at least bi-annually to discuss AHME and its progress, and will review the partnership activities to ensure that they are catalytic, innovative, evidence-based, intellectually rigorous, sustainable, significant, collaborative, learning, and equity. / A Partner Leadership Team and a Project Management Unit will be established in MSI/Kenya, The Partner Leadership Team will be chaired by MSI and will comprise representatives of each of the AHME implementing partners. This team will meet monthly and be responsible for coordinating work plans. It will write up clear responsibility and accountability frameworks for partners in each of the countries. The Partner Leadership Team will be proactive in anticipating and resolving problems. As Chair of the Partner Leadership Team, and Lead AHME Partner, MSI will resolve disputes between partners where they cannot be resolved by the Project Management Unit. Only when MSI is unable to resolve disputes amicably will these be elevated to the AHME Steering Committee. Regular meetings will allow for the exchange of lessons learned and results. Recommendations will be made to the AHME Steering Committee on progress, challenges, and resource allocations. / The Project Management Unit will be staffed by MSI. It will provide administrative support and management oversight to country-level implementation. Responsibilities will include managing for sub-contracts with AHME partners, including holding sub-contractors accountable for delivery. Where disputes cannot be resolved at the country level, the Project Management Unit will help resolve disputes. MSI will prepare reports for the Partner Leadership Team and the AHME Steering Committee on the overall performance of the partnership as a whole, and of individual partners in their specific areas of responsibility. / Country level lead partners will be MSI in Ghana, PSI in Kenya, and SFH in Nigeria Lead partners in country will be responsible for country implementation, including ensuring collaboration and coordination of work plan activities at the national level, and identifying emerging contextual opportunities and threats. If disagreement occurs at the country level, the issue would be brought to the attention of the MSI Project Management Unit for arbitration and settlement. / An Evaluation Advisory Panel will comprise advisers from DFID (5% of an A2 Health Adviser) and BMGF. They will meet twice per year with the independent impact evaluation team to identify and resolve challenges with the impact evaluation and will liaise with the AHME technical advisory panel to help resolve potential tension between the needs of the evaluators and those of the implementers (for example, if site randomisation is not being implemented as agreed). The Panel will also discuss the likely Hawthorne effects resulting particularly from the process evaluation and agree how to account for these. It is proposed that the evaluation design undergoes independent peer review by registering it as a cluster randomised control trial with a high impact peer reviewed journal, for example The Lancet. / Internal DFID management will be led by the Team Leader, Health and Education, Private Sector Department (15% FTE at A2 grade for the first year of implementation and then gradually reducing to 10% by year 5). The Health Policy Team in Human Development Department will provide technical support, supervisory and quality assurance inputs with 5% of a FTE A1 Health Adviser (AHME programme), and 5% of an A2 FTE (AHME evaluation). Health Advisers in the 3 focus countries and the Aids and Reproductive Health Team will provide advice and feedback as part of their 10% time allocation to the health cadre. There will be support from a Deputy Programme Officer in Private Sector Department on financial and project management issues.

b. What are the risks and how these will be managed? / AHME is a complex programme working in distinct and challenging environments. Each country will develop its own risk analysis and risk mitigation strategy – and many risks will be managed at this level. Table 22 sets out key risks and mitigation actions for the overall programme. / Table 22: Risks types, Rating and Mitigating actions / Risk type and description Probability / Score / –L/M/H Impact / Score / –L/M/H Mitigating action / Changes in operating environments significantly disrupt programme implementation Medium Medium Monitor political economy of the three countries / Maintain adaptive and flexible implementation strategies that are responsive to fluctuations in operating environments / The programme has limited impact on availability of high impact services and technologies Low High Regular interrogation of causal chain (inputs-activities-outputs-outcomes) / Ensure ownership of the causal chain by stakeholders delivering the programme / Ensure clearly defined exit and sustainability criteria so that outcomes are sustained after the programme / Apply Value for Money principles so that inputs are transformed to activities and outputs in an efficient manner / The programme has limited impact on utilisation of high impact services and technologies Low High All Private Provider Networks have included demand generation activities in order to increase utilisation of services including working with community health workers. / MSI, PSI and SFH all have extensive experience in behaviour change communication and marketing departments to support the work in AHME. / Demand-side financing activities will reduce the out of pocket cost to service users, making them more affordable to poor people and reducing the financial barrier for both clients (to access the service) and providers (to provide the service). / Introduction of demand-side financing is delayed (beyond year 2 of the project) due to detailed analysis and complex set-up required Medium High AHME partners have planned a 3 month inception phase for conducting the current state analysis, policy framework analysis, and donor strategies analysis. IFC and PharmAccess currently have the skills to complete this work. / A full 9 months has been allocated for consumer insights analysis. This timeframe can be shortened depending on the findings from the inception phase. / AHME partners recognize the planning and roll are necessary in order to ensure implementation in Year 2. / AHME partners already have expertise in implementing many of the DSF mechanisms proposed so the implementation would require adaptation, roll out and scale up and less piloting. / AHME unable to maintain the necessary level of funds to sustain the networks Medium High Funding to be sought from National Governments from Year 2 of programme implementation, with a view to a mixed-funding model by the end of the programme period. / User-fees to be charged as appropriate to supplement national funding, while providing free care to the poor. / Commodity supply chains severely ruptured Low Medium Work closely with government medical stores and sectoral health programmes to ensure commodity security / PPNs to forecast needs and monitor supply chains / PPNs to buffer for stock outs / PPNs to facilitate access to good quality products for providers / Rapid expansion of scale and scope compromises the performance of the individual organisations and the partnership Low High AHME Steering Committee to comprise senior representatives to ensure rapid responses to implementation challenges / Steering Committee to oversee resource allocation to support expansion / Continuing support at highest level of all participating organisations for diversifying service scope
c. How will progress and results be monitored, measured and evaluated? / The AHME partnership will use DALYs averted as a primary measure of health impact achieved through the programme (See Annex 1: Results Framework, and Annex 2: Results Framework Indicator Definitions). While international standards and practices exist to calculate DALYs at the national level, PSI has collaborated with external consultants to pioneer the application of DALYs to individual health interventions. Bearing in mind that one DALY represents a year of healthy life lost due to illness or death, the PSI “DALY calculator” (www.dalycalculator.psi.org) measures the number of DALYs averted – in other words, the number of healthy or productive years that would have been lost without the health intervention. This measure factors in local conditions and parameters, including: incidence, annual number of episodes of a given disease by country/region, mortality rate, associated disability/illness, the waste and misuse of preventive or curative health products, and the protective efficacy and lifespan of these health products. / Based on service delivery volumes, the programme will estimate the health impact and cost-effectiveness in terms of DALYs-averted, programme cost per DALY averted, maternal deaths and deaths in children under five averted. According to the WHO CHOICE (Choosing Interventions that are Cost-Effective) initiative, DALYs averted at a cost that is less than the country’s average per capita income are considered very cost-effective. Cost-effectiveness will be examined relative to the published literature on moderately and highly cost-effective interventions. Where costs remain above these benchmarks, the burden of disease in the local area will guide decisions to integrate additional services into the programme. Ultimately, the effectiveness of the programme will be measured in terms of significant changes in the cost per DALY averted. / The programme will be monitored against annual performance milestones. Programme data will be collected by AHME partners. Results at the impact level will be generated by a model. The model will be refined in year one of the programme to capture all service areas supported under AHME in the three countries. Monitoring will include the poverty status of people who use services, which will be captured using existing monitoring tools and management information systems. The programme will be monitored by DFID and BMGF and reviewed annually. / The results of the monitoring will be used to inform and adapt the programme design and, if necessary, management over the subsequent year. Critically, AHME partners will be looking for ways to remove the causes of health market failures through their portfolio of workstream options. AHME aims to strengthen and ‘shape’ health markets through greater the interaction and synergy between core supply, demand functions as well as the supporting functions and rules which govern their operation using the principles and tools of Making Markets .work for the Poor (M4P). / The AHME partnership will also be externally evaluated through a separate grant by BMGF. Dr. Paul Gertler has been selected and contracted by BMGF to lead the impact evaluation and will be supported by Rachel Gardner (Berkeley), Jishnu Das (World Bank), Philip Setel, Guy Stallworthy, Annika Grever, and Mara Hansen, from BMGF, and Gillian Mann and James McNulty from DFID. / BMGF selected Professor Paul Gertler, a leading impact evaluation expert for public health programmes, to develop a Scope of Work for and then lead the AHME evaluation. BMGF required an evaluator to design a rigorous study that would produce meaningful results in an incredibly complex intervention. BMGF was concerned the complexity of the evaluation would cause significant delays in baseline data collection, threatening the integrity of the evaluation. Professor Gertler’s experience designing complex randomised control trials for interventions in Africa and other parts of the world, and history of execution lead BMGF and DFID to believe he is well positioned to deliver quality results in a timely fashion. Compromising on either the quality of the design or the timing of the evaluation start would threaten the success of the project and the value of the investment, thus threatening the overall investment. / The external evaluation will focus on four questions: / How effective and cost-effective is social franchising compared to the existing private health service delivery system? / Is the cost of delivering the services lower when jointly implemented (i.e. are there economies of scope)? / How much more effective and cost-effective is franchising when combined with demand-side financing interventions? / How effective and cost-effective are AHME’s other supply-side interventions to improve quality (SafeCare and the Medical Credit Fund)? / Effectiveness will be measured quantitatively on the basis of a core set of health outcomes and indicators of disease prevalence. Data will be collected from a household survey and from facility surveys. The household survey will begin with a census of relevant catchment areas using two-week recall to estimate prevalence of disease, prevalence of health services utilization and out of pocket expenditure. The census will collect data on indicators of three conditions: symptomatic persistence of cough (for acute lower respiratory infection), fever (for malaria) and diarrhoea (for gastrointestinal infection) to estimate prevalence of outcomes in the target population, and utilization of clinical health services among the ill. Additionally, the team will collect summary health measures (anthropometrics and anaemia). The study team will conduct a one-month follow-up of children who are symptomatic at time of survey, some of whom will get treatment, to measure the impact of treatment on prognosis of illness. Those who are symptomatic at time of survey will be enrolled in a tracer study, whereby children brought to providers for symptoms will be followed up in one month. Symptom list and duration between initial contact and follow-up will be the same across the survey sample and the provider sample. The study team will undergo two subsequent rounds of follow up to understand the interventions’ impact on outcomes. These are planned to occur at 12 months and 24 months, where the first 12 months will allow for introduction of supply –side interventions and the second 12 months will allow for introduction of demand-side interventions in both the treatment and control groups. Timelines may be adjusted based on implementation. / A qualitative assessment will also be undertaken to address questions of broader health system impact, including impacts on the health worker labour market, health information flows, management structures and programme sustainability. A process evaluation will also be undertaken alongside the qualitative research to understand how and why AHME implementation has adapted over its lifecycle. / A detailed protocol for the study, including qualitative components will be made available prior to AHME programme implementation. / The impact evaluation will remain independent of the AHME programme implementation. Interim findings will be shared with the Evaluation Advisory Panel, but it is not intended that they should be shared with implementing partners, since the purpose is to understand whether the interventions work, why they work and what impact they have on the broader health system. It is intended that any adaptation of programme design should result only from the partners’ monitoring processes and the mid-tem review and not from the findings of the impact evaluation

Communications
African Health Markets for Equity will be profiled on the implementing partners’, the HANSHEP, CHMI and the DFID websites and digital channels (such as Facebook and Twitter). Information will be presented on project activities and progress, including the number of DALYs averted and cost per DALY, number of clients benefitting from demand side financing, and number of new providers in the private provider networks. Any public annual reviews and the results of the evaluation will also be shared.

AHME partners and DFID Advisers will regularly make presentations on or references to AHME at conferences and speaking events. These will include communications to the Social Franchising for Health Community of Practice (organised by the University of California San Francisco), the International Labour Organisation’s Micro-insurance Facility, and the Rockefeller Foundation’s Joint Learning Network. AHME partners will also publish journal articles in open access international peer reviewed journals.

Information on AHME will feature in the Secretary of State and PUSS O’Brien’s speeches, including for the Family Planning Event in July 2012 where a joint announcement of funding with BMGF is a possibility.

Quest No of Results Framework for this intervention: 3501628

An umbrella results framework is currently being designed for the overall HANSHEP programme. The AHME results framework will be nested within the overall HANSHEP results framework.