Business Case (redacted)

Summary Sheet

Title: Dar es Salaam Urban Jobs Programme
Programme Summary:
Programme Value: £10 million		Country/ Region: Tanzania
Programme Code:	Start Date: / February 2018	End Date: / August 2023
Overall programme risk rating:	Moderate
Vault Number:

Intervention Summary

Narrative summary of why UK support needed, what the funds will be spent on, where, over what period of time, via whom and what they will deliver

Dar es Salaam (Dar) is the third fastest-growing city in Africa, and is on track to become a megacity of 10 million people by 2027. However, much of the city’s rapid growth has been ‘jobless growth’. Dar’s unemployment rate is 21.5%, compared to 10.3% nationally, and underemployment rates are much higher. With up to a million young people entering Tanzania’s job market annually, harnessing labour-intensive sectors that can generate jobs for the urban poor is a critical, and growing, challenge. UK support can enhance Dar’s ability to create productive jobs and catalyse economic transformation, while reducing poverty and vulnerability for its inhabitants.

Dar Jobs is a proposed 5-year £10 million urban market systems programme, the purpose of which is to catalyse sustainable change in sectors that have the potential to generate jobs and incomes for thousands of poor people, particularly women and youth. The programme will commence with activities in the manufacturing, waste and childcare sectors. Funds will be disbursed to selected businesses to risk share and test business models that can create economic opportunities for the poor. Funds will also be used to directly fund activities enabling business, local government or civil society organisations to address constraints to development in the target sectors. Dar Jobs will deliver £20 million in additional income for 55,000 beneficiaries through creation of approximately 9,600 additional FTE jobs and increased earnings within existing jobs.

Does the programme fit with DFID’s strategic architecture: the UK Aid Strategy, Single Departmental Plan, International Development Act and the department’s Business Plan?

Dar Jobs is closely aligned with the UK Aid Strategy and Single Departmental Plan’s third strategic objective on promoting global prosperity, which emphasises, “Putting in place the enabling conditions for market development and catalytic investment across key sectors where there is growth potential”. The programme is also in line with DFID’s new Economic Development Strategy, aiming “increase the number and quality of jobs in developing countries, and to enable businesses to grow and prosper”. It supports DFID Tanzania’s Business Plan, which focuses on increasing job opportunities and incomes, particularly for women and young people, including through harnessing the benefits of urbanisation.

What percentage of DFID’s Single Departmental Plan results target does this programme represent? Could the programme be adjusted in scope or scale to deliver SDP results?

The programme will deliver results that support the Single Departmental Plan objective on promoting global prosperity, by generating at least £20 million in net additional income across 55,000 target beneficiaries, through creation of approximately 9,600 additional FTE jobs and increased earnings within existing jobs.

Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy?

The programme is closely aligned with the Government of Tanzania’s Five Year Development Plan 2016/17 – 2020/21 on ‘Nurturing Industrialisation for Economic Transformation and Human Development’, and Integrated Industrial Development Strategy 2025. The programme complements existing international and Tanzanian government investments in areas such as upgrading Dar’s infrastructure, promoting skills development, and deepening access to finance. Using an approach to strengthen market systems, Dar Jobs is designed to ensure lasting change by addressing underlying causes of market failure, and not by replacing the role of market actors; ensuring a sustainable exit strategy.

How does the programme relate to other UK aid within the specific sector, including multilateral, bilateral and centrally managed programmes?

Dar Jobs is a market systems development (private sector) programme. DFID has funded over 40 market systems programmes to a value of approximately £700 million. The majority are bilateral programmes, including a number of agricultural development programmes in Tanzania. Dar Jobs will be DFID’s first urban market systems programme.

The programme will work closely cross-HMG in support of the prosperity agenda, particularly with the Department for International Trade and the Foreign and Commonwealth Office. It will seek to strengthen UK trade and investment opportunities in Dar es Salaam. Dar Jobs will also explore opportunities to access cross-HMG UK International Climate Fund funding through interventions in waste management.

Is there sufficient flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments?

Dar Jobs is specifically designed as an adaptive programme suited to working flexibly in a rapidly changing urban market context. The programme will test different approaches and will generate rapid feedback to inform course corrections and support continual learning and improvement. Explicit contract “break points” built into the programme timeline provide DFID with the flexibility to shift programme direction and scale the programme up or down based on changes in context, programme performance, availability of budget, and need.

Does the proposed level of risk fit with DFID’s risk appetite for this portfolio?

Given Tanzania’s relatively stable economic and political context, DFID has a high appetite to take moderate and major programme risk where it may yield significant developmental returns. As the overall programme risk rating is moderate, it is within DFID’s risk appetite.

Is there a clear communications strategy to reinforce our objectives? Will the programme be branded with the UK aid logo and recognise UK funding?

The Dar Jobs communications strategy will be finalised during the 6 month programme inception phase. It will seek to build buy-in and partnership from key stakeholders, notably government, the private sector, and target beneficiaries, and maximise the impact and visibility of UK support. The programme will be branded with the UK aid logo and will reference UK funding in all relevant communications as appropriate.

Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme?

The programme design has been quality assured by a panel of technical advisers (private sector development; economic; social development; results, evaluation and statistics; and governance), commercial and procurement advisers, and the Head of DFID Tanzania. There is clear political commitment in Tanzania to job creation and economic development. Private sector contractors have market development and job creation skills, and can recruit additional skills from the market as required.

Do the SRO and team have the capability and resources to deliver this programme?

The SRO, Programme Manager and colleagues across DFID Tanzania can leverage their capabilities, knowledge, relationships, and lessons from the wider Tanzania portfolio to deliver the programme.

Strategic Case

Context and need for DFID intervention

Cities are engines of economic growth. 80% of global economic activity is generated in cities.[1] Cities concentrate activity, resources and knowledge; and drive the transformation of economies from agriculture to more productive activities. Cities are also the sites of new job creation. Analysis of 750 cities from 2000 to 2012 found that cities accounted for 58% of new private sector jobs, despite being home to only 25% of private sector employment.[2]
[1] World Bank Group (2013) “Harnessing urbanisation to end poverty and boost prosperity in Africa”
[2] Kilroy et al (2015) “Competitive cities for jobs and growth: what, who, and how”. World Bank Group

Tanzania is urbanising rapidly, but without capturing all the potential benefits. Tanzania is 30% urban and will be 50% urban by 2030. From 2002 to 2012 Dar es Salaam (Dar), Tanzania’s largest city, almost doubled its population from 2.5 to 4.4 million; and the city is on track to become a ‘mega city’ of 10 million by 2027. However, this rapid urbanisation has not been accompanied by inclusive economic transformation.[3]
[3] Economic transformation is the process of moving labour and other resources from lower to higher productivity activities, both between sectors and within sectors (ODI SET). Inclusive economic transformation generates income growth across the income distribution, including for the poor.

Tanzania’s GDP growth has averaged 6% per year over the past decade, however much of this growth has been ‘jobless growth’. High growth sectors such as finance and ICT are not labour intensive or inclusive of the poor. Rapid urbanisation has contributed to economic growth, but has not been accompanied by industrialisation. Dar is a ‘consumption city’.[4] Income from exports of natural resources, such as gold, pay for imports of manufactured goods. Employment is then concentrated in non-tradeable sectors, rather than in the production of tradeable goods or services where there is higher potential for productivity gains and quality jobs.
[4] Gollin et al (2016) "Urbanization with and without industrialization," Journal of Economic Growth

Dar has a dual jobs challenge: it needs to create more jobs, and better jobs. Dar’s unemployment rate is 21.5%, compared to 10.3% nationally, and under-employment rates are much higher. Moreover, women and young people are disproportionately affected. Female unemployment is 32.2%, and youth unemployment is 28.8%. The poor, particularly women and youth, are concentrated in unproductive ‘survival’ self-employment activities. Consistent with the concept of the consumption city, more than half of all enterprises operate in trade. Over 90% of firms are small, young, informal businesses run by self-employed entrepreneurs, with only a 40% rate of survival.[5] Even of those in wage employment, 44.6% are vulnerably employed.[6]
[5] FSDT (2012) “MSME National Baseline Survey Report”, Tanzania
[6] National Bureau of Statistics Tanzania (2014) Tanzania Integrated Labour Force Survey 2014

Dar’s economic potential has not been fully leveraged. Dar plays a critical role in the national economy, contributing 90 percent of all tax revenue.[7] The port positions the city as a key national and regional trading hub. Dar should provide the agglomeration benefits that enable rapid labour productivity gains; creating growth and decent jobs. However, poor infrastructure, land constraints and coordination failures disconnect people, industries, and markets. This weakens the link between urbanisation and productive employment.
[7] World Bank (2015) “Tanzania Economic Update: why should Tanzanians pay taxes?”

Dar risks becoming ‘trapped’ as a consumption city. Cities that produce tradeable goods increase learning and productivity; stimulating further investment, productivity gains, and economic transformation. In contrast, a consumption city may simply grow in size, becoming more costly, without significant increases in living standards and productivity.[8]
[8] Venables (2016) “Breaking into Tradables: urban form and urban function in a developing city”

Rapid GDP growth has also been insufficient to raise living standards for much of Dar’s population. Population growth is placing further pressure on basic services such as water, sanitation, and waste. Over 70% of residents live in unplanned settlements, and the proportion of households with access to safe water is declining.[9] Moreover, there is a sharp gender dynamic – given women’s primary responsibility for household work, basic service deficits disproportionately reduce their time for productive activities.
[9] Fox (2016) “Gender, Economic Transformation, Women’s Economic Empowerment in Tanzania”

Harnessing labour-intensive sectors that can generate jobs for the urban poor is a growing challenge. Half of Tanzania’s population is under 15. The labour force is expected to double over the next 20 years; with up to a million new job seekers entering the job market annually. Dar has experienced a reduction in poverty from 14.1% in 2007 to 4% in 2012.[10] However, these gains are under threat if job creation cannot keep pace with Dar’s expanding population. This is essential if Tanzania is to take advantage of a demographic dividend and avoid the risks associated with high under-employment.
[10] World Bank (2015) “Tanzania Mainland Poverty Assessment: Main Report”

Tanzania’s urban transition represents both a critical challenge and a major opportunity. Urbanisation offers strong prospects for growth, productive jobs and poverty reduction. It also poses risks in terms of public health, crime, vulnerable work, environmental degradation, and instability. For example, Dar has the highest and fastest growing crime rates in Tanzania[11] and The economic structure that develops in Dar as it rises to megacity status will also determine Tanzania’s overall development trajectory. There is an opportunity to enhance Dar’s role in creating productive jobs and catalysing economic transformation, while reducing poverty and vulnerability for its inhabitants.
[11] National Bureau of Statistics Tanzania (2015) Crime Statistics Report

Rationale for DFID intervention

There is a clear need for more inclusive, job-creating growth in Dar. Job creation relies on the removal of constraints that prevent productive firms from growing. In the Dar context, these include: lack of access to affordable finance and business services; skills gaps; lack of access to technology; high transport costs; lack of access to commercial land; and an unsupportive business environment, particularly for micro, small and medium enterprises (MSMEs).[12] Addressing systemic constraints in these areas can enable dynamic firms in labour-intensive sectors to expand and create more and better jobs.
[12] Mnenwa (2009) “Institutional Framework for Promoting the Growth of MSEs in Dar”

The intervention addresses a gap. Existing support to livelihoods and economic development in Tanzania is mainly targeted towards rural areas. The limited focus on Dar overlooks the role that the city can play in catalysing economic opportunities across the country; and the specific character of urban poverty which, beyond income measures, involves high vulnerability to a range of risks. Although there are a number of skills programmes in operation,[13] there is more limited focus on addressing barriers to labour demand. This programme could be a test case for other cities in Tanzania and beyond.
[13] E.g. Pathways to Work, Youth Employment Initiative DSM, Youth Economic Empowerment programme, ILO and UNIDO interventions, forthcoming World Bank skills programme

Dar Jobs complements a number of other DFID programmes in Tanzania, including:
- Trade: investments to improve the capacity and efficiency of the Dar Port; promote road and rail investment; and support municipal infrastructure PPPs.
- Youth and women: learning from this programme will inform DFID Tanzania’s understanding of the challenges women and young people face to participate in the economy, and this will be reflected in programming to empower youth and women.
- Governance: collaborating with the Institutions for Inclusive Development programme and the Accountabilty in Tanzania 2 Programme on urban collective action and governance challenges, as well as political economy research.
The programme fits with the DFID Tanzania Economic Development Strategy , which includes a focus on supporting the public and private sectors to maximise the transformational potential of key urban sectors, particularly industrial sectors, and those where there are opportunities for young people and particularly young women..

There are costs to doing nothing. The negative impacts of unemployment are well evidenced;[14] while employment opportunities, particularly for youth,[15] promote stability. Given Tanzania’s ‘youth bulge’, a failure to catalyse job creation will increase the risk of insecurity and impede human development. Intervention now, before Dar reaches megacity status, presents an opportunity for DFID to support a more sustainable trajectory.
[14] For example, Filmer & Fox (2014) “Youth Employment in Sub-Saharan Africa” World Bank
[15] Blattman & Ralston (2015) “Generating Employment in Poor and Fragile States”

Evidence for the intervention

Jobs boost living standards, raise productivity, and foster social cohesion. Jobs are also the principal route out of poverty.[16] However, not all jobs are equal. In Tanzania, working poverty and underemployment are prevalent; as is vulnerable work without basic rights. Different types of jobs can also generate positive or negative spillovers. There is therefore a need to focus both on creating more jobs, and creating better quality jobs.
[16] World Bank (2012) “World Development Report 2013: Jobs”

The creation and expansion of small businesses are key to job growth.[17] Evidence from Tanzania suggests that 89% of new jobs from 2002 – 2012 were created by MSMEs in the non-agricultural private sector. This underscores the importance of small and informal firms to employment. Moreover, most labour productivity growth came from a small subset of firms. Accelerating employment growth in these firms has the potential to increase productivity by 1.3 percentage points.[18] By addressing productivity constraints, Dar Jobs can enable firms in key sectors to expand and create more and better jobs.
[17] IFC (2013) IFC Jobs Study
[18] Kweka et al (2016) “Economic Transformation in Africa from the Bottom Up”

Labour demand interventions are likely to be more cost effective than labour supply interventions. DFID’s Jobs Evidence Review finds that standalone skills training programmes offer poor value for money. It may therefore be more effective to address constraints that prevent productive firms from growing. At the same time, skills gaps cannot be ignored. Dar Jobs can integrate a focus on on-the-job training and management practices in its support to firms to improve the retention and sustainability of jobs created.

Under the right conditions, through harnessing agglomeration, cities generate large-scale, productive employment.[19] However, as outlined above, a number of constraints obstruct this process in Dar. Addressing these constraints through actions across four key areas could transform Dar’s firms into vectors of employment creation: build owners’ assets; improve connectivity; reduce regulatory burden; and achieve economies of scale.[20]
[19] Miller (2014) “What are the features of urbanisation and cities that promote productivity”
[20] World Bank (2014) “Country Economic Memorandum Tanzania: Productive Jobs Wanted”

Based on DFID experience,[21] a market systems approach is best suited to tackling challenges that require intervention at multiple levels with different actors. A key strength of the approach is the ability to use financial tools and tactics – such as grants, loans, cost shares and risk guarantees – and non-financial tools and tactics – such as technical assistance, research, disseminating ideas, and facilitating coordination.[22]
[21] DFID funds approximately 40 market systems programmes, to a value of over £700m
[22] Davies (2016) “Getting to Scale: Lessons in reaching scale in Private Sector Development”

The approach is suited to delivering lasting impact through the following key principles:
- Thinking and acting systemically: recognising that Dar is a complex, and adaptive system; and therefore intervening at multiple levels with different actors;
- Achieving inclusive impact: addressing market failures to deliver benefits for the poor as workers or consumers, in particular for women and youth;
- Ensuring sustainability: by addressing the underlying causes – rather than the symptoms – of market failure; and by not replacing the role of the private sector;
- Delivering impact at scale: by targeting constraints that affect large numbers of businesses or people; or delivering interventions that can be replicated at scale;
- Learning and adapting: responding to the complexity of urban markets through active testing, learning, and adjusting tactics in response to feedback.
- Think and working politically: by investing in on-going political economy analysis and stakeholder engagement to navigate the complexities of Dar’s evolving and contested local governance and administration, involving five municipal councils, the Dar City Council, District Commissioners and the Regional Commissioner.

What will DFID support achieve?

The purpose of the Dar Jobs programme is to catalyse sustainable change in sectors that have the potential to create employment and increase incomes for thousands of poor people, particularly women and youth. Responding to the challenges outlined above, Dar Jobs will commence with interventions in the light manufacturing, waste and childcare sectors,[23] with the flexibility to modify this portfolio during implementation.
[23] The process used to determine the opening sector portfolio is detailed in the Appraisal Case

Light manufacturing will support Dar’s shift towards a more ‘productive city’; stimulating investment, productivity gains, and economic transformation. Waste management has strong links to manufacturing, can absorb low skilled workers, and is a vital service required for sustainable urban development. A better functioning childcare services market will generate higher incomes for large numbers of women, and address a barrier to female labour force participation. Intervening in these sectors will increase incomes for the poor; while promoting economic transformation and addressing key public service deficits.

The impact of the programme will be increases in the incomes of approximately 55,500 target beneficiaries[24] associated with increased productive employment, totalling approximately £20 million in cumulative additional income. Impact will be measured in terms of the number of target beneficiaries experiencing net attributable income change (NAIC). NAIC must take people above the living wage or equal at least 25% of annual income. Target beneficiaries will be disaggregated by gender and age profile.
[24] Target beneficiaries are defined as women and men, particularly youth, earning less than living wage. The living wage is the greater of the national minimum wage and the wage required to take the worker plus the average number of dependents above the $1.25 PPP poverty line (DFID HTN)

The outcome of the programme will be a net increase of approximately 9,600 Full Time Equivalent (FTE) productive jobs among target beneficiaries and improved quality of existing jobs, measured by a change in the earnings of existing workers associated with improved enterprise performance or new enterprise entry in the target and linked sectors.

How will the programme achieve its aims?

As a five-year urban market systems programme, Dar Jobs will design and implement interventions to address constraints in the target sectors – light manufacturing, childcare, and waste. For example, Dar Jobs will work with clusters of light manufacturing firms, and could fund advisers to support business service and technology providers to develop commercial products and services that are tailored to the needs of target manufacturing firms, such as equipment leasing, or financial loan facilities. Dar Jobs could share the costs with these intermediaries of marketing the new products and services. The programme could also provide subsidies for initial adoption by lead firms, encouraging the diffusion of technologies that increase competitiveness. It will link businesses to private or public investors, such as local banks or the African Development Bank. Dar Jobs could also provide technical support within firm clusters to improve collective planning and decision making; for example by supporting firms to structure shared access to infrastructure and services; by brokering linkages to enable small firms to collectively service large contracts; or by improving dialogue and advocacy with local government to address key challenges.

As DFID’s first urban market systems programme, Dar Jobs will take an adaptive management approach that emphasises experimentation, flexibility, and continual learning and improvement. Urban markets are complex, adaptive systems where all outcomes are not predictable in advance. Dar Jobs will therefore test different approaches and will generate rapid feedback and measurement of results to inform tactical adjustments and scale up successful approaches. To support this, the programme will invest in continuous political economy analysis and stakeholder engagement to navigate key structures and dynamics, including the complexities of Dar local governance; and the business-political settlement under President Magufuli, particularly in the target sectors. Lessons from the programme could be applied in Dar and other urban contexts.

Gender Equality Act

Dar Jobs is compliant with the Gender Equality Act. The programme understands that structural change does not work the same for everyone: some win, some lose and some benefit more than others. If ignored, underlying inequalities reproduce themselves and economic transformation becomes exclusive to some groups. Dar Jobs will prioritise understanding the differences and dynamics in how women, men and different demographic groups are able to take advantage of market opportunities. The focus will be on supporting women to access new and improved income generation opportunities, as evidence demonstrates women are disproportionately excluded from employment.

First and foremost, a commitment to do no harm (DNH) seeks to ensure that the programme does not privilege certain groups over others; increase drivers of conflict, including gender based violence; facilitate child labour; deepen existing inequalities; or reinforce harmful or discriminatory practices — all of which are considerable challenges requiring close monitoring and mitigation measures where appropriate. DNH is closely linked to considerations of decent work, and is itself alone a challenge in sectors such as waste which are known for creating poor quality jobs. Where possible, Dar Jobs will also endeavour to ‘level the playing field’ for women. Dar Jobs’ Gender and Social Inclusion (GESI) objectives are to: i) improve the ability of women and youth to access assets and services; ii) reduce the extent to which women and youth are disadvantaged by rules and norms; iii) improve women and youth’s market position; iv) increase women and youth’s access to and control over income; and v) reduce women and girls’ unpaid work burden.

As Dar Jobs will take an adaptive management approach, gender analysis will be mainstreamed throughout the programme design and delivery process to ensure that the programme actively supports job creation for women. Inclusion of women (and youth) was prioritised when selecting target sectors and, prior to approval, all interventions will be required to specify how they uphold DNH and contribute to gender equality and equity objectives. Sex disaggregation is integrated in monitoring and learning, and key risks are managed through the risk matrix. Dar Jobs will also go beyond indicator disaggregation; and will use qualitative and participatory assessments to analyse changes in empowerment and social norms.[25] Dar Jobs will consult women (and youth) as programme constituents throughout design and delivery. All staff will be held accountable for integrating gender analysis into the programme through key performance indicators, and two long-term advisers will provide guidance to the team on mainstreaming GESI. Finally, the supplier’s payment is partly contingent on full integration of GESI considerations.
[25] Jordan (2016) “Measuring Gendered Impact in Private Sector Development.”

Appraisal Case

What are the feasible options that address the need set out in the Strategic case?

A scoping study (June 2015) concluded that a market development programme would address the need set out in the strategic case. A programme to tackle only demand or supply side constraints, or only regulatory obstacles, would be unable to address the wide range of constraints necessary to increase employment in a way the market would sustain. Such a limited programme is not considered a feasible option.

The feasible options therefore relate to which sectors a market development programme should focus on. A scoring methodology was used to assess a longlist of ten sectors on job and income creation potential, other benefits, and feasibility. A break even analysis was then conducted to identify the number of jobs that would need to be created for the programme to break even on its investment. The shortlist was refined to eliminate sectors where these targets were unlikely to be achieved. The final shortlist was used to generate sector portfolio options, which were compared to a do nothing option.

Sector analysis and scoring

In identifying feasible options, the first step was to analyse sectors with the potential to increase employment and incomes in Dar. Following stakeholder consultation and detailed review of secondary research, a longlist of ten sectors was compiled. These were:

Agro-processing	Childcare
Construction	Hospitality
ICT	Light manufacturing
Retail and wholesale trade	Transport and logistics
Water and sanitation	Waste management

A sector scoring methodology was devised, with scoring criteria as per the table below. A number of criteria (growth potential, pro-poor impact, competitiveness, and feasibility) were assigned minimum scoring thresholds. A mix of quantitative and qualitative appraisal methods[26] was used to score the sectors according to each criterion.
[26] This included primary data collection; stakeholder interviews; and review of secondary research. A survey was conducted in Tabata and Temeke Veterinary with owners and workers of 61 MSMEs.

Criteria	Sub-criteria
Competitiveness	Comparative advantage
Growth potential	Sector size in 10 years ($m)
	Sector growth rate
Pro-poor impact	Pro-poor outreach
	Pro-poor jobs / income potential
Development priorities	Alignment with DFID and GoT priorities
Contribution to economic transformation	Sector linkages
	Potential to leverage capabilities
	Degree of value added
Broader developmental impact	Inclusion of young people
	Inclusion of women
	Contribution to urban development
	Human development impact
	Environmental impact
Feasibility	Political economy
	Exogenous threats (e.g. change in oil price)
	Implementation complexity
	Timeframe

For each sector, a 5-10 page analytical report and a summary ‘scorecard’ were produced. Based on the sector analysis and aggregate scoring, sectors were shortlisted or excluded as per the following table, which provides a summary of the rationale:

Shortlisted sectors	Rationale
Childcare	High outreach to poor women, human development impact, fills public service deficit
Hospitality	Inclusion of women and youth, relatively high pro-poor outreach, consumption city.
ICT	Some job creation potential, competitiveness, enabler of growth in other sectors.
Light manufacturing	Potential to create high value jobs, youth inclusion, feasibility, contribution to economic transformation, linkages to other sectors.
Retail	Very high pro-poor outreach, inclusion of youth and women, low barriers to entry.
Waste management	Low barriers to unskilled workers, urban development impact, fiscal impact.
Excluded sectors	Rationale
Agro-processing	Potential duplication due to DFID’s existing large portfolio in the sector.
Construction	Feasibility issues as a result of political economy factors, poor inclusion of women.
Transport and logistics	Feasibility issues as a result of political economy factors, implementation complexity (cost and timeframes), poor inclusion of women.
Water and sanitation	Feasibility issues as a result of political economy factors, implementation complexity due to infrastructure deficit, weak sustainability, potential reputational risk.

As well as generating jobs and incomes, sectors were assessed in terms of their potential to address other key challenges facing Dar: 1) public service deficits, 2) low productivity in non-tradeable sectors, 3) limited economic transformation, and 4) limited opportunities for women and youth. A further screening looked at the linkages and cross-cutting constraints between sectors to enable interventions that exploit synergies and economies of scale.

Break Even Analysis

In addition, a quantitative break-even analysis was conducted to determine the minimum number of additional jobs that would need to be created by interventions in a given sector to break even on the programme’s £10m investment. This analysis was not intended to project the total number of jobs that the programme could create in each sector; but to enable an assessment of the relative feasibility of achieving break-even point across different sectors. The main assumptions were:[27]
[27] See full break-even analysis document for all calculations and data sources

- The main benefit of programme interventions is the value of a job, captured by the proxy of Gross Value Added (GVA) per employee in a particular sector.
- GVA provides a monetary value for the goods and services that have been produced, minus the cost of all inputs that are attributable to that production.
- The justification for using GVA is that as a metric it captures the benefits that accrue both to employees and to employers within the same sector.
- For the programme to break even in cost benefit terms, the GVA per employee multiplied by the number of jobs created should equal the programme investment.
- GVA per employee in a sector was calculated using the GVA shares of different sectors, and employment levels in that sector, for Tanzania.
- For costs, DFID’s £10m programme investment, DFID’s £300k programme management costs,[28] and partner firm investment were used. The latter was estimated with benchmarking from Business Cases of previous DFID programmes.
  [28] 0.25 FTE of a PSD Adviser, 0.2 FTE of a Programme Manager and 0.05 FTE of a Team Leader
- A discount rate of 10% was used.
- It was assumed that no jobs would be created in year 1, and the number of jobs would increase 20% each year during the benefits duration.
- 7 years of benefits duration was assumed (5 years of implementation programming, and a further 2 years), in line with Donor Committee on Enterprise Development (DCED) Standard guidance, which assumes that benefits from market development programmes will continue to accrue after interventions end.
- Net[29] additional jobs created includes direct, indirect and induced jobs.
  [29] Because there may also be some losses, these will be tracked and accounted for by the programme’s monitoring and evaluation system.

Results of this break-even analysis for the six shortlisted sectors, compared to the current level of employment in the sector, are as follows:

Sector	Number of total additional jobs to break even	Current level of employment in the sector in Dar[30]
Hospitality	12,243	242,662
Retail	4,419	648,787
Childcare	2,687	45,000*
Waste	1,971	5,750**
Manufacturing	1,941	156,957
ICT	99	18,646
[30] National Bureau of Statistics Tanzania (2014) Tanzania Integrated Labour Force Survey 2014

* ILFS data not available, estimate from childcare sector review
** Waste sector review estimate drawing on ILFS data as well as other sources

These numbers represent the minimum number of additional jobs that would need to be created by the programme in order to break even on a £10m investment in each sector.

An assessment of the relative feasibility of achieving these thresholds was then carried out, based on the findings of the sector analyses and lessons from other programmes. Of all sectors reviewed, hospitality and retail present the greatest hurdle to break even on programme investment through jobs created. Evidence from DFID programmes elsewhere also points to the challenges to sustainable job creation in wholesale and retail trade. In the Dar context, the retail sector is characterised by survival entrepreneurs with little ability to grow or employ more people, high rates of displacement, and low rates of business survival.[31] Turnover and margins are very low with limited scope for productive intervention to increase incomes. Furthermore, hospitality and wholesale and retail trade services have shown weak performances recently, based on quarterly GDP data.[32] On the other hand, the break-even point for the ICT sector is very low, given the sector’s very high value added. However, jobs in ICT are unlikely to be inclusive of the poor. ICT is an enabler of growth and employment in other sectors; rather than a significant direct employer itself.
[31] See, for example, FSDT (2012) “MSME National Baseline Survey Report”, Tanzania
[32] Second quarter (2016) GDP data, available on www.nbs.go.tz

Three sectors score highly on both the sector analysis and the feasibility screening based on quantitative break-even analysis; and therefore are viable options for an opening sector portfolio: light manufacturing, childcare, and waste.

A variation on the above calculation was undertaken, by doubling partner firm costs. This analysis shows that the job numbers required to break even do not change significantly: for example for light manufacturing 2,030 jobs are needed rather than 1,941 in the original scenario, which still presents a feasible job target, considering the employment levels presented above and strong sector growth rate. Generating a slightly higher total of 2,240 jobs in the sector would produce a Benefit to Cost Ratio (BCR) of 1.14 and Internal Rate of Return (IRR) of 15%, which represents good value for money.[33]
[33] As a BCR above 1 and IRR above the discount rate (10%) mean positive economic returns.

The key characteristics of the three sectors are set out below.

Light manufacturing: Light manufacturing has strong potential as a vehicle for economic transformation and productive job creation in Dar. From a low base, there is emerging evidence of growth in the sector due to increasing demand for manufactured products linked to the growing population and middle class.[34] Nationally, real manufacturing value added has grown 7.5% annually from 2005-2015, doubling production.[35] Furthermore, evidence suggests that this is mainly attributable to growth in MSMEs, thus maximising employment impacts.[36] According to the most recent national statistics, 156,957 people are employed in the manufacturing sector in Dar.[37] Based on the sector analysis, a number of manufacturing sub-sectors demonstrate growth and employment potential in the Dar context: food processing, metal products, furniture, building materials, and packaging. According to primary and secondary research, the constraints impeding sector competitiveness are: availability and cost of inputs; access to industrial land; finance; technical and managerial capabilities; skills; and logistics.[38]
[34] Page (2016) “Industry in Tanzania, performance, prospects and public policy”, WIDER
[35] ODI SET (2016) “Supporting the preparation of Tanzania’s second FYDP 2016/17 – 2020/21”
[36] Kweka et al (2016) “Economic Transformation in Africa from the Bottom Up”
[37] National Bureau of Statistics Tanzania (2014) Tanzania Integrated Labour Force Survey 2014
[38] World Bank (2014) “Light Manufacturing in Tanzania: Agenda for Job Creation and Prosperity”

Dar Jobs could intervene with geographically concentrated informal ‘clusters’ of light manufacturing firms in Dar’s urban areas such as Gerezani, Keko and Tabata to promote enterprise growth and job creation. This would involve facilitating improved coordination and commercialisation (e.g. marketing) within a cluster; dissemination of innovation; and improved access to finance, technology, and business support services. The programme could facilitate linkages to enable small firms to supply to larger firms (see box).
There are a number of benefits to intervening in the light manufacturing sector:
Connecting light manufacturing SMEs to large firms
Large conglomerates in Dar, such as Bakhresa and Sumaria, report that the majority of the basic manufactured products that they procure are imported. However, they also report positive experiences using local suppliers in Dar’s light manufacturing clusters, and state that they could increase the volume of products procured locally if domestic firms were able to upgrade their technical processes and improve management. There is an opportunity to create jobs through strengthening linkages between Dar’s light manufacturing SMEs and larger firms.

Market development approaches have been successfully used by the IFC in Mozambique (Mozlink) and Chevron in Nigeria (PIND) to grow the domestic SME sector by improving linkages between small and large firms. Interventions include: (i) Quantifying large company procurement volumes and requirements, and securing commitments from firms to procure locally if given standards can be met; (ii) Subsidies which buy down the initial cost for SMEs to participate.

- Alignment with GoT priorities: Support to manufacturing is strongly aligned with GoT’s Five Year Development Plan 2016/17 – 2020/21, the theme of which is ‘Nurturing Industrialisation for Economic Transformation and Human Development’.
- Leveraging agglomeration: Spatial concentration provides opportunities for economies of scale and ‘crowding in’ on successful innovations. Based on primary and secondary research cooperation, sharing, and matching in these clusters is currently limited.[39] Dar Jobs could help to increase these benefits.
  [39] Jaap (2016) “Enabling Innovation and Productivity Growth in Manufacturing SMEs: Tanzania”
- Contribution to economic transformation: Support to light manufacturing sub-sectors can demonstrate pathways to higher productivity and diversification into higher value products, stimulating further investment and productivity gains.
- Opportunities for UK business: Interventions in the manufacturing sector have the potential to generate opportunities for UK business through joint or direct investment, sale of equipment; and provision of financial or consultancy services.
- Replicability: interventions that are piloted and successfully scaled up can be replicated in light industry elsewhere, particularly in Tanzania’s secondary cities.
- Sector linkages: Dar Jobs could generate benefits in linked sectors where high numbers of poor people are engaged. The sub-sectors identified have strong linkages to sectors such as wholesale and retail trade, construction, agro-processing and waste, and the programme will seek to exploit these linkages.

Waste: Waste management is a critical challenge facing Dar. Only 37% of waste is currently collected, and only 35% of collected material is recycled.[40] In the city’s unplanned settlements waste is generally either burnt or dumped, creating significant environmental and public health risks. Given Dar’s large and rapidly expanding population and poor public waste management there is high demand for services and a large supply of waste with value that is currently not captured. The sector presents low barriers to entry and can create employment for the low-skilled poor. An estimated 5,750 people are currently engaged in the sector,[41] although this figure is likely to underestimate the number of informal collectors. According to the sector analysis, constraints include transport logistics; land; cost of machinery; poor coordination; and a weak policy and regulatory environment.
[40] Waste sector analysis report produced as part of Business Case development
[41] ibid

Dar Jobs could work with waste processing and recycling companies to share the risk of expanding into new business models, enabling them to buy more waste from informal waste collectors; and enable these collectors to aggregate their waste more effectively. The programme could also make links to industry, to increase the sources of raw materials. Intervention in the sector could increase incomes for informal waste collectors; and bring more productive employment in waste recycling centres.

Beyond creating jobs and increasing incomes, secondary benefits to intervening in the waste sector include:
- Strengthening local governance: Intervening could support the role of municipal and district authorities in managing a complex challenge involving a range of stakeholders and improving service delivery.
- Mitigating public health and environmental risk: Mismanagement of waste exacerbates public health risks such as cholera and malaria; as well as environmental risks such as flooding and groundwater contamination.
- Linkages to light manufacturing: The waste sorting and processed recyclables segments have strong linkages to light manufacturing. Recycled materials open up new sources of inputs for the light manufacturing industry.[42]
  [42] For example, Kamal Group buys scrap metal to produce steel

Childcare: Consumer demand for childcare services is increasing rapidly in Dar due to population growth, rising per capita income and changing household structures. A spectrum of models exist: from unpaid care; to domestic staff engaged in childcare; to owner-operator informal providers; to established daycare centres and pre-schools operating with varying degrees of formality. An estimated 45,000 people (almost all women; mostly low skilled) are currently engaged in the sector,[43] and there is potential to increase incomes and improve the quality of existing jobs. Constraints include skills; an unsupportive policy and regulatory environment; and finance.
[43] Childcare sector analysis report produced as part of Business Case development

Dar Jobs could provide technical assistance or capital to support existing childcare businesses to expand; and support the piloting and development of low-cost micro-franchise models in informal settlements. The programme could share the risk of new models integrating childcare services attached to employers or workplaces; and work with regulatory bodies to improve the enabling environment for the sector.

Beyond creating jobs and increasing incomes, secondary benefits to intervening in the childcare sector include:
- Women’s economic empowerment: Affordable childcare services increase female labour force participation, expand employment choices, and reduce women’s unpaid care work burden.[44]
  [44] BEAM (2016) “Market Systems Approaches to Enabling WEE Through Addressing Unpaid Care”
- Contribution to human development: There is strong evidence regarding the benefits of (quality) early childhood education to human development outcomes.
- Addressing public service deficits: public pre-primary education cannot meet high demand[45] and does not cover early years. DFID can draw on lessons from other programmes applying market-based solutions in pro-social sectors: e.g. the Developing Effective Private Education Nigeria (DEEPEN) programme in Lagos.
  [45] It is estimated that government pre-primary schools serve only 7% of need

Options

Based on the sector selection process, the following three options have been identified:

Option 1: Do nothing more.
Option 2: Portfolio focused on the light manufacturing sector (multiple sub-sectors).
Option 3: Mixed portfolio across three sectors (light manufacturing, waste, childcare).

Option 1: Do nothing more

This option entails DFID investing no additional funding beyond its current portfolio of relevant programming in Tanzania. This option does not represent any costs or benefits to DFID. The option is characterised by continued unemployment and underemployment, particularly for women and youth, in Dar. It is expected to have consequences such as: rising crime and social unrest; decreased or foregone lifetime earnings; lower tax revenue; higher GoT costs associated with social protection; weaker human development outcomes; and lower aggregate demand. In the Middle East and North Africa the cost of unemployment is estimated at $40–50 billion annually, 3% of the region’s GDP.[46]
[46] IEG (2012) “Youth Employment Programs: An Evaluation of World Bank and IFC Support”

In the absence of the proposed programme, there would be no interventions aimed at addressing inefficiencies and promoting labour demand in the target sectors in Dar. This option is therefore not considered further, and the remainder of the Appraisal Case assesses options 2 and 3.

Option 2: Portfolio focused on the light manufacturing sector

Under Option 2, programme resources would be invested in light manufacturing sub-sectors, such as food manufacturing, fabricated metal products, furniture, building materials, and packaging. This would enable the programme to focus all resources on promoting more and better jobs through higher productivity in light manufacturing. Sector analysis demonstrates strong linkages from light manufacturing sub-sectors to sectors such as construction, retail and agribusiness. Under this option Dar Jobs would leverage these linkages to extend the outreach and impact of interventions. Light manufacturing enterprises tend to be clustered in certain areas of the city. This proximity presents opportunities for Dar Jobs to support rapid scaling up of interventions and economies of scale, and to focus programme attention and resources.

Costs: The total programme budget is £10 million, inclusive of the cost of sector scoping and Business Case development. DFID management costs over the programme lifetime are estimated at £300k from the Frontline Admin budget.[47] Therefore, total programme costs are £10.3 million. The break-even analysis also includes estimated partner firm investment. An indicative profiling of costs is presented in the Financial Case, below.
[47] 0.25 FTE of a PSD Adviser, 0.2 FTE of a Programme Manager and 0.05 FTE of a Team Leader

Benefits: From a job creation perspective, using the break-even calculation with resources solely allocated to light manufacturing, the programme would need to create a minimum of 1,941 FTE jobs to break even under this option. This is a minimum threshold to break even on the programme’s investment. Based on existing evidence[48] and sector outlook (see above) it is likely that programme interventions in light manufacturing would achieve this break even target. Interventions are likely to create jobs through three channels:
[48] See, for example McKenzie (2015) “Identifying and Spurring High-Growth Entrepreneurship” and Dalberg & J.P Morgan (2015) Evaluation of the Catalyst for Growth Initiative in South Africa.

- By increasing productivity and growth in existing enterprises: Supporting increased enterprise profitability and scaling up of operations.
- By encouraging new market entrants: Enabling new entrepreneurs and encouraging replication of profitable business models.
- By increasing enterprise survival rates: Reducing the number of potentially viable enterprises that close as a result of market failures.

Option 3: Mixed portfolio across light manufacturing, waste and childcare

This is the preferred option. Under Option 3, programme resources would be allocated across the three selected sectors – light manufacturing, waste and childcare. This option would enable Dar Jobs to promote economic transformation and address other key constraints related to public service deficits and women’s economic empowerment. This option diversifies programme risk and allows for a broad intervention portfolio. Using an adaptive and experimental approach Dar Jobs would test different strategies and scale up those that are successful. This option offers the flexibility to shift the balance of the portfolio, relying on established relationships and knowledge across the three sectors.

A significant share of programme resources will continue to be allocated towards light manufacturing, which will be critical towards shifting the structure of the Dar economy towards higher productivity activities. Interventions in waste management and childcare will generate increased jobs and incomes for the poor in these sectors; while also generating broader social benefits such as reduced environmental and health risk and early childhood development. Intervention in the childcare sector will help to address a barrier to female labour force participation and women’s economic empowerment. This option will require investment in understanding social norms and perceptions particularly in waste management and childcare, including through consultation with target beneficiaries.

Costs: This option would use the same resource envelope as Option 2 above.

Benefits: From a job creation perspective, assuming 50% of programme resources are allocated to the light manufacturing sector and the remaining 50% to the childcare and waste sectors (25% each), under this option the programme would need to create a minimum of 2,132[49] FTE jobs to break even on investment. Again, this is a very minimum threshold to break even. It is likely that the programme would surpass this threshold. Other benefits are discussed below.
[49] 985 FTE jobs for light manufacturing, 657 FTE jobs for childcare, and 490 FTE jobs for waste

Comparison of the options

The comparison of Options 2 and 3 and the rationale for Option 3 is as follows.

Projection: In order to provide a projection of programme outreach, a number of DFID-funded market systems programmes were benchmarked in terms of budget, cumulative NAIC, cost per beneficiary, and total outreach. Based on this benchmarking and use of living wage, poverty line and minimum wage data for Tanzania, it is projected that Dar Jobs can generate a minimum of £20 million in net additional income across 55,000 target beneficiaries, through creation of approximately 9,600 additional FTE jobs (both formal and informal) and increased earnings within existing jobs.[50][51]
[50] It should be noted that the break-even analysis uses GVA as a proxy for the value of an FTE job; whereas the benchmarking analysis uses actual FTE cost. Therefore they are not directly relatable.
[51] During the inception phase, analysis will be done of employees in non-benefitting enterprises / areas to establish counterfactuals, and to understand the net real terms change.

A sensitivity analysis was also conducted to project the potential impact of interventions in the light manufacturing sector on FTE job creation using low, base and high case scenarios. The light manufacturing sector is used for this analysis because reliable enterprise data is not available for Dar for the waste and childcare sectors. The outreach numbers are calculated as a percentage of the estimated 7,443 manufacturing enterprises in Dar.[52] Of these 7,443 enterprises, 7,055 have just 1-9 workers.
[52] NBS & MITI (2016) “The 2013 Census of Industrial Production: Analytical Report”

	Low	Base	High
Outreach / Total enterprise population / Percentage programme outreach / Total programme outreach (enterprises)
	7443	7443	7443
	20%	40%	60%
	1489	2977	4466
Existing enterprise growth effect[53] / No. of new jobs per beneficiary enterprise / Total new jobs created from enterprise growth
	0.5	1	1.5
	744	2977	6699
New market entrants effect / Attributable increase in enterprise population / Attributable no. of new market entrants / Average number of employees per enterprise / Total new jobs created by new entrants
	5%	7%	10%
	372	521	744
	4	4	4
	1489	2084	2977
Increased survival rates effect / Without project enterprise failure rate (% over project) / With project enterprise failure rate (% over project) / Attributable increase in number of surviving enterprises / Employees per enterprise / Total jobs created through increased survival rates
	20%	20%	20%
	17%	15%	12%
	223	372	595
	4	4	4
	893	1489	2382

Total direct jobs created	3,126	6,550	12,058
Total indirect jobs created	625	1,310	2,142
Total jobs created	3,751	7,860	14,469
[53] Based on evidence from C4G programme evaluation of 1 job created per beneficiary as a result of improved access to BDS

Feasibility: There is no significant difference between Options 2 and 3 in terms of the total number of jobs required to break even (1,941 and 2,132 respectively). Comparing the two Options in terms of effectiveness in achieving the outreach figures above, it is expected that Option 2 has potential to generate higher total cumulative NAIC than Option 3. There is greater scope for increasing the productivity of existing manufacturing enterprises than waste and childcare enterprises. Moreover, through strong linkages to other sectors as presented in the diagram above, productive sectors can be expected to deliver both direct and indirect results in increasing incomes and creating employment.

Broader benefits: Despite the potential for higher total cumulative NAIC under Option 2, this option demonstrates weak inclusion of women. Sector scoping suggests the vast majority of cumulative NAIC generated in light manufacture would accrue to men. Moreover, Option 2 presents few broader benefits; whereas Option 3 is likely to generate benefits associated with addressing public service deficits, addressing urban challenges associated with rapid and unplanned growth, and promoting women’s economic empowerment. Option 3 is therefore the preferred option.

The following table provides a summary comparison of the two Options:

	Option 2	Option 3
Increased jobs and incomes	Expected to generate higher total cumulative NAIC than Option 3 given higher productivity in light manufacturing and sector linkages. However, incomes likely to largely accrue to men.	Expected to generate lower total NAIC than Option 2; however expected to generate more equitable and inclusive total NAIC. Childcare sector is likely to generate increased incomes for poor women; and waste sector for the low-skilled.
Broader development impact	Not expected to generate wider benefits beyond the light manufacturing target sub-sectors or linked sectors.	Expected to generate wider benefits related to improved early childhood development; reduced environmental and health risk; sustainable urban development; and women’s economic empowerment.
Risk and uncertainty	Focus on just one sector may concentrate risk, however mitigated to some extent through multiple sub-sectors. GoT strong support for industrialisation.	Diversified risk through a mixed portfolio. However, experimentation is expected to be higher; and waste and childcare more reliant on GoT support. Higher reputational risk in the childcare sector.
Feasibility	Clustering of light manufacturing enterprises presents opportunities to deliver economies of scale. Dar Jobs can also build on evidence from established cluster development models in Tanzania and the region.[54]	Waste services and childcare enterprises are relatively more dispersed, with knock-on effects for the diffusion of innovation. Potential to scale up successful interventions in Dar and elsewhere in waste management. In contrast, implementation experience in the childcare sector is relatively limited.
Potential to generate learning	Likely to produce valuable learning for DFID future programming in manufacturing, as well as informing GoT implementation of its second Five Year Development Plan on industrialisation.	In addition to learning from manufacturing, Option 3 can produce learning in sectors that are less tested, and thereby generate greater value for DFID, development partners and GoT. Allows testing in different sectors.
[54] See, for example, UNIDO (2016) “Cluster Development Programme, Ethiopia”

Balance of costs and benefits

The break-even analysis suggests that under Option 3 a minimum of 2,132 FTE jobs[55] would need to be created, and above this level the programme would achieve good VFM. For example, creating 2,368 jobs would represent a benefit to cost ratio of 1.22 and an IRR of 18%.
[55] According to DFID’s definition of a ‘productive job’, ‘Employment that earns at least the living wage working at least 20 hours a week for at least 26 weeks per year and in conditions that comply with the 8 ILO Core Conventions’. From DFID (2012) “How to Note: Jobs Measurement”

Based on benchmarking of results from other recent market development programmes, the projection is for the programme to generate much higher targets, at £20 million across 55,500 target beneficiaries, through approximately 9,600 additional FTE jobs (formal and informal) and improvements to existing jobs. This projection will be updated in inception and on an on-going basis as interventions are designed and baseline analyses conducted.

The costs are borne largely by DFID, with supported firms also expected to contribute investment and resources in kind. Benefits will be experienced by poor men and women in the target sectors; non-poor owners and employees of supported businesses; consumers; and relevant GoT and civil society stakeholders. There may also be negative benefits occurring due to loss of employment along the value chains. These losses will be captured by the programme results measurement framework and factored into overall benefits calculations. All benefits are attributable to DFID.

Theory of Change for the preferred option

The theory of change for the preferred option is that market-led solutions can address key constraints to competitiveness in the light manufacturing, childcare and waste sectors. This can support improved enterprise performance and entry of new enterprises, which in turn can lead to higher incomes associated with the creation of new jobs and higher earnings in existing jobs. The evidence for these assumptions can be summarised as follows:
The link between labour productivity, employment and incomes is complex. However there is evidence of a positive connection between productivity and job creation, especially in the case of product innovation. There is also some evidence that productive businesses tend to exhibit not only higher job growth compared with other businesses, but also more inclusive growth. Lastly, investments in innovation might result in gains in employment at the industry level even when there are losses at the company level. There is also evidence that it is job growth coupled with increased productivity that leads to poverty reduction.[56] Key assumptions will be tested by the programme results framework.
[56] IFC (2013) IFC Jobs Study
Recently, new evidence has emerged that Tanzania’s employment creation was driven by smaller firms: the bulk of the recent employment growth in Tanzania came from the non-agricultural and largely informal private sector. Moreover, the greatest contribution to labour productivity growth came from a relatively small sub-set of firms. Accelerating employment in those firms has the potential to increase labour productivity by 1.3 percentage points.[57]
[57] Kweka et al (2016) “Economic Transformation in Africa from the Bottom Up”
The theory of change shows how enterprise performance improvements lead to new jobs from existing and new entrants (enterprises create jobs) and also to increased incomes in existing enterprises (quality of jobs improve). A representation of the theory of change, along with the key assumptions, is above. The programme will also develop and test theories of change for each intervention. These lower level theories of change are a crucial part of flexible programming where interventions are not pre-defined.

What measures can be used to assess the Value for Money (VFM) of interventions

The metrics and examples below are indicative and will be continuously reviewed. The results measurement framework is designed to address challenges in attribution. More detail is provided in the Management Case.

Economy measures are presented in detail in the Commercial Case. In addition, the following efficiency and effectiveness metrics will be monitored. These will be aligned with indicators in the programme results framework.

- Number of additional FTE jobs created and cost per additional FTE job created.
- Net additional £ income generated per £ spent.
- Cost per enterprise receiving support from the programme.
- Cost per individual beneficiary reached (gender and age disaggregated).
- Partner firm investment leveraged per £ spent.
- Measures taken to promote sustainability of interventions.
- Evidence and case studies on empowerment of women and girls.
- Evidence on attributable environmental or public health benefits.
- Economic return / cost benefit analysis of distinct programme components.

On Equity, the results framework will track the profiles and distribution of beneficiaries, by gender, age, education and income group. During inception the programme will determine realistic targets for female and youth beneficiaries within each target sector or sub-sector, which will be documented as disaggregated projections against proposed indicators. The VFM and results framework will track the cost of reaching different beneficiary groups, disaggregated by gender, age, education, disability, and income group.

Summary Value for Money statement for the preferred option

Based on global and Tanzania-specific evidence, a thorough assessment of potential sectors, and a partially quantitative analysis of the benefits, the preferred option of a mixed portfolio for the Dar Jobs programme is likely to yield significant benefits which are likely to outweigh the costs and associated risks, and offer Value for Money for UK investment. Taking a multi-sectoral approach is expected to provide better value than by only working on manufacturing, by creating broader benefits related to services and better integration of women into the workforce; as well as by diversifying programme risk.

Commercial Case

What is the commercial / procurement requirement for the intervention?

An initial scoping study confirmed the feasibility of a market development programme in Dar. Following an OJEU competition, ASI was awarded a contract to design the programme. A new OJEU tender process will be launched to identify a supplier for the inception and implementation phases. The total tender value will be £10 million over 5.5 years, to include:

- A 6 month inception phase; and
- 5 years for programme implementation.
- Only on successful completion of the inception phase will the contract for the subsequent phase be issued. A break clause is also in place after a year of implementation.

During the OJEU process, Procurement and Commercial Department will conduct due diligence of service providers’ fiduciary risk management systems.

In the first month of the inception phase, DFID approval will be required for the programme’s Standard Operating Procedures and Business Process and Governance Framework, which will set out the procedures for the procurement of goods and services. DFID will carry out on-going assessment of the programme’s procurement systems as required.

The contractor will be responsible for providing skilled personnel to manage the programme, and will procure goods and services from consortium partners and other third parties as required. The contractor will manage a Innovation Facility to fund the costs of interventions. DFID will ensure rigorous procurement processes are in place for the Innovation Facility managed by the contractor.

How is the contract structured?

The Dar Jobs contract would be structured as follows:
- £10 million total contract value, with DFID reserving flexibility to scale the programme up or down based on performance, availability of budget, and need.
- A single contract for a six-month Inception Phase, and a five-year Implementation Phase. Contract break clauses will be built in at the end of the Inception Phase and after a year of implementation to allow for re-evaluation of the supplier’s performance.
- A “hybrid” payment model, with payment for a portion of fees and intervention costs tied to performance over the course of implementation. This performance based payment model is described below and in detail in the Financial Case.
- Beyond the costs of the programme team fees and expenses, the contractor would be required to allocate 60% of funds to the Innovation Facility, to fund the costs of Dar Jobs interventions (see below).

Innovation Facility: Expenditure under an Innovation Facility typically takes the form of capital invested in high potential business innovations and opportunities; targeted technical assistance; or in-kind grants. By allowing for a menu of instruments, Dar Jobs is able to be flexible in instances of potential fiduciary risk. For example, instead of purely providing a grant, the programme also has the option to procure goods or services directly. Innovation Facility spend will generally be on a cost sharing basis to buy down risk and leverage private investment into pro-poor innovations. The Innovation Facility will be governed by rigorous fiduciary risk management procedures pre-approved by DFID to ensure proper usage of the project funds and maximum value for money.

DFID will reserve the right to scale up or scale down the programme based on performance, availability of budget and on-going programme needs. There is also a possibility of an extension of up to 12 months subject to performance, availability of funding and ongoing programme needs.

What are the key cost drivers that affect overall price?

The key costs drivers are expected to be:

- Proportion of budget allocated to programme team technical and management fees: A maximum of 40% the Dar Jobs budget will be allocated to programme team fees. As market systems programmes are a technical assistance driven modality, fees are routinely the largest cost driver (usually approximately 50% for market development programmes). Fees will be split between management inputs and technical inputs.
- Majority of budget allocated to the programme Innovation Facility to fund the costs of interventions. The Innovation Facility is a key instrument in any market systems development programme and is the mechanism through which programme investments are made. In addition to risk-sharing capital, expenditure under the Innovation Facility can take the form of technical assistance. This is distinct from core team fees, and is used for example to fund direct support embedded within partner firms.
- Fee rates, where specific drivers are expertise and experience required, level of responsibility, duration of assignment, and local market factors.

How is value added and how will we measure this?

Through the competitive bidding process and subsequent post-tender clarifications, PCD and DFID Tanzania will conduct extensive benchmarking and negotiation to ensure that fees and expenses deliver maximum value for money to DFID. Over the lifetime of the programme, DFID will require the supplier to track and report on metrics including:

- Average daily adviser fee rate;
- % of total adviser days performed by Tanzanian advisers;
- Total expense costs as % of total spend;
- Total management costs as % of total spend;
- Total technical assistance costs as % of total spend; and
- Savings achieved through negotiation or economies of scale.

Innovation Facility costs will be controlled through rigorous and competitive procurement processes, engagement of local suppliers where possible, the programme’s fiduciary management systems, and the use of output based contracts where relevant. Procurement conducted on behalf of the programme will engage local suppliers where possible to minimise costs and to support local capacity building.

DFID will require expenditure information to be supplied in a format that allows for monitoring of performance against VFM metrics on a quarterly and annual basis. Supplier benchmarking of fees and expenses will be reviewed on an annual basis. Quarterly milestone payment points, annual reviews and contract break clauses will provide a further opportunity to scrutinise cost drivers and evaluate the supplier’s performance.

Financial Case

What are the costs, how are they profiled and how will you ensure accurate forecasting?

The total value of the programme is £10 million over six years (inclusive of Design and Inception Phase).

How will the programme be funded?

Dar Jobs will be funded from DFID Tanzania’s Programme Resource allocation for the Sustainable Growth Team as outlined in the current DFID Tanzania Business plan (2016 – 2020). Funding will be 100 percent Resource Departmental Expenditure Limit (RDEL).

Who are the recipients of all proposed payments?

The service provider will be the only direct recipient of DFID funding. The service provider will manage contracts with consortium partners and other third parties to procure goods and services to deliver the programme. The service provider will manage an Innovation Facility which will fund the costs of interventions.

Through the Innovation Facility the service provider will disburse grants to selected businesses, provided on a cost sharing basis to buy down risk and encourage private sector investment in pro poor business models, or contract advisers to provide technical assistance to businesses or other partners.

What are the costs to be incurred by third party organisations?

There are no committed financial costs that will be borne by third party organisations; all costs are included in the service provider’s contract. The programme is, however, expected to leverage private sector investment in pro-poor business models. It is also expected that businesses and other recipients of Innovation Facility funding will provide resources in kind, for example staff time.

Does the programme involve financial aid to governments?

No, the Dar Jobs programme will not provide financial aid to government.

What is the assessment of financial risk and potential fraud?

Within the competitive bidding process, service providers will be assessed on the basis of their financial management capability, accountability systems and processes for effectively managing fiduciary risk. The programme team will include an experienced Finance and Procurement Manager, to be responsible, alongside the Leadership Team, for ensuring that the programme complies with all DFID financial management requirements.

Overall, the assessment of financial risk and fraud is considered to be low given the mitigation measures taken. The key area of risk relates to grants made by the programme Innovation Facility. The service provider will be required to take a number of measures to mitigate financial, fiduciary and fraud risk. These will include:

- The programme’s Innovation Facility will allow for a menu of expenditure categories. This means that, in cases where fiduciary risk makes a grant inadvisable, the programme can use other forms of expenditure to achieve the same outcome.
- Where appropriate, milestone based payment terms will be used for programme sub-contracts and grants to ensure that disbursement is not in advance of need.
- The programme’s Standard Operating Procedures and Financial Management Framework, to be developed and agreed with DFID during the first month of the Inception Phase, will set out the parameters and rules for management of programme funds. This will include procedures for due diligence of potential partners, procurement rules, and safeguards to prevent fraud and conflict of interest. Clear thresholds and approval controls will govern programme expenditure.
- Complete and up-to-date registers of fiduciary risk, programme assets and actual or potential conflicts of interest will be maintained.
- DFID will scrutinise programme expenditure in monthly expenditure reports and quarterly and annual financial reports.

Annual Reviews of the programme will assess financial risk and will make any appropriate recommendations to further improve mitigation. The DFID Senior Responsible Owner (SRO) will ensure spot checks of the service provider’s systems, expenditure statements, asset register, and other evidence as appropriate. The service provider will ensure that annual financial audits are conducted and reports are shared with DFID.

How will expenditure be monitored, reported and accounted for?

The use of funds by the Dar Jobs programme will be reported on a monthly, quarterly and annual basis. On an annual basis, the service provider will submit a detailed annual financial report which will include reporting against the programme VFM framework.

No assets will be procured directly by DFID under the programme. Any assets procured by the service provider will require DFID pre-approval and such assets e.g. vehicles will be registered and accounted for in the programme asset register.

The service provider will submit annual independently audited accounts detailing programme expenditure and revenue, in a format and at a time agreed with DFID Tanzania to inform the programme’s annual review.

The DFID Tanzania team will ensure that there is a robust Delivery Plan (DP) for the programme to enable management of programme delivery. This DP will include a risk register to enable the team to identify and mitigate risks adequately throughout the programme’s lifetime. More information on the Dar Jobs risk register and risk management process is provided in the management case.

Management Case

Adaptive management

Dar Jobs is designed to be a flexible and adaptive programme. Four aspects are considered to be key to adaptive management: knowledge, leadership, culture, and rules.[58] With this in mind, the management arrangements for the Dar Jobs programme are shaped by the following considerations:
[58] Goeldner Byrne et al (2016) “Getting There from Here: Knowledge, Leadership, Culture, and Rules Toward Adaptive Management in Market Systems Programmes” BEAM Exchange

- To be an adaptive programme it is not enough to simply react to new information; programmes must make space to experiment and anticipate potential outcomes. Adaptive management in the Dar Jobs context involves planned pilots, testing of assumptions, and changes in strategy and tactics based on the results.
- The programme monitoring and evaluation (M&E) system must prioritise rapid, useful feedback. Staff need to receive the right information at the right time, so that adjustments can happen quickly. Staff must be fully involved in measurement planning; rather than measurement being driven purely by reporting requirements.
- One of the most important enabling factors for good adaptive management is the freedom to fail. Programme culture must support curiosity, calculated risk-taking, and learning, including openly discussing failure and lessons learnt. Project systems must also ensure that failure is swiftly recognised and responded to.
- A results framework needs to articulate the programme’s theory of change and enable accountability. These two functions cannot be fulfilled by a results framework alone. Dar Jobs will use a number of practical tools to measure incremental change using lean data[59] principles; while also articulating how multiple individual outputs or outcomes feed into higher-level results.
  [59] Lean data is an approach to measurement which emphasises i) collecting data that is useful for other purposes beyond reporting; ii) methods and tools to enable efficient data collection (Acumen)

What are the Management Arrangements for implementing the intervention?

DFID Tanzania will oversee the management of the Dar Jobs Programme. The SRO (25% FTE) and Programme Manager (20% FTE) will have overall responsibility for ensuring compliance with DFID Smart Rules and high quality programme delivery. Additional oversight will be provided by the Team Leader, Sustainable Growth (5% FTE).

Dar Jobs will be implemented by a lead contractor and its consortium partners, which will include Tanzanian partners. The contractor will have full contractual responsibility to DFID, and will manage sub-contracts with consortium partners and other third parties as required.

The structures involved in the management and governance of Dar Jobs are:

- DFID Steering Group: convene for quarterly update meetings to assess programme progress and support decision-making. This group will include: the SRO and Programme Manager; the Sustainable Growth Team Leader; an Urban Development Adviser; a Governance Adviser; a Social Development Adviser; and other advisers as necessary. During inception phase, the Head of DFID Tanzania will be updated on a monthly basis by the SRO, and thereafter on a quarterly basis.
- Dar Jobs Implementation Core Team: individuals working across the programme functions of leadership, intervention management, monitoring and results, programme and financial management, and communications. The Team Leader will report to the DFID SRO and Programme Manager.
- Consortium Panel: to comprise a representative from each of the Dar Jobs consortium partners. The consortium panel will be an internal management function to ensure that responsibilities are clear across the consortium and that resourcing is effectively targeted to deliver programme results.
- Dar Jobs Advisory Panel: to comprise individuals who bring specific knowledge, expertise or insights into the programme’s target sectors, the target beneficiaries, the Dar political economy context, or urban market development. The Advisory Panel will include young people and women who are representative of, and/or advocate for, the programme’s target beneficiaries. The Advisory Panel will be convened on a six monthly basis to review the portfolio and results and advise on overall strategic direction and priorities.

The Business Process and Governance framework will set out the processes agreed for use of Innovation Facility funds; and design, approval and management of interventions and partnerships. The following key check-in points enable DFID’s full oversight:

- Fortnightly progress update meeting: with core team leadership, the DFID SRO and the Programme Manager. This allows DFID to oversee the immediate workplan, discuss issues arising, and make any necessary approvals.
- Quarterly DFID update meeting: following the consortium’s own internal meeting, the service provider will meet with the DFID Steering Group to discuss progress, review intervention strategies and results chains, failure reporting, learning, beneficiary feedback, plans for the next quarter; and risk management. In advance of the meeting the service provider will submit a Quarterly Update, VFM report, risk management plan, and proposed quarterly workplan.
- Annual Review: On an annual basis, the service provider will submit a self-assessment of results and VFM in advance of the programme Annual Review. The service provider will also submit an annual business plan for the year ahead. Adaptive programming often results in adjustments to results frameworks. Any changes to the results framework will be discussed and agreed at least 3 months ahead of Annual Reviews, as per DFID Smart Rules.
- Implementation Progress Review: After a year of implementation, there will be a contract break point to assess programme direction and strategy and allow for a termination or extension of the contract if required.

What are the risks and how will these be managed?

The key risks facing the Dar Jobs programme relate to the poor nature of the business environment, history of weak private sector engagement, and limited experience of market development programming in Tanzania. The overall programme risk rating is moderate, based on an assessment of the likelihood and impact of the initial risks identified. These risks, their scoring, and mitigating measures, are captured in the initial risk register below.

Risks will be identified, assessed, and managed per DFID’s standard risk management framework. Risks are grouped according to six categories: external context, fiduciary, delivery, operational, reputational and safeguards. The SRO will advise on an appropriate risk appetite for each risk category, which will be reviewed on a regular basis. The risk register will be a live document, owned by the SRO and Programme Manager. Risks, mitigation and scores will be re-evaluated on an on-going basis. Every month, the risk register will be reviewed by the SRO and Team Leader. At the intervention level, risks will be assessed and all mitigation strategies integrated into Intervention Plans before interventions are approved.
Risk Category	Risk	Negative Impact	Likelihood	Score	Gross Risk Rating	Mitigation	Negative Impact	Likelihood	Score	Net Risk Rating
External Context	National / local gov unsupportive of Dar Jobs programme	Moderate / (3)	Possible / (3)	6	Major	Stakeholder engagement with line ministries and local government throughout inception and on an on-going basis with designated relationship managers.	Moderate / (3)	Unlikely / (2)	5	Moderate
External Context	Economic or political shocks reduce competitiveness of target sectors or the Dar economy overall.	Major / (4)	Likely / (4)	8	Severe	Sector selection criteria targeted future growth potential, feasibility, and limited exposure to external shocks; focus on sector-specific business environment constraints. Some factors e.g. GoT move to Dodoma are outside of programme control, but strategy will be adjusted based on ongoing updates of political economy analysis.	Minor / (2)	Unlikely / (2)	4	Minor
Fiduciary	Fraud, misuse or misallocation of funds	Moderate / (3)	Likely / (4)	7	Major	Financial and fiduciary risk mitigation measures covered in Financial Case (above).	Moderate / (3)	Unlikely / (2)	5	Moderate
Delivery	Market distortion created by subsidies	Moderate (3)	Unlikely (2)	5	Moderate	Any subsidy must: be time-bound, demonstrate additionality, and be targeted to the market failure	Minor (2)	Unlikely (2)	4	Minor
Delivery	Poor response by partners due to high risk aversion or low capacity	Severe / (5)	Likely / (4)	9	Severe	Micro-pilots enable early action-based engagement; ‘Quick Win’ activities to build credibility and assess ‘will’ and ‘skill’; Innovation Facility enables targeted interventions; cost-sharing to buy down risk.	Moderate / (3)	Possible / (3)	6	Major
Delivery	Poor understanding of inequalities leads to failure to deliver benefits for women and youth	Severe / (5)	Likely / (4)	9	Severe	This risk will be mitigated by the use of robust social, gender and political economy analysis and processes across the programme and clear responsibilities for WEE and Youth Inclusion results.	Moderate / (3)	Possible / (3)	6	Major
Delivery	Intervention portfolio too broad to achieve transformational impact in any one area	Major / (4)	Likely / (4)	8	Severe	The M&E system will generate rapid information and Quarterly Strategic Reviews will be used to drop interventions / rationalise the portfolio where appropriate. Interventions will require a clear concept note and justification prior to approval.	Moderate / (3)	Unlikely / (2)	5	Moderate
Delivery	Actions of other donor programmes or GoT undermines delivery	Major / (4)	Possible / (3)	7	Major	Scan for presence of other donors with conflicting approaches during sector selection. Avoid “crowded” sectors. Engage other donors on market systems principles and design complementary interventions.	Minor / (2)	Unlikely / (2)	4	Minor
Operational	Limited internal capacity in market systems limits effectiveness	Major / (4)	Possible / (3)	7	Major	The programme team will receive training and mentoring. Programme recruitment uses non-traditional routes, assessing aptitude rather than only comparable experience (limited in Tanzania).	Moderate / (3)	Unlikely / (2)	5	Moderate
Reputational	DFID seen to be undermining GoT by intervening in social sectors	Moderate / (3)	Unlikely / (2)	5	Moderate	The programme will maintain relationships with ministries and local authorities through designated relationship managers. The programme will intervene in targeted areas seeking to complement GoT efforts.	Minor / (2)	Unlikely / (2)	4	Minor
Reputational	Investments in firms later found to be engaged in undesirable activities	Severe / (5)	Possible / (3)	8	Severe	Screening and due diligence processes for potential implementing partners; investment in political economy analysis and team with strong contextual knowledge; robust fiduciary management processes.	Major / (4)	Possible / (3)	7	Major

What role will the Partnership Principles play?

Dar Jobs will not provide direct funding to the Government of Tanzania. As such, the Partnership Principles will not be applied to manage or monitor this programme.

How will progress and results be monitored, measured and evaluated?

Progress and results of Dar Jobs will be monitored in-house by the programme implementer. The programme’s monitoring and evaluation (M&E) system will comply with the Donor Committee for Enterprise Development (DCED) Standard for Measuring Results in Private Sector Development. This will provide a credible system for data collection to be drawn on for Annual Reviews and independent evaluations. The objectives of the Dar Jobs M&E system are twofold. First, it will deliver credible evidence of results for the purposes of programme reporting and accountability. Second, it will deliver information vital to an adaptive, continuous learning approach to this experimental programme. Data gathered will feed into the continually evolving design of the programme to achieve maximum impact. DFID will ensure the M&E system is manageable, intuitive and communicable.

This section presents the Dar Jobs programme Results Framework and some indications of the expected measurement methods. The full results framework, including projections against key indicators, will be completed during the inception phase. Projections will be reviewed and adjusted on the basis of new evidence generated by the programme on an annual basis. Detailed measurement planning will also be completed during inception once the opening portfolio of interventions has been identified. The programme will determine realistic targets for the proportion of female and youth beneficiaries within each sector.

Dar Jobs results will be tracked through a small number of key indicators proxying for the key steps in the Theory of Change (described in detail in the Appraisal Case):

Dar Jobs will report results attributable to the programme. In particular, the programme will develop evidence-based narratives of the contribution of each of its interventions to change, and combine this with the generation of reliable information of the likely counterfactuals at different levels in the theory of change. Case-by-case approaches to generating counterfactual information will include trend analysis, difference-in-difference analysis, or quasi-experimental trials. An estimate of the counterfactual will be discounted from observed change before results are reported, and intermediate results will be reported alongside key results indicators.

At impact level, net attributable income change (NAIC) (reported in cumulative total £ value and average per beneficiary) measures depth of benefits accruing to the programme’s target beneficiaries. This will combine income changes from people gaining employment in the target sectors as well as increases in the earnings of existing employees. Number of target beneficiaries experiencing significant positive NAIC will be disaggregated by gender and age profile. This indicator provides a measure of the programme’s breadth of impact. The indicator also embeds in its definition a minimum level of benefit for people to be counted as beneficiaries – the additional NAIC must take people above the living wage or equal at least 25% of annual income in real terms. Women’s economic empowerment will also be tracked, with an indicator on improved access and agency of women.

At outcome level, job creation is captured by net change in Full Time Equivalent (FTE) productive jobs and improved quality of jobs by percentage change in earnings of existing employees. Improvements in enterprise performance in target sectors are tracked by gross value addition (GVA) change, which at enterprise level is equivalent to change in gross profit. This will be disaggregated by the different ways that enterprises can achieve this – through increased productivity, efficiency, upgrading and growth.

At output level, monitoring will be oriented towards fast feedback on a range of indicators to support learning and improvement in programme targeting. Areas of focus will cover:

- Progress of new models towards commercial viability and sustained adoption
- Early signs that market changes are creating opportunities for target beneficiaries (disaggregated by gender, age, and income level);
- Transfer of ownership and investment from the programme to market actors;

Measurement Methods

At impact level, the programme will use sample beneficiary surveys sourced from employee lists of enterprises that are known to be benefiting from programme outputs. Surveys will verify whether the programme is reaching its target beneficiaries. Surveys will also be conducted of employees from enterprises which are not benefitting, to understand differences.

At outcome level, measurement will combine top-down sector studies focusing on geo-spatial clusters where the programme is focusing its activities and bottom-up sample surveys of enterprises reached by the programme’s outputs.

At output level, monitoring will be oriented towards fast feedback on a range of indicators measuring incremental change (see above). The programme will use lean data techniques to identify select indicators whose measurement will have a shared value for both the programme and partners in generating insight into making new models viable. Information generated by these output methods will be translated into indices for reporting. These indices – quantitative indicators constructed on the basis of evidence-based, subjective assessments against a range of qualitative measures – will be developed transparently with DFID. The programme will seek stakeholder validation of results before reporting. This approach is informed by DFID’s experience in adaptive programming.

Overall, Dar Jobs measurement methods prioritise delivering credible evidence of results for programme accountability; while also delivering rapid, useful feedback to enable an adaptive, learning approach to this experimental programme. Beneficiary consultation and feedback will be a key part of inception phase design and ongoing monitoring, and will be presented to DFID in quarterly meetings throughout the programme. A dissemination strategy will be designed during the inception phase, to ensure useful evidence generated by the programme is disseminated to stakeholders in Tanzania and more widely. This will include promoting learning beyond the programme, to inform existing and future urban job creation efforts beyond the Dar Jobs programme.