 Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed on actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Family Planning Outreach II
Programme Value: £22,030,000		Review Date: January 2018
Programme Code: 204266	Start Date: November 2014	End Date: December 2018

Summary of Programme Performance
Year	2015	2016	2017	2018
Programme Score	A	A+	A	A
Risk Rating	Medium	Low/Medium	Minor/Moderate	Moderate

Summary of progress and lessons learnt since the last review

The Family Planning Outreach in Tanzania programme has completed its third year of implementation. The programme provides comprehensive family planning services to women and girls giving them choice over when and how many children they have. This, in turn, is important in helping women and girls remain in education, stay healthy, and participate in economic activities. The programme provides long-and-short term acting and permanent methods of family planning; Comprehensive Post - Abortion Care (CPAC); care for victims of Gender-Based Violence (GBV); and HIV counselling and testing. The programme has performed consistently well throughout implementation, scoring an A or A+ in all previous Annual Reviews. This year, the programme has scored an A.

The programme is delivered by two implementing partners who use different models and operate in different regions of Tanzania: Marie Stopes Tanzania (MST) and Population Services International (PSI). This year (2017) the programme successfully provided family planning services to 398,112 women and girls and is ahead of target in terms of beneficiaries reached. The programme gives women a wide choice of methods of family planning. The most used method in MST regions was the 3-year implant (28%), followed by the 5-year implant (26%). In PSI regions the most used method was the Inter-Uterine Device (IUD) (48%) followed by implants (45%).

2018 is the final year of implementation for this programme. As such, this Annual Review has looked particularly at recommendations for DFID Tanzania’s future programme to scale up family planning. Whereas the Family Planning Outreach in Tanzania programme is designed to reach women in rural areas, DFID will also include the urban context in the future programme. Fieldwork for this Annual Review included looking at urban areas around Dar Es Salaam and found that there is a huge need for family planning with much greater population diversity and density, different norms, and greater use of private health facilities than in rural areas.

Adolescents
This programme has met the 2017 target to have 10% of beneficiaries be under 20 years old. This is an increase from the 8% target set in the previous year of implementation. However, the challenge is reaching young people before they become pregnant. This is particularly important in the Tanzanian context where Government of Tanzania policy prevents girls who become pregnant from re-entering school after giving birth, meaning that, for an adolescent girl, becoming pregnant means the end of her education. Implementing partners have used different approaches to reach young people. In this review, DFID has documented these methods and their costs and effectiveness for comparison. There is also clearly a need for the introduction of comprehensive sexuality education in schools.

Sexual and Gender-Based Violence
This year the programme has met the targeted number of survivors of GBV receiving care and slightly exceeded the target for the number of healthcare providers trained in GBV. DFID acknowledges that GBV responses should involve multiple sectors such as education, the police and social welfare, which is beyond the scope of the programme. DFID will re-assess the approach to GBV to see if it needs to change in the future programme by learning from best practice in Tanzania including the model used by the International Refugee Commission (IRC) in refugee camps.

Staff Resource and Capacity in the Health Sector
Capacity and availability of staff remains a challenge across the health sector in Tanzania. Implementing partners have been training health facility workers and orienting unqualified health facility workers (such as medical attendants) in the provision of long-term acting family planning, CPAC and GBV. However, there is a high rate of staff attrition and movement of staff to other areas or departments where they cannot administer such services. The health sector was also affected by the recent issue in Tanzania of civil service certificate verification, whereby public sector workers were required to prove that their school qualifications were genuine. Through this process, some of the health workers trained by this programme lost their jobs. This explains why some health facilities still wait for travelling outreach teams to provide long-term acting methods of family planning, despite training.

Comprehensive Post Abortion Care (CPAC)
Although the programme has achieved its targets in the provision of CPAC to women, there are still some challenges. The number of women who seek this service is lower than expected because of the stigma surrounding abortion, and even instances of negative attitudes from health facility workers. The public sector referral system for clients in need of CPAC is working, but some women still don't go to health facilities for post-abortion care, instead, they rely on over the counter pills available in pharmacies and Accredited Drug Outlets (ADOs).

Family Planning Commodities to the Last Mile
While this programme does not procure family planning commodities (a separate DFID-supported commodities programme ended in 2017) the future programme will address commodities and supply chain issues alongside service delivery. Hence this Annual Review has looked at this issue. Although there have been real improvements in the family planning commodities supply chain in Tanzania, health facilities still experience stock-outs of contraceptives. This year PSI benefited from the remaining buffer stock commodities while MST did not use this support. Unlike the previous DFID-supported commodities programme, the future family planning programme will not maintain a buffer stock of contraceptives. Instead, implementing partners for the future programme will focus on improving the government supply chain to reduce the current stock-out problem. An analysis of the data and information from the 2017 Government Holistic Supply Chain Review report revealed some remaining supply chain issues including inconsistency in commodities quantification; data unavailability, inaccuracy and lack of sustainability; non-homogenous reporting tools; and poor monitoring and evaluation. The future programme will focus on supporting the Government of Tanzania to address these challenges.

Monitoring and Evaluation
In November 2017, DFID commissioned an Independent Data Verifier to assess the data quality of the implementing partners of the programme. This is important because payments to partners are based on results achieved every quarter. The findings from this verification will feed into the monitoring and evaluation of the future family planning programme. The main areas of analysis were accuracy and reliability of data; timeliness of reporting; methodological soundness and choice and definition of indicators. The final report is not yet finalised.

Both implementing partners use their own information management system in addition to the government Demographic and Health Information System 2 (DHIS 2). Although this is additional work, DFID encourages implementing partners to work to strengthen the government’s information system. However, there is a challenge in gaining full access to the government DHIS 2 which discourages partners from investing in the government data.

As 2018 is the last year of the implementation of the programme, documentation of the approaches used by both partners in the various components of the programme will be essential. This will also help to ensure a smooth transition from this programme to the new family planning programme, ensuring there is no breakage in the provision of services and helping new suppliers to understand challenges and continue with the good practice of the current programme. The focus for the rest of the programme will need to shift emphasis to ensure a responsible transition and sustainability. This includes documentation of different training and mentoring approaches in the provision of family planning, CPAC, and GBV services, and strengthening the government supply chain system. There is also learning, new evidence and research done by the programme that will be important to the new implementing partners.

Governance and Politics
Family planning requires sensitive handling in the Tanzanian context but all indications are of sustained government commitment to provision of family planning services at both central and local government levels, and within the two key Ministries with which the programme works – Health Community Development, Gender, Elderly and Children (MoHCDED) and the President’s Office Regional Administration and Local Government (PO-RALG). The Government of Tanzania participated in the July 2017 Family Planning 2020 Summit in London and committed to increasing the budget for family planning, reaching more young people and supply chain strengthening.

Summary of recommendations for 2018
Commodities
In the absence of buffer stock, implementing partners need to focus on strengthening government supply chains by sharing their outreach plans early in advance to match with facilities’ ordering cycle.
PSI and MST, by March 2018.

Implementing partners should connect with United Nations Population Fund (UNFPA) for continued support on electronic Logistics and Management Information System (eLMIS) and other methods to improve the visibility and accountability of commodities down to the Last Mile. They should also work closely with other partners such as USAID, Gates Foundation and DFID head office[1]. An analysis of health facilities with particular issues is required for focus.
[1] At the family planning summit, partners committed to improving the visibility of supplies from the manufacturer right down to the woman or girl receiving contraceptives and a number of initiatives are in place to do this.
PSI and MST, by April 2018

Data
Both PSI and MST should report quarterly on the progress of the recommendations from the data quality assessment including institutional data strengthening mechanisms to improve accuracy and maintaining the reliability of the information reported.
PSI and MST, by April 2018

The implementing partners should prioritise improvements to the government Demographic and Health Information System 2 (DHIS 2) data, with the aim of transitioning in future to using government information systems only to avoid parallel data collection.
PSI and MST, by May 2018

Good documentation of initiatives that work, learning and challenges of the programme ready for the programme completion and transitioning to the new programme. Annex 3 summarises what implementing partners should cover as an exit plan, but not limited to those areas.
PSI and MST, by May 2018

Change the logical framework to include a percentage in absolute numbers of women of reproductive age, to give a better idea of how much actual impact this programme may have on national Contraceptives Prevalence Rate (CPR).
DFID, PSI and MST, by April 2018

PSI should recommend realistic targets of CPAC services based on the trend of women who access the services.
PSI, April 2018

Revise the GBV milestones for 2018.
PSI and MST, May 2018

Service Delivery
To improve coordination and sustainability of the programme, implementing partners should involve both ministries – Ministry of Health, Social Development, Gender, Elderly and Children (MoHCDEC) and the President’s Office-Regional Authority and Local Government (PO-RALG) in the implementation of activities.
PSI and MST, by April 2018

Training and Capacity Building
Use the last months of the programme to consolidate training through supportive supervision and mentoring. Mentor teams of health workers in facilities including the medical attendants (already being done in some cases). If resources allow, consider building the capacity of a larger number of community health volunteers to provide a stronger community system for family planning
PSI and MST, from March to the end of the programme

Future programme recommendations:
1. The evidence around family planning interventions has increased a lot in the last few years (high impact practices), including lessons learnt from programmes in Tanzania. Set the new programme within this solid global and country level evidence base. Where gaps exist, consider carrying out baseline studies, qualitative research and needs assessments before the start of implementation.
2. Attempt to use independent verification of data to provide evidence for milestone disbursements as well as strengthening the national data collection system. This could be done by linking disbursements to the accuracy of data submitted. Additionally, consider linkages between other programmes that are already rigorously verifying data e.g. the RBF programme if feasible.
3. Consider moving away from a focus on numbers and use more quality of care and system strengthening type indicators for milestone payments.
4. Building on the success of this programme, the new Family Planning programme should focus even more on health system strengthening, coordination and advocacy. DFID could consider an approach focused on a smaller number of districts/regions but with 100% coverage and including intensive capacity building with regional and district government staff. This could include assistance with planning, budgeting, supervision, monitoring, mentoring and human resource planning. This would require a much more decentralised approach to the programme.
5. Consider strengthening community systems through volunteers or community health workers to increase the behaviour change/changing of social norms component of the programme as well as possible task shifting of service delivery.
6. Design the adolescent component based on current global and Tanzanian evidence. Decide whether tackling deep-rooted cultural norms around the age of first pregnancy, gender roles and empowerment are within the scope of the programme, given the extra inputs required.
7. DFID should be sure of the additional value of Family Planning funding in refugee settings by understanding gaps. Consider supporting existing Sexual and Gender Based Violence (SGBV) interventions in refugee settings. For other settings, plan a more holistic, multi-sectoral intervention, perhaps on a smaller scale focused on hotspots of high GBV prevalence or high population concentration (urban areas).
8. In some urban areas, there are large numbers of for-profit private facilities e.g. 80% in Dar es Salaam. Consider incorporating the for-profit private sector into the future programme.
9. Incorporate a training of trainer model at the district level and the training of district staff to carry out supervision and mentoring to improve sustainability.
10. It is important not to ‘abandon’ all the work that has already been done in training staff – consider ways of keeping them motivated and up to date through refresher training and other innovative approaches by the partners.
11. Gather global and Tanzanian existing evidence to put together best practice in this area and decide which practices can still be adopted in the coming year.

A. Introduction and Context

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4420192.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/5421913.xls

Outline of the programme
DFID Tanzania is implementing Phase II of a Family Planning outreach programme over 4 years (2014-2018) to increase family planning use in Tanzania. The outcome of the programme will be to increase women's use of family planning and availability of Comprehensive Post Abortion Care (CPAC) services across Tanzania. The impact will be to reduce maternal mortality and improve women's lives by giving them control over their family formation.
Specific outputs are as follows:
1. Private sector family planning outreach services to rural areas particularly Long-Acting and Permanent Methods (LAPM) in consultation with the government public sector services;
2. Strengthened national Comprehensive Post-Abortion Care (CPAC) in both public and private sectors (including policy work);
3. The government of Tanzania supported to strengthen its family planning programme, including training of public sector providers in LAPM;
4. Young people (<20) reached with family planning and CPAC; and
5. Integrated Reproductive Health services for women who are victims of Gender Based Violence (GBV) in the public or private sectors.
The programme responds to reproductive and maternal health challenges in Tanzania. The 2015-16 Tanzania Demographic and Health Survey (TDHS) shows that fertility is steadily but slowly decreasing. The total fertility rate (TRF), which can be interpreted as a snapshot of average family size only reduced from 5.4 in 2010 to 5.2 in 2015. Moreover, urban Total Fertility Rate (TFR) has actually increased from 3.2 in 1999 to 3.8 in 2015, possibly affected by the inward migration of rural women to cities. The teenage pregnancy rate is increasing again in Tanzania to 27% after a decrease to 23% in 2010.

This programme has completed its third year of implementation. It has two implementing partners who use different approaches and cover different regions of the country (Annex 2). All programme activities are carried out in close collaboration with the Government of Tanzania (GoT).
Marie Stopes Tanzania (MST) receives £14,498,000 over 4 years and has worked under this contract since December 2014, building on work completed under Phase I. MST’s outreach model involves 20 outreach teams ‘snaking’ through the country-side to reach different public sector health facilities, including dispensaries. Four additional two-person teams run out of three wheelers (Bajaji) in Zanzibar. Teams include an MST Bilateral Tubal Ligation (BTL) surgeon, two MST nurses, a driver, and a public sector nurse appointed by the District Medical Officer (DMO). The teams occasionally use a public sector BTL surgeon instead of an MST employee. MST returns to each facility every five to six months. In addition, MST has been training public sector providers using the Government of Tanzania family planning (FP), CPAC and GBV curricula.

Population Services International (PSI) receives £6,276,354 over 4 years, with two sub-contractors: Intra-health (for training and GBV) and Restless Development (for reaching youth). PSI began work with four teams in January 2015 and expanded to 10 teams in 2016. PSI’s outreach model is a public sector static ‘hub and spoke’. The hub and spoke facilities receive extensive training in FP, CPAC, and GBV. PSI outreach teams include one PSI healthcare provider and one public sector nurse recommended by the District Reproductive and Child Health Coordinator. Each hub oversees four spokes, with complicated cases referred to the corresponding hub.

The models have advantages that reflect the areas in which they are working. The MST model emphasises coverage and the PSI model emphasises sustainability. See Annex 1 for an analysis of the strengths and weaknesses of each model and Sections C (Outputs) and D (Value for Money) for more analysis of the implications of the different approaches.

This programme has been complemented by the DFID-supported Maternal and Reproductive Health Supplies programme (2012-2017) which supplied family planning commodities to the Medical Store Department (MSD) to address the shortage of commodities in the health facilities in Tanzania. The implementing partner of the programme was United Nations Population Fund (UNFPA). Part of the programme provided buffer stock under DKT International which supplied implementing partners with family planning commodities where they face shortage during outreach services.

The future programme
When the current programme ends in 2018, DFID will scale up family planning support in Tanzania to ensure more women have access to family planning services. This will be a £55 million programme over five years (late 2018 to 2023). The aim is to continue with the same focus – comprehensive family planning services (FP, CPAC, GBV and HIV testing). Additionally, the programme will expand to the urban areas; seek innovative ways of reaching young people, people with disabilities and refugees; strengthen the supply chain from the national to the health facility level and procure family planning commodities within the same programme.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
The programme aims to increase women's use of comprehensive family planning and availability of CPAC services across Tanzania. This is assessed at outcome level in terms of estimated Couple Years of Protection (CYP)[2] delivered by the project, and the proportion of clients who are new adopters of family planning (i.e. have never used modern contraceptive methods).
[2] The estimated protection provided by family planning (FP) services during a one-year period, based upon the volume of all contraceptives sold or distributed free of charge to clients during that period. The CYP is calculated by multiplying the quantity of each method distributed to clients by a conversion factor, to yield an estimate of the duration of contraceptive protection provided per unit of that method.

The programme is achieving well this outcome by delivering 1,487,635 CYP in 2017, which is 34% of the total programme CYP over four years of the programme implementation. Additionally, both implementing partners exceeded the planned milestone for new adopters of family planning during the third year of programme implementation. The target for both partners was 39%. MST achieved 45% while PSI achieved 50%. This means that the programme is reaching a good number of beneficiaries who have never used family planning and hence contributing to the programme target of reaching at least 285,000[3] new adopters of family planning by the end of the programme.
[3] In 2020, the Tanzania Demographic and Health Survey will release total number of new adopters/users of family planning and DFID share will be according to the % of all the family planning funding in Tanzania.

The proportion of clients who are new adopters of Family P, Year 3
	Planned (2017)	Achieved (2017)
MST	39%	45%
PSI	39%	50%

Overall output score and description:
Output 1: Delivery of Family Planning in Rural Areas. Output met expectations (A)
This output is about the delivery of family planning outreach services to rural areas (particularly Long-Acting and Permanent Methods) in consultation with government public sector services. Overall, implementing partners have delivered 98% of planned family planning services in 2017. There was also an excellent client satisfaction (91-97%) and cheaper delivery of Couple Years of Protection (CYP) than the projections. Despite the achievement, both implementing partners were slightly low on the target to reach poor people with family planning. This is 59% for MST against the 64% milestone and 51% for PSI against a 66% milestone.

Output 2: Strengthening CPAC. Output met expectations in most indicators (A).
This output is about strengthened national CPAC in both the public and private sectors, including policy work. The programme is exceeding milestones for facilities equipped and supplied to deliver CPAC, and training of health workers to provide those services. However, the absolute numbers of women accessing safe post-abortion care through the programme are under target for PSI (23%) and over target for MST (160%). This is a 92% overall achievement of the number of women who access safe post-abortion care.

Output 3: Supporting the Government of Tanzania to Strengthen its FP Programme. This output met expectations (A).
This output is about supporting the Government of Tanzania to strengthen its family planning programme, including training of public sector providers in LAPM. Both implementing partners have made a big effort to carry out on-site training and mentoring of government health workers during outreach sessions. In terms of numbers of women accessing family planning services in public health facilities, MST has achieved 500% of the milestone while PSI has achieved about 58% of the target. Both implementing partners achieved the target on the quality of teams at 95%. Moreover, PSI did not have any clinical incidents while MST reported and reacted immediately to two clinical incidents, which were both rated amber.

Output 4: Reaching Young People (<20). This output has met expectations (A).
Both PSI and MST have met the target to reach young people between 15 and 19 years by 10% out of all beneficiaries of the programme. Amongst young people reached, 12 % of MST and 17% of PSI clients were reached before they became pregnant. The most used family planning method among young people is the male condom (34%), followed by the 3-year implant (28% for MST and 49% for all implants for PSI), followed by the injectable (34%). Both implementing partners have met targets of the number of programme staff trained to provide family planning services to young people.

Output 5: This output has met expectation (A)
This output is about the integration of Reproductive Health services for women who are victims of violence (GBV) in the public or private sectors. MST has met 99.5% of the milestone while PSI reached 96.2% of the targeted number of GBV survivors receiving care. Both implementing partners have exceeded the targeted number of healthcare providers to be trained in GBV. Referrals of GBV survivors have also exceeded the milestone by meeting 113% and 105% of the milestone for MST and PSI respectively.

Has the logframe been updated since the last review? Yes.

## C: DETAILED OUTPUT SCORING

Output Title	FAMILY PLANNING. Private sector family planning outreach services to rural areas (particularly LAPM) in consultation with Government public sector services
Output number per LF		1	Output Score	A
Risk:		Minor-Moderate	Impact weighting (%):	50%
Risk revised since the last AR?		N	Impact weighting % revised since the last AR?	N

Indicator(s)	Milestones (2017)	Progress (2017)
1.1 Number of Family Planning services delivered by the project	MST: 287,981 / PSI: [4]100,656 / Total: 388,637	MST: 305,030 / PSI: 93,082 / Total: 398,112
1.2 Proportion of clients classified as poor	MST: 64% / PSI: 66%	MST: 59% / PSI: 51%
1.3 Cost per CYP (efficiency)	MST: £5.31 / PSI £5.39	MST: £2.91 / PSI: £2.73
1.4 Client satisfaction with the service they received (PSI: would you recommend a friend?)	MST: 90% / PSI: 90%	MST: 91% / PSI: 97%
[4] DFID agreed with PSI to achieve 50% of the set milestone because of the same number of people reached with other methods of family planning, receive condoms. This was to avoid double counting. The agreement was made in 2016 and the changes are made in this review.

Key Points
This output reflects the core of the outreach work performed by the implementing partners, focusing on a number of family planning services delivered, the targeting of service delivery, cost efficiency and the quality of services. These indicators are in turn affected by a range of factors including the system for delivery of commodities to the health facility visited by outreach teams; the availability and accuracy of data for monitoring service delivery; as well as factors affecting the quality of service delivery.

This output scores an A because it has just met the milestone. MST has exceeded the number of family planning services to be delivered (105%) while PSI is just below the target at 92%. Overall, implementing partners have delivered 98% of planned family planning services in 2017. In terms of the economic status of beneficiaries, both implementing partners are below the target of 64-66% of clients being classified as poor. Although the programme reaches remote and poor areas, implementing partners provide services to every person who seeks them, making the target to reach more poor people challenging. The cost of providing one CYP is almost half the projected cost for 2017. This is because more beneficiaries (80-90%) than expected opted for long-term acting methods of family planning. Both implementing partners have excellent client satisfaction scores for delivery of services.

Service delivery approaches
- Both models of service delivery have reached large numbers of women and have been successful. The MST model has reached more beneficiaries but the hub and spokes model used by PSI focuses more on strengthening the existing government system. As the programme starts the last year of implementation, sustainability is very important. Both implementing partners have completed provider training and they can focus even more on supportive supervision and mentor.
- In addition, both implementing partners have been working closely with the Ministry of Health, Social Development, Gender, Elderly and Children (MoHCDEC) by sharing the outreach plan and attending the Technical Working Groups (TWG) meetings. However, there is an increasing emphasis on working closely with the President’s Office- Regional Administration and Local Government (PO-RALG) which is responsible for implementation of all activities.
- The programme uses some community volunteers to raise awareness a few days before each outreach session but did not use volunteers for general awareness raising or behaviour/social norm change around family planning use.
- The field visit as part of the annual review included the MST outreach at Mtendeli refugee camp in Kigoma. All family planning services in the camp, apart from permanent methods, were provided by a well-financed and staffed hospital run by Tanzanian Red Cross (TRC) and International Refugee Commission (IRC). MST conducts outreach for permanent methods but the cost-effectiveness of outreach versus training the TRC and IRC staff to carry out these procedures needs to be considered carefully.

Recommendations for 2018
To improve coordination and sustainability of the programme, implementing partners should involve both ministries – Ministry of Health, Social Development, Gender, Elderly and Children (MoHCDEC) and the President’s Office –Regional Authority and Local Government (PO-RALG) in the implementation of activities.
PSI and MST, April 2018.

Recommendations for future programming
1. Building on the success of this programme, the new Family Planning programme should focus even more on health system strengthening, coordination and advocacy. DFID will consider an approach focused on a smaller number of districts/regions but with 100% coverage and including intensive capacity building with regional and district government staff. This could include assistance with planning, budgeting, supervision, monitoring, mentoring, human resource planning and other aspects. This means a more decentralised approach to the programme.
2. Consider strengthening community systems through volunteers or community health workers to increase the behaviour change/changing of social norms component of the programme as well as possible task shifting of service delivery (see output 3 as well).
3. DFID should be sure of the value addition of family planning funding in refugee settings to understand the gap in support and where the programme will add value.
4. In some urban areas, there are large numbers of for-profit private facilities e.g. 80% of facilities in Dar es Salaam are private for-profit. Consider incorporating the for-profit private sector into the future programme.

Quality of service delivery
- Both implementing partners have ensured good quality of family planning services by provision of comprehensive counselling before services which include side effects and dual protection to prevent HIV infection. However, there is no consistency in the HIV counselling for women who eventually choose not receive any method of family planning. It is also challenging to determine the impact of HIV counselling and testing in this programme as the logical framework doesn't capture this.
- Most facilities have health providers who are not qualified for the provision of family planning services. But since those are the only available health facility workers, the implementing partners orient them to gain skills to serve family planning clients. Nevertheless, due to the workload in the health facilities, such providers might fail to provide long-term acting methods of family planning until the implementing partners perform outreach services.

Recommendations for future programming
To include HIV testing and counselling in the programme monitoring in order to determine the extent of the programme impact in dual protection.

Commodities
- The supply system in Tanzania is on a positive trajectory with a ‘pull’ system of delivering commodities directly to facilities from the central Medical Stores Department (MSD) in place and electronic Logistics Management Information System (eLMIS)[5] rolled out to all facilities that have electricity down to the health centre and dispensary level. As part of the London Family Planning Summit, the Government of Tanzania committed TZS 14 billion (£4,435,210) to family planning commodities, of which2 billion is already disbursed. This is the largest family planning commitment the government has ever made.
  [5] A system of records and reports – whether paper-based or electronic – used to aggregate, analyze, validate and display data (from all levels of the logistics system) that can be used to make logistics decisions and manage the supply chain.
- The eLMIS system has improved the planning, forecasting for commodities and speed of commodity delivery.[6] If analysed with numbers of clients seen, it will also provide some assurance that commodities are reaching the women who need them. PSI, however, experienced significant stock outs, once again using the remaining commodities from the DKT International buffer stock (10-15% of all commodities). MST did not use any buffer stock in 2017. The dispensary visited during the annual review in Kigoma district was also stocked out of all methods except injectables.
  [6] Reports and requests are filled in by facilities and sent to the district pharmacist for compilation and checking before being sent on to MSD. Once packed, the requested supplies are sent directly to facilities.
- Through the new family planning programme, DFID has a new 5-year agreement with United Nations Population Fund (UNFPA) to both procure commodities (£18million) and to strengthen the supply chain system and policy influence (£4million). However, with the new funding, UNFPA will not consider buffer stock instead will work to strengthen the government supply chain to reduce stock-outs of commodities. UNFPA is planning regional commodity security meetings to improve coordination and accountability and continued support for the eLMIS and ILS gateway systems (mobile phone-based system of data collection around 20 commodities).

Recommendations on Commodities for 2018:
In the absence of buffer stock, PSI and MST need to focus on strengthening government supply chains to improve forecast, ordering and quantification of commodities.
PSI and MST, March 2018

The continued support from UNFPA on eLMIS and other methods to improve the visibility and accountability of commodities down to the Last Mile is essential and they should work closely with others such as USAID, Gates Foundation and DFID head office[7]. An analysis of facilities with particular issues is required for focus. Consider solar power for non eLMIS facilities.
[7] At the family planning summit, partners committed to improving the visibility of supplies from manufacturer right down to the woman or girl receiving contraceptives and a number of initiatives are in place to do this.
PSI and MST, April 2018

Data
- DFID assessed the quality of data that implementing partners report to determine the accuracy, reliability, timing of submission and attribution to the donor. For both partners, the findings showed some challenges relating to the data reporting. However, the Independent Data Verifier has not yet submitted the final report.
- Currently, implementing partners report the programme coverage in absolute number. This doesn’t provide a good idea of the percentage of women of reproductive age reached in respective regions to know the impact of the programme on the country’s Contraceptive Prevalence Rate (CPR).
- The implementing partners did not gain access to DHIS 2 data in the last year. MST uses its own system of data collection and PSI uses DHIS 2 data that is entered into a tablet for them by the health provider. Both implementing partners meet quarterly in a ‘data summit’ with the MoHCDEC to cross-check their data with the DHIS2 and to ensure their data is feeding into government systems.
- There are a number of data verification exercises in Tanzania done by different partners e.g. the World Bank Results-Based Financing (RBF) programme quarterly process in 7-9 regions and the health basket annual verification process. The results will inform data verification process of this programme.

Recommendations for 2018
Both PSI and MST should report quarterly on the progress of the recommendations from the data quality assessment including institutional data strengthening mechanisms to improve accuracy and maintaining the reliability of the information reported.
April 2018

The Implementing partners should prioritise the improvement of the government Demographic and Health Information System 2 (DHIS 2) data for future transitioning to using the government information system only to avoid parallel data collection.
PSI and MST, May 2018

Good documentation of initiatives that work, learning, and challenges ready for the programme completion and transitioning to the new programme.
PSI and MST, May 2018

Change the logical framework to include a percentage of absolute numbers of women of reproductive age, to give a better idea of how much actual impact this programme may have on national CPR rates.
DFID; PSI and MST, April 2018

Recommendations for future programming
1. Attempt to use independent verification of data to provide evidence for milestone disbursements as well as strengthening the national data collection system. This could be done by linking disbursements to the accuracy of data submitted by districts to the DHIS2 system, for example.
2. Consider linkages between other programmes that are already rigorously verifying data e.g. the RBF programme if feasible.
3. Consider moving away from a focus on numbers and use more quality of care and system strengthening type indicators for milestone payments.
4. UNFPA should outline a clear work plan around the use of the supply chain strengthening funds and should consider sub-contracting technical support at regional and district level if necessary.

Reproductive health in refugee camps
Women and children make up approximately 78% of the total refugee population in the 3 refugee camps in Kigoma (Nyaragusu, Mtendeli and Nduta). Birth rates for refugees remain high, with over 2,100 newly born children registered in the camps in the month of November 2017 alone. Whilst there is some access to family planning information and services in Burundi, this is largely limited to urban areas. Birth rates in Burundi remain high, on average a Burundian woman will have between 5 and 6 children, and these practices are visible in the refugee camps. However, there is significant interest in family planning information and services within the camps and scope to scale this work up. Of the 54,000 adolescent youths in the camps only approximately 14% (7,740) have been reached with age-appropriate life skills education and reproductive health clinical services.

International Rescue Committee (IRC) is the lead provider of family planning services in Mtendeli and Nduta camp whilst Medecins Sans Frontieres (MSF) is the primary provider in Nyaragusu camp. Organisations working in the camps seek to ensure availability of quality antenatal care, skilled birth attendants, newborn care, postnatal and post-abortion care. Additional training and capacity building is also provided through Marie Stopes International.

Services are also provided to prevent unintended pregnancies through access to a range of contraceptive methods for women and men of reproductive age. This includes building family planning capacity in health centres and ensuring availability of short and long-term contraceptive services. Family planning guidance is also integrated into post-natal care activities.

Both organisations are also involved in the prevention and provision of assistance to survivors of GBV. This includes building the capacity of health centres staff on clinical care of sexual assault survivors (CCSAS), direct provision of GBV case management and support and ensuring adequate supplies of essential drugs and supplies.

Summary of responses to issues raised in previous annual reviews
Issue	Status
Family planning counselling must include adequate information on both side effects and dual protection.	See above on quality of service delivery.
Informal mentoring for public health providers, especially in FP counselling and service provision should continue to be encouraged. Providers should be encouraged to participate in group & private FP counselling sessions.	Re-orientation of the public health providers on counselling for informed choice during support supervision. / Worked with the district reproductive health team to engage public sector providers during outreach teams visits for continued mentorship and learning.
In new budgeting for scale-up, a) ensure adequate numbers of IUCD insertion sets in public sector facilities and b) train sufficient numbers of staff to account for attrition.	a) There was no programme scale up as anticipated. However, implementing partners encouraged districts to order kits in advance. b) Ongoing
Implementing partners to continue to provide data for next year to allow evaluators to comment on differential effectiveness, efficiency or economy between different geographical locations.	Done but disaggregated according to age and sex. Both implementing partners should disaggregation data according to geography.
PSI needs to use Provider-initiated HIV testing and counselling. Lack of HIV test kits is an obstacle that must be surmounted.	PSI outreach team provide HIV Testing and Counselling (HTC) services during outreach services. District Medical Office provides HIV testing Kits.
As PSI adds tubal ligation to its method mix, they should work with MST to understand its tubal ligation protocols, experience, and lessons learned.	PSI did not start tubal ligation because there was no expansion of the programme as planned. Instead, there will be a new family planning which contractors will perform a tubal ligation.
Both implementing partners should remain active members in the FPTWG.	Ongoing.
DFID will need to maintain reserve commodities via Dkt International for some years longer. A follow-on programme could use a logical framework indicator to phase it out.	There is no buffer stock in the new programme design because this will create a parallel system. Instead, UNFPA and contractors will work closely with the Government of Tanzania to strengthen the supply chain to prevent stock outs.
DFID needs to consult with its fellow donors about an upcoming condom shortage in Tanzania.	Global Fund and other donors will support the supply of condoms.
DFID needs to monitor USAID FP plans and the implications of the Global Gag Rule and the US Trump budget on FP in Tanzania.	The USAID will significantly reduce funding for about 40%. USAID will share a complete plan once this is finalised. DFID will support a new family planning programme that will start in late 2018.

Output Title	CPAC. Strengthened national comprehensive post-abortion care (CPAC) in both public and private sector (including policy work)
Output number per LF		2	Output Score	A
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since the last AR?		N	Impact weighting % revised since the last AR?	N

Indicator(s)	Milestones	Progress
2.1 Number of facilities (public and private clinics) equipped and supplied to deliver CPAC	MST: 150[8] / PSI: 50	MST: 192 / PSI: 573
2.2. Number of public and private health workers trained and certified (at least 80% of those trained) in CPAC using MVA (80% of these will be public sector providers and will include government certification)	MST: 180 / PSI: 50	MST: 185 / PSI: 51 (48 more trained but not yet certified)
2.3 Number of women accessing safe post-abortion care (through this programme of support)	MST: 4517 / PSI: 5999 / Total: 10516	MST:7272 / PSI: 1378 / Total: 9650
[8] DFID changed MST log frame target after a request from the implementing partners because they were having unrealistic targets.

Key Points
This component scores an A in this review. While the programme is exceeding milestones in terms of facilities equipped and supplied to deliver CPAC, and training of health workers to provide those services, the absolute numbers of women accessing safe post-abortion care through the programme are under target for PSI (23%) and over target for MST (160%). Since the last annual review, MST revised the CPAC milestone while PSI did not request for any changes. This is the second year PSI is below the milestone (about 50% last year) because of unrealistic targets. The overall achievement of the number of women who access safe post-abortion care is by 92%.

Awareness of CPAC services is gradually increasing. The field trip and implementing partner (IP) reporting have shown some facilities carrying out large numbers of procedures while others carry out fewer than expected.

Reasons, why a fewer number of women access safe post-abortion care in the implementing partner's facilities than expected, is women have easier access to medical abortion pills from private pharmacies. There is also stigma attached to the provision of these services for both providers and users of the service. Despite value clarification, some healthcare providers feel uncomfortable delivering the CPAC services. Another reason is some clients might not receive services in the respective hubs because some hubs are far, too busy or unavailability of other important supplies such as antibiotics and blood transfusion.

Summary of responses to issues raised in previous annual reviews
Recommendation	Status
Continue CPAC training in all PSI spokes.	PSI has trained 42 Providers from 42 spokes, certification process in progress
PSI should continue to train providers in both MVA and medical abortion for CPAC.	Done
MST should add medical abortion to its CPAC training as soon as politically possible.	MST advocates for this at national level technical meetings.
PSI needs to ensure that spokes are referring women as much as possible to the hubs (where the trained providers are).	Ongoing, however, there are some challenges are highlighted above.

Recommendations for 2018
PSI should recommend realistic targets of CPAC services based on the trend of women who access the services.
May 2018

Output Title	TRAINING. GoT supported to strengthen its family planning programme, including training of public sector providers
Output number per LF		3	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since the last AR?		N	Impact weighting % revised since the last AR?	N

Indicator(s)	Milestones	Progress
3.1 Number of GoT healthcare providers trained LAPM/LARCS and certified (with supervision)	MST(cumulative): 580 / PSI: Cumulative: 300 with no training this year.	MST(cumulative): 635 / PSI: 300 whereby / 112 providers out of 175 trained in 2016 certified.
3.2 Total number of women accessing FP services in public facilities (derived from an aggregation of district data)	MST:700,000 / PSI: 200,000	MST: 3,943,447 / PSI: 116,251
3.3 Average QTA score for project teams	A score above 93%	MST: 95% (External) / PSI: 95%
3.4 All clinical incidents properly investigated and clearly communicated to all levels of Government in a timely fashion (within three days)	Yes or none	MST: Achieved / PSI: None

Key Points
- This programme works closely with the Government of Tanzania to ensure sustainability of the programme. Both implementing partners train the public health facility workers in the provision of long-term methods of family planning to encourage women to attend public health facilities for family planning services.
- This output scores an A because both implementing partners have completed their planned training and over the life of the project have trained large numbers of providers at all levels. Both implementing partners have also made a big effort to carry out on-site training and mentoring of government health workers during outreach sessions, although these are not consistently recorded. In terms of the number of women accessing family planning services, MST has achieved five times the milestone while PSI has achieved about 58% of the target. DFID would like to understand how implementing partners attribute women attendance to this programme. Both implementing partners achieved the target quality of the teams at 95%. Moreover, PSI did not have any clinical incident while MST reported and reacted immediately to the two clinical incidents following minor tearing of the ovary during the procedure and administration of family planning to a pregnant woman. Both incidents were classified as amber.
- The current recruitment freeze and the loss of many health workers who were not certified have led to significant human resource challenges, with some facilities staffed by just two people and medical attendants (one-year non-clinical training) having to play a large role in service delivery.
- The government has trained 7000 community health workers (nine-month training) but their status has yet to be formalised, including payment and scope of work so they are not working currently.
- There are also community health volunteers in every district and a small number have been used by implementing partners to mobilise women and girls before each outreach (see output 1). Task shifting of roles in Family Planning to lower level cadres has not happened to a great extent in Tanzania.
- Clinton Health Access Initiative (CHAI) has helped develop a ‘training tracker’ used by the Ministry of Health and PO-RALG to track who is trained in what areas. CHAI reports that the programme implementing partners consistently update the tracker as needed. However, the tracker cannot track staff movement. This will soon be possible when they connect it to the government system.
- During the field trip, health providers appreciated the mentoring approach used by some Non-Governmental Organisations (NGOs) where practical support is offered at the facility to a group of staff.

Summary of responses to issues raised in previous annual reviews – N/A

Recommendations for 2018
Use the last months of the programme to consolidate the training through supportive supervision and mentoring.
PSI and MST, from March 2018

Mentor teams of health workers in facilities (already being done in some cases) and record these sessions. If resources allow, consider building the capacity of a larger number of community health volunteers to provide a stronger community system for FP.
PSI and MST, from March 2018 to the end of the programme

Recommendations for future programming
1. In the next phase of the programme, budget adequately so that IPs can train sufficient numbers of staff to ensure that there are 100% in a post at the end of the training process—these means training 133% to 150% of requirement (AR 2017 recommendation).
2. Consider including a component of behaviour and social norm change through the strengthening of the community system (see also output 1).
3. Incorporate a training of trainer model at the district level and the training of district staff to carry out supervision and mentoring to improve sustainability.

Output Title	YOUTH. Young people (<20) reached with family planning (likely to be ST methods) including CPAC and SGBV
Output number per LF		4	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since the last AR?		N	Impact weighting % revised since the last AR?	N

Indicator(s)	Milestones	Progress
4.1 Proportion of all family planning services to clients aged under 20 through the outreach teams [also PSI data on youth attending the hubs]	10%	MST: 10% / PSI: 10%
4.2 Number of (public and private) programme staff specifically trained to work with or provide information, education, or family planning services to adolescents under 20 (no certification)	MST: 0 / PSI: 6 public sector; 12 Community Health Workers. / Total: 18	MST: 19 / PSI: 0 / Total:19

Key Points
- Sexual and reproductive health programming for youth is critical to improving the health, social, and economic outcomes of future generations. Supporting youth access to and use of contraception through effective policies and programmes can accelerate progress toward achieving nations' family planning goals as well as the Sustainable Development Goals and Family Planning 2020 global goals. This programme implements different activities that are youth-friendly[9] and will increase access to family planning among young people.
  [9] to create a comfortable and appropriate setting, and meet young people's needs.
- This output scores an A because both implementing partners have met the target to reach 10% young people between 15 and 19 years out of all beneficiaries of the programme. Out of all young people reached, 12 % of MST and 17% of PSI clients were reached before they get pregnant. Both implementing partners have cumulatively met targets of the number of the programme staff trained to provide family planning services. PSI has not trained this year because last year they trained 35 health providers (the target was 6 public sector and 12 community health workers).
- The situation of access for adolescents is situated within a broader environment of gender inequality and a lack of female empowerment. An estimation of the number of adolescents reached as a percentage of the total number of girls below 20 years in Tanzania would be useful to estimate the actual reach of this programme.
- As girls cannot return to school education after a pregnancy in Tanzania, trying to delay the first pregnancy in young people is essential but remains a challenge.
- A global summary of evidence-based youth FP interventions was produced in 2017 and showed the following to be effective: a strong legal-political framework; comprehensive sexuality education; community-based outreach to engage youth and provide methods; youth-friendly services providing a range of methods; and social marketing. Promising interventions were community engagement and mobilisation to build support for Adolescent Sexual and Reproductive Health Rights (SRHR) in the community and peer education.

MST approach
- As stated last year, MST has been using a two-day outreach to meet youth on the 2nd day and has also carried out promotional campaigns and sets up youth corners during outreach events. 10% of the women reached by MST are young people below 20 years. The programme prioritises young people and train staff to be ‘youth friendly’.
- MST attempts to sensitise adolescents in schools which is challenging without a change in curriculum to include Sexuality and Reproductive Health education.
- The partner is also piloting some client centred approaches this year (not part of the DFID programme). As the programme is reaching completion, it is important to document different approached used and their outcome.

PSI
PSI sub-contractor – Restless Development works through one youth peer educator per hub and also in-school and out of school youth clubs. Their orientation of young people includes some aspects of life skills but this is not a major focus.
- This year 80% vouchers were redeemed by young people and, although many still just get HIV testing, the numbers actually receiving an FP method are increasing.
- PSI has been piloting client centred adolescent programmes in a non-DFID funded programme whose findings will also inform this programme.

What services do young people use?

 Summary of responses to issues raised in previous annual reviews
Recommendation	Status
MST needs to analyse its methods of reaching youth and give DFID a sense of what is working best and where (including cost breakdowns).	Done, check the VfM session.
Both IPs should be trying to reach more young people before those young people have their first child.	Importance of shifting the way of working to addressing social norms. MST reached 12% of young people before they become pregnant.
Restless Development needs a vehicle in order to be able to supervise staff in such far-flung facilities.	Discussions took place to address the gaps though with the current funding it is difficult to solve the challenge fully
There needs to be more analysis of the Restless Development voucher redemption to determine why it is volatile across the year.	An analysis is done whereby programme is able to categorize age youth reached by age category, type of service received and FP method served

Recommendations for 2018
Both implementing partners should document their approaches to reaching youth and DFID should assess the pros and cons of both. If there is any challenge in implementing this, DFID should be notified to support the process.
PSI and MST, May 2018

Recommendations for future programming
Design the adolescent component based on current global and Tanzanian evidence. Decide whether tackling deep-rooted cultural norms around the age of first pregnancy, gender roles and empowerment are within the scope of the programme, given the extra inputs required.

Output Title	GBV. Integrated RH services for women who are victims of violence (GBV) in the public or private sectors
Output number per LF		5	Output Score	A
Risk:		Moderate	Impact weighting (%):	10%
Risk revised since the last AR?		N	Impact weighting % revised since the last AR?	N

Indicator(s)	Milestones	Progress
5.1 Number of survivors receiving post GBV care services	MST: 6332[10] / PSI: 5415 / Total: 11747	MST: 6301 / PSI: 5211 / Total: 11512
5.2 Number of public (80%) and private providers trained with good competency assessed in trainee follow-up	MST: 117 / PSI: 0 / Total: 117	MST: 124 / PSI: 38 trained and certified / Total: 162
5.3 Number of survivors referred for clinical and non-clinical services	MST: 1,502 / PSI: 1,624 / Total: 3126	MST: 1705 / PSI: 1,719 / Total: 3424
[10] Revised MST milestone.

Key Points
This programme ensures integration of Gender Based Violence (GBV) in the family planning services, recognising that women who seek family planning services are victims of GBV. This output scores an A because MST has met 99.5% milestone while PSI achieved 96.2% of the number of GBV survivors receiving care. Both implementing partners have exceeded the targeted number of healthcare providers to be trained in GBV. Referrals of GBV survivors have also exceeded the milestone by meeting 113% and 105% of the milestone for MST and PSI respectively.
- PSI has seen a steady increase in numbers of those coming forward and the range of cases. In the last quarter alone, 75 of GBV cases brought to them went to court. They are also now seeing boys who have been abused.
- Both approaches are a response only, involving the training of health care providers, selective screening, management and a safety plan. PSI has trained people in the hubs where they have a longer-term presence. Both MST and PSI refer survivors to local services which can be limited. Court cases can, for example, take months to be completed.
- Some providers interviewed felt that GBV services need to be more ‘anonymous’, located away from where they live. We also heard anecdotal stories about a village chief threatening any Sexual Gender Based Violence (SGBV ) perpetrators with the police leading to a large reduction in levels.
- The SGBV intervention, run by IRC, in Mtendeli refugee camp saw at least 5 new cases per week and between 30–95 follow up cases. Women tended to come to the IRC counsellors soon after the incidents and interventions ranged from intensive counselling, livelihood activities, referral to shelters and police/legal action.

Summary of responses to issues raised in previous annual reviews – N/A

Recommendations for 2018
Revise the GBV milestones for 2018.
PSI and MST, May 2018

Recommendations for future programming
1. In future projects, consider working on GBV prevention at the community level either as another component or a larger separate programme, given the complexities. Multiple partners will be required in order to meet the varied needs of the survivors. DFID should start to consider what their future GBV interventions will look like. (AR 2017 recommendation)
2. Consider supporting existing interventions in refugee settings. For other settings, plan a more holistic, multi-sectoral intervention, perhaps on a smaller scale focused on hotspots of high SGBV prevalence or high population concentration (urban areas).
3. It is important not to ‘abandon' all the work that has already been done in training staff – consider ways of keeping them motivated and up to date through refresher training, what's app groups, networks, further strengthening the government approach to SGBV at national, regional or district levels etc.
4. Gather global and Tanzanian existing evidence to put together best practice in this area and decide which practices can still be adopted in the coming year.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

In addition to the business case Value for Money (VfM) assessment plan, DFID has updated the programme parameters to incorporate comments from the DFID Tanzania VfM Stocktake. The added parameters are (1) Cost of training different healthcare workers in the programme and (2) Equity indicators. The review has also incorporated recommendation from the 2016 Annual Review which is to compare the cost of different methods of reaching young people.

VfM performance of the programme compared to the projections for Year 3
Estimates of VfM indicators for FP outreach, Year 3
Parameter	PSI	MST
Economy
Cost/team/year	Projection: £174,527	Projection: £ 220,165
	Achieved: £91,846	Achieved: £152,123
Cost/ training of one health facility worker (comprehensive GBV ).	-	£ 479
Cost/ training of one health facility worker (GBV Orientation).	£165.00	_
Cost/ training of one health facility worker in Comprehensive FP)	-	£953
Cost/ training of one health facility worker (CPAC). / (This does not include the follow-up post-training supervision).	£ 370.13	£249
Amortisation of capital goods	£ 37,204.00 / (2017 depreciation of 7 vehicle)	£59,023
Effectiveness
cost/DALY
cost/maternal death averted
Cost/CYP	Projection: £ 5.39	Projection: £ 5.31
	Achieved: £2.73	Achieved: £2.91
cost/unwanted pregnancy averted
Efficiency
FP Services delivered/team/year (outreach)	Projection: 20,131	Projection: 14,399
	Achieved: 9,308	Achieved: 14,504
FP Services delivered/team/year (Bajaji – three wheeler)	N/A	3,589
Long term methods of FP/team /year	Projection:10,066	Projection: 11,313
	Achieved: 8,698	Achieved: 12,141
Young people below 20 years/team/year(outreach)	940	1566
Young people below 20 years/team/year (rickshaw - bajaji)	N/A	153
% of referrals redeemed	80%	N/A
Redeem coverage monthly growth	34% between Q1 and Q4.	N/A
Cost/ one FP redemption	£ 21.10	N/A
Cost of reaching a young person with Femina Hip/ year	N/A	£0.01
Cost of reaching a young person by Youth Advisory Committee/year	N/A	£173.3
Cost of reaching a young person by sports bonanza /year	N/A	£ 10.4
Equity
Wealth -% of people classified as poor (below the poverty line)	Projection: 66%	Projection:64%
	Achieved: 50.70%	Achieved: 59%
Gender -% of men reached by the programme	36%	4%
Age - % of young people reached by the programme before getting pregnant	17% of young people	12% of young people
Age - % of all young people reached by the programme	Projection: 10%	Projection:10%
	Achieved: 9397(10%)	Achieved: 31,922 (10%)

NB: There is no baseline data for other VfM parameters.

Economy
The key cost driver of the programme is labour which mostly includes the outreach teams. In 2017, both implementing partners operated at a cheaper cost than estimated. MST has 20 DFID-supported teams whereby each team cost £ 152,123 which is 70% of the projection. In addition, each PSI team spent £91,846 which are 52% of the cost projection during the first year of the programme.[11]
[11] Refer Annual Review report 2015 for cost projection

For the first time, this review reports cost of training health facility in different skills (FP, CPAC, GBV). MST spent £ 479 the . However, this cannot be compared with PSI cost because there was no any training in GBV management this year. Instead, PSI had conducted a brief GBV orientation sessions which cost £165 for every health facility worker. Comprehensive family planning training cost MST £953 for every health facility worker reached. In 2017, PSI did not train any health provider in comprehensive family planning hence no comparison. Cost of training in CPAC was
£249 for MST and £370 for PSI; which makes PSI training more expensive.

 The training indicators have challenges because it's not easy to capture training quality. In addition, cost of training may vary from one place to another depending on the location of training, per diem cost to the government officials and duration of training. Since this is the first time to review training cost, this will be compared with the cost in the next review to get an average cost.

Efficiency
The programme is achieving most efficiency parameters. Both implementing partners have achieved the number of family planning services planned for each team. While MST has achieved the milestone by 100%, PSI has met 98% of the milestone[12].
[12] PSI uses the targets in their proposal after revision made to the milestones proposed by DFID. For long-acting, the milestone is 88320.

In terms of reaching young people, the evaluation of the number of young people each outreach team reaches shows a significant difference between MST and PSI. Each MST reaches about 1566 while PSI reaches 940 young people. This may be due to the MST’s approach of having the second day of outreach dedicated to young people. Further analysis of different costs of reaching young people shows that Femina Hip magazine is the cheapest at £0.01 per young person reached. However, there is no evidence on the percentage of young people who started to use family planning due to the magazine information. The second cheapest method is sports bonanza at £10.4 per young person reached with family planning services. DFID acknowledges that family planning information reaches more than the number of young people who received family planning services. The third initiative is the PSI’s redemption technic whereby the cost of one family planning redemption is £ 21.10. The most expensive method is the Youth Advisory Committee whereby one member costs £173. However, this is the cost of training young people whose advice shape interventions for many young people in Tanzania.

Effectiveness
The programme is effectively reaching the Couple Year of Protection (CYP) outcome with a cheaper budget than the projection. MST cost of achieving one CYP is £2.73 which is 50% of the estimated amount. Furthermore, the cost PSI spent to achieve one CYP in 2017 is £ 2.91 which is 54% of the projected cost. This is contributed by the fact that most beneficiaries of the programme (80 -90%) opt for the long-term method of family planning. DFID will calculate other effectiveness indicators (Cost/DALY, cost/ maternal mortality) in 2020 when the TDHS is out.

Equity
The programme is progressing well in ensuring equity in the delivery of services. Implementing partners reached about 50-59% of poor people. However, this is below the set milestone to reach 64-66% below the poverty line. Regarding gender, the programme reaches men as well. PSI through the youth activities was able to reach 36% men out of all beneficiaries. MST coverage of men is still low at 4%[13]. Both implementing partners actively targeted young people below 20 years and both achieved 10% of all young people benefited from the programme. This accounts for 31,922 young people for MST and 9,397 young people for PSI. Additionally, 12% and 17% of all young people reached by MST and PSI respectively have no children.
[13] This excludes men who escort women to the health clinic.

Quality of financial management
Both PSI and MST have robust financial management systems and have been cooperative with financial data. DFID checks audit reports during the life of the programme. The spend rate of the programme is on track and partners have improved in terms of providing their financial forecasts on a monthly and quarterly basis.

Both organisations give stipends to government health providers during training and outreach services. Implementing partners pay through mobile money for good monitoring and accountability. Additionally, both organisations have whistleblowing policies and there was no any fraud incident this year.

	MST	PSI
Date of last narrative financial report	31 January 2018	31 January 2018
Date of last audited annual statement	30 April 2017	11 January 2018

E: RISK

Overall risk rating: Moderate

Overview of programme risk
- Relationship with Government: Family planning still requires sensitive handling in the Tanzanian context. Recent critical attention given to pregnant teenagers as well as the ongoing prohibition of their return to school after giving birth are both indicative of prevailing social norms as well as government positioning. Nevertheless, all indications are of sustained strong government commitment to the provision of family planning services at both central and local government levels, and within the two key ministries with which the programme works – Health and Local Government. Continued close working and regular open communication with government at all levels will be important to sustain this positive commitment and dynamic going forward.
- Sustainability: The programme is set up with high levels of engagement from the Government Tanzania, including embedding of public sector health workers in the implementing partners' outreach teams, use of government trainers, curricula and certification processes, joint monitoring carried out in conjunction with District officials, use of government facilities and wherever possible use of government data management systems. This working model has significant implications for sustainability options for family planning in Tanzania, which the programme should ensure it takes into account when setting priorities. It also means the level of support government is prepared to invest is particularly important. Recent government commitment to – and partial disbursement of – funds to Medical Stores Department for the provision of family planning commodities is an important step forward. In urban areas, it may be possible to explore models involving an integration of private sector services.
- Government coordination: Recent shifts toward increased centralisation of service delivery have generated some tension between line ministries and local government. The programme can mitigate the potential impact by ensuring that meetings and consultations involve all key stakeholders wherever possible.
- Provision of CPAC services: The most controversial aspect of family planning service delivery under the programme is CPAC. There are variations in levels of comfort with the provision of CPAC services. In some facilities, health workers don’t provide services consistently. The central government position is clear, however, with health facilities clearly authorised to provide CPAC services.

Risks from previous reviews have been updated below and two new risks have been added to data quality and commodities to the last mile.

RISKS	LEVEL	MITIGATION	PROGRESS 2018
Measuring impact. One challenge of the last project has been measuring impact and the on-going changes in measurement models (e.g. the MSI Impact Calculator). This has meant that although the project has been meeting targets in terms of services delivered, the estimates of impact have fallen significantly. The models are now stronger.		This risk has largely been managed by the DFID peer review of the MSI Impact Calculator.	DFID still uses the MSI impact tool and the risk remains low.
Government commitment. There is a risk that government commitment will be reduced, and that there is increasing resentment at the reliance on NGO provision. This, in turn, can create operational difficulties and blockages for service providers, as well increasing the likelihood that NGO provision will be substituting for, rather than building, government capacity. GoT could continue to insist on lengthy training that ideally should be streamlined to increase its efficiency.		DFID and implementing partners work with the government at all levels to strengthen reproductive health policies. This will ensure more budget allocation for family planning and health system strengthening by training and supervision. Training is still long but on-site mentoring and other techniques can mitigate at this stage in the programme.	This risk continues although the Ministry of Health is supportive of the work being done on FP and the government committed its largest allocation to FP to £4.6 mil in 2017/18 from £1.7 mil in 2016/2017.
There is much sensitivity around abortion. There is a continuing risk of a political backlash against the scale-up of post-abortion care (which remains controversial). There is also an increased risk of an unsafe abortion because of the Government of Tanzania's decision to stop teenage girls to go back to school after delivery.		Value clarification with health facility workers to feel comfortable to provide comprehensive post-abortion care services. Also, increase awareness among the community and policy influence around early marriage and school re-entry policy.	This risk remains but partners still advocate for the use of comprehensive post-abortion care and the change of policy to allow teenage girls who get pregnant to go back to school.
Reaching women under 20 years of age. The programme has surpassed expectations in this area although reaching women before their first pregnancy remains a challenge.		IPs are continuing to innovate and adapt to improve this area.	Implementing partners have been able to test different methods to reach young people that this review compared.
Women who have experienced violence. Approaches for reaching women with sexual and reproductive health services are still being developed and there is much to be learned. It is possible that these women will not come forward or shun offers of service as gender-based violence carries a high stigma.		More training of health facility workers to understand how to take care of victims, engagement with the Government of Tanzania to finalise the GBV curriculum and encouraging victims to report to the health facilities for support.	The programme has reached more women with GBV services but more needs to be done to understand the best way to integrate GBV in reproductive health in the future programme.
Sustainability. There is a danger that relying on NGOs for service delivery will result in little improvement of the public sector, which in the long term must be responsible for health services. Training is just one aspect of sustainability and the programme needs to consider real ways of strengthening the systems needed for FP.		Implementing partners have been working closely with the government staff. Some areas to consolidate have been highlighted in this review.	Health facility workers are trained in the provision of family planning, CPAC and GBV care. There is also supply chain strengthening in health facilities by training in forecasting and quantification of commodities; and data management.
Data quality. A recent verification of data quality revealed some gaps. The review revealed that the data that implementing partners use is inaccurate. The reason is implementing partners don’t capture information correctly at the health facilities despite having good reporting mechanism. Other parameters scored well (accurate, timeliness and attribution of the donor).		DFID and the implementing partners are working together to address the DQA report.	To report on the progress in quarterly reports.
Supply Chain to the Last Mile. With no buffer stock this year, this will be an even more important issue.		Implementing partners need to focus on strengthening the existing system to ensure supplies are available for outreach.	DFID Tanzania is currently receiving support from the centre for ensuring commodities reach the last mile.

Outstanding actions from risk assessment. None.
This risk is becoming even more pertinent as the programme learns more about GBV.

F: COMMERCIAL CONSIDERATIONS

Delivery against the planned timeframe
Despite the delay in upscaling to ten teams last year, PSI has been able to move quickly and mostly catch up with their service delivery numbers.

On the other hand, MST has overachieved the majority of the targets. In the last year of implementation, DFID will work with MST to revise their targets considering current performance and the time remaining to complete the programme.

Performance of partnership(s)
Collaboration between partners: Part of the rationale of the decision to split the programme into two lots was to promote innovation and improved performance through competition.

Inter-partner coordination mechanism includes quarterly outreach committee meetings with all partners including Ministry of Health representatives, other implementing partners not funded by DFID and representatives of other stakeholders such as pharmacists or trainers. In 2016 MST convened an annual review meeting with all councils, bringing in representation from the district, regional and zonal levels, and from the Ministry of Health. The meeting focused on issues such as quality of service provision. DFID attended. A similar event is anticipated for 2018.

Asset monitoring and control

Assets registers for PSI was submitted in February 2018. Asset verification to PSI was carried out at the same time and established no evidence of any discrepancy between the information in the updated programme asset registers and the assets verified through a spot check.

During the last asset verification exercise, DFID found one PSI laptop under DFID funding was missing PSI/LPT/171. However, PSI could not recover this laptop from an insurer since it missed the 24 hours grace period. Going forward, PSI is constantly reminding its employees to immediately report any loss of any equipment to enable the organisation to abide by the insurance policy.

For MST, an asset register consists of items of above Tshs 4 million. All items below this value are recorded as inventories. During this review, MST was in the process of verifying and updating their inventory list hence the team could not conduct a physical verification of the same.

G: CONDITIONALITY

Update on partnership principles (if relevant) - Not applicable.

H: MONITORING & EVALUATION

Evidence and evaluation
The programme team have continued holding quarterly meetings with both IPs as part of monitoring the programme. Joint IPs review meetings have also been acting as a platform for the implementing partners to share their experience, successes and challenges. Both DFID and IPs have continued to attend Family Planning and Commodities Technical Working groups to engage with other stakeholders in the field and shape the family planning agenda.

The evidence around family planning interventions has increased a lot in the past few years including lessons learnt from programmes in Tanzania. DFID will set the future programming within this solid global and country level evidence base. Where gaps exist, DFID will carry out baseline studies and qualitative research needs assessments before the start of implementation. In addition, implementing partners should ensure it reviews whether there are adjustments to current programmes that can be made in this final year.

Youth contraceptive work – effective interventions[14]
[14] Population Reference Bureau. 2017. Youth Contraceptives use Effective Interventions.
Evidence-backed effective interventions for family planning targeting youth include:
- Strong policy framework: Ensure a strong legal-political environment that removes barriers to youth access to contraception and supports effective interventions.
- Comprehensive sexuality education: Educate young people with information regarding human development, sexuality, gender, healthy relationships, and sexual and reproductive health and rights.
- Community-based outreach: Engage youth through community-based outreach that provides contraceptive information, counselling and/or contraceptive methods directly to youth.
- Youth-friendly services: Provide a full range of contraception, including long-acting reversible contraceptives, and ensure services are accessible, acceptable, equitable, appropriate, and effective. Provide postpartum and post-abortion contraception and counselling.
- Social marketing: Combine mass media and marketing of contraception with private sector distribution channels to increase awareness of and access to contraceptive methods among youth. Promising interventions and areas where evidence is mixed include:
- Community engagement and mobilisation: Build support within the community for youth sexual and reproductive health.
- Peer education: Promote information sharing among youth social networks. Use peer educators for awareness building and referrals to services
Evidence suggests that the following do not work:
- Youth centres: Spaces in the community designed to attract young people by offering some combination of like skills training, vocational training, or recreational activities alongside sexual and reproductive health information and services has been shown to have little or no effect.
- Abstinence-only education: Educating young people about sexuality with an exclusive focus on abstaining from sex has been shown to be ineffective.

This programme will observe the recently published DFID Family Planning toolkit that emphasises programming for maximum impact:

- Family planning is best delivered as part of a comprehensive sexual and reproductive health rights package and situated within the continuum of care for Reproductive, Maternal New-born and Child Health.
- High Impact Practices are interventions with the potential for large impact in different contexts. These include post-partum Family Planning, post-abortion Family Planning, demand creation and changing social norms (including through mass media), community health workers, increasing method mix and attention to the last mile of supply chains to reduce stock-outs.
- Post-abortion Family Planning is a major opportunity, and DFID has a comparative advantage in this area because some other donors’ restrictions can make it difficult for them to support service provision to women at this time.
- Post-partum Family Planning is another important opportunity in many contexts, including to enable adolescents who given birth at a young age to delay their second and subsequent pregnancies.

Urban review (January 2018) – main findings
1. The biggest difference between rural and urban areas is the dominance of private health facilities in urban areas with, for example, up to 80% of health facilities in Dar es Salaam privately run. This presents potential challenges in terms of quality and consistency of care, as well as inequality of access to services. A major issue for the next iteration of the programme will be determining how to work with these providers.
2. Staff shortages linked to the current hiring freeze and removal of health workers without the relevant formal certificates may have a disproportionately high impact in urban areas given increasing demand.
3. For effective programming in urban areas, we need a more detailed understanding of population composition and demographic characteristics if we are to estimate coverage and also any population segments (e.g. youth, disabled, different economic classes) that are not being reached.
4. There are emerging opportunities for work on uptake and outreach in urban areas including piloting of human centred design, and outreach to address gaps in coverage (e.g. people living far away from facilities) or issues that discourage people from accessing services (e.g. the opportunity cost of lost employment income, the size and comfort of facilities, or waiting times). A sensible outreach strategy based on an understanding of these factors could be really beneficial.

Data Quality Review – main findings
The main findings of the data quality review are discussed earlier and further information is in Annex 2. DFID will follow up on the challenges highlighted in the report to ensure partners work to improve their system for good data quality.
Implementing Partners internal monitoring systems include:
- Monitoring and support mechanisms to ensure project work plans are adhered to and meet donor needs
- Data quality review and spot checks to ensure that reporting is accurate
- Technical quality assurance to ensure that services provided are of high quality
- Quarterly Joint supervision visits to a sample of Districts in conjunction with GoT representatives.
- Mechanisms to share feedback and lessons learnt between regions.
- Client feedback and exit interview studies.

People with Disabilities review
In 2017, DFID emphasised the importance of inclusion in the programme, particularly reaching people with disabilities by encouraging partners to report on this parameter using the Washington consensus. Little information is known on reaching people with disabilities in Tanzania with family planning services. However, implementing partners noted that there are some forms of disabilities such as albinism that is not part of the consensus that needs consideration when reporting on disability. The Government of Tanzania information system does not routinely report on people with disabilities.
DFID conducted the roundtable discussion with reproductive health and disability stakeholders to understand how to include this group in the programme. The findings informed the DFID Tanzania disability action plan that will be launched soon. The programme will focus on collecting data and evidence on reaching people with disabilities.

Monitoring progress throughout the review period,

Implementing partners submitted quarterly meetings to DFID Tanzania and DFID conducted a quarterly meeting with them. There were also several field visit to see the progress of the programme.
Annual review field Visits: The Annual Review team included the DFID Tanzania programme SRO and Programme Manager; representatives from the DFID global Sexual and Reproductive Health and Rights team; and DFID Tanzania Governance and Humanitarian Advisers. The process included meetings with implementing partners, other organisations and donors supporting or implementing family planning initiatives, and government representatives at central, regional and district levels. It also included visits to facilities in Dar es Salaam, Kigoma region, and Mtendeli refugee camp. It was integrated with a review of options for future programming.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / A brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output Set out the Output, Output Score
Score Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / The Risk Rating here should match the Risk currently shown on the log frame (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval? If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to log frame?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to? Include details of the last report / Have auditing requirements been met? Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How are the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / The direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process

Annexe 1. Relative Strengths and Weakness of the MST and PSI models

	Strengths	Weaknesses
MST model	Full method mix including sterilization / Reaches large numbers of women with unmet need / Reaches many facilities in remote areas / Also provides HIV testing & counselling (HTC) / One organization with no subcontractors means single organisation coordination / Able to refresh the training of public sector workers / Refers GBV survivors to strengthened public services	Less time at facilities leaves less time to build sustainability / Difficult to supervise public sector trained workers / Only able to refer to regular public sector facilities (with no additional training) / Harder to follow up post-operative problems, if any / CPAC excluded from outreach / Risk of overuse of facility commodities, if District Pharmacist does not receive notice of visits and act to allow appropriate stock accumulation (although this has improved in 2016)
PSI model	In-depth work in fewer facilities / Better training supervision / Additional partners for new work brings new ideas (CPAC, training & youth) / The static model is able to refer to trained & strengthened public sector services / Leaves sustainable and well trained public sector providers and facilities at end of the project / Allows for GBV referral to hubs and makes patient follow up easier	Does not currently include sterilization or HTC in outreach services (although they do refer clients) so does not provide a full method mix (this will change next year) / Reaches fewer facilities / CPAC excluded from outreach
Both	Incorporates public sector healthcare providers on its outreach teams / On-the-job training of public sector staff / Have a misoprostol product sold in pharmacies / Offer training in FP to public sector providers / Maintains strong relationships with GoURT	Could mean that public sector facilities ‘wait’ for the outreach team to arrive and deliver all family planning services.

Annex 2: Distribution of Family Planning Programme Implementing Partners

Annex 3: Family Planning Outreach Programme in Tanzania Exit/ Transition Strategy:
PSI and MST will provide a transition/exit plan setting out those activities that will be continued, exited or handed over (initial draft by May 2018). Where it is determined that services will be handed over, a framework for close-out will be developed.

By September 2018: Country and channel-level sustainability plans will be set out informing the basis of a transitional plan, and agreements regarding the possible transfer of services and information [this may be subject to change].

September 2018: PSI and MST will develop and provide high-level country briefs and a summary of upcoming opportunities and needs for engagement in ongoing policy and advocacy work.

October 2018: The new suppliers will organize a Transition Meeting with the incumbent. This will involve a review of the Tanzania briefs, relevant research findings and other lessons learned from the current programme.
At the start of the Handover period, PSI and MST will discuss with DFID and the new Suppliers the following:
- The current state of the Family Planning Outreach programme based on the theory of change, risks/threats, and key gaps in achieving sustainable FP, CPAC and GBV services.
- PSI and MST will provide relevant guidelines that we use for the various FP, CPAC and GBV services provided in Tanzania through the programme.
- Quality Assurance Mechanisms: an overview of the various quality assurance mechanisms used to verify compliance.
- Data: Information collected through government facility logbooks could be requested by the new Suppliers directly from the Ministry of Health.
- Training frameworks/approaches: Framework and approaches for the various types of training developed.
- Recruitment support: Job frameworks for the various service provider positions within centres and outreach will be provided.
- Evidence: PSI and MST gathered evidence over the life of the programme which will be useful to future suppliers of FP/CPAC/ GBV HIV services.
- The new Suppliers will be responsible for building relationships and creating their own agreements for future scopes of work with the Government of Tanzania, local implementing partners and other reproductive health stakeholders.