Type of Review: Annual Review

Project Title: Support towards Indian Partnership Framework (IPF)

Date started:	April 2010	Date review undertaken: March 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The India Partnership Framework (IPF) is a 5 year programme that will partner with key civil society organisations to enable them to scale-up delivery of their core development services to achieve greater poverty reduction effects in India. DFID will provide £20 million funding between 2010 and 2015.

What are the expected results?
The following high-level objectives will provide an aggregate measure of poverty impact and effectiveness of selected organisations. Each partnership will deliver results in: / development objectives (anticipated results, scale and coverage of a partner’s activities); / organisational effectiveness objectives (improvements in organisational business planning and efficiency); and / partnership objectives (strengthened collaboration and dialogue with DFID for a combined impact on poverty in India).

What is the context in which UK support is provided?
DFID support through the India Partnerships Framework (IPF) aims to work with Civil Society Organisations (CSOs) to accelerate the speed of poverty reduction in India. DFID India recognises the need to engage with a diverse set of non-state partners to deliver greater scale and coverage, and build effective and lasting institutions that can make significant contributions to poverty reduction efforts in India. / The IPF will help civil society organisations to deliver on priority areas of comparative strength by addressing two major constraints to improved effectiveness. This includes: lack of financial stability to consolidate delivery of development results at scale; and, poor capacity in middle management or preparation for transition to senior leadership. Often, this creates disincentives for organisations to plan for the long-term to achieve their full potential in influencing poverty reduction discourse and outcomes. / The IPF will help address these constraints by: / catalysing each organisation’s ability to deliver high-quality results at scale, consistent with their core comparative advantage; and, / facilitating strategic investment in business planning and institutional capability to achieve greater impact from available resources. / The IPF exists in a context of UK-India relations that increasingly highlight the importance of India’s vibrant civil society as an important source of innovative solutions to ensure more inclusive growth for India. The Government of India is increasingly recognising the role of non-state actors in leveraging solutions that can have transformative effects on the lives of India’s poorest. DFID in India is developing a portfolio of work, including with the private sector to complement the Government of India’s own efforts in this area. / IPF specifically responds to the need to directly partner with key CSOs in supporting and scaling their existing work as recommended by UK Parliament’s International Development Committee (IDC) report. The report recommended greater work with civil society in India which was endorsed by the UK Government. The IDC report was based on a multi-party visit of UK parliamentarians to India in 2011.

## Section A: Detailed Output Scoring

Output 1: TERI scales up research and programme interventions to address environmental sustainability and access to energy in India’s poorest states.

Output score: A / Progress against expected results: / The DFID-TERI partnership started in August 2011. This assessment provides an update on progress to date drawing from TERI’s own reporting, earlier visits and discussions at the DFID-TERI Steering Committee and Management Committee meetings in March and April 2012. / Overall, the Management Committee felt that TERI has made a good beginning in initiating the programme. TERI estimates that Outputs 1 and 2 have so far benefitted 150,000 people (of the target of 283,500 for Year 1). The initial phase is developing a detailed M&E approach for the partnership, including strengthening TERI’s M&E capacity. / Indicator-1: Additional number of poor Indian households adopting improved cooking energy products: Baseline-0, Target-200. / So far 100 (of the 200 target) households have been reached through TERI’s piloting efforts in 2 states. TERI has also initiated consultation with a range of stakeholders, developed and disseminated information, education and communication (IEC) material, and undertaken a perception survey with consumers. Going forward the key challenges are in working to overcome the existing gaps in commercial, technological and manufacturing capabilities that constrain the effective uptake of clean cookstoves. / Indicator-2: Additional number of poor African households adopting improved cooking energy products: Baseline-0, Target-200. / During the reporting period mapping of the existing programmes and networks in Kenya and Ethiopia has been done on the technologies and delivery modes for cooking energy. Consultations held with stakeholder and process initiated for creation of database, partner selection and MoU for partnership. / Indicator-3: Additional number of poor African households adopting clean lighting products: Baseline-0, Target-200. / The activities that were taken up during the reporting period are; Project planning and development of strategy, stakeholder mapping and engagement, capacity gap analysis of stakeholders, compilation of training modules on technical and managerial aspects of solar lighting dissemination, begun inventorisation of solar lamps in Africa, identified trial areas and field testing in Kenya, selection of solar lamp modes for field testing. / Indicator-4: Additional number of Indian households with solar lighting having access to or using functional Technology Resource Centres: Basline-0, Target-200. / A key achievement has been the launch of a state level Technology Resource Development Centre in Bihar; development of resource materials, and training of 29 Technology Resource Centres. TERI has also developed a fault reporting and rectification system which will be used by the Technology Resource Centres. Going forward, TERI will develop a business model of revenue realisation by the Technology Resource Centres so that they remain incentivised. / Indicator-5: No. of citations of TERI research in national and international journals / Too early to report. / Indicator-6: Number of patents filed as a result of TERI research / Too early to report. / Recommendations: / 1. TERI to develop a comprehensive strategy for translating research and outreach into policy formulation and implementation. This will identify prioritised areas of where we want to achieve policy change, define what success would look like, and how this might be integrated into policy plans. This will be discussed at the next Management Committee meeting (June 2012) / 2. TERI to develop a comprehensive approach for improving its own institutional capacity to plan and deliver its strategic objectives, and define how this adds value to the organisations objectives and strategies. / 3. First full review to be undertaken in July 2012; preceded by Management and Steering Committee meetings to endorse the overall approach, assess progress against annual targets, identify key challenges and opportunities. / 4. Activities to strengthen TERI’s networking systems, data storage and connectivity have begun. The Steering Committee has asked TERI to produce a more ambitious approach paper that goes beyond IT based activities, and add strategic value to strengthening organisation capacity (including human resource and financial capability). / Impact Weighting (%): 50% / Revised since last Annual Review? Y/N N / Risk: Low/Medium/High: Low / Revised since last Annual Review? Y/N N

Output 2: National membership of SEWA expanded to strengthen the national movement for women worked in the informal economy
Progress against expected results: / (i) SEWA membership / (ii) SEWA membership in DFID poorest states / DFID and SEWA have been discussing a potential strategic partnership since 2010. However the proposed IPF partnership with SEWA has not started and therefore there is no progress against the above indicators. Indirect support through UNICEF for a specific evaluation has initiated during this period. / Current Status: / A draft proposal for SEWA Bharat to deliver results in increasing numbers of women participating in self-help groups in Bihar and Madhya Pradesh is under DFID’s consideration. / Recommendations: / DFID internal team meet to consider the potential of the present proposal, including the potential for SEWA to deliver results in; / Community accountability Initiative (especially Health) / Women and work (jobs and skills) / Self help groups (strengthen, define, analytical work). / The outcome of the internal discussions should be followed up with SEWA. / Impact Weighting (%): 50% / Revised since last Annual Review? Y/N N / Risk: Low/Medium/High: Low / Revised since last Annual Review? Y/N N

## If the project involves more than 4 Outputs please copy the box above and paste below.
## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Y/N NO / 1.2 Overall Output Score and Description: A / The purpose of the framework is to strengthen the strategic capability of selected partners to contribute to poverty reduction efforts in India. Currently there is only one partnership in the project i.e TERI. Progress against output indicators is satisfactory. Efforts are on to engage with SEWA which works on issues of women empowerment and a range of other potential partners (including Public Health Foundation, Digital Green, CII, FICCI). / 1.3 Direct feedback from beneficiaries: / This reporting is based on interim assessment drawn from TERI’s own reporting and discussions at DFID-TERI steering and management committee meetings. A field level review has not happened since the IPF arrangement initiated although earlier visits did take place. Therefore direct feedback from beneficiaries is not available.
1.4 Summary of overall progress / TERI has made a good beginning in initiating the programme and has so far benefitted some 150,000 people (of the target of 283,500 for Year 1). DFID and TERI propose to initiate an evaluation of the partnership. The initial phase will help to develop a detailed M&E approach for the partnership, and will also make recommendations on strengthening TERI’s M&E capacity. / There has been limited progress on certain outputs such as on policy formulation. TERI has initiated some consultations with Government of India (Department of Personnel and Training) on the development of a Wikisustainability tool as an on-line platform to share information. The Steering Committee has recommended that TERI develop a comprehensive prioritised strategy for this output / SEWA proposal is still being developed. Progress has been slow. A number of other potential partnerships have been identified (including Public Health Foundation, Digital Green, CII, FICCI).
1.5 Key challenges / The process of these potential partnerships, involving detailed appraisal work, finalising key results and ensuring their fit with new forward priorities has been time intensive, especially at a time of numerous competing demands.
1.6 Annual Outcome Assessment / The project is contributing to strengthening the strategic capability of TERI such as in the areas of planning delivery, monitoring and evaluation, policy influencing. TERI project has made steady progress against outputs and is expected to improve the lives of about 400,000 women. / Limited progress has been made in developing partnership with SEWA or other organisations. A focussed effort is required to finalise an approach to developing new partnerships.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y/N / There was a forecast of £750,000 however £220,000 has been spent during the reporting period. The reason for less spending is the delay in start of the project. The DFID-TERI partnership started in August 2011. / 2.2 Key cost drivers / DFID plans to provide funding up to £20 million over 5 years as technical assistance to various partner organisations. / So far an Accountable Grant has been signed with TERI and the funding is being provided for areas such as professional costs, capacity building and networking, hardware (cook stoves and Technology Resource Centre), equipment, publications, workshops. / 2.3 Is the project on-track against original timescale: Y/N / There was delay of about one year in the start of TERI project. Limited progress has been possible in developing other partnerships.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Too early to asses the changes. The initial appraisals indicate that the programmes selected for potential support will reach the underserved and the marginalised. / 3.2 Where an evaluation is planned what progress has been made? / No evaluation was planned during 2011-12. A mid-term progress assessment and a full evaluation will be conducted to establish how well the TERI partnership has progressed, its achievements and impacts. The full evaluation will be carried out at the end of the funding period (April 2015). The evaluation will review the development and partnership objectives and assess their impact.

4. Risk
4.1 Output Risk Rating: Low/Medium/High: Low / 4.2 Assessment of the risk level / The overall project risk is assessed as low. Although some potential partners have capacity constraints, the partnerships will be designed to mitigate these.
Risk of funds not being used as intended / Risk of funds not being used as intended is not material. An initial assessment is always done to assess the partner’s capacity to use funds for intended purpose. The project helps the partner to further build this capacity and conducts on-going rigorous financial management assessments, including payment in arrears. / 4.4 Climate and Environment Risk / TERI Specific issues: / The positive contribution of the TERI partnership to climate and environmental risk is expected to be around infrastructure/hardware/tools; up scaling of solar photovoltaic systems; environmental safe technical options and disposal of batteries/system; infrastructure provision through environmental safe materials; cooling energy device-fuel processing, gasification, micro-enterprises; water and sanitation infrastructure; e-waste guidelines and training facility. Ensure that any infrastructure is environmental safe, low carbon and resilient to climate variability and climate change.

5. Value for Money
5.1 Performance on VfM measures / Too early to assess as the DFID-TERI partnership started in August 2011. The project has so far spent £ 220,000. / 5.2 Commercial Improvement and Value for Money / DFID received a proposal from TERI which was reviewed by the DFID team. DFID signed an Accountable Grant with TERI in August 2011 after they fulfilled the eligibility criteria set in the project memorandum. The procurement guidelines as prescribed in the Accountable Grant letter that should yield good VfM for the project spends. / 5.3 Role of project partners / The project is about strengthening the strategic capacity of partners in implementing poverty reduction initiatives. All the projects under this framework will be implemented by civil society partners. / 5.4 Does the project still represent Value for Money : Y/N / Too early to say at this stage. / 5.5 If not, what action will you take? / N.A

6. Conditionality
6.1 Update on specific conditions: None

7. Conclusions and actions
IPF has progressed satisfactorily on Output 1 with TERI and the first annual comprehensive review is scheduled for July 2012. / The current IPF review also took stock on how the Project intends to meet the overarching IPF Goal of increasing the impact of Civil Society Organisations on improving the lives of the poorest in India. There is a case to be made for IPF to further refine its focus in order to highlight how such transformative effects for the lives of the poorest can be achieved through CSOs. The current approach of IPF is to partner with leading Indian CSOs to better undertake their existing work in India. CSOs have the potential to provide transformative effects through better building information among poor communities and in empowering these communities to hold services accountable. Technology is an important enabler for CSOs delivering on this potential. / To maximise the impact on the development, organisational and partnership objectives this review suggests IPF be used as a platform to further focus on three pillars through which CSOs can deliver change and impact: (1) Information to the currently excluded and the poorest; (2) Empowerment through their greater participation and action for change; and (3) Innovative approaches, potentially using technology applications, that enable better information and empowerment. / In line with this suggested sharpened focus for IPF, discussions with Digital Green have reached an advanced stage. Digital Green have an objective “to apply an evidence-based, cost-effective and locally relevant ICT-enabled knowledge exchange, behaviour change and accountability model to improve food security and health outcomes of rural communities in India”. There will be clear results through such IPF support to Digital Green built upon the three pillars of information, empowerment and innovative use of technology. The expected outcomes from IPF support to Digital Green are that at least 21,600 rural households involved in agriculture programs and at least 14,400 rural households involved in health programs adopt at least one new practice that improves the lives of the poorest. / The IPF Project Memorandum had listed a number of leading CSOs for potential partnership through IPF support. It is suggested that the IPF be used to continue discussions with CSOs listed in the Project Memorandum as well as newly identified partners that can significantly benefit from IPF and be catalytic in delivering on the broader IPF goal and its expected results relating to (i) development objectives; (ii) organisational effectiveness objectives; and (iii) partnership objectives.

8. Review Process
The review was based on the desk work by DFID team, reports from TERI was used.