DFID SECOND ANNUAL REVIEW
PHASE III SUPPORT OF NIGERIA’S DEBT MANAGEMENT OFFICE
EXECUTIVE SUMMARY
DFID retained two consultants, Menachem Katz and Zakari Momodu, to review the progress in the second year of Phase III of DFID’s assistance to Nigeria’s Debt Management’s Office (DMO), guided by DFID’s template for annual reviews. During the week of September 12-17, 2011, the consultants held meetings in Abuja with the DMO and other key stakeholders.
Overall, the DMO has come a long way since its creation, turning from a user of technical assistance (TA) to also a provider of TA. The DFID Project has played an important role in the DMO progress. DFID’s Phase III focuses primarily on training, which has been associated with growing skills, greater professionalism, and a build-up in long-term human capital.
The mode of intervention of Phase III, consisting of a non-resident Project Manager and a DMO liaison person on the ground (the Project Coordinator), has enhanced ownership and enabled the support to be applied more flexibly and be more closely linked to DMO’s priorities and needs.
DMO’s operations in the primary bond market have improved in the past few years, as its staff have gained experience and have benefitted from training, supported primarily under the DFID project. Its ability to read and analyse market conditions, plan, consult with key stakeholders and market participants, have all been important contributing factors to these improvements.
DMO has demonstrated initiative and innovation in addressing emerging needs both in the Office and the market. It is, for instance, in the process of introducing commercial paper, to gain greater flexibility in off-date issues; it is also discussing the possibility of issuing indexed bonds, and other such instruments.
The initiative supported by the DFID project of institutionalizing debt-management best practices in the states through the setting up of DMDs is commendable. Since inception in 2009, the initiative has covered 22 out of 36 states, building on the 6 pilots supported by the Project, which has enabled the DMO to develop a credible data base of the domestic debt of these sub-nationals.
Other efforts in the year under review to improve the institutionalization and sustainability of the DMO and debt management best practice under the DFID support included, the establishment of the Public Debt Management Institute (PDMI) and the assistance provided to Governments of Zimbabwe and Sudan and the improvements to personnel management through the recently introduced staff evaluation and career development system as well as the preparation of a Communication Strategy.
However, to move to a higher plateau of performance there is a need to pay close attention to the following:
Implementation of a medium-term debt management strategy (MTDMS). While the domestic debt market more than doubled since 2005, it remains shallow, which constrains efforts to lengthen its maturity structure. The DMO’s revised strategic plan (2008-12), which provides broad guidance on DM, has been instrumental so far. Going forward however, there is a need to develop capacity for a medium-term debt management strategy based on cost-risk analysis which should guide the composition of debt, and the Project can support this area. The World Bank draft report and expected follow-up work should help guide the process. Also, there is a need to develop capacity for analysis and recording of contingent liabilities, including PPPs.
There is a need to adopt a communications strategy and an action plan building on a recent consultant’s report. For instance, the media retreat of February 2011 could have been handled differently, as part of a broad strategy with cost/benefit analysis. DMO also needs to enhance it communication with stakeholders such as MOF and CBN, and resume the quarterly monetary-fiscal policy meetings. More generally, a Monitoring and Evaluation (M&E) approach should become an integral part of DMO’s operations.
DMO’s work on institutionalizing debt management (DM) best practice at the sub-national level merits continued support, particularly as it contributes to a sustainable DM “culture” in Nigeria. In this regard, the DMO should also encourage states to collaborate with one another on DM practices.
There is a need to make the business model of the Public Debt Management Institute (PDMI) robust.
On staffing, the practice of frequent staff rotations needs to be re-examined and its impact on effectiveness of units within the DMO evaluated.
The final year of Phase III should focus on supporting the MTDS, PPP and contingent liabilities as well as the adoption of a communication strategy, and an M&E approach.
Finally, DFID estimated annual support under Phase III constitutes about 160 million naira compared with a 300 million Naira DMO overhead budget (excluding DFDI support). An abrupt withdrawal of such a level of support could be disruptive. Hence, consideration should be given to targeted support post Phase III for DMO’s work with sub-nationals, perhaps through the PDMI.
The Annex provides the reviewers’ evaluation in the DFID Annual Review template. The overall score is 2 -- “medium-high” (on a scale of 1 to 5, with 1 being the highest).
On the methodology of the review, it is worth noting that performance of the DMO is gauged against yard sticks that are sometimes outside its control. While the DMO performance can be measured on its activities towards creating an enabling environment, the reviewers are not fully convinced that the DMO can be measured against the yard stick of bond trading at a premium. This suggests that perhaps the tools for assessing its performance may need to be refined.
DFID SECOND ANNUAL REVIEW
PHASE III SUPPORT OF NIGERIA’S DEBT MANAGEMENT OFFICE
I. Introduction
DFID retained two consultants, Menachem Katz and Zakari Momodu, to review the progress in the second year (August 2010 – August 2011) of Phase III of DFID’s assistance to Nigeria’s Debt Management’s Office (DMO), guided by DFID’s template for annual reviews. During the week of September 12-17, 2011, the consultants held meetings in Abuja with the management and various departments and units of the DMO; the Ministry of Finance; the Central Bank of Nigeria; the Securities and Exchange Commission, heads of Debt Management departments of four states: Abia, Bauchi, Kogi, and Osun; and with two Primary Dealers and Market Makers (PDMM) of the United Bank for Africa, and First Securities Discount House (through a conference call).
DFID’s support to debt management in Nigeria began in 1998, predating the establishment of the DMO in 2000 and its full launching as an autonomous agency in 2003. Phase I focused on building the institutions to manage Nigeria’s debt, while Phase II focused first on obtaining debt relief--the reduction of Nigeria’s external debt with Nigeria’s exit from the Paris Club in 2005 reducing its official debt by some US$30 billion through a combination of US$18 billion write-off and a US$12 billion payoff of the remaining balance. The London Club resolution was equally successful, with a cash payoff of US$1.5 billion and an exchange of notes for the remaining US$0.5 billion. Following the debt deals the focus of Phase II shifted to managing Nigeria’s public debt on a sustainable basis. In this phase DMO shifted its focus from reducing external debt to the implementing of policy, advising, and institution building for sustaining a successful national debt management policy.
 Phase III aims to enable DMO to consolidate its capacity to manage public debt effectively. The project is monitored against delivery of the following outputs:
a. DMO delivers an effective market for Nigeria’s domestic debt;
b. DMO improves state-level debt management through support to Debt Management Departments (DMDs);
c. DMO facilitates Nigeria’s external debt sustainability while establishing a viable presence in the international capital market; and
d. DMO contributes to a more conducive and supportive institutional environment for efficient and sustainable debt management practices in Nigeria.
This report reviews progress in the four areas above consistent with the log-frame. It then seeks to answer the following questions: (i) has the mode of intervention been effective and has the project delivered value for money; (ii) what factors contributed to the success of DFID’s support to DMO and what lessons can be learned and applied elsewhere in Nigeria. The final section lists recommendations: (i) on what should be the focus of DFID support under the final year of Phase III; and (ii) on whether DFID should continue to support the DMO post Phase III.
 The Annex provides the reviewers’ evaluation in the DFID Annual Review template. The overall score is 2 -- “medium-high” (on a scale of 1 to 5, with 1 being the highest).
On the methodology of the review, it is worth noting that while the DMO can determine the number of PDMMs, it is limited in its ability to determine the performance of the markets (particularly the secondary market) once it has put in place the enabling and supporting environment. The impact of the global and domestic economic challenges and the peculiarities of participants’ demands are outside its control. Consequently, while it can be measured on its activities towards creating such an enabling environment, the reviewers are not fully convinced that the DMO can be measured against the yard stick of bond trading at a premium. This is not to relieve the DMO of its responsibilities but merely to highlight that perhaps the tools for assessing its performance may need to be refined.
II. Progress in meeting Phase III Objectives
Progress under Phase III has generally been good. The DMO prepared a National Debt Framework for 2008-12, which was updated in June 2010. Under the framework the DMO has moved to strengthen the efficiency of the primary bond issues, engages with states to develop DMDs, issued bonds in the international market to establish a benchmark price, and has taken steps to strengthen the institutional capacity for debt management. While some of the milestones in the log-frame, such as the passage of the Amendment to the 2003 DMO Act, are beyond the direct control of the DMO, in other areas such as the introduction of a medium-term debt management strategy (MTDMS), there have been delays vis a vis the time tables of DMO and Phase III.
A. DMO delivers an effective market for Nigeria’s domestic debt.
DMO’s operations in the primary bond market have improved in the past few years, as its staff have gained experience and have benefitted from training under the Project Support. Its ability to read and analyse market conditions, plan, consult with key stakeholders and market participants, have all been important contributing factors to these improvements.
The domestic debt market more than doubled since 2005. Maturities have been extended to 20 years, yields have declined and an incipient secondary market has developed. In December 2009 Fitch Ratings upgraded Nigeria’s local currency long-term rating to “BB” reflecting the “impressive development in the domestic debt market” (since the rating was first assigned in 2006). These developments notwithstanding, the shallow nature of the market continues to constrain efforts to significantly lengthen the maturity of the domestic debt portfolio.

     Table 1. FGN BOND ISSUANCE STRUCTURE 2009 – AUG. 2011 (N MILLION):

Original Tenor	2009 Allotment	% of total allotment	2010 Allotment	% of total allotment	2011 Allotment	% of total allotment
3-Year	286,500	39.44%	461,995	37.12%	333,500	54.81%
5-Year	190,000	26.15%	237,332	19.07%	225,000	36.98%
7-Year	-	0.00%	62,810	5.05%	-	0.00%
10-Year	30,000	4.13%	70,000	5.63%	50,000	8.22%
20-Year	220,000	30.28%	412,303	33.13%	-	0.00%
Total	726,500	100.00%	1,244,440	100.00%	608,500	100.00%

N: B Figures include non-completive allotments

FGN BOND AUCTION PERFORMANCE 2009 – AUG. 2011:
2009
Original Tenor	Average size of issuance (mil naira)	Average size of subscription (mil naira)	% of subscription	Average size of allotment (mil naira	% of successful allotment
3-YEAR	23,636	40,787	173%	26,045	110%
5-YEAR	21,111	36,985	175%	21,111	100%
10-YEAR	15,000	33,158	221%	15,000	100%
20-YEAR	19,455	44,823	230%	20,000	103%
Overall	21,030	40,633	193%	22,015	105%

2010
Original Tenor	Average size of issuance (mil naira)	Average size of subscription (mil naira)	% of subscription	Average size of allotment (mil naira	% of successful allotment
3-YEAR	28,333	68,822	243%	38,500	136%
5-YEAR	22,778	45,383	199%	26,370	116%
7-YEAR	9,791	9,445	96%	6,979	71%
10-YEAR	23,333	52,501	225%	23,333	100%
20-YEAR	30,833	65,912	214%	34,359	111%
Overall	29,809	62,999	211%	34,568	116%

As at August, 2011
Original Tenor	Average size of issuance (mil naira)	Average size of subscription (mil naira)	% of subscription	Average size of allotment (mil naira	% of successful allotment
3-YEAR	32,688	76,059	233%	41,688	128%
5-YEAR	32,143	71,304	222%	32,143	100%
10-YEAR	25,000	44,132	177%	25,000	100%
Overall	31,559	70,345	223%	35,794	113%

Source: DMO; September 16, 2011
Domestic debt comprises mainly marketable securities. These are issued as Nigerian Treasury bills (NTBs) with maturities of 91-, 182-, and 364 days, and Federal Government of Nigeria (FGN) bonds with tenors ranging from 3-, 5-, 10, and 20-year maturities. The gross issuance for market borrowing increased considerably between 2009 and 2010; in the first 8 months of 2011 it is about half that of 2010 (Table 1). The domestic debt strategy has been to elongate tenors and maintain the outstanding stock of short-term NTBs at 25 percent of the total. As table 2 demonstrates, this ratio has not been fully maintained. Currently, the pension funds and the insurance companies in Nigeria are primarily invested in the medium-term maturity range of 3-5 years, and prefer not to invest in longer term paper. The DMO has so far in 2011 not issued new 20-year bonds. This may be partly explained by the prevailing negative yields in real term for longer maturities and investors’ preference for more liquid instruments. In addition, the crisis in the stock market and in the Nigerian banking sector caused pension funds to incur losses and as a result they shifted their holdings to quality assets, including FGN bonds.
The DMO prepares an annual borrowing plan based on the financing need of the FGN. Prior to the monthly auction it consults with key stakeholders—CBN departments, Primary Dealers and Market Makers (PDMMs), and market participants. In discussions with the Reviewers, CBN departments involved in the bond market, representatives of the PDMMs, and the SEC all noted that DMO, in its preparatory work for auctions, market analysis and the conduct of the auctions, has demonstrated professionalism and efficiency.
 The share of “captive” investors (Banks & Discount Houses) has been at the range of 65 to 67 percent during the period 2009 to August 2011 due to persisting instabilities in the domestic and global economies, as well as the need by banks to respect prudential requirements, and is unlikely to change significantly in the very near future.
The number of primary dealers and market makers (PDMMs) has essentially been maintained since the introduction of the system. There are twenty (20) in all following the merger of two (2) PDMMs. Following the most recent banking crisis and the reform measures underway to strengthen the financial sector DMO intends to carry out a comprehensive review of the PDMMs to ensure that all primary traders continue to meet the requirements.
Secondary market activities, for which DMO has little direct control, have actually declined by over 40 percent from 2009 levels (with an estimated 72,000 trades in the first eight months of 2011 from 158,000 in 2009 valued at approximately N9.7 trillion and N24.2 trillion, respectively). To help develop the secondary market procedures for secondary market activities have been standardised and an Interbroker Dealer, ICAP Plc, is expected to commence operations upon the receipt of regulatory approvals; a timetable for this was not provided to the Reviewers.

Progress in the (market-related) IT area has been slower than targeted as IT systems in the market are not yet fully integrated, largely for factors beyond the control of DMO and the Project. However, DMO continues to improve and update it’s IT infrastructure and a DFID-funded consultant conducted a system review for the Primary market in 2009/10. The DMO is also working with the Commonwealth Secretariat to develop the necessary interface capability between the DMO's CS-DRMS and the CBN's T-24 systems. It has recently received approval for the adoption of an effective IT System for Auctioning of FGN Bonds. The review of the best auction platform for the DMO was one of the first activities funded under Phase III of the Project. Necessary appropriation has also been obtained and implementation is set to follow, though a clear timetable was not provided to the Reviewers.  An Interdealer Broker, ICAP Plc, is also anticipated to be in place by Q1 2012.   Together with the PDMM driven IT platform upgrade for the secondary (OTC) market, these should enhance the overall IT infrastructure.

Table 2. National (Fed & state) debt profile / (Domestic debt for FGN only)
	2008	2009	2010	June 2011
Debt-mix / (60/40 ratio)	Domestic * (82.61)	Domestic*(84.71)	Domestic* (86.95)	Domestic* (86.41)
	External (17.39)	External (15.29)	External (13.05)	External (13.59)
Outstanding domestic debt by tenor (75/25 ratio)	Long-term (74.47)	Long-term (75.30)	Long-term (71.30)	Long-term (70.03)
	Short-Term (25.53)	Short-Term(24.70)	Short-Term (28.06)	Short-term (29.97)
Proportion of external debt by Concessionality	Concessional (77.00)	Concessional (86.42)	Concessional (92.71)	Concessional (87.5)
	Non-Concessional (23.00)	Non-concessional (13.58)	Non-Concessional (7.29)	Non-Concessional / (12.5)
Total Public Debt/GDP (%)	11.77	15.37	17.98	20.29

Source: DMO
While publication of the borrowing plan for the budget year is a key component in enhancing transparency in the market, the uncertainty and delays in the approval of the federal budget have made cash management challenging. To enhance DMO’s capacity in this area training was conducted for DMO staff by a DFID Consultant (Mr. Steylaers) on ‘Building Capacity in Cash Management’ in Feb. 2011. And relevant government agencies involved in the cash management process were sensitised. One of the outcomes of the above is the planned introduction of Government Commercial Papers (CP) to meet short term funding gaps between scheduled auctions. To this end DMO has developed a framework for the issuance and redemption of FGN CP and is working with the OAGF and CBN on implementation.
To help with the coordination of monetary and fiscal policies the DMO initiated a fiscal monetary policy committee with the CBN, FMF, OAGF, and NPC. The committee, which would meet on a quarterly basis, last met in July of 2010. This forum provides the DMO an operational opportunity to express its concern with the expansionary fiscal policies of recent years and the rapid rate of growth of the domestic debt and its implications on the bond market and interest rates.
The MTDMS which was to be adopted in 2010 is not yet in place. DMO continues to be guided by the "National Debt Management Framework" and its "Revised Strategic Plan 2008-2012". The framework expressed as general guidelines with a mix of external and domestic financing of the budget deficit, and the share of short and long-term financing has served the government well thus far. This and the active policy to develop the domestic debt market have helped Nigeria minimize the effects of the global financial crisis. Going forward, a debt management strategy that is informed by the cost and risk consequences of alternative debt management strategies will be needed to deal with the probability that contingent liabilities materialize and growing financing needs for infrastructure investments.
The DMO is working with the World Bank and IMF to develop a suitable MTDMS. A joint World Bank - IMF mission visited Nigeria in February 2010 but the draft report has still not been finalized. A follow-up mission is planned for October 2011.  DMO indicated that a consultant has been identified to work with the Office in the first half of 2012 to begin implementing the new MTDMS.
B. DMO improves state-level debt management through support to Debt Management Departments (DMDs)
Progress in getting the DMO to build a buy-in from states has to be viewed against the backdrop of the constitution and fiscal federalism under which states are for all practical purposes independent entities in their relations with the FGN. Hence, the DMO’s success in engaging with states and developing a constructive relationship with them, following the successful implementation of the Project supported 6 pilots, is all the more remarkable. Relying considerably on “diplomacy”, enthusiasm of its staff and interest of state officials for this exercise the DMO has made headway and continues to actively engage the states at multiple levels to facilitate the completion of this exercise.

Since the last review twelve (12) additional states have completed the collation and reconstruction of their domestic debt data bringing the total to twenty two (22) of the thirty six (36) states. DMO’s plan is to complete all remaining states during 2012. Furthermore, eleven (11) states completed post-DDR exercises to monitor their progress during the review period, and capacity building and support continues for a number of target states. Since the last review, in August 2010, only four (4) more states have passed a debt management law in the form of either a Fiscal Responsibility Law or Public Debt Management Law bringing the total to fourteen (14). However, eleven (11) states have draft FR/PDM Bills before their state legislatures. As part of the institutional capacity building at state level, DMO is developing a framework of for a state-specific debt strategy including adapting the DSA framework to states.

The Reviewers met with representatives of DMDs of four states (Abia, Bauchi, Kogi, and Osun). These states are at different levels in terms of progress in institutionalizing debt-management best practices. They were all highly appreciative of the work performed by the DMO in helping them establish and build debt management capacity in their respective states.

DMO reported that all stakeholders have been sensitised and educated on the on-lending framework, but this was hard to verify by the reviewers, particularly as some officials of the Federal Ministry of Finance were unable to provide definitive answers on government guarantees issued and the Reviewers did not have an opportunity to question state government officials on this point.

C. DMO facilitates Nigeria’s external debt sustainability while establishing a viable presence in the international capital market
The Debt-to-GDP ratio has risen with the expansionary fiscal policies of the past few years but is being maintained at a sustainable level (20 percent as at June 2011 from 12 percent in 2006 and 15 percent in 2009).

The emphasis on Concessional borrowing has remained and the DMO continues to focus on maintaining debt sustainability at well below the 40 percent overall benchmark (Chart). As Table 2 above demonstrates, the share of external debt has been kept at below 15 percent and much of the external borrowing has been on concessional term.

In January 2011 Nigeria issued a US$500 million 10-year Eurobond ostensibly to benchmark the price of the country’s debt in the international capital market and thus facilitates the private sector’s access in raising financing for capital projects in the future.  The bond issue which had to be delayed because of unfavorable international market conditions appears to have been successful—it was oversubscribed and the yield has come down since the issuance.
The DMO is conducting an annual DSA (the most recent one for 2010 was posted on its web site) but the exercise does not yet cover contingent liabilities or PPP.   The framework on contingent liabilities (including PPPs) is not yet completed, and PPP guarantees/support have not yet commenced. However, The DMO is collaborating with the Infrastructure Concessioning and Regulatory Commission (ICRC) to develop a framework for infrastructure financing.
.
Source: DMO

D. DMO contributes to a more conducive and supportive institutional environment for efficient and sustainable debt management practices in Nigeria
Several initiatives are under way to strengthen institutional capacity at DMO, including HR, communications, IT and the PDMI.
To improve personnel management, the DMO, with the support of the Project, has recently introduced a new staff evaluation and career development system. This follows a consultants’ study (prepared during October 2010-March 2011) supported by Phase III of DFID’s project. The report consists of a standardised framework of job descriptions and a global competency model, on the basis of which employees’ performance is to be evaluated. The Reviewers have not received any documentation on the actual implementation of the HR reform. At a meeting with the Reviewers, DMO staff noted that the reform is in effect and the first round of performance assessments will take place at year end. The assessment will also include a career development component for all staff.
On staff remunerations, several senior staff at the DMO who came from the private financial sector have noted that they had left the private sector to join DMO because of the work challenge, but having incurred pay reductions of up to 75 percent (in at least one case), they may not be able to “afford remaining at DMO for much longer”. In this regard, the reviewers requested data on recruitment, retention and departures of staff, to be informed that there were no problems with the ability of the Office to recruit and retain quality staff; while no documentation to that effect was provided to the reviewers, the Organizational Resource Department reported that since 2009 21 permanent and 5 temporary staff were recruited (at junior and mid-levels), 32 promotions took place (that included 7 drivers though), and there were 6 resignations, 5 secondments, and 49 redeployments out of a total staff of 110.
The involvement of a large number of disparate stakeholders in the DM process places a unique emphasis on continuous and in-depth stakeholder engagement, both at the global and individual levels, and this is where a robust and dynamic communications strategy can be instrumental. The emphasis on such engagement is to try to mitigate the risks and challenges posed by the DMO limited powers to directly influence the various institutions and processes that affect the country’s debt profile.
A report supported by the Project and entitled: “DMO Communications Strategy – Stakeholder Analysis” was produced in July 2011 by Mr. Akinlose Arikawe (a former DG of the DMO). The report (which includes an implementation guide) makes specific recommendations on how to strengthen communications with both internal and external stakeholders, and calls for developing operational manuals, and the resumption of the issuance of a newsletter (the most recent DMO newsletter on the web is dated December 2007).
Hence, there is a need develop a communications strategy and an action plan building on the recommendations of the consultant’s report, which would include setting up a dedicated unit and developing continuous lines of communication and data dissemination to stakeholders, including the media.
The IT system of the DMO is being upgraded in accordance with its strategic plan (Table 7 of the revised Strategic Plan, 2008-2012). Importantly, an IT standardisation survey was conducted last year and its recommendations have been adopted by DMO’s management consistent with the plan.
The Public Debt Management Institute (PDMI) was set up in March 2011, also with the support of the Project and consistent with the DMO’s medium-term strategic plan. The PDMI conducted a two-week Train the Trainer programme in Lagos in August and has already provided TA to the governments of Zimbabwe and Sudan. It will be important to examine the potential markets of sub-national governments in Nigeria and governments in Africa (and perhaps elsewhere) and on this basis develop a robust business plan. Critically important in this regard will be the passage of the Amendment to the 2003 DMO Act, to enable the Office to collect and retain fees for service.
Finally, to enhance efficiency and effectiveness, and value for money analysis, it is important to develop a monitoring and evaluation (M&E) approach and the Project should look at including this in its plans for its remaining year. Such a framework, which should not be confused with the existing internal audit function, would enable the DMO management and staff to assess the effectiveness of its operations and policy and institutional choices on a continuous basis; it would also provide useful documentation to external reviewers.
E. Project management and value for money
The Project Management Model adopted here is a novel one and appears to have served both the DMO and DFID well thus far. It has allowed and leveraged on the DMO’s ownership of the Project objectives and flexibly adapted to the dynamic needs and peculiarities of the DMO. It is definitely worth further development and possible replication.
The project model relies heavily on a high degree of trust and competence in the on-ground project coordinator and team, and quick responses of the project manager and monitoring authorities. In this case DFID support has been provided continuously since the creation of the DMO and the latter can be viewed as a “mature user” of support, and the management of the beneficiary agency/institution has been willing to overcome any inhibitions towards dealing with the in-house coordinating team on an objective level. The biggest potential weakness of locating the Project Manager off-site and out of the country could be the limitation on their ability to ensure cost control and value for money on component spending (e.g., the Kaduna media event), although it is not entirely clear that the location of the project manager was the root cause of this laxity in scrutiny.
Table 3 below provides a breakdown of the second year under Phase III budget, showing that the funding was by and large targeted at training and capacity building. These appear to be broadly well spent as evidenced by the relatively high morale, confidence and capacities of the beneficiary DMO staff. The Project's support to stakeholder awareness activities and IT development have also proved to be good value for money as these two components are integral to the DMO's activities and success. The levels of awareness, skill and IT applications, while still in need to enhancing, are considerably higher than those that exist in other comparable government institutions. And the DMO's partners attest to this and clearly appreciate the efficiencies derived therein. It is expected that as the Staff Appraisal and Communication Strategy reports are fully adopted and embedded, the DMO will reap even more benefits in enhanced efficiency, productivity and sustainable institutional growth. Among the large budget items are three media events, the largest of which was the Kaduna retreat with journalists in January 2011, which should have been subjected to greater scrutiny. In the presence of a well developed communications strategy and an M&E framework, a different approach could have been chosen for developing durable relations with the Nigerian media.

Table 3. DMO Phase III: YEAR 2 project activities to August 2011

Capacity Building
	GBP
Bulk Training Phase III	343,338
CS-DRMS Training for DMO staff and States (ComSec)	20,749
Train the trainer for Public Debt Management Institute (FITC)	31,234
Building Capacity on Cash Management Capacity Building/Rec. on Commercial Paper	18,719
Training of 5 VP’s office staff	21,327
SAP training – DMO delegates	37,732
Total	473,099

Other events and technical assistance
Debt Data Reconstruction (DDR) for 6 States	63,714
Three Media Events (Kaduna/Lagos/Abuja)	95,886
Study Tour to Brazil for 18 Delegates for Nigeria	59,402
Optimal Primary Auction System for FGN Bond Market Review and Recommendations	106,080
HR Capacity Assessment & Strategy / Development of Performance	86,753
ICT Standardisation for the DMO	53,040
SAP Automation	83,780
Training Needs Analysis Template and Tool	13,068
External Stakeholder Engagement	7,800
Total	569,523

N.B Also covers other relevant activities and cumulative capacity building to date.
F. Factors contributing to the success of DFID’s support to DMO and lessons to be learned and applied elsewhere in Nigeria.
This project model has succeeded in this case in large part due to the contextual characteristics of the project and recipient. These include primarily the long-term involvement of DFID from before the inception of the DMO; The consistent high level of support that the DMO and its Management have enjoyed from its political masters both in the FMF and the Presidency since inception and through changing administrations; the insulation of the DMO staff from the mainstream civil service structure; the high profile and public awareness (though rudimentary) of the importance of the project objectives; the insulation of the DMO from political and civil service turf wars/claims at the very early stages of its development; the early commitment and high calibre of staff at management and ground levels; the relative small size of the DMO (110 staff) and the technical and focused nature of its mandate.
Project and DMO actions that directly and favourably impacted on the DMO’s performance included: the consistency of support over the years; the development and encouragement of a staff “culture”; the encouraging of the spirit of identity, ownership and shared responsibility; the fairly high level of targeted training and retraining given to the staff and the practice of encouraging staff to share and pass on their knowledge and experiences (internally and with stakeholders); as well as, the introduction of a basic but robust IT infrastructure to serve as a platform for further growth and development.
This is not to say that the DMO and by extension the Project, has not been without its challenges. Shifting priorities, loss of talent and high-turnover of staff, political demands, and fast changing global economic dynamics all continue to pose a threat to the success of the DMO.
In conclusion, the model used in Phase III cannot be applied as a first plan of action for support to public institutions. A beneficiary institution will have to be fairly mature and already responsible; preferably with a familiarity/history of engaging with development partner.

III. Recommendations
A. Focus of DFID support under the final year of Phase III
The final year of Phase III should focus on consolidating the gains made in past years and completing the capacity building actions that are underway to move DMO to a higher plateau of performance, while maintaining the spirit of collaboration anchored in strong ownership by DMO management and staff.
MTDMS. There is a need to develop capacity for a medium-term debt management strategy based on cost-risk analysis which should guide the composition of debt. The World Bank draft report and expected follow-up work should help guide the process. Whereas a consultant has been identified to help introduce the MTDMS reform, additional training and capacity building in this critical area will be required. Project support in this area under the third year would be highly valuable.
Contingent Liabilities and PPP. Related to the MTDMS is the need to develop capacity to collect data and perform analysis on all contingent liabilities, including PPPs. It will be desirable to incorporate these into the debt database and the DSA exercise; this work may take longer than the remaining time under phase III, but would merit support.
Communications strategy. Building on the consultant’s report of July 2011 a comprehensive communications strategy and action plan should be developed, including an operations manual, and the creation of a dedicated communications unit.
Monetary and Fiscal policy committee. DMO should be encouraged to resume the quarterly monetary-fiscal policy meetings stopped over a year ago to enhance policy coordination and to flag consequences on the bond market of expansionary fiscal policies.
M&E. To enhance efficiency and effectiveness, and promote value for money analysis, it is important to develop a monitoring and evaluation (M&E) approach that would enable the DMO management and staff assess the effectiveness of their operations and policy and institutional choices on a continuous basis.
Sub-national debt. It is important to deepen and strengthen cooperation and coordination with the sub-national governments. DMO’s plans to institutionalize best practices should be extended to all remaining states as planned. A related objective should be the development of a credible data base for sub-national debt. Continued project support will be critical without which the progress made can be easily undone.
HR management. The recently introduced staff evaluation and career development system may require external mentoring in its first round. Also, the practice of frequent staff rotations needs to be re-examined and its impact on effectiveness of units within the DMO evaluated.
PDMI. There is a need to carefully examine potential customers in Nigeria and in the continent and potential products that the PDMI can offer to determine if its business model is robust.

B. Should DFID support the DMO after the end of Phase III
DFID support under Phase III constitutes about 160 million naira compared with a 300 million Naira of DMO’s overhead budget (excluding DFDI support). An abrupt withdrawal of such a level of support could be disruptive. At the same time, however, DFID support to the DMO can be considered a success and as such, support will need to be discontinued and directed toward more needy institutions in Nigeria.
Weighing these two factors the way forward may be through limited and targeted support to areas where progress is still fragile and reversible. Hence, consideration should be given to targeted support focused on DMO’s work with sub-national governments, perhaps through the PDMI. Consideration should also be given to support for the development of capacity to collect data on contingent liabilities, including PPPs, and to analyze their risk and debt implications. Related to the latter, consideration could be given to support in the development of strong technical skills and capacity to analyze rates of return of projects for which debt is raised, either by direct borrowing or through PPP schemes.