Type of Review: Annual Review

Project Title: Programme for Improving Mental Health Care (PRIME) - RPC (2011-17)

Date started:	1st May 2011
Date review undertaken: 24th April 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context
What support is the UK providing?
The UK is providing £6 million over the period 2011 – 2017 to generate world-class research evidence on the implementation and scaling up of treatment programmes for priority mental disorders in primary and maternal health care contexts in low resource settings.

What are the expected results?
PRIME is based in Ethiopia, India, Nepal, South Africa and Uganda. Comparing experiences across these diverse settings, which include fragile settings, will enable PRIME to generate knowledge with local and international relevance. By the end of the RPC, the following key research questions will have been answered: / a) What are the feasible and acceptable components and packages of care for priority disorders and how can they be integrated into routine primary health care and maternal health care? / b) What is the feasibility, acceptability, costs and impact of various models for delivery of the packages of care in routine primary health care and maternal health care settings? / c) What are the health system requirements for scaling up: human resources; training and supervision needs; infrastructure; drugs; budgets; and the incremental cost of increasing coverage per new patient treated? / d) What are the specific barriers which influence access to services for people living in poverty with mental disorders, particularly women during the perinatal period? / e) What is the impact of scaling up of the integrated mental health care plan on coverage and utilisation of mental health care?

What is the context in which UK support is provided?
The need for mental health services is high. Life time prevalence for mental disorders is between 12.2 - 48.6 % globally and the one year prevalence is between 8.4-29.1%. Surprisingly, more than 13% of the global burden of disease is due to neuropsychiatric disorders. Almost three quarters of this huge burden lies in low and middle-income countries (LMIC) and this burden is projected to grow dramatically in the next decade, in part due to the demographic and epidemiological transitions in LMIC. Mental disorders are a major contributor to economic hardships and are strongly associated with social and economic disadvantage. / Despite this enormous burden, a multi-country survey supported by the World Health Organization (WHO) showed that almost four out of five people with severe mental disorders in LMIC had received no treatment in the previous year. "Treatment gaps" were especially large for depression and alcohol use disorders. Where treatments are accessed, they are often inappropriate and involve considerable out of pocket payments, leading to catastrophic health expenditure.

## Section A: Detailed Output Scoring
Output 1: Establish and maintain an efficient and well managed RPC which draws on the strengths of each partner to deliver a high quality research programme that achieves the RPC’s goal and purpose.
Output 1 score and performance description: A+ Output moderately exceeded expectation
Progress against expected results: / 1. The establishment of PRIME as a research consortium. This included recruitment of project staff, signing contracts with all partners and establishing key monitoring mechanisms, namely the Prime Management Team (PMT), PRIME Management Group (PMG) and the Consortium Advisory Group (CAG). Community Advisory Boards (CABs) are being established in country sites. In addition, the RPC have worked to define key internal policies and procedures for publication (Appendix I of PRIME Annual Report) and collaboration with external partners (Appendix J of PRIME Annual Report), reporting mechanisms such as the quarterly reporting format (yoked to partners’ contractual terms of reference) as well as finalising the research uptake strategy (Appendix C of PRIME Annual Report) and capacity building strategy (Appendix B of PRIME Annual Report). The RPC has also finalised key dissemination vehicles (PRIME website, brochure and poster). / 2. The synthesis of research on poverty and mental disorders, scale up of mental disorders and human resources for mental health care was published in the 2nd Lancet series on Global Mental Health. The series was edited by Prof Vikram Patel and consisted of six articles, four of which included authors from PRIME. / 3. The completion of a situational analysis in study countries. This was undertaken to acquire a detailed understanding of the mental, maternal and general health services at national and administrative health unit (AHU) level in order to formulate a contextually appropriate mental health care plan. The situational analysis was completed on a standardised template by all 5 countries and included information about 1) Relevant context; 2) Mental Health policies and plans; 3) Mental health treatment coverage; 4) District level health services, 5) Community and 6) Monitoring and evaluation. This was necessary to obtain detailed information about districts in study countries prior to commencing the formative research. / 4. The development of a detailed formative research protocol to refine the mental health care plan. The formative research includes qualitative research methods (semi structured interviews and focus group discussions), the use of theory of change workshops as a participatory method for planning, literature summaries and the development and use of a costing and human resource planning tool. The theory of change workshops replaced the Delphi Consensus Building methodology which was outlined in the proposal as it provides an opportunity for consensus building as well as complementing the theory building component of the MRC framework for complex interventions. The formative research is currently being conducted in all PRIME countries. / 5. The development of a draft Mental Health Care Plan. All countries have drafted a mental health care plans at AHU level (see Appendix K of PRIME Annual Report). The plans specify the components of care integrated into packages of care at all three levels of healthcare. These are the health organization level, the health facility level and the community level. The plans will be refined with the results of the formative research. / Recommendations: / Strong progress during this first year of the RPC. It will be important to prioritise these key activities which will directly lead to the planned outcomes. Experience from the RPC should continue to be shared widely to WHO and other interested agencies/countries. / Impact Weighting (%): 100% in Year One – thereafter 10% / Revised since last Annual Review? No / Risk: Low/Medium/High High / Revised since last Annual Review? No

Output 2 A coherent body of high quality, peer-reviewed and policy relevant research that makes a significant contribution to understanding the implementation and scaling up of packages of care for mental disorders.
Output 2 score and performance description: A Output met expectation
Progress against expected results: A mixed methods approach will be used in the range of research questions the RPC will seek to answer. Qualitative methods and quantitative studies with contextually validated tools are used in parallel to support, clarify and explain findings. In addition, the use of qualitative methods enables in-depth exploration of impacts related to issues of social exclusion, a critical aspect of the experience of mental illness. The primary quantitative methodologies are influenced by recent innovations for evaluating complex interventions implemented at the level of health systems or populations, such as surveys with attribution of outcomes to specific delivery mechanisms and matched control designs. / The evidence generated from these multiple methods will be used to answer the key research questions both at the local level (i.e. for local policy contexts) as well as to compare and synthesize findings across the settings to generate answers which have a global impact. / While the goals of each package of the intervention will be similar across settings (e.g., to improve mental health outcomes), the content of the package (e.g., which human resource cadre delivers the component) will be contextually derived and informed by individual Theory of Change maps for each setting. The RPC will then be able to describe both the impact of the intervention in each context and compare the methods used to achieve these results across contexts. All data will be disaggregated by gender, residence (rural/urban) and economic status to monitor equity of outcomes. / Recommendations: Good early progress during the first year. An ambitious programme is planned for the first year of the Implementation Phase. It will be important to prioritise these key activities which will directly lead to the planned outcomes. Early findings from the RPC should be shared, as appropriate, with WHO. / Impact Weighting (%): 50% / Revised since last Annual Review? No / Risk: Low/Medium/High High / Revised since last Annual Review? No

Output 3 Effective communication of relevant research findings and their uptake by national and international stakeholders to influence policy and practice in the study countries and other low and middle-income countries..
Output 3 score and performance description: A Output met expectation
Progress against expected results: Research Uptake is an essential component of PRIME and will ensure that research evidence generated by the RPC is translated into the longer-term outcome. PRIME’s Research Uptake output aims to mobilise and create awareness amongst a range of stakeholders. These include researchers, health practitioners (mental health specialists, and primary health care workers), people and communities affected by mental illnesses, civil society, the media, policy makers and donors. This will be done by generating key messages that are strategically targeted at respective stakeholders at appropriate levels (global, regional, national or district) and times. Key messaging, depending on the audience, includes emphasising the impact of mental illnesses, especially for priority mental disorders; the role of evidence-based mental health care and systems in scaling-up mental health services; the benefits of integrating mental health into routine maternal and primary health care; and the developmental benefits of addressing the mental health ‘treatment gap’. / The approach is guided by an initial identification and analysis of stakeholders within PRIME countries which took place during the Inception phase. It is set out in a strategic plan (Appendix C of PRIME Annual Report), which includes the appropriate dissemination and communication strategies countries will employ for attaining the research uptake objectives. / Dissemination outputs (policy briefs, working papers, open-access peer-reviewed journal publications, audio-visual presentations) will be made available to key stakeholders through a range of communication vehicles. Communication vehicles include global and national advocacy initiatives such as World Mental Health Day (10th October annually), international (including community and local) media, social media and websites, conferences, local Community Advisory Boards and direct engagement with policy makers. / Recommendations: Good early progress during the first year. The RPC has been reminded of the revised policies of the Coalition government. It will be important to prioritise these key activities which will directly lead to the planned outcomes, including liaison with WHO. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Low/Medium/High High / Revised since last Annual Review? No

Output 4 Capacity exists in study countries to conduct and effectively disseminate research to improve access to mental health care.
Output 4 score and performance description: A Output met expectation
A key component of PRIME is the development, implementation and monitoring of a structured programme to build sustainable capacity for mental health research and evidence-informed policy and planning. A detailed capacity building strategy is shown in Appendix B of the PRIME Annual Report. / The component was guided by the identification of the main strengths and weaknesses of PRIME at the individual, organisational and institutional levels and to ensure a common understanding of capacity building across all PRIME partners. This was done using an individual-based Skills Assessment of all PRIME members in July 2011, and a team-based Capacity Needs Assessment in November 2011. / Results of the Skills and Needs Assessments were synthesized, and a capacity building plan was circulated to all PRIME members for feedback. Both the Skills and Needs Assessments clearly revealed the wealth of knowledge and skills that already exist within the PRIME Consortium, in sufficient numbers, at various levels of expertise, and across countries. The majority of the individual level capacity needs can be met through various PRIME-led workshops, mentoring and supervision, enrolment in short courses such as the Complex Intervention and Leadership in Mental Health course in Goa, India. The RPC has three registered PhD students affiliated, with an additional five preparing to register this year. / Key activities to deliver the programme outcome include workshops, course enrolment & graduate degrees, mentorship and support, grants & fellowship applications, resource sharing, publications/ communications, development of networks and internships/placements. / Capacity building activities as well as emerging needs and opportunities will be monitored and evaluated regularly through the following mechanisms: / • Capacity building section of the quarterly reporting form for tracking and discussion at quarterly teleconference. / • Review of capacity building plan at annual RPC meetings. / • Assessment of workshops, training courses, conference presentations, and site visits that include a brief (less than 5 questions each) online baseline assessment, evaluation immediately after the activity, and 6 months later to determine whether or not the activities are meeting the needs and prioritise activities based on their impact. / Recommendations: Good early progress during the first year. Building up sustained capacity for mental health research is an important output of the RPC. It will be important to prioritise these key activities which will directly lead to the planned outcomes, including liaison with WHO. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Low/Medium/High High / Revised since last Annual Review? No

## Section B: Results and Value for Money.
1. Progress and results

1.1 Has the logframe been updated since last review? No / 1.2 Overall Output Score and Description: A Outputs met expectation / 1.3 Direct feedback from beneficiaries / Positive inputs from all the participating countries. Rather early for direct feedback from beneficiaries but will be examined during the first year of the implementation phase of the RPC.
1.4 Summary of overall progress / The PRIME RPC has made strong progress during the Inception Phase and is expected to perform strongly as it moves into implementation. The RPC is being well managed and has made strong efforts to involve all the various countries and lead institutions. The RPC is managing its research portfolio, dissemination and capacity building programmes appropriately and has already made strong progress. In summary, a very strong first year, creating a very strong platform for the implementation phase.
1.5 Key challenges / The current economic situation means that resources are constrained and the RPC has to find ways to work to maximise its current funding and identify long-term measures to secure further research funding into the future. / Mental Health is much neglected in almost all countries of the world and rarely stands out as a prime candidate for additional resources. By compiling the stark data on the proportion of the global burden of disease contributed from mental health conditions, the RPC is helping WHO and others to increase the profile of mental health and to solicit for additional funding in the future. / Retaining highly qualified and experienced staff is always a challenge and the RPC is developing ways to build up local capacity and then retain staff by directly engaging them on the high profile research programmes planned under the RPC’s research programmes.
1.6 Annual Outcome Assessment / The RPC has put into place strong management and supervisory mechanisms, along with clear organisational structures, designed to work effectively with other key players to achieve the planned outcomes.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / 2.2 Key cost drivers / The development and implementation of high quality research programmes, combined with adequate dissemination and building up of local research capacity, are very costly processes. Key cost drivers are direct and indirect staff, travel costs, research consumables and related transport and supervision costs. The RPC is fully aware of the need to work carefully within the planned budget and to contain costs, as far as is possible. Almost all participating countries have seen some slippage of exchange rates for the local currency, taken against international hard currencies. As the programme budget is denominated in Pounds sterling, and funds are only transferred into local currencies as the funds are directly required, the overall RPC budget has so far been largely protected from foreign exchange fluctuations. This is kept constantly under review by programme managers. / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The RPC has been directly involved in developing new evidence, such as the 2nd Lancet series on Global Mental Health, which involved six major articles, four of which included authors directly involved in the PRIME RPC. The RPC is also working in liaison with the Mental Health Department of the WHO and helped support the development and publication of the several major publications. / 3.2 Where an evaluation is planned what progress has been made? / Not applicable at this stage

4. Risk
4.1 Output Risk Rating: Low/Medium/High High / 4.2 Assessment of the risk level / The programme remains high risk but all mitigating steps are being taken and the judgement is that the risks are manageable. The RPC Prime Management Team and the Consortium Advisory Board regularly review the risks. As mental health is still a relatively low priority for many Ministries of Health, despite the considerable contribution to the overall burden of disease, it is difficult to guarantee that staff and financial resources will be forthcoming, when required, to step-up high quality mental health services. The RPC is operating across five countries, Ethiopia, India, Nepal, South Africa and Uganda, which includes fragile settings. / Risks related to the research portfolio are evaluated regularly during regular reviews. Risks related to non-technical issues such as funding and organisational functioning, supervision and management are assessed by the Prime Management Team and the Consortium Advisory Board. The main risks identified include technical failure of research, lack of adoption of new research findings, insufficient funding, failure to build institutional capacity among the key participating institutions and external disasters. / The main risk for DFID is that there will be insufficient uptake of the high quality research, as Ministries of Health struggle to provide essential services. Strong engagement with WHO, and with participating governments does mitigate this risk, to some extent, but the overall programme remains high risk, high potential impact.
Risk of funds not being used as intended / This is low risk. The earlier RPC, also managed through the University of Cape Town, had a strong reputation for management and financial oversight. The new RPC has started well and there have been no difficulties reported with disbursement or in any misappropriation of funds. The RPC Prime Management Team is effectively overseeing all aspects of the programme and has performed well during the first year. / The RPC has established strong functioning mechanisms for management and oversight. These include the Prime Management Team and the Consortium Advisory Board. The Prime Management Group, which includes all participating lead institutions, meets periodically to oversee RPC activities. The Consortium Advisory Group (CAG) and Community Advisory Boards have also been established to feed-in external points of view. / 4.4 Climate and Environment Risk / Climate and environmental risks continue to be effectively managed by the RPC. All the participating institutions review research activities to reduce the impact on climate and the environment. Where possible, tele-conference and “Skype” meetings take place, in order to minimise the impact of national and international travel. / In time, the provision of more local high quality mental health services will reduce the requirement for patients to travel to regional or national treatment centres, in order to access care. Reduction in treatment times should lead to reduced need for travel by patients and improve patient drop-out rates and overall waste.

5. Value for Money
5.1 Performance on VfM measures / Funding high quality research into neglected non-communicable diseases, such as mental health, provides value for money through: reducing the impact and burden of mental ill health; encouraging governments to provide essential services which are able to intervene early, before a lengthy and potentially costly breakdown or in-patient admission; ensuring that individuals with mental health conditions, and their direct families, are able to function in employment or farming, instead of becoming a burden on local communities or governments. / The macroeconomic impact of mental ill health is very significant, with an estimated 13% of the global burden of disease being due to neuro-psychiatric disorders. Almost three quarters of this huge burden of disease falls on low and middle income countries. Most important of all, it is projected by WHO that this global burden is projected to grow dramatically in the next decade, in part due to demographic and epidemiological transitions. Mental disorders are a major contributor to economic hardships and are also strongly associated with social and economic disadvantage. / 5.2 Commercial Improvement and Value for Money / Through its internal processes, identifying the most promising new research proposals from the participating countries and institutions, the RPC is able to provide a “competitive” environment for innovative new approaches and work to keep costs low to achieve improved value for money. / 5.3 Role of project partners / The RPC is managed by the University of Cape Town, and includes the following key institutions: University of Addis Ababa, Ethiopia; Basic Needs, an NGO; the Centre for Global Mental Health, UK; Healthnet TPO, an NGO in Nepal; Makerere University, Uganda; Sangath, India; University of Kwa Zulu Natal, South Africa; and the Mental Health Department, WHO, Geneva. All the partners are represented in the PRIME Management Group and also have Community Advisory Boards in country research sites. / 5.4 Does the project still represent Value for Money : Yes / 5.5 If not, what action will you take? Not applicable

6. Conditionality
Update on specific conditions / Not applicable

7. Conclusions and actions
The performance of the PRIME RPC is fully meeting expectations and they have made good progress during the inception year. Research is a long-term activity and the strong early development of the RPC is very welcome, as it is important to speed up the research process. The partnerships developing with the five participating countries, and the leading research institutions, are already strong and are a strong foundation for the implementation phase of the RPC.

8. Review Process
The review was carried out by members of the Human Development Research Team in DFID, with extensive support from Link Advisers in DFID India and in DFID HQ. The process involved discussions with WHO and other organisations working on mental health issues. / Materials used included reports from a variety of sources including the PRIME Annual Report; publications from the Mental Health Department of WHO; and the 2nd Lancet Special Series on Mental Health. / For full list of references, see PRIME Annual Report (Quest document 3454634)