Type of Review: Annual Review

Project Title: Humanitarian Support to UNICEF Nutrition Surveillance

Date started:	April 1 2012	Date review undertaken: May 1 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
DFID is providing £2,000,000 (47% of the total budget) to UNICEF to support nutrition surveillance programme in Ethiopia. The overall cost of the programme is about £4,200,000 over a two years period. The programme is 18 months into a 2 year life. / The nutrition surveillance programme will contribute to the Government of Ethiopia’s five-year National Nutrition Program (NNP).DFID’s support will complement funding from the World Bank (through the NNP) 28% and UNICEF 25% to finance this government-led programme to increase the timeliness, quality and transparency of nutritional information.

What are the expected results?
The goal of the project is to improve targeting, coverage and quality of the humanitarian response addressing malnutrition. The purpose of this project is to improve timely availability and quality of nutrition data using a fast track nutrition surveillance approach. Resources will be focused on data quality and rapid flow of information from sub district/district levels for analysis and use. / The main outputs of the programme include: / Improved timeliness in reporting and quality of nutrition data from the most food insecure districts in the regions of SNNP, Tigray, Amahara and Oromiya through implementation of the fast –track surveillance approach. / Credible and independent bi-annual standard nutrition surveys implemented to support early warning and humanitarian responses in six regions (SNNP, Tigray, Amahara, Oromiya, Somali and Afar) for areas with limited/no nutrition programmes (CHD,CBN,TFP) and in the fast track surveillance districts. / Strengthened capacity in nutrition information/surveillance in these six regions.

What is the context in which UK support is provided?
Ethiopia has one of the highest rates of malnutrition in Sub-Saharan Africa. Part of DFID’s response to the unacceptably high rates is to provide substantial support for Ethiopia’s humanitarian requirements. The UK the second largest humanitarian donor to Ethiopia. The effectiveness of this humanitarian response has the potential to be considerably improved by establishing more reliable data sets and systems to prioritise needs. / Some of the challenges in tackling malnutrition include: timely and inter-sectoral information sharing; gaps between ad-hoc and routine nutritional surveillance systems; and limited coverage of nutritional surveys and delays in publication (especially in sensitive areas).

## Section A: Detailed Output Scoring

Output 1: Timely availability of Nutrition indicators from existing CBN/TFP/CHD data systems to feed into early warning system
Output 1 score and performance description: A / Output met expectation. / During the reporting period, consistency, timely availability and quality of data on the community based nutrition programme (CBN), therapeutic feeding programme (TFP), and on community health day (CHD) indicators has improved. TFP, CBN, and CHD routine data has been consistently reported every month on all five ‘’agreed upon indicators’’. / The milestone for this project at 18 months was 90% of districts (36 districts) reporting on the five indicators. Due to the expansion of these programs along with established data reporting mechanisms, the TFP indicators were available in over 500 woredas and the CBN indicators in 220 woredas; this far exceeds the milestone. The monthly reporting rate on TFP in these 500+ districts was consistently above 80%. . Considering that there are over 9000 Outpatient Therapeutic Programme (OTP) sites in the 500 districts (source: ENCU/FMOH TFP database), the expected result has been far exceeded. / CBN and TFP reports are, on average, available within four weeks of collection of information, which is on track against the milestone set (4 weeks). However, the community health day (CHD) reports are only available within 6-8 weeks of collection of information. The timely availability of report on TFP/CBN/CHD remains an issue, which needs addressing. First, processing information for review of data quality is a time consuming activity, due to the size of the activity and the amount of information that needs to be analysed for producing a report. Secondly, the ownership and use of the “score-card”, tool by the regional and district officials is minimal. Field visits to sample districts in Oromia and Tigray by UNCIEF have shown that scorecard is not routinely completed. / During this reporting period, there was an improvement in the quality of information reported on TFP, CBN and CHD. UNICEF, by working with key stakeholders, succeeded in standardizing the ‘denominator’ used for collecting information on TFP and CBN, which for the TFP is related to reporting rate and for CBN is the underweight prevalence. The Training of Trainers (ToT) on ways of strengthening CBN data utilisation (which also covered TFP and CHD) for over 40 regional staff has also contributed to improving data quality. Further, data quality checklist was developed for district level staff to determine various aspects of data quality. Information on TFP/CBN/CHD is reported monthly from district though Regional Health Bureau (RHB) to the Regional Emergency Nutrition Coordination Unit (RENCU) for data quality checking. / TFP data is now routinely being reported at the district level, via the weekly Early Warning reports and with the regional DPPB and federal disaster risk management and food security sector (DRMFSS) monthly early warning reports. A great success of this process has been the cooperation of the Regional health bureaus (RHBs) and the Regional Emergency Nutrition Coordination Unit (RENCU) of the Disaster Prevention and Preparedness Bureaus (DPPB) collected on the agreed five indicators feeding into the early warning system. The Nutrition Information System (NIS) data utilisation training also has activities to train the health and early warning staff to work together to interpret the nutrition situation.
Progress against expected milestones: / Baseline (2010) Milestone 1 (12 months from start of project) Milestone 2 (18 months from start of project / Plan Achieved Plan Achieved / Indicator 1 Poor reporting rate > 80% of districts reporting all five agreed indicators Fully > 90% of districts reporting all five agreed indicators Exceeded / Indicator 2 Delay up to 8 weeks Reducing delays to 6 weeks TFP/CBN – fully / CHD – partially Reducing delays to 4 weeks TFP/CBN - fully / CHD – not achieved / Indicator 3 / Recommendations: / UNICEF will intensify engagement with districts to improve timeliness of reporting and quality of analysis. / Impact Weighting (50%): / Revised since last Annual Review? Yes / Risk: Low / Revised since last Annual Review? No

Output 2: Timely availability and quality of bi-annual nutrition survey indicators
Output 2 score and performance description: A / Output met expectation / The task of implementing bi-annual nutrition surveys started after securing approval from the GoE at the end of October 2011. As per the agreement reached, a number of districts were selected from each of the target regions, based on chronic vulnerability and agro-ecological criteria. RHBs and DPPBs, with support from NGOs, will carry out the surveys, and to this end, training has been provided to staff to strengthen their capacity. This implementation modality has helped secure Government approval/ ownership. / In 2011 as a result of the Horn crisis a programme cooperation agreement was made between UNICEF and Save the Children UK for Afar region. No nutrition information was available at the time in the form of routine data (coverage of the community management of acute malnutrition programme (CMAM) was limited and data flow poor) and no nutrition surveys had been carried out. Because of this gap in information, UNICEF engaged in a partnership with SCUK to implement three surveys in at risk districts. As a result, SCUK started nutrition programming in 15 districts in Afar, where previously there was no international NGO presence for nutrition. / The first round of surveys is now underway in three regions, Oromia, SNNP and Somali. Due to capacity limitations in Afar, Amhara, and Tigray, surveys have been delayed. Data from the first round of implementation was completed by end of February. Some delays were encountered with data analysis and report writing due to mandatory leave of ENCU staff for the month of January. This will be rectified in 2012 as the time of implementation will be September/October. The second round of implementation will commence March/April 2012.
Progress against expected milestones: / Baseline (2010) Milestone 1 (12 months from start of project) Milestone 2 (18 months from start of project / Plan Achieved Plan Achieved / Indicator 1 Delay in approval 50% surveys conducted based on seasonal calendar 50% of surveys conducted based on seasonal calendar 15 woredas from 3 regions (65%) / Indicator 2 Delay in endorsement 100% of survey reports endorsed within two weeks 100% of survey reports endorsed within two weeks Unknown at time of review: Report finalization not complete / Recommendations: / UNICEF will prioritise finalisation of surveys under the second phase commencing in March/April. / Impact Weighting (40%): / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

Output 3: Increased knowledge and guidance on nutrition data collection and interpretation in pastoral areas
Output 3 score and performance description: B / Outputs moderately met expectation. / Plans are underway to develop a Terms of Reference (TOR) to assess the current status of knowledge and review methodologies. A core group of partners have convened to review proposals. However, the nutrition emergency that developed in the Horn in 2011 has slowed progress. Nevertheless, key areas have been identified for inclusion in the research. These include nutrition survey sampling for pastoralist areas, community nutrition surveillance methods, including the potential use of SMS, and research into the interpretation of anthropometric data and determining the emergency threshold levels due to differing body composition of pastoralist children. Currently, some nutrition surveillance is active in pastoralist regions, particularly in Somali, with TFP data monitoring; SCUK has expanded CMAM in Afar region so TFP data monitoring has also improved.
Progress against expected results: / Baseline (2010) Milestone 1 (12 months from start of project) Milestone 2 (18 months from start of project / Plan Achieved Plan Achieved / Indicator 1 No best practice document available Terms of Reference (TOR) developed and request for proposal issued Not achieved – research for interpretation of anthropometric results will be included in an existing institutional contract with Tulane University and will commence by mid-April, 2012 / Indicator 2 / Recommendations: / UNICEF will prioritise the development of the Terms of Reference and review methodologies under this output during the current phase. / Impact Weighting (10%): / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Yes / 1.2 Overall Output Score and Description: / A. / After a slow start (as per previous review) progress is on track. The time invested in building relationships with Government on the sensitive issue of nutrition has paid dividends. / Outputs met expectation. / 1.3 Direct feedback from beneficiaries / The direct beneficiaries for this programme are Government and the international humanitarian community. / The routine nutrition information that was captured in 2011 was highly appreciated by Government and stakeholders. Monitoring of the TFP data was instrumental to identifying the effects of the drought. Higher than normal peaks in admissions of severe acute malnutrition were recognized in April and May, 2011 while the Horn of Africa Emergency was only declared in July. / The biannual surveys have not reached a level of implementation to gather appropriate feedback on its use and utilization for early warning. / Research on nutrition surveillance in pastoralist areas, including research on understanding anthropometry and emergency cut-off levels is highly appreciated by NGO partners who are responding to nutrition emergencies in these areas. There has been considerable discussion that the emergency cut-off point for child malnutrition need to be reviewed; this research is a step towards realizing this.
1.4 Summary of overall progress / Despite a slow start attributable to challenges in ensuring buy in to new ways of working amongst various line ministries at federal and local levels, and diversion of attentions to the nutrition crisis in 2011, substantial progress had been made with 2 of 3 outputs being met. / Time spent in building relationships and getting buy in from the various government bodies should contribute to an improved rate of implementation in the next phaseof the project.
Key challenges / The concept of “fast-track”, where five indicators would be phoned or sent by SMS by the woreda health officers, was not accepted by the government for technical reasons related to the phone system and equity among various health programs. However, as mentioned, mechanisms for data transfer of these indicators do exist and have proven to be effective for timely reporting. / CHD is a large activity with a large amount of information being captured and processed. In order to allow for appropriate data quality checking, it has proven to be a challenge to get the information reported within a 4 week turnaround time. / Government approval of the bi-annual survey methodology proved to be time consuming with significant delays encountered. Communication from government for the first methodology proposed by the working group took over 4 months, and then it was a rejection of the methodology. This pushed the timing of the planned first round of implementation beyond the appropriate window. A methodology was finally developed that government approved, however this was again late, in November of 2011. This allowed for very little preparation time, but it was felt that it was important to start the project in those regions that had the capacity to avoid further delays.
1.6 Annual Outcome Assessment / The outcome of the project is: timely available and quality nutrition reporting linked to agro economic baseline data (HEA) and the early warning system. / The project is on track to improving the quality of the reporting but intensive efforts need to be made to link this to the early warning system. This challenge is made more difficult as responsibilities cut across both Ministries of Health and Agriculture.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: / No / The project is behind the agreed financial forecast schedule. This problem is mainly attributed to lack of government approval of the methodology for nutrition surveillance proposed by the programme. / 2.2 Key cost drivers / The majority of the funds are being applied for the bi-annual nutrition surveys. This is mainly driven by costs for enumerators and vehicles. Second to this is the cost of human resources, specifically, ENCU and regional UNICEF staff who are responsible for coordinating the bi-annual surveys, and collecting and processing the routine nutrition information. These costs are likely to be increasing due to the continuing high rate of inflation which is causing most agencies to increase the level of remuneration and incentives for full and part time staff. The reporting period has not specifically tracked these increases in costs but we will request UNICEF to do so over the coming phase. / Is the project on-track against original timescale: / No / The project is behind the originally agreed schedule of implementation. The delay is mainly attributed to lack of government approval of the methodology for nutrition surveillance proposed by the programme.

3. Evidence and Evaluation
Assess any changes in evidence and implications for the project / New DHS data released during the project timeframe is relevant for the overall nutrition context in Ethiopia. In particular, rates of wasting, stunting and underweight have continued to show positive decline although not at a sufficient rate to meet MGGs. / Of particular relevance to the project within the DHS data will be the regional inequalities e.g. continued comparatively high rates of wasting for Afar. The bi-annual surveys supported through this project – largely focused on “hotspot areas” in rural areas, will be useful additional supplementary information to the DHS in corroboration of regional inequalities and tracking of trends in the 5 year timeframe between surveys. / 3.2 Where an evaluation is planned what progress has been made? / The relevance and achievements of the project will be considered during the forthcoming ICAI evaluation of the 2011 horn crisis and DFID response.

4. Risk
Output Risk Rating: / Medium / 4.2 Assessment of the risk level / Appropriate
Risk of funds not being used as intended / The overall risk rating for this programme is medium. Where output risks are high these generally relate to buy in from government to take changes in ways of working forwards. The risk of unintended use of resources is limited due to UNICEF’s overall financial management of the project which involves discrete payments for specific tasks through partners. / 4.4 Climate and Environment Risk / n/a

5. Value for Money
5.1 Performance on VfM measures / Improvements in nutritional surveillance are likely to have a high VfM identifying early were malnutrition problems are taking hold. Nutritional monitoring was instrumental in identifying early the onset of the 2011 drought indicating which areas were most affected and facilitating improved emergency coordination of partners, supplies and resources to affected areas. This translated into the lives of children being saved. / Implementation has not progressed significantly with the bi-annual surveys in order to fully adequately answer VfM at this point. This will be addressed in the PCR. / 5.2 Commercial Improvement and Value for Money / n/a / 5.3 Role of project partners / Government at all levels and NGOs are integral to the success of this project. This project has been successful in improving relationships among the key stakeholders working on nutrition. The agreement to go ahead with nutritional surveys in sensitive areas is an indicator of this. DFID plays a key role in lobbying for greater access for UN and NGOS for nutritional surveys. / Does the project still represent Value for Money / Yes / 5.5. If not, what action will you take? / n/a

6. Conditionality
6.1 Update on specific conditions. / n/a

7. Conclusions and actions
After a slow start the programme is on track. However to ensure objectives are fully achieved a no cost extension will probably be necessary. DFID will engage now to ensure that an extension is agreed thus avoiding any interruption to project activities.

8. Review Process
The review process was carried out in a participatory manner. DFID’s humanitarian advisor, Deputy program manager and program officer consulted relevant staffs from UNICEF such as the nutrition team, the M&E focal person and reports officer in the compilation of progress report, comments and suggestions. Review meetings and frequent e-mail communications were also part of the review process that helped to collect and clarify information explained in this report.