Annual Review

Title: Support to Malaria Control in the Democratic Republic of Congo
Programme Value £ (full life): £39.5 million (£36.0 million contracted)		Review Date: 08 May 2018
Programme Code: 203458	Start Date: 08/05/2013	End Date: 30/09/2019

Summary of Programme Performance
Year	Year 1 / 2013/14	Year 2 / 2014/15	Year 3 / 2015/16	Year 4 / 2016/17	Year 5 / 2017/18
Programme Score	A	A	B	A	A
Risk Rating	M	M	Moderate	Moderate	Major

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203458/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203458/documents/

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

This programme was established to support the implementation of DRC’s National Strategic Plan for Malaria Control (PNLP[1]) including prevention, malaria case management and health information. The programme has three components: distribution of bed nets; improved accessibility of quality-assured artemisinin-based combination therapy (QAACT) in Kinshasa; and increased capacity of the PNLP to generate and use data.
[1] PNLP - Programme National de Lutte contre le Paludisme.

The contract value for programme is £36 million over six years (2012/13-2018/19), out of a total programme value of £39.5 million approved in the business case. Of this, £0.9m was spent on the design phase.

Component 1: Distribution of bed nets (£15.8 million)

The availability and use of bed nets is a key component of the PNLP’s approach to prevention. At the outset, 4.4 million bed nets were purchased by the project for use in mass distribution campaigns, sufficient to cover all 44 health zones in Kasaï and Kasaï Central provinces (former Kasaï Occidental). It was subsequently agreed that Against Malaria Foundation (AMF) would provide sufficient bed nets for nine of these health zones, to be distributed using a door-to-door approach through DFID DRC’s health systems strengthening programme Accès aux Soins de Santé Primaires (ASSP). As a result, of the 4.4 million bed nets procured, 2,813,925 were utilized for mass distribution in the remaining 35 health zones. Of the balance of 1.61 million bed nets, 935,000 are being used for continuous distribution (in order to maintain the increase in coverage achieved by the mass distribution over time), and 676,000 were transferred for use by ASSP in 2016.

Component 2: Improved availability and accessibility of QAACT in Kinshasa (£14.6 million)

The private sector accounts for approximately 70% of antimalarial drugs dispensed in DRC, but at the start of the programme (in 2013) only 2.6% of these were QAACTs. Use of drugs that are not quality assured may result in inappropriate or ineffective treatment, and has the potential to drive the emergence and spread of artemisinin resistance. This is a priority issue for the PNLP, and the programme is working with drug manufacturers, the Global Fund and the PNLP to address six market constraints: the high ex-factory price of QAACTs; poor coordination in the pharmaceutical supply chain; low consumer demand for QAACTs; high taxes and tariffs; the absence of an enabling regulatory environment; and the absence of quality malaria case management by private providers. The intervention under this component is focussed in Kinshasa to facilitate monitoring and lesson learning, with the expectation that lessons learnt may be applied elsewhere in future.

Component 3: Increased capacity of the PNLP to generate and use data (£4.8 million)

There is limited data on the epidemiology of malaria in DRC, the availability and effectiveness of key interventions and the best delivery mechanisms. This hinders the strategic leadership of the PNLP. The programme is responding to this by developing malaria sentinel surveillance sites[2] in ten provinces and strengthening PNLP capacity to generate data for malaria surveillance. The Global Fund and USAID support similar interventions in the remainder of DRC’s 26 provinces.
[2] Malaria sentinel surveillance site is an early warning system for collecting information on malaria every week in four health facilities of a health zone

Expected results to the end of the programme

The programme aims to:
- Support the distribution of approximately 3.7 million bed nets in Kasaï and Kasaï Central provinces;
- Help make up to 5 million doses of QAACTs available through the private sector, to the population of Kinshasa;
- Set up or rehabilitate ten sentinel surveillance sites for malaria.

Results achieved	14/15	15/16	16/17	17/18	Total
Bed nets distributed	2,813,925	28,300	457,325	0	3,299,550
ACT supplied in the private sector	0	528,480	931,520	1,535,640	2,995,640
Sentinel sites rehabilitated	0	0	3	4	7

Summary supporting narrative for the overall score in this review (1/2 page)

Overall, the programme met expectations and scores an “A” in this review. Performance was mixed with Component 1 scoring below expectations while Components 2 and 3 met expectations for the year. This year’s performance was measured using an amended logframe that was updated in line with recommendations made in the previous annual review. The logframe amendment also reflected operational changes that occurred in the programme as described below.

Operational changes during the year

The programme is implemented by a consortium comprised of Population Service International (PSI), its local affiliate Association de Santé Familliale (ASF) and Swiss Tropical Public Health Institute (STPH). DFID’s contract is with PSI, while front line delivery for Components 1 and 2 is primarily with its local affiliate ASF. The PSI/ASF relationship also facilitated operations as ASF is locally registered to work in the DRC.

Discussions regarding separation of the two organisations started in May 2017 and on 31st December 2017 the two organisations legally separated. This left PSI without independent registration to operate in DRC. On this basis, in December 2017 DFID decided to suspend implementation of Component 1 and 2 for six months from February 2018, pending PSI securing full registration to operate in DRC. Activity continued under Component three which is subcontracted by Swiss Tropical Public Health Institute (STPH) and therefore is not subject to the same legal challenge to operating in country.

On March 21st 2018, on the basis of continued uncertainty about the PSI registration process, a decision was made to close components 1 and 2. DFID DRC is now exploring options to continue to work directly on activities under Component 3 through to the end of the programme.

Recommendations for the year ahead (1/2 page)

Programme Recommendations

By the end of June 2018, DFID should transfer the remaining bed nets (400,450) that were not distributed over the last year to DFID DRC’s health system strengthening programme (ASSP) operating in Kasais which has the ability to absorb them through routine distribution. The transfer of these bed nets will contribute to reduce the operational cost of ASSP as they have planned to purchase bed nets during no cost extension period.

DFID should continue to explore possible options to continue to deliver the work currently covered by Component 3, even if the other components need to be closed (decision by end May 2018). A related vfm assessment will be explored

Logframe related recommendations are captured at the end of section C.

DFID should assure the continuity of the supply chain in monitoring the pipeline order of 881,500 treatments courses. A vfm assessment related to this will be made.

Additional programme recommendations if delivery continues under Component 3

The programme should work with PNLP to improve the quality of data analysis undertaken at health zone level by undertaking effective formative supervision and by setting up a national workshop for data analysis once a year. (To be implemented if Component 3 continues, otherwise part of wider recommendations below)

The programme should also encourage PNLP to work with the Ministry of Health’s - District Health Information System 2 (DHIS2) - team to support better analysis of malaria data. Further to the identified areas for improvement, the Sentinel Surveillance Working Group meetings should consider how supervision of health facilities by the health zone could improve data collection and analysis. (To be implemented if Component 3 continues, otherwise part of wider recommendations below)

Wider Recommendations

Given the closure of Components 1 and 2, there are additional recommendations which may not be implemented under the current programme but should be considered in any future health and malaria programming. DRC accounts for 10% of the global malaria cases, one of the highest burdens for any one country. DFID should therefore ensure that lessons learned from the existing programme, and gains made under Components 1 and 2 of the current malaria programme are properly taken into account as it considers its approach to malaria in a new health business case (under development).

Prior to closure of the programme, DFID should work with MoH (PNLP and DPM) to ensure that progress made is sustained beyond the life of the programme including:

An evaluation of school distribution of bed nets carried out by the programme in 2016 found that bed net coverage by school distribution after a mass distribution exercise is effective. PNLP should ensure that any future mass distribution in DRC considers school distribution as additional mechanism to be used for routine distribution.

Encourage PNLP and the Ministry of Health (MoH) medicines department (DPM) to continue to advocate to Parliament for tax and tariff reductions on malaria commodities, and the setting up of committees to improve regulations, beyond the life of the programme according to recommendations from the Tanzania[3] trip in 2018.
[3] DFID co-funded (along with USAID) a trip to Tanzania for key stakeholders in PNLP, DPM and programme staff to learn how regulations in the private pharmaceutical sector were improved in that country.

As a part of promoting the use of Rapid Diagnostic Tests (RDT), PNLP should provide guidance on fever diagnosis and management instead of focusing only on malaria case management.

Wider Lessons

Any programme working with a new partner should ensure as part of the due diligence assessment that the organisation has a direct legal right to work in DRC. Teams should consider the composition of consortiums and ensure that implications of any unexpected changes in partnerships are mitigated against.
## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Increase to at least 80% the use of bed nets by pregnant women and children under five years of age in Kasaï Occidental (Kasaï and Kasaï Central) by 2018
Output number per LF		1	Output Score	C
Impact weighting (%):		20%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones / (March 2018)	Progress / (March 2018)	Comment
Non-cumulative number of bed nets distributed during the mass campaign in targeted health zones in Kasaï Occidental	N/A	N/A	Activity completed in 2015
Percent (%) children under five years of age old who slept under a bed net the previous night in targeted health zones in Kasaï Occidental	N/A	N/A	No activity undertaken this year
Percent (%) pregnant women who slept under a bed net the previous night in targeted health zones in Kasaï Occidental	N/A	N/A	No activity undertaken this year
Non-cumulative number of bed nets distributed through schools and community-based systems (households)	N/A	N/A	No activity undertaken this year
Non-cumulative number of teachers and community health workers (CHWs) trained in routine (continuous) distribution of bed nets	N/A	N/A	No activity undertaken this year
Non-cumulative number of household visits conducted by CHWs	N/A	N/A	No activity undertaken this year

Provide supporting narrative for the score

No activities have been delivered for this output over the past year. This is due to a required budget realignment not being completed by PSI. The realignment was necessary to allow the continued distribution of bed nets through schools and the community, after a budget overspend in the 2016 / 2017 financial year. The realignment was affected by the separation process between PSI and ASF, but could still have been completed in time to allow for activity this year. Delays to completion of the evaluation of the cost-effectiveness of school bed net distribution also impacted progress early in the year and were not clearly justified.

Recognising no agreed budget would mean there could be no delivery against milestones, a logframe amendment was agreed in February 2018 clarifying the expectation of no activity. In this situation therefore of scoring an output where no activity was expected, and no process indicators set, it has been agreed that the output should score a C given the ability to continue activity rested directly on PSI to present a budget to DFID for agreement.

Recommendation 1:

DFID should transfer the remaining bed nets (400,450) that were not distributed over the last year to the DFID health system strengthening programme (ASSP) operating in Kasai to contribute to the routine distribution of bed nets (end June 2018).

Logframe recommendation 1:

Once a decision is made on the future of Component 3 activity, a log frame refresh will be needed to adjust the score weighting of Component 1 is for further annual reviews and / or the Project Completion Report (PCR).

Wider recommendation 1:

Given the closure of Components 1 and 2 the following recommendations are not relevant to the current programme but should inform future health and malaria programming. DFID should ensure clear lessons are learned from the current programme and use these to inform the design of future support to malaria work under the new health business case. This should include specific consideration of how best to sustain and consolidate progress made in the sector to date. There is one specific recommendation under this output

An evaluation of school distribution of bed nets carried out by the programme in 2016 found that bed net coverage by school distribution, after a mass distribution exercise, is effective. If bed net distribution forms part of a future programme, school distribution should be considered.

Output Title	Increased availability, accessibility and affordability of Quality Assured Artemisinin Combination Therapies (QAACTs) in the private sector in Kinshasa
Output number per LF		2	Output Score	A
Impact weighting (%):		50%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones / (March 18)	Progress / (March 2018)	Comments
1.Non-cumulative number of treatment courses of QAACTs supplied through private sector importers in DRC	1,500,000	1,535,640	Met expectations (102%)
2.Number of selected accredited private sector outlets in project areas with Green Leaf QAACTs in stock (among outlets with any antimalarial in stock)	3,500	4,499	Substantially exceeded expectations (129%)
3.Percentage (%) of private sector outlets in project areas selling project supplied QAACT for children at or below the recommended retail price	50%	46.5%	Met expectations[4] (93%)
4.Cumulative number of RDTs distributed to private sector outlets/clinics in Kinshasa	813,000	1,359,150	Substantially exceeded expectations (140%)
5.Non-cumulative number of radio and TV spots on Green Leaf[5] broadcasted in Kinshasa	2,500	1281	Substantially did not meet expectations (51%)
6.Non-cumulative number of private providers (clinics and accredited pharmacies) trained in malaria case management	3,050	555	Substantially did not meet expectations (18%)
[4] At the beginning of programme in 2013, the private sector accounted for 70% of antimalarial dispensed in DRC, only 2.6% of these were QAACTs. The programme was very ambitious to set up a milestone for indicator 2.3 at 50% without clear evidence. Even if last year the programme did not met this expectation, given the challenging nature of the target set, the programme team deems the achievement at 46.5% (93% of the target) as within a range where it can be considered as met.
[5] The Green Leaf Logo (as previously used in other countries by the Affordable Medicines Facility – malaria initiative AFM-m a) is included in the product packaging by the manufacturers. This is used to demonstrate to consumers that the ACT is quality controlled.

Briefly describe the output and provide supporting narrative for the score

To make QAACT available in the private sector, the programme identified six market constraints to be addressed during the programme implementation and beyond. To address these constraints, the following approaches were put in place:

High ex-factory prices (manufacturer prices): The programme subsidises QAACT in the private sector through a form of co-payment which is used as an approach to guarantee importers and manufacturers’ orders of QAACT while making QAACT accessible to the population at lower cost. In 2016 and 2017, the commodity co-payment was 65%, which means the programme paid 65% of the manufacturer’s price and 35% is paid by the importers.

Progress over the past year
- The programme met expectations and supplied the market with 1,535,640 treatment courses. An additional manufacturer and four new importers joined the market which contributed to enabling the increase in the orders of QAACTs. An order of 881,550 treatments is underway and is expected to reach the country by the end of July.
- A total of 4499 drug outlets are now stocking QAACT with Green Leaf (quality assurance) logo, exceeding expectations. In January 2018, DFID, in consultation with the Ministry of Health and in line with the 2017 Annual Review recommendation, agreed that the programme could supply QAACT to all drug outlets covered by the programme rather than just accredited outlets. The programme judged that the withdrawal of QAACT from the non-accredited outlets would lead to their replacement by counterfeit drugs. There is a continuing need to support the availability of QAACT in unaccredited drug outlets through mapping and classifying outlets in Kinshasa city, training providers, and supporting accreditation of facilities.
- The Maximum Recommended Retail Price (MRRP) was set in 2015[6] at $1.5 per treatment course, (equivalent at that time to 1,395 Congolese Francs). The Mystery Client Survey carried out in December 2017 showed that the average price of Green Leaf QAACT is now $1.7. The programme has control of the price of QAACT at the importer and wholesale levels which is fixed at between 0.90$ and 1.05$. To address potential inflation of the retail price manufacturers and importers agreed that new orders of QAACT with Green leaf would include the price on the box. This had been expected to start in 18/19 prior to the decision to close Components 1 and 2.
  [6] In 2015 the exchange was 930 Francs for $1 (USD), currently the exchange is estimated at 1630 Congolese Francs for $1 (USD).

Poor quality of malaria case management: the programme addresses this through the distribution of malaria Rapid Diagnostic Tests (mRDTs) to private outlets, clinics and pharmacies with the objective of creating demand for mRDT and contributing to the implementation of the national policy of systematic testing of all fever cases prior to malaria treatment. In addition the programme also provides training to all private providers including those from non-accredited pharmacies. This was implemented with the objective of reinforcing their knowledge, attitude and practice on case management, antimalarial stock management and quality control.

Progress over the past year
- 1,359,150 mRDTs have been distributed so far during the programme, exceeding expectations. However an exit interview survey in February 2018 found that 45% and 31.82% of patients from private pharmacies and clinics respectively, still received an antimalarial after a negative mRDT.
- The number of private providers (clinics and accredited pharmacies) trained in malaria case management substantially did not meet expectations this year due to slowing down of activities related to uncertainty over the consortium arrangement.

Low consumer demand for QAACT: a strong communication strategy was implemented to stimulate demand. The evaluation of this strategy demonstrated that the sales increased during the intensive phase of the campaign and decreased after slowdown of the campaign. Discussions with other stakeholders concluded that there are other factors that could play on the demand, for example the existence of non-recommended, non-authorized and counterfeit antimalarial in the market could lead to the competition with QAACT with green leaf. We believe that this problem should be addressed by improving the regulation of the supply chain in country.

Progress over the past year

The number of radio and TV spots on Green Leaf broadcasted in Kinshasa has significantly not met expectations this year due to slowing down of activities related to uncertainty of the consortium arrangement.

High taxes and tariffs: , The programme is expected to provide support to reduce the retail price of QAACT in the long-term, which will removes the price barrier to utilisation of QAACTs by the poorest households.

Progress over the last year

In order to implement the commitment made by the Parliament last year to reduce taxes on malaria commodities from 69% to 9%, the National Assembly set up different working groups to review all existing tax related regulations and to elaborate and update new regulations on taxes and tariffs of anti-malarials. Programme staff was involved in these working groups. So far, there has been good progress in setting up of the structures but less progress in the implementation of the commitments made.

Absence of enabling regulatory environment and poor coordination of supply chain. The programme is expected to provide support to improve regulation of the supply chain in the private sector

Progress over the past year

In order to get more information and experience in this area, the programme, in partnership with Management Sciences for Health (MSH), USAID and an NGO working in health sector, undertook a trip to Tanzania to learn how regulations in the private pharmaceutical sector were improved. The lessons learnt from this trip are the following:

- Changes to the existing pharmaceutical system in country should be pragmatic and accepted by all parties involved.
- Changes should not disturb the existing system, but be complementary and integrated.
- Changes should be based on consensus among all actors.
- Continuous capacity building and formative supervision throughout the process are key factors for the success.
- Pharmacists are a cornerstone to successful changes.

After this mission, the programme had planned to provide feedback to the Minister of Health and set up a committee to manage the process (DPM). Unfortunately, the programme was suspended and there is a risk the gains made to date will not be sustained.

Lessons identified this year, and recommendations for the year ahead linked to this output

A Strong on-going commitment from Congolese Parliament is required to remove taxes on malaria commodities. Despite the fact that the government signed the Abuja Declaration[7] many years ago, the current political economy does not incentivise changes to the existing tax structures.
[7] http://www.who.int/healthsystems/publications/abuja_declaration/en/

Wider recommendation 2:
As part of the closure of Components 1 and 2 the programme will encourage PNLP and the Ministry of Health medicines department (DPM)[8] to continue to advocate to Parliament for tax and tariff reductions on malaria commodities, and the setting up of committees to improve regulations according to recommendations from the Tanzanian trip in 2018.
[8] DPM : Direction de Pharmacies et Médicaments.

Wider recommendation 3:
In promoting the use of mRDT, PNLP should provide guidance on fever diagnosis and management instead of focusing only on malaria case management.

Output Title	Improve the availability and use of information for malaria control in DRC for increased capacity of malaria control interventions
Output number per LF		3	Output Score	A
Impact weighting (%):		30%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones / (March 2017)	Progress / (March 2017)	Comments
1.Cumulative number of sentinel sites rehabilitated/created and provided with equipment	7	7	Met expectations
2.Cumulative number of quarterly sentinel site data validation sessions by PNLP at central level	3	3	Met expectations
3.Number of staff from the National Malaria Control Programme and research institutes trained during targeted training sessions (cumulative targets)	362	364	Met expectations
4.Cumulative number of surveys (insecticide and drug resistance, pre- and post-campaign surveys) implemented	29	30	Met expectation
5.Number of quarterly SSWG (Sentinel Surveillance Working Group) / GT-SS (Groupe de Travail - Surveillance Sentinelle) meetings (cumulative target)	8	8	Met expectation

Provide supporting narrative for the score

The overall score for this output is (A). This component was not affected by the PSI / ASF separation process as it is subcontracted by PSI to the Swiss Tropical Public Health Institute (STPH). However, activity was affected by exchange rate fluctuations of the (US$) dollar against the British pound (GBP). Whereas programme disbursement is in GBP, expenditure on the ground is made in dollars.

The continued progress made to rehabilitate and equip sentinel sites and to train health staff in use of District Health information System 2(DHIS2) has contributed to the improvement of data collection and analysis. Three Sentinel Surveillance Working Group meetings organised this year also allowed the programme to identify areas for improvement. These areas for improvement included: lack of internet access in remote areas; lack of motivation of health professionals; and lack of supervision of health facilities by the health zone. In addition, it was also observed that the use of DHIS2 and analysis of data at central level is not as effective as it could be.

In a field visit to Kenge health zone it was encouraging to observe that health workers had analysed their locally generated data to inform their malaria activities. This local ownership of the programme at health facility level should continue to be encouraged at each level of the health system.

Preparation of this annual review highlighted a difference in understanding between DFID and STPH about the definition of what constitutes a single survey for reporting against indicator four: Cumulative number of surveys (insecticide and drug resistance, pre- and post-campaign surveys) implemented. In retrospect this difference in understanding was also present in reporting of activity last year and the setting of the new logframe targets. This led to the programme exceeding expectations last year[9] and the setting of logframe targets which built on these achieved results reported. The additional results presented this year are therefore based on the understanding of DFID and PNLP that a single research protocol used in six sites is one survey and not six, despite the fact the data for each site can be analysed and used independently. If this component of activity continues in the future the logframe definition needs to be clarified.
[9] If these results were now corrected for last year’s annual review the score for the output would not have changed and thus the overall annual review score would not have changed.

Lessons identified this year, and recommendations for the year ahead linked to this output

Recommendation 4:
DFID should continue to explore possible options to continue to work on Component 3, and this decision should be taken by the end of May 2018

Recommendation 5:
PNLP and the programme should work together to improve the quality of data analysis undertaken at health zone level by undertaking effective formative supervision and by setting up a national workshop for data analysis once a year.

Recommendation 6:
In light of the areas for improvement identified in Sentinel Surveillance Working Group meetings work is needed to consider how supervision of health facilities by the health zone could improve data collection and analysis.

Logframe recommendation 2:
A clear methodology note setting out how logframe indicators will be measured for the remainder of the programme delivery and / or for the Project Completion Report (PCR) should be produced by the lead programme adviser in collaboration with the Results Adviser (DATE)

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year

At impact level the programme focusses on reducing malaria incidence and mortality and is aligned with the three pillars of DRC’s National Malaria Control Strategic Plan 2016 - 2020: (i) prevention of malaria (ii) malaria case management, and (iii) epidemiological surveillance.

The following statements from the 2017 World Malaria Report, suggest that the chosen programme interventions remain good practice, and thus their place in our theory of change is still appropriate:
- Bed nets continue to be an effective tool for malaria prevention, even in areas where mosquitoes have developed resistance to pyrethroids;
- Artemisinin (partial) resistance has not been reported to date and first-line ACTs remain efficacious in all malaria endemic settings;
- Effective surveillance of malaria cases and deaths is essential for identifying the areas or population groups that are most affected by malaria, and for targeting resources for maximum impact.

ACT
- Additional resources for activities
- Technical expertise
- Infrastructure, equipment and technology
KEY:

PNLP Strategic function
Partnership with drug manufacturers/govt. depts.

Input
Output
Impact
Outcome
Improve treatment outcomes
↑ uptake
DONOR EFFECTIVENESS
Better targeting of interventions
↑ demand for information/ empowerment and accountability
POTENTIAL ACTIVITIES
- Registration of drug vendors
- Training of drug vendors
- Community awareness raising
- Monitoring of prices and reporting stock-outs
- (subsidies)
- Reduce import fees on ACTs

- Surveillance of disease burden and resistance
- Evaluation of interventions
- Strengthened information use
- Partnership with academic institutions
↓ risk of resistance
↑ awareness/knowledge among consumers and providers

↑ coverage
Increase availability
↑ supply LLINs
Empowerment and accountability

↑ supply and demand
↑ utilisation
↑ volume and consistency of supply of ACTs
↓ cost of ACTs
↓ use of monotherapy and other drugs
↑ use of first-line ACTs

INFORMATION
- Training
- Equipment
- Rehabilitation and development of sentinel sites
- Operational research and impact evaluation

REDUCED MORBIDITY AND MORTALITY FROM MALARIA

↓ incidence and transmission of malaria
↑ effectiveness of interventions

BEDNET
Mass free distribution
- Commodities
- Training and supervision
- Management
- Awareness raising

Social marketing
- Awareness raising
- Subsidies

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

Progress against 2018 outcome targets is shown in the table below.

	Indicators	Milestones March 2018	Progress March 2018
1.	% of individuals in households who slept under an LLIN the previous night in targeted health zones in Kasai Occidental	NA	NA
2.	% of children under 5 years who received quality-assured ACT among those receiving any antimalarial in the private sector in Kinshasa	64%	65%
3.	Number of sentinel sites providing timely and complete reports (cumulative targets)	8	7

No surveys were planned this financial year to provide information on this indicator. However, the expected 2019 target for the first outcome indicator may still be achieved even with closure of Component 1, as the remaining 400,450 bed nets purchased by the programme will be transferred to our health system strengthening programme (ASSP) for use in routine distribution in the same geographical area. The programme was not able to undertake a school distribution in Kasai areas this year. Whilst progress cannot be measured this year, data will be available for the PCR, from a Multiple Indicator Cluster Survey (MICS) in 2018.

The results for this year have however already surpassed the original logframe 2019 target. However, the logframe target for 2018 under Outcome 2 was revised in February 2018, but at that time the 2019 targets were not adjusted, so accurate monitoring of progress for this year is not possible at this stage.

The third outcome target is expected to be achieved if a way to continue Component 3 activity is found.

Achievement of the impact target depends also on the actions of many other actors and thus may still be achieved despite closure of Components 1 and 2.

Logframe recommendation 3:
As part of the logframe refresh, targets for 2019 should be reviewed for Outcome 2 to take account for reduced ordering of QAACTs in 2018.

Logframe recommendation 4:
Plans for closing out of the programme and the logframe refresh need to set out how final reporting of outcome and impact indicators will be measured.

Explain major changes to the logframe in the past year (1/2 page)

The logframe was amended to reflect adjustments in the expectations for Components 1, 2 and 3 on the basis of the recommendations made in the 2017 annual review and, more significantly, the disruption of implementation of programme activities due to the changes that occurred in the consortium in 2017. As part of the logframe amendment no new indicators were added and there was no change in risk identified.

 The following changes were made to the logframe:
- Output 1: Distribution of long lasting insecticide-treated bed nets: all the milestones planned for March 2018 were transferred to the following financial year. One indicator (number of people reached during household visits conducted by Community Health Workers) was removed from Output 1 as it was no longer relevant because another indicator is reporting the same information.
- Output 2: Improving availability, accessibility and affordability of quality-assured artemisinin-based combination therapies (QAACTs) in the private sector in Kinshasa: All the milestones planned for March 2018 were updated on the basis of the performance achieved over the previous year and the suspension of the programme activities.
- Output 3: Strengthening the capacity of the Programme National de Lutte Contre le Paludisme (PNLP) to generate and use data for decision making: a number of milestones for March 2018 were reduced or increased based on the achievements made last year.
Describe any planned changes to the logframe as a result of this review (1/2 page)

There are two possibilities for required logframe amendments

Extension of Component 3

If Component 3 is continued, the programme will continue and thus the logframe will need to be updated to reflect any revised milestones for close out of Component 3 by March 2019 and then programme end in September 2019. Given that activities will likely start slowing down in advance of the final project close date this should be reflected in targets for the final six months. For components 1 and 2, milestones need to be set until the end of the delivery period (planned for end July 2018). A further annual report would be due in May 2019 and a PCR report would be due in December 2019.

Closure of all components

If all components closed, the logframe would need to be amended to capture any remaining period of delivery of the 3 components. Closure of the programme would be complete by the end of September 2019 with a PCR expected by the end of December 2019.

In both options above a logframe revision is needed to clarify targets for the programme end, and this revision provides an opportunity to correct a number of relatively minor errors detected in the current logframe (some of which are highlighted in previous sections).

### Full list of logframe recommendations

Logframe recommendation 1:
Once a decision is made on whether activity under Component 3 will continue or not a logframe refresh should be undertaken in which the score weighting of component 1 is addressed for further annual reviews and/ or the project completion report.

Logframe recommendation 2:
A clear methodology note should be produced setting out how logframe indicators will be measured for the remainder of the programme delivery and / or for the Project Completion Report (PCR).

Logframe recommendation 3:
As part of the logframe refresh, targets for 2019 and / or the end of programme should be reviewed for outcome 2 to take account for reduced ordering of QAACTs in 2018.

Logframe recommendation 4:
Plans for closing out of the programme and the logframe refresh need to set out how final reporting of outcome and impact indicators will be measured.

Logframe recommendation 5:
Revision of the logframe should clarify targets for the programme end and should correct errors found in the current logframe.
## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

Based on the past year, the programme continues to achieve VfM as assessed using DFID’s 4Es model:

Economy

On economy, the Programme is benefitting from the Global Fund negotiated prices in the purchase of QAACTs using the pooled procurement mechanism - PPM[10]. The Global Fund has established framework agreements with manufacturers of artemisinin-based combination therapy and other antimalarial medicines with the aim to achieve lower prices and to also ensure the sustainable and reliable on-time supply of the full range of necessary antimalarial medicines.
[10] https://www.theglobalfund.org/media/5812/ppm_actreferencepricing_table_en.pdf?u=636566353180000000

Efficiency

During the year and following the completion of key studies[11] conducted to assess the outcomes of the programme, some implementation adjustments were made to improve the efficiency of the programme. Capacity building and supervisory activities were re-directed towards the periphery of Kinshasa where population density and malaria risk is highest. There was also an emphasis placed on reaching private pharmacies where the poorest mostly directly seek care, in order to reduce the costs of accessing care (transport and QAACT treatment). This means that more people have access to and can afford QAACTs. This year, up to 4,499 pharmacies have Green Leaf QAACTs in stock, a 12% increase in coverage (in comparison to the previous year when 3,850 outlets were providing QAACTs).
[11] (a) Evaluation of the phase of marketing campaign (PSI, 2017) (b) Cost effectiveness of LLIN school distribution (‘c) Mystery shoppers’ studies (PSI, 2017):

During the year, 707225 malaria Rapid Diagnostic Tests (mRDTs) were distributed (funded by Global Fund support) with a cumulative total of 1,359,150 distributed since the start of the programme. The combination of QAACT with Green Leaf and mRDTs has the potential to provide further efficiency. This combination of activities means that if all fever cases were tested using mRDTs, then as long as the test result is observed this ensures that antimalarial drugs are used only when necessary - reducing the number of antimalarials consumed and preventing the emergence of resistance

Effectiveness

An analysis of the cost effectiveness of LLIN school distribution[12] was completed in June 2017. Results showed a unit cost of £7.3 per LLIN, which is more cost-effective than distribution through ante-natal care (ANC) which costs £7.8 per LLIN distributed. School distribution is also able to reach a wider population and thus strongly contributes to maintaining the bed net coverage achieved between mass LLIN distribution campaigns.
[12] Cost Analysis of School Net Distribution in the Democratic Republic of Congo, by J. Yukich (June 2017) for the PSI/Congo

The low price of QAACTs that has been obtained by the programme has been reflected in the substantial fall in the cost of these drugs to the consumer. This has rendered them much more affordable and competitive on the market. The average price for Green Leaf QAACT at the pharmacy level is $1.7. This is lower than the $2 cost to the consumer at the same point last year and the $6.50 at the beginning of the programme showing continued progress, although not yet reaching the $1.5 programme target.

Equity

This programme is aligned with the Leave No One Behind (LNOB) approach in DFID DRC. Free bed net distribution and the subsidy of malaria medicines allows better access to malaria prevention and treatment for those on low incomes. However, the estimated price of $1.7 per treatment course of ACTs remains a barrier to accessing care for many people.

The programme has responded by continuing its advocacy to the DRC Government to remove tax and tariffs on malaria commodities (in accordance with the Abuja Declaration[13]), with the objective of reducing the price of malaria drugs further. Despite taxes and tariffs on antimalarial being perceived as a source of revenue for the government of DRC, the National Assembly has demonstrated high commitment and has suggested a reduction in taxes and tariffs from 69% to 9% as a first step, with the aim of total removal of taxes and tariffs in the long term.
[13] http://www.who.int/healthsystems/publications/abuja_declaration/en/

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

The slow-down and ultimate suspension and early termination of two components of the programme means that expected results will change. The programme is on track to deliver original results under Component 1 and 3 but will have to revise its targets on Component 2. A Value for Money assessment will have to be made to compare any revised final targets that will be downgraded against the budget balance that will be remaining for those components. This VfM assessment should be made at the point where new end of programme targets are being agreed and if an extension to Component 3 is being sought.

In the context of the wider portfolio, DFID is considering if Component 3 should continue delivery until March 2019 as originally planned. Component 3 has contributed to the improvement of DRC’s capacity in malaria data reporting at a global level. The cost related to the rehabilitation of sentinel sites was underestimated at the beginning of the programme, leading to an adjustment of the number of sentinel sites planned for rehabilitation during the year. Through its support to 10 sentinel’s sites out of 26 for malaria epidemiological surveillance, Component 3 has contributed to strengthening the capacity of Nationa Malaria Control Programme (PNLP) to report routine data. There is evidence that DFIDs support to 38% of sentinel sites across the country has improved DRC’s capacity in capturing data on malaria cases. The latest WHO report has shown that DRC is ranked sixth among countries capturing malaria cases through the surveillance system after Venezuela, Brazil, Rwanda, Central African Republic, Zambia and Kenya and this is likely to be attributable to the support provided under this component but hasn’t been fully evidenced yet.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

The overall risk rating for the programme is “Major” and has gone up from a “moderate” rating in the last annual review. The change in rating is mainly attributed to an increase in the rating for delivery risk as explained below. A summary of key risks and significant changes in the programme assessment includes the following: (Net risk after mitigation is shown in brackets)

External context (Major)

The external context risk is made by three main elements: political instability, economic crisis and weak regulation of the supply chain. This has increased from the last year as political uncertainty caused by election delays in DRC could have a negative impact for any on-going delivery of Component 3 of the programme. DFID DRC’s election programme will provide regular updates on progress towards the election. In addition there is risk that weak regulation of the supply chain could allow counterfeit and non-recommended medicines to circulate in the market. The PNLP is now a member of the board that provides licences for sale of medicines which is helping regulation. The programme will continue to monitor the effectiveness of this measure. The high inflation of Congolese francs continues to increase the price of QAACTs making them difficult for those on low incomes to access.

Delivery risk (Severe)

The delivery risk is rated as severe and has been realised over the past year. DFID had to close two of the programme components due to the partner’s inability to deliver. The programme is implemented by the consortium led by Population Service International (PSI) and was largely delivered through its local affiliate Association de Santé Familliale (ASF). The separation between the two organisations affected delivery of Components 1 and 2 over the last year and the situation is unlikely to change in the coming year. DFID has therefore mitigated the risk by making a decision to close the two components of the programme by the end of July 2018. Options to continue to delivery under Component 3 are still being explored.

Fiduciary risk (Minor)

The fiduciary risk for this programme remains minor and has reduced from last year. No activity was implemented for component 1 over the past year and no further delivery activity is expected in 2018/2019. For component 2, subsidies are paid to manufacturers’ directly by PSI headquarters which has strong financial control in place. At importer level prices are fixed in collaboration between the importers and the programme. The programme conducts regular visits to ensure prices at importer level are complied with. Beyond importers, the programme set a Maximum Recommended Retail Price (MRRP) that is being monitored through tools including supervisory visits and the quarterly Mystery Shopper surveys. Furthermore, the programme agreed that future orders will have the MRRP on the Green Leaf QAACT boxes to ensure that consumers know the price, and contribute to monitoring. This was expected to start in 2018/19 but with the closure of this Component 2, this will now not be taken forward.

Financial management has been challenging over the past year as delayed reporting has led to poor financial forecasting, and delayed disbursement of funds. This is detailed out in section F below.

Safeguarding risk (Major)

Safeguarding of beneficiaries remains a major risk to the programme especially with the slowdown of activities on components 1 and 2. This risk is now likely to be realised as the programme is closing off the two components. A decision has been taken to provide a further 881,500 doses of ACTs to cover some of the on-going treatment needs and the transfer of the remaining LLINs to ASSP (which is active in the same province covered by the programme) will help to maintain bed net coverage.

Reputational risk (Moderate)

The reputational risk associated with closure of components 1 and 2 is moderate. Our intervention to date on market development for QAACT has been well perceived by all key stakeholders in the malaria sector. The close out process for Component 2 could therefore impact negatively on our reputation.  As a mitigation measure, the programme has planned to continue to make QAACT with Green leaf available on the market for a further period through fulfilling a pipeline order of approximately 881,500 treatment courses. A preliminary discussion has also taken place with the Global Fund who may be able to fill the gap in programming in the short term. In the mid-term, the programme team is exploring the option available to continue to work on malaria prevention and treatment under the new business case for health programming in DRC.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial and financial issues (1-2 pages)

Delivery and performance of partnerships

The separation between PSI and ASF led to a slowdown of activities and eventual suspension in the implementation of Component 1 and 2 for a period of six months starting February 2018. Activity continued under Component 3 which is subcontracted by Swiss Tropical Public Health Institute (STPH).
Commercial issues

The quality and timeliness of quarterly reports has been a challenge over the last financial year. There were changes to key personnel at PSI especially on the financial management side and the transition to new staff has been difficult, exacerbated by the uncertainties over their relationship with ASF and lately their status in country. This has resulted in late financial and narrative reports, leading to poor financial forecasting, and delayed disbursement of funds. The separation process between PSI and ASF has made it difficult for DFID to engage with the partner on this issue as the contractual relationship is likely to end earlier than anticipated. The DFID programme team continued to have regular monthly meetings with the staff who have remained in the project but coordination between PSI (US) headquarters and a depleted PSI (Kinshasa) in country team remains a challenge.

The programme completed an updated delivery chain map during the course of the year. This has been a useful tool for both DFID and PSI to identify full funding flows and ensure accountability lines are well spelt out. This will need to be updated further in the coming year given the likely changes to the delivery model.

Financial performance

DFID has disbursed to PSI £5,467,461 in the course of the financial year 2017/2018 out of the baseline forecast of £5,923,551. However, PSI has spent £5,227,791 out of the total amount disbursed by DFID, representing 97% of annual disbursement. The total DFID disbursement over five years of implementation (out of six) is £29.8m or 83% of the £36m contract with PSI/ASF. The expenditure for the year was distributed as follows:

Breakdown of expenditure per component

Component 1 – distribution of bed nets is now completed and 1% spend was on closing out activities related to bed net distribution through schools in Kasai Central.

Component 2 – represents 72% of the year’s expenditures with the following key activities: subsidy for QAACTs, promotion and communication of Green Leaf QAACTs and different studies around this new approach to influence the QAACT market.

Component 3 – represented 27% of the expenditures spent across rehabilitation and equipping of malaria sentinel sites, training of national malaria programme staff and surveys.

Table 1: Expenditures Financial year 2017/2018 per budget line

Budget category	Budget total (Contract Budget)	Total expenditure to date (March 2018)	Total FY 17-18 expenditure	% of total expenditure FY 17-18
Subcontracts – STPH (output 3)	£4,342,429	£2,723,744	£1,545,971	29.60%
Staff	£4,459,865	£4,136,660	£1,070,987	20.50%
Research and evaluation	£2,438,647	£1,234,402	£508,418	9.70%
Administration and procurement fees	£2,383,929	£1,721,419	£383,763	7.30%
Consultants and services	£1,352,545	£1,665,227	£366,066	7.00%
QAACTs subsidies	£2,263,950	£894,222	£349,920	6.70%
Other direct costs	£944,976	£1,286,214	£328,414	6.30%
Promotion and communication	£3,241,106	£2,219,630	£314,841	6.00%
Training	£1,691,822	£1,309,408	£149,741	2.90%
Travel	£2,032,010	£884,927	£116,050	2.20%
Health supplies and related cost (bed nets, RDTs, gloves)	£10,389,579	£11,058,636	£83,547	1.60%
Furniture/equipment	£512,826	£325,155	£10,075	0.20%
Total	£36,053,684	£29,459,644	£5,227,793	100%

Asset management

The remaining 400,450 LLINs after the completion of Component 1 will be transferred to the ASSP programme for routine distribution. A regular monitoring of assets was made as part of the quarterly narrative report package and a spot check conducted during the field visit.

With DFID’s decision to close Components 1 and 2, there are assets that will have to be handed over to other DFID programmes or to Component 3, if it is decided this component can continue. This decision is currently under discussion and the assets handover will be done in line with the SMART rules guidance.

PSI updates the asset register and includes it in the reporting cycle and as an annex to their quarterly reports. DFID DRC’s programme officer undertakes regular spot checks against the latest asset register on field visits. All asset checks completed to date have not raised any concerns and the programme team is confident that asset management is sound.

Date of last narrative financial report(s)	29 January 2018
Date of last audited annual statement (s)	19 April 2018

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

This programme is monitored through a quarterly reporting system supplemented by an annual meeting with all DRC malaria stakeholders. Additionally, the programme team holds regular monthly meetings between DFID and PSI-ASF. During 2017/2018 and as part of monitoring, the programme team also made four field visits.

Evidence (1/2 page) [Include any relevant text on evaluation in this section]]

The programme initially planned to work with accredited pharmacies and those under supervision of pharmacists reaching a targeted number of 195 outlets. The findings of the “Mystery Client” survey carried out last year however demonstrated that QAACTs were present in approximately 3800 outlets which were not complying with the inclusion criteria of the programme. Based on this, a recommendation was made to assess and decide whether the programme should change the approach or change the inclusion criteria.

In response to this recommendation, DFID, the Ministry of Health (through PNLP and the regulatory directorate in charge of pharmacies and drugs, DPM) made a decision to extend the scope of the programme to work in all estimated 5,000 outlets within Kinshasa city, with supporting measures including mapping of outlets, training of providers and accreditation. This decision facilitates access to QAACTs for poorer areas of Kinshasa and prevents the use of counterfeit drugs.

An external evaluation was not planned for this programme. However, three surveys were implemented during this financial year as follows.

Mystery Shoppers’ studies:

Objective: This study is implemented each quarter to monitor three indicators of programme: 1) availability of QAACT with Green Leaf logo in drug outlets in Kinshasa, 2) recommendation of QAACT with Green Leaf logo by providers and 3) average price of QAACT with Green Leaf logo in drug outlets in Kinshasa.

Key findings: The last (October-December 2017) survey shows the following - QAACT with Green Leaf were available in 71% of outlets surveyed; 42.5% of providers were recommending the QAACT with Green Leaf branding to antimalarial shoppers; the average pricing of QAACT with Green Leaf branding was $1.7; and 46.5% outlets were selling QAACT with Green Leaf logo below or at the MRRP.

Mystery Client survey:

Objective: Assess provider’s compliance with national guidance on malaria case management for patients with negative RDT.

Key findings:

Key findings (%):	Clinic	Accredited Pharma	Non accredited Pharma
Mystery clients mRD Tested	63.6*	100	100
Correct diagnostic (negative)	46.4	50	82.8
Correct treatment / guidelines	26.2	70	37.5
Waiting time (> 5 mins)	53.6	30	12

Exit interview

Objective: Determine the proportion of fever cases tested, voluntary testing, positive cases correctly treated and compliance with recommended price.

Key findings:
- 9.9% and 9.23% of fever patients from private pharmacies and clinics, respectively, voluntarily requested malaria RDT.
- 70.91% and 52.69% RDT positive patients from private pharmacies and clinics, respectively, received a QAACT.
- 45% and 31.82% from private pharmacies and clinics, respectively, received an antimalarial for negative RDT.

The two surveys (Mystery Client and Exit Interviews) have demonstrated that people who have tested negative for malaria are still receiving QAACTs. The National Malaria Control Programme (PNLP) should therefore continue to work on the management of fever cases.

Learning (1/2 page)

Through the quarterly and annual meeting involving PNLP and malaria sector stakeholders, the programme shares evidence and lessons learnt to get feedback for better implementation, and share information on the programme. For example, in coordination during World Malaria Day Activities on 25th April 2018, there was a presentation on key findings from the survey conducted earlier this year.

The innovative approach implemented under Component 1 (school distribution of bed nets) has demonstrated its added value in maintaining the level of bed net coverage after mass distribution campaigns and should be considered as a routine mechanism for bed net distribution...

After two years of effective implementation of the market development for QAACT with Green leaf (Component 2), the preliminary results show that malaria case management can be improved in the private sector by: implementing WHO recommendation of systematic testing prior to treatment and by reducing the price and increasing the presence of QAACT with Green Leaf logo in the market. However the weak regulation, high taxes and tariffs and poor coordination of the supply chain continues to facilitate the presence of counterfeit and non-recommended antimalarial drugs on the market.

As a pioneer in this new area, DFID has influenced key malaria donors like Global Fund and USAID who have integrated these innovative approaches in their respective interventions. Given the closing of Component 1 and 2, DFID DRC should now plan how to sustain and build on progress made over these two components.

Progress on recommendations from previous reviews (1/2 page)

Status	Recommendations	Operational responses
1	The analysis of the cost-effectiveness of the routine distribution of bed nets through schools needs to be completed / Deadline: May, 2017	This analysis was completed in June 2017. Results show a financial cost of £7.3 making LLIN school distribution an effective health tool with good Value for Money as compared to £7.8 cost per LLIN through ante-natal care.
2	The results of the evaluation and of the cost-effectiveness analysis of this intervention should be shared and discussed with the NMCP and other donors, in order to inform policy and future programing / Deadline: June, 2017	Results of the cost effectiveness of LLIN school distribution was shared and discussed under the leadership of NMCP at a workshop that gathered all malaria partners including USAID/PMI, UNICEF and the Global Fund in November, 2017. / As a result, the NMCP adopted LLIN school distribution as a national approach to maintain LLIN coverage, especially between 2 mass campaigns.
3	In view of the delay in implementation of routine distribution to households, DFID, with PSI-ASF, should re-examine the case for continuing with this, as well as the availability of funds to do so. In light of the outcome of Recommendation 2, DFID should also consider whether to continue and / or scale up the routine distribution of bed nets through schools, within the time and funds that are currently available under the business case. [NB: One or other (or both) of these will need to take place if the programme is to achieve its headline result on the number of bed nets distributed.] / Deadline: June, 2017	Following the positive outcome of the pilot phase of the LLIN school distribution in 10 health zones in the province of Kasai Central, the programme decided to scale up this approach and requested a budget realignment to make it effective, unfortunately the separation process between PSI and ASF prevented the programme completing the process.
4	In view of the fact that the small number of importers that are active in the market has imposed a significant bottleneck on number of QAACTs supplied, the programme needs to closely monitor the entry of additional importers into the market, to ensure that this takes place and has the desired effect. The programme should be ready to act (to the extent that it is able) to address constraints and facilitate market entry by importers. / Deadline: over year 5	Four more importers entered the QAACT private sector market in Kinshasa. AMT Pharma entered the market in May 2017, Prince entered in October 2017, Unique Pharma in December 2017 and Gurmed in February 2018. This was facilitated by the programme.
5	The programme must continue to closely monitor and where possible actively intervene to support progress in improving the effective regulation of the market for anti-malarial drugs in DRC, including through advocacy. A similar approach should be taken with regard to the removal of taxes and tariffs on QAACTs. / Deadline: over year 5	The program in partnership with MSH, a US based NGO, organised an experience sharing visit to Tanzania to learn from the country’s experience in shaping an unregulated pharmaceutical private sector. / The program was and is still working closely with the MoH and the national parliament on the removal of taxes and tariffs from antimalarials.
6	Apparent inconsistencies in performance in this component (e.g. high performance at outcome level despite poor performance against output indicator 1) need to be examined, explained, and if necessary addressed. / Deadline: September 2017	Through its communication strategy, the programme emphasise the message to use the antimalarial recommended by PNLP including those with green leaf and promoted by the programme since the programme is in support of compliance with the national malaria policy in the private sector. The survey methodology did not specify the brand of QAACT to be assessed and this may explain these inconsistencies.
7	PSI-ASF should strengthen measures to ensure that recommended pricing for malaria testing and treatment is understood by consumers and adhered to by service providers. / Deadline: over year 5	The program set up a hotline allowing consumers to get information whenever they need and to express concerns. Furthermore, the programme requested that new orders of QAACT with Green Leaf carry the MRRP on their boxes to ensure consumers are informed on the price that should be paid. This was planned to start in 2018/19.
8	The programme needs to systematically reassess the supply and demand side constraints to ensure that these have all been identified and are being optimally addressed. / Deadline: July, 2017	The program conducted a number of studies to assess the supply and demand side constraints. These included an assessment of market need for QAACT in Kinshasa, an evaluation of the first phase of the marketing campaign and a study of providers practice at private pharmacies.
9	The programme urgently needs to reassess the support that it is providing to outlets that are not officially entitled to carry out malaria case management, and whether (even if it is able to continue to work in these outlets) it should not adopt a more limited but intensive approach to bringing about the change in QAACT use that is sought. This needs to be done in discussion with the NMCP, the Ministry of Health and with DFID. / Deadline: August, 2017	In agreement has been made between DFID, PSI and MoH to continue promoting and supplying Green Leaf QAACT to all outlets including the non-accredited outlets, with accompanying measures in place (outlet mapping and training and supervision of providers )
10	Drawing on evidence and experience from other countries, the programme should develop a strategy with the NMCP to address the high proportion of cases in which a QAACT is administered despite a negative test result, and then implement and monitor the effectiveness of that strategy. Where necessary, the programme should be prepared to fundamentally reassess its approach if it is unable to achieve positive change. / Deadline: Ongoing	The program developed and is implementing a training and formative supervision plan to improve knowledge, attitudes and practices of private providers in national malaria policy and treatment. The focus of the training is case management including systematic testing and compliance with the test result. Training is followed by continuous formative supervision to trainees. / The monitoring and evaluation system put in place through quarterly survey (Mystery Shoppers survey) will assess progress and the programme will respond to the results accordingly.
11	This component has scored a B in two consecutive years. This component of the programme should therefore be put on a targeted Performance Improvement Plan (PIP) to support the achievement of its objectives over the course of that year. Failure of this will result in the closure of this component. / Deadline: June, 2017	The PIP was successfully implemented in six months following the annual review and this component is now on track

This annual review was led by the SRO and consisted of the following.
- Review of quarterly financial and narrative report
- Presentation on annual progress with key malaria stakeholders including WHO, USAID, PNLP, IMA on 26/02/2018
- PSI programme annual report
- A field visit to sentinel sites in Kenge health zone on 23 February 2018

The attendees at the presentation on annual progress provided their input for the improvement of the work on the Component 2, especially on tax removal and regulation of the private sector.
List of acronyms

ACT	:	Artemisinin-based Combination Therapy
AL	:	Artemether-Lumefantrine
AMF	:	Against Malaria Foundation
AMF-m	:	Affordable Medicines Facility – malaria
ASAQ	:	Artesunate-Amodiaquine
ASF	:	Association de Santé Familiale (PSI-ASF’s affiliate in the DRC)
ASSP	:	Accès aux Soins de Santé Primaire (DFID funded Access to Primary Health Care)
CHAI	:	Clinton Health Access Initiative
CHW	:	Community Health Workers
CI	:	Confidence Interval
DFID	:	Department for International Development
DHIS2	:	District Health Information System 2
DPM	:	Direction de Pharmacie et Médicament (Pharmacy and Medicines Directorate)
DPS	:	Division Provinciale de la Santé (Provincial Health Division)
DRC	:	Democratic Republic of the Congo
EACP	:	Evidence, Analysis and Coordination Programme
FDSS	:	Fonds de Développement des Services de Santé (Health Services Development Fund)
IMA	:	IMA World Health
ICP	:	Inter-Personal Communication
LLIN	:	Long-Lasting Insecticide-Treated Nets (generally referred to as ‘bed nets’ in this document)
MSP	:	Ministère de la Santé Publique (Ministry of Public Health)
NMCP	:	National Malaria Control Programme (Programme National de Lutte Contre le Paludisme)
OJEU	:	The Official Journal of the European Union
PMI	:	Présidents Malaria Initiative
PNLP	:	Programme National de Lutte Contre le Paludisme (National Malaria Control Programme)
PSI-ASF	:	Population Services International
RDT	:	Rapid Diagnostic Test
SADC	:	Southern African Development Community
STPHI	:	Swiss Tropical Public Health Institute
SSWG: Sentinel Sites Working Group
QAACT	:	Quality-Assured ACT
WHO	:	World Health Organization