Intervention Summary

## Title: Mozambique Democratic Governance Support Programme

What support will the UK provide?
The UK will provide financial and technical support to a range of non-governmental organisations and groups, including urban communities, civil society organisations, policy orientated think-tanks and the media. The support will help these groups to improve the accountability and responsiveness of government at municipal and central level. Through the support received the groups will be able to aggregate, articulate and press issues which are a priority for the women, men and youth of urban Mozambique. UK support will help improve communication initially in focal urban districts, to ensure that local priorities and concerns are incorporated into government planning at the municipal level, and become a part of the agenda at the national level. Women, men and the youth in target districts will be able to establish channels through which the locally identified priorities for their development can be represented in municipal planning processes and documents. The support provided by the UK will facilitate the space, skills, and human, technical and financial resources for this process to gain traction. / The Democratic Governance Support Programme (DGSP) approach is based on the findings of targeted analysis and design work[1]. This preparatory work has shown that democratic institutions in Mozambique have little incentive to be more proactive in providing and promoting the rights and freedoms of citizens without being held accountable for their actions and omissions[2]. This will not happen without effective demand from society, but the demand also needs to be listened to. The programme aims to facilitate a process that will identify and constructively channel such demand in a manner that is responsive to the needs of the poor, and inclusive of all relevant stakeholders from the outset. [3] / Priorities, in terms of issues, will be defined through a process of discussion and consensus-building. The process will be fully inclusive and take a discursive, rather than adversarial approach, stimulating local processes and mechanisms, not creating new ones. A fundamental part of the programme strategy is to promote gender equity, and so, at every stage, the active participation of women, men, youth, and people who are vulnerable will be emphasised. This approach directly supports the Government of Mozambique’s priority to promote peace and dialogue[4]. / DGSP will focus much of its effort in 5 urban municipalities in the south, centre and north of Mozambique. Analysis[5] of support provided to central level democratic institutions demonstrates little impact and working at the municipal level allows a greater opportunity to bring all actors, (community, political, legislative, executive) together on a pragmatic, problem-solving basis. Urban areas represent a useful incubator for deepening democratic values and processes. They are densely populated and expanding. The populations are relatively better educated, with more access to diverse media, and include large numbers of youth. In the preparatory phase for the project design[6], the youth of Mozambique are highlighted as an important emerging actor for strengthening democracy. / A second programme component aims to reinforce communication, accountability and transparency in government - at the municipal and central level, and between the two. It will link policy makers at both levels of government. It will link communities and the issues they identify as important with national policy debates and media investigations. Access to policy analysis, informed by priorities within the target communities, will be expanded by the use of a challenge fund. Academic, NGOs and think-tanks will be able to bid for small grants from the programme to pursue policy-orientated research. The programme will then use this analysis to stimulate lively, informed, and constructive public debate. / The third component supports the strengthening of a vibrant and diverse media. The media is key to enhancing communication, and promoting accountability[7]. DGSP will establish a second challenge fund to make grants to media houses, which submit proposals according to strictly objective criteria broadly in support of the programme purpose. The project will also provide support to strengthen the overall enabling environment for free, financially sustainable media. / The programme will run between 2011 and 2016 (a five year period) with implementation beginning in the third quarter of 2011. It will cost £10 million over this period. The programme has been designed in such a way that other donor funding will allow an extension of the geographical focus. Other bilateral donors are interested in participating, though there are not donors able to commit funds in the current financial year. / Security issues: A Hypothetical Example / Crime and security are key problems identified in Mozambique, particularly by urban people (Afrobarometer). Addressing crime and security is a potential area that interest groups could identify as part of this programme. Below describes how this might happen in practice. / A community organisation and the Association for Informal Vendors are both very concerned about crime affecting their well-being and their businesses. With the programmes help, they decide together to raise the problem on two local radios broadcasting in the urban area. They invite religious leaders, community leaders from different neighbourhoods, representatives from community policing councils and elected political representatives to a public meeting to discuss what are the main problems being experienced and what needs to be done. Two main issues raised by participants are the lack of police patrolling the streets in poorer neighbourhoods and the lack of street lighting in both poorer neighbourhoods and around market areas. / Municipal assembly representatives agree to raise the issue of street lighting in the municipal assembly. Community associations work together with local radio and the press to ensure crime is being reported in the media and to share views on where street lighting is most urgently needed. Community policing councils are encouraged to do more to channel concerns about crime and security to both the local police and to political representatives. The municipal government as a result holds a public consultation on its draft plan for investment in street lighting, which leads to a shift in prioritisation. A coalition of different groups has begun to form around a single issue. / One constraint identified is the lack of police accountability to municipal structures. The municipal government forms an alliance with community associations to channel concerns about policing to the provincial and national government. They demand a more rational distribution of police across the urban area and shine a light on the informal "privatisation" of police officers who are receiving additional payments for guarding certain businesses in the centre. Police commanders are receiving kick-backs for allocating their officers to do this. The argument about privatisation of the police is backed up by research carried out by a Mozambican NGO. The joint effort by municipal governmend and civil society organisations to expose corruption and gaps in the police forces a discussion at the national level about policing and how it could better serve Mozambican people. / In this example, the facilitation, organisation and networking would be supported by the programmes local facilitator or partner organisation. The issue might then be reinforced through the programmes other two components (described below).
[1] See Annexes 5,6,7,8 & 9; and Appraisal section below
[2] See Annex 9, Political Economy of Democratisation in Mozambique, Macuane, 2010; Mozambique, Balancing Development, Politics and Security, Chatham House, Jeremy Astill-Brown & Markus Weimer 2010;
[3] Outside Mozambique, recent events in Tunisia, Yemen, and Egypt have underlined the importance of entrenching a process of communication and accountability between governments and ever younger, and increasingly well-informed populations
[4] Programa Quinquenal do Goberno para 2010 - 2014 para 16 i.
[5] Annex 8, A review of past and present support to democracy in Mozambique: Macuane, Salimo, Weimer; October 2010
[6] Annex 9, Political Economy of Democratisation in Mozambique, Macuane, 2010
[7] “Uncritical Citizenship in a Low Information Society: Mozambicans in comparative perspective” Robert Mattes & Carlos Shenga, AfroBarometer Working Paper 91. Dec 2007

Why is UK support required?
There is little political pluralism in Mozambique. FRELIMO (Frente de Libertação de Moçambique) is entrenched in power; in the spheres of politics and business. RENAMO (Resistência Nacional Moçambicana) has little credibility as a political force, mainly due to poor leadership. The recent 2009 general elections tightened FRELIMO’s grip on power. The incumbent president, Armando Guebuza, won 75% of the vote. FRELIMO also won 191 out of 250 seats in the parliament. Although voting on the day was peaceful and well organised, election observers commented that electoral processes were flawed. This was a serious concern, which has been consistently noted in prior elections. / Low turnout in these elections, and the findings of Afrobarometer public opinion surveys, suggest dissatisfaction with the current system. Recent riots show that there is risk that frustration can boil over into violence. / Boundaries between party, state and the private sector are blurred. Accountability mechanisms are weak. Parliamentarians lack capacity and resources. Civil society is relatively undeveloped and largely in a service provision role rather than a strong advocate encouraging accountability. / However, there is a liberal constitution and a free media. A new party, the Movimento Democrático de Moçambique (MDM) is gaining support in urban areas and exposure in parliament and the press. There are high profile civil society organisations that are genuinely challenging the status quo. Commentators and academics publicly question the government, but mainly within the view of the urban middle-class. / FRELIMO is not without internal democracy. Moderate voices, like that of Graça Michel, do challenge the more centralising tendencies of the current president. FRELIMO wants to be seen as the party of the ordinary people, and to be democratic and responsive. / Mozambique performs comparatively well in some key areas of governance compared to other countries in sub Saharan Africa. For example, public financial management and government stability. New financial systems have tightened control of government funds. Revenue rose from 10.8% of GDP in 1998 to 17.8% in 2009, and is projected to rise to 18.4% in 2010. However, Mozambique has weaker control over corruption than other countries in the region. In addition, there are major concerns about the weaknesses in the legal and judicial system. / Concerns about the general state of governance have led budget support donors to intensify the political dialogue with government and budget support payments were suspended in 2009/10. There is concern that a lack of accountability, both internally within the government and party and externally, will allow the growing revenue from natural resources to be used for the benefit of the elite rather than for poverty reduction. Oil and gas have recently been discovered, and large deposits of high grade coal are beginning to be exploited. / While the formal institutions of democracy have not demonstrated great enthusiasm for challenging this political status quo, there are other entry points for supporting those who would deepen the democratic process in Mozambique. DFID sees an opportunity to complement the political pressure being applied for greater accountability through the budget support dialogue with practical steps to enhance democratic processes and citizen voice. The DGSP will address the core problem of failed communication, by stimulating and facilitating channels of communication between stakeholders at the municipal level in 5 cities throughout the country, where the main focus of activities will be.

What are the expected results?
As a result of the activities under this programme, women, young people and men will increasingly participate in a meaningful way[8] in the decision-making and political processes at a local level in the target municipalities. They will have a better understanding of the possibilities and limitations of municipal level government, and will have established processes and channels for discussion and communication between citizens and decision-makers. These will act as a decompression chamber for social and economic frustration. Citizens’ priorities will begin to be a part of the municipal agenda. / There will be an improvement in the sustainability of the independent media. An annual report to objectively assess the health of the independent media (reach, regulation, financial flows, investment and advertising) will be operational. Over the life of the project, the revenues of private media will increase in size and diversity by 35%. In the target municipalities, the project will see up to a 20% increase in the use of advocacy by citizens to secure Constitutional rights and freedoms, and an increase to 38% (from an estimated 20%) of citizens reporting that their voice is heard by leaders between elections. These improvements will contribute to strengthened democratic decision-making processes in the project sites. The conduct of elections in the target municipalities will be carried out in accordance with best practice, with the percentage of women candidates for municipal assembly elections rising to 30% of candidates. The improved quality of participation at the municipal level will be amplified through a more vibrant policy debate at the national and local level. This will be informed by successes, challenges and priorities identified through project activities, completing a circle of communication, improved transparency and increased accountability. / The immediate beneficiaries of the project will be the members (women, youth and men) of the communities in target cities who are participating in the awareness-raising and dialogue activities. Beneficiaries at the local level will also include other stakeholders participating in the dialogue process, members of municipal assemblies and local councils, political parties, independent media. Beneficiaries will also include the local implementing partners whose capacity to manage processes of this kind will be enhanced by their participation in the project. Specific beneficiaries may vary depending on the issues identified, such as the local offices of STAE where conflict management training with political party participation may take place, as well as other activities to strengthen political parties in their role pertaining to voter registration and education. / With regard to activities in support of media strengthening, direct beneficiaries will be practitioners in the independent media in all its diverse forms. An increasingly vibrant policy debate will benefit communities and policy-makers over the longer term, and serve to increase positive perceptions of the democratic process in Mozambique. / While there is clear data on some of the measures of progress to be used for the programme, or appropriate proxy data, there will need to be a baseline survey completed in the target municipalities during the planned inception phase. Much of the planned activity is specific to the programme and the target municipalities, or addresses new areas, on which relevant data is sparse, such as the proposed media activities. It will be very important that accurate baseline data is defined from the beginning of the programme in order to be clear on its achievements. It is also the case that there is less quantitative data generally available relevant to democratic participation (aside from voting figures) than there may be for other areas, such as education or health. For this reason the programme proposes a combination of standard indicators, such as election-related data, with more qualitative data, in order to honestly measure the changes which it anticipates.
[8] As defined by Arnstein’s Ladder of participation, see Annex 1 Logframe Purpose Indicator 1