## Project Logical Framework, English in Action

PROJECT NAME	English in Action
GOAL	Indicator	Baseline 2008/9	Milestone 2011	Milestone 2014	Target 2016/17
To contribute to the economic growth of Bangladesh by providing English language as a tool for better access to the world economy.	Income levels in relevant professional groups[1].	Project targeted groups in employment = specific groups in socio economic groups B,C and D	NA[2]	Significant measurable increases in income levels of project targeted groups in employment	Further significant measurable increases in income levels of project targeted groups in employment
		Source
		GOB Ministry of Trade & Industry Statistics / GOB Ministry of Labour and Manpower Statistics / Export Promotion Bureau Statistics, Bangladesh / Project Cohort Studies / Commissioned External Study
	Indicator	Baseline 2010/11	Milestone 2011	Milestone 2014	Target 2016/17
	Access to improved employment and higher education	% of children who complete secondary education cycle and graduate to higher education and/or employment	NA[3]	Significant measurable increases in % of children who complete secondary education cycle and graduate to higher education and/or employment	Further Significant measurable increases in % of children who complete secondary education cycle and graduate to higher education and/or employment
		Source
		National Census: BBS Statistics / Labour market statistics; WB/UNDP Statistics / School leavers destination data and studies / Destination study commissioned in 2010
	Indicator	Baseline 2008/9	Milestone 2011	Milestone 2014	Target 2016/17
	Education indices in Global Competitiveness Report (GCR)	Primary Education Ranked 119 / Higher Education and Training Ranked 129	NA[4]	Improvement in Primary Education and Higher Education and Training Ranking	Further Improvement in Primary Education and Higher Education and Training Ranking
		Source
		Global Competitiveness Report 2009 (GCR) http://gcr.weforum.org/gcr09/
[1] Readymade garments, banks & financial institutions, hotels & restaurants, tourism, ICT-based, high value fishing/frozen foods exporters, agriculture, labour exports, medical services industries
[2] Not considered appropriate to have a milestone at the Goal Level for 2011
[3] Ibid
[4] Ibid

PURPOSE	Indicator	Baseline 2008/09/10			Milestone 2011			Milestone 2014			Target 2016/17	Assumptions
To increase significantly the number of people able to communicate in English to levels that enables them to participate fully in economic and social activities and opportunities.	Proficiency in English speaking and listening communicative English among the population of Bangladesh.	Baseline data teachers and students need to be based on ‘pooled data’ as the original baseline was biased. Will shortly become available / adults: / Self assessed ability scale 1 (no ability) to 10 (expert) / (SEC A to D 15+ Mobile user and/or C&S TV Viewer / SEC E 15 to 45 Mobile user and/or TV viewer) / ≥ 4 Speaking 33% / ≥ 4 Understanding 43 %			Increase in scores in Trinity tests[5] / Primary students: / ≥ level 1: 0.01% / Secondary students: ≥ level 2: 0.01% / Primary teachers: / ≥ level 2: 0.01% / Secondary teachers: ≥ level 3: 0.01% / adults: / Highly engaged BBC media product consumers / ≥ 4 Speaking 38% / ≥ 4 Understanding 48%			Increase in scores in Trinity tests / Primary students: / ≥ level 1:0.23% / Secondary students: ≥ level 2: 0.37% / Primary teachers: / ≥ level 2: 0.20% / Secondary teachers: ≥ level 3: 0.23% / adults: / 71% of highly engaged BBC media product consumers are using English.			Increase in scores in Trinity tests / Primary students: / ≥ level 1: 2.18% / Secondary students: ≥ level 2: 4.1% / Primary teachers: / ≥ level 2: 2.46% / Secondary teachers: ≥ level 3: 0.55% / adults: / tbc	Policies, institutions, and processes governing international trade and other economic activities favour pro-poor participation and economic growth. / Social inclusion cuts across everything EIA does. / Bangladesh Government proactively pursues institutional reforms necessary to attract inward investment / Sustained economic growth over project lifetime. / Sustained pro-poor growth delivers self- and wage employment opportunities for the poor. / Other government and NGO programmes deliver planned benefits for the poor. / Political stability. / Exam reforms that take place during the project period will include assessment of communicative English language.
		Source
		Baseline Study 1: Assessment on English Language Competence (using methodology developed by Trinity) / Studies above the baseline / Project Cohort Studies / Commissioned External Formative and Summative Studies
	Indicator	Baseline 2008/9	Milestone 2011			Milestone 2014			Target 2016/17
	Employer satisfaction (with applicants’ / employees’ communicative English).	50.5% of employers indicated that applicants did not have necessary English skills for posts requiring EL skills. / 68% of employers indicated that employees did have necessary English skills.	47% of employers indicate that applicants do not have necessary English skills for posts requiring EL skills. / 71% of employers indicate that employees do have necessary English skills.			42% of employers indicate that applicants do not have necessary English skills for posts requiring EL skills. / 75% of employers indicate that employees do have necessary English skills			35% of employers indicate that applicants do not have necessary English skills for posts requiring EL skills. / 80% of employers’ indicate that employees do have necessary English skills
		Source
		Baseline Study 2b: Demand for English Language in the workplace and in post school Education / Business Community/Leaders Perception Survey / Studies above the baseline / Labour Market surveys when available
	Indicator	Baseline 2008/9	Milestone 2011			Milestone 2014			Target 2016/17
	Pass rates in English at SSC and HSC.	SSC / 75.82% (M) / 76.63% (F) / HSC / 74.85% (M) / 74.05% (F)	SSC / 78% (M) / 79% (F) / HSC / 76% (M) / 76%(F)			SSC / 81% (M) / 82% (F) / HSC / 78% (M) / 78% (F)			SSC / 85% (M) / 86% (F) / HSC / 80% (M) / 80% (F)
		Source
		National statistics of examination results (annually) / BANABEIS : http://www.banbeis.gov.bd/db_bb/out_sta.htm
	Indicator	Baseline 2008/9		Milestone 2011			Milestone 2014			Target 2016/17
	Motivation for learning and using English among the population of Bangladesh.	51% of students and 64% of teachers believed that English was very much necessary for Bangladesh. / 60% of students and 45% of teachers believed that English was difficult to learn. / Adults:[6]		55% of students and 70% of teachers believed that English was very much necessary for Bangladesh. / 58% of students and 43% of teachers believed that English was difficult to learn.			60% of students and 75% of teachers believed that English was very much necessary for Bangladesh. / 55% of students and 40% of teachers believed that English was difficult to learn.			65% of students and 80% of teachers believed that English was very much necessary for Bangladesh. / 50% of students and 35% of teachers believed that English was difficult to learn.
		Source
		Base line study 2A: Motivations and experiences of school students, teachers and adults in the community. / Studies above the baseline
	Indicator	Baseline 2008/9	Milestone 2011			Milestone 2014			Target 2016/17
	Use of English Language news and media: online; broadcast or print based.	Estimated under 5% of population regular users[7]	10% improvement above the baseline			15% improvement above the baseline			z% improvement above the baseline
		Source
		Press Institute (Bangladesh) / Bangladesh Sangbad Shangstha (BSS)
INPUTS (£)	DFID (£)	Govt (£)	Other (£)			Total (£)			DFID SHARE (%)
	£49.8 M	-	-			£49.8 M			100%
INPUTS (HR)	DFID (FTEs)
[5] Only lower Trinity level improvements are defined, as this is where our main contribution is directed.
[6] Motivators for learning and using English among adults is covered by the 2nd indicator for output 2.
[7] Regular users are defined as those who report doing any of the following often or all the time: read English language newspapers, watch English language programmes on the TV, browse/surf the internet in English

OUTPUT 1	Indicator	Baseline 2008/9	Milestone 2011	Milestone 2014	Target 2016/17	Assumption

(Revised OPR 2009) / English language proficiency of both students and teachers, and the pedagogic practice of teachers enhanced and sustained through the development of Interactive audio instruction package for use in primary schools.	Reach: The numbers of schools, teachers and pupils participating in English in Action primary interventions.	0	200 schools / 400 teachers / (160M; 240F) / 16,000 pupils / (7,800M; 8,200F)	2,500 schools / 7,500 teachers / (3,000M; 4,500F) / 300,000 pupils / (146,250M; 153,750F)	30,000 schools / 67,500 primary teachers having participated in EIA / (27,000M; 40,500F) / and / 6.75 million pupils / (3.29 million M; 3.46 million F)	Access for project to work in primary sub-sector agreed and supported (e.g. 200 schools in phase 2) / Donor support for phase III equipment can be secured. / Reach, Practice and Competence indicators are aligned to EIA’s Social Inclusion Strategy / EIA can be embedded within pre-service and continuous professional development strands of the PEDPIII programmatic framework / No fundamental textbook changes in the foreseeable future / Buy in of stakeholders and capacity available for supported open and distance learning / Some English subject specialism developed
		Source
		Project Management Information System, Dhaka (end of phase).
	Indicator	Baseline 2008/9	Milestone 2011	Milestone 2014	Target 2016/17
	Practice: the numbers of teachers evidencing Communicative Language Teaching (CLT) approaches in their classroom practice.	Limited student talk in a lesson and low percentage of that talk in English.	% Student talk in a lesson: 20% / % of that student talk in English: 50%	% Student talk of EIA new cohort in a lesson: 20% / % of that student talk in English: 60%	% Student talk of EIA new cohort in a lesson: 20% / % of that student talk in English: 70%
		Source
		Project Research Information System, Open University, UK. (annual) / (Representative sampling) (annual)
IMPACT WEIGHTING / Output 1	Indicator	Baseline 2010	Milestone 2011	Milestone 2014	Target 2016/17
25%	EL Competence: / The numbers of teachers and students with demonstrable competence in communicative English Language.	Primary teachers: / Achieving Trinity level 2 or above[8]: / 86.1% and 62.6% achieving Trinity level 3 or above. / Primary students: / Achieving Trinity level 1 or above: 35.7% and 7.7% achieving Trinity level 2 and above	Significant measurable / increases in EL competence. / increase in 10% of teachers reaching the criterion of Trinity level 2 and above; / increase in 5% of students reaching the criteria of Trinity level 1 and above.	Significant measurable increases in EL competence. / Increase in 10% of new cohort EIA teachers reaching the criterion of Trinity level 2; / increase in 10% of new cohort EIA teachers reaching the criterion of Trinity level 3; / increase in 5% of new cohort EIA students reaching the criterion of Trinity level 1 and above; / increase in 5% of new cohort EIA students reaching the criterion of Trinity level 2 and above.	Significant measurable increases in EL competence. / Increase in 10% of new cohort EIA teachers reaching the criterion of Trinity level 2. / Increase in 15% of new cohort EIA teachers reaching the criterion of Trinity level 3; / increase in 10% of new cohort EIA students reaching the criterion of Trinity level 1 and above; / increase in 5% of new cohort EIA students reaching the criterion of Trinity level 2 and above.
		Source**				RISK RATING
		Project Research Information System, Open University, UK. (end of phase) / Baseline study 1, & re-sampling at milestones 1, 2 & Target, adopting Trinity equivalent measures. / (Representative sampling) (end of phase)				LOW
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£7.3 M	-	-	£7.3 M	100%
INPUTS (HR)	DFID (FTEs)
[8] Trinity Level 2 is the assumed criterion to be able to teach Class 3

OUTPUT 2	Indicator	Baseline 2008/9	Milestone 2011	Milestone 2014	Target 2016/17	Assumptions
(Revised OPR 2009) / Change people's perceptions of language learning, reduce barriers to English and support the development of an English language media sector through the innovative use of television, radio, mobile phone and other media platforms.	Number of Bangladeshis accessing BBC produced EIA media products	None – outputs not yet available	6 million Bangladeshis have accessed BBC produced EIA media products by the end of April 2011 / (56% M; 44% F)	8.5 million people will have used EIA media products regularly, at least 5 times. / ( 65% M; 35% F)	Y million Bangladeshis have accessed BBC EIA produced and influenced media products by the end of April 2017 / ( _ M; _ F)	Broadcasters broadcast TV programmes at agreed times and with some consistency / Prothom Alo continues to print BBC Janala lessons 3-4 times a week / Internet and mobile phone penetration proceeds at anticipated rate / English Clubs are taken up around the nation
		Source
		BBC Baseline and Midline Surveys / BBC Monthly TV Audience Monitoring Surveys / BBC Mobile Service Aggregator Uptake Data / BBC Web Metrics Data
	Indicator	Baseline 2008/9	Milestone 2011	Milestone 2014	Target 2016/17
	Perception of reduced barriers and increased positivity towards learning communicative English among school leavers and adults	Current attitudes and perceptions have been comprehensively measured using a range of attitudinal statements on the baseline survey.	3.6 million people exposed to BBC produced EIA media products will report reduced barriers and increased positivity towards learning communicative English by the end of April 2011 (38 % M; 27% F)	45% of people who have used BBC EIA products regularly* will report increased motivation to learn and/or be more confident to use English in their everyday life / (48% M; 33% F) / *use more than 5 times
		Source
		BBC Qualitative Barrier Research / BBC Employer Research / BBC Baseline and Midline Surveys / BBC Bangladeshi Audience Cohort Study
	Indicator	Baseline 2008/9	Milestone 2011	Milestone 2014	Target 2016/17
	Influencing the development of an English language media sector through improvements in the capacity to develop products and programmes	3 English Language Teaching Programmes (Engregi Shikshar Anusthan and Unmukto Biswabiddalay – BTV Dur Path – Desh TV) / No equivalent Youth Magazine TV programmes / No equivalent TV dramas / 4 Mobile phone based dictionary based services (Teletalk Warid Banglalink Shabox) / No Learning English websites produced in Bangladesh	Relationships built with key organisations, as evidenced by prominent programming slots negotiated with media companies for free distribution of all BBC EIA media outputs that will be available by April 2011	Key organisations and 100 sector professionals (Broadcast and ELT) have taken part in ELT media capacity building initiatives	Demonstrable increase in ELT media outputs available to Bangladeshi audiences by April 2017
		Source
		BBC Baseline and Midline Surveys / BBC Media Environment Monitoring
IMPACT WEIGHTING Output 2	Indicator	Baseline 2008/9	Milestone 2011	Milestone 2014	Target 2016/17
25%	Bangladeshi Diaspora engage with BBC produced EIA media outputs	None- outputs not yet available	Members of the British Bangladeshi community will have engaged positively with BBC produced EIA media outputs by the end of April 2011 / ( _ M; _ F)	Indicator removed as per recommendation Annual Review 2011	-
		Source				RISK RATING
		BBC UK Bangladeshi Opinion Former / Qualitative Interviews / BBC UK Bangladeshi Diaspora Survey / BBC UK Bangladeshi Diaspora Interviews				MEDIUM
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£20.2M	-	-	£20.2M	100%
INPUTS (HR)	DFID (FTEs)

OUTPUT 3	Indicator	Baseline 2008/9	Milestone 2011	Milestone 2014	Target: 2016/17	Assumptions
(Revised OPR 2009) / Communicative English language teaching practices promoted through Information and Communications Technology enhanced Teacher Professional Development interventions that are tested and adapted in secondary schools.	Reach: The numbers of schools, teachers and pupils participating in English in Action interventions	0	100schools / 200 teachers (144M; 56F) / and 24,000 pupils / (11,500M; 12,500F)	2,500 schools / 5,000 teachers (3,500 M; 1,500F) / and 600,000 pupils (287,500M; 312,500F)	9.000 of the total English language teaching population having participated in EIA (6,210M; 2,790F) / and / 3.75 million pupils / (1,80 million M; 1.95 million F)	Access for project to work in secondary sub-sector agreed and supported / Donor support for phase III equipment can be secured. / Reach, Practice and Competence indicators are aligned to EIA’s Social Inclusion Strategy / Buy-in of GoB, TTIs & Telcoms sector for distributed Public Private Partnerships PPP model in phase IV. / Buy in of stakeholders and capacity available for supported open and distance learning
		Source
		Project Management Information System, Dhaka. (end of phase)
	Indicator	Baseline 2008/9	Milestone 2011	Milestone 2014	Target: 2016/17
	Practice: the numbers of teachers evidencing Communicative Language Teaching (CLT) approaches in their classroom practice	Limited student talk in a lesson and low percentage of that talk in English.	% Student talk in a lesson: 20% / % Student talk in English: 50%	% Student talk of EIA new cohort in a lesson: 20% / % of that student talk in English: 60%	% Student talk of EIA new cohort in a lesson: 20% / % of that student talk in English: 70%
		Source
		Project Research Information System, Open University, UK. / (Representative sampling) (end of phase)
IMPACT WEIGHTING / Output 3	Indicator	Baseline 2010	Milestone 2011	Milestone 2014	Target: 2016/17
25%	EL Competence: / The numbers of teachers and students with demonstrable competence in communicative English Language.	Secondary teachers: / Achieving Trinity Level 3 or above[9]: / 77.4% and 54.4% achieving Trinity level 4 or above. / Secondary students: Achieving Trinity level 2 or above: 46.2% and 22.1% achieving Trinity level 3 and above.	Significant measurable increases in EL competence: / increase in 10% of teachers reaching the criterion of Trinity level 3 and above; / increase in 5% of students reaching the criterion of Trinity level 2 and above.	Significant measurable increases in EL competence: / Increase in 10% of new cohort EIA teachers reaching the criterion of Trinity level 3 and above; / increase in 5 % of new cohort of EIA teachers reaching a criterion of Trinity level 4 and above; / Increase in 10% of new cohort EIA students reaching the criterion of Trinity level 2 and above; / Increase in 5% of new cohort EIA students reaching the criterion of Trinity level 3 and above.	Significant measurable increases in EL competence: / Increase in 10% of new cohort EIA teachers reaching the criterion of Trinity level 3;and above; / Increase in 5 % of new cohort of EIA teachers reaching a criterion of Trinity level 4 and above / Increase in 15% of new cohort EIA students reaching the criterion of Trinity level 2 and above; / Increase in 10% of new cohort EIA students reaching the criterion of Trinity level 3 and above.
		Source
		Project Research Information System, Open University, UK. (end of phase) / Baseline study 3, & re-sampling at milestones 1, 2 & Target, / (Representative sampling) (end of phase)
						RISK RATING
						LOW
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£6.4M	-	-	£6.4M	100%
INPUTS (HR)	DFID (FTEs)
[9] Trinity grade 3 is the assumed criterion to be able to teach Class 6

OUTPUT 4	Indicator	Baseline 2008/9	Milestone 2011	Milestone 2014		Target: 2016/17	Assumptions
A rigorous monitoring and evaluation framework and research programme built upon Baseline studies to monitor and assess Project impact and generate knowledge products and support capacity building.	Evaluation Activities taking place according to the M&E framework / .	No project interventions in place	All planned research studies carried out to match requirements of logframe.	All planned research studies carried out to match requirements of logframe, to respond to the annual reviews, and to cope with upscaling of project.		All planned research studies carried out to match requirements of logframe and the overall goals of the project, to respond to the annual reviews, and to cope with an institutionalised approach.	Access to all project activities and outputs as required. / Access to appropriate individuals. / That R&E activities e.g. distinctive research methods , data collection, analysis and reporting skills are refined across a range of (public and private) Bangladeshi agencies to support skilled, sustainable, rigorous practice.
		Source
		Baseline studies. / Sector’s evaluation studies. / EIA project documentation including paper based and internally and externally focused EIA electronic (web based) resources / Project Management Information System (PMIS) / Media reports and academic articles / Interviews with stakeholder beneficiaries and project staff
	Indicator	Baseline 2008/9	Milestone 2011	Milestone 2014		Target 2016/17
	Monitoring Activities taking place according to M&E framework and Project Management Information System.	No project interventions in place	Appropriate monitoring of project sector’s activities and achievements.	Ongoing and appropriate monitoring of project sector’s activities and achievements that cope with an upscaled project.		Demonstrably rigorous comprehensive and completed monitoring of project sector’s activities throughout the project lifespan and which is institutionalised in current education system procedures.
		Source
		Baseline studies. / Project Management Information System (e.g. including knowledge products) (Annual)
IMPACT WEIGHTING / Output 4	Indicator	Baseline 2008/9	Milestone 2011		Milestone 2014	Target 2016/17
10%	Disseminating research to key local, district, national and international audiences, via appropriate knowledge products.	Dissemination of baseline study reports to key stakeholders to raise awareness of state of English language education in relation to the project’s outputs.	Fully-developed dissemination strategy. / Dissemination of research findings to initial key audiences (national): / stakeholders / policymakers / practitioners / relevant national-level organisations / To raise the project’s profile and enlist support, in line with institutionalisation. Through this to find champions and advocates for EIA approach.		Dissemination of research findings to further audiences (local & district): / schools (teachers & headteachers) / communities (e.g. community leaders, parents) / To begin cultural change (attitudes & mindsets) and influence educational practice, in line with institutionalisation. Through this to find champions and advocates for EIA approach.	Dissemination of research findings to further audiences (international): / policymakers & practitioners / academic / development agencies & NGOs / To showcase EIA and develop a wider awareness, in line with institutionalisation. Through this to find champions and advocates for EIA approach.
		Source					RISK RATING
		Baseline studies. / Project Management Information System (e.g. including knowledge products). / RME reports. / EIA extranet. / Conference & journal papers. / Seminars and workshop activity. / Interviews with key individuals across Bangladesh.					LOW
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)		DFID SHARE (%)
	£3.3M	-	-	£3.3 M		100%
INPUTS (HR)	DFID (FTEs)

OUTPUT 5	Indicator	Baseline 2008/9	Milestone 2011	Milestone 2014	Target: 2016/17	Assumptions
New output agreed during OPR 2009 / Influence institutionalization and sustainability of EIA approach through critical engagement with crucial stakeholders and advise on revised English Language Education policy for the GOB	Developing sustainable strategic partnerships with key institutions and built necessary capacities in order to sustain EIA interventions beyond the life of the Project.	No EIA partnerships in operation	1 or more key strategic partnerships for joint delivery of EIA interventions	key strategic partnerships established and strengthened capacity of partners in the areas of teacher training, materials development and research. / Increased partners’ responsibilities for implementing EIA interventions.	National systems and structures take on the programme initiatives (training methodology, revised curriculum, research, etc.) as business as usual.	Appropriate involvement and relationships with MoPME & MoE to influence GOB education policies and initiative I / Appropriate commercial or donor models will be found to sustain the project’s media outputs / Appropriate involvement and relationships with NCTB & Education Boards to influence changes in curriculum, text book and assessment / Effective working partnerships with Upazila Education Office stakeholders / Effective working partnerships with key teacher education institutions to implement policy changes at an institutional level
		Source
		Project Management Information System, Dhaka (end of phase) / Teacher Development Partnerships
	Indicator	Baseline 2008/9	Milestone 2011	Milestone 2014	Target: 2016/17
	Media sector engagement with project goal and purpose	None	Key media partners agree to carry and repeat BBCWST produced EIA media content	Key media partners make a strategic commitment to carry educational content, including ELT content	TBC
		Source
		BBC Media Environment Monitoring / EIA Public Private Partnerships
	Indicator	Baseline 2008/9	Milestone 2011	Milestone 2014	Target: 2016/17
	English Language education policy in Bangladesh supporting communicative language teaching practices.	Current EL education policy does not sufficiently promote CLT practices	Strategic dialogue with core policy stakeholder bodies on future policy reforms	Core policy stakeholder bodies, including MOPME and MOE, engaging in development of new architecture for EL education policy in Bangladesh.	Policy reform to support communicative language teaching practices.
		Source
		Baseline studies / Project Management Information System (annually) / Project Management Information System (e.g. including knowledge products) / Revised Policy documents & proposals from Key Stakeholders. (annually)
IMPACT WEIGHTING / Output 5	Indicator	Baseline 2008/9	Milestone 2011	Milestone 2014	Target: 2016/17
15%	Influencing and ultimately change curriculum, textbook and assessment changes supporting Communicative English Language Teaching	Evidence of considerable variability in levels of appropriate training for the teaching of communicative English. / Considerable weaknesses identified in GoB training institutions (e.g. PTIs and TTCs)	Strategic dialogue with key Government institutions	EIA actively engaging with GoB institutions to reform the curriculum, revise the textbook and adjust the assessment mechanism	Curriculum, textbook, and assessment mechanism / supporting communicative English language teaching.
		Source				RISK RATING
		Baseline studies / Project Management Information System (annually) / Project Management Information System (e.g. including knowledge products) / Revised Policy documents & proposals from Key Stakeholders. (annually)				HIGH
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)
	£2.4M	-	-	£2.4M	100%
INPUTS (HR)	DFID (FTEs)