Business Case

Summary Sheet

Title: Humanitarian protection for vulnerable refugees and host communities in Jordan
Programme Summary: / Marginalised and vulnerable refugees and Jordanians have improved access to integrated protection services.
Programme Value: up to £15,000,000		Country/ Region: Jordan
Programme Code: 300537	Start Date: 01/04/2018	End Date: 31/03/2021
Overall programme risk rating:	Minor
Vault Number:	XXXX

Intervention Summary
Narrative summary of why UK support needed, what the funds will be spent on, where, over what period of time, via whom and what they will deliver (1/2 page max)
The Syrian refugee crisis has placed a significant burden on Jordanian services at a time that the country is facing its own challenges. Affected people with stigmatising health and protection needs (including people lacking documentation, people with disabilities or mental health conditions, female-headed households, children) are at a disadvantage.
This £15m programme will build capacity in the operating environment and deliver life-changing activities to address basic protection needs of 62,167 of the most vulnerable Jordanians and refugees (including Syrians), in a way that promotes sustainability and resilience. Specialised organisations will target those with complex legal needs and health vulnerabilities, which affect their ability to achieve a minimum acceptable standard of living. Results will include:
- Legal counselling and case management for up to 24,700 people.
- Health inclusion for 8,000 people in remote communities, 4,640 persons with disabilities (PWD) requiring physical rehabilitation, mental health support for 2,304 patients, and additional psychosocial services for 4,980 patients.
- Child protection case management for 2,400 children.
- Training on best practice for 200 legal experts for specific legal advice, 188 health professionals, 412 community leaders and 10 NGOs.
- Awareness-raising and advocacy through continuous community outreach, 6 social media campaigns, and publication of policy briefs.
Does the programme fit with DFID’s strategic architecture: the UK Aid Strategy, Single Departmental Plan, International Development Act and the department’s Business Plan?
The programme fits with the Single Department Plan’s Strategic Objectives 2 (strengthen resilience and response to crisis), and 4 (tackle extreme poverty and help the world’s most vulnerable). This programme also therefore aligns with Strategic Objectives 2 and 4 of the DFID Jordan Country Business Plan 2016-2020 and NSC objectives.
What percentage of DFID’s Single Departmental Plan results target does this programme represent? Could the programme be adjusted in scope or scale to deliver SDP results?
The programme contributes directly to the following results in the SDP:
- Tackle the causes of instability, insecurity, and conflict.
- Support for ongoing crises, including that in Syria and other countries in the Middle East and North Africa region.
- Support the world’s poorest people to ensure that every person has access to basic needs.
- Prioritise the rights of girls and women.
- Deliver value for money.
The programme can be expanded in scale to serve more affected people should the needs still be there and funding is available.
Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy?
The programme activities are represented within the Jordan Response Plan and proposed partners are active within the relevant humanitarian coordination mechanisms. The programme is designed to hand over services from international to national actors as per our Grand Bargain commitments and to effect sustainable change through working with government ministries to develop legislation and build capacity. Partners are required to set out their exit strategy from the outset.
Has the programme considered working with HMG Departments and accessing cross-HMG funds?
There are no other HMG funds which can be accessed for this programme. However, regular dialogue within DFID and with other HMG departments based in Jordan ensures that this programme complements wider UK programming, in particular when integrating cross-cutting themes such as conflict sensitivity, gender, disability and youth.
How does the programme relate to other UK aid within the specific sector, including multilateral, bilateral and centrally managed programmes?
Within DFID Jordan, this programme is uniquely positioned to complement activities under the other thematic pillars (Economic Opportunities, Education) of the Business Plan and achieve stability for Jordan. It will also contribute to the UK-Jordan Partnership where services to the most vulnerable ensures no one is left behind; and reduces the possible negative impacts of the marginalisation of refugees and vulnerable Jordanians. For example, resolving documentation gaps, including work permits, will allow refugees to play a more active role in the formal work sector. Case management for child protection and health-related interventions will improve prospects for children in the education sector. The programme also supports CSSF objectives to reduce conflict in the community and home through protection and health activities.
The programme will be complemented by DFID centrally managed funding to Humanity & Inclusion (HI) to train national and international organisations in Jordan on use of Washington Group Questions for disability inclusion, building towards DFID’s commitment to having disability disaggregated data for all programmes by 2022.
Research and evidence between the country office and DFID centrally managed programmes (e.g. HIEP) will be coordinated through the newly-established MENAD Research Hub, to ensure that there are no overlaps in evidence building.
Is there sufficient flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments?
Disbursement of funds to the partner(s) will be phased and DFID will regularly review progress through project reporting cycles and annual reviews to ensure programme alignment with emerging priorities and changes in the operating context in Jordan.
The monitoring and evaluation strategy, including mid-term evaluations, will rigorously assess the performance of the programme and provide opportunity to adapt.
Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio?
The overall programme risk, assigned as “minor”, aligns with DFID Jordan’s risk appetite, currently set at “moderate”.
Is there a clear communications strategy to reinforce our objectives? Will the programme be branded with the UK aid logo and recognise UK Government funding – and, if not, why not?
We will work with the communications teams in DFID and at the British Embassy in Amman to develop a strategy, highlighting the programme’s response to UK priorities, e.g. ensuring Jordan’s stability, disability, and continued humanitarian support. Communications channels include local, international, and social media. All partners will be required to return a signed Visibility Statement during contracting and use UK Aid branding throughout the programme.
Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme?
This programme has not been reviewed by the Quality Assurance Unit (QAU) as the value falls below the threshold. However, it was developed in close consultation with DFID Jordan’s cross-cutting advisors. The political will to continue humanitarian support for refugees through a sustainability lens exists within the Government of Jordan, who lead on the Jordan Response Plan process. The programme is aligned with JRP priorities. The JRP has broad international support from within the region and from other donors. However, we note with concern the recent cut to refugee health subsidies imposed by the Ministry of Health[1].
[1] In a letter to the Minister of Health, the Prime Minister in Jordan cancelled a previous cabinet resolution whereby Syrians were asked to pay a subsidised rate at public health facilities, and now required to pay 80% of the rate charged to foreigners which is considerably higher.
The recommended option for this programme would be delivery by partners currently contracted with DFID Jordan (until March 2018). These were selected through a competitive “call for proposals process” that was open to all agencies working in protection and wished to apply. Each has received “A” or above in latest Annual Reviews.
Does the SRO and team have the capability and resources to deliver this programme?
The SRO will be the Deputy Head of Office of DFID Jordan supported by the Amman-based humanitarian team comprised of one Deputy Programme Manager and two Humanitarian Advisers.

Strategic Case
Context
The Syria crisis is entering its eighth year and shows no signs of abating. UNHCR has registered 655,000 Syrian refugees in Jordan, accounting for nearly 7% of the total population of the country. Around 20% of registered refugees, half of whom are children, live in official refugee camps at Zaatari and Azraq, with the rest in host communities.[2] Support to the Palestinian refugee caseload of 2.2m people falls under the mandate of UNRWA. In addition to Syrians and Palestinians, there are 65,500 Iraqis, 9,000 Yemenis, and 4,000 Sudanese refugees residing in Jordan.[3] An estimated 50,000 people are trapped in an informal camp at Jordan’s north-eastern border with Syria, in the area between the two countries known as “the berm”.
[2] UNHCR, 31st December 2017, “Registered Syrians in Jordan”
[3] UNHCR, 2017, “Jordan Operational Update: October 2017”
The conflict in Syria evolved through 2017, including the establishment of de-escalation areas (DEAs) in four areas, backed by Russia, Turkey and Iran. A significant proportion of refugees in Jordan originate from the DEAs. However, UNHCR maintains that conditions are still not suitable to facilitate safe and dignified returns. Cross-border access for aid distribution into Syria is assured until January 2019 under UN Security Council Resolution 2393, as some areas are still too dangerous for aid to reach across conflict lines.[4]
[4] Renewal of UNSCR 2165 (2014)
The wellbeing of Syrian refugees has deteriorated since the start of the Syria crisis. Over 70% of Syrian refugee households are at risk of food insecurity, and over 80% of families report being in debt; often borrowing money from family and landlords to avoid evictions. There is little aid reaching other refugee groups.
With subsidy and taxation reforms in Jordan contributing to worsening financial hardship for Jordanians, refugee hosting is placing a significant burden on Jordan’s resources and services, exacerbating pressures on the country. Local integration is not an option. Remaining options are resettlement to a third country, alternative access to a third country (e.g. family reunification) and temporary access to economic opportunities and public services. Resettlement to third countries is limited in scope (18,000 people in 2016) and is not anticipated to increase in the coming years. With no durable solutions, the situation for Syrian refugees in Jordan has transitioned from being an acute emergency to a protracted crisis, bringing with it a shift in the way assistance is delivered, bridging the humanitarian-development nexus.
Jordan is making efforts to protect the most vulnerable. Despite some improvements to the protection environment for refugees, refugees still face some significant risks including unpredictability in subsidy provision..
Most refugees in Jordan can be considered vulnerable by virtue of their low economic status, difficult access to public services and their exposure to protection threats such as lack of formal residency status, lack of documentation, limited legal assistance, domestic violence, and early marriage. Current systems are not responsive enough to those who need them, with few opportunities for advanced training for professionals or health infrastructure investment. Sustainability cannot be achieved through service delivery alone and the resilience of systems assisting extremely vulnerable people is negatively impacted by capacity and funding gaps.
Why UK financing is required
The crisis in Syria has contributed to worsening economic indicators including a fall in GDP and an increase in unemployment. Public services are overstretched in all sectors and the crisis is impacting the daily lives of Jordanians as systems struggle to absorb the increased demand. It is unlikely that conditions will improve within Syria enough to facilitate safe return. The UK was the 3rd and 4th largest donor to the Jordan Response Plan (JRP) in 2016 and 2017 respectively; coming after the US, Germany, and the EU who give considerable contributions. The 2018 contribution, including this humanitarian programme, will reaffirm DFID’s leading role in supporting the JRP.
How the programme contributes to strategic priorities
Jordan Compact: The UK has been committed to supporting the Government of Jordan in implementing the 2016 Jordan Compact, which aims to provide Jordan with support for hosting refugees by alleviating pressure on services and creating economic opportunities. Humanitarian programming will strengthen the enabling environment for persons with extreme vulnerabilities, thereby improving their ability to access services and jobs.
Jordan Response Plan (JRP): The humanitarian response for Jordan is led by the GOJ and aligns with priorities under the Compact. The JRP forms a component of the Regional Refugee and Resilience Plan for Syria (3RP), a rolling 2-year plan for five refugee hosting countries. The JRP for 2017 attained 65% ($1.7bn) of requested commitments, of which $654m was for refugee support. The 2018 JRP ask is $2.5bn, of which$1.6bn is for programmatic response including both the refugee and resilience pillars.[5]
[5] Jordan Response Plan for the Syria Crisis 2018-2020
DFID Jordan Country Strategy 2016-2020: All programming contributes to delivering Jordan NSC strategy objectives, coordinating closely with other UK Government Departments and other funding mechanisms, such as the CSSF. This programme contributes to Strategic Objective 2 under the Country Strategy; strengthening resilience and response to crises while strengthening IHL under the political pillar of the NSC Strategy. It will complement and act as a ‘multiplier’ of the outcomes of the education and economic opportunity pillars to increase overall effectiveness of DFID’s engagement. The programme is also a contribution to the UK-Jordan Partnership where it supports getting Jordan onto a more sustainable path and minimising the negative impacts of the refugee presence.
Single Department Plan (SDP): This action will contribute to the following results under the SDP, contributing to the principle of “Leave No One Behind”, which correspond to the UK Aid Strategy; (2) Strengthen resilience and response to crisis (2.1 support for ongoing crises, including Syria), (4) Tackle extreme poverty and help the world’s most vulnerable, (5) Deliver value for money and efficiency.
The Humanitarian Reform Policy (November 2017) reiterates the UK’s commitment to the Grand Bargain and to protecting the most vulnerable through upholding international humanitarian law (IHL) and humanitarian principles. The programme will contribute to UK’s commitment to strengthening the data disaggregation on the basis of gender, disability and age.
Programme rationale
This programme will enhance the protection of refugee and Jordanian families most affected by poverty and vulnerability. These include persons with disabilities or mental health conditions, children requiring health and protection support, female-headed households, survivors of sexual and gender-based violence (SGBV), and others without resources to exercise their legal rights. The programme will also seek to build the capacity of national systems and local service providers to pave the way for more sustainable services.
Documentation and legal issues are barriers to obtaining basic services (including safe shelter) and place refugees at risk of deportation or forced relocation. Refugees are registered by UNHCR, receiving an Asylum Seeker’s Certificate (ASC) and Ministry of Interior (MOI) card. In 2015, GoJ initiated an exercise to provide new MOI cards to Syrians outside camps. However, 110,000 still need assistance. Unregistered Syrian refugees cannot access most basic services and are at risk of arrest, detention, or involuntaryrelocation to refugee camps. Meanwhile, 41% of Syrian children in Jordan do not have birth certificates.
There is increasing need for awareness-raising of Syrian refugee employees on work rights and work permits, which are limited to a few sectors. Those without permits risk exploitation, abuse, low wages, and conflicts with local communities. Itinerant Syrian refugee communities are found throughout Jordan in informal tented settlements (ITS), concentrated in agricultural areas. Protection concerns are particularly acute, with high rates of early marriage, child labour, SGBV, and documentation gaps. Access to specialised health care is a struggle due to costs of treatment and transportation, which will now be compounded following a directive in February 2018 to increase the costs that Syrian refugees have to pay when accessing public health services.
Around 20% of vulnerable Jordanian families have had at least one member exposed to legal issues in the past five years, most were unrepresented in court.[6]
[6] JCLA in conjunction with the Department of Statistics
Women and girls are disproportionately affected by health and protection inequalities, within an environment experiencing shifts in gender roles. Jordan is ranked 134/144 countries by the 2016 Gender Gap Report. The roles of men and women have seen a gradual shift. Unaccompanied men and boys can suffer from significant psychological distress and adult men feel dispossessed of control over their life and their future. Women have scarce control over assets. Syrian refugee women face major challenges in everyday life due to their restricted social mobility and early marriage is common. A third of women and girls (refugees and Jordanians) experience physical violence, mostly in the home.
Child protection systems continue to be weak in Jordan. Close to 90% of children experience psychological or physical discipline at home. Refugee children face bullying and violence. Up to 60% of Syrian households in host communities rely on child labour.[7]
[7] HRW, 2016, “Barriers to Education for Syrian Refugee Children in Jordan”
The health system is struggling to cope with the influx of refugees, especially evident in some specialised services (disability care, mental health) which were under-developed prior to the crisis. The Vulnerability Assessment Framework (VAF) found that 16% of households have members with pre-existing medical conditions and the JRP prioritises non-communicable disease, mental health, persons with disabilities.[8] Children account for 59% of severely vulnerable cases. In 2014, UNHCR ceased paying for healthcare for Syrian refugees and user fees were introduced at a subsidised rate. As of February 2018, all refugee patients will pay the same rate as uninsured foreigners- unaffordable for most. Financial barriers are cited as the main reason for not seeking medical assistance, followed by problems with refugee registration and lack of suitable services.
[8] JRP 2018-2020
Mental health services in Jordan are unable to cope with demand, which has further increased since the start of the crisis in Syria.[9] There are very few registered psychologists and psychiatrists, and only one child psychiatrist in Jordan. Children have little autonomy over their situation and are directly affected by the impact of parental mental health disorders.[10] Stigma against mental health disorders is prevalent.
[9] Jordan Mental Health and Psychosocial Support (MHPSS) sub-working group, December 2016
[10] GOWA, 2015, “Information sheet 13: Parental Mental Illness can be a Child Protection issue”
There are no official government data to show how many persons with disabilities are living in the host communities but the World Health Organisation (WHO) estimates that 15% of the global population are affected by a disability.[11] People with complex needs are referred to tertiary rehabilitation centres, of which there are very few in Jordan. This can lead to poor access to appropriate care for people living outside the catchment of these centres, risking lifelong impairments. Persons with disabilities can face prejudice in their communities. Impairments in children are often detected late, leading to delayed treatment.
[11] WHO & World Bank, 2011, “World Report on Disability”
Resource and knowledge gaps are evident within national organisations and government ministries, and the regulatory environment is not sufficiently developed to assure safety and security for refugees and vulnerable Jordanians. Ministries have limited capacity to respond to child protection violations although work is continuing to mainstream child protection. Community-level interventions for people with disabilities are limited, despite a National Disability Strategy. Ministries recognise where gaps exist and are supportive of efforts to build capacity within their systems. Most national NGOs and community based organisations (CBOs) lack the technical and management competencies required by international donors, and are therefore dependent on limited contracts. There exists a strong opportunity to prepare them to take over specialised services.
Due to significant access constraints at Rukban (“the berm”), this community will not be targeted by the programme. An existing DFID programme with UNICEF includes a tranche of funding for WASH and health services at the Berm.
Programme outline and results
The programme will reach up to 62,167 direct beneficiaries in all 12 governorates of Jordan. The programme aims to ensure a positive impact on the wellbeing of refugees and vulnerable Jordanians through direct assistance and by building the resilience of national systems. The following outcome will be achieved:
Needs of the most vulnerable met by greater access to expanded and strengthened protection, rehabilitation and legal services
High level results of this three year programme will include:
Indicator	Target (03/2021)
IMPACT
% beneficiaries who report confidence in the protection of their basic rights	50%
% beneficiaries reporting an overall improvement in their wellbeing	80%
% beneficiaries reporting an overall improvement in their social participation	80%
OUTCOME
% beneficiaries who report exercising their legal rights	80%
% beneficiaries surveyed who rate the service provided positively	85%
% beneficiaries showing improvement in functional independence	80%
% training participants demonstrating an improved knowledge in topics covered	70%
# instances where partner recommendations are reflected in targeted policies, decisions and/or other arenas by the GOJ	11

The impacts and outcomes will be achieved through the following outputs:
Training and capacity building of key stakeholders including NGO staff, GOJ staff and community leaders.
We will sustainably strengthen the systems which deliver assistance, through capacity-building and technical support to downstream partner organisations and GOJ ministries. Direct service provision, where being carried out by implementing partners, can gradually be handed over. Activities will include training for 200 legal experts on access to justice, training to 188 health service providers in best practice relating to disability and mental health, and 412 community leaders.
Awareness is raised amongst beneficiaries and other community members on protection issues, research is produced to influence advocacy and policy change.
NGO partners will raise the profile of key vulnerabilities within inter-agency standards and policies through sector-level coordination, with 8 policy briefs produced on refugee rights. Social media campaigns will raise awareness within communities.
Vulnerable persons receive direct assistance, and have increased access to services
Mobile units will reach 8,000 people in remote communities to identify child protection and MHPSS concerns. Up to 1,350 children (0-8) will benefit from early detection and early intervention of disabilities. Case management will be provided for 2,400 children and their families. Cash for protection will assist for 300 families. Rehabilitation services will be provided free of charge for 4,640 persons with disabilities, mental health case management for 2,304 patients, and psychosocial services for 4,980 patients. Up to 24,700 refugees and vulnerable Jordanians will be counselled on legal issues, and 20% referred for legal assistance.
The majority of beneficiaries reached will be in the governorates hosting nearly 90% of refugees, including Mafraq, Zarqa, Irbid and Amman (Annex A). Existing referrals networks between NGOs will be strengthened, thereby multiplying the benefit to those who receive multiple services.
Beneficiaries will be selected from extremely vulnerable groups who currently have few resources or services available to them. Partners will apply criteria from the Vulnerability Assessment Framework (VAF), adapting or expanding for appropriateness for the targeted beneficiary groups and applied through community-based engagement by community volunteers and downstream partners. They will include persons with disabilities or mental health conditions, children (including those at risk of early marriage), and women. People at risk of detention or deportation and those who have not been registered with UNHCR will also be reached. Refugee beneficiaries will not be limited by nationality or origin.
International Development Act (Gender Equality) 2014
The programme will contribute to reducing inequalities for women, girls, boys and men in both refugee and affected host communities in Jordan. Addressing needs of women and girls will be at the heart of this programme. Programming will address SGBV prevention, access to services and referrals, counselling and psychosocial support. Partners will be required to clearly and consistently monitor the impact of this programming on women and girls, ensuring that the programme does not have a negative impact. Learning will be recorded and disseminated across DFID. We will work with partners in developing appropriate gender and disability inclusion indicators.
We will do more to strengthen our approach to ‘do no harm’, which will contribute to the advancement of equality in Jordan, through direct support to address the immediate needs of people affected to initiatives to supportive national policies that enhance the emergence over time of a more enabling environment for addressing protection needs. All partners will demonstrate advanced safe-guarding procedures aligned to DFID policies.
Disability inclusion
DFID is committed to collecting results data that is fully disaggregated by disability, using the Washington Group Questions, by 2022. Monitoring and evaluation frameworks for this programme will be supported to work towards disaggregated by disability in advance of the deadline. The programme will retain the flexibility to align with DFID’s updated Disability Framework, which will be announced at the UK-hosted high level Global Disability Summit in July 2018. Direct assistance for people with disabilities and mental health conditions will be complemented by building the capacity of local organisations, health professionals and Jordanian ministries. Technical assistance will be provided for national and international organisations to build their capacity in disability inclusive programming.
Terrorism and financing
All partners in Jordan are made aware of their responsibilities to be compliant with UK government counter-terrorism financing policies. The due diligence assessments check whether partner organisations have policies and procedures in place for monitoring risk and reporting suspected cases. Partner organisations are obliged to ensure that their staff receive appropriate advice and training.
The risk of terrorism financing in this programme is low. All aid is being disbursed within Jordan, where strict counter-terror laws are strongly enforced. Direct monitoring of project activities is possible as the field security risk is low. Due Diligence Assessments will be conducted for all partners prior to contracting.
Public Sector Equality Duty
The programme will be compliant with the Public Sector Equality Duty Act, with attention on: (i) disability, as the protracted nature of the situation means that impact on the lives of people with disabilities is exacerbated as a direct and indirect consequence of the conflict; and (ii) women and girls, as the gendered impacts of the conflict remain in complex.

Appraisal Case
What are the feasible options that address the need set out in the Strategic Case?
The Strategic Case demonstrated the need to address the protection gaps faced by people with documentation needs, legal issues, and stigmatising health conditions. As part of the preparation for the Business Case, a competitive proposal review process was initiated to review what services different implementing partners could offer. Through this process, a preferred implementation methodology was identified and partners pre-selected.
The options are presented below:
- Option 1: Implement a protection programme with one agency
- Option 2: Contribution to the UN
- Option 3: Implement protection programmes with multiple NGOs (recommended)
- Counter-factual “do nothing” approach.

For the purposes of assessing the options, the following criteria were considered:
- What is the option’s geographical reach?
- What is the option’s ability to deliver to hard-to-reach beneficiaries?
- Does the option have the expertise in-house to deliver specialised services?
- What is the option’s experience in Jordan in delivering such services?
- Will the option have the capacity to work with local organisations and hand over?
- Is the option able to align with DFID’s strategic priorities?
Option 1: Implement a protection programme with one NGO
Providing funding to a single NGO partner would offer DFID the opportunity to reach refugees and vulnerable Jordanians in most or all governorates in Jordan with specialised services and case management in legal assistance, health vulnerabilities, or other relevant protection activities. Collaboration with local partners would build sustainability of activities.
A programme with one NGO would allow that organisation to expand their reach, or uplift existing services. There would be efficiencies gained in management costs and human resources. Less resourcing would be required in DFID for monitoring and managing the programme than with multiple partners.
No single NGO was able to demonstrate that they would meet the vulnerabilities prioritised in the Strategic Case during the market scoping phase. Whilst the potential to refer people with additional needs to other organisations exists, if these organisations are not funded to a sufficient level, they will not be able to address the needs of referred beneficiaries.
Option 2: Contribution to the UN
There are multiple UN agencies responding to the impacts of the Syria crisis on Jordan through a range of programming in all sectors. However, none of the priorities identified in the Strategic Case are provided at scale by any of the UN agencies, with the exception of child protection. Where they do have such activities, they are often sub-contracted to the same organisations presented in Option 3. Protection issues relating to documentation are led by UNHCR (including registration, ASC, returns) with some legal assistance provided through partners. ILO engages at a high level on work permits. The health sector, under which most disability and mental health programmes are categorized, is led by WHO. Other key UN agencies in the health sector are UNHCR, UNFPA, and Unicef. None of these agencies provide dedicated mental health or disability programmes directly. Given that the leading organisations in the priority areas are international and national NGOs, the UN would not be able to meet the identified needs without sub-contracting.
The UN will play a critical role in this programme regardless of whether direct funding is supplied by DFID or not. The mechanisms by which NGOs and the UN will continue to successfully cooperate will be two-way referrals, coordination and advocacy. For example, resolution of some documentation issues will not be possible without the assistance of UNHCR; coordination with Ministry of Health may be facilitated with assistance from WHO. Whilst the contract would be multi-year, visibility on programming is not clear beyond the current appeals and earmarking for priority activities would be challenging.
DFID Jordan already supports the UN through two Unicef programmes: (1) a humanitarian contribution of £16m gives national coverage (including camps and the berm) until 12/2019, and (2) an education contribution of £13.3m as part of the Jordan Compact Education Programme (JCEP). DFID is funding technical assistance to the UN in 2017-18 through a secondment to the office of the Resident Coordinator.
Option 3: Implement protection programmes with multiple NGOs (recommended option)
A multi-year programme implemented by several NGOs will address the needs of some of the most vulnerable people in Jordan and increase the capacity of local and national actors to provide specialised services and build sustainable systems.
Three NGOs have been pre-selected through the competitive Request for Proposals, identified as having comparative advantage through specialist expertise; International Medical Corps (IMC), Norwegian Refugee Council (NRC) and Humanity and Inclusion (HI)[12]. They can collectively address the priorities identified in the Strategic Case.
[12] Previously “Handicap International”. The global brand changed on 24th January 2018.
All governorates would be covered by legal and documentation assistance. Other governorates with highest proportions of refugee populations would be included for disability and mental health programming. Geographical overlap between partners is an asset as their projects are significantly different enough that one organisation is not able to provide all of the proposed services. Where referrals between partners take place, some beneficiaries may receive complementary services from more than one organisation, depending on vulnerability and need.
Option 3 would require greater time invested by the DFID Jordan humanitarian team for monitoring and management, but would not impact on human resource planning as each role in the team is essential regardless of the option chosen. Reviews will be carried out against the whole business case rather than the partners (components). Monitoring systems are already in place to track progress and the partners would continue to follow the same protocols. This option represents a decrease in the number of implementing partners from the current programme.
This multi-year option meets DFID’s goals under the Jordan Country Plan, UK Aid Strategy, commitments to the Grand Bargain and would be directly attributable to the JRP.
Counter-factual “do nothing” approach
Through this option, DFID would not provide humanitarian funding for protection programmes in Jordan. The funds could be re-allocated elsewhere in DFID Jordan’s portfolio or re-programmed to meet other humanitarian objectives. The principle of “leave no-one behind” would be compromised for some of the most marginalised people.
Several priorities under the JRP “refugee pillar” would be highly likely to face a shortfall, if the trend in funding gaps presented in the Strategic Case for previous years continues. Resilience against further hardships for affected refugees and vulnerable Jordanians will be impacted as they will continue as legal issues remain unresolved, or they are unable to access treatment for disabilities or mental health conditions. The opportunity for national actors to trained in and implement the proposed services will be interrupted, which will have an impact on sustainability.
Disability and mental health are priorities for DFID and the legal documentation issue is at the heart of protection issues in Jordan. DFID can have a strong influential voice in these areas, advocating for policy reform and adding value beyond our financial investment.
Conclusion of Appraisal case
The preferred option is Option 3. As each of the NGOs proposed in the three-partner approach has expertise with different vulnerabilities and protection threats, eliminating two of these partners would lead to a reduction in support for extremely vulnerable people.
This extends beyond the provision of direct aid, as each partner will also carry out capacity building and advocacy to downstream partners and the Government of Jordan, which will have a sustainable impact beyond the end of the programme. The complementary approach of multiple partners includes inter-agency knowledge sharing, training, and beneficiary referrals.
The projects proposed by all three organisations are priorities within the JRP and some activities would be dependent on DFID funding as other donors have not yet been identified (for example, most of the IMC programme and HI’s early detection / early intervention component). An integrated package of services meeting multiple vulnerabilities will achieve outcomes across a range of protection concerns which are DFID priorities. Through existing programmes and continuous coordination with sector working groups and other coordination mechanisms, DFID Jordan has experience with the supplier market and costs of NGO delivery of the proposed activities. Through this we are able to drive efficiency through costs, e.g. through the NGO administration charge.
In comparison, Option 1 would be implemented by one NGO, thereby scaling up the response to a specific set of vulnerabilities, with a greater geographical reach by governorate. Whilst this would in theory reach a greater number of beneficiaries, the ability to refer beneficiaries with other vulnerabilities to other organisations will be reduced. It is therefore a less holistic approach, as the option would work in a ‘silo’.
Theory of Change (ToC) for preferred option

The theory of change which underpins this project is that by improving the protection status of vulnerable and marginalised people, suffering will be reduced, social participation will increase and their resilience to further shocks will be improved. Indirect outcomes will be achieved, such as greater uptake of work permits and more inclusive participation in education.
Strength of the Evidence Base
Jordan has become a hub for humanitarian organisations with an interest in research and evidence building. Strong evidence (e.g. assessments and reports) exists on documentation needs and the impacts that legal and documentation issues can have. There is a growing body of evidence, through health actors, primarily IMC, on mental health and psychosocial impacts of the crisis on refugees and Jordanians, but this is countered by gaps in evidence at the government level.
Analyses drawn from secondary data collection, strengthened through primary data gathering (including direct beneficiary engagement), have been utilised by all three of the pre-selected NGOs through current programmes funded by DFID and other donors. Previous DFID funding in Jordan has been utilised to produce thematic reports, e.g. NRC’s study on social media and communications (NRC) which was disseminated widely.
Evidence gaps are still apparent on the scale and distribution of disabilities and mental health conditions at the national level, numbers of undocumented and unregistered refugees (including PRS), and locations of ITSs. For example, nationwide data on the extent of disabilities in Jordan does not exist and currently is inferred from local data collection and the VAF. The number and location of ITSs is being mapped through a collaboration between NGOs but progress has been slow.
Where evidence is lacking, partners will undertake baseline assessments prior to starting activities, especially needed for remote and ITS communities. DFID Jordan will encourage partners to strengthen evidence, particularly in new or under-reported areas such as situation for ITSs, disabilities, refugee returns, and cash for protection.
Gender considerations
Each of the recommended partners has proven experience in addressing issues of gender sensitivity and vulnerability in Jordan in their respective specialisms. Each partner will refer to internal controls throughout their project cycles and international standards will be applied, such as the Inter-Agency Standing Committee (IASC) Gender Handbook in Humanitarian Settings. The particular needs of women, girls, men and boys, have been identified at the project design stage. Implementation strategies have been devised, ensuring that specific gender vulnerabilities are captured and reflected in beneficiary assessments and selection, so that the specific needs of female-headed or female-only households are addressed. Human resources policies are in place to encourage equal participation and opportunities for women and men.
Outreach teams, including mobile units and community based volunteers, will be composed of men and women, to ensure that the different voices will be heard, taking into account access constraints at each location. The downstream partners of preferred NGOs presented in this appraisal case have been selected carefully and their capacity to respond to gender-related issues will be built where necessary. For example, NRC’s partner JCLA has specialisms in gender justice, gender rights, women’s personal status law, and legal representation to survivors of GBV. Over 70% of JCLA’s beneficiaries are female.
Outreach will ensure that vulnerable groups, including women and girls, can be assessed and receive services without travelling if they cannot afford transport or have curfews.
Conflict sensitivity
The DFID Jordan team has developed a set of minimum standards for conflict sensitivity, which also covers sensitivity to violent extremism. These standards have been incorporated into the proposed approach. The programme will draw upon guidelines for youth engagement which have been developed for all HMG departments based in Jordan.
The overarching aim of DFID Jordan’s conflict sensitive approach is to minimise harm and strengthen solidarity, cohesion and conflict management within and between communities. The approach is based upon three building blocks: regular conflict and risk analysis, rapid and accessible feedback and accountability systems; and flexible programming tools. These apply equally to DFID as to partner organisations. During the proposal phase of programme development, bidding organisations were required to outline their approaches to conflict sensitivity and the new projects will be assessed against DFID Jordan’s “Conflict Sensitivity Matrix” within the first quarter to define a baseline for improvement. Key strengths are as follows:
Analysis and Design: At the household level, the root causes of tensions include conflict-related trauma, challenges to traditional roles and masculinity, marginalisation, and economic stress. Hard-to-reach households will receive health and protection services without risking negative attention from authorities. The economic burden of caring for individuals with mental health conditions and disabilities will be reduced. Beneficiaries will be equipped with better coping strategies for household stressors and violence, improving family well-being.
Tensions can exist between different groups within the Syrian refugee community, between refugee groups of different nationalities, and with host communities. At the community level, programme activities will promote awareness through campaigns on key issues and build support networks for vulnerable individuals and families.
With Jordan continuing to face economic and political fragility at the national level tolerance for continued refugee presence is waning as narratives about the refugee “burden” as the cause of Jordanian difficulties are becoming more prevalent. Programmes under the “refugee pillar” of the JRP are required to include Jordanians as 30% of their caseload, which this programme will adhere to.
Accountability: The implementation partners, each of which has been present in Jordan for several years, predominantly employ national staff and implement with national organisations. Staff will be trained in conflict sensitive techniques and, where appropriate, mediation strategies. Staff will be visible and approachable, able to respond to community questions and concerns. Partner organisations have in place their own accountability systems, and DFID will conduct due diligence on proposed partners factoring in their accountability to affected populations.
Many of the downstream activities will be carried out by national NGOs. The partners will be responsible for raising local NGO capacity to a level that allows for handover, including on conflict sensitive and accountable approaches to aid. Sustainability will be demonstrated through supporting community groups, civil society and governmental organizations to improve their service delivery to all affected people in the community. This will be done through specialist training, partnerships, and engagement on legislative and regulatory issues.
Flexibility: Conflict sensitivity planning is a requirement at from the outset and the DFID Jordan team, including the Conflict Adviser, will work with partners to develop their strategies, and stress the importance of adaptive programming in response to changing context and needs. Areas for improvement will be identified during conflict sensitivity audits, due diligence assessments and organisational learning during the programme cycle and improvements expected from their baselines. Progress will be followed throughout the programme during scheduled monitoring meetings, field visits and annual reviews. The programme will retain the flexibility to adapt and respond to beneficiary feedback and internal monitoring.
Resilience
The Jordan Response Plan (JRP) is shifting further towards a resilience approach. Whilst this programme is designed to address needs presented under the refugee pillar, all three projects within the preferred option are designed to be flexible and responsive to changes in context within Jordan. Providing multi-year funding will allow implementing partners to train and mentor their Jordanian delivery partners (including GOJ facilities) within a timeframe which allows feedback and learning to become integrated into practice. Mid-term evaluations will provide an opportunity to re-configure project activities.
Climate change and environment
The programme is not expected to have a negative impact on climate change and the environment. Programme activities are involve face to face contact with beneficiaries. Partners will use vehicles for staff transport and outreach but impact will be negligible as all rented vehicles are new and well-maintained and staff will share vehicles. Disposal of medical waste will be minimal and in accordance with Jordanian law.
Value for Money (VfM)
The below section assesses value for money across the three identified potential partners based on information provided by them (out of 9 who submitted full proposals), and the Jordan office’s VfM implementation plan. Details of each NGO will be addressed, as well as common parameters across the three.
Economy
Throughout the duration of implementation, partners will monitor key cost drivers described below as a measure for economy and will report progress to DFID through quarterly monitoring. As part of the proposal review process, the DFID team identified key cost drivers for each NGO, and it was found that across the three proposed agencies, staffing was identified at the top. This is due to the high technical expertise needed to deliver these specialised protection programmes, where these agencies need to hire and maintain technically capable staff to deliver the desired quality and services. Each organisation has technical expertise in house at the country and international levels but will require locally-hired staff for programme implementation. All three agencies apply reasonable salary scales and regularly review those to compare with the local market. Moreover, the agencies seek to nationalise some management positions where possible to reduce staffing costs, which will take place gradually over the three years.
Key Cost Driver (% of total budget)	IMC	NRC	HI
1	Staffing costs (45%)	Staff salaries (54%)	Staff salaries (50%)
2	Procurement of medications (4.5%)	Transfers to downstream partners (11%)	Procurement of assistive devices, prosthetics, and orthotics (12%)
3	Cash transfers (3.7%)	Fleet costs (4.7%)	Support access to rehabilitation services (7%)

For procurement, IMC and HI will apply competitive tender processes in order to procure the best quality items at economical costs and will report to DFID on their success. Details on procurement are provided in the Commercial Case.
Efficiency
To assess the efficiency of the interventions, we will measure the indirect/ overhead costs of each project, and a cost per beneficiary for each of the different interventions.
The partners are conducting distinct, independent projects which would prove challenging to implement through a consortium approach. Each partner has established relationships with local stakeholders (e.g. IMC has offices within government clinics) despite the challenges associated with the often unpopular and stigmatising issues being addressed. Professional skills are vastly different between the projects. All three organisations have established headquarters in Amman. For this reason, it is not deemed realistic for partners to aim for efficiencies through consolidating space and resources.
The table below compares the indirect costs of each agency, which shows they are broadly similar. These costs have been negotiated down during the proposal stage in order to channel more funding towards beneficiaries and less towards overhead costs. The budget split between partners is presented in the Financial Case. A “benefits approval form” (BAF) will be submitted by DFID upon approval of the Business Case.
Agency	Overhead Costs as % of Budget
NRC	7%, negotiated down from 8.6%
IMC	7.85%, negotiated down from 8%
HI	7%, down from 9.5% from a similar current DFID programme

On costs per beneficiary, the below table outlines the cost per beneficiary for each intervention as well as the types of services that will be received (the cost per beneficiary was calculated using the full budget and the number of direct beneficiaries). DFID will monitor these costs throughout implementation and encourage partners to find ways to improve efficiency where possible. Costs per beneficiary are higher for HI due to the technical skills and cost of assistive devices required for the intervention, but this is justified by the high quality services provided by HI and the significant degree to which beneficiary lives are improved. Detailed activity costs have been shared during the proposal submission stage and the average cost per beneficiary per organisation is shared below, although costs can vary significantly by activity.
Agency	Cost / beneficiary	Services received (as outlined in the Strategic Case)
NRC	£70	Information, counselling, and legal services.[13]
IMC	£284	Mental health and primary health consultations, child protection, psychosocial support, cash assistance.
HI	£468	Physical rehabilitation for persons with disabilities, support to local Ministry of Health, coaching other NGOs on disability inclusion, early detection and intervention for children.
[13] excluding the number of beneficiaries to be reached by mass communication on social media

Effectiveness
All three agencies conduct regular monitoring exercises to measure outcome indicators which form the effectiveness indicators of this proposed programme (as per the logframe). They will track the outcome unit costs across the period of implementation to have further quantifiable indicators and measure the unit cost per beneficiary to achieve the desired outcomes. Indicative outcome indicators are presented within the DFID logframe and will be agreed with the partners during contracting. Partners will receive payment on a quarterly basis upon submission of reports to assure DFID that activities are on track.
Previous DFID experience with these three agencies in Jordan demonstrates effective programming where outputs and activities are leading to positive outcomes. Moreover, the three year programme proposed in this business case has the potential to bring about more change on the long-term where agencies have the ability to develop sustainable approaches and not just emergency interventions without clear longer term outcomes. Activities aimed at sustainability include building the capacity of downstream partners and other implementers to eventually take over service provision, rehabilitate spaces to make them more appropriate for the intended use, engage with the GOJ on strengthening the enabling environment, and increase downstream partner responsibility over time whilst gradually withdrawing their own staff. DFID will explore ways of measuring the effectiveness of sustainable programming.
In addition to the above, all three agencies will be conducting mid-term and end of project evaluations to measure the effectiveness of the programme at different intervals, and adjust programming as/if necessary.
Equity
The three agencies address equity in all aspects of their implementation where their services are focused on reaching the most vulnerable and marginalised in society.
NRC will be measuring the impact of its interventions on each sub-group of beneficiaries (disaggregated by age, gender, nationality, and disability) and tailor programming to address their different needs.
All three agencies employ mobile teams and conduct home visits to beneficiaries who are unable to reach their centres, and cover rural areas where services may not be available, and possibly the most vulnerable reside.
The services provided under this proposed programme target gender equally, as well as people with specific health or protection concerns like people with disabilities or mental health issues. The comprehensive package of support offered by these agencies can respond to the most vulnerable people.
All three agencies will disaggregate data by age, gender, location, and disability; and are committed to meeting DFID’s target of using the Washington Group Questions in their programmes by 2022. Working with multiple agencies will improve the equity proposition of the intervention as they work across different areas and with different vulnerable groups with particular needs.
Commercial Case
Funding arrangements
The three agencies referred to in the preferred option were selected through a competitive call for proposals process, and as they are all non-governmental organisations, the most appropriate funding mechanism for delivery of the recommended option of this programme would be an Accountable Grant Agreement (AGA) with the implementation partners. The AGA details the total funds available for this intervention and indicative tranches over financial years, the reporting requirements, financial disbursement details, and DFID reserving the right to conduct audits and evaluations of the partner. Due diligence is elaborated in the AGA and the document commits partners to following international best practices on procurement, financial management, risk mitigation, fraud and corruption, and termination if the conditions of the AGA are not fulfilled.
The AGA includes the facility to adjust the programme subject to situation or context changes. This would be agreed between both parties and other documentation would be adjusted accordingly. Requests can be made by DFID or the partner through regular monitoring meetings or ad hoc.
Payment in advance has been requested by some partners and may be approved, if justifications are strong enough. The timing of payment would be agreed in advance of signing each AGA and will be approximately distributed equally throughout the three years.
Core competencies of the organisation(s) to deliver the programme
Due Diligence Assessments (DDAs) will be completed for all partners prior to disbursing funds. All three organisations are current partners of DFID Jordan’s humanitarian programme conducting similar activities. Their performance is rigorously checked through quarterly reporting and monitoring visits. Most recent annual reviews scored IMC with “A” (10/2017), HI with “A” (04/2017), and NRC with “A+” (12/2017). Outputs will be delivered in accordance with the logframe.
Procurement capability
All procurement processes are conducted in an open, transparent and competitive manner by each of the partners to maximise VFM when making purchases and to prevent impropriety in the process. Changes to budget lines as a result of procurements will be communicated with DFID quarterly. Detailed budgets were provided to DFID during the proposal stage. Procurement processes for each partner are summarised below.
IMC has developed a procurement plan for the entire duration of the grant and coordinates with the relevant departments for the initiation of these procurements. IMC has a Global Logistics Department, tasked with facilitating procurements of drugs, medical supplies, equipment, and other items required. IMC’s Health Technical Unit based in the USA, includes doctors and public health professionals who oversee and manage their medical supply chain. IMC will supply psychotropic medication to supported clinics for the affected population in line with international, WHO and GoJ/MOH standards. Purchases are done through competitive bidding, financial and quality controls, committee reviews and approvals, and delivery standards. Procurement of medicines will be done from IMC prequalified vendors meeting organizational and JFDA (Jordan food and drug Authority) requirements and standards.
Humanity and Inclusion will set a procurement plan and follows strict procedures in order to secure the appropriate quality and best price for the required inputs. This includes regular Calls for Tenders at a country level in order to recurrently assess the market, obtain required inputs at the best costs, and sign framework contracts with the selected suppliers. Processes will be in place for the production and supply of specialist equipment, e.g. prosthetics, orthotics (P&O), and assistive devices. Availability of these items remains limited in Jordan and the ratio between quality and price is often low. HI will maximise quality of procurements by increasing its internal capacity to monitor the quality, a competitive call for tender to select private suppliers, and collaboration with a local NGO specialised in the production of P&O.
NRC’s purchasing is regulated by the global NRC logistics handbook, which mandates that, where possible, schemes such as the comparison of quotations and open tenders are used. When establishing a framework agreement, the agreement must undergo an annual review for quality of service and price. All framework agreements must be re-tendered a minimum of every three years to ensure appropriateness of price. International tenders for high value contracts are also in place to ensure cost effectiveness of procurement. NRC uses in-country price lists to manage the quality and price of procured items. In 2017, NRC had in place in excess of fifty long-term agreements from transparent tendering processes, allowing for competitive pricing and quality of goods and services. In addition to ensuring competitive prices for goods and services, these agreements also facilitate more efficient and timely procurement, leading to an increased overall efficiency.
All partners will seek to encourage local supply of products and services where quality and cost is relatively competitive and will report to report to DFID when the need for global purchasing has overridden the ability to deliver locally. This helps increase the impact of every pound spent since the local purchasing of goods and services has a positive stimulatory impact on the economy, creating opportunities for income generation. The Due Diligence Assessments may identify areas for improvement within each organisation.
Delivery risks (financial)
The programme is assessed to be low financial risk. The operating environment is accessible, and strong, direct oversight of delivery is achievable for partners and DFID. Hawala will not be used. The main financial risks were assessed and are presented in the Risk Matrix (Annex C). All levels of the delivery chain will be made aware of their responsibilities to prevent aid diversion, fraud and corruption and NGO codes of conduct will be signed by staff. DFID Jordan will mitigate residual risks through DDAs, quarterly monitoring (including risk updates) and field visits. Key financial risks are presented below.
- Aid diversion, fraud, corruption: mitigation: the stable operating environment allows for close scrutiny of activities in the field by partner staff. Human resource requirements include c-fraud training, organisational codes of conduct and “whistleblowing” systems. For example, IMC recently issued their “Guidance for Responding to Suspected Fraud and Other Illegal Conduct” for all staff. Any suspected aid diversion, fraud or corruption must be reported to DFID immediately. All downstream partners have been or will be assessed through due diligence and their responsibilities clearly defined in their contracts. Training will be provided where standards require a boost and follow-up will continue throughout the project. Activities involving cash (e.g. IMC’s cash for protection) or payments for services (e.g. NRC’s legal assistance, HI’s Equity Fund) will be safeguarded through safe delivery mechanisms (Jordan Post for IMC) and agency monitoring in all cases.
- Exchange rate fluctuation: mitigation: each partner will continuously monitor exchange rates and reassess the impact on budgets each quarter. Funds will be transferred from DFID to partners on a quarterly basis, thus spreading out the risk and allowing time to adjust. Partners are responsible for mitigating any financial impacts this risk may have on their activities.
Negotiating costs
DFID has negotiated cost savings with pre-selected partners of £3,606,223 (including £170,177 from reduced NPAC). BAFs will be submitted following approval.
- Reduction of IMC’s overall project cost from £9,034,155 to £6,116,932 by reducing budget lines, shortening the project by 4 months, removal of one activity and lowering the NPAC.
- Reduction of HI’s overall project cost from £5,689,000 to £5,000,000 through reducing programme and support costs.
- Reduction in the NPAC rates from initial proposal:
  - NRC: from 8.6% to 7%, representing an extra £44,859 for the programme.
  - IMC: from 8% to 7.85%, representing savings of £8,496 for the programme.
- Reduction in NPAC rate from previous programme:
  - HI: from 9.5% to 7%, equivalent to £116,822 of the new programme value.
Financial Case
Overview of costs
The programme is ODA eligible and there will be no costs incurred directly by DFID. The table below represents a breakdown of the financial chapters in the proposed combined budget:
Chapter	£ value
A. Inputs	£ 4,378,967.00
B. Transport	£ 453,797.00
C. Security	£ 29,990.00
D. Logistics and overheads	£ 601,766.00
E. Staffing and support	£ 7,524,014.00
F. Monitoring and evaluation	£ 75,015.00
G. Capital items	£ 76,912.20
Total	£ 14,108,436

Cost profiling and planning
Funding from this programme will be taken from the humanitarian pillar’s budget for 2018-2021. This programme represents up to £15m over 3 years, from a total pillar budget of £75m. The programme will begin on the first day of the 2018 financial year.
DFID’s contribution to NRC would support a critical programme which has proven results in Jordan. Additional support will come from the US, Swiss State Secretariat for Migration, Swedish Development Agency (SIDA), European Commission Humanitarian Office (ECHO), and the Dutch Ministry of Foreign Affairs. The IMC project is entirely dependent on DFID funding to go ahead as proposed. The contribution to HI will co-fund some activities and solely fund others. The DFID share for each partner is outlined below, taking into account that this is indicative based on anticipated financial projections in later years. This share may change as other donors are sought.
- IMC: 100% of total programme cost over 32 months.
- NRC: 54% of total programme cost over36 months.
- HI: 35% of total programme cost over 36 months.
Payment of funds
Funds will be disbursed on a quarterly basis based on quarterly financial reporting and forecasting. All payments will be made in GBP. Each organisation’s contract will represent a single component under the full programme.
Component	AMP number	Title	% allocation of total
1	300537-101	Support to Humanity and Inclusion	35.6%
2	300537-102	Support to International Medical Corps	43.5%
3	300537-103	Support to Norwegian Refugee Council	21.3%

Financial risk
The risk of fraud, corruption and aid diversion for all partners is assessed as being “low”. All partners will have a completed Due Diligence Assessment at the time of contracting. The top risks for the programme are presented in the Management Case.
All agencies have appropriate systems in place to deal with bribery, corruption, and security risks. There are policies in place on whistleblowing where new staff have to be trained and made aware of the different mechanisms in place on reporting such cases. Jordan’s operating environment makes such risks possible but DFID assesses the systems in place at all three agencies to be sufficient; based on current experience through existing grants and previous due diligence assessments. Further assurances will be obtained before disbursing funds should this business case be approved.
Monitoring, reporting and accounting for funds
A monthly budget forecast for each partner will be supplied at the start of the programme. Financial reports will be submitted by partners to DFID on a quarterly basis, which will include refinements to monthly forecasting for the following quarter. The forecasts and actual spend will be reviewed along with reporting narratives and the logframes to assess progress against the outputs and outcomes. Partners will disclose on a quarterly basis any assets with a value of over £500 purchased with this grant and at the end of the programme asset transfer will be agreed in accordance with Smart Rules. Any unspent funds at the end of the grant will be returned to DFID.

Management Case
What are the management arrangements for implementing the intervention?
DFID will be the only donor contributing to the share of results outlined in the logframe. All three proposed partners rely on funding from other donors for scaling or complementary actions, although some activities will be solely reliant on DFID funding. DFID will be directly managing each of the three proposed partners which will have an impact on DFID staff time.
DFID Jordan
All management, technical support and administration will be led by the country team in Amman, supported by colleagues in the UK. The SRO will be the Amman-based Deputy Head of Office (A1). The Lead Humanitarian Advisor (A2) will provide oversight of the Humanitarian Adviser (A2L/DESA) and Deputy Programme Manager (B1), all in Amman, who will provide technical input, monitoring, and lead on day-to-day dialogue with the partners. A Policy Advisor (B1) will provide policy advice and support from London. Support to the humanitarian team in Amman will be provided by the Social Development Adviser, Conflict Adviser, Statistics and M&E Adviser, and a Commercial Delivery Manager.
Implementing Partners
All three of the pre-selected organisations have similar organisational management structures. Country teams are led by a Country Director, responsible for overall progress and coordination with international and institutional partners. Support teams include administration, finance, human resources and logistics managers. Each organisation will receive support from technical and operational teams based in regional offices or in headquarters. Projects will be overseen by programme directors, with dedicated project managers responsible for project cycle management and team supervision. They will apply the expertise of their technical teams in supporting their projects.
Each contracted partner will be responsible for the due diligence and follow-up of their downstream partners, which include national NGOs and Ministry of Health structures.
What are the risks of intervention and how these will be managed?
This has been assessed to be a low risk programme. A table outlining the key risks and mitigations is included in Annex C and a more comprehensive version of the risk matrix is included in the logframe workbook. The most significant risks are:
External context: a fluctuation in the number of refugees, or their needs, is a possibility but with moderate severity. Triggers could include relocations or returns to Syria, changes in policy, epidemics/outbreaks, and other unforeseen events. Any impact is likely to be proportional to the number of people affected. Mitigations will include advocacy against forced relocations/ deportation and harmful policy changes, continued support to the GOJ through the Compact, Partnership and other mechanisms, and flexible programming that can adapt to a change in needs.
Deterioration in security conditions is possible and would be of major severity. Such triggers could include recent changes in US policy in the Middle East, unrest in Jordan due to economic issues, and expansion or evolution of active conflicts. The risk will be managed through monitoring of the regional political climate, security incident trends, NGO security planning, and alternative counselling methods with beneficiaries (i.e. phone).
1. Reputational: whilst unlikely to occur, negative attention to activities could be of major severity. The programme does not include contentious or controversial activities and will target beneficiary groups largely recognised as vulnerable. Programme design is conflict sensitive. DFID will maintain transparency through publication of projects on DevTracker and regular updates to external lines. Strategic communications planning the British Embassy (Amman) will incorporate opportunities to positively showcase humanitarian achievements.
2. Fiduciary: See Financial and Commercial cases for fiduciary risks.
3. Delivery: Local partners may be lacking in the skills required to deliver the programme, this is moderate severity overall. Therefore, the DFID partners will provide comprehensive capacity building according to assessed needs throughout the programme, and delivery will be carried out by local partners where possible to build experience. The delivery of technical and professional training will raise the employability of participants, particularly those in front-line delivery national NGOs. This may make it difficult to retain skilled staff in an environment where such skillsets are in deficit. Mitigations will include competitive salary scales and incentives, and multi-year funding (leading to long-term contracts).
4. Safeguards: it is unlikely that beneficiaries will come to harm as a result of the programme, but overall impact would be moderate. Risks can include inappropriate behaviour by DFID or NGO staff, exploitation of beneficiaries by third parties, or local conflict. The risk will be managed through regular monitoring by DFID with partners (quarterly) and field visits, as well as safe NGO procedures for whistleblowing. Enhanced procedures from DFID’s Safeguarding Unit will be implemented as and when they become active.
5. Operational: some organisations in Jordan have faced registration and approval difficulties, particularly in relation to soft activities in the psycho-social sphere. It is possible that DFID partners will face the same challenges, with significant consequences. This will be mitigated through working with partners with pre-existing registration, who have strong connections in place within relevant ministries. Regular communication between partners and DFID will raise issues early and give a window of time to intervene. Partners will coordinate with other organisations in the same “sectors”, to share experiences and learning.
How will progress and results be monitored, measured and evaluated?
This programme will require rigorous monitoring and evaluation to assess the impacts, drive results and value for money, and for policy advocacy and influencing. The evidence will make a significant contribution to national and global debates on protection for vulnerable communities. The monitoring framework will therefore build instruments for gathering both quantitative and qualitative data for rigorous monitoring of the logframe.
Monitoring for this programme will assess progress through reviewing logframe results, finances, activities, compliance, context, risks, and accountability.
DFID Jordan
Security in most operating areas is good and DFID can conduct field visits to verify information provided by partners during reporting. Each partner will provide DFID with a quarterly logframe (performance), risk, narrative and financial reports. These tools are used in parallel to appraise the partner’s progress toward agreed results and timeframes, according to the budget forecasted. Value for Money (VFM) indicators will be reported against internally.
Since early 2017, DFID Jordan has used a modified version of the DFID Syria network’s “CASCADE” project monitoring system, which allows partners to upload monitoring reports online using standardised templates. Data and results are extracted automatically from spreadsheets and used to populate logframes. All three partners are familiar with this tool.
DFID will meet formally with all three partners once each per quarter to discuss progress on the programme and plans for the next quarter. Downstream partners will be required to attend these meetings. The quarterly meetings will alternate between field visits and office-based meetings with a focus on implementation, progress, context changes, opportunities and challenges. DFID may also conduct spot checks to partner facilities to observe operations outside of an organised site visit, including communications opportunities.
Annual Reviews (AR) will be carried out by DFID against the business case, with a Programme Completion Review (PCR) at the end of the programme. The ARs and PCR will primarily draw from data provided in quarterly reports and monitoring visits.
Partners
The partners each have dedicated M&E teams and strategies in place. As current partners, they are all familiar with and fulfil DFID’s requirements in Jordan. Teams are supported by regional and/or headquarter specialists. Programme outcomes will be assessed by partners using their own tools to develop lessons learned, which can be used as a feedback mechanism to improve programme strategies and procedures. Reviews of objectives and results will be complemented by contextual and institutional monitoring. The capacity of downstream partners will be evaluated in each case and capacity building plans developed to raise standards. By the end of the programme, downstream partners will be expected to have the capacity to design, implement, and learn from M&E plans, ensuring accountability to their beneficiaries whilst meeting donor requirements. Data collected will adhere to DFID disaggregation requirements and uploaded to CASCADE.
In addition to the organisation-level MEAL plans, HI and IMC projects will be subject to mid-term evaluations, which will inform any necessary changes to design in the outer years based on changes in needs or context. Each partner will have an external impact evaluation at the end of the programme. Evaluations will include the needs of and impact on women and girls and other vulnerable groups. They will be used to determine the effectiveness of the programme in achieving its outcomes and fill key evidence gaps in the theory of change. The midterm evaluation will be timed to allow any recommended changes to be made to the outer years of implementation to improve outcomes.
These costs have been budgeted in the programme design. The terms’ of reference for these external evaluations will be agreed with DFID in advance of contracting external bodies. Evaluation reports will be signed off by DFID.
Other relevant monitoring and evaluation considerations are outlined for each NGO:
- IMC: Capacity building for MEAL will be included in JOHUD’s three year continuous training plan.
- HI: All programmes globally adhere to their 2015 Project Monitoring and Evaluation (PME) Policy. Downstream partner IFH/NHF will benefit from the support of a HI Project Officer and data management will be progressively transferred.
- NRC: The ICLA team uses a case management database, updated daily, which is used to generate protection monthly reports. ICLA conducts biannual outcome monitoring exercises aimed at assessing the impact and the quality of the services. NRC evaluations take place every 2 years, as per their global M&E strategy.
A “DFID partners’ forum” will be established, through which all three of the implementation partners will have an opportunity to discuss programme challenges and opportunities, and share learning. This will be held on a quarterly basis.
Accountability to beneficiaries
Assuring that projects are accountable to affected persons, including direct beneficiaries, was a requirement during the design phase and each partner has outlined their commitment during proposals. Accountability and transparency mechanisms include:
- Complaints response mechanisms (CRM): Each partner has visible CRM in place at all of their sites in Jordan to actively seek the input of beneficiaries and other stakeholders. Methods used include hotlines, complaints boxes, social media, two-way feedback with case managers, group discussions and email. Reporting and feedback will take place as per each organisation’s MEAL strategy in Jordan.
- Outreach, consultation, and community mobilisation: Outreach efforts will ensure that the most marginalised and vulnerable have a voice. Each of the partners will conduct outreach in different ways. For example, people with disabilities will benefit from outreach by HI’s CBR network. IMC and JOHUD’s mobile unit will engage with people in hard-to-reach communities in ITS’s and NRC community mobilisers will conduct Outcome Monitoring Exercises. Two-way communication will be implemented through individual and group settings. All beneficiaries will benefit from individual follow-up from case managers.
- Rights-based awareness and advocacy: Partners will strive to ensure that affected populations in their sectors know their rights and entitlements. Capacity building and advocacy with other stakeholders, including INGOs and GOJ, will increase access to rights and services for people with specific vulnerabilities and target stigmatising attitudes.
Partner monitoring and evaluation teams will support projects to ensure they are beneficiary centred and responsive to changing needs and priorities. Quarterly monitoring in DFID, including field visits with spot checks, will review accountability mechanisms and support will be provided if necessary. The programme will retain the flexibility to adapt following trends and outcomes identified during the complaints and feedback process, so that beneficiary participation is ensured during all stages of the project cycle.
The impacts of the Syria crisis on Jordan has become a protracted crisis and sustainable strategies are required to support the Government of Jordan in responding to the increased burden on basic services. The programme has been designed with the anticipated outcome that activities will be handed over to downstream partners, or will no longer be necessary. A focus on accountability to affected persons will be included in evaluation terms of reference.
Annex A: Map showing registered refugees by governorate

Figure 1 - UNHCR-registered Syrian refugees in Jordan, December 2017 (source: UNHCR)
Annex B: Comparative analysis of Options
	Option 1: Implement a protection programme with one INGO	Option 2: Contribution to the UN	Option 3: Implement a protection programme with multiple INGOs
Geographical reach?	Most governorates, or national. A single partner could achieve a good geographical coverage but for a narrower range of activities.	Most governorates, or national. UN agencies in Jordan have a broad geographical reach.	National. Smaller numbers and geographical reach for each of the targeted vulnerable groups but greater power of referrals and a magnified effect in locations where all three organisations operate.
Ability to deliver to hard-to-reach beneficiaries?	Possible, in one sector or activity type, if it is specified in the programme design.	Possible, but at a reduced scale due to the need to sub-contract to NGOs.	Yes, in multiple sectors through mobile units and community outreach.
Expertise in-house to deliver full range of services?	No. Specialist approaches for some vulnerable groups will be lost (e.g. for persons with disabilities). Relevant national partners and GOJ ministries will not receive the full range of capacity building by specialists in different sectors.	Globally, most of the expertise exists within the UN system.	Yes. Extremely vulnerable and marginalised people from several groups at risk of protection issues will be targeted for assistance, whilst simultaneously building the capacity of local and national services and professional specialists in multiple complementary sectors.
Experience in Jordan in delivering the specialised services?	In some of the prioritised sectors, but not all. We would select a partner with a good track record in Jordan.	Some, not all.	Yes. Each of the three preferred organisations is a current DFID partner carrying out similar activities and scored well in latest reviews.
Capacity to work with Jordanian organisations and prepare for hand over?	In some of the prioritised sectors, but not all.	This is not something that the UN in Jordan typically does.	Yes.
Aligned with DFID’s strategic priorities?	Yes.	Partially	Yes.
Other advantages/ disadvantages	Advantage: / Programme risk of relying on a single partner for delivery. / Disadvantage: / Fewer resources required within DFID for programme monitoring.	Advantage: / Lower VFM as NGOs may be sub-contracted for these services. / Disadvantage: / Fewer resources required in DFID for programme monitoring. / UN is able to advocate at higher levels for inclusion of vulnerable groups.	Advantage: / Greater resources required in DFID for programme monitoring. / Disadvantage: / Efficiency of specialised referrals for co-existing vulnerabilities, between DFID partner organisations in working areas, is increased.

Annex C: Risk Table
Risk	Probability	Impact	Severity	Mitigation Actions
Government approval for the project implementation delayed	Possible	Major	Major	Partners prepare registration documents in advance. Partners and DFID sign project documents well in advance. Regular communication between partners and GOJ line ministries. Regular and open communication between NGO partners and DFID. Reviewing risk matrix during every reporting period. Coordination between partners and other agencies working in similar fields.
Aid diversion Fraud and corruption	Unlikely	Moderate	Moderate	Due diligence and downstream partner risk mapping on implementing partners. Quarterly monitoring incorporates fraud risk assessment. Having strong policies in place and different lines of defense including strong internal controls and reporting mechanisms. Policy of zero tolerance to fraud and corruption incorporated into grant agreements. Extensive procurement SoPs in place, and staff trained on relevant codes of conduct. Clear separation of programme departments from logistics and m M&E. Prompt reporting of any suspected or confirmed instances of fraud, corruption, or aid diversion to DFID.
Exchange rate fluctuation affecting activities	Almost certain	Moderate	Severe	Partners to look for savings in the case of exchange rate loss and reduce expenses in a way that does not affect service quality. Closely monitoring the exchange rate fluctuations in relation to the budget. Timely implementation of activities.
Partners are unable to recruit or retain qualified staff	Possible	Minor	Moderate	Recruitment to commence as quickly as feasible. Collaborate with GOJ on accreditation and training of additional specialists in the health sector. Building a pool of qualified candidates. Working with universities to train and target fresh graduates. Ensuring salaries and incentives are aligned with the market. Advertising positions widely through relevant networks.
Capacity of local service providers	Possible	Moderate	Major	Strong oversight of partnerships by INGO partners including the selection process and capacity building of downstream partners. Regular communication and monitoring of downstream partners. Supervision and technical coaching of downstream partners. Strong CRM in place to monitor downstream partner performance and beneficiary engagement.
Security conditions deteriorate in Jordan	Possible	Moderate	Major	Monitoring of the regional political climate. Monitoring of trends in security incidents. And attending security coordination meetings. Security plans in place and being implemented, in addition to developing security SoPs for each implementation area. Conducting counselling by another method with beneficiaries (e.g. telephone)
Projects receive negative attention	Unlikely	Major	Major	Transparency of programme activities on DevTracker. Visibility planning, including media engagement. Appropriate programme design. Regularly update external lines on humanitarian programmes.
Fluctuation in number of refugees or their needs	Possible	Minor	Moderate	Advocate against forced relocations/ deportation. Working with agencies inside Syria to follow-up with vulnerable cases where possible. Mobilisation of resources to either focus on remaining most vulnerable or scale-up in the case of an influx of refugees. Close monitoring of border situations and the security environment inside Syria to anticipate movements. Plan for flexible programming that can adapt to a change in needs.
Refugees harmed as a result of DFID-funded activities	Unlikely	Moderate	Moderate	Conduct conflict sensitivity analysis of partners and work closely with them on recommendations. / Enhanced safeguarding procedures.
Changes in government policy (particularly on health) negatively affects partners’ ability to deliver	Likely	Moderate	Major	Advocacy with the GoJ to change policies. / Working with other donors and the health working group to develop more sustainable strategies for health services to refugees. / Monitor the effects of the policy change closely and scale-up the programme if needed and funding is available.