Type of Review: Annual Review

Project Title: GDNet- Research Communication from and for the Global South

Date started: 24th April 2012
Date review undertaken: 24th – 26th April 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
GDNet is a multi-donor Knowledge Initiative, which brings together and communicates policy-relevant research from the Global South. It has over 12,000 members (researchers from developing and transition countries) to whom it provides access to online journals, grey literature and other research documentation, data and access to information about research funding. GDNet supports southern researchers in making their research accessible and available to a global audience and strengthens their research communication capacity through training materials and workshops. It aims to be an internationally recognised organisation for sharing knowledge on development research to inform policy debate. GDNet is a partnership with regional networks and leading experts in the field. GDNet is currently supported by DFID, DGIS and the World Bank.

What are the expected results?
The programme’s aim is to impact on research and policy audiences who will make better use of development research from the south. The longer term objective of the programme is contribute to ensuring that better policy for achieving poverty reduction is informed by better research. The programme aims to deliver on five results: / Southern research are better informed by current ideas and knowledge / Researchers are better able to communicate their research to policy / Knowledge networking between researchers and with policy actors is increased / GDN Fellows’ research is better communicated to different, identified audience / Lessons about knowledge brokering best practice in the global south are learnt and communicated

What is the context in which UK support is provided?
Researchers in developing and transition countries (often referred to as “the South”) have valuable knowledge to contribute to decisions being made about development in their countries and elsewhere. However they face several challenges in being heard by government staff and other people involved in policy-making, such as lacking the confidence and ability to communicate their research effectively, or lacking access to the academic journals they need in order for their research to be published. DFID funds GDNet to build capacity of researchers to help them produce and share their research findings to reach as wide an audience as possible so that development decisions are more likely to be informed by the best available local knowledge. DFID, through its Research and Evidence Division, has a specific mandate and policy commitment to strengthen the science, innovation and research environment in the South.

## Section A: Detailed Output Scoring

Output 1: Southern research better informed by current ideas and knowledge
Output 1 score and performance description: / A – the outputs met expectation. / The programme is performing on output 1 as milestones have been exceeded. GDNet site receives an average of 29,416 visitors per month, with 39% coming from the Global south. / The programme cannot report against indicator 2, as the baseline will only be collected at the end of 2012.
Progress against expected results: / Milestone 1 (for indicator 1) has been achieved on target (to the end of 2011) and milestone 2, halfway through the reporting year (2012). The milestone (indicator 1) measures a 10% year on year increase in use, yet four months into the year this milestone has been exceeded as there has been a 24% increase in use (almost the target for 2014). The baseline against which the milestone is measured, is 23,617 visitors per month, of which 33% come from the Global South. / The milestones for indicator 2 cannot be reported as the baseline will be established in November 2012. GDNet piloted a beta version of eleven themed services in July 2011 and launched a full set of 23 themed services on 11 November 2011 (these can be explored at http://cloud2.gdnet.org/cms.php?id=knowledgebase ). The level of use and satisfaction of these services will be monitored, but it is too early to make an evaluation. / Recommendations: / The user survey data provides useful insights into user requirements, priorities and behaviour. The monthly stats provide a useful tool to monitor trends. Further analysis of the webstats is needed and should be triangulated with results of the user survey. This is necessary to better understand user preferences and behaviours. / For example, webstats for the month of July indicate a very low number of researchers accessing online journals (58 visitors for July accessing online gateway to MUSE and JStor) despite researchers’ claims that this is a main incentive for joining the GDNet Community. There are 21,000 document downloads from GDNet Knowledgebase from around 28,000 visitors (for July). But we don’t know how many visitors downloaded the 21, 000 documents; there is a need to better interrogate the webstats and the user survey to have a better idea of users. / Since the programme was conceived there has been a increasing trend in moving towards open access data, repositories and journals. For example, in the last year the World Bank and the Wellcome Trust both launched open access policies; JSTOR has opened free access to Africa, but now restricts some access to India and Pakistan); DFID is about to launch its own Open Access Policy. / Visitors from the global south to www.gdnet.org are only 39%, yet the main target audience for GDNet is the global south – the webstat figures need better explanation in light of the survey findings. GDNet’s “Connect South” campaign aims to increase this percentage. / GDNet launched the first phase of its “Connect South” campaign in a bid to encourage development research and policy communities to adopt a more inclusive approach to southern research. The campaign calls researchers, partners and knowledge providers to promote southern knowledge and perspectives at every level. It will be formally launched in Q3 2012. This will serve as an enabler to deliver against purpose level indicators. / It would be useful to get a better understanding of the user profiles and requirements to tailor knowledge products such as ‘how to guides’ or ‘search skills’ to facilitate access to journals. IT would also be useful to provide sign posting (from other services to and from the site) to facilitate access to free online journals and to guide researchers through further development of information literacy guides. / GDNet currently provides a document delivery service through BLDS, where they invoice BLDS for the service, yet the service is already funded by DFID. / Specific actions: / GDNet to interrogate the webstats and explain the anomalies; GDNet to correlate the user survey with the webstats and try to explain and map the trends they should also look at comparisons to see how they compare to similar services. / GDNet to re-visit the landscape for open access and how this increasing trend impacts on GDNet services. / Consider separating ‘use’ and ‘satisfaction’ and exploring users’ perceptions of quality of Southern Research (in relation to how satisfied they are with the research, e.g. would they reference it in their own work). / GDNet to coordinate a zero cost arrangement with BLDS so that BLDS bills DFID directly for services (rather than via GDNet) for document delivery services used by GDNet. / Action for DFID / It is acknowledged that stats are not easily available for comparison or benchmarking with other similar services. DFID should investigate how webstats data and other relevant M&E data from similar services (funded by DFID) might be shared. Find a mechanism to encourage better analysis and interpretation of webstats in M&E reports. / Work with GDNet on the action to better signpost similar services to and from the site (if necessary – i.e. to build relations, or make introductions with relevant programmes / services). / Impact Weighting (%): 45 / Revised since last Annual Review? Y / Risk: Low / Revised since last Annual Review? N

Output 2: Researchers better able to communicate their research to policy
Output 2 score and performance description: / A - The output met expectation / This output is performing well, though it should be recognised that the target for indicator 1 probably needed revising last year to reflect extremely high levels of achievement.
Progress against expected results: / Four workshops were held and on a before and after self-assessment scale, the average increase in confidence was 50% and the average increase in ability was 89%. This compares to figures across two workshops in 2010, where similar figures were achieved. / The first set of nine ‘pledge’ cases that resulted from the four workshops held in 2011, partly indicate the sustainability and application of GDNet’s capacity building effort. These cases were followed-up three months after the event and qualitative data is provided in the GDNet M&E Report 2012 (quest no. 3473691). / Some concern was raised about the distribution of funds to different networks and whether or not this needs re-visiting in view of some networks receiving substantial funding outside GDNet. There is a question about continued support to networks through GDNet and at what stage GDNet should exit. / Recommendations: / There is no milestone for output 2 (indicator 1) as it is not a year on year, accumulative figure. Rather it aims to monitor the consistency of value added in training workshops in each year of the programme. Therefore the target is set to achieve a level of confidence and ability at the end of each workshop of 30-40%. / Consider how to develop and support new networks, rather than supporting those that should by now be self-sustaining. / Actions: / Review the target for ability and separate ability and confidence. / Set the ability target at a more realistic target to demonstrate what GDNet is achieving. / Provide the analysis in percentages rather than on a scale of 1-5. Provide analysis that refers back to previous years to show consistency in both ability and confidence. / For indicator 2, consider follow-up again after 12 months, rather than only 3, to really assess sustainability. / Review GDNet exit strategy once a network is deemed to be self-sustaining / Impact Weighting (%):20 / Revised since last Annual Review? Y / Risk: Low / Revised since last Annual Review? Y

Output 3: Knowledge networking between researchers and with policy actors increased
Output 3 score and performance description: / A – the output met expectation / There is evidence to show that GDNet has established on-line interactive spaces over the past year, however assessment of performance of ‘interaction’ is difficult as there is little analysis of data. Researchers’ interactions with the policy domain have been achieved through four events. The GDN management still consider GDN to be weak at linking research and policy and to understanding how research is used in policy. This is an area where GDNet could be expanded.
Progress against expected results: / Indicator 1, the programme has developed a range of interactive on-line tools to engage the user base. A full log is provided in GDNet M&E Report 2012 (quest no. 3473691). However, it is difficult to assess exact progress due to a lack of analysis and interpretation of results from these activities. For example, the log provides figures on visits to a blog post for the GDNet Annual Conference in 2010 and 2011, yet there is no analysis or interpretation of these figures (but there is a 29% increase in visitors, which is very positive but not obvious from the analysis). / Indicator 2 was achieved through four interactions (though the milestone was to achieve at least two) between Southern research and the policy domain (details contained in GDNet M&E Report 2012 (quest no. 3473691). The experience has generated a small number of valid lessons including the requirement for GDNet to actively host any researcher-policy domain interaction in order to introduce both parties and encourage interaction based on common interest. / Actions: / GDNet need to provide better collection of data, analysis and aggregation of figures for user base interaction, rather than only a log of activities. For example, indicator 1 provides a few figures on views of blog posts, but this is not consistent for all activities, there is no comparison or trend mapping to visualise and quantify progress and performance. / Revisit the milestones and target for indicator 1 to better define what is meant by a ‘network’ and ‘active user base networking’. / There is a need to disaggregate figures, especially by country and region and gender. It is not clear from the analysis, for example, what proportion of ‘southern research’ is from different regions. There is some concern that francophone countries are rather absent from engagement under this output area. GDNet should consider how francophone countries should and can be included in the social media work. / Re-visit the milestones in view of the rapid increase and use of social media, recognising use of web 2.0 amongst researchers, especially in the South. / There are lots of positive figures and successes, but they are not apparent on reading the documentation. GDNet could be much better at showcasing its successes and strong performance. / Impact Weighting (%): 15 / Revised since last Annual Review? Y / Risk: Medium / Revised since last Annual Review? Y

Output 4: GDN Fellows’ research better communicated to different, identified audience
Output 4 score and performance description: / A – has met expectations. / It is not possible to score this output based on the current indicators, as there is still no agreed definition of a ‘GDN Fellow’. GDNet has devised an alternative indicator as an interim measure, which defines GDN Fellow as including all GDN Grantees. This indicator has been achieved.
Progress against expected results: / There has been no progress if the indicators’ are taken literally to mean ‘GDN Fellows’. However, there has been good progress in view of there being no definition of GDN Fellows (by GDN). As an interim measure GDNet has provided a number of new and interactive media services for GDN Grantees, such as blogging, video interviews and the use of Twitter to disseminate their research at key events. All Grantees’ material has been made available on-line. The results go beyond what would have been required if the only GDN Fellows’ research had been included on GDNet. / Actions: / Remove Output 4. DFID’s support is to GDNet as a programme for the availability and accessibility of southern research through good practice in research communication. / Impact Weighting (%): 0 / Revised since last Annual Review? Y / Risk: Medium / Revised since last Annual Review? N

## If the project involves more than 4 Outputs please copy the box above and paste below.
Output 5: Lessons about effective knowledge brokering in the global south learnt and communicated
Output 5 score and performance description: / A – outputs met expectation / A number of best practice products were delivered and a paper presented at the World Association of Sustainable Development (WASD) conference. For example, the GDNet study of use of web 2.0 tools by southern researchers was quoted in a Guardian online expert panel discussion (http://www.guardian.co.uk/discussion/comment-permalink/14830270 ) about using new tools to communicate research A reflective paper on ‘Capacity Building of Knowledge Management among research institutes: reflections from the GDNet experience’, was published in the World Journal of Science, Technology and Sustainable Development’
Progress against expected results: / The target for 2014 has already been met, based on the current description of the indicator. The same examples have been used for both indicators (GDNet M&E Report 2012 quest no. 3473691).There is some confusion over what the indicators actually mean, hence the reason for a duplication of results against each indicator. The programme needs to distinguish between how it communicates its lessons to others and how it uses lessons it learns from others. / The milestones for the indicators (e.g. two GDNet best practice products) are at an activity level. There needs to be an analysis of how these products contribute to both GDNet’s learning and broader debates around knowledge brokering. / As GDNet approaches its final two funding periods it is important that it thinks of its sustainability, at the same time, more organizations are entering its area of operations, and so it is increasingly important that it continues to review its niche. GDNet is about to implement two new initiatives in response to user feedback and continuous M&E. The first is a microsite, The Research Policy Linkage Think Net, which brings all of GDNet’s output areas into one single activity:. / Actions: / Revise this output to reflect GDNet as a learning institution (a ‘think net’? e.g. CEPR) and differentiate between / lessons learnt by GDNet and communicated / how GDNet learns from others and uses this learning in its development. / For DFID: to better articulate the type of lessons that DFID is interested in, for example, stories of use? Measures of research uptake, etc. / Impact Weighting (%):20 / Revised since last Annual Review? Y / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Y / 1.2 Overall Output Score and Description: / The overall output score is A - the programme met expectation. / Outputs 1 and 2 received an A, though the milestones were reached and exceeded well before the milestone date. It is unclear whether the milestones were set too low, hence the score of A, the programme met expectation. Outputs 1 and 2 account for an impact weighting of 65%. / 1.3 Direct feedback from beneficiaries / A strength of GDNet is its ability to reach young southern based researchers who are not reached by other networks. GDNet has a presence across Africa, Asia and Latin America; there is not another (networking) platform that has this outreach for southern research. The intangible social capital it has produced is its strongest point. See beneficiaries responses below in the highlights and lessons section.
1.4 Summary of overall progress / Despite a challenging institutional environment, including recent changes to the management of GDN (current President steps down in June 2012; new Head of the GDN Board, Professor Alan Winters, appointed in 2011) and uncertainty of funding to both GDN and GDNet (DGIS funding not approved post March 2012 due to the situation with the Government), GDNet has managed to remain on track and in some cases exceed expectation. GDNet is working very hard to look beyond the norm, for example, testing new ways of working with researchers such as the profile pages on the website and being much more active with social media. GDNet recently hosted the communications for the K* knowledge brokers conference, which indicates its expanding profile and work beyond the work supported through the DFID accountable grant. / Highlights and Lessons / GDNet has built up a successful reputation over the past ten years for bringing together and communicating policy-relevant research from the South. By convening opportunities, providing information and encouraging sharing and learning, GDNet has helped create an enabling environment for southern researchers to communicate their work better and more widely. GDNet has positioned itself as a leading knowledge service provider focussing on research communications from and for the South. / The GDNet Team are proud of the difference GDNet has made and six key highlights particularly stand out: / Sharing knowledge / “GDNet has helped me to disseminate my findings to people I didn’t know, who in turn, have helped my research by providing feedback on it.” Professor, Delhi / GDNet has long acknowledged the value of southern research and the distinctive contribution the southern perspective can make to the knowledge and understanding of complex issues. By providing platforms that profile their work and opportunities to engage with others, GDNet has begun to level the playing field between southern researchers and their northern counterparts. One significant accomplishment is the GDNet Thematic Windows, which were launched in 2011 and organise research papers and researcher profiles from the GDNet Knowledgebase to reflect 23 major policy and development-related topics, from agriculture to urbanization. / Linking research to policy / GDNet’s work is underpinned by the belief that good research leads to better policy-making and there is considerable demand for the training and support GDNet provides to researchers on writing for policy. Most recently, GDNet has developed with CIPPEC a series of online courses to Build Influence Plans and a special platform to debate issues of critical importance to Executive Directors of Think Tanks in Latin America, worked with the Economic Research Forum (ERF) to produce a collection of papers, policy perspectives and reports and organized a two-day workshop for Asian researchers of the PEM project on how to influence policy decisions in their respective countries with their research results. / Building confidence / “My policy worldview has been radically transformed after this course – and this will be beneficial not only to me, but my Institute." Participant in GDNet/CIPPEC Spaces for Engagement online course / GDNet’s capacity building work aims to increase researchers’ confidence and their ability to communicate their research more effectively. During the life of the program, more than 1200 researchers have benefited from regional knowledge management and regional research communications training events in Latin America, Africa, the MENA region and South Asia. Assessments of recent workshops demonstrate that they significantly increase both the confidence and ability of the participants to communicate research to policy. / Improved monitoring, evaluation and learning / In the last year, GDNet has placed a greater focus on understanding the reach and impact of its work, resulting in a baseline study of the program and a systematic monitoring and evaluation framework. The GDNet Team is also committed to reflecting on what it has learnt about good practice in knowledge brokering for the Global South and sharing its experiences and lessons as widely as possible. In 2011, this included commissioning studies, presenting at conferences, an academic journal article, network participation and social media. / Better technical support / In order to develop online services that meet the needs of an ever-growing membership, GDNet has been keeping up with the rapid changes in technological innovation. Recent examples include cloud computing expansion completed in Egypt and the UK and the GDNet Community Groups which have been engaging registered researchers through blogs, photo galleries, message boards, and more. / Working in partnership / Sharing knowledge, making a difference and fostering connections between researchers and decision-makers are at the heart of GDNet’s work. GDNet cannot achieve its ambitions alone and a core element of the program is forging suitable partnerships to extend the reach and impact its work as widely as possible. One such example is GDNet’s Latin American Partnership Program with CIPPEC that has become a valued source of expertise in the region on how to improve the use of research in public policy. / GDNet: In numbers / The GDNet Knowledgebase, an online portal to development research produced in developing countries, contains more than 17,500 research papers. / GDNet’s members include more than 12000 researchers and institutions from developing and transition countries. / GDNet provides southern researchers with free access to over 1,000 online journals. / 32,000 subscribers receive GDNet’s Research in Focus newsletter to keep them abreast of the latest policy research knowledge from the Global South.
1.5 Key challenges / The main challenge for GDNet is to assure its identity. There is still confusion over who is GDN (www.gdn.int) and who is GDNet (www.gdnet.org) and what is the relationship between the two. This is an on-going issue that is yet to be resolved. Funding is also a challenge, both for GDN and GDNet. DFID will not support (under the UK rationalisation of government websites) funding to the website (of www.gdnet.org) above 50% of overall costs. The DGIS funding has just ended and World Bank funds are diminishing. Both GDN and GDNet are actively approaching others to fund the service, but in the current climate this is a major challenge. AusAid and IDRC are both currently in discussion with GDN about funding. / GDNet can only operate from Egypt if it is registered with an existing legal entity. This is currently the Economic Research Forum (ERF). ERF has been hosting GDNet management and operations since 2002. The relationship is good, but a challenge remains in how to ensure that GDNet does not incur excessive overhead costs by working through two organisations ERF (manages local staff, salaries, the legal position of GDNet in Cairo, etc – currently 15% overheads, which the review team consider to be fair) and GDN (the DFID Accountable Grant is with GDN as the host organisation. The overhead costs must reflect the proportion of funds that go through GDN). Clarity has been sought on overhead costs and an agreement reached. / The whole open access agenda is gaining momentum. This is affecting some of the services that GDNet has offered in the past. For example, recent changes to JSTOR mean that India and Pakistan can no longer access these journals through GDNet. This is a future challenge for the programme as it prides itself on providing better access to southern researchers to scientific journals. The programme needs to assess how the changing environment of opening access will affect GDNet in the long term. / The new GDN President (will be in post from June 2012). Although the GDN Strategy was approved by the Board in 2011 for implementation, it is not unusual for a new President to have his own ideas and demand some changes. The challenge remains as to the relationship between GDN and GDNet, especially in terms of funding and strategy. There has been some concern over the past few years about the efficiency and operations of GDN based in Delhi and GDNet in Cairo. The current president feels that the relationship is not ‘fluid’ being in two locations, however it is recognised that the person heading the organisation is rather more important than the location per se.
1.6 Annual Outcome Assessment / Based on this review and achievement of outputs, we expect the programme to achieve its outcome: Diverse research and policy audiences make better use of development research from the global south. / A survey was conducted (by GNDet) as part of its regular M&E, which indicates that there is significant use of Southern Research. For the outcome there are two measures (i) Southern researchers’ use of other southern research in own research and (ii) Cases of knowledge into use in developing countries. / The year one summary for indicator 1 indicates that 64% of respondents use Southern research to a great or moderate extent. This figure comes from a web survey where respondents were asked to what extent Southern researchers use Southern research in their own work, 64% of respondents claimed that Southern research was used to a great or moderate extent. When asked to describe the type of research that they read, the most common response given by researchers is that they do not distinguish between Northern and Southern research (32%). However, the next biggest group (28%) believe they read more Northern than Southern research, followed by 27% who believe they read the same amount of Southern and Northern research. These results are very similar to the baseline year as would be expected, as any transition in the use of Southern research will be slow and dependent on multiple exogenous factors. / As with the baseline, what emerges from the results of the web survey is a nuanced picture of use – significant use of Southern research by Southern researchers but perhaps no more significant than their use of Northern research. The web survey again provided a number of interesting insights into the nature and perceptions of Southern research by Southern users and how they tend to combine use of Northern and Southern research in a complementary manner. The following responses illustrate this: “A good part of "southern research" is of very low quality, although some of it is top-notch quality. I therefore find most useful to read mainly "northern research" and the best southern research I can find.” / “Academic research on subjective wellbeing (my current area of interest) is predominantly produced in Northern academic/research organizations and CSO/think tanks.” / “Because there is little research by southern researchers that is published in internationally ranked journals I naturally tend to favour Northern research.” / These responses hint at a potentially important niche for GDNet to consider and for which it may be well suited – raising the profile of the best Southern research so that it is perceived as on a par with Northern research in terms of quality. To a certain extent GDNet already does this through its tagline to ‘showcase’ Southern research but it is not clear that GDNet’s remit covers an explicit focus on raising perceptions of quality in order to increase use. This is an issue that GDNet needs to consider in the next year. / Indicator 2 - Cases of knowledge into use in policy processes / The aim for this indicator is to develop a robust and credible portfolio of cases of knowledge into use on a year on year basis. The first set of cases will be developed in June 2012 (after the annual review). The process for developing new cases involves 3 stages which are repeated annually: / Stage 1 – Case identification from GDNet Registered Researchers - A broad number of ‘cases’ (approx. 35-50) are identified from responses to the annual GDNet user base web survey. / Stage 2 – Most significant selection and validation panels – Engaging a group of GDN A&M Finalists at the GDN Annual Conference which is held in Budapest in June 2012 to review and select the ‘most significant’ cases. The A&M Finalists panel is followed by a second panel of GDNet key stakeholders including GDNet staff and independent research communications experts to further review and select the most significant cases down to a shortlist of 8-10 cases. / Stage 3 – Development and Validation of Most Significant Cases - The authors of the 8-10 selected cases are invited to an informal telephone interview to discuss and develop their case in more detail.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y/N / Yes (for DFID funds), though there is currently a deficit in the overall programme spend due to non-renewal of DGIS funding, which ended in February 2012. / World Bank funding (via GDN) is declining and is currently around USD200,000 per year. / Concern on overhead charges of GDN for 2012, which are around 40% (as the amount is set by a figure rather than a percentage of the amount of funds managed). Alongside those to ERF (15%). ERF overhead charges are reasonable for the services they provide to GDNet (including providing a legal home for GDNet, staff salaries, etc). The overhead issue with GDN has been discussed and resolved. / 2.2 Key cost drivers / There are no anticipated changes in the near future to the cost drivers. Overhead costs to GDN have been reduced due to a change in the way they are calculated (now as a percentage of funds managed, rather than a flat rate). / The key cost drivers are: / the maintenance and cost of servers and related software – these are kept as low as possible, through competitive tendering and also through managing the service from Egypt (rather than the UK) / The team is kept small. For web work and the social media work new graduates have been sought. Existing team members have been trained and mentored to fill new and changing roles. / Flights and travel to the Headquarters in India have been reduced. / 2.3 Is the project on-track against original timescale: Y/N / Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / None. / 3.2 Where an evaluation is planned what progress has been made? / No evaluation planned this year. A small amount of funds (£15,000) has been set aside for a user satisfaction review in 2012/13.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / Low. / 4.2 Assessment of the risk level / The risk level is low, though this needs to be closely monitored over the next year as funding arrangements to GDN are uncertain. World Bank funding is diminishing and the DGIS funding to GDNet has recently ended. GDNet obtains small funds through other work, outside the direct deliverables of the programme that are funded by DFID.
Risk of funds not being used as intended / Low. / Climate and Environment Risk / Low / Institutional Risk / In June 2012 GDN should finally gain its status as an International Organisation as the Assembly will meet to formally appoint the new GDN International Organisation Board; the final step required to formally convene GDN as an International Organisation. As GDN moved out of the World Bank, it was registered as a 901C Non-for-Profit organization in the US. GDN then pursued an International Organization Status and the Agreement became effective in July 2008 with the required three countries for ratification (India, Colombia and Sri Lanka) (GDN history is detailed on http://cloud2.gdnet.org/cms.php?id=gdn_history). GDN has also been reviewing its governance structure. It is expected that in June 2012, the Assembly would meet to formally appoint the new GDN IO Board. The last step required to formally convene GDN as an International Organization. The DFID Accountable Grant is signed with GDN Inc. / The only foreseeable risk to GDNet is the funding situation of GDN, especially if World Bank funds continue to diminish and if the AusAid and IDRC funding is not approved. The question is then whether GDNet becomes a break-away organisation, or remains as an essential and necessary part of GDN.

5. Value for Money
5.1 Performance on VfM measures / The GDNet VfM indicators are based on the three Es – economy, efficiency, and effectiveness / GDNet Value for Money – Economy (Minimising the cost of resources used whilst having regard to quality) / List of examples of what GDNet does to maintain economy: / Cairo-based office costs / Employees on local salaries / Economy air fares / Outsourced IT support / Independent experts and organisational partners are contracted on a deliverable rather than input basis / Good practice in the procurement of services / GDNet Value for Money – Efficiency (The relationship between outputs and the resources used to produce them) / List of examples of what GDNet does to maintain allocative efficiency: / GDNet’s M&E system supports GDNet to: / Using VfM measures to allocate resources e.g. GDNet employs an output-based budgeting and contracting systems / Piloting new methods of enhancing allocative efficiency e.g. piloting online capacity building courses for Southern researchers / List of examples of what GDNet does to maintain comparative efficiency: / Comparison with other DFID funded knowledge services e.g. Eldis etc. / Comparison benchmarks – size of team – 8-person core team, cost per researcher trained, cost per web site visitor, ratio between salaries and activities, / Sustainability of capacity building efforts – GDNet is creating a team of Southern-based knowledge services and research communications experts in-house in GDNet. This represents a direct and sustainable resource to support Southern research in the future. / GDNet’s outsourced web and IT support is based on a UK-based cloud server for security but managed and maintained by a Cairo-based outsourced IT expert for economy and efficiency / GDNet Value for Money – Effectiveness (The extent to which objectives are achieved and the relationship) / M&E system allows GDNet to map progress at the purpose and across outputs in order to claim success but as importantly also identify constraints and learn lessons / Ensuring sustainability after programme closure / Currently establishing self-sustaining community groups / Establishing the KnowledgeBase as a global public good and long term sustainable legacy to the Programme / GDNet is very responsive to the feedback and recommendations of external reviews / The logframe is a ‘living’ management document which has been and will be revised in line with DFID Annual Review recommendations. / GDNet is run according to the principles of agile management- and can demonstrate an ability to respond quickly to change – opportunities and risks / constraints. / Measuring effectiveness - GDNet’s M&E systems support them to identify and credibly claim contribution and some direct attribution from activities / inputs up to the purpose-level in the logframe: / Purpose level case studies of knowledge into use in policy process generated through most significant change process involving GDN Awards and Medals Finalists. / Output 2 indicator 2 cases of researchers’ confidence and ability to communicate their research – ‘pledge’ indicating long-term sustainable behavioural change as a result of GDNet’s capacity building efforts. / 5.2 Commercial Improvement and Value for Money / Economy air fares and competitive procurement process. / GDNet’s outsourced web and IT support is based on a UK-based cloud server for security but managed and maintained by a Cairo-based outsourced IT expert for economy and efficiency / 5.3 Role of project partners / The proportion of funds going directly to partners to implement activities is relatively low. Partners VfM follow the same principles as those employed by GDNet and ERF. / 5.4 Does the project still represent Value for Money : Y/N / Y / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
Overall, the programme is performing well. The team in Cairo is very dedicated and enthusiastic and is led and managed by a very strong, capable and committed leader. / There are a number of recommendations under each output, which are there to guide the programme over the next year. There are specific actions which the programme needs to address in the next year. In summary: / Action for GDNet / GDNet to interrogate the webstats and explain the anomalies; GDNet to correlate the user survey with the webstats and try to explain and map the trends they should also look at comparisons to see how they compare to similar services. / Re-visit the landscape for open access (and review in light of DFID’s open access policy, World Bank Open Access, Wellcome Trust open access and others) and this increasing trend might impact on GDNet services / Hold discussions with BLDS (with DFID present if necessary) to stream the process of document delivery at zero cost to GDNet and direct billing to DFID. / Overall, review the milestones as detailed under each output and re-visit some of the analysis (especially triangulation with other sources) of monitoring results. Disaggregate figures, especially by country, region and gender. / Re-visit the milestones in view of the rapid increase and use of social media, recognising use of web 2.0 amongst researchers, especially in the South. Consider how to better showcase successes and the story of GDNet – how to build and implement a successful global network for promoting and utilising southern research. / Consider how to build and support new networks – or even an exit strategy for those that are deemed to be successful and self-sustaining. / More disaggregation and interrogation of M&E data. / Re-instate GDNet Steering Committee with representation from knowledge partners (possibly MK4D, IFPRI, INASP), regional network partners (Latin America, Africa, MENA), DFID (Potential donors NORAD, SIDA), independent relevant expertise (CommsConsult, ITAD) / Sustainability Strategy: that there is a clear strategy in place for continuation of activities beyond the DFID grant. This may include a marketing strategy to seek other donor’s support and increased capacity of the RNPs to source their own funds and become self-sustaining. / GDNet is encouraged to consider partnership opportunities with MK4D, INASP and other DFID funded programs and other knowledge intermediaries to build on synergies / Revise this output to reflect GDNet as a learning institution (a ‘think net’? e.g. CEPR) and differentiate between / lessons learnt by GDNet and communicated / how GDNet learns from others and uses this learning in its development. / For DFID / Approve budget for 2012/13 / Approve modified logframe in view of Annual Review recommendations / Engage in discusisons with NORAD and SIDA if funding is likely to assess whether a joint-donor initiative is a more suitable funding mechanism / 2013 Annual Review – expanded effort to feed into the end of program evaluation and process of GDNet strategy formulation 2015 – 2020. / It is acknowledged that stats are not easily available for comparison or benchmarking with other similar services. DFID should investigate how webstats data and other relevant M&E data from similar services (funded by DFID) might be shared. Find a mechanism to encourage better analysis and interpretation of webstats in M&E reports. / Work with GDNet on the action to better signpost similar services to and from the site (if necessary – i.e. to build relations, or make introductions with relevant programmes / services). / Better articulate the type of lessons that DFID is interested in, for example, stories of use? Measures of research uptake, etc.

8. Review Process
Visit to GDNet, Cairo from 23rd – 27th April by Abigail Mulhall (research uptake advisor / programme manager) and Rubbina Karruna (Outreach Advisor) / People met: / Dr Sherine Ghoneim, Director GDNet / Shahira Emara, / Zeinab Sabet / Maya Madkour / Dina Manaa / Haitham El Khouly / Dina Saada / Shahira Moneib / Dr Julian Barr, Director ITAD (Strategic Advisor / M&E Consultant) / Prof. Ahmed Galal, Managing Director, ERF / Phone / Dr Gerry Gerardo della Paolera, President GDN / Prof. Ernest Aryeetey, Board of Directors, GDN / Julie Brittain, INASP / Megan Lloyd-Laney, Director CommsConsult / Vanessa Weyrauch, CIPPEC – network partner