Type of Review: Annual Review

Project Title: DFID Support to the National AIDS Council - HIV Common Fund 2009 -2013

ARIES Code: 200605

Date started:	01/06/2012	Date review undertaken: 22/06/2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
DFID is supporting the Mozambique National AIDS Council (CNCS acronym in Portuguese) to coordinate the national response to HIV & AIDS in Mozambique. The Project budget is as follows: / CY 2005 2006 2007 2008 2009 2010 2011 2012 Total / Amount in £ 0,5m 1m 0,3m 0,5m 0,36m 0,36m 0,36m 0,36m 3,74m / This is the final year when disbursements will be made for this project, as DFID will be phasing out of the HIV sector as agreed in 2010 during the bilateral aid review. The project completion report will be done next year in order to report on the results from this year.

What are the expected results?
Through our support to this programme, we expect the following results: / Impact level / Contribute to the government’s Poverty Reduction Action Plan target to reduce the number of new infections per day from 500 to 350 by 2014; / Outcome level / To improve the coordination of the national response by ensuring that all stakeholders implement their HIV activities according to the national strategic plan / Output level / Coordination: Regular coordination meetings and activities enabling a multi-sectoral response to HIV / Communication: To strengthen HIV communication activities at all levels / Monitoring and evaluation: To guarantee supervisory visits and the integration of HIV indicators in all sectors / Management and financial monitoring: More effective utilisation of the resources used for HIV prevention / Indirect outputs (outside the HIV sector but contributing to the national HIV response) / Increase prevention of mother to child transmission for at least 40% of newborn children; / Increase the number of people on treatment to at least 50% of those who need it. / Results directly attributable to DFID in 2011 were : / Indicator 2011 target [1] 2011 actual Progress DFID attribution[2] / Number of children benefiting from treatment 23,053 23,818 Not met 1,153 / Number of women benefiting from prevention of mother to child treatment 70,270 81,428 Not met 3,514 / Number of adults receiving treatment 250,508 241,240 Met 12,524 / Number of condoms distributed 132,000,000 71,000,000 Not met 448,560
[1] Source: 2011 Annual Joint report for the health sector

What is the context in which UK support is provided?
HIV&AIDS continues to be one of the greatest threats to Mozambique’s development. It is estimated that 1.4 million people in Mozambique have HIV & AIDS. According to sentinel surveillance sites, the HIV prevalence for 15-49 year olds was estimated to be 15% in 2004.[3] According to a national survey (INSIDA) that uses a different methodology the HIV prevalence has levelled off at 11.5% (2009). However these national statistics mask large regional variations – from 25% in Gaza Province to 4% in Niassa Province. Furthermore, urban areas had a higher prevalence (15%) than rural areas (9%). Prevention efforts in HIV in Mozambique lag behind many other countries in the region because they were slow to start. However, as table below shows, there has been significant progress in HIV prevention awareness and treatment between 2003 and 2009. / Table 1: Information about HIV knowledge and treatment in 2003 & 2009 / Indicator 2003 (Demographic Health Survey) 2009 / (INSIDA) / % of women aged 15-49 who have the correct knowledge about HIV and AIDS 45 72 / % of women aged 15-49 who received information about HIV in pre-natal visits 3 55 / Number of health units offering treatment for HIV 24[4] 213 / Coverage of treatment for adults needing it (%) 3 37 / Knowledge about HIV prevention increased by 27% between 2003 and 2009. There has also been more integration of HIV services as evidenced by the proportion of women who get information about HIV in pre-natal visits. Treatment has also improved significantly with coverage increasing more than tenfold by 2009. / Background on the support to CNCS / CNCS was established in 2000 with the mandate to supervise, evaluate and provide orientation in relation to the multi-sectoral AIDS response. In 2006-2009, another function was added, that of manager and grantor of HIV funds to implementing agencies. This was in response to HIV receiving more resources than any other public sector programme in Mozambique. The majority of these resources were external, coming from multilaterals particularly the World Bank’s Multi-Country HIV& AIDS Programme for Africa (MAP) and the Global Fund to fight AIDS, TB and Malaria (GFATM). MAP funding alone was $55 million between 2006- 2008. These funds were channelled through a common fund which DFID joined in 2006. CNCS was not adequately equipped with the systems and capacity to perform its mandated function. Furthermore, the addition of this on-granting role resulted in CNCS giving more focus to resource mobilization and fund management for implementing organizations rather than performing their coordination role. / In 2008, disbursements from CNCS to implementing agencies declined and the project was rated as “unsatisfactory” by the World Bank. Due to poor performance, it was decided that CNCS should focus on its core mandate of coordinating the HIV response and withdraw from the function of providing grants to civil society, the private and public sectors. This mandate comprised a three pronged approach of (i) coordinating the national response, (ii) monitoring and evaluation and (iii) communication. In light of this change, both international partners and the Government of Mozambique (GoM) significantly reduced their funding to CNCS. And CNSC has gone through a process of restructuring to become more effective and more closely aligned to the government structure and payroll. Government have yet to approve this request for the integration of CNCS submitted in August 2011. / The United States Government through the Presidential Emergency Programme for AIDS Relief (PEPFAR) is a key supporter of the national response, mainly through the Ministry of Health and civil society organizations. The total amount of funding the United States provides to the national response is over $50 million annually, mostly off-budget. Another key player is UNAIDS who do not have much funding, but are respected for their leadership in this area. They also led the sector in 2009 and 2010 on behalf of partners. / The Common Fund (Canadian CIDA, Danida and DFID) will be coming to an end in 2012 as initially planned when set up in 2007. Partners are keeping to this decision given the shift in international policy to address HIV through the health sector and promote a continuum of care from prevention to treatment. Government have yet to decide who will be leading the national response. If they approve the integration of CNCS staff into the government payroll and start to fund most of the operations from 2013, then CNCS will continue to coordinate the national response. To ensure a responsible exit from the Common Fund, partners are following a dual strategy: to encourage GoM to fund most of CNCS core functions; and to encourage the US Government and UN agencies, as key players in HIV, to take more of a leading role in policy dialogue. / Reflecting CNCS’ mandate to coordinate the national response, this annual review reports not only on how well the institution performs this function, but also the role and contribution of other stakeholders (public sector, private sector and civil society) to the national HIV response with oversight from CNCS.
[3] Source: WHO Summary Country Profile for HIV/AIDS Treatment Scale Up. Mozambique, 2005
[4] Source: Report on the Millennium Development Goals , Republic Mozambique 2010

## Section A: Detailed Output Scoring

Output 1: New multisectoral strategic plan in 2009 (NATIONAL HIV PLAN), informed by good quality policy work and evidence based priority setting
Output 1 score and performance description: / C – Output did not substantially meet expectation: the national HIV plan is not being implemented in all districts and prevention activities are not yet at scale.
Progress against expected results: / Indicator 1: Inclusive participatory process used for elaborating the national HIV plan / 2011 Milestone: To ensure operational plans based on the national HIV plan are elaborated, disseminated and implemented. / Score: Partially met. The HIV plan was disseminated in all provinces to the district level. This is evidenced by the fact that civil society organizations, partners, public sector and private sector respondents all reported using the national HIV plan to define their goals and plan their activities. For example, the Ministry of Planning and Development agreed to integrate HIV & AIDS into the methodology to develop annual plans for 2012. However, the extent to which the HIV strategic plan is used tends to vary. Furthermore, each organization or Ministry tends to select the activities they will implement according to their remit rather than to focus on those defined as priorities in the plan. / It was also expected that 33 districts (three districts for each of the 11 provinces) would use the HIV plans to write their operational plans. 90% of the 33 districts were found to have written plans. Nevertheless, the level of implementation of these plans was undermined by insufficient funds available to non-state actors and the late nomination of HIV focal points in each province. / Indicator 2: National Prevention Policy/Priorities approved and implemented / 2011 Milestone: Coordination of effective prevention activities at scale / Score: Partially not met: The most cost-effective prevention methods according to the WHO include voluntary counselling and testing; treatment for people living with HIV and to prevent HIV transmission from mothers to children; the treatment of sexually transmitted infections and prevention in most at risk groups.[5] CNCS and the Ministry of Health have been doing these activities and these are increasing, albeit still at relatively low scale. However, CNCS has struggled to coordinate prevention activities with other stakeholders including the public sector and civil society. This milestone was therefore rated not met. / A main achievement has been the expansion of voluntary counseling and testing services. The number of people tested grew by 79% from 2009-2011 to 2,961,099 people last year. This growth was made possible because of the integration of voluntary counseling and testing services into other health services including laboratories, blood banks and consultation services for youth. The role of civil society in achieving this target cannot be underestimated as a third of people accessed these services in their communities. / Prevention activities with high risk groups also increased in 2011. These targeted men who have sex with men, a previously ignored group; prisoners, long distance truck drivers and defense and security forces. However, these activities were of limited coverage. For example, prevention services targeting prisoners were reported in 3 provinces (one per region in Mozambique). The lack of funding available for non-state actors and insufficient reporting of prevention activities by these to CNCS is contributing to this low coverage. / In 2011, CNCS signed an agreement with the Ministry of Health for better integration of sexually transmitted infection awareness and treatment activities between both institutions. This contributed to the number of STI cases increasing by 11% between 2010 and 2011, to over 656,000 people. / Prevention of mother to child continued to increase in 2011 with a slight increase in the number of pregnant women getting treatment from 2010. This was below the target set for 2011 which proved ambitious due to the unpredictable funding for HIV treatment provided by the Global Fund for Aids TB and Malaria (GFATM) in the last couple of years. / Challenges / The number of condoms distributed in 2011 was 71 million, 54% of numbers planned for the year. This happened because of problems in the supply chain at the Ministry of Health. As a consequence only emergency distribution took place in the latter half of 2011, and condoms were not prioritized in the distribution chain. Without an adequate supply of condoms, HIV prevention cannot be sustained in the medium term. / There is a lack of funding for implementing HIV activities at subnational level. The funding for non-state actors created by the World Bank ended in June 2011 and did not generate sufficient evidence that this mechanism was effective in managing funds for partners to want to channel their funding through it. / Recommendations: / DFID to explore alternatives to improve condom distribution with the Ministry of Health through a new contraceptive distribution pilot. / Impact Weighting (%): 25 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N
[5] Source: DFID value for money in HIV Prevention taken from HIV value for money teamsite.

Output 2: Strengthened coordination of the multi-sectoral response with the public sector, private sector and civil society and donors
Output 2 score and performance description: / B – Outputs moderately did not meet expectations. CNCS has been quite successful in coordinating all stakeholders through joint planning meetings. It has had more limited success in collating reports partly because of their limited capacity and also because their role has not been enforced by government. On a positive, note CNCS also reported not disbursing any funds to implementing partners by the end of 2011, a sign that their on-granting function has ended. However, this was foreseen for 2010 and was therefore a year late.
Progress against expected results: / Indicator 1: Coordination and Accountability structures between CNCS and other stakeholders strengthened / 2011 Milestone: CNCS establishes formal coordination and reporting activities with stakeholders / Score: Partially met: / Public sector / The following line ministries were selected by CNCS as the main implementers of the HIV national response at the national and district levels: Ministries of Health, Education, Women and Social Action, Youth and Sports, Defence, Labour and, Interior. Visits to provinces showed that these sectors do joint planning of HIV activities with CNCS at provincial levels and the HIV focal points placed in each line ministry. However, implementation is limited largely because focal points are remunerated for their other activities rather than the focal point function. In addition, most of these sectors tend not to report their activities to CNCS. Coordination among the public sector organizations is also improving. For example, the Ministries of Education, Youth and Sports, and Health are working with UNFPA to continue to deliver the multi-sectoral prevention project targeted at youth in 561 schools, representing a 9% increase from last year. Evidence shows that behaviour change communication and school based education activities of this nature are not cost-effective in preventing HIV& AIDS.[6] Although these examples show that CNCS is performing well in its coordination role, the actual contribution of these activities to the HIV& AIDS response is limited. / Another example of strengthened coordination was a workshop between the Ministry of Health and CNCS to agree on joint planning and coordination of HIV prevention, treatment and care activities. The workshop was the first initiative of this kind and agreements were made to train district HIV focal points and CNCS staff at subnational levels to provide counselling and supporting services for people considering testing or on treatment. These activities are expected to reduce the demand on health centres for counselling services. / Private sector / The private sector, represented by the network of private sector institutions combating HIV & AIDS (ECOSIDA) continued its activities. ECOSIDA reports at least once a year to CNCS and participates in key planning and reporting meetings both at central and subnational level. Last year over 29,000 private sector employees were tested for HIV and 57 HIV workplace policies were written. These policies state how organizations will prevent their employees from contracting HIV and in the event of employees being HIV positive, how they will be protected from stigma and discrimination in the workplace and have access to treatment and support. / Civil society / Civil Society Organisations continue to focus on HIV activities at the community level. They play an important role in expanding counselling and testing services at the community level. They are also involved in joint planning of activities with CNCS. Their engagement with CNCS is varied. Some do not consistently report their activities in HIV prevention, treatment and care to CNCS while others still have weak capacity to actively plan and report their activities. There is also evidence of some civil society activities stopping due to funding shortfalls since CNCS changed its mandate from sub-grantor to coordinator of the national response. These challenges in coordination are in part due to government’s ambiguous position regarding CNCS’ coordination role. All stakeholders should be obliged to report their HIV activities to CNCS at least once a year as happens in the health sector. / Partners / Coordination between development partners and CNCS has improved. For example, in 2011, three out of four planned meetings between partners and the CNCS management group took place. All the monthly partners’ forum meetings also took place. Nevertheless, none of the board meetings chaired by the Prime Minister took place. These are important because partners can discuss issues related to public financial management, and financing of the national response. To address this issue, in December 2011, partners sent a letter to the Prime Minister outlining their concerns regarding the sustainability of the national response and how to fund this once the Common Fund comes to an end in 2012. The Prime Minister is now alert to the issue and risk, but has yet to come forward with concrete solutions. / In 2011, there was more engagement of other donors beyond the Common Fund in the policy dialogue between CNCS and partners. For example, in 2011, the United States Government participated in most of the monthly meetings between CNCS and partners, an improvement from 2010. This will be important to ensure continued dialogue between partners and CNCS in 2013 after the Common Fund ends. / Indicator 2: Phasing out of on-granting work by CNCS / 2011 Milestone: CNCS no longer provides any funding to implementing agencies / Score: Met / During 2011 CNCS continued their transition from that of grant manager to coordinator of the national response. According to the annual joint review report, CNCS has stopped managing all HIV grants. In 2010 they were managing a few grants and by 2011 no grants. This transition was important because it helped to reduce the level of fiduciary risk associated with weak financial management systems among the implementing agencies and CNCS’ limited capacity to ensure that funds were used for their intended purpose. There is still a need for partners and government to set up a funding mechanism for civil society and government departments to access funding to implement cost effective HIV interventions. / Challenges / There has been limited institutional endorsement of CNCS as the coordinator of the national response by Government. This has called into question the political will of government to support CNCS as the coordinator of the national HIV response. Government has given more support to the Ministry of Health in their ability to coordinate stakeholders working in health including HIV than CNCS. / Limited technical skills have made it difficult for CNCS to coordinate all of the civil society organizations. . This is confirmed by the findings from a 2010 report on the national HIV response commissioned by the Danish Embassy: / “… on the basis of the discussions with the staff members at central level and in the two provinces it appears that the task of coordination is understood differently by different staff members. Most of the interviewed key informants relate coordination with joint planning. “[7] / Recommendations / DFID to encourage government to host a CNCS Board meeting ahead of the closure of the Common Fund in December 2012 to discuss allocation of domestic funds and sustainability of the national response for the next couple of years. / DFID to use its leverage to influence key HIV stakeholders, notably the United States Government, UNAIDS and UNICEF to take a lead in promoting dialogue between partners and CNCS. / Impact Weighting (%): 25 / Revised since last Annual Review? Y- indicator 1 is now for all stakeholders including donors and not just for private sector, civil society and public sector. / Risk: Medium / Revised since last Annual Review? N
[6] DFID analysis of systematic reviews on value for money in HIV Prevention (taken from HIV value for money teamsite).
[7] AustralCowi (2010) Overview of the HIV/AIDS Response in Mozambique: Final report. Commissioned for the Royal Danish Embassy. August. Maputo Mozambique.

Output 3: Improved accountability within CNCS
Output 3 score and performance description: / B – Output moderately met expectations: The HIV indicator is used in policy dialogue between government and donors at General Budget Support level as well as by CNCS and the Health sectors. In addition for the first time the 2012 annual plan had several indicators for each programme which will allow implementation to be assessed.
Indicator 1: Consistent use of HIV indicators across government / 2011 Milestone: Same HIV indicators used by different sectors / Score: Partially Met. / The milestone set for 2011 was to have consistent use and reporting on HIV indicators in government plans. The indicator for prevention of HIV transmission from mother to child was reported in the Annual Joint Review of the Budget support donors, the health sector performance assessment framework and CNCS in their joint annual review. Although this does not cover all sectors, it shows progress in HIV reporting as CNCS, the Ministry of Health and the Ministry of Planning and Development are being consistent in reporting HIV. This needs to be expanded to ensure that the indicators used by CNCS in their other reports are the same as those used by other line Ministries and civil society. / Indicator 2: One agreed overarching HIV performance assessment framework with supporting M&E framework / 2011 Milestone: A framework against which the annual plan can be assessed. / Score: Partially Met and on track / The HIV performance assessment framework established in 2010 was improved in 2011 with the number of indicators reduced to 4 for each of the four components of CNCS mandate. In the previous year when the framework was introduced, CNCS had 66 indicators. This was considered to be too many. A joint review of the Annual Operational Plan for 2011 was positive showing that CNCS were able to implement the national strategic plan to a large extent. The level of implementation of the different activities in the annual 2011 plan was as follows: in 80% for communication, 75% of Monitoring and Evaluation, 67% for Management and Financial Monitoring, 50% for Coordination and 33% for Capacity Building and Institutional Development. The latter performed badly because activities started later than planned. / Challenges / There is limited M&E capacity in CNCS at all levels. This has meant that: reports are not collated from all stakeholders at subnational level; reports are submitted late to the centre; reports have limited analysis; and there are few supervisory visits. / Recommendations / The HIV performance assessment framework should not have significant changes in 2012, so that progress can be compared against 2011. / Impact Weighting (%): 25 / Revised since last Annual Review? Y – This indicator used to look at results based monitoring. This is difficult given CNCS’ coordination role. Results tend to be process oriented. / Risk: Medium / Revised since last Annual Review? N

Output 4: Better planning, allocation and tracking of HIV resources in order to achieve improved outcomes
Output 4 score and performance description: / A Outputs met expectations: The annual plan had a budget broken down according to main programmes. It also had indicators for each programme. The joint annual review included civil society and private sector participation at central and subnational level. It also fed into the government review process.
Indicator 1: Annual operational plan, prioritised, costed and with clear M&E framework to review performance. / 2011 Milestone: Annual plan is costed with indicators to assess progress / Score: Met : / The annual operation plan for 2012 was submitted to partners on time. However, a slow response from CNCS to partner comments delayed approval of the final plan which in turn delayed partner disbursements. The quality of the plan for 2012 was much improved compared to the annual plan for 2011. It was more strategic, more clearly set out and included a more robust costing. It also set four annual indicators against which to assess progress in each area of coordination, monitoring and evaluation, communication, institutional development and financial management. / Indicator 2: CNCS joint planning and review processes adhere to GoM cycle / 2011 Milestone: Annual review is consultative and feeds into high level government review process / Score: Partially met / Field visits to 5 provinces for the Joint Annual Review took place on time with representation from CNCS, civil society and partners. Compared to last year, these were better planned and allowed time to design a questionnaire and interview both CNCS staff and other stakeholders at subnational level. Despite this, the review meeting only took place in the last day of the government’s Joint Annual Review process in May 2012. This was an improvement from last year when the meeting took place in September 2011. Since the draft report was available, findings were for the first time used to inform the high level dialogue. / Recommendations: / DFID to encourage CNCS to get the joint review process finalized by March of each year in order for the recommendations to be implemented within that year and for findings to feed into the General Budget Support dialogue between partners and government. / Impact Weighting (%): 25 / Revised since last Annual Review? No / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Yes / The log frame has been updated into the new excel format. The impact and outcome levels indicators were reviewed and some of the outputs adjusted to reflect CNCS’ new coordination role. / Outputs changed: Output 3 that now reads “Improved accountability within CNCS.” Previously this indicator included results based monitoring which is no longer feasible given CNCS coordination role. / Change in the wording: / Four indicators were altered to make them easier to understand. For example: Indicator 2.1 now states “Coordination and accountability structures between CNCS and other stakeholders strengthened” instead of the previous wording of “listing the stakeholders”. / Indicator 2.2 now includes donors in addition to civil society, private sector and public sector. / Output removed: Output 1.2 “Evidence of effective AIDS interventions documented and lessons shared” was removed because CNCS never reported against this indicator. Furthermore, in 2011 this indicator was removed from the performance assessment framework. / 1.2 Overall Output Score and Description: / B – Moderately did not meet expectations / CNCS has struggled to coordinate the national response. The integration of the HIV strategic plan into the planning process of stakeholders was successfully done. However, the implementation of these plans has not been consistent. Even in sectors such as health where CNCS has secured an agreement for increasde collaboration, the coverage rate of prevention activities was of insufficient scale to be effective. Reporting to CNCS by all stakeholders has been inconsistent, partially because of the institutions’ limited capacity but also because their coordination role is not acknowledged. / 1.3 Direct feedback from beneficiaries / This report is based on the HIV Sector joint review process which involved partners and other stakeholders including beneficiaries (in this case civil society organizations); other public sector institutions and the private sector. Beneficiaries’ comments were collated during the field visits to 5 provinces as part of the Annual Joint Review process. .
1.4 Summary of overall progress / Overall progress is satisfactory as evidenced by the achievement of most of the milestones set for 2011. A key issue is that prevention activities particularly among high risk groups and male circumcision are not done on a large enough scale to be cost effective. Another is that CNCS does not yet have adequate capacity to implement HIV plans and perform regular supervisory visits at the subnational level, nor to fully analyse all the information they collate from different stakeholders.
1.5 Key challenges / There is a lack of funding for implementing HIV activities at subnational level. The funding for non-state actors created by the World Bank ended in June 2011 and did not generate sufficient evidence that this mechanism could effectively manage funding for partners to want to channel their funding through it. / The number of condoms distributed in 2011, was 71 million, 54% of what had been targeted for 2011. This happened because of problems in the supply chain at the Ministry of Health. As a consequence only emergency distribution took place in the latter half of 2011, and condoms were not prioritized in the distribution chain. HIV prevention without an adequate supply of condoms cannot be sustained in the medium term. / Male circumcision is at a scale that is not sufficient to make an impact in preventing HIV. In 2011, over 20,000 males between the ages of 15-49 were circumcised throughout Mozambique contributing to 1,729 new infections being averted by 2015.[8] Male circumcision has been proven to be a cost-effective way to prevent HIV. However, it is only effective when the intervention is undertaken on a large scale. / There has been limited institutional endorsement of CNCS as the coordinator of the national response by Government. This has called into question the political will of government to support CNCS as the coordinator of the national HIV response. Government has given to the Ministry of Health more support to coordinate stakeholders working in health including HIV than CNCS.. / Limited technical skills have made it difficult for CNCS to coordinate all of the civil society organizations because of their limited technical skills / There is limited M&E capacity in CNCS at all levels. This has meant that: reports are not collated from all stakeholders at subnational level; reports are submitted late to the centre; reports have limited analysis, and there are few supervisory visits.
1.6 Annual Outcome Assessment / Based on the progress on the outputs and reading from the joint annual evaluation report for 201, targets set at the outcome level are not being achieved: / Coordination: There is a functional coordinating mechanism (CNCS Board, partners’ forum and management committee meetings, technical working groups). The number of meetings planned (in total of 20) was mostly achieved with the exception of the Board which has not met this year. This is important as it is the board that decides on policy and strategic matters particularly regarding the allocation of domestic funds to the sector which have decreased substantially. / Communication: The national communication plan was written and approved in 2011. This document outlines what partners, civil society and public sector will do in communication over the next 2 years. The process of drafting the document was inclusive, involving different stakeholders. Community authorities (traditional healers and other key informants) were targeted by interactive dialogue. The number of meetings planned (in total of 35) was fully achieved. As yet there is insufficient evidence of the effect of these meetings. / Capacity building: An internal re-structuring plan was elaborated and is in the process of approval by the Prime Minister. This should speed up the implementation of activities in the national strategic plan at provincial and at district level. At the moment implementation varies across the country and there is limited accountability of provinces for delivery and performance. An institutional development plan was developed and is in the process of being implemented. This aims to grant more autonomy to CNCS at provincial and district level to plan and implement activities. / Monitoring & Evaluation: The number of progress reports produced and published was partially met with challenges in getting reports on time and of an adequate quality to provide oversight of HIV interventions in different regions of the country.
[8] Source: http://www.jhpiego.org/en/node/1261

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / Yes, DFID disbursed £360,000 worth of financial aid according to plan. / A total of US$ 4.5 million was disbursed into the common-fund in 2011. However the overall common-fund execution has been relatively low at about two thirds of available resources. / This is largely explained by delays in donor disbursements. Around US$ 1.6 million or about 36% of total disbursements for 2011 only took place in the fourth quarter of the year. / This is likely to have contributed to a large positive common-fund balance of US$ 1.4 million at the end of the year which is accounted for in the 2012 opening balance. This corresponds to more than 4 times the outstanding positive balance registered at the end of 2010, which amounted to about US$ 304,800. / As shown in the table below, overall budget execution for the sub-sector stands at 83%, which is due to the low execution of the common-fund given that execution from other sources of CNCS funding (funds from the State Budget and from donors outside of the common-fund) was according to plan. / Table 2: CNCS budget and execution for 2011 for expenditure source and type / 2.2 Key cost drivers / Although in the CNCS initial budget proposal (contained in its Plano Economico e Social for 2011) there is a general planned budget allocation per type of expenditure and per activity, these are not reported against in the available end-of-year performance and financial reports. / This means that an analysis of key cost drivers in 2011, and of how execution performed against plan at a detailed level, is not possible with the information currently available. / The initial budget proposal suggests that, as would be expected due to the nature of CNCS activities, the key cost driver is recurrent expenditure of CNCS operations: planned expenditure on goods and services, such as equipment and consultancies accounts for 58% of total planned expenditure; salaries and per-diems for 39%; and just 3% for investment in capital goods. Part of the reason for this is that CNCS staff are not hired as civil servants as the institution is not yet fully aligned with government. Staff salaries are therefore higher than those of civil servants. The transition to integrate the institution into the public sector has taken 3 years, with the approval of the proposed organizational statutes still awaiting approval from government. / Recommendation: DFID to continue to monitor if CNCS staff are classified as civil servants and the institution’s organizational statues are approved in order to reduce the organization’s operational costs by December 2012. / 2.3 Is the project on-track against original timescale: Yes / This project is expected to finish in 2012 as originally planned. However, partners are still in discussions among themselves and with CNCS in order to ensure that the national response is sustainable and in particular that domestic resources to the national HIV response increase by 2013.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / When DFID started to channel their funding through the common fund there was little evidence about the effectiveness of different HIV prevention activities including behaviour change communication, school based prevention and prevention among people living with HIV & AIDS. These were the main activities that CNCS funded for implementing agencies. There is now strong evidence that these activities are not cost effective in preventing HIV. [9] / There was no evaluation carried out in 2011 and an independent evaluation is not planned for this project. The annual joint review for 2011 did not sufficiently look at the national response at the district level which is important given that many of the HIV prevention and treatment activities take place at this level according to the decentralisation policy. Danida carried out an overview of the HIV/AIDS Response in Mozambique in 2010. This was used during this annual review. It highlighted that the main issue in CNCS as (i) limited technical capacity (ii) limited authority to exercise its coordination mandate and (iii) limited financial resources. / 3.2 Where an evaluation is planned what progress has been made? / Does not apply
[9] DFID analysis of systematic reviews on value for money in HIV Prevention (taken from HIV value for money teamsite).

4. Risk
4.1 Output Risk Rating: Medium / The milestones for 2013 will be to ensure that DFID along with other Common Fund partners exit the sector responsibly. This will involve strengthened efforts to secure allocations from Government to the HIV sector, ensure that CNCS is accorded a clear mandate by Government to coordinate the HIV response, and ensuring that key stakeholders such as UNAIDS, UNICEF and the United States Government continue policy dialogue with government. / Political Economy risk: High / Budget allocation from the state budget to the HIV sector is not sufficient to deliver planned outputs in 2013. Since December 2011, partners have been trying to get a firm commitment from government on allocations to CNCS for 2012. The Prime Minister has indicated that government are aware that external funding to the sector next year will be low but has remained ambiguous about whether Government will increase allocations. A positive sign was the slight increase of the State Budget for CNCS in 2012. / Fiduciary Risk Rating: Medium to High / The fiduciary risk assessment commissioned by DFID in 2011 showed that not all the funds disbursed to CNCS were used for the purposes intended, adequately reported or accounted for. Note must be taken that for most of the weaknesses identified in the assessment the risks were associated with CNCS’ on-granting function that had ended by December 2011 and the financial management weaknesses of implementing agencies. The report states that “most of these risks become marginal with the change in role that is taking place in CNCS that will only be a coordinating institution”[10] Furthermore, since 2009, DFID funds had been ring-fenced to ensure that they were nolonger disbursed to implementing agencies. / Institutional risk: Medium / Limited M&E capacity will undermine CNCS ability to supervise and effectively report on HIV prevention, treatment and care activities. This risk is likely to be addressed if government commit sufficient resources for CNCS to implement their plan in 2013.
Climate and Environment Risk : Medium / Flooding or other environmental hazard disrupts service delivery and diverts resources. Mozambique is prone to natural disasters and there is now some degree of preparation for such events. The climate change programme at DFID will be working with the relevant authorities to build resilience and minimize this risk. DFID will continue to build health system capacity to monitor and respond to changes in climate sensitive health indicators, both due to episodic climate shocks and longer-term climate trends. This is key to improved resilience and adaptation. These should include the indicators that affect the national HIV response.
[10] Umarji, M.; Paulo, A. (2011) Avaliacao do risco fiduciario: Relatorio Preliminar. Relatorio para o CNCS com o apoio do DFID.MB Consulting. Maputo, Mocambique. p.4

5. Value for Money (VfM)
5.1 Performance on VfM measures / The programme did not benefit from a formal economic appraisal as it was approved prior to the introduction of the new Business Case format. / As a result, no explicit value for money (VfM) metrics that can capture the level of economy, efficiency and cost-effectiveness of CNCS’s activities, were developed and monitored throughout the life of the programme. / VfM aspects of CNCS operations are currently not reported on in financial and physical performance reports, and the information available is not sufficiently detailed to enable ex-post VfM analysis. / This is partly a consequence of the nature of many of the indicators specified in the log-frame, which does not make them amenable to this type of analysis. Targets relate more to processes (such as producing plans and reports or strengthening capacity) and coordination activities, rather than to directly quantifiable outputs and outcomes. / In any case, measuring VfM in the context of CNCS operations is extremely difficult, given that CNCS is not an implementing institution but manages the national HIV response by coordinating the planning, coordination and monitoring of programmes implemented by third parties. / CNCS used to transfer funds implementers to from the private and public sectors and CSOs, for prevention activities. Detailed appraisals and subsequent evaluations of each project funded would be necessary to arrive at some firm conclusion with respect to the VfM of the activities implemented by these actors, and indirectly of CNCS as the agency deciding on funds allocations. This has not been done. / Although CNCS budget attempts to cost activities at a general level, the annual activity reports do not provide details on actual expenditure by activities. Only a very aggregate economic classification of expenditure is provided in GoM’s financial execution reports. / 5.2 Commercial Improvement and Value for Money / All procurement undertaken by CNCS, including Common Fund resources, is carried out in accordance with the government’s rules and procedures. A procurement audit is currently being undertaken in the sector to be made available before the end of the year. This should highlight weaknesses in procurement and make recommendations for how to strengthen them. / Low budget execution suggests weak capacity to manage large amounts of funds and limited capacity to write and submit narrative and financial reports on time. This has contributed to delays in disbursements by donors. A recent fiduciary risk assessment commissioned by DFID also raised concerns about financial management and internal controls (the overall risk was rated as substantial). / Weak financial management and accounting capacity was identified as an issue especially at the level of implementing agencies at provincial and district level. / 5.3 Role of project partners / CNCS is responsible for coordinating the national response to HIV&AIDS through programmes implemented by third parties such as Government entities (eg. Ministries), national and international NGOs, line ministries, the private sector and Civil Society Organisations (CSOs). / At provincial level, CNCS is represented by the Provincial AIDS Nuclei responsible for collating reports from implementing agencies and coordinating the national response with all stakeholders. Focal points in each line ministry have also been appointed at all levels. These are responsible for overseeing HIV prevention and awareness activities. Oftentimes these tasks are in addition to their other functions. / DFID and other Aid Agencies (Canadian CIDA and Danida) are responsible for the provision of financial aid into a common-fund, and joint monitoring with the government. GIZ provides funding and technical assistance for institutional development at the subnational level. / 5.4 Does the project still represent Value for Money : N / As mentioned earlier, no hard evidence is currently available to assess the VFM of the programme against ex-ante agreed benchmarks. As DFID has now made its last disbursement to the programme it is not considered worthwhile (and may not be accepted by the partner) to develop a set of metrics with which to monitor VfM in future. / Evidence shows that investing in AIDS prevention and awareness-raising represents good value for money, and offers excellent rates of return given the huge economic costs of HIV&AIDS to society. According to WHO estimates, in 2004 HIV&AIDS accounted for 22% and 25% of total Mozambican DALYs[11] and deaths respectively. As manager of funds for HIV until 2008 and coordinator of the national response, CNCS played a positive role in enabling the incidence and prevalence curves to finally plateau after 9 years of steady increase. In recent years, the new infection rate and HIV prevalence has somewhat stabilised in Mozambique at 11.5% (INSIDA 2009). However note must be taken of the fact that despite the large resources channelled through CNCS, the evidence suggests that behaviour change communication and focusing on most at risk groups at a small scale are not effective HIV interventions. Only some of CNCS’ interventions such as peer to peer support are cost effective.[12] / However, the majority of cost effective interventions for HIV prevention and treatment (such as the provision of anti-retrovirals for people living with HIV; prevention of transmission from mother to child; voluntary counselling and testing and the treatment of STIs) are being undertaken by the Ministry of Health.[13] There is a lack of evidence that coordinating the national HIV response is effective in preventing HIV. The savings in terms of new infections averted are to be attributed not to CNCS but to the Ministry of Health. DFID’s decision to phase out of HIV and continue to address it through our support to the Ministry of Health is therefore good value for money. / 5.5 If not, what action will you take? / DFID will be phasing out of HIV at the end of 2012 and addressing HIV through the health sector. The Ministry of Health is responsible for implementing cost effective HIV prevention, treatment and care activities at a national level. They will also continue to collaborate with CNCS.
[11] DALY – Daily adjusted life years – the health gap in terms of potential years of life lost due to ill health or death
[12] DFID analysis of systematic reviews on value for money in HIV Prevention (taken from HIV value for money teamsite).
[13] DFID analysis of systematic reviews on value for money in HIV Prevention (taken from HIV value for money teamsite).

6. Conditionality
6.1 Update on specific conditions / Summary Assessment of Shared Partnership Commitments / 1 Commitment to poverty reduction and the MDGs: / Mozambique has averaged an annual growth rate of over 7% in the last 10 years. However, there is evidence that poverty reduction has slowed down in recent years with renewed focus from government to reduce poverty. Progress towards the MDGs is mixed. Support to CNCS was to contribute to the achievement of MDG 6 to halt and reduce the prevalence of HIV & AIDS which is happening with the stabilisation of the epidemic. Despite rapid progress in treatment, prevention efforts have not been at a sufficient scale to get consistent condom use and reduce HIV incidence in the transport corridors. However, the expansion of voluntary counselling and testing sites is an encouraging sign that government are doing more to address prevention. / 2. Commitment to uphold human rights and international obligations: / Human rights in Mozambique has been been classified as “partly free” by Freedom House.[14] The government is focused in improving people’s access to justice and is determined to place at least one judge in each of the main districts throughout the country. A human rights commission was set up in April 2012 to monitor human rights in the country as country as part of a regional initiative. / 3. Commitment to strengthening PFM and fighting corruption: / Fiduciary risk in HIV has reduced with CNCS ending the management of projects in 2011. However, the sector is still classified as medium to high risk. In 2011, CNCS showed greater commitment to strengthening their financial management systems by addressing almost all the audit annual recommendations by December 2011. / The Ministry of Finance is responsible for implementing PFM reforms across government. In 2011,PFM was one of the main issues discussed in General Budget Support dialogue with government. / 4. Commitment to strengthening domestic accountability: / CNCS has increased its accountability by allowing the active involvement of civil society in the monthly meetings with partners as well as the annual joint review process. However, this involvement is limited to these fora and there is little consultation in budget formulation, activity implementation and reporting.
[14] Country ratings and status, FIW 1973-2011 (EXCEL); http://www.freedomhouse.org/report-types/freedom-world

7. Conclusions and actions
CNCs has improved its coordination of the national response in the last year. It managed to meet most of the milestones for 2011 including greater collaboration with the Ministry of Health, an increase in prevention activities targeting high risk groups and joint planning with all stakeholders at subnational level. / This was achieved despite the capacity constraints in monitoring and evaluation and insufficient funding for the implementation of the operational plans at district level. The ending of the Common Fund which supports most of its operational costs will exacerbate this situation if government does not increase allocations to the sector. Part of DFID’s exit strategy is to influence government to continue support to the national response, preferably through CNCS. / DFID will not make any further disbursements to CNCS and will phase out of the sector in 2012. This was a decision made in 2010 during the bilateral aid review process. HIV & AIDS will be addressed through the health sector which is more cost-effective. In 2012 the focus will be on exiting the sector responsibly by trying to get government to: allocate a greater share of domestic resources to the sector; integrate CNCS staff into the government payroll; and acknowledge CNCS as coordinator of the national HIV response at all levels. In addition, DFID will use its leverage to get key stakeholders in HIV, notably the United States Government and UNAIDS, to take a lead in HIV policy dialogue and coordination. In 2013, DFID’s engagement in the sector will centre on monitoring activities delivered with 2012 funding and ensuring timely efforts to advocate for government to clarify the mandate for CNCS and for USAID and UNAIDS to take an active lead in coordinating the HIV response by partners. / Recommendations / DFID to explore alternatives to improve condom distribution with the Ministry of Health through their contraceptive distribution pilot. / DFID to encourage government to host a CNCS Board meeting ahead of the closure of the Common Fund in December 2012 to discuss allocation of domestic funds and sustainability of the national response for the next couple of years. / DFID to use its leverage to influence key HIV stakeholders, the United States Government, UNAIDS and UNICEF to take a lead in promoting dialogue between partners and CNCS. / The HIV performance assessment framework should not have significant changes in 2012, so that progress can be compared against 2011. / DFID to oversee that CNCS staff are classified as civil servants and that the institution’s organizational statues are approved by the end of 2012 in order to reduce the organization’s operational costs. / DFID to encourage CNCS to finalize the joint review process by March of each year. This will ensure that recommendations from that year will be implemented within that year and findings will feed into the General Budget Support dialogue between partners and government.

8. Review Process
This review was conducted by the Health Adviser with inputs from inside DFID Mozambique. It was preceded by the logframe review exercise which was led by the Office Results Manager. The key sources of information were the: / CNCS 2011 Joint Annual Review report; / CNCS Activity Plan for 2011. / Aide Memoire of Workshop between CNCS and Health Sector for more complementarity and optimization of resources at provincial and district levels (June 2012). / CNCS Fiduciary Risk Assessment Report (2011) / Mozambique report on the MDGs (2010) / Overview of the HIV/AIDS Response in Mozambique (2010) Austral Cowi / DFID analysis of systematic reviews on value for money in HIV Prevention