Type of Review: Annual Review

Project Title: iiG: Improving Institutions for Pro-poor Growth (Oxford)

Date started: May 2012	Date review undertaken: 28 June 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
Improving Institutions for Growth (iiG Oxford) is a DFID-funded Research Programme Consortium (RPC). It was launched for a five year period in January 2007 with an allocation of £2,749,891. In July 2011 approval was given to extend the project to December 2013 and provide additional funding of £1,085,042 to support an extension to the programme’s work. Total funding now stands at £3,834,933. / In addition to DFID, the William and Flora Hewlett Foundation and the Open Society Institute provided funding to the project.

What are the expected results?
Phase 1 / To provide governments and civil society in Africa and Asia, and development agencies, with usable and useful knowledge as to how institutions can be redesigned so as to be more conducive to growth and empowerment. / Phase 1 focused on three themes: / Institutions to promote manufactured exports / Institutions for accountability / Institutions for rural development and empowerment / Phase 1 is producing outputs which include: / An accessible body of research output for skilled policy makers on the themes of the RPC / Accessible, non-technical output based on the research on institutions, growth and poverty. / New comparative and context specific quantitative data sets on institutions. / Strengthened capacity of partner institutions in RPC, especially in Africa, in analyzing the role of institutions and their reform for growth and poverty. / Phase 1 is expected to complete delivery of its outputs by September 2012. / Phase 2 / The research programme extension will study various means by which private sector activity and markets can assist growth and development in Africa, and the institutional constraints affecting this. The research will study three closely-related issues that are central to understanding the potential for market-led development in Africa: / what are the constraints to firm expansion in Africa? Does firm size matter for performance, and how can small firms grow large? / What role does innovation and entrepreneurship play in determining firm success? Can an entrepreneurial class be fostered? / What are the institutional constraints to making markets work better for growth in Africa? Can emerging private markets help to overcome failures in factor and output markets to ensure that markets work for the poor? / The research will focus on a range of projects aimed to provide strong and convincing evidence on these hypotheses. It will, in many cases, build on other work already happening/being funded and use the extensive research network that exists at the Centre for the Study of African Economies (CSAE). / An important part of the work will be to generate papers for dissemination. As well as producing a further 6 to 10 journal articles and 10 to 15 working papers, iiG will develop 3 specific synthesis papers on the three sub-themes.

What is the context in which UK support is provided?
Phase 1 / The following lines from the original submission[1] outline the context in which the decision to fund was first taken: / The programme fits with DFID’s overall objective for research ‘to promote the production and uptake of technologies that will contribute to poverty reduction and achievement of the MDGs’. Nearly 60% of poor people outside India and China live in states affected by conflict or failing institutions. In many countries, public services do not work, states struggle to manage social tensions, and governments fail to secure broad and sustainable development for their citizens. / The evidence increasingly suggests that weak states represent both (i) the biggest challenge to achieving the MDGs and (ii) the greatest potential for increased global conflict and instability. Research on situations where states do not work for the poor is one of the priorities under the Research Funding Framework 2005 – 2007 and builds on some of the earlier work on ‘Drivers of Change’ in countries’ national development and poverty reduction strategies. / Phase 2 / High policy relevance is given to a Private Sector Development research agenda in DFID’s corporate objectives. As set out in DFID’s Structural Reform Plan, under ‘wealth creation’ private sector development has become a key priority. The extension to the programme is focusing on carrying out further work on firm development. Research on firm development has been slower to develop under the existing iiG programme and remains under-researched in general. A series of new opportunities for relevant and high quality research in firm development have been identified. A focus on firms will also complement our overall research programme in the area of growth and developing work on Private Sector Development.
[1] Quest doc. 1542299

## Section A: Detailed Output Scoring

Output 1: Research on links between institutions, growth and poverty, quantitatively validated and with specific recommendations for institutional and policy design.
Output 1 score and performance description: / A – broadly on track, exceeding target on working papers but care to maintain throughput to journal publication going forward. Action needed to make datasets available.
Progress against expected results: / Indicator Milestone (Dec 2011) Achieved / 1a Number of papers accepted for publication in peer-reviewed journals 30 29 / 1b Number of papers submitted for publication in peer-reviewed journals 10 4 / 2 Number of working papers, book chapters and research reports 25 41 / 3 Number of datasets 3 1 / iiG has almost met the milestone for indicator 1 (publication), supplementing the 27 papers at last annual review with the 2 below. In addition there are 4 papers at the revise and resubmit stage. Although this pipeline is somewhat below the milestone target of 10, there should be future submissions from among the abundant supply of working papers. / Paul Collier and Tony Venables, 2010 "International Rules for Trade in Natural Resources", Journal of Globalization and Development, volume 1, Issue 1 Article 8 / Erlend Berg, Maitreesh Ghatak, R Manjula, D Rajasekhar and Sanchari Roy, 2011, "Implementing Health Insurance: The Rollout of Rashtriya Swasthya Bima Yojana in Karnataka”, Economic and Political Weekly, XLVI(20) / iiG had already exceeded the target for working papers etc. at the last review – and has continued to do so with a further 14 papers: / Rocco Macchiavello & Ameet Morjaria: "The Value of Relational Contracts: Evidence from a Supply Shock to Kenyan Flower Exporters" forthcoming / Christopher Ksoll, Rocco Macchiavello, Ameet Morjaria, "The Effect of Ethnic Violence on an Export- Oriented Industry". BREAD Working Paper 287 , November 2010 / Tessa Bold, Mwangi Kimenyi, Germano Mwabu and Justin Sandefur. "Does Abolishing Fees Reduce School Quality? Evidence from Kenya. CSAE WPS/2011-04 / Munshi Sulaiman. "Incentive and crowding out effects of food assistance: Evidence from randomized evaluation of food-for-training project in Southern Sudan. Economic Organisation and Public Policy Discussion Papers no.19, December 2010. / David Donaldson, "Railroads of the Raj: Estimating the Impact of Transportation Infrastructure", October 2010. NBER Working Paper No. 16487, October 2010 / Oriana Bandiera, Robin Burgess, Markus Goldstein, Selim Gulesci, Imran Rasul and Munshi Sulaiman, "Intentions to Participate in Adolescent Training Programs: Evidence from Uganda". ELSE Working Paper #355. 2010. / Tessa Bold, Mwangi Kimenyi, and Germano Mwabu, Justin Sandefur. "Why did abolishing school fees not increase public school enrollment in Kenya?" CGD Working Paper 271, October 2011. / Tessa Bold, Mwangi Kimenyi, Germano Mwabu, Justin Sandefur, ""The High Return to Private Schooling in a Low-Income Country"". Center for Global Development Working Paper 279, December 2011." / Raymond Guiteras, “Eliciting and Utilizing Willingness to Pay: Evidence from Field Trials in Northern Ghana,” University of Maryland Working Paper. / Oriana Bandiera & Niklas Buehren & Robin Burgess & Markus Goldstein & Selim Gulesci & Imran Rasul & Munshi Sulaiman, 2012. “Empowering Adolescent Girls: Evidence from a Field Experiment in Uganda”, mimeo. / Oriana Bandiera & Robin Burgess & Selim Gulesci & Imran Rasul & Munshi Sulaiman, 2012. “Can Basic Entrepreneurship Transform the Economic Lives of the Poor?”, mimeo, LSE. / Erlend Berg, Sambit Bhattacharyya, Rajasekhar Durgam and Manjula Ramachandra. Can rural public works affect agricultural wages? Evidence from India. / Barr, A. and A. Zeitlin 'Conflict of interest as a barrier to local accountability', CSAE Working paper WPS/2011-13 / Tessa Bold, Mwangi Kimenyi, Germano Mwabu, Alice Ng'ang'a and Justin Sandefur 'Interventions and institutions: Experimental evidence on scaling up education reforms in Kenya / iiG had already published a dataset from Kenya on its website. The dataset for Bangladesh has been delayed but should be available soon once the data has been cleaned. The Ethiopia survey work has been severely delayed and is unlikely to be available soon. iiG is somewhat behind on this indicator, but the logframe notes the risk of delay to the survey work. Moreover, iiG has committed to providing additional datasets from other projects – specifically 2 political economy projects in Nigeria and Uganda/Tanzania education work. There was also agreement that iiG would move to publish datasets wherever possible and do so on a separate data section of the project website. / Recommendations: / To maintain the pace of journal submission from the (strong) remaining pipeline. / To make the Bangladesh and additional datasets (Nigeria, Uganda/Tanzania) available as soon as possible. They should appear, with the Kenya dataset, on a dedicated area of the website. In the long-run all data collected by the project should appear there. / Impact Weighting (50%): / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 2: Strengthened capacity of partner institutions in RPC in analyzing the role of institutions and their reform for growth and poverty.
Output 2 score and performance description: / A – far exceeding working paper targets, but care with same issue as O1 on publication. Somewhat slow to spend, (but we’ll drop this input-based indicator).
Progress against expected results: / Indicator Milestone (Dec 2011) Achieved / 1a Number of papers with co-authors from partner institutions published in peer reviewed journals, book chapters and in working paper series 10 19 / 1b Of which: number of papers with co-authors from partner institutions published in peer reviewed journals 4 3+1* / 2 Spend on developing country partners £899,636 £682,556 / In addition to the 8 papers (2 of which published in journals) at last review, iiG has produced a further 11 papers with co-authors from developing country partners, one of which has been published in a peer-reviewed journal (in bold): / Tessa Bold, Mwangi Kimenyi, Germano Mwabu and Justin Sandefur. "Does Abolishing Fees Reduce School Quality? Evidence from Kenya. CSAE WPS/2011-04 / Munshi Sulaiman. "Incentive and crowding out effects of food assistance: Evidence from randomized evaluation of food-for-training project in Southern Sudan. Economic Organisation and Public Policy Discussion Papers no.19, December 2010. / Erlend Berg, Maitreesh Ghatak, R Manjula, D Rajasekhar and Sanchari Roy, 2011, "Implementing Health Insurance: The Rollout of Rashtriya Swasthya Bima Yojana in Karnataka”, Economic and Political Weekly, XLVI(20) / Tessa Bold, Mwangi Kimenyi, and Germano Mwabu, Justin Sandefur. "Why did abolishing school fees not increase public school enrollment in Kenya?" CGD Working Paper 271, October 2011. / Tessa Bold, Mwangi Kimenyi, Germano Mwabu, Justin Sandefur, "The High Return to Private Schooling in a Low-Income Country". Center for Global Development Working Paper 279, December 2011. / Raymond Guiteras, “Eliciting and Utilizing Willingness to Pay: Evidence from Field Trials in Northern Ghana,” University of Maryland Working Paper. / Oriana Bandiera & Niklas Buehren & Robin Burgess & Markus Goldstein & Selim Gulesci & Imran Rasul & Munshi Sulaiman, 2012. “Empowering Adolescent Girls: Evidence from a Field Experiment in Uganda”, mimeo. / Oriana Bandiera & Robin Burgess & Selim Gulesci & Imran Rasul & Munshi Sulaiman, 2012. “Can Basic Entrepreneurship Transform the Economic Lives of the Poor?”, mimeo, LSE. / Erlend Berg, Sambit Bhattacharyya, Rajasekhar Durgam and Manjula Ramachandra. Can rural public works affect agricultural wages? Evidence from India. / Barr, A. and A. Zeitlin 'Conflict of interest as a barrier to local accountability', CSAE Working paper WPS/2011-13 / Tessa Bold, Mwangi Kimenyi, Germano Mwabu, Alice Ng'ang'a and Justin Sandefur 'Interventions and institutions: Experimental evidence on scaling up education reforms in Kenya / In addition to the 3 published so far, there is a paper with a co-author from a partner institution at the revise and resubmit stage. Including this, iiG is on-track against indicator 1b, but there is evidently some lag between completion of a paper and publication, as the strong pipeline has been relatively slow to produce publications. / The project has spent somewhat less than its logframe milestones, although the pace has increased in recent years. Evidently, this has not hindered the project’s output of research papers, while feedback from some of the partner research institutions in developing countries has highlighted the strong relationships between local researchers and UK-based academics. / Recommendations: / To revise the logframe for output 2, as follows: / Indicator 1 milestones relating to phase 2 reworded to clarify number of publications. / Indicator 2 (spend) scrapped for phase 2 as it is input-based and not greatly informative. / Impact Weighting (%): 10% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 3: Research on links between institutions, growth and poverty, quantitatively validated and with specific recommendations for institutional and policy design, with a clear gender dimension
Output 3 score and performance description: / N/A (A for purposes of scoring) as no milestones yet due. iiG has been selected as a case study in RED’s gender stocktake because it has performed well in mainstreaming the study of gender dimensions of its work where relevant. There is a strong pipeline for phase 2.
Progress against expected results: / No milestones are yet due, but iiG phase 1 has delivered a series of papers with a strong gender component from a number of projects: / Human Capital, Financial capital, and the Economic Empowerment of Female Adolescents: Evidence from a Randomized Intervention in Uganda and Tanzania / Female Empowerment through Inheritance Rights: Evidence from India / Evaluating the Impact of Relief Teachers on Academic Achievement in Kenyan Primary Schools – data on teachers & students disaggregated by gender / Elections, Ethnic Polarisation and Management Post-Electoral Conflict In Kenya – sex-disaggregated dataset on voting intentions / In addition it has produced a policy brief summarising its findings on gender. / There is also forthcoming work from the following projects: / Gendered labour market effects of the asset transfer experiment in Bangladesh / Innovation, social contracts and business acumen: a field experiment in Ghana / Gender, property rights, credit markets and business outcomes in urban Tanzania / Recommendations: / Discussed the pipeline for phase 2 and it seems there are lots of opportunities for gender to be addressed. iiG has been praised for the amount of work it has produced with a gender dimension and it will be important to maintain the momentum in phase 2. / Impact Weighting (%): 15% / Revised since last Annual Review? Y (new output) / Risk: Low / Revised since last Annual Review? Y (new output)

Output 4: Effective communication of research outcomes
Output 4 score and performance description: / A+ iiG has already exceeded the targets for phase 1. Delivery of the final phase 1 briefs and an event at DFID will bring this to a conclusion soon.
Progress against expected results: / Indicator Milestone (Dec 2011) Achieved / 1 Number of briefing papers on research outcomes 20 26+4 / 2 Number of workshops with at least 5 relevant stakeholders 4 18 / 3 Project website, kept up to date All briefing papers, data and research papers available on website in structured form. Yes, but see recommendations / iiG is far exceeding both the briefing and workshop targets. In addition to the 17 briefing papers produced at last review, iiG has completed a further 6: / "The consequences of crime", iiG Briefing Paper 15, October 2011 / "Raising revenue to reduce poverty", iiG Briefing Paper 16, October 2011 / "Insurance products for the poor should not be poor products", iiG Briefing Paper 17, November 2011 / "When does community monitoring improve school performance?", iiG Briefing Paper 18, December 2011 / "Aspirations matter: Shaping aspirations can play a crucial role in enabling people to pull themselves out of poverty", iiG Briefing Paper 19, February 2012 / "How to improve knowledge and take-up of public services by the poor: The case of the RSBY National Health Insurance in India", iiG Briefing Paper 20, March 2012 / These have been disseminated at conferences and are available on the website. / In addition, it has prepared 4 policy lessons papers. The lessons papers have been praised for locating iiG’s work in the broader evidence base, but in some cases the policy prescriptions could be more focused. A final 2 case studies highlighting iiG’s work on gender are now due. / The target for workshops had already been exceeded at last review. Since, a further four events have been held: two policy seminars in Kampala on education and youth, workshops attached to the iiG conference and the CSAE conference. / The website is clearly structured and largely up-to-date. Presentations from the iiG conference need to be uploaded, and there appear to be a few missing/broken links to some pages, but these minor issues should be easy to resolve. A data section of the website should be created as originally planned (see output 1). / Recommendations: / We agreed final communications deliverables as phase 1 concludes. iiG will deliver 2 policy seminars at DFID on 4 July, and produce 2 case studies covering their work on gender. / Address the minor website issues and set up a data page. We also agreed to use the CSAE blog where possible to promote findings from iiG research and raise the profile of the programme. / We agreed that 2 of iiG’s future policy briefs will cover: / Gender aspects of private sector development / Poverty and job creation / We should consider revising the logframe indicators under output 3 to clarify what the milestones are (and possibly revise them). / Impact Weighting (%): 25% / Revised since last Annual Review? Y (previously 35%) / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? Y / Logframe was updated at last review. We propose some further updates following the review, largely cosmetic/proof-reading but also substantive changes to indicators and milestones under output 2 and possibly 4. / 1.2 Overall Output Score and Description: / A – the project is on track to deliver against its targets, and is exceeding them in some areas, although outputs have been delayed in others. With some minor improvements the project will be well placed to achieve A+/A++ at the phase 1 completion review. / 1.3 Direct feedback from beneficiaries / Mukhtar Ogle, National Coordinator and Principal Examinations Secretary, Kenya National Examinations Council (KNEC), said that iiG’s research had informed the debate around a controversial issue (contracting of teachers), engaging officials and prompting government consultations. He said it was novel for the government to use top-quality research to inform its practices and that iiG had inspired KNEC to carry out further policy evaluations.
1.4 Summary of overall progress / The project is performing well, as reflected also in work not captured by the logframe: a successful, well-attended conference attached to CSAE 2012; the work on policy lessons papers and blogs, and the planned event at DFID in July to share the programme’s findings. / Next steps are: / to bring phase 1 to a conclusion: (final deliverables July, bar delayed work due to conclude September 2012) / Phase 1 completion review by January 2013
1.5 Key challenges / The key challenge for the programme is to maintain the same rate of research output as it enters phase 2, and to ensure that it keeps up the pace of journal submission of working papers etc. Gender will be a key aspect of work in phase 2 and it will be important to ensure that the programme continues to build on the good experience of phase 1.
1.6 Annual Outcome Assessment / Indicator Milestone (Dec 2011) Achieved / 1 Number of major policy changes related to institutional design in the context of growth and poverty reduction. 3 3 / 2 Number of cases of significant impact on institutional design debates in the areas of the programme: / - governance and accountability / - firm development and exports / - institutions for inclusive growth in poor settings 5 5 / In addition to previously reported policy changes on EPA rules of origin and Indian economic liberalisation, there is now a third policy change attributable to iiG’s research. Work on India’s RSBY health insurance scheme had been implemented in collaboration with government (in particular the Department of Labour) and had also generated significant press attention. This strategy has succeeded in influencing the future contract design of RSBY. In particular, research findings had shown low levels of take-up amongst the poor covered by the scheme. This was partly because the concessionaire insurance companies implementing the scheme had no incentive to provide information to ensure it was actually utilised. The design has now been altered so that the premium paid to the insurance concessionaire falls if utilisation falls below a certain rate. / In terms of influencing debates at the last review 2 clear examples were educational reform in Kenya and agricultural strategy in Ethiopia. One new example is press coverage of iiG’s findings on security in Lagos – the state’s governor, Fashola, has said that findings revealing the importance of investment in security to growth were, “at least a reinforcement of the innovative thinking of this government to set up the State Security Trust Fund…”[2]. / In the context of the lively debates surrounding India’s rural work guarantee (NREGA) press articles have been reporting iiG’s findings that, “rural public works constitute a potentially important anti-poverty tool.”[3] / Finally, iiG’s work on education in Uganda has culminated in seminars with the participation of ministers and senior officials, as well as detailed press coverage[4].
[2] “Fashola gives security equipment, 300 trained police drivers to command”, PM News Nigeria, 25 October 2011
[3] “NREGA2.0: Does it have what it takes to be the poor’s portal to a brighter future?”, Times of India, 10 June 2012
[4] “Higher pay not top on teachers’ priority list, says research report”, Mwalimu, Dec 2011 gives a detailed account of the research findings

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / Yes, on track against forecasts as recorded in ARIES. / 2.2 Key cost drivers / The key cost driver is (direct) research costs (i.e. fieldwork). / 2.3 Is the project on-track against original timescale: Y / Project broadly on-track, with a few deliverables pending, against the current logframe. The original project life has been extended to both complete phase 1 and carry out a second phase of work focusing on the private sector until December 2013. We discussed the need for any extension to the programme but it’s too early for this to be clear.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / No new evidence is available that fundamentally challenges the rationale for this research programme / 3.2 Where an evaluation is planned what progress has been made? / Phase 1 review will involve peer review using a (lone) consultant. We discussed and agreed an outline plan for the end of phase 1 review, including documents to deliver: / Phase 1 report (annual report format) / Financial reports (to cover whole of phase 1) / More systematic consultation with beneficiaries / Peer review process / The review will be completed by the end of January 2013.

4. Risk
4.1 Output Risk Rating: Low / 4.2 Assessment of the risk level / Risks were considered during discussion of the logframe, with staff agreeing that the risks originally identified had not changed materially and the appropriate output risk level remains low.
Risk of funds not being used as intended / We judge these risks to be low in this case. The University’s Financial Regulations contain various provisions to prevent “leakage” and highlights the need for the university’s purchasing activity to leave an audit trail. / 4.4 Climate and Environment Risk / Climate change and environment risks and impacts: C (no/low risks) / Climate change and environment opportunities: C (no/low opportunities)

5. Value for Money
5.1 Performance on VfM measures / The project is delivering to cost, and administration costs are in line with our other research programmes. / 5.2 Commercial Improvement and Value for Money / Under the University of Oxford’s Financial Regulations, iiG must follow the approved ordering process, including seeking value for money from suppliers. / 5.3 Role of project partners / No longer active. / 5.4 Does the project still represent Value for Money : Y / 5.5 If not, what action will you take?

6. Conditionality
N/A

7. Conclusions and actions
The project continues to perform well, with a few final improvements to be made to strengthen its preparations for the end of phase 1 review in January 2013. The project has delivered an impressive volume of research output and has engaged deeply with policymakers to encourage the uptake of its findings, with clear examples of policy impact. The programme has worked successfully with developing country partners, and has embraced the gender dimension to its work. / Going forward the project should be careful to maintain the momentum in the research programme, particularly ensuring there is a healthy pipeline of papers for journal submission. It should also make sure that all outputs are available on the project website. / Key actions are: / July 2012 – DFID policy seminar / July 2012 – discuss and agree revisions to logframe / Aug-Dec 2012 –phase 1 review

8. Review Process
Primarily desk-based review, supplemented by attendance at the iiG conference in April 2012, phone interviews with stakeholders and meeting with project team.