Type of Review: Annual Review

Project Title: MPRLP II

Date started:	June 2008	Date review undertaken:
- Impact Assessment Study: Feb – April 2012
- Field visits: 26-28 March;
- Wrap up session: 17-18 April 2012; and
- Lesson learning workshop: 10 May 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
DFID is providing £45 million to the Madhya Pradesh Rural Livelihoods Programme (MPRLP: Phase II) for the Government of Madhya Pradesh (GoMP, India) to sustainably enhance livelihoods of the rural poor in the state. The programme (ending in June 2013) will directly and indirectly reach over 2.3 million poor people spread over 9 poorest tribal districts. Lessons from the programme will inform a new Government of India (GoI) flagship programme - the National Rural Livelihoods Mission (NRLM), which will operate across the country. NRLM is expected to roll out in Madhya Pradesh (MP) during 2012.

What are the expected results?
Impact of the Programme / Overall recommended score: A / Phase 2 of MPRLP is directly and indirectly improving the livelihoods of over 2.3 million men and women in the project area by end of project. The key outcome of the project is to ensure effective policy, institutions and programmes that sustainably enhance the livelihoods of the poor rural people in 9 tribal districts of MP (see figure 1). At the policy and advocacy level, the project has envisaged better resource mobilization and improved uptake of funds by the Gram Panchayat (GP). Along with this the project has also envisaged a reduction in the population below poverty line, besides improved food security in the state. / Figure 1: Map of MP highlighting 9 MPRLP Districts / The key impacts of the project are: / A significant impact on poverty reduction for the poor and poorest (using both income and well-being measures) and reduced distress migration: / Income measures: By end of project (EoP), against a target of 31% of poor households, the percentage of poor MPRLP households is expected to be about 33%, compared to 36% of the control group. The reductions in both cases are from a baseline of 51%. Overall therefore, there is expected to be an 18 % reduction in income poverty for MPRLP households (HH) and a 15% reduction in the control villages. Although the MPRLP percentage is likely to be below the target set, MPRLP villages fared significantly better than the control. / Well-being ranking (WBR): Overall, the percentage of households belonging to C (poor) & D (poorest) category have declined from the baseline of 63% to 40% (i.e. a 23% decline at EoP). Correspondingly, the percentage of households belonging to the A (well off) & B (manageable) categories has increased by 24% (see Figure 2). Further disaggregation shows that a) D category (poorest) households reduced by 7% (from 9% to 2%); b) C category (poor) households reduced by 16% (from 54% to 38%); c) B category (manageable) households increased by 15% (from 26% to 41%); and d) A category (well off) households increased by 9% (from 11% to 20%). / On average a 55% reduction in distress migration is expected for households in the Project Target Area (PTA). See Figures 2 and 3. / Figure 2: Well Being Ranking of HHS in MPRLP villages at baseline and EoP Figure 3: % reduction in HHs migration / A significant improvement in food security for the poor and poorest households: / As a result of project interventions, the proportion of a) poor and b) poorest households in the project target area (PTA) assessed as critically food deficient (i.e. not getting two square meals a day), has reduced from 8 to 4.5% (against a target of 3%) and from 15 to 6% (against a target of 5%) respectively (see Figure 3). On the other hand, in control villages, the proportion of a) poor and b) poorest households assessed as critically food deficient has reduced from 10 to 8% and 15 to 10% respectively. In other words, the performance was significantly better in MPRLP villages. The project has also set up 3,064 emergency funds and 446 grain banks across the 9 districts (see Figures 4 and 5). / At the output level, MPRLP also directly assisted 0.81m people, and will overachieve against a target of 0.73m / Figure 4: Incidence of food deficient days Figure 5: Emergency fund and Grain Banks at District level / % households / Piloting low carbon technologies for scale up and saving over an estimated 0.5m tonnes of CO2e (see section 4.3). / MPRLP was primarily designed as a livelihoods programme, rather than as a climate change adaptation programme. MPRLP has adopted a sustainable livelihoods approach which has significantly contributed to improved climate resilience of the 2.3 million people it was working with, in particular the poorest and most vulnerable. This has been substantiated by 2 recent reports[1] which have confirmed that apart from other benefits to beneficiaries, low carbon technologies have resulted in significant impacts in terms of reduced carbon emissions and improved adaptation mechanisms. Consequently, an estimated 533,352.98 tCO2e has been saved (also see Section 4: Risk; Para 4.3) / The key outcomes are: / Leveraging an additional INR 394.7 million or £4.9m for Gram Sabha community micro-plans through convergence with other government schemes and sub-schemes: / The programme’s ability to leverage such significant resources through convergence with other government schemes has been a major outcome for MPRLP beneficiaries. The bulk of such convergence has occurred through leveraging of resources from specific schemes [NREGS (INR 234 million or £2.9m); Sahariya Vikas Abhikaran (INR 73.2 million or £915,750); and Integrated Tribal Development programme (INR 23 million or £287,200) (see Table 1)]. However, another major contributor to the success of convergence has been the presence of a large number of field staff and village workers who implemented a range of other such schemes in the project target area, in addition to MPRLP’s core activities. Any amount that has been received by the Gram Sabha has been routed through the project. / Table 1. Funds leveraged through convergence / Scheme INR (in lakhs) GBP (@ 80 Rs) / Vermi pit 1 625 / ATMA Project 98 122,625 / Biogas Project (Agriculture dept) 43 54,225 / Biogas Project (MNRE) 160 200,363 / BRGF 171 214,088 / NREGS 2340 2,925,088 / MP Rajya Ajeevika Forum 3 4,263 / Seed subsidy 1 1,163 / Biosphere reserve 2 2,713 / Integrated Action Plan 78 97,475 / Integrated Livelihoods Programme 22 27,000 / National Rural Horticulture mission 1 638 / Sahariya Vikas Abhikaran 733 915,750 / Akshay urja 0 313 / SGSY 52 65,250 / Integrated Tribal Development Programme 230 287,200 / NABARD 1 825 / TSC 11 14,075 / Total 3947 4,933,638 / The delivery of state rural development programmes which translate into pro-poor budget allocations and services / There have been year on year budget increases across key budget lines (see Table 2), although direct attribution to the project is hard to make: / Table 2: MP Outcome budget estimate increases / Budget line OUTCOME BUDGET ESTIMATES / 2008-09 (INR Crore) 2012-13 (INR Core) % increase / Panchayat & Rural Devt. 2159 6913 220% / Tribal sub plan 3056 6109 100% / Caste sub plan 3056 4241 39% / Source: GoMP reporting / In addition, as part of a commitment to Government of Madhya Pradesh, DFID transferred £5m from MPRLP to the National Rural Livelihoods Mission in 2009. The focus of this project (also known Community Institution Intensification and Strengthening Project) is to enhance social and economic empowerment of the rural poor in Madhya Pradesh by strengthening member owned, member controlled and member managed groups and institutions of the poor that enable them to secure sustainable livelihoods; and development of Social Capital to enable the community to develop, own and strengthen their institutions. Out of the total amount of £5m, some £1.2m of these resources have been used and accounted for. In February 2012, the PS MoRD had requested for a 1 year action plan and budget for SHG strengthening for the remaining £3.8m. This request has been superseded by the Chief Minister requesting a state-wide roll out plan for SHG strengthening. The draft plan that has been prepared will be implemented by the State Livelihoods Forum. The focus of the enhanced state wide approach will be on ensuring convergence between the District Poverty Initiative Project and the erstwhile MPRLP, working with Panchayati Raj Institutions, working with Banks and financial institutions, engaging civil society organisations to strengthen the programme, and encouraging cross learning with other livelihoods projects. We have conveyed to GoMP that this balance money should be completely utilised by 31 March 2013, failing which any remaining funds available from the £5m will lapse, and should be returned to DFID. / The project also targeted the development of one common sector plan for rural development for the state of MP for the effective utilization of human and financial resources. The externally aided projects were also to be part of the integrated plan. This target has been overtaken by moves to establish the National Rural Livelihood Mission (NRLM) in MP[2]. The implementation of NRLM will take note of key lessons drawn from MPRLP and DPIP[3]. These include developing institutions aimed at empowering women, building up human resource capacity in the project target area (unleashing the potential of community resource persons and enhanced training and skill development for beneficiaries), developing a comprehensive management information system to monitor progress of self-help groups and village development committees, convergence with other government schemes, technical and financial support to producer companies, modernising agricultural methods, and replication and scale up of successful interventions in other area, and encouraging innovation. / Strengthening the programme’s delivery mechanism at the community (or Gram Sabha) level (for details and results see Output 1).
[1] Climate Change Impact Assessment Report; and End of Project Impact Assessment Report
[2] NRLM in MP will include the erstwhile MPRLP and the World Bank funded DPIP.
[3] This was agreed at the lesson learning workshop held on 10 May, 2012. Participants included officials from GoMP, GoI, the World Bank and DFID.

What is the context in which UK support is provided?
What are we trying to address / Madhya Pradesh (MP) is one of the poorest states in India. If the state were a country, it would be amongst the poorest twenty in the world and be comparable to Uganda, with per capita income of $476 (2008-09). As per revised poverty estimates (based on $1.25 a day), the incidence of poverty in MP in 2004-05 was 48.6%. This has now fallen to 36.7% implying that about 55 million people have been lifted out of poverty. Despite this, on current trends, MP will struggle to meet most MDG targets, especially those on hunger, maternal and child mortality, water and sanitation and environmental sustainability. / According to the 2011 Census, MP has a population of 72.59 million, of which, 72.36% of the total population is rural. More than one third of the combined population are Scheduled Castes (SC) and Scheduled Tribes (ST) (SC 15% and ST 20%). These communities show far higher poverty levels (estimated at 57 %) than the rest of the population. They live in isolated areas with poor access to resources, communication facilities, services, markets and livelihood options. Consequently, such constraints hinder realizing the potential of available opportunities, as well as diversification of livelihood strategies in tribal areas of MP. Several factors inhibit the development of such communities, for example; fragmented and unproductive landholdings; high dependence on seasonal daily wage labour; drought; and poor access to resources, markets and information. Gender based discrimination is reflected in unequal sex ratio and low human development index for women (see Box 1). / The Government is committed to poverty reduction in rural areas. DFID has sought to complement government efforts by facilitating the inclusion of the needs and priorities of the poorest in such plans. DFID provided flexible finances to conduct area specific pilots (taking into account the needs and priorities of people) and additional human resources to work with communities, to increase their understanding of government schemes and to enable communities to access such resources. / What DFID is trying to do / The first phase of the project was operational in 822 villages of eight predominantly tribal districts namely Barwani, Dhar, Jhabua, Mandla, Dindori, Anuppur, Shahdol and Sheopur. The MPRLP Phase 2 programme covered 2901 villages in 9 tribal districts of Dhar, Mandla, Dindori, Annuppur, Shahdol, Sheopur, Barwani, Jhabua and Alirajpur (see Table A – note that Jhabua district was bifurcated into Jhabua and Alirajpur districts) including 822 villages of the first phase. The project envisioned improved ability of the Gram Sabhas to identify and implement effective support for poverty reduction. This was in line with the Madhya Pradesh Panchayati Raj and Gram Swaraj Adhiniyam (Act) 1993, which defined Gram Sabha as the fourth tier of the Panchayati Raj Institutional set-up and as a unit for decentralized governance. This structure was at the core of institutional development imperatives, both in the Phase 1and the Phase 2. / The project has therefore provided an opportunity to test and identify best practices and approaches that could be incorporated in the wider Government system, thereby enhancing the effectiveness of state sponsored livelihoods interventions. MPRLP Phase 2 has supported the creation of a wide range of livelihood opportunities and improved social protection for the poor, with particular emphasis on women and environmental sustainability. It has scaled up learning from Phase 1 in relation to: Pro-actively targeting the poor; Focussing on social protection for reduced vulnerabilities; Convergence so as to seek synergies with other government imperatives; and adopting a gendered approach to improving livelihoods. / Working through the local government, DFID has enabled the village community to identify the poor and poorest and to provide them with a mix of grants/loan and has helped them to access their entitlements under government schemes. MPRLP funds village institutions (Gram Sabhas) to improve the effectiveness and accountability of government schemes, and provides direct assistance to the poor to improve their livelihoods through on and off farm activities. In addition, the programme addresses food security (for example, through grain banks and emergency funds), which is particularly critical in drought prone areas. The programme also supports sustainable natural resource management practices (e.g. soil and water conservation, tree planting, use of low carbon technology and renewable fuels). / Table A: Project area statistics / District Block Cluster GP Villages Households Population reached directly and indirectly / Aalirajpur 6 14 108 191 21,856 131,136 / Anuppur 4 24 194 384 71,366 285,464 / Barwani 7 22 196 315 74,575 372,875 / Dhar 12 28 227 445 70,210 421,260 / Dindori 7 32 153 340 49,837 199,348 / Jhabua 6 14 118 211 33,862 237,034 / Mandla 9 30 189 431 56,842 227,368 / Shahdol 5 22 176 350 62,609 250,436 / Sheopur 3 13 127 234 45,246 180,984 / Total 59 199 1,488 2,901 486,403 2,305,905 / Source: MPRLP MIS data (2012) / Who is implementing the programme? / The programme is being implemented by a State Programme Management Unit (SPMU) located within the Panchayati Raj and Rural Development Department, (PRDD), GoMP. A Project Co-ordinator heads the SPMU, which is also supported by a team of consultants who provide technical support. MPRLP is being delivered on the ground through Project Facilitation Teams (PFTs) working with: / Government in traditional sectors like: agriculture, horticulture, and animal husbandry; and by promoting coordinated working among these departments (including on harmonising their policies and programmes). / Non-government organisations on issues like: a) awareness generation on health and hygiene; b) rights and entitlements to empower the poorest and ensure their access to basic, necessary services; and c) ensuring financial security for the poorest, especially women through facilitating access to finance from banks, micro finance institutions, and various government schemes.

## Section A: Detailed Output Scoring

Output 1: Enhanced capacities of Gram Sabha to plan and manage resources in a transparent, effective and accountable manner in response to community driven demands.
Output 1 score and performance description: : A++
Progress against expected results: / Indicator 1.1: Proportion of Gram Sabhas (GS) carrying out annual reviews of micro-plans and updates. / Target: 70%; Achieved: 91% / Results: Participatory micro-planning and review has facilitated decentralised planning and better poverty targeting and accountability. Under Phase 2, MPRLP has reached 2,091 villages in total. All 2,086 Gram Sabhas in Phase II villages have developed micro-plans and identified actions based on the specific needs of the poorest. While performance varies across districts (see Table 4), on average 91% of GS have reviewed, and revised their micro-plans annually (against a target of 70%). This process included a review of the planned activities as well as the planned budget. / Table 4: Micro-plan review and updates / District Micro-plans prepared Micro-plans reviewed & updated (%) / Alirajpur 128 100 / Annuppur 265 80 / Barwani 213 93 / Dhar 327 100 / Dindori 240 100 / Jhabua 166 100 / Mandla 329 100 / Shahdol 244 62 / Sheopur 174 85 / Total 2,086 Average = 91 / Source: MPRLP MIS data and Impact Assessment data (2012) / Indicator 1.2: Percentage of GS meeting the financial benchmarking criteria: i) financial management systems; ii) statutory audit; iii) social audit; iv) voluntary disclosures. / Target for all: 70%. Achieved: i) 93% ii) 94% iii) 95% iv) 100% / Results: There has been an improvement in financial skills, awareness, transparency and accountability of Gram Sabhas: This has enabled the poor (particularly women) to demand services and hold service delivery agents to account, including elected representatives. Take up of government schemes has improved and it has strengthened the faith of the tribal communities in the performance of GoMP as a consequence. / Financial management systems established and operational in 93% of GS’s (against a target of 70%). These GS maintain the loan register in the prescribed formats and the procedure for disbursing all new loans/grants in these GS has followed relevant financing guidelines and norms. / Annual statutory internal audits of all Gram Kosh (GK) funds: In the last financial year (against a target of 70%), internal audit of funds was undertaken in 94% of GS, using external Chartered Accountant firms. / Social audits: Undertaken in 95% of villages for 2010-11 year (against a target of 70%); and / Voluntary disclosure: This is practiced in 100% of MPRLP GS’s (against a target of 70%). GS receipts and expenditure details, and lists of beneficiaries are displayed in public places (e.g. painted on walls) in all MPRLP villages. Further disclosure takes place during GS meetings where receipts and expenditures are read out and explained. / Indicator 1.3: Proportion of GK funds utilized for i) the poor and poorest (C & D) and ii) women / i) Target: 70% Achieved: 76% ii) Target: 50% Achieved: 46% / Results: Use of funds to reach poorest and women: Gram Kosh funds were utilised for meeting needs of the poorest and women either as a loan or a grant. Specific activities focusing of women include animal husbandry, access to financial services, drudgery reduction and support activities). While results vary across districts (see Figure 5 below), the results show that: / Against the indicator End of Project target of 70%, an average of 76 % of GK funds have been utilized for the poor and poorest (C& D category); and / Against the Indicator End of Project target of 50%, there was a slight under-achievement as an average of 46% of GK funds have been utilized for women. / Figure 5: Use of GK funds for the poorest and women across Districts / Source: MPRLP MIS data and Impact Assessment data (2012) / The project has therefore shown that a more effective Gram Sabha can strengthen decentralised planning, provide space for the poor and women, and increase confidence in demand-led approaches for improved service delivery. Other village institutions (e.g. Village Development Committees and Self Help Groups) representing the poor and marginalised are essential to embed effective participation in local governance. / Recommendations: On the whole, project performance has exceeded expectations against this output. It has overachieved against indicators 1.1 and 1.2. On Indicator 1.3, while it has overachieved on utilisation of Gram Kosh funds for the poor and the poorest, it has marginally underachieved against utilisation of Gram Kosh funds for women. It is recommended that efforts be stepped up against Indicator 1.3 to meet the target.
Impact Weighting (%): 18% / Revised since last Annual Review? No / Risk: Low/Medium/High Medium / Revised since last Annual Review? No

Output 2: Improved access to assets, employment, and services that support the livelihoods of the rural poor.
Output 2 score and performance description: A (2.1-2.2 A+ + and 2.3 B)
Progress against expected results: / Indicator 2.1: Number of people in the project area directly assisted by food security programmes (GK grants, loans and other project activities) / Target: 0.73m. Achieved: 0.81m / Results: MPRLP directly assisted 0.81m people, overachieving against a target of 0.73m through food security programmes like Gram Kosh grants, loans and other project activities. / Indicator 2.2: Number of men and women adopting project promoted practices, both i) farm and ii) non-farm / Farm Target: 58,400 men and women, of which 20% are women. Achieved: 140,231 men and women of which 43% (60,299) are women. / Non-farm target: 29,200 men and women, of which 50% are women. Achieved: 108,917 men and women, of which 44% (47,923) are women. / Results: / On-farm: Against the EoP target of 58,400, 140,231 men and women have adopted various project promoted farm based activities. In addition, against the EoP target of 20%, 43% (or 60,299) of these were women. This significant increase in people adopting farm practices has resulted in: an average128% increased cropping intensity; a 1,706% increase in the number of vegetable farmers from 4,234 to 76,276; and 23% of the cultivable area has been brought under double cropping (see Figure 6a-c); the opening of 31 “Aajivika Fresh” outlets (an innovation of the project) for sale of fresh vegetable produce (see Figure 7) and uptake of the System of Rice Intensification (SRI) across districts (see Figure 8). / Figure 6 a: Cropping intensity (through double cropping) in MPRLP Districts from Phase 1 baseline to EoP / Figure 6 b: Increase in the number of farmers’ from Phase 1 baseline to EoP / Figure 6 c: Increase in the area farmed (ha) / Source: MPRLP MIS data and Impact Assessment data (2012) / Figure 7: Aajivika Fresh outlets Figure 8: Adoption of SRI / District No. of outlets No. of villages covered No. of farmers covered / Alirajpur 2 7 41 / Anuppur 2 77 253 / Barwani 2 7 17 / Dhar 5 13 32 / Dindori 1 8 20 / Jhabua 2 5 30 / Mandla 2 8 42 / Shahdol 3 21 180 / Sheopur 12 104 178 / Total 31 250 793 District No. of farmers Area in ha. No. of villages / Alirajpur 13 3 5 / Anuppur 3,282 772 252 / Barwani 85 12 15 / Dhar 0 0 0 / Dindori 15,405 4,762 340 / Mandla 8,185 1,802 300 / Shahdol 23,000 9,850 350 / Sheopur 0 0 0 / Total 49,970 17,201 1,262 / Source: MPRLP MIS data and Impact Assessment data (2012) / ii) Non-farm: Against the EoP target of 29,200, 108,917 men and women have adopted project promoted non-farm based practices (e.g. vocational training programmes; 25 new village haats (markets) covering 628 villages; Agarbatti (incense sticks) cluster and federation; handicrafts and toy making clusters; ‘Non-Timber Forest Products (NTFP)’ producer company; and naturopathy). In addition, against the EoP target of 50% women, 44% (or 47,923) of these were women. / Indicator 2.3: Number of Self Help Groups (SHGs) i) accessing financial services from formal banking institutions and Micro Finance Institutions (MFIs) and ii) loan repayment rate of SHGs to the lending agencies / Target: 2920 SHGs linked to banks; 730 SHGs linked to MFIs. Achieved: 2795 SHGs linked to banks; 136 SHGs linked to MFIs / Target: 90% of SHGs repay loans to lending agencies. Achieved: loan repayment rate to Gram Kosh (GK) is 52%; and to MFIs is 92% / Results: This low level of financial inclusion occurred for 2 reasons: a) the project focussed on working with and through SHGs only in the penultimate year of Phase 2; and b) most of these SHGs are situated in extremely remote, near inaccessible and far flung areas. In all, 10,199 SHGs exist in the programme area of which 6,796 groups have been formed and 3,403 SHGs have been revived. / Against the EoP target of 2,920 SHGs linked to banks and 730 SHGs linked to MFIs, 2,795 SHGs have been linked with banks and 136 groups have been linked to MFIs (see Table 5). Consequently, these SHGs have been graded. The process of grading is ongoing and the number of graded SHGs will increase as linkages with financial institutions occur. Most of the SHGs consistently perform certain basic functions like meetings and savings, though inter loaning has been initiated in few SHGs only. The meetings in the SHGs are usually conducted once every month and sometimes fortnightly also. / Against the combined EoP target of 90%, the average loan repayment rate of SHGs to the Gram Kosh is 52% (see Figure 8), and to MFIs is 92%. This figure on repayments to the Gram Kosh should be viewed in context: although the target was ambitious, the project has created a culture among the beneficiaries, of paying back loans taken from the government. / With respect to the functioning of the SHGs, most of the SHGs have updated records with well-documented details of proceedings and financials. The project employed a health check-up of the SHGs for assessing the status of the group. Detailed criteria and indicators have been developed on the basis of various parameters of group functioning, development and adherence of norms, operations and performance. The overall status of the group is assessed against these indicators and scores assigned for each of the assessment indicator. On the basis of the overall score, the groups are categorized as A, B, C or D category. The summary of the assessments of 7,496 SHGs is given in the matrix below. / Table 5: Number of SHGs across districts Figure 8: Grading status of 7,496 SHGs / District No. of SHGs No. of SHGs graded under SGSY No. of SHGs linked with MFIs / Alirajpur 1006 241 0 / Anuppur 1066 343 0 / Barwani 1269 163 0 / Dhar 1039 447 0 / Dindori 1819 309 22 / Jhabua 606 369 0 / Mandla 1139 586 0 / Shahdol 1479 145 114 / Sheopur 776 192 0 / Total 10,199 2,795 136 A B C D Total / No. of SHGs 2566 2606 1373 951 7,496 / Source: MPRLP MIS data and Impact Assessment data (2012) / Recommendations: On the whole, performance against this output has met expectations. It has overachieved against indicators 2.1 and 2.2, but has underachieved against indicator 2.3. However, considering that this indicator was included in the programme only in 2009, progress is reasonable considering a) that the remoteness of villages considerably constrains access to financial linkages, and b) that the project is introducing behavioural change in that people are starting to consider that loans taken from government should be repaid. It is recommended that the process of grading SHGs be completed, and that efforts be stepped up to meet the target for indicator 2.3. / Impact Weighting (%): 38% / Revised since last Annual Review? No / Risk: Low/Medium/High Medium / Revised since last Annual Review? No

Output 3: Effective mechanisms for social protection, which reduce vulnerability and build assets of the poorest, and reduce constraints to productive activity.
Output 3 score and performance description: A
Progress against expected results: / Indicator 3.1: Proportion of poor and very poor (C&D) households with improved productive assets from Enabling Grants / Targets: 70% of C&D households improve productive assets from Enabling Grants. Achieved: 79% of C&D households. / Results: This indicator reflects the enhanced asset base for poor and very poor (C&D) households. / Against the EoP target of 70%, 79% of C&D households have acquired improved productive assets or enhanced their existing assets from enabling grants through the Gram Sabha and Gram Kosh (see Table 6 for a list of productive assets). / Table 6: List of productive assets funded through the Gram Kosh enabling grants / Category Improved Productive Assets / Agriculture Farm implements, Pump set, Irrigation support items, SRI paddy etc. / Animal Husbandry Goatery, Commercial poultry, dairy etc. / Micro Enterprise Development Grocery store, Hotel business, Flour mill, Vegetable/fruit vending etc. / Service Provider Centering, Carpenter, Electrician, Tailoring, Mason, Bicycle repairing etc. / Non-Timber Forest Produce Non-Timber Forest Produce collection, processing and trading / Source: MPRLP MIS data and Impact Assessment data (2012) / Indicator 3.2: Proportion of eligible poor and poorest households (C & D households) with access to: i) 30 days work under MGNREGS, ii) full Pension entitlements and iii) BPL households with access to Government Insurance schemes / Target: 40% of C&D households have access to 30 days work under MGNREGS. Achieved: 62% of C&D households. / Combined Target: 60% of eligible C&D households receive full pension entitlements. Achieved: 45.8% received full old age pension entitlements; 53.8% received full disability pension entitlements; and 64.6% received full widow pension entitlements. / Target: 60% of BPL households have access to Government Insurance Schemes. Achieved: 100% / Results: / Against the EoP target of 40%, 62% of C & D households have got work under MGNREGS for at least 30 days, as compared to 59% in control villages (see Figure 9). / Figure 9: % of HHs with access to at least 30 days of work under NREGS across WBR / Source: MPRLP MIS data and Impact Assessment data (2012) / Against the combined EoP target of 60% (see Figure 10): / 45.8% of eligible C & D households received full old age pension entitlements; / 53.8% of eligible C & D households received full disability pension entitlements; and / 64.6% of eligible C & D households received full widow pension entitlements. / Figure 10: % of eligible C & D HHs with access to pension entitlements for MPRLP and control villages / Source: MPRLP MIS data and Impact Assessment data (2012) / Against the Indicator End of Project target of 60%, 100% BPL households are covered under the Janashree Beema Yojana, so have full access to Government insurance schemes (see Figure 11). Some 185,000 individuals were linked to social protection schemes and 194,000 individuals covered under life insurance schemes / Figure 11: Access to social protection entitlements for eligible C&D category Households / Source: MPRLP MIS data and Impact Assessment data (2012) / Recommendations: On the whole, performance of the project against this output met expectations. The project overachieved against indicator 3.1. Against indicator 3.2, the project overachieved against the subtarget for poor and poorest people seeking a minimum of 30 days work under MGNREGS, and for BPL households with access to insurance schemes, but underachieved against full pension entitlements for old age, disabilities and for widows. It is recommended that efforts be made to meet the target on pension entitlements. / Impact Weighting (%): 15% / Revised since last Annual Review? No / Risk: Low/Medium/High Medium / Revised since last Annual Review? No

Output 4: Women and men have equitable access to and benefit from resources, decision-making and opportunities to enhance livelihoods.
Output 4 score and performance description: A+
Progress against expected results: / Indicator 4.1: i) Proportion of participants in Gram Sabha committees who are female and ii) proportion of women in Gram Sabha committees with leadership roles / Target: 33% of women participate in Gram Sabha committees. Achieved: 33% (target met) / Target: 33% of women with leadership roles in Gram Sabha committees. Achieved: 43% of women are members of various GS committees; about 54% of women are in leadership roles. / Results: / Participation and representation of women: Women’s participation is almost 33% of the total participation levels. 54% women are also in leadership positions of the various Gram Sabha committees. / The Indicator End of Project target of 33% has been met as regards representation of women in the Gram Sabha meetings. / Against the combined Indicator End of Project target of 33%, about 43% of women are members of various GS committees, and about 54% of women are in leadership roles in GS committees (owing to 50% state enforced reservation), / Indicator 4.2: Proportion of the MPRLP programme costs allocated for interventions /activities targeting women / Target: 33% of MPRLP programme costs are allocated for women’s interventions/activities. Achieved: 45% of programme costs allocated for such activities. / Results: / Against the EOP target of 33%, on average 45% of programme costs have been allocated for activities targeting women although performance varies across districts (see Figure 12). Women of individual households are the primary conduit through which activities such as revolving fund grants under MPRLP, bank linkages of SHGs and linkages with other schemes are occurring. Specifically, funds have targeted women-centric activities such as animal husbandry, access to financial services, drudgery reduction and support activities are being undertaken. / Figure 12: District wise MPRLP programme costs allocated to women / Source: MPRLP MIS data and Impact Assessment data (2012) / Recommendations: On the whole, the project has moderately exceeded expectations against this output. The project met the target for women participating in Gram Sabha committees and exceeded the target for women in leadership roles. The project also exceeded the target for programme costs allocated for women oriented activities. However, there is scope to do more. Strengthening performance against output 2 (SHG linkages) will positively impact on activities for women beneficiaries. / Impact Weighting (%): 14% / Revised since last Annual Review? No / Risk: Low/Medium/High Medium / Revised since last Annual Review? No

Output 5: Programme results, methodologies and structures inform State and Central level programmes and policies.
Output 5: score and performance description: A / Progress against expected results: / Indicator 5.1: GoMP adopts micro planning as a tool for implementing local development plans / Target: Line departments implement their respective schemes and programmes through consolidated micro plans at district level. Achieved: GoMP has endorsed (at the highest level) micro planning in every village.
Results: / Against the EoP target that line departments would implement their respective schemes and programmes on the basis of consolidated micro plans at the district level, the Government of Madhya Pradesh (through the Honourable Chief Minister of Madhya Pradesh) has appreciated the importance of micro planning, and has endorsed micro planning in every village as one of the 36 points in the Chief Minister’s manifesto. / Indicator 5.2: GoMP adopts programmes /schemes implementing the Project Facilitation Team (PFT) model as an enhanced delivery mechanism. / Target: PFT model implemented in 2 schemes /programmes. Achieved: In terms of govt schemes, PFT model has only been adopted for implementation in National Rural Livelihoods Mission. However, the World Bank has also adopted the PFT model in its District Poverty Initiatives Project (DPIP). / Results: / Against the EoP target that the PFT model would be implemented in 2 schemes /programmes, PFT model has been adopted for implementation of the State National Rural Livelihoods Mission (SNRLM). / During the initial phase, the SNRLM would target 10 districts, 9 MPRLP districts and one new district. The PFT model would be adopted for implementation of the mission in all the districts for a period of next 10 years. / SNRLM Plan defines clear role for the Gram Sabha to support the vulnerable; and provide public goods and services and for SHGs to concentrate on being economic entities. / Climate induced vulnerability to be explicitly addressed and the programme will make use of the micro planning approach at village level. / Management and support framework recognises need for village level resources to directly support implementation. / The PFT model is also being used under the World Bank DPIP. / Indicator 5.3: Formal institutional set up at state and district level for sharing experiences, use of financial and human resources and collaborative working / Target: State level apex body set up to share project experiences, for joint planning and for use of resources. Achieved: State Learning Forum set up under MPRLP. / Results: Against the EoP target that a State level apex body would be formed and activated for sharing project experiences, joint planning and use of resources, the results were as follows: / A State Learning Forum (an autonomous unit for MPRLP) was established with the basic objective of knowledge management. Innovative methods were adopted for knowledge sharing by State Learning Forum. The state learning forum is specific to MPRLP, but other opportunities exist to protect knowledge management and lesson learning under NRLM. / Knowledge sharing has resulted in MPRLP being nominated for the Prime Minister’s Excellence Award for 2011-12 / The District Project Management Committee acts as a forum at which lesson learning on ways of working have been shared with other departments. / 83 peer learning programmes aimed at community sharing have been conducted over the last 2 years. In addition, intra project component sharing has also taken place among staff. / Management institutes (IIM Indore, XIMB Bhubaneswar) sent students to Dhar and Sheopur districts to study programme impacts. / Officers from other states (Gujarat) have also visited the programme to learn / Benefits of MPRLP were quickly visible to non MPRLP villages. This created public pressure on elected representatives, who in turn lobbied for an increase in NRLM blocks from 38 to 46. / Strengthening human resources for delivery: Investing in the software takes time but yields results: leadership with motivated, local staff at district level who coordinate with local government; it takes time to gain trust & sensitise the community; role of community staff crucial. NRLM seen as being influenced by MPRLP (especially HR element). NREGA and other GoMP and GoI programmes have benefited from using Community Resource Persons (CRPs) to leverage community engagement. / Recommendations: The project has met expectations against this output. GoMP has endorsed the use of micro planning at the village level. GoMP also recognised the value of dedicated human resources as part of the delivery mechanism. For a start, GoMP adopted the use of the Project Facilitation Team in the implementation of NRLM. GoMP also set up an apex body – the state learning forum, for dissemination of knowledge and learning under the programme. Though this is yet to extended to other programmes, GoMP also undertook several other measures to disseminate information. Going forward, efforts should be made to mainstream and strengthen good practice within communities, so that sustainability improves. Such efforts will become even more critical if for any reason, the significant HR support within the programme (via the Project Facilitation Teams) is scaled back, redeployed to other programmes, or withdrawn. / Impact Weighting (%): 15% / Revised since last Annual Review? No / Risk: Low/Medium/High Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? Y/N / Yes. Due to the decrease in Phase 2 PTA from 4,000 to 2,901 villages, any numerical targets were reduced proportionately (i.e. to 73% of their original number). This was done in the pre-PCR finalisation meeting and agreed with GoMP. It was also recommended by the Impact assessment and agreed at the Project Completion Review. / 1.2 Overall Output Score and Description: / The overall output score is A + i.e outputs have moderately exceeded expectations. This final output score is based on the project having met or exceeded most of its targets, across all outputs. Under Output 1 the project has overachieved against the targets for Gram Sabhas reviewing micro plans; improving their financial skills, awareness, transparency and accountability; and proportion of Gram Kosh funds used for poor and poorest. Under Output 2 the project has overachieved against number of people directly assisted by food security programmes; and number of people adopting project promoted farm and non-farm practices. Under Output 3 the project has overachieved against poor and very poor households with improved productive assets from Enabling Grants; poor and poorest households with access to 30 days work under MGNREGS; and access to coverage under Government Insurance Schemes. Under Output 4, the project has overachieved against women participating in Gram Sabhas and also holding leadership roles. Under Output 5, the project has achieved against the state adopting micro planning as a tool for implementing local development plans; the state adopting the project facilitation team model as an enhanced delivery mechanism; and the setting up of a state level apex body for sharing experiences, use of financial and human resources, and collaborative working. / However there were a few areas where the outputs were not met (e.g. OVIs: 1.3 on women; 2.3 on SHG bank and MFI linkages and loan repayment rates; 3.2 on full old age pension and disabled entitlements). / 1.3 Direct feedback from beneficiaries / What went well: / “Reduced dependency on money lenders” / “We are more aware of government schemes: MGNREGS, pensions and other things” / “The Gram Sabha now meets monthly, more women are participating” / “We got loans for seed and fertiliser, we now get a summer crop and yields have doubled” / “My cycle & motor repair shop has sales of Rs 2,000 a day!” / “In the weekly rural haat (market), I can sell (goods worth) ..Rs 3,000 a day…before I was breaking rocks” / “We got drinking water…smokeless challahs (stoves)…houses for the zaharaia … a chakki (grain grinding mill)…mobility has increased” / “Working in mission mode, Well Being Ranking, systematic approaches, (besides) local Project Facilitation Teams (PFTs) and community staff engagement” / “We are more united now; we won’t let anyone go hungry now” / “I had nothing but my labour to offer…I took a loan for a goatery project and (with the money I made) managed to get two of my children married…” / “Through the total sanitation campaign, we got toilets, it gave us more privacy and improved our well-being” (women) / “We used to eat just chillis and chapatti (an Indian bread), now we also have daal (lentils) and green vegetables and sometimes chicken” (women) / “I got my cataract operation done and now I can look after my 4 grandchildren” (women) / “Earlier we used to migrate (to other places); now we are going to see those places for leisure!” / “Bori-bandan (a rainwater harvesting technique using sacks) has changed our lifestyles…we can grow more crops and eat better” / “Because of MPRLP support, I am rearing chicks, I have money and my family values me more and I can help them more” (women) / “Because of the emergency fund, I don’t default on school fees anymore” / “Because MPRLP has helped improved livelihoods, we can ensure our children go to school” / What could have been done better: / “(We should have been) Given grants (rather than loans) for livestock…they die (and this results in loss to us)! Dairy would have been better” / “(The project should have) Come earlier and stayed longer” / “(The project had) A lot of stand-alone activities” / “Reach was an issue for livestock activities” / “SHG grading needs to be completed” / “On convergence, success in delivery meant we maybe took too much on” / “Finances for the field work did not reach well in last 6 months” / “Phase 1 had intensive capacity building; Phase 2 it was broader rather than deeper” / “Scaling up access to markets – volume and scale matter…could we have done more to develop scale up and access?” / “Could DFID have been clearer about grants vs loan eligibility and converting between them, it confused the communities” / “DFID could have done better on: clarity on policies; faster response times; and more direct communications”
1.4 Summary of overall progress / Previous sections have already detailed progress against outputs. However, when viewed through the lens of sustainability, the overall progress of the project is as follows: / Institutional sustainability: MPRLP has experimented with Gram Sabha as the service delivery mechanism and strengthening the Gram Sabha for effective delivery has been the mainstay of the institutional development imperatives of the project. The other institutions were in the form of Self Help Groups, Livelihood Promotion Groups, and other User Groups. Given the centrality of Gram Sabha in the design, institutional sustainability of Gram Sabha is critical. Madhya Pradesh has been one of the only states in the country to acknowledge Gram Sabha as the fourth-tier of the Panchayati Raj through a statute. Institutional sustainability of the Gram Sabha gets ensured by the Act. While the existence of the institution is ensured by the Act, the functioning of the Gram Sabha as a unit of decentralized governance is the issue. / Intervention sustainability: The Gram Kosh available with the Gram Sabhas is one of the key instruments that can provide some continuity to the project imperatives. Loan activities would be of critical importance as continuity would directly depend on recoveries and further lending. Linkages forged with the SNRLM can also provide for active engagement of the Gram Sabhas in mission initiatives. Village-level service providers (e.g. livestock gopals) have also been created that can directly provide community services and act as resource persons for the Gram Sabha in its service delivery mandate. / MPRLP has changed the lives of its beneficiaries, in particular women. It has made significant progress on women’s empowerment, SHG strengthening[4], and the establishment of emergency funds. The programme’s emphasis on transparency “has restored the faith of the people in government”. Participatory processes have been adopted to strengthen communities and the role of the gram sabha. Thanks to this, active participation by women (particularly the poorest, and including in leadership roles) has increased. / Awareness: MPRLP has enhanced people’s awareness with regard to a range of issues such as access to information, social protection, services, nutritious food, health, education, financial services, better agricultural inputs and productivity, increased cropping intensity, realisation of the need to invest in the health of domestic livestock, improved use of natural resources, and awareness creation on the use of non-conventional renewable energy. This has increased awareness on rights and entitlements, and has empowered beneficiaries to seek accountability on services delivered by the state. / Replication: At the district level, MPRLP’s success has been demonstrated to other line departments. This has created pressure on other line departments to perform better and improve the quality of their service delivery. This is expected to continue under NRLM. In addition, the women leadership development model created under MPRLP has been replicated in DPIP. / Result sustainability: The result matrix shows substantial achievement in majority of the intended result areas. Also, by far the trend of outcomes is positive and reflects of an upward trend. Therefore, it is expected that this will continue. An ex-post assessment is currently underway aimed at all rural livelihoods programmes implemented by DFID in India. The study will assess sustainability and delineating factors contributing to result sustainability. The outcomes of this assessment are expected to result in significant learning for livelihoods augmentation imperatives.
1.5 Key challenges / A major challenge has been strengthening financial inclusion, and the project has sought to address this through Output 2 (Indicator 2.3: Number of Self Help Groups (SHGs) i) accessing financial services from formal banking institutions and Micro Finance Institutions (MFIs) and ii) loan repayment rate of SHGs to the lending agencies). Performance against this indicator is as follows: / Target: 2920 SHGs linked to banks; 730 SHGs linked to MFIs. Achieved: 2795 SHGs linked to banks; 136 SHGs linked to MFIs / Target: 90% of SHGs repay loans to lending agencies. Achieved: loan repayment rate to Gram Kosh (GK) is 52%; and to MFIs is 92% / This low level of financial inclusion occurred for 2 reasons: a) the project focussed on working with and through SHGs only in 2009-10; and b) most of these SHGs are situated in extremely remote, near inaccessible and far flung areas. In all, 10,199 SHGs exist in the programme area of which 6,796 groups have been formed and 3,403 SHGs have been revived. As for the indicators; / Against the EoP target of 2,920 SHGs linked to banks and 730 SHGs linked to MFIs, 2,795 SHGs have been linked with banks and 136 groups have been linked to MFIs (see Table 5). Consequently, these SHGs have been graded. The process of grading is ongoing and the number of graded SHGs will increase as linkages with financial institutions occur. Most of the SHGs consistently perform certain basic functions like meetings and savings, though inter loaning has been initiated in few SHGs only. The meetings in the SHGs are usually conducted once every month and sometimes fortnightly also. / Against the combined EoP target of 90%, the average loan repayment rate of SHGs to the Gram Kosh is 52% (see Figure 8), and to MFIs is 92%. This figure on repayments to the Gram Kosh should be viewed in context: although the target was ambitious, the project has created a culture among the beneficiaries, of paying back loans taken from the government. / With respect to the functioning of the SHGs, most of the SHGs have updated records with well-documented details of proceedings and financials. The project employed a health check-up of the SHGs for assessing the status of the group. Detailed criteria and indicators have been developed on the basis of various parameters of group functioning, development and adherence of norms, operations and performance. The overall status of the group is assessed against these indicators and scores assigned for each of the assessment indicator. On the basis of the overall score, the groups are categorized as A, B, C or D category. The summary of the assessments of 7,496 SHGs is given in the matrix below. / Table 5: Number of SHGs across districts Figure 8: Grading status of 7,496 SHGs / District No. of SHGs No. of SHGs graded under SGSY No. of SHGs linked with MFIs / Alirajpur 1006 241 0 / Anuppur 1066 343 0 / Barwani 1269 163 0 / Dhar 1039 447 0 / Dindori 1819 309 22 / Jhabua 606 369 0 / Mandla 1139 586 0 / Shahdol 1479 145 114 / Sheopur 776 192 0 / Total 10,199 2,795 136 A B C D Total / No. of SHGs 2566 2606 1373 951 7,496 / Source: MPRLP MIS data and Impact Assessment data (2012) / During the proposed no cost project extension period of 1 year (referred to elsewhere in this report) the focus will be on utilising the remaining £3.8m available in the project to strengthen SHGs, thereby enhancing financial inclusion in MP.
1.6 Annual Outcome Assessment / The overall outcome score is A i.e. overall outcome met expectation: The project has achieved many impacts, as detailed above and even gone beyond expectations (e.g. Climate change). However, it has marginally fallen short of targets set at outcome level. This could mean (i) targets set were too ambitious; and or (ii) risks and assumptions about the output to purpose level held true and affected performance, for example: / Outputs 1 and 5: The assumptions about the role of the decentralisation and its ability to promote increased transparency and accountability, as well as the ability of MPRLP to mainstream its approaches state wide have been tested. / Purpose level: The assumptions about the integration of lessons and evidence into rural development policy making have largely held true, but as noted above, using the project mechanisms, they have been tested. That said, the project has provided the foundation for NRLM in the state.
[4] In preparation for the rollout of NRLM in MP, MPRLP has helped focus GoMP’s attention on SHG strengthening. In 2009, in response to a request from GoMP, a decision was taken to earmark £5m of programme funds for SHG strengthening. Initially, GoMP proposed to adopt a targeted, region-specific approach to utilising these resources. GoMP has now scaled up its ambition and proposes to roll out SHG strengthening across the entire length and breadth of the state. A workplan is being prepared for approval by GoMP, which proposes to utilise the available resources within FY 2012-13.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y/N / The project is largely on track against financial forecasts. However, spend to date includes £5m which was transferred from MPRLP to NRLM in 2009. This amount was meant for SHG strengthening. The money was originally meant to be spent in the project area, and as of date, out of this £5m, £1.2m has been spent. The GoMP has recently taken a decision to roll out SHG strengthening across the state, and a plan has been drawn up to disburse the balance £3.8m. This plan is to be formally endorsed in July. DFID is extending the project by a year (at no cost) in order to allow for spend and accounting of this balance money. DFID is also informing GoMP that any moneys remaining unspent as on 31 March 2013 will need to be returned. / 2.2 Key cost drivers / A breakdown of costs (in INR) is given below: / PARTICULAR/PROJECT YEAR PY1 PY2 PY3 PY4 PY5 PY6 PY7-20 / 2007-08 2008-09 2009-10 2010-11 2011-12 / COSTS / A. PROJECT COSTS / Gram Kosh funds 305,800,000 320,200,000 362,100,000 327,000,000 / Programme costs 36,300,000 100,100,000 83,600,000 127,700,000 / Administration 62,300,000 200,000,000 203,600,000 225,400,000 / Total Project Costs 404,400,000 620,300,000 649,300,000 680,100,000 / B. GRAM SABHA PARTICIPATION COSTS / Gram Sabhas held 7002 14,125 18,567 17,281 / Average attendance 56 55 56 56 / Average meetings per GS / Total Cost of participation in Gram Sabha 23,918,832 47,389,375 63,424,872 59,031,896 29,515,948 29,515,948 29,515,948 / C. GROUP ACTIVITY MANAGEMENT COST / Groups 2,034 4,944 9,257 10,058 / Members 22,374 51,574 96,861 108,746 / Average attendance 0.7 0.7 0.8 0.8 / Average number of meetings 23 23 24 24 / Total group activity management costs 21,973,505.4 50,650,825.4 113,443,603.2 127,363,315 63,681,657.6 63,681,657.6 63,681,657.6 / TOTAL ECONOMIC COSTS (A+B+C) 450,292,337.4 718,340,200.4 826,168,475.2 866,495,211 93,197,605.6 93,197,605.6 93,197,605.6 / Management and delivery arrangements: MPRLP had an administrative cost component of 33% principally on account of the programme’s management and delivery structure. The GoMP formed a Society under Indian Law for the implementation of MPRLP. This was designed to enable the project to operate flexibly, yet comply with DFID project planning and management systems, so as to fulfil its objectives, while remaining fully integrated with its parent department and other state government departments and agencies. A three tier management structure was established, consisting of (i) a State Programme Management Unit (SPMU) located within the Panchayati Raj and Rural Development Department, (PRDD), GoMP, headed by a Project Co-ordinator; (ii) District management units; and (iii) Project Facilitation Teams (PFT) located in each district which provided direct support to (on average 5-10) targeted village communities. The additional presence of these PFTs (essentially, NGOs) resulted in a strong field presence: MPRLP had staff strength of 1000 field functionaries for 2901 villages. This intensive engagement resulted in building strong relationships with beneficiary communities. Consequently, MPRLP was better placed to understand (and address) the needs of the people: not only through the programme itself, but also through successful convergence with other government schemes. / Management framework: In terms of operational efficiency, the project has shown that there are mixed results from: (i) use of government and non-government systems and processes under the Society established; and (ii) operating as a departmental project outside government interaction and linkages between MPSRLP and government departments. It is recommended that the composition of the Management Units at all levels reflects the balance of experience, expertise and competencies needed to reflect the change in focus and emphasis, particularly in social protection, gender and capacity building. The State Learning Forum was an ambitious undertaking requiring shared vision and commitment among stakeholders. The forum functioned well within the project environment, but external impact was limited in part as it was positioned outside mainstream government and therefore lacked wider ownership. / 2.3 Is the project on-track against original timescale: Y/N / As mentioned in Section 2.1, the project is virtually complete. However, the remaining money (£3.8m) under the component earmarked for SHG strengthening needs to be spent and accounted for. DFID is extending the programme by one year to facilitate spend and accounting of this balance money.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Total Project Area: The Phase 2 project target area was originally 4,000 villages reaching 3m tribal people. However, Phase 2 project target area was reduced to 2,901 villages (i.e. 73%) of original project target area. Numerical targets for the logfame were adjusted accordingly. / Total population reached: According to the MIS (see Table A) the total households in the project target area were 486,403, and total population reached was 2,305,905 (based on a household size of 4.7). However, the C & D category households directly targeted were (59%) at 286,978 households or 1,348,797 people. / Planning and Monitoring and Evaluation: The project maintained a robust MIS but was unable to fully establish the log-frame driven strategic planning and implementation framework, and supporting M&E framework, making reporting and assessment of performance and achievement of outputs more difficult. / Project Impacts: Two key studies were carried out in the final year of the project: a) a Climate Change Impact Assessment; and b) an end of project Impact assessment. Both assessments have demonstrated in detail what has worked in this project. Their findings have significantly informed this report / 3.2 Where an evaluation is planned what progress has been made? / During the period under review, DFID commissioned a Climate Change Impact Assessment Study, and an overall impact assessment study. Both are complete. In addition, DFID has recently commissioned an independent retrospective evaluation covering 20 years of Rural Livelihoods investments in India. MPRLP will also feature in this evaluation.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / Medium / 4.2 Assessment of the risk level / The risk rating has not changed over the life of the project.
Risk of funds not being used as intended / All areas of funding were been agreed with DFID. Annual budgets have been made and discussed, and regular audits have been undertaken. Some £5m of funds were allocated to the SNLRM for strengthening SHGs in 2009. Some £1.2m of these resources have been used and accounted for. In February 2012, the PS MoRD had requested for a 1 year action plan and budget for SHG strengthening for the remaining £3.8m. This request was superseded by the Chief Minister requesting a state roll out plan for SHG strengthening. This plan has been prepared but has yet to be agreed due to a delay in meetings. All other funds used have been appropriately audited and accounted for. / 4.4 Climate and Environment Risk / MPRLP was primarily designed as a livelihoods programme, rather than as a climate change adaptation programme. MPRLP adopted a sustainable livelihoods approach which has significantly contributed to improved climate resilience of the 2.3 million people it was working with, in particular the poorest and most vulnerable. The project approach itself has helped with: targeting and including the poor; reducing distress migration; improving disaster coping capacity; increasing incomes and food security; building the institutions of the poor (e.g. GS and SHGs); improving access to assets and credit; and enhancing agricultural productivity. 2 recent reports (climate change impact assessment; end of project impact assessment) have confirmed the following: the project has demonstrated evidence that decentralisation and convergence have brought benefits to the poorest; capacity building has resulted in better implementation of outcomes; specific targeting of women has led to gender inclusion; diversified livelihoods have led to more inclusive development; and low carbon technologies have resulted in significant impacts in terms of reduced carbon emissions and improved adaptation mechanisms. Consequently, an estimated 533,352.98 tCO2e has been saved (see Table 7). / Table 7: Low carbon technology impacts and estimated tCO2e saved / What Units Benefit to Cost Ratio Est. tCO2e saved / Biogas units 6,021.00 1.66 55,576.27 / Smokeless Chulhas 216,000.00 2.96 474,985.13 / Solar lighting 7,615.00 0.96 1,961.91 / Treadle pumps 5,224.00 1.35 211.00 / Fibre sheets 25,037.00 2.84 618.67 / Total tCO2e saved 533,352.98 / Source: Winrock report; MIS data and DFID calculations.

5. Value for Money
5.1 Performance on VfM measures / As compared to control villages, the project villages have registered an additional 4% incremental reduction in poverty (BPL). The programme leveraged rights and entitlements worth approximately £4.9m from other centrally sponsored and state government schemes. There has been a significant improvement in the capacity of Gram Sabhas – micro planning and financial management strengthened for almost all Gram Sabhas. The project enabled women’s empowerment as reflected in higher participation of women in Gram Sabhas (33%) and in leadership roles (54%). Some 62% of poor households got more than 30 days employment under NREGA in project villages as compared to 58% Households in control villages. / 5.2 Commercial Improvement and Value for Money / Standard procedures involving competitive bidding have been followed, where MPRLP has used FA funds to procure services. Similarly, where DFID has used TA funds to directly procure services, standard procurement procedures have been adhered to. In both cases, vfm has been ensured in procuring services. / 5.3 Role of project partners / TA support: DFID provided MPRLP SPMU with access to technical assistance, implementation support and capacity building consultancy and training services through a Technical Cooperation Project Support Unit (TCPSU).The TCPSU delivered demand-driven assistance to address specific needs of MPRLP and DFID. The TA support provided focus to MPRLP demand led technical support. For example, TA support, helped with the benchmarks in terms of reaching the marginalised beneficiaries (C&D category, loan recovery, women SHGs). / While delivering their mandate, TCPSU had to contend with the challenge of contextualising DFID priorities within the operating realities of the project. For example: in response to DFID’s priorities, a range of studies was initiated on different aspects of the programme, but implementers on the ground were not able to benefit to the extent expected. This was due to difficulties in accessing internet connectivity in remote areas, and also because these were not always presented in a reader friendly manner to the end user on the ground. While some of the pilots initiated (e.g. on social protection and malnutrition) were considered useful, these were of extremely short duration (9 months and 6 months respectively), and could not be disseminated more widely or scaled up. Implementers did value the engagement of individual members of the TA support team, but would have also appreciated the existence of an appropriate feedback mechanism. / 5.4 Does the project still represent Value for Money : Y/N / Yes. There has been considerable achievement in all the five project outputs. This reflects on efficient translation of employed inputs into desired outputs and thus the project efficiency. This assessment is based on an economic analysis of the project, which was done to reflect on the overall efficiency of the investment. This included a cost benefit analysis aimed at determining the economic, social and environmental costs and benefits of key project interventions at the output level; and to comment on the economic efficiency of the project at the aggregate level. / The analysis attempted to estimate and value the incremental benefits incidental to the project. At the same time, the analysis attempted to value costs incurred – both direct and indirect. On-site and off-site economic, social and environmental impacts[5] were assessed, followed by a valuation of costs and benefits. These were analysed using a cash-flow analysis to arrive at the efficiency of the project. The study was essentially based on collation of secondary data, with primary data used to corroborate and validate the former. The analyses were done for a 20 year base case scenario. / Based on the net incremental benefit flows, the Economic Rate of Return (ERR) has been calculated. The ERR for the project comes to 23 percent which presents strong vfm. Out of the total project benefits, economic benefits contribute 43.5 percent; enviromental benefits contribute 36.7 percent; and social benefits contribute for the remaining 19.8 percent. / The sensitivity analysis reveals that even under conservative assumptions, the project would have an ERR greater than the opportunity cost of capital (12%). A ‘medium sustainability’ scenario (15 years) yields an ERR of 22 percent, and a ‘limited sustainability’ scenario (10 years) yields an ERR of 15 percent. Therefore, the project offers significant vfm. / 5.5 If not, what action will you take? / Not applicable
[5] MPRLP is a livelihood initiative that focuses on augmentation, enhancement and diversification of both natural resource and non- natural resource based livelihoods. Economic benefits of the projects are in terms of increased yield and production of agriculture and livestock, and increased returns from enterprises, service provision and placement services. There are environmental benefits in terms of reduction in soil erosion, increase in ground water table, amelioration of soil and water regime, carbon sequestration. Social benefit is in the form of reduced morbidity and funds leveraged through convergence at Gram Sabha level and reduced drudgery of women. The offsite benefits of the project are those associated with the bio-gas and plantation activities of the project. These include emission reduction and watershed benefits beyond the project target area.

6. Conditionality
6.1 Update on specific conditions / As such, there were no specific conditions attached to the programme.

7. Conclusions and actions
At the impact level, the project has made several significant gains for the poor and poorest through a considerable reduction in poverty and distress migration, a significant improvement in food security, leveraging resources for GS micro-plans through convergence with other govt schemes and sub-schemes, and substantial improvements in pro-poor budget allocations and services. / At the output level, the project has significantly overachieved against some of its targets and overall achieved nearly all its targets. While it has significantly overachieved targets linked to overall poverty impact, strengthening of social accountability mechanisms, climate resilience, social protection and in leveraging funds from other programmes and schemes, it has not achieved targets on linking SHGs to micro-finance and loan recovery. / The team noted the major achievements of MPRLP as having: / Made a significant impact on poverty reduction (both income and well-being). / Strengthened GS capacities and supported GS as vehicle for LH improvement and decentralised unit of governance. / Improving awareness, transparency and accountability and strengthening voice (in particular for women) and the interface between elected representatives and the community / Improved access to assets, employment and services, both on and off farm (particularly for women). / Demonstrated the power of convergence. / Improved social protection for the poor and poorest. / Improved food security and reduced distress migration for the poor and poorest. / Piloted low carbon technologies for scale up. / Strengthened Human Resources for improved service delivery. / Made a difference in the lives of the poor, who themselves articulated how it had positively impacted their lives. / A retrospective 20 year evaluation of rural livelihood programmes in India will also capture key impacts of this programme.

8. Review Process
The review process consisted of: / Impact Assessment Study (including Economic Analysis of project’s costs, benefits, and efficiency): Feb – April 2012 / Climate Change Impacts Assessment Study (delivered March 2012) / TA study / Field visits: 26-28 March; 3 teams to 4 districts: Jhabua, Sheopur, Mandla and Dindori. The team composition consisted of staff drawn from DFID, the project, the TA consultants, an independent Impact Assessment team, and a cross-Whitehall observer from the FCO. / Wrap up session in Bhopal with project team and the Principal Secretary, Rural Development, GoMP: 17-18 April 2012; and / Lesson learning workshop in Bhopal: 10 May 2012; There was participation from JS Vijay Kumar, MoRD, GoI; GoMP; Banks; State functionaries; MPRLP and NRLM staff as well as other projects (DPIP and ex WORLP Director). A workshop note has since issued.