Business Case and Intervention Summary
Intervention Summary
Three MDG Fund: addressing essential health needs of poor and vulnerable women, children and people with HIV, TB and malaria in Burma

What support will the UK provide?
The UK will provide up to £80 million over four financial years (April 2012 to March 2016) to support the multi-donor Three Millennium Development Goal (3MDG) Fund, the successor to the 3DF in Burma. The overall budget for the 3MDG Fund is estimated to be £180 million. Other donors to the fund will be Australia, European Union, Sweden, Denmark, Netherlands and Norway.

Why is UK support required?
What needs are we trying to address? / Burma is unlikely to meet the health Millennium Development Goals[1] without a significant increase in health services for the most vulnerable people. Burma health statistics are poor for the region, and for malaria, tuberculosis and malnutrition it has amongst the highest burdens in the world. At least 70,000 children and 2,400 pregnant women die every year from largely preventable causes. Health indicators in Burma are the way they are primarily because poor and vulnerable people cannot access good quality health services. Long-term under-investment and other health system challenges undermine the capacity of the public sector to deliver basic health care. / Although there are some early signs of long term political change, Burma has suffered 48 years of military rule and more than 60 years of internal conflict. In a region containing some of the fastest growing economies in the world, Burma has become one of the poorest countries in Asia. Poverty declined between 2005 and 2010, but a quarter of Burma’s 55 million population still live below the poverty line, with levels twice as high in rural areas, and highest in some ethnic states around Burma’s borders. / The UK does not have a normal aid relationship with Burma. We work within the framework of the European Union’s (EU) sanctions policy (called the EU Council Decision), which suspends non-humanitarian aid to Burma, except for certain sectors (health, education, livelihoods, environment and civil society). The UK’s experience in the last six years shows that it is possible to increase aid within this framework, while ensuring it reaches the poor. / What we will do? / Since 2007 the UK has worked with six other donors to support the 3DF (3DF)[2]. This £82 million fund has helped contain the epidemics of HIV, tuberculosis and malaria. The success of the 3DF assisted in persuading the Global Fund to return to Burma in 2011, after a six year gap. The 3DF will end in 2012. / The donors have agreed to continue to work together for a second phase fund from 2012 which will have a wider scope and address maternal and child health needs in addition to HIV, TB and malaria. This new phase 3MDG Fund will support essential health services for pregnant women, their babies and children, plus access to life-saving emergency care during delivery. It will also provide flexible and strategic support for HIV, TB and malaria programmes for vulnerable populations and remote areas not supported by the Global Fund. A third area of work is to strengthen some critical areas of the heath system to promote longer term sustainability This area of work will also build mechanisms for communities to have a say in health issues, so as to encourage services that are responsive to their needs. / Who will implement the support we provide? / The 3MDG Fund will build on the implementation experience of the 3DF. Core responsibility for the Fund will rest with the Fund Board, which will include representatives from all donors, including the UK, and three independent experts. The Fund Board will appoint a UN agency or international organisation to be the Fund Manager with responsibility for effective, transparent and efficient management of the Fund. The programme will directly and indirectly support services provided by public health sector, UN agencies, international and local NGOs, and the private sector. / This is an ambitious programme that has the potential to deliver significant health benefits, but involves risks. Risk monitoring and mitigation will be given high priority. UK assistance in Burma reflects international principles for engagement in fragile contexts; to build effective and responsive institutions capable of promote sustained development. The 3MDG Fund will be able to respond flexibly to changes in the country should circumstances permit.
[1] MDG 4 focuses on child health, MDG 5 on maternal health, and MDG 6 on HIV, TB and malaria
[2] Australia, European Union, Sweden, Denmark, Netherlands and Norway.

What are the expected results?
What will change as a result of our support / The impact of the 3MDG Fund will be pregnant women, newborn and children’s lives saved and the burden of HIV, tuberculosis and malaria reduced in Burma. The outcome is that in programme areas poor and vulnerable people will benefit from better health services focused on maternal and child health and HIV, TB, and malaria. / What are the planned results attributable to UK support / Based on modelled estimates (only), the programme may save up to 25,150 children under five; and 3,153 pregnant women (of which 11,569 and 1,450 are attributable to DFID). / It is estimated that over 5 years this programme will result in: / 613,000 women delivering with the help of a nurse, doctor or midwife; an increase from 56% to 81% (282,000 deliveries attributable to DFID) / An additional 37,000 pregnant women receiving antenatal care; an increase from 64% to 85% in programme areas (22,000 attributable to DFID) / 290,000 unwanted pregnancies averted (134,000 attributable to DFID) / An additional 121,000 children immunised with three doses of the vaccine to combat the childhood diseases of Diphtheria, Pertussis, Tetanus (DPT3) (56,000 attributable to DFID); an increase from 85% to above 95%. / An additional 120,000 children immunised against measles (55,000 attributable to DFID); an increase from 82% to above 95%. / An additional 35,000 infants aged 0-5 months exclusively breastfed (16,000 attributable to DFID). / 200,000 people reached with prevention or treatment in areas of high risk of drug resistant malaria (92,000 attributable to DFID). / How will we determine whether the expected results have been achieved / The 3MDG Fund will be accountable for delivering health results, showing that funding and inputs lead to effective services, increased use of those services by those in need and, ultimately, better health for them. The 3MDG Fund will also demonstrate that its programmes are cost effective and make the most of resources available. Impact, outcome and output indicators will be monitored throughout the lifetime of the programme. Data will be obtained through a mix of routine information systems as well as programme area surveys. The 3MDG Fund will support existing national monitoring and evaluation systems and robust national surveys that improve country information on health needs. There will be an independent evaluation including robust impact analysis. An evaluation framework will be established at the outset to set out the priority evaluation questions throughout the life of the fund.

Acronyms

3 MDG Fund	Three Millennium Development Goal Fund
3DF	3DF
ACT	Artemisinin Combination Therapy
AIDS	Acquired Immune Deficiency Syndrome
AMW	Auxiliary Midwife
ARI	Acute Respiratory Infection
ART	Antiretroviral Therapy
AusAID	Australian Agency for International Development
B/CEmONC	Basic/Comprehensive Emergency Obstetric and Newborn Care
BCC	Behaviour Change Communication
CBO	Community Based Organisation
CCM	Country Coordinating Mechanism (Global Fund)
CEDAW Convention on the Elimination of all forms of Discrimination
        Against Women
CHW	Community Health Worker
CMAM	Community Management of Acute Malnutrition
CRC	Convention on the Rights of the Child
DAC	Development Assistance Committee
DALY	Disability Adjusted Life Year
DFID	Department for International Development (UK)
DHS	Demographic Health Survey
DOH	Department of Health
DPT3	Diphtheria, Pertussis, Tetanus (3rd immunisation)
EC	European Commission
EHSP	Essential Health Service Package
EPI	Expanded Programme on Immunisation
EU	European Union
FB	Fund Board
FM	Fund Manager
FSW	Female Sex Worker
GAVI	Global Alliance for Vaccines and Immunisation
GDP	Gross Domestic Product
GFATM	Global Fund to fight HIV/AIDS, TB and Malaria (Global Fund)
GNI	Gross National Income
GOB	Government of Burma
HIV	Human Immunodeficiency Virus
HMIS	Health Management Information System
HSS	Health Systems Strengthening
ICER	Incremental Cost Effectiveness Ratios
ICPD	International Conference on Population and Development
IDU	Injecting Drug User
INGO	International Non-Government Organisation
IOM	International Organization for Migration
IP	Implementing Partner
ITN	Insecticide Treated (bed) Net
JICA	Japan International Cooperation Agency
JIMNCH	Joint Initiative on Maternal and Neonatal Child Health
LBW	Low Birth Weight
LIFT	Livelihoods and Food Security Trust Fund
LiST	Lives Saved Tool
LLIN	Long Lasting Insecticide Treated Net
M&E	Monitoring and Evaluation
MDG	Millennium Development Goal
MICS	Multi Indicator Cluster Survey
MNCH	Maternal, Newborn and Child Health
MMA	Myanmar Medical Association
MOH	Ministry of Health
MOU	Memorandum of Understanding
MSI	Marie Stopes International
MSM	Men who have Sex with Men
MTE	Mid-Term Evaluation
MW	Midwife
NGO	Non-Government Organisation
OECD	Organisation for Economic Cooperation and Development
ORS	Oral Rehydration Salts
PHC	Primary Health Care
PMTCT	Prevention of Mother-to-Child Transmission (HIV)
PONREPP	Post-Nargis Recovery and Emergency Preparedness Plan
PSI	Population Services International
RDT	Rapid Diagnostic Test
RH	Reproductive Health
RHC	Rural Health Centre
SCG	Senior Consultation Group
STI	Sexually Transmitted Infection
TB	Tuberculosis
TBA	Traditional Birth Attendant
TCG	Tripartite Core Group
TMO	Township Medical Officer
TOR	Terms of Reference
TSG	Technical and Strategy Group
UN	United Nations
UNAIDS	Joint United Nations Programme on HIV/AIDS
UNDP	United Nations Development Programme
UNFPA	United Nations Population Fund
UNHCR	United Nations High Commission for Refugees
UNICEF	United Nations Children’s Fund
UNOPS	United Nations Operations and Procurement Services
USAID	United States Agency for International Development
US$	United States Dollars
VCT	Voluntary Counselling and Testing
VFM	Value for money
WFP	World Food Programme
WHO	World Health Organisation

Business Case

Strategic Case

A. Context and need for a DFID intervention / Country Context / Burma is geographically and culturally diverse with an estimated population of 57.5 million[3] people comprising 135 groups speaking over 100 languages and dialects. Ethnic groups comprise an estimated 35-40% of the population. Approximately 32% of the population live in urban areas[4]. / Despite its vast natural resources and rich potential Burma is one of the least developed countries in the world. The country ranks 132 among 169 nations on the UN Human Development Index[5] and has a lower economic growth rate than all of its neighbouring countries. 25% of the population live below the poverty line, with 5% living in extreme poverty[6]. Poverty incidence shows sharp inequities: / Poverty is twice as high in rural areas (29%) than urban areas (15%), / Poverty is highest in the rural areas of the ethnic states of Chin (80%), Rakhine (49%), Shan (39%) and Kachin (31%). / 68% of all household expenditure is spent on food. More than one third of all households have insufficient money to cover basic food and non food needs. / Prevalence of malnutrition is high (32%), and particularly so in Rakhine (53%) and Shan (48%). / Levels of public expenditure are low and social sectors are critically under-funded. There has been no World Bank lending since 1987 and no IMF programme since 1981-1982. Overall development assistance is the second lowest per capita amongst low-income countries. / Political Context / Burma’s political settlement is fragile and excludes many groups in society. Burma was under military rule from 1962 to end 2010, with more than 60 years of internal conflict. As well as the political opposition, the aspirations of Burma’s ethnic minorities (30%-40% of the population) for a degree of local autonomy, control over their resources and recognition of their language and culture have gone largely unmet. Conflict is now confined to a few parts of the country, but the historical causes of conflict still have the potential to drive future fighting if they are not addressed. In conflict areas, fighting is accompanied by serious human rights abuses. / Military rule has given a low priority (and few resources) to basic services over decades but there are signs that long term political change is underway. In 2010 elections brought new government and constitution which makes provisions for a degree of local decision-making in the 14 state and regional parliaments. Elections were not judged free and fair by the international community. However, Aung San Suu Kyi was released from house arrest in November 2010 and the NLD party contested bi-elections in April 2012, winning 42 out of 44 seats. A number of political prisoners have been released. There is cautious optimism on progress on reforms, and the international community is increasing its engagement significantly. Any lasting reform will require settlement of former ceasefires and the on-going conflict along Burma’s borders. In Kachin and Rakhine States conflict has escalated in recent months. / DFID’s increasing aid is provided within the parameters of European Union Council Decision (EUCD) on Burma, which imposes sanctions on the regime’s leaders, and restricts non-humanitarian aid to certain sectors. This Council Decision was suspended in April 2012. Donor assistance in Burma reflects the OECD Principles for Good International Engagement in Fragile States, which aim to build effective and responsive institutions capable to promote sustained development.[7] / Sustainable poverty reduction will require more than humanitarian aid. It requires respect for human rights, political reconciliation, more accountable government and sound economic policy-making. Analysis of the causes of conflict and fragility[8] indicates that sustainable poverty reduction depends on changes that can catalyse social interaction, local decision making and accountability and state-responsiveness. These changes are essential for the sustainability of any future democratic society. / Women and men have equal rights under the law, including in employment, and gender-based discrimination is not highly visible, but traditional attitudes and behaviours towards women persist. Low investment in health, education and other areas of service delivery, coupled with chronic poverty and under-nutrition tend to have stronger impacts on women and girls as they are responsible for the family, and tend to be more vulnerable. Availability of data in Burma is limited, so it is difficult to compare gender equity indicators with other countries, but progress appears patchy. There are some promising signs: there is a new National Strategic Action Plan for Women, which the Ministry for Women’s Affairs will adopt, which sets out a strategy to address the commitments of CEDAW in the Burma context. However, implementation of the plan requires political will and financial resources for specific programming and mainstreaming across sectors / Health in Burma / Burma is unlikely to meet the health Millennium Development Goals[9] without a significant increase in funding for the sector and in access to essential health services for the poorest and most vulnerable. Low levels of public expenditure and poor service provision are reflected in overall health indicators (see Table A1). The National Health Plan 2007-2011 highlights persisting high rates of maternal and child mortality and of communicable diseases, which are attributed to fundamental weaknesses in the health care system, particularly in rural areas. / Overall official Burma health indicators are poor for the region, and for some areas – malaria, malnutrition and tuberculosis– Burma ranks amongst the highest burden countries in the world. / Table A1: Selected health indicators in Burma / Burma[10] South East Asia[11] / Comparison of key indicators / Maternal mortality ratio 240/100,000 live births 300/100,000 live births / % deliveries with skilled birth attendant / % women delivering at home 57% [12] / 64%[13] 75% / Contraceptive prevalence rate 46%[14] / Under-five mortality rate 71/1,000 live births 38/1,000 live births / Neonatal mortality rate 48/1,000 live births[15] / Moderate and severe stunting (height for age) in under-fives 48%13 22% / Children with pneumonia treated with antibiotics 34%13 / TB prevalence 525/100,000 population[16] / Malaria incidence / Estimated annual number of malaria cases 170 new cases per 1000 population[17] / 4.2-8.6 million,[18] 26 new cases per 1,000 population / Access to clean water 80% / HIV prevalence (15-49 year olds) 0.61% / Maternal, newborn and child health / At least 2,400 pregnant women and 70,000 children under five die from preventable causes every year[19]. Although H4 time trend estimates show a small reduction in maternal mortality from 250/100,000 live births in 2005 to 240/100,000 live births in 2008, the rate of decline is slow regionally. The trend analysis is based on modelled analysis based on official data. Antenatal care coverage has variable quality. 64% of deliveries take place at home[20], and 90% of maternal deaths occur in rural areas. Emergency obstetric care is limited and often unaffordable to the poor. / The under-five mortality rate is estimated at 71 and 66 per 1,000 live births by the UN and Ministry of Health respectively[21]. The risk of neonatal death is higher in home deliveries in rural areas and in deliveries conducted by a volunteer auxiliary midwife or traditional birth attendants. The main causes of death in children under five are ARI, including pneumonia (28%), diarrhoea (18%), cerebral malaria (17%) and malaria (8%)[22]. Malnutrition is a contributing factor in a high proportion of deaths[23]. / Communicable diseases / Among specific diseases, the leading causes of death and illness in Burma are TB, malaria and HIV/AIDS. The 2009-2010 national survey found that TB prevalence was up to three times higher than previously thought[24]. Prevalence is estimated at 525 TB cases per 100,000 population, although in parts of the major cities (Rangoon and Mandalay) prevalence is estimated to be over 1000 per 100,000 (1%) of the population. No country has experienced such a drastic upward revision in TB estimates in a decade[25]. Multi-drug resistant TB (MDR-TB) is also a concern[26]. / Malaria is a major cause of death and illness in adults and children. Estimates of the number of cases of malaria range from 4.2 million to 8.6 million a year, and 76% of the population lives in malaria-endemic areas[27]. The emergence of artemisinin-resistant malaria on the country’s eastern borders is threat to global malaria control. Experts agree that there is a limited window of opportunity to contain resistant parasites before they spread to areas of higher transmission. The urgency is increased by the fact that no other antimalarial medicines are currently available that offer the same level of efficacy and tolerability as artemisinin combination therapy (ACTs). A comprehensive national response strategy, the Myanmar Artemisinin Resistance Containment Framework (MARC), in line with the WHO Global Plan for Artemisinin Resistance Containment, was launched in March 2011[28]. / HIV is concentrated among most-at-risk groups, with overall prevalence of 0.6% of the adult population. Prevalence is estimated at 11% in female sex workers, 11% in men who have sex with men, and 28% in people who inject drugs. Only 20% of those in need receive antiretroviral treatment. / Health sector policy context / The national policy framework in the sector is relatively well developed. The National Health Policy outlines a primary health care approach, producing sufficient human resources for health, expanding health services not only to rural but also to border areas, and augmenting the role of the private sector and NGOs in delivery of health care[29]. Rural health is also an emerging policy priority. / The GoB has recently announced commitments to the Global Strategy for Women and Children’s Health to 2015 including: 80% antenatal care coverage; 80% of births attended by a skilled attendant; 70% access to emergency obstetric care; and 80% coverage for prevention of mother-to-child transmission of HIV and integration within MCH care. GoB has committed to universal childhood immunisation coverage, increased coverage of newborn care, increased contraception prevalence to 50%, and improve the midwife to population ratio from 1:5,000 to 1:4,000, / Institutional context / The MOH is organised at three levels: central, 7 regions and 7 states, and 66 districts and 325 townships. Health Committees at each level support collaboration and coordination. Decentralisation is currently under consideration. Township health administrations serve a population of 100,000-300,000 and are headed by a Township Medical Officer. In rural areas, Township Health Departments oversee 1-3 Station Hospitals and 4-5 Rural Health Centres. Each Rural Health Centre has 4-7 sub-centres and outreach centres. Sub-centres are staffed by a midwife and a public health supervisor, while community level services are provided by volunteer community health workers and auxiliary midwives. / Economic and social context of the sector / Burma has one of the lowest levels of spending on health[30] in Asia and the second lowest per capita aid expenditure amongst low-income countries. There are significant inequalities in health status and access to quality health care, especially in rural and hard-to-reach areas and among the most vulnerable populations. Many areas of the country are poorly served by health services, hindered by geographical remoteness and conflict. Immunisation rates are low in geographically inaccessible and conflict affected areas, among the urban poor, and the socially and economically marginalised[31]. Gaps exist between the poor and non-poor, urban and rural dwellers, and between ethnic regions with respect to health outcomes, nutritional status, health services, antenatal care and skilled attendance at birth[32]. Even where services are available, access for the poorest is limited by financial and other barriers. High out-of-pocket expenditure means that households bear the brunt of health financing. Serious illness or a medical emergency can lead to ‘catastrophic’ expenditure, resulting in or exacerbating household poverty. / Equity in access to public services requires efforts to improve service coverage for hard to reach areas and populations. This will need to be in partnership with non-state actors who can help reach these vulnerable populations. Challenges of expanding coverage are considerable since non-state organisations are only permitted to work in geographic areas as per their MOUs with government. Private for profit providers are largely unregulated and not limited by MOU. / Maternal and child health indicators underline that women and girls of reproductive age, and young children, are the most adversely affected by the lack of affordable, quality health services. There is a lack of gender analysis and gender-related health research on issues such as health-seeking behaviour and access to and quality of health care. Rights and accountability have been given little attention in the health sector in Burma. / Health system challenges / The health system in Burma faces limitations in each of the building blocks of strengthening[33], which undermine the delivery of basic health care. Key challenges are summarised below. / Health financing / The public health sector is critically under-funded constituting 0.2% of GDP and less than US$1[34]. Overall per capita health expenditure, including donor support, public and out-of-pocket expenditure, is less than US$8 per year[35]. International estimates for the cost of financing an essential package of health services range from US$12 to US$34 per capita per year[36]. / Out-of-pocket expenditure represents more than 80% of total health expenditure (see Figure 1), A 2007 survey found that out-of-pocket expenditure ranged from US$22 to US$90 per capita per annum. More than 90% of these households reported that they sought care from the private sector[37]. / Figure 1 Health Expenditure by Source of Fund 2002-2007 (MMK million) / Cost sharing in public health services and patient costs of reaching these services accounts for a significant proportion of out-of-pocket expenditure. Informal payments in public health facilities and income generation from out-of-hours private practice are reported. This may result in a bias in health care provision by township health staff towards curative care[38]. / Health planning and management / The situation analysis in the National Health Plan highlights the need to strengthen the management role of the township health team and for better coordination and integration of services, including stronger partnerships between the public and private sectors. A multiplicity of programmes and projects, with separate planning, management and monitoring arrangements, contributes to inefficiencies and fragmentation in service delivery. There are few administrative staff to support the Township Medical Officer’s wider planning, management and coordination role. / Health Workforce / There is currently no strategic plan for human resources for health, although the GoB has committed to the development of a strategic plan for 2012-2015. According to WHO, 23 health care providers with midwifery skills are required for a population of 10,000 in order to achieve 80% coverage of skilled delivery. In Burma, the corresponding figure is 14 health care providers per 10,000, with most being concentrated in urban areas, leaving rural areas severely underserved.[39]. / Between 1988 and 2007 the number of medical graduates doubled, but the number of midwives increased by only 11%. Most midwives have to wait 3-5 years for a government appointment due to the shortage of staff positions. A recent analysis of the workload of midwives found lack of clarity of functions, overload with administration and role confusion with other staff. In more remote, insecure and culturally diverse regions, midwives are difficult to retain, resulting in significant numbers of unfilled posts[40]. Volunteer auxiliary midwives and community health workers play a critical role in provision of community level health care. Lack of consistency in types of cadres, training and incentives provided by different programmes and projects remains a challenge. / Infrastructure, drugs and supplies / The rural health centre and sub-centre health infrastructure is limited; with many facilities requiring upgrading and refurbishment[41]. Between 1988 and 2007, there was a 31.8% increase in the number of hospitals but only a 10.2% increase in the number of rural health centres. / The public sector budget for pharmaceuticals was less than US$2m in 2007. Most of the drugs and supplies available in the public sector are procured by donor-funded programmes. Consequently, most donor-funded programmes use parallel warehousing and distribution mechanisms. / Health information / Accurate population data is not available and there is no Demographic Health Survey. Health data is inconsistent, with variations in estimates for key indicators. E.g. estimates of the annual number of cases of malaria vary from 0.5 million; to 4.2 million[42], to 8 million cases17. Official and UN statistics of key indicators are based on national surveys, which may omit parts of the country affected by conflict, and datasets are not available for external validation. The National Health Plan notes the lack of quality data and the under-utilisation of health research. There are gaps in evidence, and there has been limited systematic analysis of cost-effectiveness or service delivery costing. / Leadership and Governance / Stewardship of the health sector is limited. Users of public health services have little influence on decisions about health care. Finding ways to improve the responsiveness of health services[43], through rights-based approaches and improving accountability is a challenge in Burma. Regulation, accreditation and quality assurance are critical to enable the poorest to benefit from good quality services delivered by non-state providers. The MOH and decentralised health authorities require support to develop the capacity to oversee the provision of services by non-state providers. / Other actors in the health sector / UN agencies / There are 13 UN agencies in Burma, supporting projects that address MNCH, HIV, TB and malaria as well as supporting the MOH on policy development and implementation. UN agencies channel funds through the government and through international and local NGOs for service delivery. UNOPS is currently the Fund Manager for the 3DF and the JIMNCH. / Civil society organisations / Since the mid-1990s, the GoB has allowed a growing number of international NGOs to work in the country, including in some sensitive border areas. In the health sector, the areas of operation and scope of work of NGOs must be agreed in a MOU with the MOH. Some NGOs, and many CBOs, provide health services to hard-to-reach areas and populations. Religious organisations have set up social welfare and development programmes serving local communities.[44] These non-state actors have a long history of community-based work, have a sound understanding of the constraints and opportunities in each area and have built trust with local communities. / Private sector / The private sector is an important provider of health care. The private sector is estimated to account for 75-80% of ambulatory, 83% of diarrhoea, 90% of ARI, 20% of TB care. An estimated 7-10 million cases of malaria are treated by the private sector[45] as compared to an estimated 0.5 million cases by the public sector and NGOs. A significant proportion of family planning services are delivered through private not-for-profit organisations such as PSI and MSI, working through private sector channels. / The health sector in Burma has examples of international good practice in terms of representation and accountability of national coordination and oversight bodies. The Country Coordinating Mechanism (CCM) has been re-convened to provide oversight of the national strategies of HIV, TB and malaria. This is a unique coordination forum for this setting where elected representatives of people living positively with HIV sit alongside the representatives of Ministries of Health and Home Affairs, UN, donors and NGOs to agree policy direction for HIV, TB and malaria. Under the CCM, Technical and Strategic Groups (TSGs) have been set up for HIV, TB, malaria and MNCH. A separate National Health Sector Coordinating (NHSC) Steering Committee has been convened for HSS to focus is on the GAVI funded health systems strengthening project. / Burma remains a difficult operating context. Requirements for MOUs, visas, and travel permissions influence coverage and scope of some programmes. Time for approval of official requirements can be lengthy. Permissions to operate need to be negotiated with officials at lower levels of government. A number of planned activities are postponed or cancelled due to these bureaucratic controls. / Current health funding mechanisms and resources / Until 2011 the largest contributor to health was the 3DF which contributed 30-50% of national targets and 10% of the overall needs to fight HIV/AIDS, TB and Malaria. This $138 million multi-donor fund (2007 to 2012) has shown that it is possible to deliver health aid effectively within the framework of the EU Council Decision on Burma. Programmes are implemented through UN agency support to the national programmes and public health system, and international and national NGOs. Since starting operations, 47 million condoms have been distributed to prevent HIV infection; 1.5 million people treated for malaria; 138,000 people identified with TB and life saving drugs provided each year to over 15,000 people living with HIV. DFID contributes £34 million ($56 million or 42%) to the 3DF. / The success of the 3DF helped persuade the Global Fund for HIV, TB and Malaria to return to Burma in 2011 after a six year gap. Burma was awarded up to US$305 million over 5 years by the Global Fund Round 9 to support national programme responses to HIV, TB and malaria. / In November 2011 the Global Fund announced that it was cancelling Round 11 and reducing by up to 25% the second phase budgets of existing grants due to lack of funding. Burma had been preparing a proposal for the round, and its cancellation represents a risk to protecting the modest gains in recent years and addressing new health threats. / However, on 15th December 2011 the Global Fund released details of the Transitional Funding Mechanism for two years from 2012-2014 and Burma is identified as eligible. The CCM is currently preparing a case to (i) demonstrate where it can make efficiency gains or austerity measured to reprogram funds to priority areas (ii) make a case for the existing Round 9 grants and (iii) demonstrate needs for transitional funding for Burma, in particular to address artemisinin resistant malaria. This is discussed further in the Management Case, Risk section. / GAVI is funding the main initiative to strengthen the health system in Burma. The $34 million HSS plans to cover 180 townships in hard-to-reach areas. The programme is based on a coordinated township assessment and plan, and funds are channelled to MOH through WHO. / A new partnership to deliver essential health services at township level is beginning to address particularly hard-to-reach MDGs such as maternal mortality. Australia, Norway and the UK are funding the Joint Initiative on Maternal and Neonatal Child Health. These donors have committed US$12.8 million, which represents per capita per year expenditure of US$4.54. This 3-year initiative targets 5 townships in areas affected by Cyclone Nargis, providing an integrated package of MNCH services, including nutrition and immunisation, as well as responding to psychosocial needs and supporting emergency preparedness activities. Activities are based on joint assessments and township plans developed with service delivery partners and the Township Medical Officer. The JIMNCH is implemented through international organisations in partnership with township health services. The JIMNCH has piloted a minimum ‘service commissioning’ approach to funding. This standardisation of approach has allowed more detailed analysis of unit costs and standardisation of delivery. The UK contributes $8 million (£4.95 million or 62%) for the JIMNCH. / Rationale for DFID investment / DFID’s Business Plan and Structural Reform Plan 2011-2015 commits to honour the UK’s international commitments to achieve the MDGs. This includes embedding plans to take forward the promotion of choice for women over whether and when they have children and action to restrict the spread of major diseases like HIV/AIDS, tuberculosis and malaria. Two framework papers set out specific priorities for the UK. The Framework for Results for improving reproductive, maternal and newborn health details how DFID will double the number of maternal and newborn lives saved, and enable 10 million couples to access modern methods of family planning over the next five years[46]. The UK’s Framework for Results on Malaria outlines the UK commitment to contribute to halving malaria deaths in at least ten high burden countries by 2014/15. / Tackling maternal and child health, and major communicable diseases in Burma has strong strategic fit with DFID health priorities: / Burma is one of five focus countries in Asia in the DFID Framework for Results for Maternal, Newborn and Reproductive Health. Burma’s overall health indicators are poor and there are sharp inequities in access by the poor to maternal and newborn services. / Burma has been identified in the Malaria Framework for Results contributing to both strategic priorities, namely reducing mortality and morbidity in high burden countries and sustaining the gains into the future. Burma has the highest malaria burden in the region and is the main focus of DFID’s programme response to the emergence of artemisinin resistance amongst the countries in the front-line of containment efforts (Cambodia, Thailand, Vietnam and Burma). / Improving reproductive, maternal and newborn health is one of the most cost-effective ways to empower women and has far-reaching returns for women, families, societies, economies and the environment. The Framework is an important way in which women and girls are being placed at the heart of the UK’s development assistance. / The UK promotes investments in enabling people to increase their health assets and rights[47].11 Women’s and children’s health is recognized as a fundamental human right in treaties such as the International Covenant on Economic, Social and Cultural Rights, the Convention on the Elimination of All Forms of Discrimination against Women, and the Convention on the Rights of the Child. / Improving access to health care helps tackle poverty. It enables poor families to spend more money on food, housing, education and activities that generate income. Preventing illness and disability saves billions of dollars in treatment and promotes productivity and economic growth. Healthy women work more productively, and stand to earn more throughout their lives. Addressing under-nutrition in pregnant women and children leads to an increase of up to 10% in an individual’s lifetime earnings[48]. In contrast, poor sanitation leads to diarrhoea and parasitic diseases, which reduce productivity and prevent children attending school. 30 to 50% of Asia’s economic growth from 1965 to 1990 has been attributed to improvements in reproductive health and reductions in infant and child mortality and fertility rates[49]. In many countries, every dollar spent on family planning saves at least four dollars that would otherwise be spent treating complications arising from unplanned pregnancies. / Investing in health in Burma can help support peace building goals. In this complex context, health is perceived as a largely neutral area where it has been possible to support multi-stakeholder responses to issues. This builds bridges between different groups, systems and wider society. Well in advance of recent political changes, the government health sector has been increasingly prepared to work with civil society and adhere to international standards for aid, for examples: / Accountability mechanisms such as the CCM for HIV, TB and malaria, and township coordination forums provide a platform to promote greater responsiveness and accountability of services. / In Cyclone Nargis affected areas joint needs assessments and township health plans have been developed under the leadership of the Township Health Authorities in partnership with NGOs / The new Government has committed to address health needs of poor and remote populations. / The New Deal for engagement in fragile states agreed in Busan in 2011 highlights the need for international partners to harmonise with the national and local context, and avoid support for short-term results at the expense of medium to long-term sustainable results brought about by building capacity and systems[50]. Experience in Burma’s health sector shows that assistance can move towards more sustainable results, and support more accountable and fair service delivery. / The key priorities for DFID Burma are areas where change may be possible and where aid can be instrumental: the rural economy; civil society, and service delivery at a local level. DFID Burma programmes need to meet basic needs and maximise their contribution to longer-term changes that address the root causes of conflict and fragility. The DFID Burma Operational Plan (2011-2015) has a strong focus on girls and women, with targeted interventions to reduce maternal mortality. / Feasibility of intervening / DFID has a strong track record in health in Burma, as lead donor. DFID has played a key leadership role in the 3DF, responding to the emergence of drug resistant malaria and establishing the JIMNCH after Cyclone Nargis. / A number of key lessons have been learned from working in the health sector since 2007[51]: / Aid can be delivered effectively, results achieved and vulnerable populations reached through increased and focused investment despite a challenging political and operating environment. / Effective and functional governance arrangements can be established for joint donor support. / The MOH is open to coordination with partners, and their ownership and leadership is critical. / Effective national coordination structures, such as the CCM and TSGs led by the MOH, that are consistent with the principles of accountability and transparency can be established / Some current programming approaches contribute to fragmentation in service delivery and uneven geographical coverage[52]. More effective coordination between partners is critical. Joint assessment and planning of health needs and interventions is feasible at township level, as are complementary working relationships between the public sector and the non-public sector / Partners need predictable, multi-year funding for sustainable support for interventions / Involvement of the private sector in improving access to health care for the poor is feasible[53]. / Donor collaboration through the 3DF has supported the aid effectiveness principles to the extent possible and reflected the OECD DAC principles of engagement in fragile states[54]. The 3DF has been supported through a pooled donor fund, involving seven donors, resulting in harmonised support aligned as far as possible with national strategies. It has facilitated the development of joint donor planning, implementation and reporting frameworks. It has enhanced health sector coordination, strengthened national plans and increased country leadership and ownership.
B. Impact and Outcome that we expect to achieve / DFID will work with international donors, including Australia, Sweden, Denmark, Norway, Netherlands and the EU to contribute towards the health MDGs through a rights-based approach[55]. / The impact of the funding will be improved maternal, newborn and child health and a reduction in communicable disease burden. The outcome is that by the end of the programme there will be increased access and availability of (i) MNCH services in areas supported by the 3MDG Fund and (ii) HIV, TB, and malaria interventions for populations and areas not readily covered by the Global Fund. This will be achieved through the expansion of coverage of essential health services, particularly for the poor and most vulnerable. Supportive health systems strengthening will promote longer term sustainability. Work on improving voice and accountability through capacity development of target communities, civil society organisations and the public sector will lead to increased responsiveness of services to citizen’s health needs. The way in which the health funding is implemented is expected to enable and support wider transformational change in health sector, and Burma. / Modelled projections suggest that the programme might be expected to save the lives of 25,150 children under five; and 3,153 pregnant women (of which 11,569 and 1,450 are attributable to DFID) and significantly reduce the disease burden in mothers and children. For most interventions, a cumulative increase in coverage of 25% over 5 years is anticipated in programme areas. / It is estimated that over 5 years this programme will result in: / 613,000 women delivering with the help of a nurse, doctor or midwife; an increase from 56% to 81% (282,000 deliveries attributable to DFID) / An additional 47,000 pregnant women receiving antenatal care; an increase from 64% to 85% in programme areas (22,000 attributable to DFID) / 290,000 unwanted pregnancies averted (134,000 attributable to DFID) / An additional 121,000 children immunised with three doses of the vaccine to combat the childhood diseases of Diphtheria, Pertussis, Tetanus (DPT3) (56,000 attributable to DFID); an increase from 85% to above 95%. / An additional 120,000 children immunised against measles (55,000 attributable to DFID); an increase from 82% to above 95%. / An additional 35,000 infants, 0-5 months, exclusively breastfed (16,000 attributable to DFID). / 200,000 people reached with prevention or treatment in high risk malaria drug resistant areas / Efforts to address emerging threats will have significant wider social and health benefits. The funding will support women to constitute over 30% of community level and township level oversight bodies. / These results will be achieved through: / Delivery of MNCH services in targeted townships with a focus on hard-to reach populations. / Strengthened systems for the delivery of essential MNCH services in programme townships. / Prioritised HIV, TB and malaria interventions provided to targeted populations or areas not readily covered by the Global Fund. / Prioritised components of the health system are strengthened for long term sustainability. / Enhanced health services accountability through participation of beneficiaries and ongoing consultation with target communities on quality, relevance, availability and accessibility of services. / Optimal fund management results in use of evidence generated to inform policy, funding and programming decisions. / Indirect benefits include increased capacity of state and non-state actors to deliver health services; improved sector governance; increased civil society participation in health and services more responsive to needs of people. / Not intervening would mean that the expected health impacts of the 3MDG Fund will be significantly reduced: the expected health impact on maternal and child health, HIV/AIDS, TB and malaria would fall significantly in the country. Furthermore the broader health gains made from investing in health systems strengthening would not be realised. Furthermore, DFID technical advice to the programme would cease.
[3] UN Thematic Analysis March 2011 (Statistical Yearbook 2009, CSO)
[4] UN country profile Burma
[5] UNDP Human Development Report 2010.
[6] UNDP Integrated Households Living Conditions Survey, 2010
[7] The principles are: take context as the starting point, do no harm, focus on state-responsiveness, prioritise prevention, recognise the links between political, security and development objectives, promote non-discrimination as a basis for inclusive and stable societies, align with local priorities in different ways in different contexts, agree on practical coordination mechanisms between international actors, act fast but stay engaged long enough to give success a chance, and avoid pockets of exclusion. OECD www.oecd.org/dac/fragilestates
[8] Strategic Development Assessment, 2006.
[9] MDG 4 focuses on child health, MDG 5 on maternal health, and MDG 6 on HIV, TB and malaria
[10] Except where indicated, data from United Nations Statistics Division data for Burma.
[11] All figures from United Nations Statistics Division data for south-eastern Asia region, except for Children under 5 moderately or severely underweight. This is indicator for UNICEF region of ‘East Asia and the Pacific’ (includes Burma, Cambodia, China, Indonesia, Papua New Guinea, Philippines). (Note Burma is in UNSD region ‘South East Asia’)
[12] GoUM/UNFPA Country Report on 2007 Fertility and Reproductive Health Survey (2009)
[13] UNICEF Multiple Indicator Cluster Survey. 2010.
[14] UNICEF Multiple Indicator Cluster Survey. 2010.
[15] Ministry of Health, 2003. MICS
[16] Ministry of Health, 2010. Report on national TB prevalence survey 2009-2010.
[17] Korenromp E (2005) WHO/RBM Malaria Incidence Estimates at the Country level for the year 2004
[18] Korenromp E (2005) WHO/RBM Malaria Incidence Estimates at the Country level for the year 2004
[19] UNICEF, 2010. Levels and trends in child mortality. Estimates developed by the UN inter-agency group
[20] Department of Population and UNFPA, 2007. Fertility and Reproductive Health Survey
[21] UNICEF, 2010. Levels and trends in child mortality. Estimates developed by the UN inter-agency group. Ministry of Health, 2003. Burma Overall and Cause specific under-five mortality survey 2002-2003
[22] Ministry of Health, 2003. Burma Overall and Cause specific under-five mortality survey 2002-2003
[23] Globally, under-nutrition contributes to 30% of child deaths. Black R et al, 2008. Maternal and child under nutrition: global and regional exposures and health consequences. Lancet 371(9608): p. 243-260
[24] Ministry of Health, 2010. Report on national TB prevalence survey 2009-2010
[25] External TB programme Review Mission findings, November 2011.
[26] 4,800 cases reported in 2009. Addressing this is a challenge in a country where laboratory technicians and health workers who can diagnose and manage such cases are in short supply.
[27] M&E Reference Group. Roll Back Malaria. 2009
[28] Ministry of Health and WHO. Strategic Framework for Artemisinin Resistance Containment in Burma 2011-2015
[29] Ministry of Health, National Health Plan 2007-2011
[30] Proportion of government expenditure was 1.8% in 2006.
[31] GAVI, 2008. Health systems barriers to improving immunisation and MCH coverage in Burma
[32] UNDP, 2011. Integrated Household Living Conditions Assessment
[33] WHO, 2007. Everybody’s business. Strengthening health systems to improve health outcomes. WHO framework for action
[34] Ministry of Health figures for 2008 and 2009 budgets do not show any fundamental change (respectively MMK 52 and 57 billion)
[35] Ministry of Health, 2008. National Health Accounts 2002-2005; 2009. National Health Accounts 2006-2007 (not published)
[36] The 1993 World Development Report essential package was costed at $12 per capita for low-income countries (now about $16), while the 2001 Commission on Macroeconomics and Health package was estimated at around $34 per capita. According to the 2010 World Health Report, which focused on health financing, low income countries will need to spend around US$60 per capita by 2015 in order to achieve the health MDGs
[37] Ministry of Health, 2007. Health care financing methods and access to health care in Burma
[38] Ministry of Health and GAVI. Mandalay HSS Workshop
[39] 3DF Scoping Mission, 2010
[40] GAVI, 2008. Health System Working Paper: Health systems barriers to improving immunisation and MCH coverage in Burma
[41] GAVI, 2008. Health System Working Paper: Health systems barriers to improving immunisation and MCH coverage in Burma
[42] Country Coordinating Mechanism grant application to the Global Fund 2009
[43] DFID, 2004. Understanding the 'demand side' in service delivery
[44] Kramer 2007.
[45] This represents an estimate of treatments sold, not necessarily malaria cases.
[46] Department for International Development. Choices for women: planned pregnancies, safe births and healthy newborns. The UK’s Framework for Results for improving reproductive, maternal and newborn health in the developing world. 2011.
[47] United Nations. Committee on Economic, Social and Cultural Rights. “General Comment No. 14: The Right to the Highest Attainable Standard of Health” 2000. E/C.12/2000/4. Constitution of the World Health Organization. July 22, 1946. Basic Documents. Forty-fifth edition supplement. October 2006. http://www.who.int/governance/eb/who_constitution_en.pdf.
[48] Horton S, Shekar M, McDonald C, Mahal A, Brooks JK. “Scaling up Nutrition: What will it Cost?” World Bank. Washington DC. 2010.
[49] Maternal, Newborn and Child Health Network for Asia and the Pacific. Investing in maternal, newborn and child health – the case for Asia and the Pacific. World Health Organisation and the partnership for Maternal, Newborn and Child Health. Geneva. 2009.
[50] International Dialogue on Peacebuilding and Statebuilding; A New Deal for engagement in fragile states. Busan 2011.
[51] Verulam Associates Ltd, 2009. 3DF Burma. Mid-Term Evaluation June-July 2009, Final Report
[52] Verulam Associates Ltd, 2009. 3DF Burma. Mid-Term Evaluation June-July 2009, Final Report
[53] Montagu D et al, 2011. Can subsidised private TB care serve the poor? Evidence from Burma. Global Health Group and PSI.
[54] These principles are: take context as the starting point, do no harm, focus on state-responsiveness, prioritise prevention, recognise the links between political, security and development objectives, promote non-discrimination as a basis for inclusive and stable societies, align with local priorities in different ways in different contexts, agree on practical coordination mechanisms between international actors, act fast but stay engaged long enough to give success a chance, and avoid pockets of exclusion
[55] MDG 4: Reduce child mortality; MDG 5: Improve maternal health; MDG 6: Combat HIV/AIDS, malaria, and other diseases.

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / The Appraisal Case puts forward two strategic options 1 & 2. Both options have the same budget (£80m) and some common components, but vary in the nature of the health package, coverage, key stakeholders and implementing partners. Option 3 is a ‘Do Nothing’ case[56]. / Options 1 & 2 both involve complementary funding to the Global Fund for TB, HIV/AIDS and malaria for populations and geographical areas that are not served by the Global Fund; and both involve health systems strengthening on the demand and supply side. The key differences are: / Option 1 proposes an essential package of maternal, neonatal & child health services including community level services and access to emergency obstetric and neonatal care; / Option 2 involves community-level services focusing on maternal, newborn & child health covering a larger number of townships than Option 1. / The Appraisal Case sets out critical arguments for both Options, but proposes that whilst Option 2 is more cost-effective in the short-medium term and would have wider coverage, Option 1 is likely to have longer-term sustainable impact and model best practice on access and improved quality of health care for the poorest populations and engagement in fragile states principles. / Feasible Options / Option Description / 1 / An essential package of maternal, neonatal and child health services including community service and emergency obstetric care and referrals for emergencies / and TB, HIV and malaria and systems strengthening to support longer term sustainability Up to £80 million over five years to 2016 to support the ‘Three MDG Fund’ with three components: / Component 1: Increased availability and accessibility of essential services focusing on maternal, newborn and child health, including community service and emergency obstetric care and referrals for emergencies / Component 2: Flexible and strategic support for HIV, TB and malaria interventions for populations and geographical areas that are not supported by the Global Fund. / Component 3: Complementary health systems strengthening to support long-term sustainability and demand-side interventions to ensure accountability, access and participation of beneficiaries / Contribution towards an estimated $300 million (£180 million) fund. / 2 / Community-level services focussing on maternal, neonatal and child health / and TB, HIV and malaria and systems strengthening to support longer term sustainability Up to £80 million over five years to 2016 to support the ‘Three MDG Fund’ with three components: / Component 1: Increased availability and accessibility of community-level services focusing on maternal, newborn and child health / Component 2: Flexible and strategic support for HIV, TB and malaria interventions for populations and geographical areas that are not supported by the Global Fund. / Component 3: Complementary health systems strengthening to support long-term sustainability and demand-side interventions to ensure accountability, access and participation of beneficiaries / Contribution towards an estimated $300 million (£180 million) fund. / 3 / Counterfactual Release funds for other uses in DFID Burma / Options 1 and 2 / The feasibility of delivering a package of essential services at township level is based on experience of the Cyclone Nargis recovery work, the MNCH Joint Initiative and the GAVI HSS programmes. Based on lessons learnt the proposed approach is a ‘lighter’ implementation model, with a wider set of partners in support of township health services. The approach moves towards a ‘service commissioning’ of partners working together under a coordination framework of the township plan. / Both options include strategic funding to HIV, TB, and malaria. The need to continue funding for these diseases is based on high disease burden, the humanitarian needs of the population and threat to public health. Donors wanted to support areas where there is complementarity and value added to Global Fund through a flexible fund in country. The model for Option 2 is based on the current operation of the 3DF, building on considerable experience and lessons learned. / Options 1 and 2 contain Component 3 - complementary health systems strengthening to develop a more effective and responsive system. Systems strengthening includes measures to strengthen voice, voice and participation by beneficiaries on the ‘demand’ side, and for greater accountability and responsiveness by health service providers on the ‘supply’ side. Global evidence reviews show that demand-side citizen engagement can empower people with greater choice in service delivery, and can also improve access and quality of the services by holding service providers to account[57]. / Overall principles and approach for both option 1 and 2 / Donors are committed to continue joint donor support for the health needs of the most poor and vulnerable in Burma. The design of the 3MDG Fund is intended to promote transformational change and a rights-based approach. This includes support for representative accountability mechanisms that enable communities and beneficiaries to engage in the design, implementation and monitoring of health services, and an emphasis on non-discrimination for excluded and marginalised groups, equality of access to health services, and transparency of information. / Option 1: An essential package of maternal, neonatal and child health services including community service and emergency obstetric care and TB, HIV and malaria and systems strengthening / How it will work: / The logical framework sets out the expected impact, outcome and outputs, as summarised below. / Goal At impact level, the 3MDG Fund is expected to result in: Improved maternal, newborn and child health and a reduction in communicable diseases in areas supported by the 3MDG Fund. / Purpose. The expected outcome of 3MDG Fund support is: Increased access and availability of (i) essential MNCH services for the poorest and most vulnerable in areas supported by the Fund and (ii) HIV, TB and malaria interventions for populations and areas not covered by the Global Fund. / Results 3MDG Fund support is expected to deliver six outputs: / Delivery of essential services, with a focus on maternal, newborn and child health, in townships supported by the 3MDG Fund. / Strengthened capacity for essential MNCH services in townships supported by the 3MDG Fund. / Prioritised HIV, TB and malaria interventions provided to targeted populations or areas not readily covered by the Global Fund. / Prioritised components of the health system strengthened for long term sustainability. / Enhanced health services accountability and responsiveness through capacity development of target communities, civil society organisations and the public sector. / Fund Management demonstrates value for money and cost-effectiveness, generates evidence to inform policy and programming decisions, and strengthens aid effectiveness. / Component 1 / Component 1 is an integrated package of essential health services for MNCH at township level and below, aligned with national strategies. The package consists of cost-effective interventions that will address the main causes of MNCH death and illnesses. Midwives, auxiliary midwives and community health workers will play a role. The 3MDG Fund will support the staff to population ratios to achieve increased coverage: auxiliary midwife 1:2,000 and community health worker 1:2,000. / Box 2: Examples of what will Component 1 look like on the ground / Maternal health services examples Child health services examples / Family planning delivered through public health facilities, community health workers and private sector providers / Skilled birth attendance with doctors nurses and midwives / Emergency obstetric and neonatal care: referrals for emergencies with well trained health staff with the right knowledge skills and equipment. / Prevention and management of haemorrhage after delivery: staff with the right knowledge, skills, drugs and equipment / Antenatal and postpartum care: regular checkups for pregnant women with a midwife (e.g. blood pressure, danger signs etc) / Nutrition: e.g. antenatal checks for anaemia; iron and folic acid supplements for pregnant women / Safe blood supply for obstetric emergencies Essential newborn care: frequent critical checks of the newborn after birth by midwives and auxiliary midwives / Case management of diarrhoea, acute respiratory infection, malaria: oral rehydration salts and zinc; antibiotics; diagnostic tests and treatment for malaria available at community level and in health facilities / Breastfeeding and complementary feeding: promotion of breastfeeding to mothers by midwives, community health workers / Immunisation: midwives vaccinate children at community level / Nutrition: community screening for malnourished children and / Malaria prevention, control and treatment: long lasting bed nets, indoor residual spraying and diagnosis and treatment for malaria / Water, latrines, hand washing: promotion of good hygiene practice by community volunteers / Continuum of care / Pre-pregnancy Pregnancy Birth Neonatal Childhood / This does not include all activities. A summary of the full package of services is provided in Annex 1. / This component will address supply-side barriers through provision of drugs, equipment and commodities; referral for and provision of emergency obstetric and neonatal care, and minor refurbishment of health facilities. Training in MNCH for government-employed Basic Health Staff, in particular of midwives for skilled attendance at birth, community health workers and auxiliary midwives will be a critical element of support (this is included in the budget under health systems strengthening). Training will be based on needs assessment and linked to supervision. / Component 1 will also finance schemes to reduce financial and other barriers to use of health services. A range of initiatives is currently being used or tested. Some focus on reimbursement or subsidy of patient costs, for example, of transport or treatment, while others focus on removal of fees by covering facility costs. These include piloting a MNCH voucher scheme, piloting of community health insurance, and township hospital or equity funds to cover payment for care for the poorest. The approach taken by the 3MDG Fund will be determined by the outcome of an upcoming review, which will map current initiatives, identify options, and agree a way forward with the MOH. / At township level the fund will support several partners in support of the joint needs assessment and implementation of the coordinated township plan. Partners working together are Township Medical Officer and team; UN agencies support to public health facilities, NGO support to community health workers and auxiliary midwives, and private sector channels to reach poor and vulnerable populations. The following diagram summarises how this coordinated approach looks: / Component 1 coordination of partners at township level through a joint assessment and township planning approach. / The number of townships will be scaled up over the duration of the programme, from 10 in Year 1, to 20 in Year 2, and 40 in Years 3, 4 and 5, reaching an estimated total of between 4-12 million people, assuming the population of a township ranges between 100,000 and 300,000. Maximal efficiency and impact depends on fully funding a core package of services across an entire township as opposed to funding a partial package over many townships. Equity will be addressed by targeting the most under-served townships and populations within these townships. / In programme areas over 5 years this investment will result in an estimated : / 3,153 deaths among women during pregnancy and childbirth / 25,150 deaths prevented in children under five / 613,000 women deliver with the a nurse, doctor or midwife; an increase from 56% to 81% / An additional 47,000 women pregnant women receive antenatal care; an increase from 64% to 85% in programme areas / An additional 95,000 children being immunised with DPT3; an increase from 85% to above 95%. / An additional 35, 000 infants aged 0-5 months being exclusively breastfed. / 200,000 people reached with one or more malaria interventions in areas a high risk of artemisinin resistance. / The estimated cost of the township package ranges from US$272,300 in Year 1 to US$946,800 by Year 5. The increased cost over time reflects increased coverage of 5% per annum and commensurate increases in the budget for commodities. The mean estimated annual cost per township per annum is US$605,000. This represents a per capita expenditure of between US$6.05 and US$2.01, assuming the population of a township is between 100,000 - 300,000. If the costs of support for delivery of the package are factored in, the per capita expenditure is between US$11.47 and US$3.82, which is still low compared with international estimates for the cost of financing an essential package of health services, which range from US$12 to US$34 per capita per year. / Component 2 / This component will support priority gaps in the national responses for HIV, TB and malaria that are not readily funded by the Global Fund and funding to respond to emerging health threats. Priority will be given to vulnerable and marginalised populations, including for HIV female sex workers, men who have sex with men, people who inject drugs and prisoners, to hard-to reach areas and to emerging health threats. HIV, TB and malaria interventions funded under the 3MDG Fund will be consistent with national strategies and priority groups. The component will provide technical support for future Global Fund applications. Potential support under Component 2 will be guided by the following principles: / Maintenance of high-priority HIV, malaria and TB interventions currently supported through the 3DF and not readily supported by Global Fund such as work in geographically remote areas or with populations such as prisoners or miners that the Global Fund cannot access. / Top-up support to Component 1 townships where HIV, malaria and TB interventions are required based on the disease epidemiology but are not readily funded by the Global Fund / Interim support for high priority interventions not supported through the 3DF or by Global Fund. Based on a gap analysis, this might include support for life-saving ART, first-line TB drugs, containment of MDR-TB and artemisinin resistance, and safe blood. / Component 3 / Component 3 will support HSS at national, state/region and township levels, to help develop a more effective and responsive health system. This component supports the longer-term sustainability of investment in the MNCH and communicable disease control components of the 3MDG Fund. / Component 3 will encompass support for voice, accountability and transparency both through structures that are directly linked to the 3MDG Fund and through national structures. Support for civil society will emphasise capacity development. It is expected that civil society will play a key role in independent monitoring and feedback and will be responsible to report on specific beneficiary feedback indicators on the logframe. The 3MDG Fund will build on 3DF progress in developing a Beneficiary Accountability Framework (see Box 3), ensuring this is linked to existing township plans. / Box 3: Objectives of the Beneficiary Accountability Framework[58] / Improve the way an agency engages with local communities in decisions that affect them by striving to enhance participation and to seek informed consent. / Share information with beneficiaries to promote and improve transparency and information provision. / Provide beneficiaries with channels through which concerns can be raised. This is part of the ethical commitment to listen, monitor and respond to beneficiary concerns. / Ensure that all staff are provided with a thorough understanding of Accountability and Quality Management Principles and Standards. / This framework is in line with DFID corporate definition of empowerment and accountability as “interventions that enable poor people to have the resources and capability to have greater choice and control over their own development and to hold decision-makers – including governments and service providers – to account”. Guidance notes for DFID country programmes on E&A are also in keeping with the principles of the 3MDG Beneficiary Accountability Framework[59] / The 3MDG Fund will support HSS through policy dialogue and advocacy, technical support, capacity development and training, sector and systems analysis, research studies and other activities to improve information for decision making. Based on initial consultations, the possible scope of 3MDG Fund support for health systems strengthening is outlined below. State and region level support will be determined once the decentralisation agenda has been further developed. / Institutional and sub-systems development / At national level this might include strengthening policy and strategy development for MNCH, sector financing, planning and budgeting; sector coordination; human resources for health; procurement, logistics and supply chain management; and demand-side financing. / At regional/state level this might include strengthening capacity for planning, budgeting, and support to township health authorities. / At township level this might include supporting township health authorities to conduct more comprehensive assessments and develop more detailed coordinated township health plans; and leadership and management training for township health teams. / Strategic information / At national level this might include strengthening the HMIS; supporting communicable disease surveillance; improving the availability of data on maternal and child mortality; strengthening the capacity of the TSG M&E working groups; and supporting health systems and qualitative research. / At regional/state level this might include strengthening the HMIS focusing on analysis, feedback and use of data. / At township level this might include training for township health teams to improve analysis and use of data; and strengthening the maternal and neonatal death audit system. / Stewardship and accountability / At national level this might include developing policy options and approaches to strengthen accountability; training to develop capacity on accountability and responsiveness issues; and improving capacity for oversight and regulation of the private sector. / At regional/state level this might include training to develop capacity on accountability and responsiveness issues. / At township level this might include reviewing the capacity of existing structures for accountability; training for township health teams and committees; capacity building for civil society organisations for independent monitoring of service delivery; strengthening community mechanisms for voice and accountability and ensuring that these are integrated within coordinated township plans. / Expected beneficiaries and key stakeholders / Beneficiaries / The main beneficiaries will be mothers, women and girls of reproductive age, newborns and children under five in townships covered under Component 1. Other members of the community are also expected to benefit from improvements in health service availability and quality. The assumption is that poor people will use public sector services if they are more accessible and of better quality, hence reducing out-of-pocket expenditure. The burden of health care costs for the poor, in particular women and children, will also be addressed by 3MDG Fund support for demand-side financing schemes. These reductions, and changes in access to health services, will need to be monitored through routine data collection, operational studies and population-based surveys. / The main beneficiaries under Component 2 will be people living with HIV and people with TB and malaria in the selected townships. This includes people in hard-to-reach areas, and marginalised groups such as female sex workers, men who have sex with men, people who inject drugs, and prisoners. Efforts to address emerging threats under Component 2 will have significant wider social and health benefits. Apart from the direct beneficiaries of the programme, the wider population should – in the longer term – benefit from Component 3 support to strengthen the health system. / Ministry of Health / The MOH at central and decentralised levels has been consulted on the programme design. Detailed consultations on the operationalisation of the programme in townships will take place directly and through sector coordination mechanisms chaired by MOH (i.e. CCM and relevant TSGs). Areas of support for HSS will be based on joint analysis and consultation with MOH. Senior government representation is expected to be through a Senior Consultation Group which will advise the Fund Board (see Management Case). / Option 2: Community-level services focussing on maternal, neonatal and child health / and TB, HIV and malaria and systems strengthening to support longer term sustainability. / The overall principles and approach of option 2 are the same as options 1. / The key differences (and therefore strategic choice) relate to the types of interventions offered, where and balance of organisations for component 1; and a knock on effect to the opportunities and options for health systems strengthening under component 3. Component 2 support for HIV, TB and malaria remains unchanged. / Component 1 / The basic community package involves scale up of services from 10 to 60 townships from 2012 to 2016. The basic package covers community level services provided by midwives outreach and volunteer auxiliary midwives and community health workers. The supporting rationale for Option 2 is maximum coverage with a limited set of high impact low cost interventions. / Box 3: Examples of what will Component 2 look like on the ground / Maternal health services examples Child health services examples / Family planning delivered through community health workers and private sector providers – mainly pills and condoms / Skilled birth attendance at community level / Antenatal and postpartum care: regular checkups for pregnant women with a midwife (e.g. blood pressure, danger signs etc) / Nutrition: e.g. antenatal checks for anaemia; iron and folic acid supplements for pregnant women / Safe blood supply for obstetric emergencies Essential newborn care: frequent critical checks of the newborn after birth by midwives and auxiliary midwives / Case management of diarrhoea, acute respiratory infection, malaria: oral rehydration salts and zinc; antibiotics; diagnostic tests and treatment for malaria available at community level and in health facilities / Breastfeeding and complementary feeding: promotion of breastfeeding to mothers by midwives, community health workers / Immunisation: midwives vaccinate children at community level / Nutrition: community screening for malnourished children / Malaria prevention, control and treatment: long lasting bed nets, indoor residual spraying and diagnosis and treatment for malaria / Water, latrines, hand washing: hygiene promotion by community volunteers / In contrast to Option 1 it does not include: / Basic or comprehensive emergency obstetric and neonatal care (BEONC and CEONC) / Patient costs for referrals for emergencies and support for essential referral services offered at township hospital and health facility levels / A fuller range of family planning commodities through public health services, since midwives are not allowed (by law) to provide injectable family planning commodities, and IUDs are only provided in health facilities. / Any health facility based services or minor refurbishment particularly for deliveries (e.g. rural health centres) / Support for basic health staff (except for midwives) except for activities to ensure their adequate supervision of volunteer community-based workers / Modelled estimates for Option 2 suggest it is expected to save more lives: 39,000 in total including the lives of 34,500 children under five; and 4,300 lives of women during pregnancy and childbirth, significantly reducing the disease burden in mothers and children. / Option 2 includes a coordinated approach by a range of service provides including the public sector and township health authorities. With the emphasis on the community-level services the main cadres of health workers are midwives, volunteer community health workers and auxiliary midwives. Programmes supporting these volunteer cadres are supported through UN and NGOs. The most successful programmes, in terms of performance of volunteers are through NGOs. This means the balance of implementing partners for Option 2 will increase towards international and national NGOs as there is less implementation through other parts of the public health system. Funding to support public sector services will be limited to supporting midwife activities at community level. / Component 2 / This component would be identical to Option 1. / Component 3 / The balance of partners for Component 1 will have an impact on the options and opportunity for HSS, and longer term sustainability. Implementation of services at community level through volunteer auxiliary midwives and community health volunteers means that NGOs will have a relatively increased role. Public health service delivery will be limited to the community level activities of midwives. HSS options will remain but be linked to the service supported directly by the Fund. With such limited engagement with public health services, there is a risk that it will not be possible to influence change, particularly on promoting services responsive to the needs of the people. This risk will need to be mitigated through more intensive engagement with township health authorities on the rationale for component 3. / Funding for both Options 1 and 2 will be through a multi-donor funding mechanism, building on the experience of the 3DF. The management arrangements are outlined in the Management Case. / Cross-cutting issues for both Options 1 and 2. / Access, affordability & availability of services / The programme aims to ensure that essential services are accessible, acceptable and of a high quality. This means that the poorest and most marginalised people who are unable to pay for health care will receive financial assistance (demand-side financing). The Monitoring & Evaluation system will track key indicators on these using baseline surveys, qualitative data and routine checks. / Inclusion and human rights / Excluded, marginalised and discriminated groups will receive special attention. Safeguards will be built into ensuring that the benefits of the programme reach those for whom it is intended, and are not subject to ‘elite capture’ or biased selective targeting by local actors. Data will be disaggregated by sex, age and other relevant categories, as appropriate (e.g. ethnicity, religion, disability) and key indicators to measure outcome and impact will be established at the outset. Activities at community level will inform people about their health rights and entitlements. / Voice, Choice and Participation / The programme will support an approach that strengthens the role of all partners, including communities, CBOs and self-help groups in addressing the health MDGs. To achieve this, implementing partners will set out clearly how they will involve beneficiaries in planning, design, implementation and monitoring of health services, as well as supporting participation in township and community coordination mechanisms. In a number of townships the Township Medical Officer already convenes a multi-stakeholder body to coordinate partners working in the health sector, and this offers a potential model for other townships. / Transparency and Accountability / Component 3 activities will support increased accountability and responsiveness, such as strengthening the functions and representativeness of village heath committees and establishing local complaints mechanisms. Health committees will be important focal points for coordination of activities, and the Fund will support efforts to ensure that these structures are representational, transparent and accountable. The Fund will establish clear accountabilities on the part of service providers, defined and monitored at township and community levels, and independent monitoring systems to track levels of satisfaction, uptake and access to services by target beneficiaries. / Transparency / The Fund Manager will make public all official documents, including tender decisions, budgets, programme and project plans, monitoring and evaluation reports. Reporting on Fund’s activities will provide clear and easily understandable information about governance structures, staff roles and responsibilities, implementation progress and results. / Gender / Delivery of essential interventions will benefit women and girls of reproductive age. Public and private health providers will work together to expand women’s reproductive health choices. / Sex-disaggregated data will be collected, and gender-relevant indicators are included in the logical framework. The uptake of services by women will be monitored to ensure services respond to their needs, and are accessible and affordable - if necessary with support of demand-side financing. The programme will ensure that accountability mechanisms support equal engagement of women and men, promote women’s representation and voice, and monitor the participation of women. / The Fund Manager and implementing partner staff are required to have a good understanding of gender issues and access to gender expertise. New research will be commissioned to improve the programme’s understanding of how gender affects health, health seeking behaviour, health care expenditure and other gender-related issues, including knowledge and attitudes of men and women concerning utilisation of health services. / Engagement in fragile states principles / 3MDG Fund assistance will continue to be consistent with donor requirements and policy positions with respect to Burma. Specifically, it will: / Strengthen country ownership / Ongoing support for TSGs, and the development of coordinated township plans will increase ownership, as well as strengthening the coordination sector activities at township level. / Manage aid resources more effectively and aligning these resources for results: / Joint funding arrangements, planning, financial management, M&E and reporting procedures. This complements other donor funded programmes including HSS supported through GAVI and activities supported through the Global Fund, and foster greater coherence and coordination / Strengthened alignment by ensuring interventions are consistent with national strategies on MNCH, HIV, TB and malaria. Support at township level will build on existing coordinated township plans, developed through the GAVI HSS supported assessment and planning process. M&E will be aligned as closely as possible to the HMIS and use national indicators. / Managing for results and mutual accountability through commitment to multi-year funding and aid transparency. Strengthening national and township level accountability mechanisms and building capacity for more responsive, accountable health services. / Theory of Change / The Theory of Change for the next phase of the 3DF is shown diagrammatically on the next page. This is based on a well-evidenced logic in the health sector that increasing availability and access to quality health services and simultaneously reducing demand side barriers will lead to increased utilisation of health services and therefore improve the health of the population. / The underlying logic to the steps from inputs, outputs, outcomes and impact are based on the principles that: / An integrated package of essential interventions delivered at scale leads to significant improvements in health / Partnership of state and non-state service actors can reach poor and vulnerable populations / Strengthening health systems improves access to and quality of health services, improves health outcomes and promotes longer term sustainability / Increased community voice and civil society engagement will lead to increased accountability and responsiveness of services / Strengthened systems, results and accountability will lead to increased government commitment to health / Preventing illness promotes economic growth and enables poor families to spend more money on food, housing, education and income generation / Continued timely access to programme sites (through travel permissions etc) is a core assumption. This includes access for data collection and sharing of data across partners, including information from the health management information system. / Component 1 relies on the assumption that skilled midwives will be available, particularly in hard-to-reach areas, to support increased access to safe deliveries by pregnant women, and increased vaccinations of children under 5 years. The level of the allocation to Component 2, HIV, TB and malaria is based on the assumption of continued support from the Global Fund for the highest priority interventions. The 3MDG Fund would then fill the gaps not readily funded by the Global Fund. Component 3 areas of work to increase voice and accountability rely on the openness and confidence of Ministry of Health, township health authorities and communities to engage in process of feedback and making services more responsive. / Importantly the way in which the Fund is implemented should contribute to indirect outcomes (shown in pink) which support wider transformational change. The Theory of Change best reflects Option 1. The differences in Option 2 which will impact on this Theory of Change: / Option 2 focussed on community level services with limited engagement of the public system / This will lessen opportunities for health system strengthening, and engaging in a process of dialogue and change (see blue boxes at top of Theory of Change) / This is likely to reduce the indirect outcomes of promoting responsive services, improving sector governance and increasing capacity of public services to deliver essential health care / “Do Nothing” counterfactual / This involves DFID not funding the 3MDG Fund and allocating the resources for other purposes. This would result in a large funding gap, and likely redesign and significant scale down. There is a risk that a downsizing of the programme would mean that essential elements of the programme package would need to be removed. DFID technical advice to the programme would cease. / The health impacts of will be significantly reduced, including MNCH, HIV/AIDS, TB and malaria nationally. Furthermore the broader health gains made from investing in HSS would not be realised. / The only alternative funding is to fund a number of bilateral projects with different non-governmental implementing partners to deliver the same type of services as through the 3MDG Fund. It is not possible to fund through government. Funding bilaterally would not generate the same results or scale as the 3MDG Fund. This is because DFID alone would not have the capacity to manage the sheer number of projects in the number of townships required to generate similar results. DFID would not be able to fund the projects to the extent required to avail of economies of scale; to draw lessons from one township to another; or to be able to draw lessons from one township to another or leverage opportunities to promote longer term transformational change through engagement at sectoral level. This would particularly apply to options for supporting HSS for longer term sustainability and promotion of greater accountability and responsiveness of services. Experience from 3DF shows that there is value added for donors to work collectively when mitigating risks related to the complex operating environment. There is strong donor commitment to work together and the benefits of a multi-donor mechanism of coordination were judged to greatly outweigh a DFID bilateral programme approach[60]. / Allocating resources away from MNCH would mean losing all of the health impact in this area of need. Health impact in other areas would decrease as there are few alternative instruments – again largely because funding through government is not an option.
B. Assessing the strength of the evidence base for each feasible option / Evidence of the need for intervention / Data is difficult to obtain. Some national data is unreliable and availability of good quality evidence is generally limited. A number of clinical research studies are published, with HIV and malaria studies being well represented. Impact evaluation, rigorous programme evaluation and operational research is limited. Our ability to engage in large scale, systematic data collection and impact assessment is limited due to sensitivities of data collection, permission and access restrictions. / Burma health indicators are poor for the region. The basis of these indicators varies considerably. / Estimates of tuberculosis prevalence are based on a jointly funded national survey[61] which is documented as an example of international best practice in the 2010 World TB Report. / Estimates of malaria cases are wide ranging - from 4.2 million[62] to 8.6 million[63] a year, suggesting that the evidence base is weak. / Other official statistics from some national surveys have questions about limited sampling in sensitive or restricted areas; external validation of data sets and the transparency and accountability of survey oversight bodies. / Maternal mortality estimates have been revised globally, but is based on modelled analysis including skilled birth attendance. ‘Skilled’ birth attendance definitions can vary country to country, and Burma is no exception. / Small scale population-based surveys conducted by implementing partners suggest that some of the national statistics may give an optimistic view, or there are sharp inequities in some remote areas so that national averages do not reflect the health needs in these areas. / There are limited studies of where people seek care and why, and what the major barrier to access to health services for poor people. A study of care seeking for maternal services in a township in Yangon identified high rates of antenatal care (79% had at least 4 ANC visits). Nearly 39% of women sampled delivered at home, especially in rural areas, and 79% of home deliveries were attended by TBAs. Only 56.6% of women received at least one postnatal care visit[64]. A series of studies conducted by MOH on maternal health costs shows that the direct and indirect costs of accessing maternal health services are high. A normal delivery costs an average of £54 in a health facility but the cost can rise to over £100 if the woman has an emergency and can rise by an additional £117 if the baby requires hospital care[65]. Such costs can be catastrophic for families pushing them further into debt. There are very few analyses of costs and cost effectiveness of interventions or programmes. Several published papers demonstrate the role of the private sector in the delivery of TB services, and show that they are as accessible, if not more so, for poor populations[66],[67],[68]. A series of papers from Burma’s conflict affected eastern border show human rights and health needs, and assess the feasibility of providing MNCH and malaria services in these areas[69],[70],[71],[72],[73]. An analysis of an approach to HSS provides the basis of the GAVI programme[74]. / The limitations on data collection may be lifting and there is greater openness to research. Under the auspices of the Tripartite Core Group comprising the government, ASEAN and UN, robust population surveys were conducted at regular intervals after Cyclone Nargis. The 3DF has supported national surveys and a robust documentation of lessons is being conducted with MOH and JIMNCH partners. Population-based surveys have been, or will be conducted in each of the JIMNCH five townships. The Management Case sets out a comprehensive M&E approach, building upon the lessons of the 3DF and JIMNCH. Emphasis is on establishing robust baselines and data collection at programme level so that impact can be assessed; and robust strategic information at national level, such as national surveys to improve overall estimates of need. / Evidence of the approach / International evidence-base shows that a package of high-impact, cost-effective MNCH interventions can deliver results[75]. The technical interventions[76][77] and demand- and supply-side policies and programming necessary to address maternal and child death and illness are known. Modelled based analyses[78] coupled with research findings from several countries in Asia[79].[80],[81],[82],[83] have demonstrated the impact of implementing a package of maternal and neonatal services. The service packages are highly cost effective; with a cost per DALY averted of between USD$35 and $200[84],[85]. Family planning to prevent unwanted pregnancies has the potential to reduce 32% (UNFPA estimates) of all maternal deaths.[86] Further, with delivery in equipped clinics with trained midwives, it is estimated that maternal and child deaths could be halved.[87] / Additional impact is achieved with the inclusion of a wider package of cost effective interventions. Providing services in the community through trained volunteers, “community health workers”, can impact on neonatal mortality.[88] Community based case management of diarrhoea, pneumonia and malaria, can reduce under-five mortality. Evidence from community-based trials have demonstrated that in order to maximise their impact the interventions should be delivered as a coordinated package – a “continuum of care”- and that coverage of the interventions must be at scale. This evidence is supported by the Global Consensus for MNCH which recommends a limited set of cost-effective interventions; including quality skilled care for women and newborns during and after pregnancy and childbirth, with access to emergency care; improved child nutrition and prevention of major childhood diseases, including diarrhoea and pneumonia; safe abortion services; comprehensive family planning; integrated care for HIV, malaria and other services[89]. / The evidence base on empowerment and accountability approaches to service delivery is still fairly weak but emphasises the need for context-specific and appropriate systems for community-based approaches to ensure that services match demand and manage expectations of citizens. There is growing evidence that strong partnerships between beneficiaries and service providers can deliver increased efficiencies by targeting services to those who need them most and can improve the effectiveness, responsiveness and capacity of service providers by holding them to account[90]. / There is no evidence from Burma on the impact of implementing a package of essential services focussed on MNCH; or which delivery channels (public, private sector) will deliver most results. The national strategies on HIV, TB, malaria, reproductive and MNCH are based on international evidence. For developing the options for Component 1 we have used modelled predictions based on the Lives Saved Tool (LIST)[91]. This modelling tool allows users to set run multiple scenarios to look at the estimated impact of different intervention packages and coverage levels. LIST uses the UNICEF Multiple Indicator Cluster Survey (MICS) data from 2000. As outlined earlier it is not clear if all data provide robust baselines. It is highly likely that in the targeted poor and hard-to-reach townships the baselines for all indicators will reflect lower health status and service coverage than the national averages used in LIST. With such paucity of data, it was not possible to estimate for each indicator what the possible range would be, so the national data was used in the model. Option 1 and 2 are based on two operationally feasible alternatives; use interventions outlined in the national strategic plans and based on international evidence and estimate the potential impact of the programme. Annex 1 provides a summary of the interventions. Similarly, for HIV, TB and malaria there is little evidence from programmes on what works and why. A final evaluation of the 3DF is currently underway which will examine three areas in particular: impact on health outcomes; impact on the operating context; and cost and cost effectiveness of services. / In the table below the quality of evidence for each option is rated as Strong, Medium or Limited. / Option Evidence rating / 1 Limited / 2 Limited / 3 Counterfactual / What is the likely impact on climate change and environment for each feasible option? / Option 1 and 2 / Overall the environmental risks associated with the 3MDG Fund are low. The main area where there is a potential risk relates to increased environmental contamination associated with the production of hazardous medical waste as a result of expansion of health services into rural areas. This applies to both options but to a lesser extent for Option 2 where the focus is on community level services only, limiting the amount of hazardous medical waste. To mitigate this risk, improved waste management is an integral part of proposed support to townships under both options under Component 3. Effective management of emergencies during pregnancy and delivery will require referral to a health facility and will require transport. The programme should mitigate the risk of some emergencies through better quality antenatal care and of health staff. / The effects of climate change pose a risk to health. Natural calamities such as floods are increasing in incidence, predominantly affecting poor populations. With a large coastal population, Burma is vulnerable to the potential effects of climate change and natural disasters as recently demonstrated by the devastating effects of Cyclones Nargis and Giri. Severe climatic events and natural disasters may interrupt services. Changes in rainfall patterns will further influence the distribution of water and vector-related infections such as diarrhoea and malaria. Shortening of the monsoon season, already being experienced, and flash floods threaten agricultural productivity, increasing the risk of food insecurity and under-nutrition. In turn social and economic impacts of a changing climate, e.g. rapid urbanisation impacts upon communicable diseases and demand for services. Burma’s extremely high prevalence of TB in urban areas, where airborne transmission of the TB bacillus can be increased by overcrowding in poorly ventilated houses illustrates[92]. / Since Cyclone Nargis, the government committed to formulate and implement a natural disaster preparedness plan. As a result of a more effective early warning operation by local authorities and the Red Cross, the loss of life was much lower for Cyclone Giri (2010) than in Cyclone Nargis (2008) (a storm of comparable strength). This augurs well for the introduction of policies that support disaster risk management, as all stakeholders now recognise the importance of such practices. / At health sector level, the building blocks of robust health systems need to include a climate lens, for example comprehensive information systems, including a comprehensive integrated disease surveillance system. Similarly human resource policies need to include emergency preparedness and disaster response. The 3MDG Fund has an entry point through Component 3 to ensure that climate change is well addressed in health systems strengthening. / Reported sanitation coverage shows urban coverage having risen from 77% to 86% and rural coverage from 39% to 79% (1995 to 2008). This could help reduce the risk of cholera posed by severe weather events. Rural access to safe drinking water has risen from 47% in 1900 to 69% in 2008, but urban coverage has declined from 87% to 75%. This is a concern, given the high population density of urban areas and the vulnerability of poor urban communities to cholera epidemics. Significantly rates of diarrhoea and associated deaths in children under five remain very high. Poor hygiene conditions and practices may contribute, so efforts to improve infant and child health will include hygiene promotion. Support for provision of clean delivery kits will reduce the risk of maternal and neonatal sepsis. Option 1 provides for minor renovations of health facilities to support safer deliveries. This includes ensuring water supply and waste management systems to enable the maintenance of hygienic conditions. These measures are not included in option 2. / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C C / 2 C C / 3 Counterfactual
C. What are the costs and benefits of each feasible option? / By using a Lives Saved Tool (LiST), we are able to construct the cost effectiveness of averting a DALY[93] in Burma for component 1. This is a modelled analysis, which provides estimates of expected results. We have not been able to do this for components 2 and 3. For component 2, we have presented international evidence on the cost effectiveness of averting a DALY and for component 3 we have completed a qualitative assessment of its impact. Combining all of this evidence generates a strong economic case for options 1 and 2. / Incremental Costs of each option: / The overall cost of the programme is $296 million for option 1 and $300 million for option 2. The table below shows how the costs are spread amongst the 3 different components for the two options – option 1 provides more money for the HSS component. DFID contribution would be 46% of the total. The economic case presented is based at the cost effectiveness of the whole programme. / Component 1 Component 2 Component 3 Management Total / Option 1 $204 million $42 million $31 million $19 million $296 million / Option 2 $220 million $42 million $19 million $19 million $300 million / Component 1: / The cost of component 1 is $204 million for option 1 and $220 million for option 2. These costs are made up of project implementation costs, incremental provider costs and household out of pocket payments. Programme implementation costs are drugs and medical supplies as well as partners’ costs[94]. Incremental provider costs include travel reimbursement costs necessary to ensure that community based health providers can attend work meetings[95]. Catastrophic household costs cover out of pocket expenditure for emergency obstetric care, and abortion and newborn complications[96]. / TOTAL COMPONENT 1 COSTS / Option 1 Option 2 / Township package $97,720,447 $73,099,100 / Of which: Pre-pregnancy 13,680,863 14% 10,233,874 14% / Pregnancy 3,908,818 4% 3,654,955 5% / Delivery care 7,817,636 8% 730,991 1% / Post partum care 14,658,067 15% 10,964,865 15% / Newborn 3,908,818 4% 6,578,919 9% / Infancy and Childhood 53,746,246 55% 40,935,496 56% / Implementing partner support costs $82,733,634 $121,556,155 / Total Townships 40 60 / 7% Indirect costs $12,631,786 $13,625,864 / 6% M&E $10,827,245 $11,679,312 / TOTAL COST $203,913,112 $219,960,431 / Costs associated with provision of infant and child health constitute over 50% of package costs at a township level for both options. This is not surprising, given the high burden of disease in this age group and the strong emphasis placed upon community-based service provision. The next highest expenditures are reasonably comparable across options in terms of magnitude for pregnancy, delivery, and postpartum care. Differences in the total cost of the options reflect the number of programmatic components included, and option 1 achieves intensity by concentrating resources on fewer townships and including referral services for mothers and children and basic and comprehensive emergency obstetric and neonatal care. / Component 2: / The costs for this component, including M&E and indirect costs amount to $42 million. This remains the same regardless of whether we look at option 1 or 2. Component 2 costs are based on current gap analysis of the three diseases. This will need to be updated. (See Risks section). / TOTAL COMPONENT 2 COSTS / ART $530,914 / HIV hard to reach areas $2,654,568 / IDU (HIV/TB/harm reduction) $2,654,568 / MARC $20,174,716 / First-line TB drugs $300,000 / MDR TB $200,000 / HIV blood screening $2,654,568 / Flexible funding $7,963,704 / 7% Indirect costs $2,599,313 / 6% M&E $2,227,982 / TOTAL $41,960,332 / Component 3: / The costs for this component, including M&E and indirect costs amount to $31 million for option 1 and $19 million for option 2. The proportions under each part of component 3 are roughly the same; the difference reflects the amounts committed to component 3 by the different options. / TOTAL COMPONENT 3 COSTS / Option 1 Option 2 / Technical Support $2,123,655 $1,289,573 / Strategic Information & Research $2,654,568 $1,611,965 / Accountability $2,654,568 $1,611,965 / Township Capacity Development $18,889,000 $11,470,195 / Township Waste Management $808,827 $491,154 / 7% Indirect costs $1,899,143 $1,153,240 / 6% M&E $1,627,837 $988,491 / TOTAL $30,657,598 $18,616,583 / Management Costs: / Management costs are the same for both options ($19 million) and are made up of four key parts: the Fund Manager who will be contracted to manage implementation; the Fund Board made up of donors and independent experts; a Senior Consultation Group including government representatives and elected donor representatives; and an impendent Evaluation Group. / Incremental Benefits of each option: / Component 1: / Measuring Health Impact: / The health effects of implementing MNCH services through Options 1 and 2 were derived through the use of the Lives Saved Tool (LiST)[97][98]. As family planning is not included in the LiST model, a separate family planning model (operating in much the same way as LiST) was used to approximate the impact of family planning services[99]. / In order to generate estimates of health impact, we needed to choose the mix of interventions to be included in the 3MDG Fund and the increase in coverage over the project period. / Defining the mix of interventions: / A number of MNCH interventions were considered for inclusion in the model. These are all under the heading of periconceptual/pregnancy, delivery and post natal care. These options were considered against national data on baseline mortality rates and the causes of death. These were then combined with LiST to determine the mix interventions that would have the largest impact. / Defining the coverage of the interventions: / Beyond baseline coverage data[100], LiST requires estimates for the potential changes in individual indicator coverage over time to 2025. Given that the 3MDG Fund is a five-year grant, the timeline of interest stipulated was 2012-2016. Within that time period, an increase in annual coverage of 5% was assumed to be attainable for those interventions with a baseline coverage rate of 0-74%; a 3% annual increase was assigned to interventions with a baseline coverage rate between 75%-94%; whilst a small increase of 0.5% was assumed to be attainable amongst interventions with 95% or greater baseline coverage. These coverage rates are based on ambitious but attainable rates for each indicator and have been tested with a number of partners and stakeholders in-country. / Estimates of Health Impact: / The impact of implementing the services were considered in two ways: / Maternal, newborn and child deaths averted / Maternal, newborn and child DALYs averted / A disability-adjusted life year (DALY) is a common indicator of the burden of disease in a population. One DALY can be thought to represent one lost year of healthy life due to disease or injury. / Following the selection of MNCH package components and the specification of coverage rates – baseline as well as anticipated changes over time – simulations of LiST were run to derive estimates of the total number of deaths averted. The first table below summarises the number of lives saved per township for the two options. The following table presents the cumulative number of lives saved when the options are scaled-up across multiple townships. / On a per township basis, the services provided under Option 2 correspond to the greatest number of lives saved – 39,000 over 5 years compared with 28,258. This is because it is a more basic package of care and can be scaled up to more townships in the short term thereby saving more lives. However, on a per township basis, because it provides a more comprehensive package of services, option 1 saves more lives (911) than option 2 (876) or an additional 35 lives per township. / We have also looked at the impact of the two options if they were extended over a longer period (2017-2025). In this case the additional lives saved per township by option 1 increases to 104 – option 1 saves 2,198 per township and option 2 saves 2,094. This is the impact of providing a more comprehensive package of services (option 1) over a longer period. / For the two options considered, the greatest impact on lives saved is observed among children under 5 years (89%), and in particular, children 0-28 days of age (53%). Maternal lives saved correspond to 11% of the total. / Number of Deaths averted per township / 2012 2013 2014 2015 2016 TOTAL Long term impact* / 2017-2025 / Total townships 10 20 40 40 40 / Option 1 - 120 189 256 346 911 2198 / Total Child (0-60 months) - 145 226 304 419 1,094 2,175 / <1 month - 87 135 181 246 649 1,379 / 1-59 months - 58 91 123 173 445 796 / Maternal - 19 27 38 55 139 439 / Total townships 10 30 60 60 60 / Option 2 - 159 182 247 332 876 2094 / Total Child (0-60 months) 0 140 219 296 407 1063 2084 / <1 month 0 82 128 173 235 618 1291 / 1-59 months 0 58 91 123 172 445 793 / Maternal 0 18 27 37 53 135 426 / Number of Deaths averted Total: / Cumulative Deaths Averted DALYs Averted % of total / Option 1 28,258 766,915 / Total Child (0-60 months) 25,105 699,389 89% / <1 month 14,938 424,773 53% / 1-59 months 10,167 274,617 36% / Maternal 3,153 67,526 11% / Option 2 38,856 1,053,956 / Total Child (0-60 months) 34,516 960,997 89% / <1 month 20,149 572,948 52% / 1-59 months 14,367 388,050 37% / Maternal 4,340 92,959 11% / Components 2 and 3: / The economic rationale presented above only looks at component 1 and certain parts of component 3 that directly support the services provided under component 1. We have not been able to determine cost effectiveness numbers for components 2 and 3 as the mix of interventions and areas funded under component 2 are yet been defined and it is too difficult to generate cost effectiveness numbers for central health systems strengthening. However we have presented some evidence and arguments in the next section as to why these components constitute good value for money. / Balance of Costs and Benefits: / We have supplemented the cost effectiveness analysis of component 1 by providing international evidence on cost effectiveness for component 2 and qualitative evidence on component 3. In this context, we are interested in the cost effectiveness of averting a DALY as compared to the GDP per capita of Burma (which is the approach recommended by the Health Services Team). If an intervention averts a DALY at a cost that is less than GDP per capita, then the intervention is deemed to be cost effective. The GDP per capita approximates the tangible economic loss associated with losing a DALY in the short-run. As this does not consider the full value that might be attached to a DALY by an individual or society, it would normally also be appropriate to draw on the WHO approach to cost effectiveness. WHO tries to approximate the full value attached to a DALY by stating that an intervention is cost effective if it averts a DALY at a cost less than three times GDP per capita. GDP per capita in Burma was $702 (£410) in 2010 according to the IMF. / Component 1: / The table below shows the cost per death averted and the cost per DALY averted for options 1 and 2 compared with the do-nothing option. When weighed against health effects and compared against status quo, estimates of the cost per DALY averted are $266 for Option 1 and $209 for Option 2. / When compared against the GDP/capita, both options compare very favourably. According to the WHO approach, these interventions would be highly cost effective. Even if we were to include the costs of components 2 and 3 as well as management costs, the cost effectiveness numbers are $391 per DALY averted for option 1 and $285 for option 2 thus remaining highly cost effective. / As the 3MDG Fund does depend on existing infrastructure to some degree. e.g. clinics and hospitals, it could be argued that these numbers overestimate the impact of the 3MDG Fund. We will look at this in the sensitivity analysis. Unfortunately we do not have access to government accounts in health so we cannot estimate what this existing investment is. However this is something that we will include in any future analysis as soon as it becomes possible. / 2012 2013 2014 2015 2016 TOTAL / Option 1 $8,625,644 $20,692,794 $50,388,715 $58,186,697 $66,019,262 $203,913,112 / Total Townships 10 20 40 40 40 / Option 2 $7,242,575 $25,007,207 $56,274,130 $62,553,913 $68,882,546 $219,960,371 / Total Townships 10 30 60 60 60 / Option 1 versus Status Quo / Township years of implementation 150 / Cumulative deaths averted 28,258 / Cumulative DALYs averted 766,915 / Cost per DALYs averted $266 / Cost per Death averted $7,216 / Option 2 versus Status Quo / Township years of implementation 220 / Cumulative deaths averted $38,856 / Cumulative DALYs averted $1,053,956 / Cost per DALYs averted $209 / Cost per Death averted $5,661 / Valuing Household Cost Savings: / We have also calculated the savings to households from not having to pay catastrophic out of pocket costs. Under option 1 (but not option 2) the Fund will compensate families for these costs (which could otherwise put them into debt.) The table below shows that the benefits are not unsubstantial generating a total saving to households under option 1 of over $7 million. These have not been included in the above cost effectiveness figures and are therefore additional benefits. / 2012 2013 2014 2015 2016 Annual Mean Total / Option 1 Total benefit $464,157 $942,239 $1,898,821 $1,955,786 $2,014,460 $1,455,093 $7,275,464 / Number of townships 10 20 40 40 40 / Benefit per township $46,416 $47,808 $49,242 $50,720 $52,241 $49,400 $246,500 / Option 2 Total benefit $- $- $- $- $- $- $- / Number of townships 10 30 60 60 60 / Benefit per township $- $- $- $- $- $- $- / Component 2: / It is not possible to generate specific estimates on the impact that this particular component will have. However, evidence from the literature suggests that the range of interventions that will be funded under this component will provide good value for money. / Estimates put forth by the Disease Control Priorities Project, on the provision of HIV/AIDS services (including VCT, peer based knowledge sharing, ARVs to prevent vertical transmission, etc.) are second only to childhood immunizations as being one of the most cost-effective interventions recommended for adoption in South Asia (cost per DALY averted of $68 USD). Similarly, harm reduction activities carried in a variety of settings with varied content and target population groups have achieved cost per Quality Adjusted Life Year (QALY) gained estimates of slightly more than $1,000 USD. A QALY is a measure of disease burden. It is the number of years of life added by an intervention adjusted by the quality of that year – one year of perfect health equals one QALY whereas a year that was not lived in full health would equate to less than one QALY. According to the Commission of Macroeconomics and Health, an intervention is cost effective if it results in a QALY gained at a cost of three times GDP. Therefore if harm reduction activities led to a QALY gained at the same cost as the estimates above, these would be cost effective activities. / The focus on malaria and targeted townships at risk of artemisinin resistant is anticipated to be among the 3MDG Fund’s most cost-effective interventions. Another DFID programme which aims to replace malaria monotherapy drugs found this to be a highly cost effective intervention averting a DALY in Burma at a cost of $196. If we include the potential impact of preventing the spread of resistance to monotherapy globally, this becomes extremely cost effective averting a DALY at a cost of $5. These favourable cost effectiveness numbers are consistent with findings from Africa which show that how cost-effective both preventative and therapeutic strategies are for combating malaria. Findings indicate that the cost per life year gained for insecticide treatment of nets ranged from $9–$27, and for provision and treatment of nets from $10–$118. Treatment regimens were also found to be cost-effective with a single estimate of $167 cost per life year gained reported. / The table below reports some evidence on cost effectiveness of comparable interventions. Overall findings support the assertion that this component would likely yield a positive return on investment. / DCP2 Evidence on Cost Effectiveness / Intervention Description Cost per DALY averted / ART Treatment In low-cost settings with high adherence rates US$350 to US$500 / Significantly poor value for resources spent in low-adherence settings if drug resistance is allowed to emerge and proliferate. / Tuberculosis (endemic) Management of drug resistance US$500 - US$900 / Treatment of latent TB in patients uninfected with HIV US$4,000 to US$25,000 (cost-ineffective); however more cost-effective for groups of patients who are coinfected with TB and HIV. / Management of TB drug resistance Use of a standardized regimen that includes second-line drugs costs US$70 to US$450 / TB/HIV Co-infection prevention and treatment US$7 - US$600 / Malaria Intermittent preventive treatment in pregnancy with drugs other than sulfadoxine pyrimethaminec / Residual household spraying US$9 to US$24 / Insecticide-treated bed nets US$5 to US$17 / Residual household spraying US$9 to US$24 / STI prevention Social marketing, promotion, and distribution of condoms US$19 to US$205 / HIV/AIDS Blood and needle safety US$9 - US$110 / Peer-based programs Educate high risk groups, including sex workers and injecting drug users US$1 to US$74 / Component 3[101]: / There is a strong argument to fund HSS in a country such as Burma where women and children die of preventable conditions as a result of weak health systems. The graph below illustrates how inefficient health systems can undermine health delivery in a country. It shows that although 85% of children under 5 in Tanzania have access to basic health services, only 55% receive the appropriate treatment for a disease. Some of the reasons for this are the lack of trained staff onsite, the number of clinics that have the appropriate treatment in stock (especially rural areas), the number of families that actually seek treatment and the number of health facilities that have laboratory capacity. / HSS is about ensuring that health services are effectively delivered. It looks at the following areas: / Improving policy so that the health system can make the best decisions with scarce resources / Health facilities have adequately trained, supported, available and accountable staff / Medicines and supplies are affordable, in stock, dispensed rationally and consumed correctly / The health system is adequately and predictably financed / Information management systems produce reliable information upon which to base decisions on how to allocate the scarce resources / Good leadership and governance to ensure the right issues are prioritised and that resources are spent in such a way to maximise impact / Source: Bhargavi Rao, Barriers to Effectiveness: Artemisinin Combination Therapies (ACT) and the health system, Imperial College, 2010 / There is little direct evidence about the impact of health systems strengthening because of the difficulty of generating such information. However some evidence does exist: / The Lancet series on child survival estimated that the lives of 6 million children could be saved each year if 23 proven cost-effective interventions were universally available in the 42 countries responsible for 90% of child deaths[102] / WHO estimates that 22m additional women would have access to essential services if countries followed advice on building more capacity and accountability into their health services. This would save over 4.5 million lives / It is estimated that in Tanzania, investing $1 per capita into management strengthening contributed to a 52% decline in child mortality over 5 years[103] / Option 1 is likely to result in wider opportunities for HSS to promote longer term sustainability. / Overall: / The evidence relating to component 1 shows a strong economic case for both options 1 and 2. Evidence from components 2 and 3 offer strong arguments that the options will provide vfm. / If we were to base our decision on the cost effectiveness of component 1 alone, then the strongest case put forward relates to option 2 as it saves an additional 10,598 lives. A more basic health care package delivered in more townships will generate a larger quantitative impact in a country with considerable health needs and a low amount of health spending per capita. However what the quantitative analysis cannot capture is the impact of using an approach that will greatly strengthen the public health system to such an extent that we judge it to be the more cost effective option overall. There are a number of other reasons that strengthen the case for option 1 but the main reason is the way it will work with the public health system. We will describe this first and then describe the other reasons which are: / Option 1 reduces the catastrophic medical costs borne by households / Both options partly rely on existing infrastructure but only option 1 contributes to this essential health sector infrastructure / Option 1 is in line with the UK’s international commitments on Maternal, Newborn and Child Health whereas option 2 falls short of this commitment / Option 1 provides a more sustainable and inclusive partnership approach at a township level / The approach under option 1 is more consistent with principles of engaging in fragile states / Strengthening the Public Health System in Burma: / Option 1 uses public health systems to deliver the interventions (but not public financial systems). This is reflected in the costs of option 1 for basic and comprehensive EMOC delivery care and management of septic abortions - $232,000 and $56,900 per township respectively. Option 2 only devotes $18,000 per township to basic and comprehensive EMOC delivery care and nothing to the management of septic abortions. Option 2 uses NGOs to deliver the interventions. By using the public health systems to deliver the intervention, option 1 achieves two key things: / Option 1 will improve the ability of all parts of the health to deliver health services. Rather than creating parallel systems and using NGOs, the public health system’s ability to deliver health services will be enhanced. Experience suggests that improving health systems in MNCH also has important externalities in delivering health services in other areas. / Options 1 and 2 emphasise an approach to working closely with communities. Option 1 brings the public health system closer to the communities they serve. Thus they will be in a better position to offer a health services approach that is more responsive to community needs. / This should mean that the public health system will deliver better health services over the course of the project and will be better placed to deliver better services after the project finishes. We have tried to demonstrate this by calculating the longer term impact (2017-2025) per township. / Catastrophic Costs: / Option 1 generates additional benefits to poor households by reducing the costs that they have to bear on catastrophic medical treatment. / Infrastructure: / Option 1 includes some investment into existing health infrastructure thereby increasing the likelihood that the impacts will be delivered and recognising that it needs to contribute to these costs. As option 2 does not make these investments, the realisation of its impact is less certain and it makes no substantive contribution to the infrastructure it is using. / Meeting UK international commitments on Maternal, Newborn and Child Health: / Option 1 is in line with UK commitments to expand quality services including safe delivery, emergency obstetric and newborn care; and promoting reproductive choice through a range of family planning methods outlined in the UK Framework for Results, which is in line with the priorities for action in the ‘Global Consensus on Maternal, Newborn and Child Health. Option 2 falls short of this and does not support access to basic or comprehensive emergency obstetric and neonatal care, and would only support pills and condom family planning methods at community level. / Sustainable Partnership Approach: / Option 1 outlines a partnership approach at a township level through a range of service delivery partners, under the coordination of a joint Township Health Plan. Option 2 will operate through the same approach, but the focus on community level activities only, means the balance of implementation is shifted towards NGOs. Lessons from ongoing programmes in country suggest that a focus on international NGOs had can lead to parallel systems and duplication of activity. In this political context some international NGOs have also been unwilling to be seen working too closely with township health authorities. Option 2 does not support the pivotal role of township health authorities in taking full responsibility for planning, management and coordination of services of all providers. This risks limiting the opportunity to engage in HSS through ongoing programmes implemented jointly by all partners. This limits the longer term sustainability of the interventions. / Engagement in fragile states / Options 1 and 2 adhere to principles of Busan (as detailed earlier) in approaches to service delivery at the township level. Capacity building of public sector institutions ensures the building blocks are in place to support delivery of health services sustainably. WHO’s review of the role of community health workers confirms they remain a good investment, but the approach works optimally when part of a wider functioning health system[104]. / Option 1 provides the opportunity to both increase the stewardship and management capacity of public health authorities at all levels, and to build the capacity of CSOs and users of health services to hold service providers to account. This is more likely to result in services responsive to people’s needs and is in line with peacebuilding and statebuilding principles of engagement in fragile states. / UK funds under both Options are delivered in line with the EU Council Decision on Burma. Both options provide a more comprehensive response to service delivery, moving from a basic needs humanitarian response to longer term sustainability. This is through Component 3 which supports both health systems strengthening and promotes voice of civil society and greater accountability of services. However, option 2 limits the opportunities for this component. / As designed the 3MDG Fund provides for flexibility in the fund which could respond quickly to positive political change in Burma. Option 1 gives the greatest flexibility for this. / Risk and Uncertainty: / We have tested the impact of changing a number of the key assumptions on the cost effectiveness numbers. Both options are robust against a number of different tests. Parameters tested were chosen on the basis of those that the biggest impact on the cost-effectiveness numbers generated. / A 3% inflation rate was used as the basis for all cost estimates as this is consistent with current Government estimates of inflation. However sensitivity analyses were done to explore the impact of alternative inflation rates of 10% and 20% which is in line with historical inflation rates in 2008 and 2009. Results suggest that for Option 1, an increase in the inflation rate from 3% to 10% would increase the total budget by nearly $36,000,000 over 5 years and correspond to an increase in the cost per DALY averted from US $266 to US $296. At a 20% rate of inflation the total budget requirements increase by $95,000,000 to over $390,000,000 and result in an estimate of the cost per DALY averted of US $346. Similarly, option 2 increases to $236 and $282 per DALY averted. / Sensitivity analyses were run on variations in discount rates. In keeping with WHO CHOICE recommendations a base of 3% was used in final estimates of cost-effectiveness in the economic analysis. However, as the agreed discount rate for DFID Burma is 10%, we conducted sensitivity analyses on the discount rate to ensure that the value for money case would still be robust using a 10% rate (we also looked at a discount rate of 3.5%). Overall findings for both Options illustrate that changes to the discount rate did not significantly change the cost-effectiveness of the two options – both options retain cost effectiveness ratios of under $300 per DALY averted. / Furthermore sensitivity analysis was carried out around the exchange rate. The rate used was the average exchange rate in 2010 of Kyat 978 to one US Dollar. However the exchange rate has been volatile in the past five years, both weakening and appreciating against the dollar. It currently sits at around Kyat 800 to the dollar. We have looked at the impact of both a weak and strong Kyat by testing the impact of the exchange rate being at 1,200 and 720. A weaker kyat slightly improves the economic case by improving cost effectiveness ratios whereas a stronger kyat weakens the case marginally. However the impact is insignificant in both cases with cost effectiveness ratios remaining between $200 and $300 per DALY averted regardless of the option and exchange rates tested. / The case where the attribution to the Fund was too optimistic was considered. We attributed a portion of the impact to the government through their existing infrastructure. Option 1 remains cost effective (cost per DALY averted of no more than $700) if up to 45% of the impact is attributed to existing government infrastructure. The case is even stronger for option 2. / Incidence of Costs and Benefits: / The programme will predominantly benefit those most vulnerable to health risks. It ensures this targeting through the interventions of the components but also through the selection of townships. / The main beneficiaries under component 1 will be mothers, women and girls of reproductive age, newborns and children under 5. Under component 2, PLWHA and people with TB and malaria who are most vulnerable or at risk will be the main beneficiaries. This includes people in hard-to-reach areas, and marginalised groups such as FSW, MSM, people who inject drugs, and prisoners. Component 3 should benefit the wider population through a strengthened health system. / Townships will be chosen on the basis of a two stage process which first ranks them on the basis of immunisation coverage and poverty incidence. However, because of ongoing conflict and limitations of access to sensitive areas, it may not be possible to find appropriate implementing partners with sufficient access. Therefore there is some risk that some needy townships cannot be reached. / Attribution to DFID: / We expect the attribution to DFID to be in line with the proportion of funding provided by DFID. It could be argued that this should be higher given the presence of a full time health advisor in-country but conservative estimates suggest that this should be in line with the proportion of funding by DFID. / Competition Assessment: / Partners will include public sector health bodies, UN agencies, international and local NGOs, CBOs, private sector providers and research institutions. We do not expect this programme to have a major impact on competition within the sector as the procedures for choosing partners has been developed carefully and should not give rise to anti-competitive practices. / For component 1, potential partners will be chosen through assessing: availability; implementation and absorptive capacity; authorisation and access to work in selected townships and poor and under-served populations; scope to provide capacity building to ensure longer term sustainability through local organisations; and opportunities to maximise synergies and efficiencies with other initiatives. The first stage will involve a call for expressions of interest. The second stage would be a request to shortlisted partners or consortia to submit a full proposal. Selection of implementing partners or consortia will be undertaken by the Fund Manager using standard grant appraisal procedures. / For component 2, the Fund Manager will review the performance of existing partners. Consideration will be given to a bridging extension of existing contracts where performance is satisfactory and partners meet the criteria, to ensure a smooth transition between the 3DF and the 3MDG Fund and avoid gaps. Selection of partners will be undertaken by the Fund Manager using standard calls for proposals to assess eligibility, capacity and experience. For component 3, the choice of partners will be determined after joint planning with the MOH and key stakeholders. / Fiscal Impact: / This programme will not have any direct impact on public expenditure as in line with the EU Council Decision on Burma no money will be spent through central Government systems. / Financial Sustainability: / The Fund provides additional services in the townships that it is focused on so it does depend on existing infrastructure to a certain extent. However it does not depend on the Government financing recurrent costs, as the recurrent costs required for the programme work are covered in the budget. / An important issue relating to financial sustainability is what happens once after the 5 year funding period. If the recommended option is chosen, one of the reasons will be because of the stronger long term impact of this option. Securing funding for additional years or managing a Government take over or expansion of these services if appropriate will be key issues. These cannot be resolved now but should be the subject of the programme reviews, particularly in the later years. / 85% children in Tanzania have access to primary heath facilities / (WHO Statistics report 2008) / 40% - 50% of health facilities have trained staff on site / (J Schellenberg et al BMC Public Health 2008) / 40% of facilities have ACT in stock in rural areas/up to 80% in urban areas / (Clinton Foundation report: Pilot ACT Subsidy 2008) / 62% of families seek treatment for fever in U5 / (Clinton Foundation report: Pilot ACT Subsidy 2008) / 40% health facilities have laboratory capacity / (G. Mfinanga et al Tanzanian Journal of Health Research 2008) / % of children U5 with fever / 55% of all children U5 with fever receive treatment / (WHO Statistics report 2008)
D. What measures can be used to assess Value for Money for the intervention? / The appropriate measure for VFM in this case is the cost effectiveness of the intervention in averting a DALY. We were able to present the cost effectiveness of averting a DALY for component 1 but not for components 2 and 3. It will be important for component 2 to consider the cost effectiveness when deciding on which interventions to pursue. As we do not have evidence that relates specifically to Burma under this component, we will draw on international evidence. As the evidence is not specific to Burma, it will also be important to draw on qualitative evidence relating to Burma which may provide important lessons as to the likely impact of these interventions. / Other measures that will be useful in assessing VFM will be national data gathered through household surveys or other means that describe the burden of disease and evidence relating to the uptake of health services. Understanding the impact that this programme has and its overall VFM will be a major part of the monitoring and evaluation framework of the programme.
E. Summary Value for Money Statement for the preferred option / The cost effectiveness analysis for the two options shows that both options generate good VFM. Focusing on women and children are highly cost effective. We also know from work in existing programmes (JIMNCH) that similar packages in other townships in Burma provide good VFM. / However, in spite of the fact that option 2 is more cost effective according to the evidence available under component 1, there are good reasons why investing in option 1 may provide greater VFM. / Option 1 has a larger long-term impact per township and is more suited to longer term sustainable development whereas option 2 is more suited to a humanitarian response / Option 1 reduces the catastrophic medical costs borne by households / Both options partly rely on existing infrastructure but only option 1 contributes to this / Option 1 is in line with the UK’s commitments on MNCH whereas option 2 falls short of this / Option 1 provides a more sustainable and inclusive partnership approach at a township level / Option 1 is more consistent with principles of engaging in fragile states. / Burma is currently in a time of political change. The 3MDG Fund is a flexible funding model, able to respond to change, for example in the allocations across components or to emerging health threats. Option 1 allows for a more strategic development approach, should circumstances allow. / Both options are robust against a number of sensitivity analyses. Option 1 remains cost effective as long as 55% of its estimated impact is realised, giving confidence that this programme will deliver VFM. This programme would cease to provide VFM if more than 45% of its impact was wiped out.
[56] Options for future funding were considered at the concept note stage in 2010 based on scenarios on whether new donor funding initiatives would come on stream or not. These were Global Fund Round 9 for HIV, TB and malaria, GAVI support for Health Systems Strengthening and the Joint Initiative on Maternal, Neonatal and Child Health in Nargis affected areas; with the Global Fund being the most important because of its magnitude. With the approval of the Global Fund to commence programmes in Burma in 2011, the donors to the 3DF agreed that there is value in continuing to provide joint support to address the basic health needs of the most vulnerable population of Burma, and the next phase of the support from 2012 should have a broader scope and address the three health Millennium Development Goals (MDGs). (The risk of the recent cancellation of the Global Fund Round 11 is considered under Risks).
[57] See DFID DPC Empowerment & Accountability paper with evidence review and Ramkumar, V. (2008) “Our Money, Our Responsibility”. International Budget Project reviewing citizen report cards in Bangalore, India 2003.
[58] See 3DF Beneficiary Accountability Framework. August 2010
[59] DFID Emerging Guidance on Empowerment & Accountability, DPC Paper 2011.
[60] For reasons of access and security of implementing partners this rationale may not apply to humanitarian programmes for conflict affected populations, where a DFID bilateral approach may have number of advantages.
[61] Funded by 3DF, PSI and WHO, and implemented by WHO and MOH.
[62] Myanmar application to the Global Fund Round 9, 2009.
[63] Korenromp E (2005) WHO/RBM Malaria Incidence Estimates at the Country level for the year 2004
[64] Sein KK. Maternal Health Care Utilization Among Ever Married Youths in Kyimyindaing Township, Myanmar. Maternal Child Health J. 2011 May 19
[65] Ministry of Health, World Health Organisation and HITAP. A feasibility study of the Community Health Initiative for Maternal and Child Health in Myanmar. 2010.
[66] Saw S, Manderson L, Bandyopadhyay M, Sein TT, Mon MM, Maung W. Public and/or private health care: tuberculosis patients' perspectives in Myanmar. Health Res Policy Syst. 2009 Jul 28;7:19.
[67] Lönnroth K, Aung T, Maung W, Kluge H, Uplekar M. Social franchising of TB care through private GPs in Myanmar: an assessment of treatment results, access, equity and financial protection. Health Policy Plan. 2007 May;22(3):156-66. Epub 2007 Apr 12.
[68] Maung M, Kluge H, Aye T, Maung W, Noe P, Zaw M, Jost SP, Uplekar M, Lönnroth K. Private GPs contribute to TB control in Myanmar: evaluation of a PPM initiative in Mandalay Division. Int J Tuberc Lung Dis. 2006 Sep;10(9):982-7.
[69] Mullany, LC, Lee CI, Lin Yone, Palae Paw, Eh Kalu Shwe Oo, Cynthia Maung, Lee TJ, Beyrer C. Access To Essential Maternal Health Interventions and Human Rights Violations among Vulnerable Communities in Eastern Burma 2008 PLoS Medicine December 2008 | Volume 5 | Issue 12 | e242.
[70] Lee CI, Smith LS, Shwe Oo EK, Scharschmidt BC, Whichard E, Kler T, Lee TJ, Richards AK. Internally displaced human resources for health: villager health worker partnerships to scale up a malaria control programme in active conflict areas of eastern Burma. Glob Public Health. 2009;4(3):229-41.
[71] Teela KC, Mullany LC, Lee CI, Poh E, Paw P, Masenior N, Maung C, Beyrer C, Lee TJ.Community-based delivery of maternal care in conflict-affected areas of eastern Burma: perspectives from lay maternal health workers. Soc Sci Med. 2009 Apr;68(7):1332-40. Epub 2009 Feb 18.
[72] Mullany LC, Lee CI, Paw P, Shwe Oo EK, Maung C, Kuiper H, Masenior N, Beyrer C, Lee TJ.The MOM Project: delivering maternal health services among internally displaced populations in eastern Burma. Reprod Health Matters. 2008 May;16(31):44-56.
[73] Lee, C.I. , Smith, L.S. , Shwe Oo, E.K. , Scharschmidt, B.C. , Whichard, E , Kler, T. , Lee, T.J. , Richards, A.K.Internally displaced human resources for health: Villager health worker partnerships to scale up a malaria control programme in active conflict areas of eastern Burma. 2009) Global Public Health, 4 (3), pp. 229-241
[74] Tin N, Lwin S, Kyaing NN, Htay TT, Grundy J, Skold M, O'Connell T, Nirupam S. An approach to health system strengthening in the Union of Myanmar. Health Policy. 2010 May;95(2-3):95-102. Epub 2009 Dec 16.
[75] Essential interventions, commodities and guidelines for reproductive, maternal, newborn and child health. A global review of key interventions 2011; and the Consensus on Maternal and Newborn Health 2009.
[76] Knowledge into action for child survival. Bellagio study group and child survival. Lancet 2003:262; 323-327
[77] Bellagio study group, 2003. Knowledge into action for child survival. Lancet 262; pp 323-327
[78] Darmstadt, G.L., et al., Evidence-based, cost-effective interventions: how many newborn babies can we save? Lancet, 2005. 365(9463): p. 977-88
[79] Baqui, A., et al., Effect of community-based newborn-care intervention package implemented through two service-delivery strategies in Sylhet district, Bangladesh: a cluster-randomized controlled trial. Lancet, 2008. 371(9628): p. 1936-44.
[80] Borghi, J., et al., Economic assessment of a women's group intervention to improve birth outcomes in rural Nepal. Lancet, 2005. 366(9500): p. 1882-4.
[81] Kumar, V., et al., Effect of community-based behaviour change management on neonatal mortality in Shivgarh, Uttar Pradesh, India: a cluster-randomized controlled trial. Lancet, 2008. 372(9644): p. 1151-62.
[82] Bang, A.T., et al., Effect of home-based neonatal care and management of sepsis on neonatal mortality: field trial in rural India. Lancet, 1999. 354(9194): p. 1955-61.
[83] Bhutta, Z.A., et al., Improvement of perinatal and newborn care in rural Pakistan through community-based strategies: a cluster-randomised effectiveness trial. Lancet. 377(9763): p. 403-12.
[84] LeFevre, A.E., et al., Economic evaluation of a community-based newborn care intervention implemented through two service delivery strategies in Sylhet district, Bangladesh: A cluster randomized controlled trial. (submitted to BMJ).
[85] LeFevre, A.E., et al., Economic evaluation of a community-based newborn care intervention implemented in Sindh, Pakistan: A cluster randomized controlled trial. (submitted to WHO Bulletin).
[86] Maternal mortality: who, when, where and why. Rousmans C, Graham WJ. Lancet 2006, 308; 368; 1189-1200
[87] Countdown to 2015 .decade report (2000-10): taking stock of maternal, newborn and child survival. Lancet 2010: 375; 2032 - 2044
[88] Cochrane Review: Community-based intervention packages for reducing maternal and neonatal morbidity and mortality and improving neonatal outcomes
[89] UN Secretary General Ban Ki-moon Global Strategy for Women and Children’s Health (2010)
[90] Making Services Work for Poor People, World Development Report 2004, World Bank; Who Answers to women? Gender and Accountability, UNIFEM 2008/2009; Rosemary McGee and John Gaventa; The impact and effectiveness of Accountability and Transparency Initiatives, DFID Draft September 2010; Deepa Narayan (2005) Measuring Empowerment: Cross-Disciplinary Perspectives, Washington: World Bank and (2002)
[91] List was developed by the Future’s Group with support from the Bill and Melinda Gate’s Foundation, USAID, and other donors. Its technical content is presently managed with support from Johns Hopkins School of Public Health’s Institute for International Programs (JHU/IIP) with support from the Child Health Epidemiology Group (CHERG). LiST was chosen in preference to the Marginal Budgeting for Bottlenecks (MBB) approach because it has more up-to-date effectiveness measures and allows for configuration of a much wider variety of options for service delivery. http://www.jhsph.edu/dept/ih/IIP/list/.
[92] The National Tuberculosis Prevalence Survey 2010 estimates that TB prevalence is over 1000 per 100,000 populations in the urban cities of Mandalay and Yangon.
[93] The cost effectiveness of averting a disability-adjusted life year (DALY) is a common approach used to assess the impact of a health programme. A DALY is a common indicator of the burden of disease in a population. One DALY can be thought to represent one lost year of healthy life due to disease or injury therefore averting a DALY is preventing the loss of a year of healthy life.
[94] Programme implementation costs were obtained from reported NGO costs from the Joint Initiative on Maternal and Neonatal Health project (JIMNCH) or from costs reported from the delivery of separate services in Burma (e.g. PSI’s Social Franchising Programme). These were combined with mean population figures to estimate the amount of supplies needed. Annual increases in coverage were then applied to calculate annual costs. Sensitivity analyses were applied to these population estimates. Implementing partner costs were estimated for both public and private partners using actual costs posted by implementing partners in the 3DF.
[95] Incremental provider costs were estimated as part of a negotiated reimbursement initiative wherein implementing partners reimburse health facilities for costs incurred in the provision of care to mothers and children. Building upon a similar initiative tested under the Joint Initiative, under this reimbursement scheme the implementing partner offsets the expenditures family members otherwise would have been charged for treatment, including drugs/ medical supplies and transportation. Reimbursement thresholds were estimated based on discussions with NGO partners currently implementing similar reimbursement schemes under the Joint Initiative.
[96] Catastrophic costs were estimated as part of a negotiated reimbursement initiative wherein implementing partners reimburse health facilities for costs incurred in the provision of care to mothers and children. Building upon a similar initiative tested under the Joint Initiative, under this reimbursement scheme the implementing partner offsets the expenditures family members otherwise would have been charged for treatment, including drugs/ medical supplies and transportation. Reimbursement thresholds were estimated based on discussions with NGO partners currently implementing similar reimbursement schemes under the Joint Initiative.
[97] List was developed by the Future’s Group with support from the Bill and Melinda Gate’s Foundation, USAID, and other donors. Its technical content is presently managed with support from Johns Hopkins School of Public Health’s Institute for International Programs (JHU/IIP) with support from the Child Health Epidemiology Group (CHERG). LiST was chosen in preference to the Marginal Budgeting for Bottlenecks (MBB) approach because it has more up-to-date effectiveness measures and allows for configuration of a much wider variety of options for service delivery.
[98] The LiST model was run at the national level in order to generate overall estimates of cost effectiveness for the 3 MDG Fund however a more intensive analysis is already underway which is looking at the township level. The aim of this latter analysis is to provide recommendations for the mix of services that the 3 MDG Fund should provide at a township level. This means that the mix of services will be more appropriate for each township and cost effectiveness will be enhanced.
[99] The family planning module was utilized to approximate the impact of family planning services. This module operates in the much the same was as LiST, with the analyst stipulating annual changes in coverage deemed attainable for the intervention. Since Demographic and Health Surveys data are not available for Burma we manually entered the data based on alternative in-country reports. With coverage data in place, emerging effectiveness data were derived based on a 5% annual increase in coverage. These effects have been included in the final estimates generated.
[100] Data on baseline mortality comes from recent reports produced in Burma including the July, 2010 UNFPA report on the Situation Analysis of Population and Development, Reproductive Health and Gender in Myanmar. The exception to this is with neonatal mortality which was felt to be underestimates of actual rates and thus MICS survey data were used. Baseline coverage data are not available for a large number of critical indicators. Furthermore there were concerns about the quality of some of the available data in light of the wide intra and inter regional variations across Burma’s states and population groups. Therefore whenever possible, MICS data extrapolated to 2011 was used based on the assumption that there are few comparable alternatives; and the use of a single source may ensure some consistency in the level of any associated biases.
[101] Much of this argument comes from the following DFID Paper DFID’s work in Health Services and Systems Strengthening, Health Services Team, June 2010
[102] G. Jones, R. Steketee, R. E. Black, Z. A. Bhutta, S. S. Morris and the Bellagio Study Group on Child Survival. 2003. How Many Child Deaths Can We Prevent This Year? Lancet 62: 9377 65 - 71
[103] Source: deSavigny, D et al: Tanzania Essential Health Intervention Project (TEHIP), 2005
[104] Lehmann U and Sanders D. Community health workers: What do we know about them? The state of the evidence on programmes, activities, costs and impact on health outcomes of using community health workers. A report for the World Health Organisation (2007)

Commercial Case

Indirect procurement

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / The 3DF has been supported through a pooled donor fund. A similar approach, building on the experience is proposed for a next phase. The EC chairs the Fund Board and leads a small donor group (of which UK is a member) for selection of the Fund Manger against the ToRs agreed by all donors[105]. Terms of engagement between all donors will be defined in a Joint Collaboration Arrangement[106]. / There is a strong rationale for working with other donors through this pooled funding arrangement. It: / Ensures coordinated and harmonised support from multiple funding sources for national priorities. / Avoids a multiplicity of individual projects, thereby reducing duplication and inefficiency. / Maximises the impact of limited aid resources available. / Enables donors to comply with the Paris Declaration on Aid Effectiveness[107] and OECD DAC Principles of Engagement in Fragile States to the maximum extent possible in the Burma context. / The lessons from the 3DF show wide benefits to the health sector including: enhanced sector coordination, dialogue and information sharing; strengthening of national sector strategies and plans and the development of joint donor planning, implementation and monitoring frameworks[108].
B. Value for money through procurement / The main elements of selection and procurement for the 3MDG Fund will include: / Selection of a 3MDG Fund Manager. / Procurement of support structures and services. / Procurement or commissioning of the services of Implementing Partners. / Provision for procurement of goods and supplies. / Selection of a 3MDG Fund Manager / The EC policy and procedure that will be followed to select a Fund Manager to manage the multi-donor fund. Eligibility for organisations is determined by (i) the EU Council Decision on Burma (ii) EC financial rules and procedures (iii) and the requirement for authority to work in country. / (i) EU Council Decision on Burma. Article 8 states that Member States programmes and projects should be implemented through UN agencies, Member States agencies and international organisations, non-governmental organisations, and through decentralised cooperation with local civilian administrations. Under the EU procedures under the EU Council Decision private sector organisations are not eligible to implement programmes. / (ii) EC financial rules and procedures. EC grant procedures for NGOs only allow sub-grants up to the value of Euro 10,000. This is the only contractual instrument the EC has to fund NGOs. These procedures rule out NGOs as a Fund Manager for the multi-donor fund, where grants are likely to be in excess of ~ US $50,000. EC have framework agreements with international organisations, which have passed a “Four Pillar Assessment”. Using a framework agreement allows the EC to enter an agreement called a ‘joint-management arrangement’. This is a more flexible arrangement, allowing the fund to be managed according to the rule and procedures of the Fund Manager. The EC has framework agreements with the UN ; the World Bank and with a number of international organisations. All UN agencies and international organisations in country have passed the four pillar assessment. / (iii) Authority to operate in Burma All organisations require authority to operate in Burma. This is usually given through a MOU with the relevant Government Ministry. Such authority takes a long time, often years, for organisations trying to establish a presence in country. A selected organisation not having authority to operate in country could risk the Fund not starting in this and the next financial years. / For the EC, the requirement to select the Fund Manager is that the authorising officer should choose the UN or International Organisation in an objective and transparent manner. The Description of Action sets out a competitive process for the selection of the Fund manager against the eligibility criteria. It requires an ‘expression of interest’ by organisations, which are technically reviewed by a panel comprising representatives of EC and other donors against the pre-determined scoring. Following the expression of interest stage, the selection process moves to a negotiated process with the selected agency. The provider will be required to submit a proposal that satisfactorily addresses all of the specific evaluation criteria, as well as a budget that falls within an agreed threshold. Donors will seek an Efficiencies Savings and Delivery Plan of year on year cost savings[109]. / The agreement will commence in the first half 2012. Fund Management tasks will be undertaken for a period of 5 years. The final 3 months will be dedicated to Fund closure activities. / The EC framework agreements with UN and international organisations, and EC rules provide several safeguards to ensure value for money: / Indirect costs for the overall fund cannot exceed 7% / Indirect costs cannot be ‘cascaded’, that is indirect costs charged on the same funds by the Fund Manager and Implementing Partners / Financial and procurement systems will have been assessed under the EU Four Pillar Assessment / For the 3DF donors agreed with the Fund Manager, UNOPS, to establish a ‘pass through’ mechanism for funds in line with the UNDG-wide agreement on multi-donor trust funds. This arrangement ensured a pass through of indirect costs to implementing partners on programme funds. The arrangement ensured that the indirect costs to the 3DF did not exceed 7% and no indirect costs were cascaded. Direct costs were charged according to EC rules. Each year the Annual Budget was approved by donors. / Performance appraisal of the fund as a whole is set out in the Management Case. For the Fund Manager an annual “benchmarked” workplan will be agreed each year by the Fund Board. This will set out clear deliverables or milestones and the timelines for delivery. This workplan will be the basis of the report made to the Fund Manager to the Fund Board at quarterly meetings. / Procuring the services of Implementing Partners / Procurement and contracting through the Fund Manager to be undertaken using UN or international organisation procurement procedures and rules. (Under EC rules and the eligibility criteria, these rules and procedures will have been pre-assessed under the EC Four Pillar Assessment). Financial resources will be allocated to implementing partners through direct or competitive grants. / Direct grants may be allocated to partners that meet certain criteria as established by the Fund Board, which may include demonstrated technical competence, capacity, speed of delivery, monopoly, coherence with ongoing activities, and access to specific target areas or populations. / A competitive grant allocation procedure will be used in any other case. The Fund Manager will assess expressions of interest and proposals against standard criteria. Specific contracting arrangements for components will be in accordance with the Fund Manager rules and procedures and are as follows: / Component 1 / Selected UN agencies may be contracted through a direct grant agreement to provide technical support across townships, including for activities such as township assessment and planning, and training. In exceptional circumstances where an NGO or organisation is required to undertake this task, the Fund Manager will extend the procurement procedure to a call for proposals. / The Fund Manager will issue a call for proposals to support direct implementation of services at township level in both the public and private sectors. To ensure a manageable number of contracts and achieve economies of scale, preference will be given to organisations or consortia that have the capacity to provide support to at least five townships during the funding timeframe. / Component 2 / Selected UN agencies may be contracted through a direct grant to enable them to provide technical support for specific activities related to the three diseases as appropriate. / Other partners may also be contracted through a direct grant, where this is necessary to avoid gaps in implementation during the transition from the 3DF to the 3MDG Fund. Renewal of direct grant agreements will be subject to satisfactory performance, meeting the current criteria set, and demonstrated VFM by the implementing partner[110]. Procurement may also be undertaken using restricted procurement procedures and a direct grant where it is clear that there is one or only very few eligible organisations. / For other activities, as far as possible, selection of partners will be through open competition following calls for expressions of interest, and subsequent calls for full project proposals[111]. / Component 3 / Selected UN agencies may be contracted through a direct grant to provide technical support for HSS at national and sub-national levels. The Fund Manager may contract technical assistance. / The Fund Manager will issue a call for expressions of interest and subsequent invitation to submit a full proposal for organisations to implement activities to support strengthening of accountability mechanism and related capacity development for the MOH at central and decentralised levels, civil society organisations and communities. / Research activities will also be contracted by the Fund Manager following a call for proposals or through standard procurement procedures for service contracts. / The Fund Manager will enter into contracts with individual partners. The duration of the contracts for Component 1 will be for 2-3 years. Multi-year contracts will provide predictable funding to enable partners to plan implementation over a longer timeframe but will also enable the 3MDG Fund Board to consider a transition to direct contracting with township level health authorities after 2-3 years. / The duration of contracts for Component 2 will depend on the nature of the activity. In some the support will be required for the entire 5 year duration of the 3MDG Fund, in others, interim support may only be required for 1 year. Similarly, with Component 3, some activities, such as long-term technical assistance or research studies, may require a contract for at least 2-3 years, while for other activities, such as specific reviews, analyses or pilot projects, the duration of contracts may be less than 1 year. / The Fund Manager will be responsible for administering grant allocations, auditing and fund monitoring, and undertaking annual performance monitoring. Performance monitoring will involve visits to project sites, data quality assessments, review reports and expenditure, review of progress in implementing planned activities, achievement of agreed targets and milestones. All contracts will be conditional on performance. / Independent evaluation / The independent Evaluation Group will be contracted through the Fund Manager under the auspices of the Fund Board. The contract will be a service-level agreement to provide evaluation services. / Drugs and commodities procurement and distribution / 3MDG Fund resources will be used by the Fund Manager and contracted partners to finance the purchase of essential drugs, commodities and equipment; to support the costs of facilitating training and supervision, referral, minor refurbishment of health facilities, and M&E; operating, maintenance and office costs; baseline and end line surveys and other studies; and local and international technical assistance. / The Fund Manager will be responsible for fixed assets[112], drugs, medical supplies and commodities, whether the procurement is done directly through the Fund Manager or indirectly through implementing partners. Procurement may involve strategic partnerships with UN agencies and international NGOs with procurement experience. The 3DF demonstrated that it has been possible to achieve VFM using UN procurement agreements through UNICEF and UNFPA (which are based on global procurement at high volumes). Unit costs for major items will be tracked in the 3MDG Fund. / The Fund Manager will develop Standard Operating Procedures for implementing partners for local procurement. The Fund Manager will ensure that essential drugs and non-pharmaceutical medical supplies procured under the 3MDG Fund meet internationally recognised quality criteria. / It is anticipated that initiatives associated with the Global Fund and GAVI-HSS grants will lead to a strengthening of national procurement and supply chain systems. The initiative for support for strengthening procurement and supply chain management of HIV-related commodities in Burma originally funded by the 3DF provides an opportunity for more integrated approaches to procurement of drugs and supplies and systems strengthening. National supply chain systems can be used by UN agencies, and efforts have been made to strengthen drug and supplies management. Supplies of essential drugs and commodities from central to state and township levels appear to be reasonably reliable, but distribution to facilities at township level is problematic, due to lack of transport and fuel. The 3MDG Fund Manager will need to work closely with partners to ensure there are adequate local distribution systems in place. The emphasis will be on strengthening existing systems. All aspects of supply systems used will be routinely monitored by the Fund Manager. / Financial flows / The 3MDG donors will sign bilateral agreements with the Fund Manager. The 3MDG Fund financial flows will be in line with donor requirements. Funds will flow from the donors to the Fund Manager, with strategic direction being provided by the Fund Board. Signing of grant agreements will trigger fund flows from the 3MDG Fund Manager to contracted partners, in accordance with the terms and conditions of the agreement. As a co-signatory, the implementing partner will be responsible for implementing agreed activities and for managing and accounting for 3MDG funds. / Direct funding by the Fund Manager of decentralised health authorities will be considered, with a view to enhancing their role as implementing partners and reducing transaction costs. The Fund Manager will analyse models set up by the Global Fund and GAVI-HSS and commission a fiduciary risk assessment which will make recommendations on how to take forward harmonisation of approaches and ensure fiduciary oversight. / In keeping with international good practice, a number of elements have been included in the design of the 3MDG Fund to reduce fiduciary risk. These include: provision for appropriate accounting and reporting, external scrutiny, independent monitoring and external audits; separation of roles and functions between the Fund Board and the Fund Manager, and the Fund Manager and implementing partners; and opportunities for ensuring accountability to beneficiaries.
[105] This process has commenced following the process outlined in Section B. DFID is represented in the donor Steering Group for the 3MDG Fund design. Compliance with DFID third party procurement procedures have been checked with DFID Procurement Group.
[106] The wording of the current Joint Agreement remains appropriate for the 3MDG Fund but may need to be reviewed by individual donors before renewal.
[107] (i) Ownership: Partner countries exercise effective leadership over their development policies and strategies and co-ordinate development actions; (ii) Alignment: Donors base their overall support on partner countries’ national development strategies and procedures; (iii) Harmonisation: Donors’ actions are more harmonised, transparent and collectively effective; (iv) Managing for Development Results: Results-oriented policies and programmes are needed, and actual outcomes are regularly monitored, in order to identify corrective measures where relevant; (v) Mutual accountability: Donors and partners are accountable for development results.
[108] Verulam Consultants. Mid Term Evaluation of the 3DF. 2009.
[109] Donors agreed a similar approach to reduce UNOPS costs for the delivery of the 3DF which has led to year on year reductions in these costs.
[110] Should performance of the existing Implementing Partner prove unsatisfactory, an alternative provider may be sought through a restricted procurement process.
[111] As for Component 1, the Fund Manager will need to issue all calls for expressions of interest and development of full proposals in consultation with the Fund Board.
[112] Non-expendable goods (vehicles, furniture, medical and non medical equipment, IT equipment etc)

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / The budget for 2012-2016 is shown in Table A1. The indicative range of donor commitments over 5 years is between US$250 and US$300 million. The budget assumes donor commitment at the high end and a 3% annual inflation rate. Annual budget allocations are based on donor forecasts. / The indicative allocation of the programme budget to Components 1, 2 and 3 is 74%, 15% and 11%. The figures include an allocation of a minimum of 6% for M&E and of 7% for indirect costs. The budget reflects the increase in townships covered under Component 1 from 10 in Year 1, to 20 in Year 2, to 40 in Years 3, 4 and 5. The budget includes the costs of fund management, governance and independent evaluation. Costs for evaluation have been spread over the 5 years, although the main costs will be incurred in Years 3 and 5, for the mid-term and final evaluations. / The experience of the 3DF forecasting will provide the basis for forecasting for the 3MDG Fund. For the programme (not including Fund Management costs) these are initially based on a technical review of implementing partner proposals. The 3DF and the Joint Initiate on MNCH have conducted detailed cost analysis, including unit costs for service delivery and the key drivers of the costs. Since the JIMNCH programme implements a common package of services across township, this has enabled some benchmarking of unit costs for services and service quality to be established across partners. This has also helped negotiate cost savings, and provide an important baseline for the 3MDG Fund. / Programme performance and fund absorption are monitored through the programme management, 6 monthly reports and disbursement requests. Updating forecasts are amended through this process. / All donors agree a disbursement schedule with the Fund Manager and cash flow against forecasts is presented by the Fund Manager to the Fund Board meeting on a quarterly basis. / Table A1: Summary indicative budget (US$) / 2012 2013 2014 2015 2016 Total / Component 1 8,625,644 20,692,794 50,388,715 58,186,697 66,019,262 203,913,112 / Component 2 8,362,000 8,030,910 8,271,837 8,519,992 8,775,592 41,960,332 / Component 3 2,959,470 4,453,330 7,559,066 7,734,130 7,951,599 30,657,598 / Governance & management / Governance 155,720 160,400 140,910 144,990 149,270 751,290 / Fund Manager 2,800,000 2,884,000 2,970,520 3,059,640 3,151,430 14,865,590 / Independent evaluation 475,000 489,500 503,930 519,050 534,620 2,521,850 / Indirect costs (7%) 240,150 247,355 253,075 260,658 268,472 1,269,710 / Total 23,617,995 36,958,039 70,088,053 78,425,157 86,850,245 295,939,489 / DFID’s commitment / Up to £80 million over four years FY 2012/13 to 2015/16. This represents 42% of the fund at current predicted levels of funding from other donors. This is consistent with the proportion of the total of DFID funding towards the 3DF (42%). DFID’s contribution is profiled as follows: / FY 2012/13 £12 million / FY 2013/14 £28 million / FY 2014/15 £20.5 million / FY 2015/16 £19.5 million / Note £60.5 million is projected within the approved DFID Burma Operational Plan and allocation. £19.5 million is tentatively allocated in the next spending review period. It and will need to be approved in DFID Burma’s Operational Plan from 2015 onwards and by HM Treasury. / There are two funding options to be considered: / Option 1: Approval of £60.5 million within this DFID Burma Operational Plan and an additional £19.5 million for 2015/16 subject to approval of the next DFID Burma Operational Plan from 2015 onwards. This would be committed as up to a total of £80 million over four years FY 2012/13 to 2015/16. / Option 2: Approval of £40 million for two years FY 2012/13 and 2013/14 and up to an additional £40 million for FY 2014/15 and 2015/16 subject to reviews of progress and government and other donor commitments (and for FY 2015/16) subject to approval of the next DFID Burma Operational Plan
B. How will it be funded: capital/programme/admin? / Up to £80 million will be funded on programme as an MOU with the selected Fund Manager. £60.5 million has been accounted for and approved in DFID Burma’s Operational Plan. An additional £19.5 million will need to be approved by HM Treasury for the next spending period. / There is no contingent liability associated with these funds. DFID Accounts Department and Treasury will be informed about payments.
C. How will funds be paid out? / On approval, an MOU will be agreed with the Fund Manger of the 3MDG Fund, including the schedule of disbursements. Disbursement will take into account the results of performance assessment, the budgetary forecast for the next year and the annual operational work plans.
D. What is the assessment of financial risk and fraud? / In 2010 Burma was ranked 176 out of 178 countries on an international corruption perception index[113]. The World Bank’s Worldwide Governance Indicators confirm this in terms of voice and accountability, control of corruption, regulatory quality, government effectiveness, rule of law and political stability. / The 3MDG Fund will take steps to ensure that the risk of corruption is minimised by channelling resources through a UN or International Organisation which has international fiduciary controls in place; conducting fiduciary risk assessment of implementing partners and monitoring fiduciary risk as part of ongoing risk management. Specific measures to reduce financial and fraud risk are: / Pre-emptive work – financial capacity assessments of implementing partners: / Selection of implementing partners is in accordance with the Fund Managers procedures, involving calls for proposals, expressions of interest or open procurement. This includes appraisal on the organisation’s experience and track record in managing funds according to international accounting standards. The Fund Manager will conduct financial management capacity assessments to rate partners as high, medium, serious or high risk. Funding is suspended for any implementing partners receiving a high risk rating until critical recommendations made by the Fund Manager have been implemented. The financial capacity of implementing partners will then be reassessed. / Looking for danger signals - regular monitoring of partners / Fund Management staff will conduct project monitoring visits to field offices and project staff. These will review whether adequate management and oversight processes are in place, and include data quality assurance. Findings from field monitoring are documented through a standard approach and shared with the management team. / Financial audits of implementing partners / All non-UN implementing partners will audited annually by an independent international audit firm. The firm is contracted by the Fund Manager. Areas of audit focus include: a) Effective, efficient and economical use of resources; b) Reliability of reporting; c) Safeguarding of assets; and d) Compliance with applicable legislation. Summaries of audit findings will be presented to the Fund Board; together with a tracking mechanism on progress on closing all audit issues. Under the 3DF progress against audit findings are monitored at each Fund board meeting. In the 2010 audit of 28 non-UN partners there were a total of 248 audit recommendations; none were rated as high priority. / UN partners are not audited separately. UN organizations are governed by UN ‘one audit principle’ agreed at the Executive Boards. / Commodity tracking / The 3DF has conducted commodity tracking reviews to ensure that all commodities procured with 3DF grants are utilised according to the agreements and all partners have functional and transparent commodity tracking systems in place. The reviews, which were conducted amongst 23 partners, are outsourced to an independent company with international experience in evaluating pharmaceutical distribution systems. A similar system of commodity tracking will be established for the 3MDG Fund. / Audits of the Fund Manager / The FMO will be audited regularly according to the audit procedures agreed at the Executive Board level of the organisation. For the 3DF UNOPS is audited by the Internal Audit and Investigations Group. Audits of UNOPS are not provided to the Fund Board. The Executive Board of the United Nations Development Programme and UNOPS resolution 2008/37 sets out that UNOPS can only disclose audits within strict provisions and only upon an approved request by a member state by the Executive Board. In the same resolution the Executive Board approved UNOPS accountability framework and oversight policies. The UK is represented at the UNOPS Executive Board. In the 3DF UNOPS has shared summary findings of audits, and progress in closing any recommendations have been tracked by the Fund Board at each meeting. Of the last audit, no audit recommendations were rated as high priority and all issues have been closed. / Culture of reporting suspicions of fraud and procedures for action: / The 3MDG Fund will have procedures for reporting suspicions of fraud within the operational guidelines and grant agreements with partners. As an example, 3DF is governed by UNOPS Organisational Directive 10 which states that "Any staff member or other personnel who has a reasonable basis for suspecting that fraudulent acts have occurred has a duty to report immediately his/her suspicions to his/her supervisor, to the Internal Audit and Investigations Group (IAIG) or to the UNOPS General Counsel. In addition a Fraud Hotline may be used (E-mail: fraudhotline@unops.org; or the telephone number(s) posted on the intranet: https://intra.unops.org/Global/Legal/Pages/ / ReportingFraud.aspx) If a staff member or other member of personnel is found having knowledge of a possible fraud and not reporting it, he/she could be subject to disciplinary or administrative action(s)." / To date there have been three organizations reporting suspicions of fraud. In all cases action was taken immediately and DFID Counter Fraud unit was also informed. Two of these cases have been closed and action is ongoing with the third.
E. How will expenditure be monitored, reported, and accounted for? / Fund Manager / DFID’s standard procedures on accounting, audit and reporting will be followed through a MOU with the Fund Manager. Based on the practice with the 3DF, the Find Manager provides an annual budget to the Fund Board by November each year for approval prior to 1st January. Cashflow statements and expenditure against the annual budget are presented on a quarterly basis and remains a standing item for review and discussion by the Fund Board. / For the 3DF, annual certified financial statements and annual expenditure reports are analysed by the Fund Board in terms of capacity to forecast. A final programme report six months after the end of the project will account for all funds received, including DFID’s. Under the 3DF arrangements, DFID checks the amount received in the UNOPS bank account, and the exchange rate for each disbursement against the certified financial statements. / Under the 3DF, UNOPS has established and maintains financial systems that ensure that funds are held, disbursed and accounted for in a timely, transparent and efficient manner. These systems include, but are not limited to, the establishment and maintenance of appropriate bank accounts, contracting Implementing Partners in a timely manner as well as rigorous Implementing Partner and internal audits and fund tracking. / Similarly to 3DF, the Fund Manager will be audited annually by a team of auditors appointed by its Internal Audit Department. The objective of the audit is to ascertain the effectiveness and efficiency of operations, including the economical use of resources in addition to verification of compliance activities of the office with the relevant UN and international organisation rules and regulations. / In terms of experience in country, the mid-term review of the 3DF in 2009 included as assessment of financial and procurement systems. UNOPS, as Fund Manager, was found to have established good financial management procedures and staffing levels were appropriate to maintaining standards. Audit reports were satisfactory and gave a good basis for follow up. / Implementing Partners / As part of the yearly financial reporting requirements, the Implementing Partners submit an annual work plan and budget. Following a review of the partner’s submission, the Fund Manager approves a budget allocation for the next implementation period, in line with overall programme agreement. As laid out in the operational guidelines, subsequent fund disbursement will only be approved following a review of achieved progress and results against agreed outputs and implementation plans. Implementing Partners will be contracted for 36 months. Financial reports are made every six months. / All programme expenditure is externally audited annually. The Fund Manager will appoint independent and internationally qualified auditors to ensure that the financial control systems of the partners are sound, the accounting returns are true records and funds are used for the purpose for which they are authorised. Adverse and disclaimer opinions from auditors will result in suspension of any further disbursement to the partners by the FMO until they satisfactorily demonstrates that issues identified have been resolved. UN Implementing Partners are subject to the auditing procedures provided for in the regulations of the participating UN Organization. All national and international NGO partners (19 in total) were audited in May/June 2011. / Following UN Development Group best practices, the Fund Manager will conducts a financial capacity assessment (FCA) of each partner. Financial management arrangements relating to accounting, reporting, audit, and internal controls are reviewed. Financial management arrangements are rated as fully acceptable if: they are considered capable of recording correctly all transactions and balance, support the preparation of regular and reliable financial statements, safeguard the entity’s assets, and are subject to acceptable auditing arrangements. Financial management will be assessed against international standards. A FCA report is completed for each partner. The draft assessment report is discussed with the partners and the final report will be shared with the partner. Where a report indicates a high or significant risk, the partner must submit a management plan to address the weaknesses. The Fund Manager is responsible for monitoring implementation of the agreed plan. A summary of the FCAs will be a standing item for review and discussion by donors at the Fund Board.
[113] Transparency International Corruption Perceptions Index 2010. http://www.transparency.org/policy_research/surveys_indices/cpi/2010/results

Management Case

A. What are the Management Arrangements for implementing the intervention? / This programme will be managed by the UK based DFID Burma Health Adviser, and locally appointed DFID Health Adviser and Programme Officer. The Programme Officer will be responsible for monitoring the UNOPS narrative and financial reporting against the DFID MOU. The DFID Health Advisors will be responsible for overseeing the annual workplan, monitoring plan and logframe, reviewing the narrative reports and representing DFID on the 3MDG Fund Board and technical subcommittees. The head of DFID Burma will represent DFID Burma at key policy meetings and for the Annual Review. / Governance arrangements for the 3MDG Fund build on the experience from the 3DF, while also taking into account the expanded scope of the new Fund. Consideration has been given to international best practice on: promoting participation and accountability; “do no harm”; capacity building; transparency and financial probity; promoting a rights-based approach; and supporting the aid effectiveness agenda. / A Joint Collaboration Arrangement (JCA) will be put in place between donors, providing donor cooperation in relation to the Fund. This agreement describes the roles and responsibilities between the donors and provides procedures for joint approaches to fund management and operations including for monitoring, reporting, accounting and a mechanism to address disputes. The JCA includes an exit strategy if invoked by a donor(s) for set criteria including if the Fund ceases to represent good VFM or fails to achieve expected results and outlines arrangements for funds if this occurs. / The core structure to oversee the Fund is the Fund Board. Membership of the 3MDG Fund Board will include donor representatives and three independent experts recruited by the 3MDG Fund donors. DFID will have a seat at the Fund Board. The Fund Board will: / Contract and oversee the Fund Manager. / Support 3MDG Fund replenishments. / Make funding decisions for the 3MDG Fund. / Review and approve operating policies developed by the Fund Manager. / Receive analysis of national strategies and operational plans to inform decision making. / Dialogue with the Ministry of Health, national coordination structures including the Country Coordinating Mechanism and Technical Strategy Groups, and with other key stakeholders. / Receive and approve annual work plan and budget, annual reports and audit reports and tracking of action points from the Fund Manager. / Identify any additional output and result areas required. / Ensure appropriate ‘voice and accountability’ within governance of the 3MDG Fund. / Commission[114] and receive independent external evaluation reports from the Evaluation Group. / Monitor, and where appropriate, mitigate risks. / Official communications for the Fund. / The independent experts will complement donor experience and skills, providing technical support on maternal, newborn and child health, HIV, TB and malaria, and the political and operational context in Burma[115]. The independent experts will also provide inputs on issues including oversight of the Fund Manager; development of TOR for reviews, evaluations, special studies and surveys; review of narrative and financial reports; development of 3DMG Fund policies and guidelines; policy dialogue; assessment of national strategies, programmes and operational plans as a basis for allocation of 3DMG Fund resources, and monitoring risk. Provision will be made for fees, retainers and costs. / The Senior Consultation Group will provide high level inputs to the Fund Board. This will be an advisory group and ‘sounding board’ for the Fund Board. Members will include senior MOH representatives and representatives elected by the Implementing Partners Forum. The Senior Consultation Group will meet with the Fund Board before each regular Board meeting to review programme implementation and provide advice and recommendations. The Group will also: consult with the Implementing Partners Forum (see Section 4.1.4), MOH and other stakeholders before and after Board meetings; monitor the performance of the 3MDG Fund with respect to gender, human rights and accountability; and monitor risks and advise the Fund Board on risk mitigation. The services of the Senior Consultation Group do not need to be procured, but provision will need to be made for reimbursement of costs. / The Evaluation Group will provide independent evaluation (see Section D). The Evaluation Group will establish an evaluation framework at the outset of the fund, ensure that programme M&E design, including baseline surveys, will generate required data, conduct a mid-term and a final evaluation, and conduct an impact evaluation, and other special studies as required. / Figure A1: Oversight and management of the 3MDG Fund / Role of Government / Public health services will form the core of service delivery for the programme at township level, supported by partnership with non state actors (non-government service providers and the private sector). The approach centres on increased dialogue and cooperation on the delivery of essential services at township level, through township coordination mechanisms. Selection of townships for Component 1 implementation will be based on analysis of criteria for prioritisation of townships and discussions with MOH on priorities for addressing the needs of rural and underserved populations. / Similar coordination will be supported through national level stakeholder forums, such as the CCM and TSGs. These bodies at national and decentralised levels are chaired by the MOH. The policy context for health is well developed, and these fora provide the opportunity to assess the implementation of national strategies, and engage in dialogue on areas where greater impact could be achieved. / The detailed operationalisation of Component 3, on HSS, has not been defined in detail; awaiting donors and UN to engage with MOH on joint analysis and agreement on priorities. The 3MDG Fund offers an opportunity for the UK and other donors to build trust and understanding around concrete service delivery goals with a range of stakeholders, including MOH and wider national authorities. Health sector work could increase dialogue and more sustainable development approaches, rather than just humanitarian interventions. Health programmes offer this possibility because there is strong international consensus around the need to support life-saving interventions for vulnerable people. / In terms of governance arrangements, the MOH will be represented at a senior level in the Senior Consultation Group, overseeing the Fund and providing advice to the Fund Board. If circumstances allow, it may be possible for an expanded role for Ministry of Health in Fund governance arrangements. / Coordination, policy dialogue and feedback / Components 1 and 2 of the Fund will be implemented in line with national policies and strategies for MNCH and the three diseases. A steering group of key stakeholders including MOH, UN and Fund Board members will oversee the planning and implementation of Component 3, which will also be implemented in line with national policies and strategies for health system strengthening. / Policy dialogue and coordination of activities will take place under the auspices of the TSGs (which will receive support from the MDG Fund). The 3MDG Fund donors will explore the scope to engage in sector-wide policy dialogue with the MOH. It is anticipated that the MOH might play an increased role in decision making should there be further positive developments in the political context. / To further promote and support consultation, an Implementing Partners Forum will be established, which will be open to all implementing partners and other key stakeholders. This forum will provide a mechanism for exchange of experience and review of progress, focusing on the 3MDG Fund, and will provide feedback to the Senior Consultation Group and the Fund Board. It is not intended to replace the CCM or TSGs or other coordination bodies, which oversee national strategies for health. / Feedback from beneficiaries and communities through accountability mechanisms will be collated by the Fund Manager and provided to the Senior Consultation Group and the Fund Board, to ensure that the views at township level are heard by those responsible for 3MDG Fund management and oversight. / Implementation arrangements / The Fund Manager will be responsible for effective, transparent and efficient management of the 3MDG Fund on behalf of the Fund Board, and will have delegated authority for the management of the Fund in accordance with its policy and priorities. While the Fund Manager is expected to liaise with the MOH and national coordination structures, including the CCM and TSGs, the Fund Manager will refer any issues concerning 3MDG Fund policy, strategy and funding to the Fund Board. / The Fund Manager will be expected to ensure that there is sufficient technical expertise within its staffing and have access to additional technical support as required. Core areas of expertise and responsibility will include MNCH, health systems, capacity development and training, engagement with partners including MOH, NGOs and the private sector, human rights, equity and gender. / In summary the Fund Manager will be responsible for: / Implementation of the 3MDG Fund in line with the Description of Action, donor priorities, agreed policies and procedures, and best practice principles for international aid. / Establishing effective working relationships with all stakeholders. / Establishing transparent financial systems, managing and disbursing funds in an efficient manner and demonstrating excellent value for money. / Drafting, under the auspices of the Fund Board, 3MDG Fund operating policies and guidelines. / Managing service commissioning through direct and competitive grant-making procedures. / Providing high quality technical advice, drawing upon expert resources as necessary to augment Fund Manager staff capacity, to implementing partners and the Fund Board. / Ensuring that the agreed outputs of the 3MDG Fund are delivered, monitored and reported on in a timely and cost-effective manner. / Providing central procurement services for implementing partners or contracting, where appropriate, independent agents to undertake procurement of commodities, and ensuring that drugs, equipment and commodities procured meet internationally recognised quality criteria. / Ensuring that implementation is consistent with rights-based approaches and advances gender equality, including the representation of women in decision-making roles at all levels. / Timely preparation of annual work plans and budgets, and summary of audit findings. / Developing an overall M&E plan, including baseline studies, financial and technical monitoring of implementing partner performance, and mechanisms for lesson learning. / Programme and financial reporting to the Fund Board, submission of financial forecasts and commissioning of external audits. / Establishing an Implementing Partners Forum. / Monitoring risks and implementing a risk management strategy. / Providing sub-contracting, administrative and secretariat support to the Fund Board. / Developing and implementing a 3MDG Fund Communications Strategy. / Implementing partners / Potential implementing partners for each component are outlined below. / Component 1 Implementing partners will include township health authorities, international and local NGOs, UN agencies and the private sector. Township health authorities will be responsible for coordination of service delivery and will work with others to assess township health needs and priorities, focusing on poor and underserved populations; develop coordinated township plans; make information and data available; maximise allocation efficiencies; facilitate staff training and ensure optimal support, supervision and oversight of health staff. / UN agencies and international and local NGOs will work in partnership with township health authorities to address supply-side and demand-side barriers. The 3MDG will draw on the comparative advantages of UN agencies to provide support across all townships covered by Component 1 including, for example, for township assessment and planning, and training of health workers in MNCH. Working with UN agencies may present efficiency gains based on collaborative working, the use of standardised approaches, and increased access to relevant data and information from within the UN system. / International NGOs are expected to play a key role in providing support for implementation activities, including facilitating training of Basic Health Staff and community health workers; ensuring the availability of essential drugs supplies and commodities; facilitating supervision and referral; supporting minor refurbishment of health facilities, and strengthening the capacity of local NGOs. Complementary private sector activities are expected to be supported, where these have the potential to improve coverage and health outcomes for poor women and children, through an intermediary organisation(s). / The Fund Manager will encourage consortia and collaborative working in order to ensure that townships receive a comprehensive package of support. All partners will be expected to coordinate activities under the auspices of the township plan, to make full use of accountability mechanisms and to participate in joint reviews of progress, using existing structures, including township and village health committees. The modalities of coordination at township level will be further developed during programme planning, will be reviewed and adapted to reflect experience of implementation. / Component 2 Implementation is likely to use a similar approach as by the 3DF. Implementing partners will include public sector programmes working with UN agencies, international and national NGOs, CBOs, and private sector partners, in partnership with national and decentralised MOH. There will be coordination between partners, including with township health authorities, as for the 3DF. / Township health authorities will ensure that activities are coordinated with interventions funded through other funding initiatives, such as the Global Fund and GAVI programmes. Where new strategic initiatives are proposed under the 3MDG Fund, the township health authority will be requested to work with other 3MDG Fund implementing partners in a similar way to that described for Component 1. / Component 3 Implementing partners will include MOH, UN agencies, international and local NGOs and research institutions. The MOH, UN agencies and other partners will participate in joint planning of HSS support from the 3MDG Fund and other funding initiatives. MOH will participate in performance management of the technical support provided, as well as relevant joint reviews and evaluations. / UN agencies that have experience of working with national government, and specifically the MOH, are likely to be preferred implementing partners. National and international NGOs are the most likely implementing partners for accountability activities. The 3MDG Fund will encourage applications from consortia that include partnership with local civil society organisations. / Implementation steps / Implementation will be divided into two phases. The inception phase will be 5 months (April-August 2012) and will include establishing the Fund Manager, developing supporting structures and procedures, and consultation. The implementation phase will be from September 2012 to the end of the programme timeframe. Key initial steps to be taken for each component are summarised below. / Component 1 / Identification of criteria for potential target townships Identification of criteria for townships will consider ranking exercises that have already been conducted by GAVI, the Global Fund, UNICEF and the MOH[116], sources such as the Integrated Household Living Conditions Assessment, and analysis of existing township data. / Assessment of potential implementing partners This will be determined by strategic issues including: availability; implementation and absorptive capacity; authorisation and access to work in selected townships and under-served populations; and scope to provide capacity building to ensure longer term sustainability through local organisations. / Selection and contracting of partners to support implementation This first stage would be a call for expressions of interest from partners that meet the criteria. The second stage would be a request to shortlisted partners or consortia to submit a full proposal. Selection will be undertaken by the Fund Manager using standard grant appraisal procedures. / Selection of townships This will be based on proposals submitted in Step (iii). Final selection will be made in consultation with the MOH and other stakeholders. / Completion of comprehensive township assessments and coordinated health plans This process will be led by the township health team and involve all implementing partners. Where township assessments and plans have not been completed, the 3MDG Fund will support township health authorities to coordinate this in partnership with other implementing partners. Township assessment and planning will be led by the MOH, following their guidelines, with support from UN agencies, such as WHO, which is currently providing support for the process through GAVI HSS. Should selected UN agencies be unable to facilitate this in a particular area then the Fund Manager may contract an alternative Implementing Partner, such as an NGO with appropriate technical skills and capacity. / Identify gaps and priorities for 3MDG Fund support This will be done by township health authorities, with implementing partners. Gaps will be prioritised and addressed by the 3MDG Fund to ensure that the full package of services is provided. The 3MDG Fund will build on the existing township plans, which reflect all inputs required to deliver essential services. / Baseline data collection The Fund Manager will coordinate the development of a common protocol for surveys to establish baseline data in the selected townships, in close consultation with partners. Baseline data will be collected within 6 months of agreements being signed. / Develop work plans and budgets The implementing partners will be expected to develop a 3-year work plan and a 1-year detailed operational plan and budget, based on activities identified in Step (vi). This will include procurement requirements and baseline data collection. / Component 2 / Finalise analysis of gaps and priorities The Fund Manager will outline the process to address strategic gaps identified, as per the principles set out in Section 3.3.2. / Selection and contracting of implementing partners The Fund Manager will select partners using standard calls for proposals to assess eligibility, capacity and experience. Consideration will be given to a bridging extension of existing contracts where performance is considered satisfactory and partners meet the criteria for support under Component 2, to ensure a smooth transition between the 3DF and the 3MDG Fund and avoid gaps in implementation. / Development of a procurement plan This is a critical early step, to ensure continuity of drugs and supplies. This plan will need to be integrated into the overall procurement plan for the 3MDG fund as township plans under Component 1 are developed. / Component 3 / Further consultation with the MOH and other key stakeholders and further analysis A steering group of stakeholders including MOH, UN and Fund Board members will oversee the detailed planning and implementation of Component 3. Priorities for specific support will be determined following further consultation and analysis. Further scoping will be also be conducted to identify HSS requirements at state and region level, as plans for decentralisation are finalised. / Selection and contracting of implementing partners Implementation modalities for each area of activity will be determined after joint planning with the MOH and key stakeholders. / Core Structures / Supporting Structures / Fund Board / Donor representatives + / 3 independent experts oversee Fund Manager / Senior Consultation Group Elected representatives of Implementing Partners Forum + representative of the MOH provide advice to the Fund Board / Fund Manager / Contracted by the Board to manage implementation of all components of the Fund in accordance with Fund policy / Evaluation Group / Contracted to provide independent evaluation services
B. What are the risks and how these will be managed? / The 3MDG Fund is high risk, but is considered to be justified by the potential impact on people’s lives. Risks relate to the political and operating context, and to programme management and implementation. / Political risks include the unpredictable political environment; relationship between the Government of Burma and donors; domestic priorities in donor countries; GoB and MOH support and approval for key elements of the 3MDG Fund, and restrictions on the operation of non-state actors. / Contextual risks include the policy environment for MNCH interventions; capacity of township health authorities and health systems, including shortages of midwives; absorptive capacity of UN and NGO partners; predictability of funding from other sources, in particular the Global Fund, and challenges of working in areas where renewed tensions and conflict are a possibility. / Programme management and implementation risks include timeframes for start up of activities; capacity and skills of the Fund Manager and implementing partners to move towards a more sustainable development approach, and management and coordination at township level. / A detailed risk matrix, outlining these risks is in Table B1. / An emerging risk for the 3MDG Fund are the financial constraints currently experienced by the Global Fund, which have resulted in the cancellation of the current Round 11 and a global call for reductions of up to 25% in the second phase budgets of existing grants. This has a number of serious implications: / 1. Cutting Burma's existing grants (Round 9) by up to 25% will put the modest gains made in containing the epidemics at risk. Grants are already conservative and do not fully address these epidemics. / 2. The Round 11 application would have addressed critical gaps in the country response. These gaps remain. / 3. With the cancellation of Round 11, there will be no new Global Funds to address the emergence of artemisinin resistant malaria until 4 years after the launch of the WHO strategy to address this urgent threat to global malaria control. / The 3MDG Fund is based on the assumption that the Global Fund would return to Burma, which it did on 1st January 2011, and that Burma would be successful in subsequent rounds of funding. Lack of Global Funds at global level was not anticipated, and partners in country are identifying the possible implications. The situation changes rapidly as new information emerges from the Global Fund. On 15th December the Global Fund the Global Fund released details of the Transitional Funding Mechanism for two years from 2012-2014. New funding will then be available from 2014. Burma is identified as eligible for this funding, particularly for malaria and TB. The CCM is currently preparing a case to (i) demonstrate where it can make efficiency gains or austerity measured to reprogram funds to priority areas (ii) defend the existing Round 9 grants and (iii) develop a proposal for transitional funding. / There is likely to be less than the anticipated funding for HIV, TB and malaria. The worst case scenario is that Burma is unsuccessful in its application for the Transitional Funding Mechanism and there is a gap (2012/13) on anticipated funding for high priority activities. The 3MDG fund is designed to respond flexibly to changes in the context, which would require additional resources from donors. Without this, reallocation of funds from component 1 (maternal and child health) to component 2 (HIV, TB and malaria) will cost of women and children’s lives. / Programme management and implementation risks can be managed by the Fund Board and the Fund Manager, through early planning, development of clear TOR and effective performance monitoring, and capacity development. Contextual risks can be mitigated to some extent through policy dialogue, support for analytical work, including that related to human resources for health, and engagement with the CCM and TSGs. Political risks can be mitigated to some extent through effective donor coordination and diplomatic presence, building on the credibility of the 3DF, maintaining dialogue through the CCM and TSGs, close consultation with the MOH on prioritisation, and complementary capacity building for government and civil society on accountability and responsiveness issues. / However, many contextual and political risks are outside the control of the Fund Board and the Fund Manager. Consequently, they will need to develop a risk management strategy, and monitor changes in the environment that influence risk. Key aspects of the risk management strategy include: / Regular review of risks and mitigation measures by the Fund Manager and as standing items at Fund Board meetings. / An independent Fund Board member analyses changes to the operating context. For the 3DF this member has provided two weekly updates using media and his personal contacts. / Regular review of risks and risk mitigation measures by a Risk Management Advisory Group, comprising UN, donor, Fund Manager and independent representatives. This group is responsible to update the risk assessment matrix and make recommendations to the Fund Board on mitigating actions at each Fund Board meeting. Any significant risks which arise between meetings are addressed out-of-session. There may be options to combine risk management advisory groups to monitor risks across all donor-funded programmes for the sector, including for the 3MDG Fund. / Inclusion of risk management on the agenda of donor meetings with the MOH. / Inclusion of risk management and risk advice in the responsibilities of the Fund Manager CEO. / Inclusion of risk monitoring in the 3MDG Fund M&E plan. / Development and implementation of a communications strategy agreed by the 3MDG Fund donors and coordinated by the Fund Manager. / These processes contribute to a culture of monitoring risk. From experience of the 3DF, responses to risks to date have been rapid and have taken the highest priority for the Fund Board. Where significant new risks have arisen between Fund Board meetings, there is rapid information gathering and response and actions developed by the Board (including via remote working.) / Table B1 Risk Matrix / Risk factors Probability Impact Mitigation Measure / Political risks / Unstable and unpredictable political environment High Medium The 3DF has shown that political risks can be managed to a significant degree through effective donor coordination, including shared intelligence and informed communication about the situation from a humanitarian and development perspective. / The relationship between the Government of Burma and the 3MDG Fund donors deteriorates Medium High The 3MDG Fund donors will maintain dialogue through the CCM, the TSGs and the SCG. Donors will explore opportunities to increase engagement with the GOB, in response to positive political developments. The experience of the 3DF has established credibility and created political awareness within and outside the MOH. This will be built on and further enhanced through a consistent communication strategy. / The EU Council Decision becomes more restrictive Low High Build a clear political understanding within the EU of the 3MDG Fund and humanitarian need in Burma. / The Fund Board comes under pressure due to divergent views amongst donors or domestic political questions about support for the Fund Low High Develop a shared MOU including dispute resolution mechanisms at the outset, and maintain open and clear communication with regular meetings, minutes and clarity on formal agreements reached. Donor representatives should ensure their respective senior managers and diplomatic presence are well briefed and aware of issues facing the Fund Board and the 3MDG Fund well in advance so that a common position is maintained. / Lack of Government and MOH support for the 3MDG Fund Low High Donor consultation with MOH and other relevant ministries on the design and approach of the 3MDG Fund. Seek involvement from the Ministry of Planning and the Prime Minister’s Office as well as other political interests to develop a positive view of the 3MDG approach across the MOH and government. / Failure to obtain approval for selected Implementing Partners and increased political restrictions on Implementing Partners operating in hard-to-reach townships Medium High Reach early agreement on township selection through dialogue with MOH, building on experience of GAVI HSS, WHO and UNICEF. Build on earlier experience and approval of non-state Implementing Partners, some of which are likely to be the same under the 3MDG Fund. The 3MDG Fund will support closer working partnerships with township health authorities, which will be a key partner. Establish an early positive relationship between the Fund Board, Fund Manager, MOH and other ministries. The Fund Board should secure access for Implementing Partners during donor-MOH negotiations and through MOU for selected townships. Use donor’s diplomatic presence to reinforce agreements. / Lack of Government of Burma support for civil society engagement and capacity building and proposed actions to increase voice and accountability Medium Medium Build on credibility based on the experience of the 3DF and establish relationships outside the MOH. 3MDG Fund design includes joint assessment of existing structures, capacity building for MOH at central and township level and for township coordination and health committees on accountability and responsiveness of health services. Build on experience of other programmes that have promoted accountability and developed civil society capacity. Clear and consistent communication strategy. / Introduction of registration requirements exclude local NGOs and CBOs from operating Medium Medium Build on credibility based on the experience of the 3DF. Dialogue with government. Support local NGOs and CBOs to engage with government. / Contextual risks / MOH and UN agencies unable to provide sufficient leadership and inclusive processes for MNCH, HIV/AIDS, TB and malaria strategy development Low Medium Establish close relationship between the Fund Board and the UN Country Team. Provide specific support for TSGs and managers responsible for MNCH and 3 diseases strategy development. Fund Manager has access to technical expertise. / MOH does not agree to policy changes required to expand community and facility based services and/or imposes restrictions on service provision e.g. range of family planning methods available Medium Medium Work through UN partners including WHO and UNICEF on policy dialogue and advocacy. Engage professional associations in advocacy. Share and disseminate evidence. Provide support for operations research and technical assistance. / Delays in GF 9 implementation results in requests for additional funding for 3D from the 3MDG Fund to address gaps Medium Medium Dialogue with 3D TSGs to prevent and address implementation bottlenecks and ensure early planning of contingency measures, including seeking funding from additional sources. / Cancellation of Round 11 and postponement of next resource round from GF High Medium Dialogue with 3D TSGs to ensure early planning of contingency measures, including (i) prioritisation and reprogramming Round 9 (ii) seeking funding from GF Transitional Funding mechanism or other sources. / Limited capacity or willingness of township health services to manage 3MDG Fund inputs or cooperate with Implementing Partners Low High Capacity building for township health teams in leadership, management, and M&E. Experience of JIMNCH suggests the risk is low or can be mitigated. 3MDG Fund will give greater emphasis to partnerships with township health authorities responsible for coordination and leadership and will build on coordinated township health plans. Role of non-state Implementing Partners will be to support delivery of services by the public sector. Scope to directly contract of provide direct funding to townships will be explored should the political context improve, in order to build ownership and buy-in. / Unfilled posts for midwives, who are critical to supervision of community health workers and provide the link between the community and the lowest level of the health system High High Support for HRH analytical work and strengthening HRH planning and management. In particular looking at current bottlenecks in effective deployment of midwives. / Support for advocacy by UN agencies with MOH, particularly as budget allocation for health may increase. / Detailed analysis of and reimbursement for full costs for outreach services. / Consideration of non-monetary forms of incentives, particularly for hard-to-reach areas / Renewed tensions/ conflict between ethnic communities and between ethnic communities and government threatens implementation especially of Component 1 Medium Low Establish good relations at township level and with community leadership. Build in measures to mitigate this risk in voice and accountability strategies. / Programme management and implementation risks / Timeframe for start-up and commencement of implementation Medium High Preparatory work prior to contracting Fund Manager. / Fund Manager lacks adequate skills, management and technical capacity Low High Active Fund Board involvement in the appointment of the Fund Manager and senior and external staff. Engaging a technical support facility for the Fund Manager. Performance measured as part of the contract. / Fund Manager does not perform to expectations Low High Clear TOR and monitoring of Fund Manager against agreed inception and annual workplans with clear deliverables and target dates. Fund Board exercises oversight of Fund Manager. / Senior Consultation Group lacks leadership and technical capacity Low Medium Early selection of team, clear TOR specifying expected outputs, and monitoring of SCG performance by the Fund Board. / Limited interested or able Implementing Partners as programme requires shift from humanitarian approach and greater coordination with townships Medium High Early engagement with potential Implementing Partners. More open approach to existing and new partners and involvement of consortia and new actors. / Implementing Partners’ M&E systems inadequate to ensure quality data recording and reporting Medium Medium Capacity building of Implementing Partners including township health teams for M&E including use and analysis of data. Regular supervision and support by the Fund Manager. / Limited capacity for financial and fiduciary risk management Medium High Capacity building in financial management for township health teams and Implementing Partners.
C. What conditions apply (for financial aid only)? / The intervention does not include any financial aid to the Burmese Government. / UK funds will be implemented within the parameters of the EU Council Decision on Burma which was adopted in 1996 and revised in 2004, 2010 and 2011. This allows humanitarian aid and non-humanitarian work in a few sectors (including health) through UN and member state agencies, NGOs and decentralised support to local civilian authorities. This Council Decision was suspended in April 2012.
D. How will progress and results be monitored, measured and evaluated? / Approach / The 3MDG Fund will have a strong focus on accountability for results. There is a logical framework showing a clear logic model of the relationship between inputs, outputs, outcomes and expected impact of the 3MDG Fund. In line with best practice principles, the 3MDG Fund monitoring and evaluation system will harmonise efforts with existing national monitoring and evaluation structures for health, such as the Health Management Information System as well as collecting information on specific programme activities supported through the Fund. / Township surveys will generate population-based baseline data. The 3MDG Fund will consider support for robust national surveys (that will improve strategic information on specific health issues) and to strengthen the Health Management Information System under Component 3. This three-pronged approached – township surveys, national surveys and HMIS support – aims to ensure that robust data is generated on the programme results and impact and to strengthen the Ministry of Health’s routine monitoring system. This three-pronged approach allows triangulation of data and analysis of trends. / Independent evaluation is a core principle of the 3MDG Fund. / Key elements / Indicators and targets. The indicators in the logical framework are aligned as closely as possible with indicators already in use in Burma; some are taken directly from national strategies and operational plans or Global Fund Performance Frameworks. Previous templates, such as for 3DF or UNAIDS, can be used to ensure that all needed information is included. Initial targets will be set based on township assessments and plans. Targets may need to be adjusted when baseline surveys are completed. / Routine monitoring. Implementing partners at township level will support and strengthen reporting of health and service delivery data by community health workers and facility staff to the township health team. The Fund Manager, together with implementing and technical partners, will develop instructions for all reporting forms and ensure that all relevant staff are trained in completion of the forms through. Both the Fund Manager and implementing partners will implement monitoring and evaluation activities as part of a broader supportive supervision approach, which should use objective measures and a series of short checklists to foster improvements in service delivery. / Monitoring visits and reviews Monitoring visits will be conducted by the Fund Manager. Monitoring includes: reviewing technical and financial reports, client checklists and service provider checklists, and community feedback tools such as citizen score cards. Visits will: provide a summary of the implementing partner’s performance; track progress against work plans; verify achievements described in 6-monthly reports by reviewing primary documentation and through direct observation; follow-up of previous recommendations; assess management, administration and human resources, and identify challenges and solutions. The data obtained from monitoring visits will be used to: provide feedback to the implementing partner on its performance; suggest corrective measures to be taken, and assist partners to improve their monitoring and reporting, as necessary. DFID staff will join monitoring visits. / The 3MDG Fund Board (of which DFID is a member) will conduct formal monitoring field trips. Joint annual performance monitoring reviews will be conducted annually by the 3MDG Fund Board. / Baseline data Baselines are required for all logical framework indicators in the targeted townships. An area of innovation for the 3MDG Fund is that programme-specific outcome data will be collected through township-level surveys. This is not only valuable for assessing programme impact, but will allow triangulation with national survey information and official statistics. Surveys to collect population-based baseline data at township level will be completed within 6 months of agreements being signed with partners. A common survey protocol will be developed by the Fund Manager, as outlined above, to ensure a consistent approach. The 3DF has supported national data collection and national surveys (such as the National Tuberculosis Prevalence Survey 2010[117]). The Joint Initiative on MNCH in Cyclone Nargis affected areas successfully implemented knowledge, practice and coverage surveys with MOH support. Township survey findings and baseline information will be shared with national programmes and multi-stakeholder Technical Strategic Groups through formal meetings or reports. / Measures for health programmes are usually obtained from surveys in relevant areas. However, using small geographic areas, such as townships, can result in wide variations in population-based indicators, and the more variable a health characteristic is, the more difficult it is to predict accurately. This is particularly the case with higher-level indicators, such as mortality, which can have large confidence intervals because of the small population size of townships. One option is to use small area estimators, which allows the combination of information from different sources (surveys, censuses and registers) to estimate an attribute of a small population generally defined by geographic boundaries. This approach could be considered as one method for measuring impact at the township level. / Data quality assurance Data quality assurance will be the responsibility of the Fund Manager and, if needed, data quality audits will be conducted by the Fund Manager or by another organisation. A data quality assurance system will allow managers and decision makers to verify the quality of reported data, and also allow stakeholders to develop action plans to remedy data quality issues. Feedback on data inconsistencies will be linked to technical support to be provided by the Fund Manager. / Use of data: M&E data will be used to assess the performance of the Fund Manager; assess whether activities implemented by partners are on track; and identify gaps, problems, key priorities and areas for interventions; measure the effectiveness of specific interventions and measure programme coverage. In addition, M&E data will be used in programme development, advocacy, resource allocation and to modify programme design where needed after consulting with the Fund Board. The M&E system is expected to provide the information required for the comprehensive evaluation of the Fund and to develop new evidence-based strategies and derive lessons learned. / Strategic information: Wherever possible the 3MDG Fund will promote the establishment of robust national strategic information on the health MDGs. An example of this type of approach is 3DF joint funding for the National Tuberculosis Survey 2010. An account of the conduct of this survey is provided as an example of best practice in the WHO 2010 Global TB Report. / System strengthening: Component 3 can strengthen systems, such as the national Health Management Information System at local and central levels. Possible areas of support may include: / Supporting communicable disease surveillance such as national HIV serological and behavioural surveillance in 2013. / Improving the availability of data on maternal and child mortality. Specific support could be considered for a national maternal and under-five mortality population-based survey, including technical assistance for design of the survey protocol and analysis of findings, as well as financing for implementation of the survey. This could build on the experience and approach taken to support the recent national TB prevalence survey. / Strengthening the capacity of the TSG M&E working groups. / Conducting a systematic review of the HMIS to identify gaps and assess capacity and training needs, and develop a plan for strengthening the generation, analysis and use of data to inform decision-making, planning and monitoring at all levels. / Supporting the MOH to conduct quantitative and qualitative research on health-seeking behaviour and expenditure on health care related to maternal, neonatal and child health / Supporting analysis of the contribution of the private sector to health care and use of private sector providers by the poor. / Identifying other health systems and operations research priorities and providing technical support to strengthen research capacity, including through promoting partnerships between international and national research institutions. / Training for township health teams to develop their capacity for analysis and use of data. Consideration could also be given to provision of IT equipment and related training. / Strengthening implementation of the existing system for maternal and neonatal death audit. / Equity Approach in M&E / Monitoring equity: The 3MDG Fund is pro-poor. It addresses the major causes of illness and death for the poor, and targets poor and vulnerable areas and populations. Services will be delivered as close to the beneficiaries as possible, and accountability mechanisms will promote their voice in how services are delivered. The strong focus on equity will be monitored including: through disaggregated data from population-based surveys and routine information systems (where feasible); and operational research including qualitative and participatory approaches linked to the beneficiary accountability framework. / Human rights: The 3MDG Fund will take a rights-based approach to M&E, founded on the principles of impartiality, independence, credibility, and usefulness. It is critical that M&E measure issues such as non-discrimination, equality, participation, inclusion, transparency and accountability, to ensure that health services are accessible, acceptable and of high quality. Information captured through the indicators in the logical framework, will be supplemented by qualitative studies and evaluations. / Civil society monitoring: Component 3 HSS includes measures to strengthen voice and accountability, and support for civil society will emphasise capacity development for increased transparency and accountability. It is expected that civil society will be involved in independent monitoring and feedback. The logframe indicator on health committee and beneficiary satisfaction of services delivered will be monitored through surveys conducted by civil society organisations. It is highly likely that these organisations will need capacity strengthening and technical assistance to conduct these surveys. / Beneficiary Accountability: Transparency and accountability for results is a key element in M&E. The 3MDG Fund will build upon the 3DF Beneficiary Accountability Framework[118]The objectives are to: / Improve the way an agency engages with local communities in decisions that affect them by striving to enhance participation and to seek informed consent. / Share information with beneficiaries to promote and improve transparency and information provision. / Provide beneficiaries with channels through which concerns can be raised. This is part of the ethical commitment to listen, monitor and respond to beneficiary concerns. / Ensure that all staff are provided with a thorough understanding of Accountability and Quality Management Principles and Standards. / Evaluation: / The evaluation framework will be established at the outset of the Fund, including methodological approaches and quality assurance of data collection and analysis. The questions have not been determined but should cover some of the major evidence gaps (below). The programme design is based on the underlying assumptions that increasing availability of quality health services and simultaneously reducing demand side barriers will lead to increased utilisation of health services and therefore improve the health of the population. Analysis of this will disaggregate the population by quintile income groups, sex, age and other indicators of vulnerability so as to assess whether the programme differentially benefitted the poorest and most vulnerable. The evaluation framework will consider options for evaluation of impact of the intervention and test this assumption. The township approach and phased roll out provides a natural opportunity for a quasi-experimental design to assess the impact of this complex intervention and attribution through assessment of the counterfactual, using for example a stepped-wedge impact evaluation design. In this approach each township would have a baseline and end line comparison of impact but in addition late starting townships could serve as comparison ‘controls’ for early starting townships. The feasibility of a quasi-experimental design will be assessed in the development of the evaluation framework. / Figure D1: illustrative example of a quasi-experimental design to impact evaluation / Stepped - Wedge Impact Evaluation Design / Unit of analysis Programme period: / e.g. township 1 2 3 4 5 / 1 control innovation Innovation innovation innovation / 2 control control Innovation innovation innovation / 3 control control Control innovation innovation / 4 control control Control control innovation / Evaluations could test whether the cost and cost effectiveness assumptions for the programme from the LIST modelling hold with implementation. A ‘societal’ or holistic analysis of cost and cost effectiveness would also capture the costs to households. As a fragile state, a more qualitative assessment of the impact of the fund on operating environment on the implementation of the fund. / It is anticipated that a number of stand alone research studies will be commissioned under the evaluation framework. It will not be possible to fill all evidence gaps, so priority will be given to the most relevant studies, particularly to service delivery in a fragile state context. Where people seek care and why, and what the major barriers to access to services in this setting should be priorities. Linked to this is the contribution of the private sector to service delivery and whether increased health provision overall leads to increased update of services, and if so, which ones (public, private, community-level)? / Independent evaluation: An independent Evaluation Group is part of the core governance and management arrangement of the 3MDG Fund. The Evaluation Group will provide independent evaluation services and specifically: / Establish an evaluation framework at the outset of 3MDG Fund implementation / Conduct a mid-term evaluation, assessing programme, financial and management issues. / Conduct a final evaluation, again including assessment of programme, financial and management issues. / Rigorous evaluation of impact. / Specific evaluations or research studies addressing key questions identified in the evaluation framework at the outset, or arising from the Mid Term Evaluation. / With restrictions in access and sensitivity around research and data collection, it is unlikely that the Evaluation Group will be able to collect data independently. In developing the evaluation framework the group will assess the 3MDG systems and proposed data collection tools and methods (including surveys) so that routine information will generate the required information for evaluations. Specific TORs and research protocols will be developed for each of the required areas of evaluation. / The scope of the framework will cover the evaluation criteria endorsed by the OECD-DAC, namely relevance, effectiveness, efficiency, sustainability and impact. Importantly this should include an equity and gender analysis of who has benefitted from the Fund and whether the Fund has delivered VFM? / The Evaluation Group may periodically be requested by the Fund Board to conduct specific research, provide technical review of the design of operational research, human rights audits and evaluations as related to health services, and qualitative studies. The core evaluation tasks will be funded through a core budget (with an allocation of £2.5 million) with an option to fund additional activities as requested. / The Evaluation Group will be contracted through an open procurement process conducted under the procedures of the Fund Manager. Review of the applications will be by the Fund Board (or by experts appointed by the Fund Board) and will be independent of the Fund Manager. The Evaluation Group will be precluded from any implementation role to avoid conflict of interest. The Evaluation Group will report to the Fund Board but all reports will express the independent conclusions of the Evaluation Group. / A ‘Sounding Board’ group will be available to the Evaluation Group and the Fund Board if requested. The group will comprise a virtual team of nominated experts from the donor agencies (however, outside the management chain and donor country team concerned). They will review and provide a steer to the Evaluation team and Fund Board on the direction or independence of the evaluation. / Documenting and disseminating learning The 3MDG Fund will promote lesson learning and sharing of findings and experience through meetings, workshops, seminars, conferences, dissemination events and publications. E.g. annual and quarterly reports, case studies, evaluation and research findings. / Roles and responsibilities for monitoring and evaluation / The Fund Board is responsible for monitoring the Fund’s performance. The Senior Consultation Group will provide guidance to the Fund Board on M&E. Advice will also be sought from the Technical and Strategic Groups, which have been initiated to provide guidance and co-ordination. The TSGs will review the 3MDG Fund M&E framework and help to ensure consistency with national plans and indicators, and it is anticipated that semi-annual TSG meetings will review 3MDG Fund results. / The Fund Manager will be responsible for developing an overall M&E framework; aggregating results; and assessing performance of partners. The M&E plan will include: indicator definitions, information on methods for data collection, analysis and reporting and on how data quality assurance will be coordinated. The Fund Manager will report to the Fund Board, possibly through use of a dashboard tool employed by the 3DF, and will ensure co-ordination with national programmes and TSG M&E working groups. The Fund Manager will formally report to the Fund Board every six months. / The Fund Manager will provide technical support on M&E to implementing partners and ensure that they establish population-based baselines, develop indicator definitions, conduct routine programme monitoring to measure progress and conduct periodic data quality assurance checks. Within the logical framework, potential data sources for measuring results against baselines, milestones and targets have been suggested. During the first 6 months of implementation, the Fund Manager will, in conjunction with partners, establish methods to be used to obtain the necessary data to measure results. Some indicator baselines and targets may need to be updated from more accurate data from surveys. / The Fund Manager will develop, maintain and share a standardised database of information from monitoring reports, special studies, research, field visits, reviews and evaluations. The Fund Manager will be responsible for ensuring that data on 3MDG Fund results is disseminated to partners, government and donors; and used to inform evidence-based policy and programme decisions. / The Fund Manager will collaborate with the independent Evaluation Group, which will review the 3MDG Fund M&E framework to ensure that data required can be collected. / Implementing partners for Component 1 will collect and report data at township level, from health workers, health facilities, laboratories and other service delivery points. This will feed into the HMIS through the TMO and into partners own reporting to the Fund Manager, using standard reporting templates, based on national reporting formats as far as possible. Though the M&E system may, at the peripheral level, require manual recording of data by health workers, partners should be prepared to enter data into a computerised system and to report electronically. UN and NGO partners will provide technical support for data analysis, reporting and improving the data quality, as required. / Implementing partners for Component 2 will monitor and evaluate activities, either on a project or programme basis or as part of wider activities. Partners for Component 3 will monitor and evaluate activities including technical support, and capacity development for accountability. Indicators for all three components will, where appropriate, be derived from the logical framework (see Annex 1). / All implementing partners will be responsible for six month progress and annual reports, including reporting against the agreed indicators in the logframe. Each implementing partner will be responsible to collect baseline, mid-term and final evaluations of their specific programme. In addition implementing partners will be encouraged to take a continual learning approach through operational research. / Terms of the donor bilateral agreements will be harmonised to the requirements outlined in the Description of the Action. Internal DFID Annual Reviews will be conducted based on 3MDG Fund report and field monitoring visits. / Monitoring and evaluation coordination The 3MDG Fund will support MOH-led coordination activities. These include: organisation of quarterly TSG meetings; encouraging partners to submit monthly data at township level; updating and harmonising data collection forms; organisation of quarterly, annual and planning meetings with partners at township and central levels; and joint monitoring missions. The 3MDG Fund Manager and Evaluation Group will liaise with the other donor-funded programmes, including the Global Fund and GAVI Health Systems Strengthening, to ensure that monitoring and evaluation is consistent with Ministry of Health planning. / Figure D2: Detailed relationship of the M&E stakeholders / Budget for M&E: / M&E budgets will have clear budget lines within partner grants. The 3MDG Fund has a minimum of 6% for M&E activities in each of the components of the Fund. £2.5 million is nominally allocated to the Independent Evaluation Group. (This allocation recognises that it is unlikely that this group will be able to undertake independent data collection but will have to ensure that sources of data for the evaluation, including population based surveys, are robust). The Fund Manager’s role is central to M&E of the Fund. For 3DF costs for M&E account for approximately 32% of Fund Management overall budget[119]. Using this percentage, this would represent £4.76 million of Fund Management costs for M&E. Taken together the allocation for M&E is 7.4% of the 3MDG Fund.
Logframe / Quest No of logframe for this intervention: 3320163
[114] The Fund Board will be responsible for evaluation of proposals and selection of the independent Evaluation Group
[115] National experts would be especially valued in this role
[116] GAVI has selected 180 townships based on immunisation coverage; the Global Fund will cover approximately 280 townships, excluding townships in difficult to reach border areas; MOH has identified 70 townships as hard-to-reach; UNICEF has prioritised 150 townships of which 70 are the same townships defined as hard-to-reach by MOH
[117] For a summary of the survey as an example of good practice see World Health Organisation Global Tuberculosis Control Report 2010
[118] See 3DF Beneficiary Accountability Framework. August 2010
[119] This is based on the 2011 approved budget for the 3DF and defining direct M&E costs to be technical and M&E staff costs and programme monitoring costs (including in-country travel and transportation). Administrative support and indirect costs fro M&E are not included.

# Annex 1: Essential MNCH Health Services Package (Option 1 Component 1) with evidence for interventions.
Continuum of care	Intervention	Who delivers the intervention				Inputs
		Family; community	Outreach	RHC, sub-centre	Hospital (SH/TH)	Supply side / (drugs, commodities / equipment, HRH)
Pre-pregnancy	Birth spacing/ family planning/ pregnancy surveillance	CHW	MW	MW		Contraceptives
Pregnancy	Management septic abortion / Antenatal care / Fe/folate supplementation[120] / Multiple micronutrients[121] / Screening: VCT, STI (VDRL) / Ensuring optimal maternal nutrition status[122] / Malaria prevention[123] / PMTCT[124] / De-worming / Tetanus toxoid (2 doses) [125] / Birth planning / Breastfeeding promotion, nutrition / Pre-delivery care / MgSO4 for pre-eclampsia / Steroids for premature labour / Antibiotics for premature rupture of membranes / Safe blood	CHW / CHW / AMW / CHW / CHW / AMW / CHW		MW / MW / MW / MW / MW / MW	Doctor / Doctor	Theatre, antibiotics / Fe/Fol / Blood screening kits / Food supplements / LLIN / Mebendazole / Tetanus toxoid / Training and support for village committees, CHW, AMW / MgSO4 / Steroid drugs / Antibiotics / HIV blood screening kits (procured under Component 2)
Delivery	Delivery / Skilled birth attendant delivery / Active management of 3rd stage of labour [126](Prevention post-partum haemorrhage [127], distribution of clean delivery kit[128], identification and management of maternal sepsis[129]) / BEmONC at RHC, CEmONC at TH / Caesarean section	AMW, MW	MW	MW	MW / Doctor, MW	Safe delivery kits / Misoprostol/ Oxytocin / Theatre equipment / Drugs, commodities
Postpartum	Postpartum care including family planning	AMW	MW	MW	MW, Doctors	Oxytocin; referral
Newborn	Essential newborn care package including visits at 0/1, 3,7, 15 days post-delivery / Resuscitation[130] / Cord care / Care of LBW / Referral sick newborns / Sepsis (CCM)[131][132] / Temperature control (KMC)[133] / BF within 1 hour / BCC ENC[134],[135], exclusive breastfeeding and appropriate complementary feeding	AMW	MW / MW	MW	MW, Doctors	Resuscitation equipment / Antibiotics (sepsis) / Referral mechanisms / E.g. voucher schemes
Infancy and childhood	Childhood prevention and management of illness / Community case management ARI[136] and diarrhoea[137] / Malaria prevention / Malaria diagnosis and treatment[138] / Measles treatment / Referral sick child / Childhood immunisation / Nutrition / Exclusive breast feeding 0-6m / Continuous BF and complementary feeding >6m / Micronutrients (Vit A, B1, Fe, Zn[139]) / Growth monitoring and promotion / CMAM / Nutrition support for high-risk / children / Teaching hand-washing to children and parents	CHW	MW	MW	Doctor	ORS and Zn / Antibiotics / RDT, ACT, LLIN / Referral mechanisms / Vaccines, cold chain / Vit A, Vit B / Sprinkles / MUAC, scales / Plumpy’nut
Waste	Waste segregation and waste disposal			Basic health staff	Doctors Nurses	Guidelines/ protocols / Disposal bins, gloves
Safe blood supply	Screening				Lab staff	Screening test kits / Storage facilities
[120] Kidanto H et al. Risks for preterm delivery and low birth weight are independently increased by severity of maternal anaemia. S Afr Med J 2009. 99(2): 98-102
[121] Christian P et al. Effects of maternal micronutrient supplementation on fetal loss and infant mortality: A cluster-randomised trial in Nepal. Am J Clin Nutr 2003. 78(6): 1194-1202
[122] Kramer M and Kakuma R. Energy and protein intake in pregnancy. Cochrane Database Systematic Review 2003 (4): CD000032
[123] Richards A et al. Cross-border malaria control for internally displaced persons: Observational results from a pilot programme in eastern Burma/Myanmar. Trop Med Int Health 2009 14(5): 512-21
[124] Both J and van Roosmalen J. The impact of PMTCT programmes on maternal health care in resource-poor settings: Looking beyond the PMTCT programme--a systematic review. BJOG, 2010. 117(12): 1444-50
[125] UNICEF. Maternal and neonatal tetanus elimination by 2005: Strategies for achieving and maintaining elimination. 2000
[126] WHO. Recommendations for the prevention of postpartum haemorrhage. 2007
[127] Hofmeyer G. Misoprostol to prevent and treat post-partum haemorrhage; a systemic review and meta-analysis of maternal deaths and dose-related effects. Bull WHO 2009:87; 666-677
[128] Darmstadt G et al. Impact of clean delivery-kit use on newborn umbilical cord and maternal puerperal infections in Egypt. J Health Popul Nutr 2009. 27(6): 746-54
[129] Van Dillen J et al. Maternal sepsis: Epidemiology, etiology and outcome. Curr Opin Infect Dis 2010 23(3): 249-54
[130] Lawn, J et al. Reducing one million child deaths from birth asphyxia: A survey of health systems gaps and priorities. Health Research Policy and Systems 2007. 5(1): 4
[131] Baqui A et al. Effectiveness of home-based management of newborn infections by community health workers in rural Bangladesh. PIDJ, 2009. 28(4): 304-10
[132] Bang A et al. Is home-based diagnosis and treatment of neonatal sepsis feasible and effective? Seven years of intervention in the Gadchiroli field trial (1996-2003). J Perinatol, 2005. 25: S62-S71
[133] Conde-Agudelo A et al. Kangaroo mother care to reduce morbidity and mortality in low birthweight infants in Cochrane Review. 2000, The Cochrane Library (Update Software): Oxford
[134] Kumar V et al., Effect of community-based behaviour change management on neonatal mortality in Shivgarh, Uttar Pradesh, India: A cluster-randomised controlled trial. Lancet, 2008. 372(9644): 1151-62.
[135] Kohn D. Community involvement saves newborn infants in India. Lancet, 2008. 371(9620): 1235-6
[136] Sazawal S and Black R. Effect of pneumonia case management on mortality in neonates, infants, and preschool children: A meta-analysis of community-based trials. Lancet Infect Dis, 2003. 3(9): 547-56
[137] UNICEF is piloting prescribing of antibiotics by CHWs. Current policy does not allow prescribing at this level for e.g. pneumonia
[138] Kamat V and Nyato D. Community response to artemisinin-based combination therapy for childhood malaria: A case study from Dar es Salaam, Tanzania. Malar J. 9: 61
[139] Baqui A et al. Effect of zinc supplementation started during diarrhoea on morbidity and mortality in Bangladeshi children: Community randomised trial. BMJ, 2002. 325(7372): 1059

References