Type of Review: Annual Review

Project Title:	Ecosystem Services for Poverty Alleviation (112082)

Date started:	23/10/2007	Date review undertaken:	12/06/2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet willcalculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
DFID is providing a total of £27 million from 2009-2017 to fund research on the linkages between ecosystem services and poverty alleviation, in partnership with NERC(£10 million) and the ESRC (£3.5 million) The total budget for ESPA is £40.5 million.

What are the expected results?
In the long term, ESPA will enable people, communities and development actors to manage ecosystems in ways that benefit the poor, support sustainable and inclusive growth and protect their functions for future generations. / In the medium term, ESPA will enable policy makers, planners and development practitioners to understand the role of ecosystem services in poverty reduction and growth, the current threats those ecosystems are facing and what policies and practices are most effective at promoting their sustainable management. / In the short term, ESPA will enable the research community to deliver robust and relevant evidence to business, government and other key users, on how ecosystem services contribute to poverty alleviation. This will include evidence on ecosystem dynamics, values and how to manage these values more effectively.

What is the context in which UK support is provided?
Ecosystems are being degraded at a significant rate. The recent Millennium Ecosystem Assessment concluded that 60% of ecosystem services studied are severely degraded or being used unsustainably. In addition, impacts arising from exogenous change, such as climate change and economic volatility are accelerating ecosystem deterioration and presenting much more acute policy and management challenges. Such changes have the potential to initiate large-scale ecosystem collapse and irreversible change. / All this has significant consequences for development. The poorest and most vulnerable groups, especially those living in rural areas, tend to be most directly dependent on ecosystem services and are most likely to suffer the consequences of change. This is because poor people are also less able to access substitutes to services provided by ecosystems. Additionally ecosystems services provide a direct source of wealth for developing countries, such as through forest and fisheries products, as well as their underpinning of key economic sectors such as agriculture. / Despite international, national and local efforts to prevent the deterioration of ecosystem services, success remains limited. This is because there are many inherent trade-offs in the policies and methods for managing ecosystem service management and poverty reduction and understanding of how to manage these more effectively remains limited. / ESPA aims to work at the heart of this urgent challenge. This presents some distinct challenges as this will entail bringing together different research approaches, paradigms and thinking, between natural and social sciences as well as ensuring that the science that will be produced can deliver a development impact at some point in time. / It is for this reason that ESPA is committed to supporting interdisciplinary research with impact. It will do this by supporting research -that can deliver an improved understanding of how to sustainably manage ecosystem services with a focus on delivering poverty reduction and inclusive growth.

## Section A: Detailed Output Scoring

Output 1: [A high quality interdisciplinary body of knowledge generated on ecosystem services, their dynamics, their [human] uses, and pathways to sustainable management and poverty reduction]
N.B. All outputs and indicators were revised following the last annual review which recommended that the ESPA logframe was brought in line with the new format and guidance on theories of change. A process led by the Directorate was set up and revisions made through a process of consultation with all funding partners. This year’s Annual Review was conducted against the new logframe, which has been largely agreed as information has been collected by the Directorate alongside new outputs and indicators. This Annual Review has revealed, however, that some minor adjustments are still needed to outputs and indicators - mainly to improve clarity not purpose. This will be completed and agreed by the other funding partners and DFID within six weeks of this Annual Review being completed. / Output 1 score and performance description: A / The original output 1 was: ‘A strong research and evidence base on the interface between ecosystem services, their dynamics and management, human use and pathways to sustainable poverty reduction.’ The revision of this output maintains its focus on the delivery of a high quality knowledge base but has added emphasis on the delivery of a multi/interdisciplinary approach to research and evidence, which is core to ESPA and was not sufficiently reflected in the previous formulation of output 1. / In determining progress on this output, the review team looked at research commissioned to date, key research outputs and how previously defined research gaps were being addressed. / During 11-12, ESPA ran two calls for research, and oversaw the research undertaken by the 18 Framework Projects (FP) commissioned during 10-11. The Directorate also ensured that it captured any research outputs that had arisen from the 11 Strengthening Research Capacity Projects, which had been commissioned during the ESPA scoping phase in 2008-09, but which had not yet been reported on key research outputs. / The ESPA Call 2011 was for medium sized research consortia. This was a very large call which aimed to commit £16M (Full Economic Cost – FEC) – but due to various challenges - managed to secure projects worth less than originally envisioned - £9M. The call resulted in 90 full applications, 44 going to Panel with three selected. The final three projects were selected on the basis of their multidisciplinary teams, research objectives and method. There was a delay of a few months in contracting these projects as all had to meet further conditions to ensure that they fell wholly within ESPA’s remit. All three projects are now contracted and have started pulling together teams and have submitted their inception reports. / Some very important lessons were learnt on how to run effective commissioning process within ESPA were learnt (see Section B 1.5 on Challenges). These lessons have been fed into and resulted in a complete restructuring of the next ESPA 2012 call thus bringing in further reassurance that ESPA will deliver on output 1. They included reducing the number of full projects that go to Panel, provide greater opportunities for applicants to better understand key requirements and engage in dialogue with other researchers in the ESPA community. / Overall, there is also a good geographic spread of programmes and a good spread across different types of ecosystems, including forests, agricultural systems, coastal systems and freshwater systems. In the ESPA portfolio, there are projects investigating thresholds and tipping points in ecosystems and how these affect vulnerable groups. Decision making, incentives and management of ecosystems are also covered well. Dynamics between ecosystems and social and economic influences feature in a number of research programmes, as do impacts of exogenous changes. Contributions of ecosystems to national economies and opportunities for green growth are topics less well represented.
Progress against expected results: / Indicator 1.1 Understanding of the gaps in current knowledge of ES for PA research that can meet the demand and needs of sustainable management of PA and growth / The Directorate conducted a gap analysis (see Annex 2) of the existing ESPA portfolio during design of the call for the ESPA 2012 projects. The analysis highlighted the need to focus the next call on collection of new primary data from in-situ analyses of ecosystems and poverty. This is because the analysis revealed that the 2010 call had a preponderance of applications seeking to do modelling work based on secondary data only. The Directorate also issued two questionnaires to identify lessons from the 2010 call application process, and also to identify any further research gaps. The questionnaire results were published in the ESPA website . / This indicator may needs some adjustment as gaps identification will be less relevant one all the research has been commissioned. Furthermore ‘understanding’ of the gaps is not really sufficient but the programme should also be ensuring that it is feeding knowledge and information into the identified gaps. / Indicator 1.2: Number of research calls and funded ESPA projects that will generate new & useful evidence for sustainable management of ecosystem services that will achieve poverty alleviation and growth. / The ESPA programme commissioned it’s most significant portfolio of new research during FY 2011-12. This included three major projects with values of up to £4m working in Africa, South Asia and the Amazon. The first project will explore the links between ecosystem services affecting the rural poor at the forest-agriculture interface in Malawi and Colombia. The second will evaluate ecosystem services and poverty in the context of subsidence and sea level rise, land degradation and population pressure in the Ganges-Brahmaputra-Meghna (GBM) Delta. The third project will explore the relationships between ecosystems, health and poverty with a focus on zoonotic diseases in Africa which are emerging or re-emerging as public health problems. / Four smaller Evidence and Impact Research Grants (EIRG projects (circa £50,0000 each) were also commissioned by the ESPA Directorate. These have a specific aim of feeding evidence into key policy processes during 2012 including Rio+20, the UN Convention on Biological Diversity(CBD) and the development of the Sustainable Development Goals (and the MDG+ agenda). / The 120 researchers funded by ESPA during FY2011-12 join 298 individuals who have been involved in the earlier ESPA Partnership and Project Development grants and Programme Framework Grants (see Annex 3 for an analysis of the thematic and geographic spread of the Programme Framework Grants). / Indicator 1.3:ESPA research projects produce high quality research outputs in ISI journals addressing the issues of ecosystem services and their link to poverty alleviation in a range of formats. / Considerable effort has gone into collating all research publications funded by ESPA to date. Challenges with the Research Councils Research Outputs Database mean that it has not been possible to capture all research outputs during 11-12. Work to ensure that research outputs reporting for ESPA will improve will continue during the next year. Information available indicates that d the reporting period, ESPA projects produced 12 high quality academic publications, including five which were published as open access, listed below. See Annex 1 for full list of 2011-12 publications. / Maize grain and soil surveys reveal suboptimal dietary selenium intake is widespread in Malawi, Scientific Reports; article also includes a developing country author. / A Battle Lost? Report on Two Centuries of Invasion and Management of Lantana camara L. in Australia, India and South Africa, PLoS ONE. / Biodiversity and global health—hubris, humility and the unknown, Environmental Research Letters. / Basin-Scale Control on the Phytoplankton Biomass in Lake Victoria, Africa, PLoS ONE. / Web-based environmental simulation: bridging the gap between scientific modelling and decision-making, Environmental Science and Technology / In addition, there have been 20 other outputs reported, including conference reports, working papers, and policy briefs. It has not been possible this year to pull together a list of these publications, but the Directorate is working on this and this information will be available for the next review. / Recommendations Output 1: / Whilst there are clear indications from the research commissioned, ability to learn from commissioning process, and research outputs to date, that output 1 is heading in the right direction, considerable effort must be sustained to ensure that this output is fully achieved given the challenges experienced to date in commissioning ESPA research. / The commissioning process for the large grants was time consuming and cumbersome, especially for developing country applicants. The project has now put in place mechanisms to address these issues in subsequent calls but will need to ensure that it continues to learn lessons from its experience of commissioning the right type of ESPA research. / The Directorate will need to re-evaluate knowledge gaps following the outcome of the next call and make proposals to the Board to address those before issuing the next calls. / The Directorate should continue its work to develop an effective and accessible research outputs reporting system as a key priority. / This output’s indicators may still need some minor adjustment and milestones need to be formulated and agreed within six weeks of this Annual Review. / Impact Weighting (%): 40% / Revised since last Annual Review? Yes - was 45% / Risk: Low/Medium/High - Low / Revised since last Annual Review? N

Output 2: [Capability built amongst ESPA researchers to conduct multi/interdisciplinary ecosystems services and poverty alleviation research that meets the needs of users, supported by new multi/interdisciplinary methods, frameworks, data, tools and syntheses ]
Output 2 score and performance description: B / This output has been revised from the original output 2 ‘Innovative, interdisciplinary research and methodologies, delivering tools and approaches that enable the simulation and prediction of socio-ecological responses to multiple drivers.’ The key change in this output is to ensure that the programme is also building capability within the research community for this type of work including delivering knowledge and evidence that is relevant to users’ needs. / This output scored B as whilst there are indications that this output is on track it has been slower than expected. ESPA has worked hard this put the processes and structures to increase the likelihood that this output will be delivered and there is every expectation that this output will rise to A or higher by next year’s review. / Key results are from the 18 Framework Projects (PFG) commissioned in the 2010 call and which are now in their second year. A quick overview of all projects indicates that researchers are addressing linkages between ecosystem services and aspects of human wellbeing are well represented in the programmes, and the projects are delivering methods, conceptual frameworks. Two projects are notable for the development of methods that are being adopted outside ESPA. There is significant interest in the application of experimental economics (Randomised Control Trials) to evaluate payments for ecosystem services in Bolivia (NE/I00436X/1) whilst the ESPA Framework Project (NE/I002952/1) has developed a conceptual framework making the link between ecosystem services and poverty alleviation which has fed into a major new European Commission (FP7) project of €9 million value. There is also evidence that the recently awarded ESPA 2011 consortia are utilising methods developed by a number of PFG projects. / Whilst there is progress demonstrated by research outputs arising from the PFGs, there is still further work to be done to ensure that ESPA can continue to deliver the types of methods, tools etc. that are relevant to other users. In an attempt to help applicants and researchers address this challenge, the Directorate has provided guidance for applicants and researchers (Knowledge and Impact frameworks) as to how to approach multi/interdisciplinarity in a way that is relevant to user needs. / Learning from the ESPA 2011 call, the ESPA 2012 call is structured in such a way as to provide more opportunities for building multi and interdisciplinary partnerships and ways of working. By using a three stage process, non-starters will be quickly eliminated at an early stage, enabling interaction between a smaller group of applicants and the Directorate throughout proposal development, to foster a better understanding of how to achieve multi/interdisciplinarity science with development impact. / As illustrated by analysis of applications to previous calls, and low level of southern lead applicants, there remains a greater need for building capability in southern institutions. Whilst all ESPA projects have both northern and southern researchers in their teams, there are very few that have southern research leads. ESPA should carefully consider over the next year how it should better address the acute lack of interdisciplinary working and leadership capability in the South. Launching a fellowship scheme later this year will only in part address this challenge.
Progress against expected results: / Indicator 2.1: Multi/interdisciplinary frameworks / methods tools developed and applied by ESPA support to interdisciplinary research. / The 18 ESPA Programme Framework grants (commissioned through the 2010-11 call – see Annex 3) aim to provide tools and frameworks that could underpin future ESPA research, or other research in this area. A number of projects are currently making progress developing new methodologies for ESPA. For instance, a cluster of PFG projects are working on issues relating to the social processes and necessary trade-offs underlying the delivery of enhanced human well-being through ESPA. The projects are considering the role of constructs such as environmental justice and equity, as well as the role and importance of effective institutions and governance systems. Other projects are pioneering new analytical and modelling approaches – including linking agent-based modelling with compartment flow modelling, the application of experimental economics to understanding the benefits of different approaches for Payments for Ecosystem Services and a project leading to web based approaches for environmental simulation (published in Environmental Science and Technology). Some specific examples include: / NE/I002960/1 has developed a new index for describing changes in a range of ecosystem services providing the world’s first environmental health index . The research has also been published in PNAS thus exposing it to a much wider research community. / NE/I003673/1 has developed tools and frameworks linking agent-based models and deterministic models to study biodiversity, ecosystem services, social sustainability and tipping points in African drylands. / NE/1001448/1 has developed a conceptual framework for understanding decision networks in coastal resource management based on research in Kenya and Bangladesh. / NE/I002952/1 has developed a framework for socio-ecological systems in ESPA designed for use by other ESPA projects which has also been adopted as part of a proposed follow-on project to the European Commission. / There is not yet much evidence to show that these tools are being applied by other ESPA projects. / The ESPA Directorate also developed a set of frameworks and guidance documents to support the programme, applicants and researchers to better address interdisciplinarity. These include the ESPA Knowledge Framework and Impact Framework . The Knowledge Framework scopes out a framework for linking ecosystem services with poverty and the aim is that it will evolve as ESPA’s understanding of key links improves. / Indicator 2.2: Number and proportion of new ESPA projects delivering interdisciplinary research. / The 2011 call resulted in fewer than expected projects. The success rate from the call was disappointingly low. / All of the 3 major projects that were selected from the ESPA 2011 call were chosen on the basis of having potential for multi/interdisciplinarity. For instance, Project NE-J001570-1: Dynamic drivers of disease in Africa: ecosystems, livestock/wildlife, health and well-being; has a particularly impressive team of researchers working across various disciplines. The other two ESPA 2011 consortia projects (forest- agriculture interface in Malawi and Columbia and subsidence and sea level rise, land degradation and population pressure in the Ganges-Brahmaputra-Meghna (GBM) Delta) still need to do more work to effectively integrate the disciplines involved in their research. The Directorate is working on this and will need to be carefully monitored over the next year through the projects; regular updates. The projects’ inception reports are due to be presented to the PEB in September. / Indicator 2.3: Number and proportion of new ESPA projects delivering research that responds to the ESPA knowledge frameworks / The call for ESPA-2011-12 projects was launched prior to the Knowledge Framework being published by the Directorate and many applicants were delivering project proposal that dealt with either ES or PA but not the inter-linkages between the two.The Knowledge Framework was developed to elaborate on some of the possible links between ES and PA. By responding to the Knowledge Framework this means responding to the links between ES and PA. It will be important to assess whether the existence of such a guidance document and a different call structure will deliver research projects that are better linking ES and PA objectives in the ESPA 2012 call. / Indicator 2.4: Number and type of high quality multi/interdisciplinary research outputs produced by ESPA projects / 3 projects out of 12 papers (25%) published in FY 11/12 had been classified as interdisciplinary across Natural and Social Sciences. It is expected that the programme will experience an increase on this figure next year. / It will be important to develop a methodology to measure and define the level of ambition around quality of research outputs. / Indicator 2.5: Interdisciplinary graduate qualifications achieved through ESPA projects or for staff linked to an ESPA project / Data unavailable for this year, but projects will start to report this from FY2012-13 through the new RCUK Research Outcomes System. All projects will be asked to report retrospectively for previous reporting periods. / In future information collected under this indicator should include whether qualifications are being achieved by northern or southern researchers, and the project should also consider desegregating this information by gender. / Recommendations Output 2: / ESPA researchers have demonstrated that they are beginning to deliver new methods, tools and frameworks in the area of ecosystem services and poverty alleviation. However, ESPA will need to work further on ensuring these meet user needs, and that ESPA is prioritising working to build this capability among southern researchers. / ESPA needs to evaluate success of the 3-stage project proposal process to see if it delivers better on ESPA’s objectives. / ESPA Directorate needs to regularly review the various methods, tools, frameworks and syntheses being delivered by ESPA researchers to ensure that they continue to be relevant to user needs. / ESPA Directorate and Secretariat should develop and submit options to the PEB on how the programme could further build multi/interdisciplinary capability in the South, for instance by hosting events in the South. / The Directorate should keep track of the range of different approaches to multi/interdisciplinarity being adopted by ESPA researchers and share these within the ESPA community to encourage further discussion and learning. / A methodology will need to be agreed on how to measure and define the level of ambition with regard to the quality of ESPA’s research outputs. / This output’s indicators may still need some minor adjustment and milestones need to be formulated and agreed within six weeks of this Annual Review. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Low/Medium/High- Low / Revised since last Annual Review?Y – was previously medium

Output 3: [Demand for ecosystems and poverty alleviation research is stimulated by the ESPA Directorate and ESPA supported researchers] evidence into use agenda
Output 3 score and performance description: A / The original output 3 was ‘High uptake of research outputs and their synthesis by early and on-going engagement and communication with policy makers, practitioners and decision’. The revised output and indicators still need some further adjustment to ensure that they are fully capturing the programme’s commitment to research uptake as stated in the project’s business case. / Over the last year, ESPA has established a firm requirement for all applicants to fully justify the relevance of their research and to whom, as well as to identify how the research is likely to have an impact. Every ESPA applicant and researcher now has to identify how they will maximise the chance that their research is used by policy and decision-makers, and/or others who may in future demand the results of ESPA’s research. / To assist in this, the ESPA Directorate has produced a specific guidance note on Impact for use by ESPA researchers and applicants. All potential projects are also assessed and scored against potential for development impact. ESPA has clearly worked hard to put the necessary structures and incentives in place to deliver on impact over the last year – it is therefore expected to see demand increase as ESPA progresses. However, as this is a new area for many ESPA researchers, monitoring progress closely on this element will remain important. / The ESPA Directorate has also started a process by which researchers are monitored in terms of their invitations (and attendance) at relevant (policy and research) committees.
Progress against expected results: / Indicator 3.1: ESPA programme is stimulating new demand for interdisciplinary research on Ecosystem Services and Poverty Alleviation. / 7 significant requests for ESPA support have been noted but there is notably less demand from low income countries. Know requests include those from: / the Government of India for ESPA assistance in integrating impact considerations into water resources research; / the Ministry of Science and Technology in Brazil on biodiversity and the private sector; / The World Bank’s Wealth Accounting and Valuation of Ecosystem Services (WAVES) programme invited ESPA to collaborate in their work linking ecosystem services into national systems of accounting; / UK institutions, including both DFID’s Forestry Team and the UK’s Global Food Security Programme; / The National Science Foundation and USAID who are keen to develop joint working on food security, ecosystems and health. / Indicator 3.2: ESPA projects are engaging in knowledge exchange and forming partnershipsand networks across disciplines / ESPA projects reported 48 Achievements in the past year, including stakeholder engagement, working with local and national governments, major research milestones, and the development of researcher-user partnerships to submit proposals to the ESPA-2011 consortia funding call. / A total of 146 other activities were initiated(including public lectures and debates, online publications, press interviews and conferences, articles in popular magazines and media appearances. / Most projects reported as being relevant to policy development, and a significant number had given advice to government in the past year. However, the information under this indicator has not been well captured until now. A move to the Research Outcomes System from FY-2012 onwards will assist in better reporting in the future / Indicator 3.3: Demand for ESPA research from end users. / 4 requests to use ESPA research, including the Government of Kenya, Ministry of Environment in Bolivia and UNDP. / Indicator 3.4: ESPA researchers prominent in national development agendas using ESPA results. / 8 researchers or projects presented evidence of the policy relevance of their work at a national level. ESPA was also invited to present early findings at a (UK) All Party Parliamentary Group on Environment and Development event at the Houses of Parliament. Presentations of ESPA early findings were made to MPs and representatives of NGOS. The DFID PUSS gave the keynote speech. As yet, no recorded ESPA researchers have been invited to join committees, and no research outputs have been reflected in national development policies / Indicator 3.5: New investments in ESPA related research provided by agencies outside the ESPA partnership. / There are no further investments beyond the current partnership agreed yet. However, ESPA funded projects have reported that they had submitted proposals to seek funding from other agencies in order to build and add value to already funded ESPA activities. The Directorate has begun discussions with National Science Foundation in the US, FAPESP in Brazil and Department for Science and Technology in South Africa to investigate interest and potential for collaboration. / Recommendations Output 3: / Further revision of the output and indicators are needed to ensure that this adequately captures research uptake in a way that delivers benefits for the poor in developing countries and as originally intended in the DFID business case. This should also include defining milestones – to be completed within six weeks of this review. / The Directorate must ensure that it captures all relevant information on how projects are ensuring the research is being used, and generating greater demand for ESPA research The Directorate will report to September PEB on how the programme will capture this information. / ESPA should be encouraged to continue its engagements with other programmes that are potential ‘ready’ users of ESPA research (e.g. WAVES, PEI, IPBES) however the Directorate should manage their time inputs to these initiatives very carefully. / Impact Weighting (%): 20% / Revised since last Annual Review? No / Risk: Low/Medium/High: Medium / Revised since last Annual Review? No

Output 4: [New developing country-led (institutional) relationships, networks and partnerships formed for ecosystems services and poverty-alleviation, research, influencing and impact, nationally and internationally]
Output 4 score and performance description: B / This output has been adjusted from the original output 4 ‘Enhanced capacity of southern researchers to conduct, lead and use/communicate high quality ESPA-type interdisciplinary research, including through effective north-south and south-south research partnerships’. The rationale behind the adjustment was to broaden out southern engagement from research partnerships to research – user partnerships. The indicators under this output will still need some adjustment to ensure that they reflect the original ambition stated in the business case and are able to capture quantitative information, particularly on the extent and depth of southern engagement. / This output scored a B because the programme is still in early stages of working towards delivering of this output. It has also been faced with several challenge of understanding how to run international calls to maximise developing country participation within the systems and resources available to the Research Councils. The programme has demonstrated that it is working to resolve these issues both at a programme and system-wide level. It is possible to say that there is an expectation that this output will deliver A or above by the next review cycle. / ESPA does continue to have very few southern lead applicants although all projects have developing country researchers but for this review, it has not been possible to find out what position and status they hold not in the research projects. The JeS system and the administrative burden it presents, has continued to discourage southern applicants, as evidenced by the ESPA 2011 call where very prominent southern researchers did not even get through the first stage as they had made one small application error. Some basic adjustments have been made to reduce the chances of this e.g. removing the need for administrative approval prior to submission and financial information at the first stage. However, more needs to happen but working through the Shared Service Centre of the Research Councils presents challenges. There are plans to hold a special RCUK – DFID forum to discuss in greater detail how to address the challenge in the SSC/RC systems to make it easier for southern applicants, as well as those less well versed in Research Council formats. There will also be further discussions to address developing country capacity building through DFID – RC programmes. NERC and ESRC are contributing to this discussions and any progress made should also benefit ESPA. Given RC’s centralised systems, this is the only practical way of moving forward for ESPA on these matters. / The ESPA 2012 call has, by operating a three stage application process, removed the need for using JeS in the first two stages, making it again easier for non-JeS users to apply in the early stages. This has unfortunately still not had the desired effect for increasing the number of southern led applicants at the first stage. However, it is early in the process and it is not until we receive full applications that an proper assessment of the level and nature of southern engagement can be made. / There are some encouraging signs via the quality of academic papers published with developing country authorship. ESPA has develop a very clear set of criteria regarding how papers will be assessed using a 5* system that requires developing country authorship, open access, international peer review and responsiveness to the ESPA research framework.
Progress against expected results: / Indicator 4.1: Proportion of projects where developing country institutions and researchers play a significant role in management and delivery in the ESPA portfolio. / All of the ESPA-2011 grants have significant contributions from developing country researchers and institutions. Two of the much smaller ESPA Evidence and Impact Research Grants (EIRGs) also have significant developing country participation: EIRG-2011-175 and EIRG-2011-180. The third ESPA EIRG grant will feed results into one of the ESPA-2011 grants by supporting work by developing country researchers and institutions (EIRG-2011-166). The remaining EIRG is a desk-based systematic review being undertaken by a UK organisation. This indicator has reached 75% achievement. / Out of all projects funded 2011-12 which involve a total of 120 researchers 50 (42%) are developing country researchers. / Indicator 4.2: Developing countries gained greater prominence in national and international research agendas. / Data currently unavailable. However there is a process in place to report in FY 2012/13 via the RCUK Research Outcomes System. / Indicator 4.3: Developing country-led research projects produce high quality, interdisciplinary research outputs of the links between ES and PA. / A total of 12 high quality academic papers were published with half of them having some developing country authors - 20 authors out of a total of 61 were from a developing country institution (33%). Some examples of the papers are included below, with a full list in Annex 1: / The potential use of storm water and effluent from a constructed wetland for re-vegetating a degraded pyrite trail in Queen Elizabeth National Park, Uganda, Physics and Chemistry of the Earth; all four authors are from Ugandan institutions. / Maize grain and soil surveys reveal suboptimal dietary selenium intake is widespread in Malawi, Scientific Reports; lead author is affiliated with the Malawi Ministry of Agriculture and Food Security, the article is also open access. / Managing the natural capital of papyrus within riparian zones of Lake Victoria, Kenya, Hydrobiologia; one Kenyan author. / Web-based environmental simulation: bridging the gap between scientific modelling and decision-making, Environmental Science and Technology, two DC authors. / Challenges and opportunities in linking carbon sequestration, livelihoods and ecosystem service provision in drylands, Environmental Science & Policy, 11 DC authors out of 21 total. / Agricultural encroachment: implications for carbon sequestration in tropical African wetlands, Global Change Biology, second author is with a Ugandan university. / Indicator 4.4 New investments, putting ESPA research into use in developing countries. / 1 activity of value £88,000. ESPA’s research is being put into practice in Kenya through the Swahili Seas project. The team leveraged £88,000 from Aviva for a range of activities including supporting set up costs for the project and supporting postgraduate students. / ESPA has also started held some early stage discussions with a few potential ‘southern’ donors who may wish to collaborate with ESPA: FAPESP in Brazil and the Department of Science and Technology in South Africa. / Recommendations Output 4: / Further adjustment of the output and indicators are needed to provide further clarity and ensure that it meets originally intended in the DFID business case. This should also include defining milestones – to be completed within six weeks of this review. / Aligned with the activities to engage southern partners, the Directorate should track and monitor progress, and capture lessons learnt, from ESPA’s work to engage developing countries and developing country researchers in ESPA. ESPA might also benefit from a better way of communicating and reporting on developing country engagement in ESPA. / ESPA (NERC and RED) should play a key role in planned RED – RCUK discussions on southern engagement, and should push for an early meeting on this. / By November 2012, obtain data for Indicator 4.2 either through RCUK Research Outcomes System or other credible and available method. / Impact Weighting (%): 20% / Revised since last Annual Review? Yes – was 15% / Risk: Low/Medium/High - Medium / Revised since last Annual Review? No

## If the project involves more than 4 Outputs please copy the box above and paste below.

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Yes / The 2010-11 Annual Review recommended that: ‘ESPA's Logical Framework, along with associated milestones and indicators will be reviewed and revised in line with current DFID thinking in terms of theories of change by November 2011 to ensure that the logical framework can be used to capture evidence describing the overall impact of the programme.’ / The revision of ESPA’s logframe took longer than expected and is the result of an extensive process with LTS/ITAD and the Directorate leading, and has been through PEB discussion and agreement. The logframe milestones are still missing and this has made it more difficult to assess (over and above judgement), whether the programme is on track to meet indicator targets and output aims. / This Annual Review has pointed to the need to make some further adjustments in the indicators and wording of output 3 and 4. / Recommendations: Logframe / 18. ESPA must set out the milestones for all outputs and make the further adjustments to the output 3 and 4 and output indicators as identified by this review. This must be completed within 6 weeks of this review and be finally signed off by the September PEB. / 1.2 Overall Output Score and Description: A / This project is deemed as meeting expectations at this point in time. / Whilst two of the outputs have been scored B – this is largely due to the slightly slow start up and there is every indication that despite scoring Bs, ESPA has learnt lessons and applied them, and set up the structures and process to ensure that these two outputs deliver effectively over the next year. ESPA is a large programme, a new partnership, dealing with research in a cutting-edge area that is bringing science with development impact. Setting up the strategies for implementing this programme has therefore taken longer than expected. / That said, research has been commissioned as expected, with a few delays, for instance the consortia projects were contracted a few months later than originally envisaged. These delays are however what would normally be considered to be the norm for such a large programme. NERC normally allow a six month start-up phase for large projects, i.e. from point of approval to point at which the project starts operating and spending. The ESPA 2010 calls are now beginning to deliver results, with the first set of academic papers being published in peer reviewed journals. The ESPA 2011 call consortia projects are up and running and there are indications that over the next year these projects will start to deliver some findings. / Key concerns lie around the continued lack of southern leadership in ESPA research and a lower than expected interaction between the programme and developing country networks and for a. The programme needs to address this more effectively over the next year. / A key concern for the next step is the extent to which the full programme of activities is commensurate with demand from users – especially policy makers. It will be important, prior to the next annual review, to provide the review team with a full picture of how the programme fulfils demand, where the major gaps are and how it proposes to address those in the final calls. / This review had to be conducted without milestones, and there is an urgent recommendation for the Directorate to set up a clear set of milestones that link to output targets and the dates at which these should be met for PEB approval in September. / 1.3 Direct feedback from beneficiaries / The ESPA directorate conducted a survey after the last call to ascertain lessons learnt from how the call was run. This survey results can be found at http://www.espa.ac.uk/resource-centre/online-resources/espa-applications-process-review).
1.4 Summary of overall progress / ESPA now has a growing portfolio of research. Information about projects that have been funded by ESPA is available from the ESPA website at: www.espa.ac.uk/projects. For an analysis of thematic and geographic distribution of Framework Projects see Annex 3. / Call Period Number of projects / ESPA Situation Analyses 2007–2008 6 / ESPA Strengthening Research Capacity 2008–2010 11 / ESPA Partnership and Project Development 2009–2011 28 / ESPA Programme Framework Grants 2008–2013 18 / ESPA 2011 Grants (Consortium Grants) 2012–2017 3 / During 2011-12 there were twenty-seven papers published in a range of academic journals/books, for full list see Annex 1. It has not been possible to pull together information on grey literature this year, as the reporting outputs database has not yet been set up for ESPA, but there is every indication that there have been grey literature outputs arising from ESPA projects. This information will be collected and reported on at the next (mid-term) review. / The Directorate is now up and running and ESPA’s governance arrangements are more firmly established. Some important lessons have been learnt through the 2011 research calls, and this has fed into the 2012 call. ESPA has also contributed to the design of other DFID – Research Council programmes – notably the Zoonoses programme and the design of the new Groundwater research programme – which have modelled their governance arrangements on ESPA and learnt key lessons from ESPA’s commissioning processes. / ESPA has made progress in determining the specifics of how to identify an impact pathway of for ESPA research. However, much still has to be done to make the emerging impact pathway much clearer and more integrated into researchers’ way of working.
1.5 Key challenges / A key challenge for the programme was the time it took to get the governance structure working well, and as prescribed by the original project memorandum. This increased the DFID staff time originally allocated to the programme. By the end of the year, however, this settled by increasing the number of PEB meetings from two to four/year and ensuring that there is much greater clarity over respective roles and responsibilities. Reviewing governance is now a standing item on the PEB agenda. As the programme moves forward it will be important to ensure that roles and responsibilities are maintained as originally agreed in the Terms of Reference, and that the PEBcontinues its strategic decision making function. It is very important that all those bodies involved in overseeing and managing ESPA fully understand and acknowledge which key decisions are for PEB and for the Programme Management Group (Secretariat, Directorate and funders’ management officers). This issue came to light particularly in the context of some lack of clarity with regard to how to communicate interactions with new donors in MICS. Such confusion should be avoided at all costs in future. / Running the large 2011 call presented several challenges and executive and management seriously underestimated the workload that this call would place on applicants, peer reviewers and the secretariat. Selection of final list of projects also proved very difficult with the type of peer review and panel process that was agreed upon. The Directorate ran a survey to learn lessons from this call (see http://www.espa.ac.uk/resource-centre/online-resources/espa-applications-process-review), which identified several shortcomings which included a complex specification, challenges with going to straight to full application on the Research Council’s application system, and a lack of interaction between the applicants and the ESPA Directorate and PEB to better understand key requirements, and also insufficient orientation of the peer and panel reviewers. The latter would not normally be expected but was raised mainly because ESPA is dealing with a complex and relatively new area of research. These have been hard lessons learnt but the executive and management have demonstrated an ability to reflect, learn lessons, adjust and modify the research commissioning and management processes. These lessons have not only helped make ESPA more effective, but also contributed to the design of new DFID – RC programmes (e.g. the Zoonoses programme and new water research programme). / The last year has been an extremely busy one for ESPA, and the Secretariat has delivered very effectively given the significant workload placed uponit . Over the next year, the Programme Executive Board should ensure that there is sufficient capacity and support to the Secretariat to meet the administrative demand related to ESPA placed upon it. / A key challenge, moving forward will be to ensure that the programme delivers and communicates research that is relevant to key policy asks on sustainable ecosystem management, i.e. that the research is of the type that can deliver the necessary impact. The other key challenge will be to ensure that developing country researchers are fully and equitably engaged in ESPA research. / Recommendation / 19. The MTR should review progress with governance, particularly to ensure that PEB continues to maintain oversight over key executive-level decisions.
1.6 Annual Outcome Assessment / Overall, after a few challenges associated with the ESPA 2011 call, the programme has made progress in setting up the structures that will increase the likelihood that ESPA commissions the right type of research and research processes that will help deliver on the outcome. ESPA has worked hard to establish the necessary processes, such as call assessment criteria focused on science and impact, improvements in application processes and peer review, guidance documents, project reporting requirements and systems, ethical guidance, research communications support to ensure that the programme delivers on the indicators in the outcome. / Whilst some of the ESPA 2010 projects are beginning to deliver results (notably the Framework Projects), it is still too early to expect there to be much evidence yet in various policy fora or research indices. ESPA did host two particularly successful events to showcase some of these early findings in the House of Commons in February 2012 and at Rio 2012 in June. There is every indication that ESPA research, as it is delivered, will continue to be showcased at many more such events and the Directorate will continue to work on this. The establishment of the Intergovernmental Panel on Biodiversity and Ecosystem Services should also constitute a key audience for ESPA research over the course of the next few years as will other initiatives such as the World Bank WAVES and UNEP/UNDP Poverty and Environment Initiative. It is envisaged that the number of ESPA project specific events will increase, in addition to those hosted and organised by the Directorate. / The next year will be a crucial one for ESPA as the 2011 consortia projects become fully operational and the next set of ESPA 2012 projects are commissioned. These two groups of projects constitute approximately two thirds of ESPA’s research budget and will underpin whether or not the programme will fully deliver on its outcomes. / A key priority for next year will be to ensure that ESPA is able to monitor and track all the on-going and new projects, events and activities. This will enable better reporting at annual review and to ensure that there is a very clear understanding (via the milestones) as to what the annual expectation is for programme deliverables.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts / Yes. The project is performing broadly against envisaged financial targets, with reasonable forecasting. There is however an expected drop in budget requirement for the next financial year, the detail of which will be advised by the Secretariat in the coming month. This is largely due to the 3-month delay start-up of the three consortia projects and that the budgetary commitment to projects was lower than originally planned for the 2011 call. / 2.2 Key cost drivers / In an attempt to analyse the cost drivers during this Annual Review, some distinct challenges in sourcing cost information from Research Councils were revealed, which did not arise in last year’s Annual Review as the template did not require an in-depth costing analysis. / It transpires that, NERC’s financial information is collated centrally by the Shared Service Centre (SSC), as with all other Research Councils. The SSC requires three months’ notice to extract detailed financial information. DFID had not been informed of this and was therefore unaware of this time requirement. As a result, it was not possible to give enough notice to the Research Councils in time for their systems to deliver the right financial information for this Review. In addition, it appears now that the way that Research Councils analyse direct and indirect costs is quite different to how DFID analyse these costs and the necessary restructuring of financial information would be a very lengthy task for the Secretariat. / Given the importance of analysing cost drivers for DFID, resolving financial reporting for ESPA will need full resolution over the next six months. Clearly, this is a Research Council wide issue that NERC and ESPA cannot resolve in isolation. There are some useful precedents that already exist, e.g. the DFID/ESRC International Development Scheme, which ESPA could learn from and adapt. / 2.3 Is the project on-track against original timescale: / The profile envisaged early on in the programme was to have spent £17,000,000 by 31st March 2012. The actual current spend is £7,039,936[1] as at the same date. This indicates that the programme as a whole is financially off track. / This overall slippage was mainly due to an over-ambitious profiling of spend, and an underestimation of the amount of time it would take to fully operationalize the governance and management of the programme, and set up appropriate commissioning arrangements for large international calls through the JES system and the Shared Service Centre, which include certain rules about timing. / With governance and management arrangements now in place and three major research calls underway, most spend has therefore occurred in the last year: a spend of £3.1M versus a revised budget of £4.1m. This demonstrates a marked improvement in financial performance in the last reporting year and there is currently every indication that this trend will continue. / Recommendation: Costs and timescale / 20. To identify and agree, at PEB level, how ESPA will report financial information to DFID, including on how to separate out direct and indirect costs, and ensuring that any decisions are made within any wider decisions made about how Research Councils should prepare financial reports and forecasts to DFID. This issue needs urgent resolution, and ideally within three months of this review. / 21. Finances should become a standing item on the PEB agenda.
[1] Both these figures include a spend / budget of £2,999,710.06 for the original scoping study as has been reflected on the ARIES financial system

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There are no changes in evidence identified at this stage. The Rio 2012 final decision did emphasize the importance of more work on valuing nature. International agreement to establish the Intergovernmental Panel on Ecosystem Services and Biodiversity, which will be a key client for ESPA research, also provides further justification for the need for ESPA research. / 3.2 Where an evaluation is planned what progress has been made? / There are two mid-term reviews planned, and both are in the earliest stages of preparation. The ESPA Directorate is planning to run a mid-term review, and DFID is required to hold a formal mid-term review also next year. There is already broad agreement that these two reviews should be merged if possible. The recommendation from DFID is also that the MTR should be an independent review. / Recommendation – Evidence and Evaluation / 22. DFID should communicate the decision to hold an independent MTR to ESPA PMG and PEB by September. PEB and PMG should look into how the two reviews could be merged and there needs to be firm agreement plans by the end of the year on process for commissioning the mid-term review.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / Medium / 4.2 Assessment of the risk level / As the project enters into a new phase of developing new funding partners, there is the heightened risk that some parts of the programme may become subject to discussion. We would however consider that this risk is at the lower end of medium pending a formal strategy for partnering and co-funding being agreed. The co-funding strategy is due to be revised and discussed for agreement at the October PEB.
Risk of funds not being used as intended / Low –the current research call process indicates that the research outcome is very likely to ensure that funds are used as originally intended. / Climate and Environment Risk / Low – however, the programme should consider how it is monitoring the trajectory of its environmental and carbon footprint, especially with the increase in international travel as the programme moves further into the research phase.

5. Value for Money
5.1 Performance on VFM measures / It has not been possible to comment on Value for Money overall, as it has proved difficult to obtain timely information on expenditure costs from the ESPA Secretariat. This is largely related to a wider system capability issue and that the ESPA Secretariat needs considerable advance notice (3 months) to deliver this information. This is because NERC must access the systems in the Shared Service Centre to obtain this information, as mentioned in Section 2.0, and RCs do not desegregate cost information in the same way as DFID. All these issues must be resolved in the course of the next year. / 5.2 Commercial Improvement and Value for Money / It has proved difficult to provide robust analysis this year given the challenges of obtaining financial information mentioned above and in Section 2.0. There are clear recommendations that aim to resolve this issue urgently. Once resolved an interim analysis should be presented to the PEB for discussion. / It is important to note that the all services provided to ESPA by the Shared Service Centre are not charged to the ESPA programme budget, but this is a service covered and provided for by the Research Councils. In addition all UK applicants only charge 80% of the full economic cost to the ESPA budget, the remainder of the cost (20%) is supposed to come from the UK’s core support to UK research institutions. This means that, in the UK, any projects funded through the Research Councils leverage in an additional 20%. / ESPA is also seeking out partnerships with other donors and some have expressed interest. This is still at earliest stage but if an acceptable approach can be agreed, ESPA may be able to leverage in resources from other donors. / 5.3 Role of project partners / No changes have been made to these roles during this financial year. / 5.4 Does the project still represent Value for Money / Although specific financial information did not become available in time for this review, there seems to be reassurance from the structure of research partnership that there is added value from working in partnership with the Research Councils. Their role in managing and administering research commissioning, contracting and payments to contractors that / However, action should be taken to address fundamentally address the issue of timely information and the ability to deliver such (or related) information in the future. / 5.5 If not, what action will you take? / A key recommendation, in order to be consistent with the Whitehall value for money and transparency initiative, would be to seek to get ESPA to discuss, minute, and report on their (website) each partner costs, on a quarterly basis, in a way that clearly specifies direct and indirect costs for each programme. / Future disbursements to ESPA should be made conditional on the Secretariat meeting requirements of using widely accepted standards for use of public funds. / A short audit of the NERC’s accounting system to ascertain the system’s ability to provide the data required by DFID could assist in building an understanding of how the Research Council systems could better address the expected scrutiny on the use of DFID funds. / Recommendation: Value for Money / 23. The issue of reporting on costs needs to discussed urgently within the RC – RED forum and must be informed by on-going discussions by FCPD, RED Directors and the Research Councils. ESPA should look also to how other programmes such as the DFID – ESRC scheme have dealt with this. Full resolution of reporting on costs is required by the end of the year so that DFID is then able to make an accurate assessment of value for money. / 24. Depending on the various RC – RED discussions, an independent review of RC systems to investigate further how the RC’s could better respond to such donor requests in the future should be undertaken.

6. Conditionality
6.1 Update on specific conditions / No conditionality was set in the previous annual review.

7. Conclusions and actions
Recommendations Output 1: / Whilst there are clear indications from the research commissioned, ability to learn from commissioning process, and research outputs to date, that output 1 is heading in the right direction, considerable effort must be sustained to ensure that this output is fully achieved given the challenges experienced to date in commissioning ESPA research. / The commissioning process for the large grants was time consuming and cumbersome, especially for developing country applicants. The project has now put in place mechanisms to address these issues in subsequent calls but will need to ensure that it continues to learn lessons from its experience of commissioning the right type of ESPA research. / The Directorate will need to re-evaluate knowledge gaps following the outcome of the next call and make proposals to the Board to address those before issuing the next calls. / The Directorate should continue its work to develop an effective and accessible research outputs reporting system as a key priority. / This output’s indicators may still need some minor adjustment and milestones need to be formulated and agreed within six weeks of this Annual Review. / Recommendations Output 2: / ESPA researchers have demonstrated that they are beginning to deliver new methods, tools and frameworks in the area of ecosystem services and poverty alleviation. However, ESPA will need to work further on ensuring these meet user needs, and that ESPA is prioritising working to build this capability among southern researchers. / ESPA needs to evaluate success of the 3-stage project proposal process to see if it delivers better on ESPA’s objectives. / ESPA Directorate needs to regularly review the various methods, tools, frameworks and syntheses being delivered by ESPA researchers to ensure that they continue to be relevant to user needs. / ESPA Directorate and Secretariat should develop and submit options to the PEB on how the programme could further build multi/interdisciplinary capability in the South, for instance by hosting events in the South. / The Directorate should keep track of the range of different approaches to multi/interdisciplinarity being adopted by ESPA researchers and share these within the ESPA community to encourage further discussion and learning. / A methodology will need to be agreed on how to measure and define the level of ambition with regard to the quality of ESPA’s research outputs. / This output’s indicators may still need some minor adjustment and milestones need to be formulated and agreed within six weeks of this Annual Review. / Recommendations Output 3: / Further revision of the output and indicators are needed to ensure that this adequately captures research uptake in a way that delivers benefits for the poor in developing countries and as originally intended in the DFID business case. This should also include defining milestones – to be completed within six weeks of this review. / The Directorate must ensure that it captures all relevant information on how projects are ensuring the research is being used, and generating greater demand for ESPA research The Directorate will report to September PEB on how the programme will capture this information. / ESPA should be encouraged to continue its engagements with other programmes that are potential ‘ready’ users of ESPA research (e.g. WAVES, PEI, IPBES) however the Directorate should manage their time inputs to these initiatives very carefully. / Recommendations Output 4: / Further adjustment of the output and indicators are needed to provide further clarity and ensure that it meets originally intended in the DFID business case. This should also include defining milestones – to be completed within six weeks of this review. / Aligned with the activities to engage southern partners, the Directorate should track and monitor progress, and capture lessons learnt, from ESPA’s work to engage developing countries and developing country researchers in ESPA. ESPA might also benefit from a better way of communicating and reporting on developing country engagement in ESPA. / ESPA (NERC and RED) should play a key role in planned RED – RCUK discussions on southern engagement, and should push for an early meeting on this. / By November 2012, obtain data for Indicator 4.2 either through RCUK Research Outcomes System or other credible and available method. / Recommendations: Logframe / ESPA must set out the milestones for all outputs and make the further adjustments to the output 3 and 4 and output indicators as identified by this review. This must be completed within 6 weeks of this review and be finally signed off by the September PEB. / Recommendation: Key challenges / The MTR should review progress with governance, particularly to ensure that PEB continues to maintain oversight over key executive-level decisions. / Recommendation: Costs and timescale / To identify and agree, at PEB level, how ESPA will report financial information to DFID, including on how to separate out direct and indirect costs, and ensuring that any decisions are made within any wider decisions made about how Research Councils should prepare financial reports and forecasts to DFID. This issue needs urgent resolution, and ideally within three months of this review. / Finances should become a standing item on the PEB agenda. / Recommendation: Evidence and Evaluation / DFID should communicate the decision to hold an independent MTR to ESPA PMG and PEB by September. PEB and PMG should look into how the two reviews could be merged and there needs to be firm agreement plans by the end of the year on process for commissioning the mid-term review.
Recommendation: Value for Money / 23. The issue of reporting on costs needs to discussed urgently within the RC – RED forum and must be informed by on-going discussions by FCPD, RED Directors and the Research Councils. ESPA should look also to how other programmes such as the DFID – ESRC scheme have dealt with this. Full resolution of reporting on costs is required by the end of the year so that DFID is then able to make an accurate assessment of value for money. / 24. Depending on the various RC – RED discussions, an independent review of RC systems to investigate further how the RC’s could better respond to such donor requests in the future should be undertaken.

8. Review Process
The Programme Executive Board meets regularly (quarterly) to review ESPA business over the preceding quarter and to approve plans for the next quarter. The PEB also approves the Directorate’s annual report which in future will be timed to feed straight into DFID’s annual review. / The next DFID review will be undertaken in one year’s time and will be a MTR. The preference at this stage is for the MTR to be an independent review with careful consideration put into nature and type of review method. Team members could include DFID staff who have not previously been involved in the ESPA programme, and it may be helpful to involve staff and/or member working with other related initiatives, such as WAVES or IPBES.

## Annex 1

ESPA Scientific Publications 2011-12
## Strengthening Research Capacity Projects
NE/G008078/1	CAMARV: Capacity Building for Mangrove Assessment, Restoration and Valuation in East Africa	Strengthening Research Capacity

K.B. Kirui, J.G. Kairo, J. Bosire, K.M. Viergever, S. Rudra, M. Huxham, (In press) R.A. Briers Mapping of mangrove forest land cover change along the Kenya coastline using Landsat imagery Ocean and Coastal Management (online 16th December)
NE/G008213/1	The impacts of ecosystem services and environmental governance on human well-being in the Pongola region, South Africa	Strengthening Research Capacity

Lankford, C. Pringle, Dickens C, Lewis, F, Mander, M, Chhotray, V, Goulden, M, Nxele Z and. Quayle, L (2011) Hydrological modelling of water allocation, ecosystem services and poverty alleviation in the Pongola Floodplain, South Africa Journal of Environmental Planning and Management Volume 54, Issue 9, 1237-1260
NE/G008264/1	BESSA: Building Ecosystem Services Research Capacity in Semi-Arid Africa	Strengthening Research Capacity

Balana, B.B.; Yatich, T; Makela, M. (2011) A conjoint analysis of landholder preferences for reward-based land-management contracts in Kapingazi watershed, Eastern Mount Kenya Journal of Environmental Management 92, 2634-2646
NE/G008337/1	Building Capacity for Sustainable Governance in South Asian Fisheries: Poverty, Wellbeing and Deliberative Policy Networks	Strengthening Research Capacity

Coulthard, S. (2011) More than just access to fish: The pros and cons of fisher participation in a customary marine tenure (Padu) system under pressure Marine Policy 35 (3): 405-412
Coulthard, S. Johnson, D. and J.A. McGregor (2011) Poverty, sustainability and human wellbeing: A social wellbeing approach to the global fisheries crisis. Global Environmental Change 21 (2), 453-463
Bavinck, J.M and V. Vivekanandan (2011) Conservation, Conflict and the Governance of Fisher Wellbeing: Analysis of the Establishment of the Gulf of Mannar National Park and Biosphere Reserve Environmental Management 47 (4) 593-602
Coulthard S (2012) Can we be both resilient and well, and what choices do people have - incorporating agency into the resilience debate from a fisheries perspective Ecology and Society 17 (1): 4
NE/G008531/1	Valuing rainforests as Global Eco-Utilities: a novel mechanism to pay communities for ecosystem services provided by the Amazon	Strengthening Research Capacity

A. Marengo, S. C. Chou, G. Kay, L. M. Alves, J. F. Pesquero, W. R. Soares, D. C. Santos, A. A. Lyra, G. Sueiro, R. Betts, D. J. Chagas, J. L. Gomes, J. F. Bustamante, P. Tavares. (In press) Development of regional future climate change scenarios in South America using the Eta CPTEC/HadCM3 climate change projections: Climatology and regional analyses for the Amazon, São Francisco and the Paraná River Basins Climate Dynamics
Rival L (2012) Sustainable Development through Policy Integration in Latin America: Comparative Approach Development 55, 1-8
OmettoJP, Aguiar APD, Martinelli LA. (2011) Amazon deforestation in Brazil: effects, drivers and challenges Carbon Management 2, 575-585
Farley, J., A. Schmitt Filho, J. Alvez and N. Ribeiro de Freitas, Jr. (2012) How Valuing Nature Can Transform Agriculture Solutions 2, 64-73
Chapter in book: Governing the provision of environmental services Schmitt Filho, A., J. Farley, G. Alarcon, J. Alvez and P. Rebollar (In press) Springer Verlag Chapter 5: Integrating Agroecology and PES in Santa Catarina’s Atlantic Forest
NE/G008582/1	Strengthening research capacity of China and South Africa (SA) in sustainable water resources management with UK and Australian experiences	Strengthening Research Capacity

Wei, Y.P., Ison, R.L., Colvin, J.D. & Collins, K. (2012) Reframing water governance in China: a multi-perspective study of an over-engineered catchment. Journal of Environmental Planning & Management 55 (3), 297-318
Ison, R.L., Collins, K.B, Colvin, J.C, Jiggins, J. Roggero, P.P., Seddaiu, G., Steyaert, P., Toderi, M. and Zanolla, C. (2011) Sustainable catchment managing in a climate changing world: new integrative modalities for connecting policy makers, scientists and other stakeholders Water Resources Management 25, 3977-3992
Ison, R.L. Cybersystemic conviviality: addressing the conundrum of ecosystems services (2011). ASC (American Society for Cybernetics) Column, Cybernetics & Human Knowing 18, 135-141

## Partnership and Programme Development Grants
NE/I003010/1	Water governance, livelihoods and wellbeing: adapting to change in African river basins	Partnership and Project Development

Franks T, Bdliya H, Mbuya L (2011) Water governance and river basin management: Comparative experiences from Nigeria and Tanzania. International Journal of River Basin ManagementVol 9 (2) 93-10
NE/I003134/1	Amazonia-Yungas Observatory on Biodiversity and Indigenous Health and Well-being: Development of a South-South-North Research and Partner Consortium	Partnership and Project Development

Stephens C (In press) Biodiversity and Human Health – Hubris, Humility and the Unknown Environmental Research Letters
Chapter in book: Public Health Ethics: Key Concepts and Issues in Policy And Practice, Kessel A, Stephens C (2011) Cambridge University Press, Chapter 5: The environment, ethics and public health: the dilemmas of global warming
NE/I003320/1	Managing land for carbon in southern Africa: relationships between carbon, livelihoods and ecosystem services	Partnership and Project Development

Stringer LC, DougillAJ, Thomas AD, Spracklen DV, Chesterman S, IfejikaSperanza C, Rueff H, Riddell M, Williams M, Beedy T, Abson D, Klintenberg, P, Syampungani S, Powell P, Palmer AR, Seely MK, Mkwambisi DD, Falcao, M, Sitoe, A, Ross S, Kopolo G (In press) Challenges and opportunities in linking carbon sequestration, livelihoods and ecosystem service provision in drylandsEnvironmental Science and Policy
NE/I003347/1	Ecosystem services to alleviate iodine, selenium and zinc malnutrition in sub-Saharan Africa	Partnership and Project Development

Chilimba ADC, Young SD, Black CR, Rogerson KB, Ander EL, Watts M, Lammel J, Broadley MR (2011) Maize grain and soil surveys reveal suboptimal dietary selenium intake is widespread in Malawi Scientific Reports 1, 72

## Programme Framework Grants
NE/I003266/1	East African Great Lake Observatory	Programme Framework Grant

David M. Harper, Edward H.J. Morrison, Michael M. Macharia, Kenneth M. Mavuti and Caroline Upton (2011) Lake Naivasha, Kenya: ecology, society and future Freshwater Reviews 4, 89-114
E. H. J. Morrison, C. Upton, K. Odhiambo-K’oyooh& D. M. Harper (In press) Managing the natural capital of papyrus within riparian zones of Lake Victoria, Kenya Hydrobiologia
Cózar A., M. Bruno, N. Bergamino, B. Úbeda, L. Bracchini, A. M. Dattilo, S. A. Loiselle (2012) Basin-scale Control on the Phytoplankton Biomass in Lake Victoria, Africa PLoS ONE 7(1) e29962
R. Osaliya, F. Kansiime, H. Oryem-Origa and E. Kateyo (2011) The potential use of storm water and effluent from a constructed wetland for re-vegetating a degraded pyrite trail in Queen Elizabeth National Park, Uganda Journal of Physics and Chemistry of the Earth 36, 842-852
NE/I00324X/1	Participatory Modelling Frameworks to Understand Wellbeing Trade-offs in Coastal Ecosystem Services.	Programme Framework Grant

Tim Daw, Katrina Brown, Sergio Rosendo, Robert Pomeroy (2011) Applying the Ecosystem Services Concept to Poverty Alleviation: The Need to Disaggregate Human Well-Being Environmental Conservation 04, 370-379
NE/I004017/1	Towards a virtual observatory for ecosystem services and poverty alleviation	Programme Framework Grant

Buytaert, W., Baez, S., Bustamante, M., Dewulf (2012) A. Web-based environmental simulation: bridging the gap between scientific modelling and decision-making Environmental Science and Technology 46, 1971–1976
Beven, K., Buytaert, W., Smith, L. (In press) On virtual observatories and modelled realities (or why discharge must be treated as a virtual variable) Hydrological Processes

NE/I004149/1	Human Adaptation to Biodiversity Change: Building and Testing Concepts, Methods, and Tools for Understanding and Supporting Autonomous Adaptation	Programme Framework Grant

Bhagwat, S.A., Breman, E., Thekaekara, T, Thornton, T.F, & Willis, K.J. (In press) A battle lost? Report on two centuries of invasion and management of Lantana camara L. in Australia.

Annex 2 Summary of Knowledge Gap Analysis

## Background
This paper is a gaps analysis which reviews the extent to which the currently short-listed consortium projects meet the intentions for the ESPA consortia call announced in September 2010. The purpose of the gaps analysis is to contribute to the design of a new call which would ideally focus on perceived gaps.

The Directorate was not established when the AO6 call was developed, and made some inputs in an advisory capacity only after the call was published. So, this assessment of what the PEB intended for the call is based only on the information in the call documentation.

The selection of successful consortium projects for funding is still pending. The four teams in the short-list are currently revising their projects. In some cases it appears that the revisions are quite substantial, even fundamental. So, the assessment of what the project may ultimately address, if funded, is based on the initial proposals. Where there are indications that substantial changes may affect the gaps analysis, some flexibility is noted below.

The gaps analysis is therefore necessarily rather tentative at this stage.

## Objectives of the AO6 call
The Consortia call for substantial ESPA projects (AO6) closed in January 2011, and final decisions on awards are pending. This was intended to be the major call for large and synthetic projects that would address the major research and impact objectives that are agreed for ESPA by the funders (see Box 1).

Box1. ESPA Goal, Purpose and Outputs
The goal is ‘sustainably managed ecosystems contributing to poverty reduction and inclusive growth in developing countries’.
The purpose is ‘To positively influence end users and decision makers through the generation of cutting edge evidence on ecosystem services, their full value, and links to sustainable poverty reduction’.
The outputs are:
1. A strong research and evidence base on the interface between ecosystem services, their dynamics and management, human use and pathways to sustainable poverty reduction;
2. Innovative, interdisciplinary research and methodologies, delivering tools and approaches that enable the simulation and prediction of socio-ecological responses to multiple drivers;
3. High uptake of research outputs and synthesis by early and on-going engagement and communication with policy makers, practitioners and decision makers;
4. Enhanced capacity of southern researchers to conduct, lead and use/communicate high quality ESPA-type interdisciplinary research, including through effective north-south and south-south research partnerships.

The call also specified a number of other priorities for the programme, so that projects should be conducted in the context of the 6 thematic areas:
- Water: Impacts of climate variability and other changes on ecosystem services that underpin the water cycle and water security
- Forests: Forests, land use change and ecosystem services
- Coasts: Strengthening the management of coastal ecosystems to support sustained ecosystem service delivery for reduced poverty and vulnerability in coastal zones
- Health: Ecosystem services, disease ecology and human well-being
- Biodiversity: Biodiversity and ecosystem services - ensuring a sustainable flow of goods and services to enhance human well-being
- Political Economy: The political economy needed for sustainable management ecosystem services for poverty alleviation and sustainable growth

and in the following geographic regions:
South Asia;
Sub-Saharan Africa;
Amazonia
China;
as well as marine/coastal systems.

In addition, the call listed a number of generic principles and criteria for successful projects that stressed true inter-disciplinarity, connected social-ecological systems, systems analyses, and a focus on the complete pathway from fundamental environmental science to the impacts on people, especially the poor.
## The short-listed projects
These can be summarised as follows:
1. Emerging disease risks, in 4 sub-Saharan African countries. (Currently being developed to extend the range of ecosystem services and the fundamental environmental science)
2. Ecosystem services contrasted between agricultural and non-agricultural ecosystems (mostly forest) in 1 sub Saharan and 1 South American country site. (Currently being revised to reflect a the continuum of landscapes and a wider range of ecosystem services, perhaps also extending study sites).
3. Water-based ecosystem services under climate change in 3 African river basins. (Currently being revised to clarify the ecosystem services, the environmental change scenarios, and the links to poor people).
4. Basin modelling for a delta environment in South Asia, examining future scenarios for water management. (Currently being developed to clarify links to the poor, to other projects and the ecosystem service inter-linkages).
## Mapping projects to AO6 objectives
Across the 6 thematic areas, the short list contains one project on health, two on water (related to climate variability), and on food production (with some links to forest-non forest comparisons). In fact, it is not clear at the moment that the health project will cover the ecosystem services and ‘health ecology’ that was intended; this would require quite an intensive and coordinated set of linked ecosystem service studies at each site, which is so far not part of the project. In practice, the only thematic area that might be considered to be at all adequately addressed is water. Forests, biodiversity, the political economy and coasts are not addressed.

The geographic regions included in the short list includes one in South Asia, two in Africa and one that is co-located in South America and Africa. There is no project focus in China at the moment and only partial representation in Amazonia.

The principles and criteria identified for AO6 include many desirable features and characteristics for successful projects. There is some evidence in the short-list for inter-disciplinarity and for clear engagement with policy and decision-makers, but it is not clear that any project addresses connected social-ecological systems, systems analyses, or includes the complete pathway from fundamental environmental science to the impacts on people.
## Are the AO6 call criteria too demanding, should they be taken literally in the gaps analysis?
Given the weak coverage exhibited in the short list, it is appropriate to consider what kind of coverage is necessary, and what might be realistic. It was always likely to be challenging to achieve good coverage of thematic areas, regions and other criteria in a small number of successful projects. But the narrow focus of many on the shortlist means that there are more gaps than cover.

Ecosystem service science is of course evolving, and recent reviews and widely well-regarded assessments stress the significance of two emerging themes.

1. First, that as human populations grow, as the pressures for development intensify, and as poverty elimination is achieved, pressures on the environment must increase. This will be especially marked in those areas of the world that are growing and developing rapidly, and that are economically poor. Therefore, current approaches to ecosystem service delivery that focus on one service at a time (e.g. agricultural versus intact landscapes; flood plains for flood regulation alone) will not be sufficient. Increasingly, ecosystems will need to be managed with multiple services in mind, including provisioning, regulating and cultural services. This is very different to a business-as-usual scenario, and to land-use decision-making processes which tend to be largely independent for different service types (food, water, biodiversity conservation, energy extraction). Integrated assessments addressing multiple use landscapes are expected to necessary for the desired outcomes, recognising that the same solutions are not going to work in different context, and that biophysical constraints, and socio-political processes, are also critical components.
2. Emerging analyses of linked social-ecological systems, incorporating resilience thinking and integrated assessments, suggest key features for successful governance and decision making. It is becoming clear that some simple design principles are necessary for groups to overcome problems to do with either tragedy of the commons, or top-down management that benefits only a few. Community groups need to be able to organize and govern their own actions, develop rules well matched to local needs and conditions, have wide participation of the relevant community, external respect, and effective monitoring. For the many environmental resources that are used outside the local community, there need to be mechanisms for appropriation, provision, monitoring, enforcement, conflict resolution, and governance activities organized in multiple layers at nested but relevant scales.

These emerging themes have great significance for ESPA, in that projects should be addressing the integrated set of services, their biophysical basis, as well as the governance and decision-making processes in the political economy. This is almost completely lacking from the current suite of shortlisted projects.
## Conclusions on gaps
1. There are many gaps, especially in thematic coverage. The current set of projects largely misses forests, biodiversity and coasts, and is generally weak on the political economy. The geographic areas miss China completely, and have very limited coverage in Amazonia and in marine and coastal areas. The other generic principles and criteria are hard to assess objectively, but seem to be poorly represented in the short-list.
2. Recent work in ecosystem service science, especially in relation to resilience and sustainability, reinforce the significance of integrated ecosystem service assessments, and for linked socio-political and environmental studies.
3. A call that is geared to filling all the gaps identified from a forensic analysis of AO6 requirements is going to require a set of very specific criteria. This is unlikely to be useful and may in fact generate proposals less likely to deliver the kind of novel, integrated and interdisciplinary science that ESPA now requires.
4. Therefore the better strategy may be to focus less on regional and thematic coverage, but instead concentrate more on generating proposals for soundly-based, integrated, scientific studies of significant systems (landscapes, water basins, coastal zones etc.) in areas that are especially relevant to the well-being of large numbers of the poor.

Annex 3 List of Programme Framework Projects

			Water	Health	Forests	Biodiversity	Coasts	Political Economy	SSA	Burundi	Congo	Ethiopia	Ghana	Kenya	Malawi	Mozambique	Rwanda	Tanzania	Uganda	Zambia	South Africa	Amazonia	Bolivia	Brazil	Ecuador	Peru		South Asia	Bangladesh	India	China
NE/I002448/1	Whole decision network analysis for coastal ecosystems (WD-NACE)	Professor D Raffaelli					x	x	x					x														x	x
NE/I002952/1	The ESPA Framework: A socio-ecological systems analysis of the political economy of Ecosystem Services for Poverty Alleviation.	Dr G Patenaude			x			x	x													x						x
NE/I002960/1	Poverty and ecology: developing a new evolutionary approach	Professor JA Dearing	x																												x
NE/I00307X/1	Integrated Carbon, Water and Land Management for Poverty Alleviation	Professor P Vidale	x		x				x				x									x		x
NE/I003185/1	The REDD Game: A didactic tool for designing effective, efficient and equitable policies to deliver REDD in Bolivia	Dr C Palmer			x	x																x	x
NE/I00324X/1	Participatory Modelling Frameworks to Understand Wellbeing Trade-offs in Coastal Ecosystem Services.	Dr T Daw	x				x		x					x
NE/I003266/1	East African Great Lake Observatory	Professor Eric Odada	x	x		x			x	x	x	x		x	x	x	x	x	x	x
NE/I003282/1	Just ecosystem management: Linking ecosystem services with poverty alleviation	Dr T Sikor						x	x																			x		x	x
NE/I003401/1	Swahili Seas	Dr M Huxham			x		x		x					x
NE/I00341X/1	Safeguarding local equity as global values of ecosystem services rise	Dr K Schreckenberg	x		x			x	x										x			x						x
NE/I003673/1	Biodiversity, Ecosystem services, Social sustainability and Tipping points in African drylands	Professor KM Homewood				x		x	x			x		x				x
NE/I003819/1	BKS - Bridging knowledge systems for pro-poor management of ecosystem services	Dr S Vermeylen						x	x											x
NE/I003924/1	Negotiating Tradeoffs: Making Informed Choices about Ecosystem Services for Poverty Alleviation	Dr B Vira	x		x	x		x																				x		x
NE/I004017/1	Towards a virtual observatory for ecosystem services and poverty alleviation	Dr W Buytaert	x		x																	x			x	x
NE/I004149/1	Human Adaptation to Biodiversity Change: Building and Testing Concepts, Methods, and Tools for Understanding and Supporting Autonomous Adaptation	Professor P Howard				x		x	x												x							x		x
NE/I004335/1	Landscape Diversity and Ecosystem Services in Agricultural Ecosystems: Implications for Sustainable Growth and Rural Poverty in China	Dr M Rosegrant		x				x																							x
NE/I00436X/1	What types of investment can most cost-effectively ensure ecosystem service provision? A randomized program evaluation	Dr N Asquith	x		x																	x	x
NE/I004661/1	Integrating Forest Ecosystem Service Assessment with Pro-Poor Governance in India	Dr O Springate-Baginski			x			x																				x		x
		Totals							11	1	1	2	1	5	1	1	1	2	2	2	1	6	2	1	1	1		7	1	4	3