Type of Review: Project Completion Review

Project Title: Support to the Interim Presidential Election

Date started: 09/01/2012	Date review undertaken: 25/09/2012

## Introduction and Context
What support did the UK provide?
DFID contributed £1,605,000 to the United Nations Development Programme (UNDP), in support of the Yemeni Supreme Commission for Elections and Referenda (SCER)’s delivery of the interim presidential election on 21st February 2012. / DFID’s funding was via a multi-donor elections basket fund managed by UNDP. £4.7 million total donor funding was committed to the basket fund, covering the delivery of the elections in terms of logistical support, equipment and training. The SCER, UNDP, and USAID made a further contribution to the delivery of elections outside the framework of the basket fund, mainly to support salaries and security costs. / DFID’s support, as part of a multi-donor effort, meant that the SCER was able to deliver the interim presidential elections on the 21st of February, 2012 in accordance with transition timetable.

What were the expected results?
The outcome of this intervention was to enable SCER to deliver the interim presidential election. This would have a positive impact, contributing to a more stable and secure Yemen. / The planned overall project results were: / Effective UNDP support for SCER: / 3,372 polling stations provided with adequate equipment. / 60,000 polling staff trained in the rules, procedures, and special arrangements for the conduct of the interim presidential election. / Citizens, in particular women and youth, understand the interim presidential election: / An adequate Communications Strategy is prepared that is appropriate, achievable and targets women and youth. / 180 minutes of original election outreach content broadcast over radio. / These targets were decided in consideration of the potential challenges posed by the security situation, alongside the short timeframe which could potentially affect UNDP’s or SCER’s delivery mechanism.

What was the context in which UK support was provided?
Yemen has the highest poverty levels in the Middle East, and faces a range of deep-seated development challenges including a poorly managed and weak economy characterised by: a dependency on declining oil reserves; endemic corruption; and lack of jobs. In addition, Yemen faces food and water insecurity, high population growth, and almost non-existent social service provision. It is unlikely to meet any of the Millennium Development Goals (MDGs). On-going conflict in the north and the south of the country has displaced thousands of civilians and put some areas of the country beyond effective state control. Poverty, inequality and patronage continue to threaten and undermine social cohesion. Many of these problems are rooted in the government’s lack of accountability to Yemeni citizens. These development challenges were compounded by political crisis and an upsurge in conflict sparked by widespread demonstrations against the rule of former President Ali Abdullah Saleh in 2011. This resulted in a further deterioration of the economy and a humanitarian crisis, which is marked by high levels of malnutrition, high mortality, outbreaks of infectious diseases and widespread food insecurity. / A deal brokered by the Gulf Cooperation Council (GCC) in November 2011 enabled a process of political transition to begin. The transition, though fragile and far from assured, is the best chance in a generation to make progress towards a more secure and prosperous future for Yemen. If the transition is successful, the development challenge will remain enormous. If it fails, Yemen could be facing any or all of state failure, large scale conflict and a humanitarian catastrophe. / The Support to the Interim Presidential Election project was regarded as an opportunity to help maximise the chances of a successful start to the transition process. The interim presidential election was the first test of the transition. A well-managed, “good enough” election would bolster citizens’ confidence in the wider transition process and increase the chances of its success. Conversely, failure to achieve this could lead to failure of the transition process and a path towards cycles of greater violence, fragmentation and instability, and continued or accelerated economic decline. This would in turn impact on the livelihoods of the most vulnerable, and frustrate the achievement of further UK policy objectives in Yemen, such as countering radicalisation and terrorism. / The requirement of the GCC agreement to hold a presidential election within 90 days of its signing was a significant challenge, with high risks should the election not take place to the minimum standard expected; and the deepening economic crisis and deteriorating state of government finances meant that it was unlikely that the government’s Supreme Commission for Elections and Referenda (SCER) would have been able to fund the entire needs for elections. There was a high risk that elections could fail purely for want of better logistical support which international assistance could easily provide. There was therefore a clear strategic case for DFID to provide support to the interim elections.

## Section A: Detailed Output Scoring

Output 1: Under the Electoral Institutions and Processes and Effective UNDP support for SCER
Output 1: final score and performance description: / A++ (Outputs substantially exceeded expectation) / Under the Electoral Institutions and Processes and Effective UNDP support for SCER strand, the programme aimed at two output indicators: / Number of polling stations provided with adequate equipment and, / Number of polling staff trained in the rules, procedures, and special arrangements for the conduct of the interim president elections. / Expected Result: / 3372 polling stations provided with adequate equipment. / 60000 polling staff trained in the rules, procedures, and special arrangements for the conduct of the interim presidential election.
Final results: / 6514 polling stations provided with adequate equipment. / 100000 polling staff trained in the rules, procedures, and special arrangements for the conduct of the interim presidential election. / UNDP equipped 5620 polling centres in addition to special polling stations, which were extended by SCER from 732 to 894, with a polling kit including tamper-evidence seals, ballot boxes, and polling booth equipment.[1] UNDP also provided SCER with 385 laptops and USB modem flash disks which were used across 65 districts.[2] UNDP note in their report that all materials were procured, and distributed on time. / The expected results represented what was considered by DFID to be a realistic proportion of polling centres and staff to be reached out of the total number possible, given the likelihood that security and logistical challenges would be encountered. In the event, UNDP report that it proved possible to reach the total number of polling centres and staff involved in the elections, hence the outputs substantially exceeding expectations. Although it was possible to exceed the number of polling staff trained in preparation for the election, it is to be noted that despite the training and the instructions by the SCER, some polling committees did not abide by all guidelines and failed to provide certain data such as the registered versus unregistered numbers of voters. UNDP plans to include significant further training to address this in the future phase of elections. ii / Impact Weighting (%): 75% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No
[1] UNDP, (2012), Yemen Early Presidential Elections “Support to Elections during the Transitional Period (SETP): Project Report Phase –I”.
[2] Meeting with A. M. Al-Dhourafi, from SCER, 10th of September, 2012

Output 2: Participation: Citizens understand Interim Presidential Elections in particular women and youth.
Output 2: final score and performance description: / A+ (Outputs moderately exceeded expectation) / The Output scored an (A+), having significantly exceeded the targeted minutes of original election outreach content broadcast over radio, and met the target regarding the communications strategy. / Under the Participation and Citizens understanding of interim presidential elections in particular women and youth strand, the programme aimed at two output indicators: / The extent to which the elections communication strategy was appropriate, achievable and targets women and youth; and / Number of minutes of elections outreach content broadcast over radio.
Expected Result: / Under the assessment criteria of 0-3, (0= No plan, 1= Plan produced to low standard, 2= Plan is reasonable, 3= Plan is fully appropriate, achievable, and well-targeted to women and youth); the programme was expected to score Two, which would indicate a reasonable plan. / 180 minutes of original election outreach content broadcast over radio. / Final results: / The programme achieved a score Two, with a reasonable and adequate Communications Strategy prepared. / 2928 minutes of original election outreach content were broadcast over radio. / The activities under the communication strategy were implemented by the UNDP administered Joint Electoral Assistance Programme (JEAP), International Foundation for Electoral Systems (IFES), and UNDP’s Support to Elections during the Transitional Period (SETP). The campaign included standard print and electronic media, as well as modern means such as; billboard, theatre, mobile media, music, posters, face-to-face engagement, and SMS. In addition, there was a civic education campaign which paid extra attention to women.[3] Nonetheless, this was assessed a Two rather than a Three as the strategy did not consider a means of communication relevant to the significantly larger population located outside the main cities, and with minimal access to modern means of communication. / As with output one, the expected result represented what was considered by DFID to be a realistic level of election outreach content to be broadcast out of the total UNDP target, given the likelihood of some logistical constraints. In the event, UNDP report that it proved possible to undertake a greater amount of outreach broadcasting, hence the target being significantly exceeded. / Impact Weighting (%): 25% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No
[3] Lopez-Pintor, R., Cook, M., and Blanchet, D. (2012), Final Evaluation Report “Evaluation of International Assistance to the February 2012 Presidential Election, Yemen”.

## Section B: Results and Value for Money.

1. Achievement and Results
Has the logframe been changed since the last review? No / This is the programme’s first review. As the programme’s duration was less than 12 months, no annual review was conducted. / 1.2 Final Output score and description: / A+ (Outputs moderately exceeded expectation)
Direct feedback from beneficiaries / A key mechanism for overall beneficiary feedback is the actual turnout at the election. The project Business Case predicted a turnout of 1.84 million[4], based on a widely perceived lack of public interest resulting from the lack of challenge and choice in a single candidate election. There were also doubts about the perceived legitimacy of a single candidate election and potential boycott or spoiled ballot campaigns. However, in the event some 6.6 million people voted[5], reflecting Yemeni public enthusiasm for the interim presidential election and political transition as a whole. / The public endorsement of the transition indicated by the turnout is supported by the more nuanced picture painted in a post-election survey conducted by the International Foundation for Electoral Systems (IFES) in March 2012. Of the people surveyed, 60% said they had voted –similar to the number reported in official figures (65%). Turnout was higher among men (75%) than women (45%), and older people were more likely to vote than younger people (56% for 18-24 year olds and 70% for people over 65). Turnout was lower in the south and east of the country (28% and 27% respectively), than the midlands, western and northern regions (64%, 69% and 78% respectively). Of those who voted in the election, 92% felt that the result reflected the will of the Yemeni people, while 54% of those who didn’t vote felt the same.[6] / Regarding problems faced by the election, there was a clear distinction between the views of people from the south, which witnessed a boycotting campaign lobbied by the Southern Mobility Movement, and those from the rest of the country – 48% of whom reported no problems. People from the South identified incidents of violence (40%), forced closures of polling stations (30%), robbing of ballot boxes (24%), threats of violence (21%) and voting with a false identity (14%) as problems. On the particular issue of distance to polling stations, 18% of people in the south and 9% of people from the rest of the country said this was a problem. vi / To most respondents, the broader political context of the election, rather than its administration, represented the main positives of the event: 30% felt the election represented a good political solution. The peaceful conduct of the election was cited by 25% of respondents, while 24% and 22% cited free voting and transparency as positives. 21% noted the good organisation of the elections. vi / The survey further relates that most people with a disability were able to vote. Of those surveyed who had a family member with a disability, 53% said it was very easy for them to vote and 24% said it was somewhat easy. 17% said it was somewhat hard and 7% said it was very hard for their family member to vote.vi / The data above is being used by UNDP to inform elections planning for the rest of the transition period.
Overall Outcome score and description: / B (Outcome moderately did not meet expectation) / The targeted outcome on the logical framework[7] relates to the quality of the election, as assessed by DFID, with UNDP and third party input. The methodology outlined in the logical framework for scoring of the outcome considers five factors contributing to the overall quality of the election (election administration; voter registration; the election campaign; media and elections; and election day, set out in further detail below) against the following scale: (1) - Very poor, undermining; (2) - Weak, fragile, (3)- Good enough, maintaining; and (4) - Strong, building The overall targeted result was an election which was “3” or “good enough”. vii / On the basis of the below analysis of the 5 components of the election, the overall Quality of Election scored “2”, “weak and fragile” where the “quality was weak and consequently is likely to do nothing to boost citizen confidence and lead to a fragile political transition” vii. This means that the outcome moderately did not meet expectation. On reflection, this may be due to the way the target and scales were defined as opposed to genuine underachievement. The fact that the quality of the election was sufficient to allow 6.6 million people – vastly more than expected - to participate suggests that in reality the “good enough” target was achieved. DFID will consider this as it designs its next phase of support to elections in Yemen. / Scoring for each of the factors contributing to the overall target is detailed below: / Election Administration - To what extent were SCER able to discharge their responsibilities in a responsible manner? - Score 2 (Weak, fragile): / SCER had some independence but was not fully impartial and there was a lack of transparency in their work. This however, could be due to the short time frame in which SCER were due to deliver the elections. Other issues raised by the EU’s Electoral Expert Mission (EEM) were that although boxes were sealed they were not given serial numbers; there was confusion due to absence of a numerical or alphabetical voter ID list; locations of voting centres was not provided on the voting centres list; and the internet-laptop connected special polling stations were not working at the opening of the stations,[8] due to infrastructure issues.i / Voter Registration - To what extent were unregistered but eligible voters able to vote? (est. 2,000,000 total[i]) (dissag.)- Score 2 (Weak, fragile): / Although gender disaggregated information on the voter register was provided, SCER was unable to provide numbers on registered and non-registered voters. Hence they were also unable to provide gender disaggregated information on the overall number of voters ii. This was an impediment to demonstrating the effectiveness of outreach work in encouraging non-registered women to participate in the vote, however the overall higher than expected turnout does point to this being the case for women as well as men. To avoid this in the future, DFID should make clear their expectation with SCER and UNDP that non-registered as well as registered voters are monitored. In addition, gender disaggregated targets should be embedded in UNDP’s own results framework in order to better monitor this. / Election Campaign -To what extent was the election campaign open? - Score 3 (Good enough): / A few security issues did affect the campaign environment - but this was not widespread and only affected a few areas. 103,000 security personnel were deployed and a security committee was formed, consisting of pertinent ministries of Interior, Defence, Justice, and Foreign Affairs, in addition to the SCER and the Attorney General’s Office.ix / Media and Elections - To what extent was the media coverage before, during and after the election unbiased and responsible? - Score 3 (Good enough): / The context of an uncontested (low stakes) election meant it would be difficult to identify significant media bias. Bias was therefore judged by whether media was perceived to be in support of, or critical of, the participation in the election and sustenance of the transition process. Between media outlets in favour of former regime, former opposition, independent, and state media; press were sometimes biased but in general were largely responsible in their reporting on the election.[9] This generally positive reporting continued after the elections as well.ix / Election Day - To what extent did the election take place in a satisfactory manner? Score 2 (Weak, fragile): / Reports point out that most violent incidents occurred in the southern governorates, with a few incidents reported in the upper northern region of the country.vi,ix Other than that, security was well organised and easily identified (two per polling station with IFES provided identifiable armbands). However, occasional poor behaviour of security personnel at polling stations was observed on the day.ix / 1.5 Impact and Sustainability / The overall impact goal was a “stable and secure Yemen”. The programme was designed to contribute to this by responding to the requirements of the formal political transition process (GCC Agreement) which provided Yemen with a pathway out of the conflict of 2011, and provide Yemenis with an early opportunity to be positively involved in the process of a peaceful transition. The target was measurable through the number of people voting in the interim presidential election, with a target of 1.86 million. This target was significantly exceeded, with a turnout of 6.6. Million Yemenis. The fact that so many Yemenis endorsed the selection of the interim President can be seen to have had a significant impact on the security and stability of the country, as it confirmed their acceptance of the transition process and provided the interim with much-needed legitimacy to govern. If turnout had been lower, this would not have been true to the same extent. / Nonetheless, DFID support did not address electoral security and election-related conflict. As can be seen from the assessment of the outcome indicator, violence and security deficiencies had an impact on the overall conduct of Election Day. The UNDP support provided no assistance on election-security. DFID support to subsequent votes in transition should consider what support could be provided to ensure effective and professional administration of election related security. / In the circumstances of political transition and interim elections, sustainability of impact is hard to judge, as security and stability are affected by much wider issues than the electoral outcome alone. Nonetheless the significant endorsement of President Hadi has empowered him to proceed with difficult actions to take forward the political transition, which aim at providing greater security and stability to Yemen. These would have been much harder to undertake had Hadi not received significant backing, suggesting that the project has helped achieve some sustainable results. More prosaically, the establishment of the UNDP programme and donor engagement in support of this election will have a sustainable impact on the remainder of the transition. UNDP have procured assets and recruited key staff who will work on the subsequent phases of their project and who have built strong relationships with the SCER that will facilitate close cooperation, necessary for successful support to the referendum and elections respectively planned for 2013 and 2014 in the GCC transition plan.
[4] DFID (2012), Support to the interim presidential election: Business Case. [Online] Available at: http://projects.dfid.gov.uk/project.aspx?Project=203030
[5] Nance, D. (2012), 21FEB2012: Yemen Early Presidential Elections data email sent by Darren Nance from UNDP on 11th September, 2012
[6] IFES (2012), Yemen Survey Briefing Report: A Nationwide Survey of the 2012 Presidential Election in Yemen.
[7] DFID (2012), Support to the interim presidential election: Logical Framework. [Online] Available at: http://projects.dfid.gov.uk/project.aspx?Project=203030
[8] European Union (2012), Electoral Expert Mission: Yemen Early Presidential Election.
[9] Al-Arashi E. A. (2012), Media coverage by former deputy head of political section to the British Embassy, Yemen.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Yes / The project was completed within the expected budget of £1.605 million. / 2.2 Key cost drivers / The cost drivers identified during the programme’s design were relevant for its duration. These were categorised as: / Cost of setting up polling stations and providing them with the necessary equipment. / Cost of training polling staff according to the rules, procedures, and special arrangements for the conduct of the interim presidential elections. / Cost associated to the strengthening of a communication strategy which targets women and youth. / Cost of elections outreach content broadcast over radio. / Further detail is provided in the below tablev: / Summary breakdown of Phase 1 costs (US$) / Staffing Training Goods & equipment Consultancy Travel Transport Expenses Sundries TOTAL / 357,000 759,950 4,605,096 130,000 70,000 323,000 60,000 90,000 6,395,046 / 2.3 Was the project completed within the expected timescale: Yes / In accordance with the GCC agreement signed in November 2011, the Government of Yemen and SCER in particular managed to deliver the interim presidential elections within 90 days, on the 21st of February.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / The theory of change underpinning DFID’s support to the project suggested the provision of technical assistance and resources to the SCER, in order to improve its performance, would result in a consequent improvement to the quality of elections delivered by the SCER. Good conduct of elections would contribute to citizens’ confidence in the wider political transition, and good quality elections would boost citizen confidence in the transition process as a whole. As noted in section 1.3, the high voter turnout on election day reflected public enthusiasm for the transition –reported in media coverage at the time as well as the UNDP Project Report.i So overall, the theory of change appears to hold true. / This is qualified by the IFES survey, which provides further insight into Yemeni public perceptions of the election. In the survey, 68% of the respondents were dissatisfied with the state of the country, leaving only 33% of voters satisfied. This somewhat questions the rationale in the theory of change: that a good enough election would immediately equal a stable and secure Yemen. Clearly, many other factors will also have an impact on stability and security, and at the time of the survey (one month after the election) the hardships and challenges faced by Yemenis in their daily lives remained, as they do now, severe. In addition, there were some issues with the quality of the elections that might have had an impact on citizen confidence, as noted in section B 1.4. Nonetheless, the idea that a successful electoral process would boost citizen confidence in the transition process, and that a successful transition process will contribute to security and stability, still appears valid. It is encouraging that respectively 69% and 80% of the survey’s respondents stated their intention to vote in the upcoming referendum and legislative elections, the next stages of the GCC backed transition plan –signalling continued enthusiasm and involvement in the on-going political transition process.vi We therefore judge that the theory of change remains true; but that while each transition milestone will have an impact on stability, it needs to be understood as one piece of the wider transition process; and accompanied by wider indirect transition progress, on issues such as access to basic services and jobs, It is only in this way that there will be a lasting and transformative impact on Yemen’s security and stability. / 3.2 Set out what plans are in place for an evaluation. / UNDP coordinated a sector wide independent evaluation of the interim presidential election, planned for and delivered in the second quarter of 2012. This covered all elements of donor support to the election, including those external to the UNDP programme. The evaluation was intended to form a key piece of evidence in guiding the design of further support to the second phase of the GCC backed transitional plan, in which the new presidential Elections will be carried out in 2014. / Terms of Reference (ToRs) for the evaluation were shared with donors, providing the opportunity for input and comment, which resulted in a robust set of ToRs. However, conduct of the evaluation differed from the plan, the evaluation team’s time in Yemen being shortened. DFID was concerned that, as a consequence, the evaluation team did not meet with some of the people recommended in the TORs and that the report did not adequately cover the areas of focus in the TORs. UNDP has promised a management response to DFID’s comments and concerns although this has yet to be received. DFID continues to request this to ensure that future support to elections is informed by key lessons learned.

4. Risk
4.1 Risk Rating (overall project risk): High / Did the Risk Rating change over the life of the project? No / 4.2 Risk funds not used for purposes intended / UNDP’s provisional financial statement of 7 July 2012 provides a fully reconciled, itemised account of expenditure of DFID’s contribution. The provisional financial statement also reported a breakdown of underspend, the final remainder of which will be returned to DFID. / The programme was managed in accordance with UNDP’s standard Financial and Resources Management procedures, judged “satisfactory” by the MAR. / Under the terms of the DFID/UNDP Framework Agreement, UNDP are required to provide DFID with details of any fraud or maladministration of the programme. Having received no such information on the programme’s delivery, directly or anecdotally, and in the absence of further information, DFID considers the risk of misuse of funds minimal. / 4.3 Climate and Environment Impact / The business case rated both the programme’s Climate and Environment impact and opportunity C. / While the overall impact of the programme was considered insignificant, opportunities for improved environmental management were identified. It was felt that these opportunities, particularly concerning the procurement of goods and services, could have a small direct impact and establish procedures that would have wider benefits to the environment and efforts to reduce greenhouse gases. / Opportunities identified in the business case included: / Sourcing of ballot papers from sustainable or environmentally friendly suppliers. / Environmentally friendly disposal arrangements for used ballot papers. / Minimised CO2 emissions from electricity generation or transport. / In the event, UNDP noted that due to Yemen’s specificities and the urgency of the project, there were limited opportunities to pursue these opportunities (e.g. limited suppliers of ballot papers, no options other than the standard disposal procedures through burning of garbage, no alternative to diesel high capacity generators).
5. Value for Money
5.1 Performance on VfM measures / The business case selected the cost effectiveness of the interim presidential election, measured by the average cost of the election per vote, as the key measure of Value For Money (VfM) of this programme. The table below outlines the business case’s projection of VfM, with an average cost of the election per voter of £19.71. / Cost effectiveness - projected / Voter turnout, millions 1.84 / Total interim election costs, £m 36.27 / Cost per voter, £ 19.71 / Cost effectiveness - delivered / Voter turnout, millions 6.6 / Total interim election costs, £m 36.27 / Cost per voter, £ 5.50 / In the event, concerns registered in the business case of a low turnout were not borne out on election day. With 6.6 million votes cast, the average cost of the election per vote was £5.50 –a result almost 4 times better than anticipated in the business case. / 5.2 Commercial Improvement and Value for Money / As agreed in the DFID/UNDP Framework Agreement, the procurement of goods and services for this programme were conducted in accordance with UNDP procedures and regulations. The MAR judged UNDP’s cost and value consciousness “weak” as it did not find sufficient evidence of UNDP driving forward cost control across its programmes and administration. After the MAR, DFID undertook a review of UNDP’s procurement in 2011. The review noted UNDP’s apparent commitment to improving its procurement capability, but that it was still at a fairly early stage in the process. / In compiling its team for this programme, UNDP sought to employ experienced, high quality staff to fill key roles - including the Elections Coordinator, Finance and Procurement Experts. / UNDP have not provided evidence of further cost savings demonstrating extra value for money achieved by the programme. We will encourage them to do so in future election programming for Yemen. / 5.3 Role of project partners / The implementing project partner was UNDP. Delivery and monitoring was completed through collaboration mainly between UNDP and the SCER. Certain aspects of the project were via UNDP’s association with other partners such as International Foundation for Electoral Systems (IFES), National Democratic Institute (NDI), and European Commission (EC). Collaboration between donors and implementing partners, including those working outside of the basket fund, was important and positive. A high level Donor Working Group on elections was established to complement the pre-existing Basket Fund Working Group. This enabled the coordination of the UN basket fund’s activities with those outside of the fund and collaboration between UNDP and INGO delivery partners. / The independent evaluation of the elections mentioned above noted “unanimous recognition among both donors and SCER of the role played by UNDP as implementer of electoral assistance iii; emphasising the exceptional conditions under which UNDP was operating. Nonetheless, donors requested a higher level of transparency with respect to specific challenges faced by UNDP, such as sharing of information on earmarking of certain items by some donors. Some donors have also questioned the very high cost of ink used in support of elections delivery ($1.2 million); UNDP have responded that as SCER allowed non-registered voters to vote in the 2012 elections, inking was considered the only means to avoid multiple voting. SCER therefore opted for a type of ink much harder to remove and consequently more expensive. Finally, although UNDP devoted a procurement officer to the country office to ensure VfM and procurement planning through the “fast track” procedure, it was clear that a “defined strategy and consequent operational plan was lacking.” iii / Overall, the performance of both UNDP and SCER was judged as good. The capacity of delivery, and results obtained, were excellent. However, communication and coordination were better at times than others, often requiring repeat requests; in particular, DFID’s comments regarding the independent assessment have yet to be addressed. As a result DFID considers that follow up on certain specifics and the responses could have been more prompt and better coordinated. In consequence, DFID will look to UNDP for significant improvement in its coordination and communication with donors during the remainder of the transition. Additionally, in the successor programme of DFID support to transitional elections and referenda, currently in design DFID should look to commission its own evaluation to better ensure its quality and timeliness. / 5.4 Did the project represent Value for Money : Yes / As with the results delivered, quantitative analysis of this programme’s VfM is flattering of its performance. The high turnout at the election resulted in an average cost per voter roughly one quarter of that anticipated in the business case and a consequent VfM greater by a factor of four. / Metrics aside, given the stakes riding on successful conduct of Yemen’s interim presidential election and the success that it was, it is clear that this programme has achieved the value for money set out in the business case.

6. Conditionality
6.1 Update on specific conditions / No conditionality was applied to this programme.

7. Conclusions
Summary of the programmes achieved targets, and comments: / The programme scored A+ against its outputs, but B against its outcome. / The conduct of the presidential election faced challenges, some arguably beyond the SCER’s control and not least due to difficulties implementing according to the compressed timeline set by the GCC backed transition plan. Nonetheless, as a vital early step in the transition process, the election has laid the ground for broader progress and change - with the support of a large majority of Yemeni people. / 6514 polling stations were set up and provided with adequate equipment / 100000 polling staff were trained in the rules, procedures, and special arrangements for the conduct of the interim presidential election / A reasonable and adequate Communications Strategy was prepared. / 2928 minutes of original election outreach content broadcast over radio. i / The scale of overachievement against targeted results suggests that the set indicators and targets might have been over-cautious. / Donors / A good level of donor communication and organisation was demonstrated. i / Early start including the formation of a high level Donor Working Group in addition to the existing Election Working Group was an advantage. / Donors recognised the exceptional nature of the event under which project partners were operating. iii / UNDP / SCER as well donors expressed their appreciation of UNDP’s role as implementer of electoral assistance. / The performance of UNDP and SCER against programme metrics was outstanding. / UNDP’s capability of delivery and the achieved results were excellent. / The conducted evaluation did not fulfil the terms of reference agreed between DFID and UNDP and the quality of the evaluators report was therefore not to the standard DFID expected. Despite repeated follow up and requests, UNDP has yet to issue a revised draft of the report or a management response. / Communication and coordination were better at times than others, often requiring repeat requests; in particular, DFID’s comments regarding the independent assessment have yet to be addressed. / Other conclusions / Election-related conflict and security provision was not addressed under this project, however it should be considered as part of future support to votes during the Transition. / DFID should make clear their expectation with SCER and UNDP that non-registered as well as registered voters are monitored. In addition, gender disaggregated targets should be embedded in UNDP’s own results framework in order to better monitor this. / To insure better quality and timeliness in future projects, DFID should commission its own evaluation.

8. Review Process
This review was conducted by DFID’s Assistance Governance Adviser and Deputy Programme Manager through a combination of desk and field based working. The review was conducted over the months of August and September of 2012. Evidence for judgements was derived from a number of independent reports and discussions with UNDP and SCER which are referenced below.