## Sheet1
PROJECT NAME | Trade Transparency Project
IMPACT | Impact Indicator 1 |  | Baseline - Aug'12 | Milestone 1 - Nov'12 | Milestone 2 - Feb'13 | Milestone 3 - Aug'13 | Milestone 3 - Jan'14 | Milestone 3 - Apr'14 | Target - Oct 2014
Governments’ trade policy decisions become less protectionist as a result of citizen-lead lobbying and advocacy, impacting on trade and poverty | Decreasing rate of protectionist measures in countries covered by the pilot | Planned | - | - | - | - | - | Yes | Yes
Achieved
Source
Global Trade Alert
| Impact Indicator 2 |  | Baseline - Aug'12 | Milestone 1 - Nov'12 | Milestone 2 - Feb'13 | Milestone 3 - Aug'13 | Milestone 3 - Jan'14 | Milestone 3 - Apr'14 | Target - Oct 2014
| Pilot countries proportion of world trade rises or does not decrease | Planned | - | - | - | - | - | Yes | Yes
Achieved
Source
Comtrade
OUTCOME | Outcome Indicator 1 |  | Baseline - Aug'12 | Milestone 1 - Nov'12 | Milestone 2 - Feb'13 | Milestone 3 - Aug'13 | Milestone 3 - Jan'14 | Milestone 3 - Apr'14 | Target - Oct 2014 | Assumptions
Citizens are informed about the costs of trade barriers and engaged with the free trade debate | Number of people who react: composite count of comments, retweets, likes and other reactions | Planned | 0 | 0 | 0 | 0 | 0 | 200 | 500 | 1% of those reached by communication channels will react to the TTP output
Achieved
Source
Online monitoring and analytics
| Outcome Indicator 1 |  | Baseline - Aug'12 | Milestone 1 - Nov'12 | Milestone 2 - Feb'13 | Milestone 3 - Aug'13 | Milestone 3 - Jan'14 | Milestone 3 - Apr'14 | Target - Oct 2014
| Debate stimulated: Number of national and online media mentions/coverage of the impact of trade barriers on consumer prices | Planned | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 1% of reactions to TTP will take the form of national or online media reaction, lagged
Achieved
Source
Factiva search, Google news, local monitoring of coverage
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 150000 |  | 150000 | 0 | 150000 | 100%
INPUTS (HR) | DFID (FTEs)
1
OUTPUT 1 | Output Indicator 1.1 |  | Baseline - Aug'12 | Milestone 1 - Nov'12 | Milestone 2 - Feb'13 | Target - Aug'13 | Milestone 3 - Jan'14 | Milestone 3 - Apr'14 | Target - Oct 2014 | Assumption
Online tool are launched, developed and effectively disseminated to help ordinary people understand trade and engage with trade-related issues | Online tool launched | Planned | No | Prototypes - Yes | Prototypes - Yes | Prototypes - Yes | RLabs Full Launch - Yes CCHubs Full Launch - Yes | - | - | Delivery of workstreams are not delayed. Data clearly shows a significant impact of trade barriers on consumer prices Number of people subscribing to communication channels stays stable in line with August 2012
Achieved
Source
Project team
| Output Indicator 1.2 |  | Baseline - Aug'12 | Milestone 1 - Nov'12 | Milestone 2 - Feb'13 | Target - Aug'13 | Milestone 3 - Jan'14 | Milestone 3 - Apr'14 | Target - Oct 2014
| App are developed continually in line with user feedback | Planned | - | - | - | - | Evidenced - RLabs Q2 Report | Evidenced - CCHubs Q2 Report Evidenced - RLabs Q4 Report | Evidenced in RLabs Q4 Report
Achieved
Source
Project Team Quarterly Management Reports
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline - Aug'12 | Milestone 1 - Nov'12 | Milestone 2 - Feb'13 | Target - Aug'13 | Milestone 3 - Jan'14 | Milestone 3 - Apr'14 | Target - Oct 2014
| Number of people reached through communication channels | Planned | 0 | 25000 | 50000 | 50000 | 200000 | 250000 | 350000
Achieved
|  | Source | [7 empty] | RISK RATING
|  | Project Team | [7 empty] | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
| 150000 |  | 150000 | 0 | 150000 | 100%
INPUTS (HR) | DFID (FTEs)
1