Type of Review: Annual Review

Project Title: Special Programme for Research & Training in Tropical Diseases (TDR)
Date started:	31/12/08	Date review undertaken: July 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
UK will provide £15.5m to TDR over the 5 year period 2008-2013.

What are the expected results?
Formed in 1975, the Special Programme for Research & Training in Tropical Medicine (TDR) is a global programme of scientific collaboration that helps coordinate, support and influence global efforts to combat a portfolio of major diseases of the poor and disadvantaged. It is hosted by the World Health Organisation (WHO) and co-sponsored by the United Nations Children’s Fund (UNICEF), the United Nations Development Programme (UNDP), the World Bank (WB) and WHO. / With a vision of making research and innovation improve the health of those burdened by infectious diseases of poverty, TDR aims to: / Foster research on infectious disease of poverty that leads to health improvement / Engage disease endemic regions and countries in setting the health research agenda and harmonizing the global response / Strengthen the capacity of individuals and institutions in disease endemic countries to perform research related to their own priority health issues / Develop innovative knowledge, solutions and implementation strategies that respond to the health needs of disease endemic countries / Translate innovation, knowledge, solutions and implementation strategies to policy and practice improving health / Promote the involvement of individuals, communities and societies in the use of research evidence to reduce the burden of endemic diseases in their countries. / To achieve this vision and the associated aims TDR have developed two main programmes of activity: / Intervention and implementation research / Intervention research / Implementation and operational research / Research of vectors, environment and society / Research capacity strengthening and knowledge management / Research capacity strengthening / Gap analysis for agenda setting / Partnership and engagement

What is the context in which UK support is provided?
Through the UK’s Framework for Results, DFID is committed to supporting nations to achieve the universally-agreed Millennium Development Goals (MDGs). Through its focus on infectious diseases of poverty, TDR’s work supports disease-endemic countries to better control malaria and other infectious diseases including Neglected Tropical Diseases (MDG6, Framework for Results Pillar 3 - health). TDRs work, supporting research aimed at improving infectious disease control, the work contributes to MDG4, to reduce child mortality and to MDG1, to eradicate extreme poverty and hunger. The strong emphasis on capacity building ensures a sustainable approach to research, supporting disease endemic countries to conduct their own research now and the future.

## Section A: Detailed Output Scoring

Output 1: Countries & Major Funding Agencies Use TDR Scientific and Strategic Reports to Set Research Priorities (Stewardship Function)
Output 1 score and performance description: A Output met expectation / Progress against expected results: / TDR convened a process for the production of the Global Report for Research on Infectious Diseases of Poverty which was launched at a European Union (EU) meeting in early 2012. The report had 14 authors, 8 from disease-endemic countries. The EU has expressed strong interest in using the report to develop its strategy for research on infectious diseases and the report launch prompted commentary in The Lancet, 379 (April,2012): ‘we welcome this report, as well as TDR’s new director, John Reeder. The vision expressed by TDR should earn wide new commitment and partners. It deserves that commitment’. / In 2012, linked to the report, TDR scientists contributed to a special edition of the online, peer-reviewed, open-access journal, Plos Neglected Tropical Diseases laying out a useful Research and Development Agenda for Helminth Diseases (April 2012). This agenda represents the outcomes of a significant prioritisation process which included regular meetings of the Disease Reference Group on Helminth Infections (DRG4), stakeholder consultations and a Delphi process that resulted in the list of 10 top research priorities. A WHO Technical Report Series no. 97,1 on Research Priorities for Zoonoses and Marginalized Infections, was published in June 2012, consolidating the analysis and recommendations of TDR’s Reference Group on this subject. / In May 2011, the Global Health Council, on the behalf of the Bill and Melinda Gates Foundation,awarded TDR the Gates Award for Global Health, demonstrating the influence of their research and capacity-building efforts on both the BMGF and the wider development community. / Convening a large number of stakeholders TDR developed and published the reference document Implementation Research for Control of Infectious Diseases of Poverty, discussing a collection of case studies on how implementation research can strengthen the evidence base for the access and delivery of new and improved tools, strategies and interventions / Providing the secretariat for Essence for Health Research initiative, TDR and partners conducted a wide consultation that resulted in the publication of two strategic good practice documents intended to harmonise support to implementation research and capacity building: 1) Planning, Monitoring and Evaluation Framework for Research Capacity Strengthening and 2) Five keys to improving research costing in low- and middle-income countries.
Recommendations: / The new TDR strategy, and organisational structure, mean that there is a more integrated approach to activities that were previously brought together under the stewardship work programme. TDR still has a role in these activities, but will change its ways of working. For example in the future there will be a greater focus towards the need for the development and implementation of a methodology to measure the effectiveness and impact of such publications and TDR will consider the post-publication process and communication and dissemination strategies, in particular trying to focus on those areas and/or strategies likely to have highest impact. / Impact Weighting (%):25% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? Y

Output 2: Disease Endemic Countries (DEC) are Leading New/Strengthened Health Research Initiatives (Empowerment Function)
Output 2 score and performance description: A Output met expectation
Progress against expected results: / 2011 saw the successful transition of ISHReCA, an African research network initiated by TDR and the Wellcome Trust from TDR-Geneva to Yaounde, Cameroon. The African Network for Drugs and Diagnostic Innovation (ANDi) is now fully operational and operating out of Addis Ababa. There were over 300 research abstracts submitted to the stakeholders meeting, resulting in the recognition of 32 centres of excellence and the selection of priority research projects to be led by DEC scientists. It is hoped that an Asian equivalent, Asian Network for Drugs, Diagnostics and Vaccines Initiative (ASEAN-NDI) will learn lessons from the development of ANDi and be operational with a strategic business plan in place by the end of the next financial year. / 12 developing country scientists continue to participate in the TDR/Gates Career Development Fellowship Programme and, in partnerships with the IFPMA and 11 pharmaceutical countries, recently undertook some development about drug and vaccine quality preclinical research and development. The programme has been very successful leading to an increased number of requests from the pharmaceutical industry and PDPs and a consequent expansion of placements with additional support from BMGF / Of 233 TDR-funded research papers published in 2011, almost two thirds (143, 61.4%) had DEC scientists as their first authors. / The Gates Award for Global Health was further public recognition of TDR’s ground breaking work on capacity building of local researchers in disease endemic countries. / Recommendations: / TDR continues to play a critical and effective role in developing DEC capacity and expertise in tropical disease research. In particular they have shifted their focus away from developing the capacity of individuals, towards focussing on institutions and networks. TDR will work to build regional capacity in a number of areas and enable promising individuals can be supported as they build their scientific careers. / Impact Weighting (%): 25 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: New/Improved Knowledge, Tools & Implementation Strategies are used in DECs
Output 3 score and performance description: A Output met objective
Progress against expected results: / Progress has been good. For example , TDR worked with partners in India to test the use of single-dose liposomal amphotericin and to develop more effective treatment of visceral leishmaniasis (VL): the new approach, which also including diagnosis at peripheral level, has been adopted and has contributed to the optimised VL elimination programme in Bangladesh, Nepal and India; TDR developed a prediction-detection-response for Dengue outbreak model which is now being used in 7 endemic countries; TDR are working with the Ministries of Health in Guinea-Bissau, Uganda, Tanzania and Ghana to better understand the epidemiology of severe malaria and develop partnership to pre-qualify and improve access to malaria drugs; and they have worked with National TB Control Programmes in Eastern Europe, Central Asia, Africa, WHO (both Headquarters and Regional Offices), Stop TB Partnership and others on the SORT IT Initiative in order to develop an integrated operational research and capacity building partnership for disease endemic countries. / Recommendations: / TDR will need to embed their new strategy and work programme and the focus of some of their research will change over the next year. They will need to identify ways that their work impacts on national policies and programming TDR are working on their ongoing communications and monitoring strategies, which should include ways to measure the uptake of TDR research findings, strategy recommendations and publications on in-country (as well as regional and international) policy and programming decisions. / Impact Weighting (%): 50 / Revised since last Annual Review? N / Risk: Low/Medium/High Medium / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? N / 1.2 Overall Output Score and Description: A Outputs Met Expectation / 1.3 Direct feedback from beneficiaries / DEC researchers represent the most immediate and direct beneficiaries from TDR’s efforts, poor people on the ground representing a second but more indirect beneficiary group. While it is easier to directly monitor impacts on researchers benefiting from TDR’s capacity building activities, there are structures to gauge eventual impact on community members on the ground. / TDR has a number of thematic working groups including the social science and gender thematic reference group which considers the social, gender, cultural, economic and policy-related issues affecting infectious diseases of poverty. This group is hosted by the WHO Country Office in Ghana. / The programme is particularly committed to addressing gender issues and ensuring that gender and wider social science issues (including equity and social determinants of health) are investigated as part of the overall ‘research for health’ agenda.
1.4 Summary of overall progress / TDR has been through a difficult time, financial constraints have required a two stage process of reorganisation and this has been coupled with a change in Director. The previous director left in August 2011 and the new Director (John Reeder) was appointed in February 2012. / TDR appear to have managed this period of uncertainty well and have responded to the external evaluation that was completed in late 2011. Under Dr John Reeder’s leadership, TDR have responded strongly and positively to the recommendations of the external review and, at their Board Meeting held in June 2012 presented a thoughtful new programme strategy and proposed staffing structure for a future slimmed-down TDR. The scope and portfolio of projects and activities have been streamlined responding to recommendation from the External Reviews and Scientific and Technical Advisory Committee (STAC). / In spite of significant organisational challenges, TDR continued to fulfil its key functions over the period of uncertainty. Overall, things look positive for moving forwards and TDR has already made substantial progress during the year.
1.5 Key challenges / While TDR has experienced a number of difficulties (see above) over the last couple of years, most major challenges have been addressed in the recent strategy and budget refresh which point towards a more streamlined, strategic and slimmed down programme of research and a smaller, more efficient core staff and governance structure. Associated with these changes however will the challenge of managing workloads and maintaining staff morale among remaining staff members and associates.
1.6 Annual Outcome Assessment / While it has been a turbulent couple of years for TDR, they have weathered the storm well and members of the Board came out of the 2012 Annual Board Meeting feeling confident about TDR’s future. DFID will continue to monitor progress and ensure that new strategic directions, budgetary handling and governance structures are maintained, and recommendations from the external review carried forwards to a support an efficient, effective and well-regarded TDR.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / 2.2 Key cost drivers / A key cost driver is the significant programme staff costs; at the Annual Board Meeting it was agreed to reduce staff numbers thus reducing the burden of this budget line. TDR is changing its systems, to work differently in the future, with the development of a more accurate project costing system and strong systems and processes for handling restricted and unrestricted funding and grant reporting, in order to prevent budget overspends. TDR is currently developing new policies and processes to ensure effective cost recovery and management of designated funding projects, covering the whole process from proposal development to final reporting. / Like all organisations based in Switzerland TDR staff costs have been affected by the increasing value of the Swiss Franc against the US dollar. WHO as an organisation are trying to respond to this, in the short term, but there are significant issues to be addressed institutionally. / 2.3 Is the project on-track against original timescale: Y / TDR does not work on single project timescales but is on track to achieve agreed annual and biennium targets. Each individual project has its own timeline and management structure to ensure it meets its stated objectives.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / An external evaluation was conducted in 2011, highlighting a number of points of concern. TDR has responded to the report incredibly positively and proactively, and changes in the organisational strategy and structure are addressing the recommendations of the review. / 3.2 Where an evaluation is planned what progress has been made? / In light of the organisational troubles experienced by TDR in the period 2010-12, the External Review scheduled for 2012 was brought forward and following open competition was conducted by HLSP in 2011. The lessons and recommendations from this review contributed significantly to the development of TDR’s new strategy and new reporting structures to improve efficiencies, and to the changes in the Governance Structure, adopted at the Board meeting in June 2012, following recommendations made by a sub-group of the Board.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / While TDR have recently experienced a period of turbulence they have managed the difficulties well and have successfully navigated through these challenges with the appointment of a new Director (Dr John Reeder) and development of a new streamlined strategy, accompanied with significant structural changes to the organisation to maximise their added value and increase their efficiency. While there are still risks associated with a programme in transition the early signs are promising.
Risk of funds not being used as intended / This is low risk as the programme follows WHO financial management practices and procedures is audited annually by the WHO and all funding agencies have the right to call for additional external audits, if required. The external review included reviewing the portfolio and grant reporting structures. Recommendations made by the external evaluation team, and the Board, have resulted in a much clearer, more strategic and more narrowly defined work programme that capitalises on TDR’s strengths and added value as an organisation, alongside plans to develop stronger policies and processes to ensure the effective management of designated funding projects. / 4.4 Climate and Environment Risk / There are unlikely to be any major negative impacts of this programme though they do have a specific work stream on ‘environment and infectious diseases.’ This reflects TDR’s understanding of how the environment plays a powerful role in the transmission of infectious diseases, including vector-borne and soil-transmitted infections. Their research not only explores how to improve vector control measures for disease prevention, but also how policies of health, environment and development can be aligned, in this manner having a potentially positive impact on climate and environment. Examples of recent and on-going pieces of TDR research and/or publications that might have a positive impact on climate and environment include a project exploring community-based ecosystem and management interventions against Dengue and Chagas disease vectors in Latin America, and another looking at the effect of environmental and climate change on major vectors and vector-borne diseases (this work supports the WHO African Regional Committee for Africa's Framework for Public Health Adaptation to Climate Change in the Africa Region).

5. Value for Money
5.1 Performance on VfM measures / TDR is a unique organisation, with no other organisations having the scope and reach of research partners in developed and disease endemic countries. In addition TDR has a wide range of resource contributors (both developed and disease endemic countries (DEC)). TDR is able to carry out a broad base of activities contributing to DFID priority areas. The value for money of the programme is considerably greater than supporting smaller projects commissioned on an individual basis. TDR produces high quality research and trains high class DEC scientists, the results of which have had a significant impact on the control of a core set of neglected infectious diseases of poverty and, consequently ,for the outcomes of the populations in the poorest countries. / 5.2 Commercial Improvement and Value for Money / TDR has undergone significant restructuring to overcome the financial challenges it has faced. DFID has worked with TDR through its governance structures to ensure its systems are designed to provide value for money. / 5.3 Role of project partners / TDR has worked closely with the co-sponsoring agencies, chair and vice-chair of the board to develop solutions to the challenges faced during the last year. The Joint Coordinating Board (JCB) has endorsed the new, realistic, budget and changes to the Governance and accountability of the organisation. TDR has now moved from its own, stand-alone, offices to WHO HQ which has allowed far greater integration with the WHO disease departments (neglected tropical diseases, malaria, TB etc.). / The TDR Joint Coordinating Board (JCB), is Chaired by DFID enables all resource contributors and disease endemic country partners to have a strong input to the programme. / 5.4 Does the project still represent Value for Money : Y / 5.5 If not, what action will you take? / NA

6. Conditionality
6.1 Update on specific conditions / NA

7. Conclusions and actions
The TDR programme enables DFID to meet some of its key research priorities for infectious diseases because of its unique position with the WHO, its broad coalition of resource contributors and strong support by disease endemic countries. They should be congratulated upon negotiating difficult times so well and, in particular, for both continuing to manage to produce such high numbers of high quality outputs during a time of massive organisational stress and upheaval, and for responding so positively and professionally to the findings and recommendations of the external review. / DFID is aware of the issues recently faced by TDR but is confident in its response including the organisational restructuring and strategy streamlining. DFID will work with the programme to ensure these positive changes are built upon and continue to develop to ensure DFID's investment continues to represent excellent value for money. As Chair of the Board, DFID is particularly well placed to monitor the successful implementation of agreed organisational and financial restructuring and the new streamlined strategy.

8. Review Process
This review was completed by members of the Human Development Team, Research and Evidence Division. The review used key documentation produced by the TDR programme, a 2011 external review of the programme, personal contacts with the programme, donor partners and the co-sponsors of the programme together with the outcomes of the Annual Board Meeting held in June 2012.