Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Science for Humanitarian Emergencies and Resilience (SHEAR)
Programme Value: £17.87m (+£6m from NERC)		Review Date: November 2017
Programme Code: 201884	Start Date: 10 December 2014	End Date: 30 September 2020

Summary of Programme Performance
Year	2015	2016	2017
Programme Score	A	A	A
Risk Rating	M	M	Moderate

The SHEAR programme aims to support improved disaster resilience and humanitarian response by advancing the monitoring, assessment and prediction of natural hazards and risks across Sub-Saharan Africa and South Asia, and through working with users, bring this into use in reducing the impacts of disasters. A large component of the programme is a partnership between DFID and the Natural Environment Research Council (NERC). SHEAR aims to catalyse earlier and more effective action to respond to imminent natural hazards and enable greater and more effective investment in disaster resilience and preparedness. SHEAR has three ‘pillars’: SHEAR Applications, SHEAR Research and; SHEAR Applied and &Innovation. Details of the pillars can be found at Section A below. The programme also has a knowledge broker (KB) and a research consortium coordination team (CCT) to drive better learning, information exchange and coherence between the different research projects and activities.

Summary of progress since last review

This is the third Annual review of the SHEAR programme. Good progress has been made over the reporting year, notably:
- DFID-NERC Research (‘SHEAR Research’): The four main SHEAR Research consortia are now fully operatonal and generally on track with research workplans. The Knowledge Broker (KB) and Consortium Coordination Team (CCT) are now established and operational. 12 NERC studentships (6- 8 from southern institutions) across the DFID-NERC research consortia, led by Imperial College London, have been advertised and are to be awarded in May with a start date of September 2018. The next stage of research work aimed at filling remaining gaps is currently underway with a research competition ‘announcement of opportunity’ (AO) with projects being selected early in 2018.
- Global Facility for Disaster Reduction and Recovery (GFDRR) led (‘SHEAR Applications’): Challenge Fund has completed the competition for Round 1 (phase 2) and Round 2. Round 1 phase 2 funded 7 scale-ups of successful phase 1 projects. The Round 2 competition resulted in three new consortia being selected to advise on aspects of an open-source risk database to inform preparedness and response mechanisms, all of which are now fully operational. Discussions are underway with GFDRR and with PSD colleagues on the development of ‘use case’ materials developed from the Round 2 pilot work, to demonstrate the application of global risk data on an open source platform and to obtain broad acceptance of the agreed format etc.
- Emergency response and preparedness projects (‘SHEAR Applied and Innovation fund’): Continued provision of El Niño-state monthly global country-scale 1, 1-3 and 4-6 month weather/climate forecastsin response to growing demand, These products, developed by the University of Reading and UK Met Office and issued jointly by CEW / CHASE, continue to ensure DFID senior management, DFID Country Offices and emergency response partners have been kept well informed and able to respond and prepare appropriately as the La Niña phenomena has recently evolved. A potentially enormous amount of unnecessary activity based on rumours of a 2017 El Nino was also averted based on these forecasts and accompanying advice. Associated work is well underway to improve our understanding of forecast-user needs, improved communication of climate model skill and capabilities related to advisory products of this type so as to develop better and more relevant future products.
- Also under the SHEAR A&I component, the 14 smaller research projects commissioned in 2016 and designed to take advantage of opportunities to collect data on one of the strongest El Niño phenomena on record, are now all well established and working to complete their data collection and analyses on impacts, both biophysical and socio-economic. Work is progressing well and plans for synthesis (drawing together the 14 separate pieces of research) and a finale event at the Royal Society in May 2018 are well advanced.
- Work funded under the SHEAR A&I component on earthquake induced landslides, commissioned in the aftermath of the 2015 Nepal earthquake, continues to be strongly linked into key national and international actors in Nepal as well as DFID’s Nepal office. The University of Durham team and partners continue to work closely with the National Reconstruction Authority and UNOPS to feed in their geo-hazard assessments and provide training and support. These links are important in terms of getting the science/analysis into decision-making. This will need ongoing and proactive effort given the dynamic context in Nepal, and changing contacts in government. Related work led by the University of Cambridge on seismicity analysis following the Nepal earthquake concluded in 2017. Information generated by this project was used to help update the building codes for Nepal. The project also contributed to an information note to DFID’s permanent secretary on earthquakes in Africa following .
- Within SHEAR A&I: DFID-NERC innovation co-funded research into disaster risk financing triggers, bringing the risk academic research and financial services provider communities together, to improve the design of scientifically robust triggers for financial mechanisms that improve resilience through more efficient preparedness. This work, co-funded within DFID by CEW (£0.5M) PSD (£0.2M) and ARD (£0.5M), was advertised in July; 22 proposals were received. In mid-November the proposal assessment panel recommends those (approximately 8) projects to be funded.

Key lessons

1. Experience to date suggests that there is significant latent demand from a range of actors (DFID and external partners) for tailored weather and climate forecasts and importantly, likely impacts. Tailoring can cover geographical or sectoral / sub-sectoral as well as how information is presented / communicated to stakeholders.
2. Although it’s still early days, coordinating information emerging from a broad set of projects led by a wide spectrum of organisations scattered globally is likely to be a challenge for the Knowledge Brokers (Practical Action and Red Cross/Crescent Climate Centre). Early stage discussions are underway regarding bringing together knowledge brokers from across DFID and NERC funded projects to share lessons and approaches.

Summary of recommendations for the next year

1. As we move closer to programme conclusion (March 2020), to keep a close eye on the unspent component of the SHEAR A&I (emergency preparedness and response research) budget, ensuring strategic spending on ad hoc necessary work as time progresses but also ensuring sufficient funds are retained in order to be able to respond efficiently to any unforeseen emergency throughout the next 2 years. DFID CEW team. Ongoing.
2. In order to ensure the Knowledge Broker is effective at facilitating information exchange within the programme and to external stakeholders, the contract has been agreed for one year only (until June 2018) during which time they will establish a SHEAR website and process of knowledge exchange; prior to the conclusion of this trial year we will take stock of the effectiveness up to that point and either amend the ambition or resources available before embarking on any continuation. DFID and NERC teams to review and make a decision on future years. By May/June2018.
3. It has been broadly acknowledged and was highlighted in the last AR that the initial SHEAR lograme is too complex for all reportees and arguably not well suited to the overall objectives of the programme. We have therefore proposed a much-simpler alternative that more closely fits the design of the various programme strands and are discussing with the Knowledge Brokers and various PIs, working towards settling on a modified logframe suitable to all. All partners and key suppliers. Revised log frame to be agreed by end Jan 2018.
4. As a result of feedback from medium-term climate/weather outlook notes for CHASE and others, we will ensure that the results of the outlook-note improvement research, along with feedback and information regarding new climate impacts research capabilities, inform a step-change improvement in the notes, in their communication, representation of model skill (confidence over forecasts in particular regions) and the extent to which they include forecasts of socio-economic impacts such as possible floods, crop failure, water resources stress and human health threats. We seek to commission a refreshed forecast note before July 2018, when the current note provision contract comes to an end. DFID CEW team to agree future arrangements. By April 2018.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-201884/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-201884/documents/

Outline of the programme
DFID is providing £17.87 million over five years to enable greater and more effective investment in disaster resilience and earlier action to respond to imminent natural hazards by providing decision makers with enhanced risk mapping and analyses and more reliable warning systems. The programme focuses on flood and drought risk monitoring and warning systems in Sub-Saharan Africa and multi-hazard risk assessment and monitoring across South Asia, with a focus on the interaction of ‘cascading hazards’ such as landslides, which can be triggered by heavy rainfall. It covers four areas: disaster risk assessment (mapping and analyses), sub-seasonal to seasonal forecasting, disaster risk monitoring, and the integration of these into practical decision making. The programme consists of three principal components:

1. SHEAR Research: working with the NERC to support world-leading international research to: improve the underpinning understanding of risk in DFID priority countries to inform disaster preparedness and resilience; enhance the reliability of seasonal (up to 6 months ahead) forecasts to strengthen early warning system; and demonstrate the practical application of these within decision making on preparedness and resilience. DFID is providing £7.5 million to support work in Africa and South Asia with additional funding from NERC of £6 million. This partnership has secured sizeable in-kind contributions, including leveraging the Natural Environment Research Council’s existing project portfolio and programme commissioning, contracting and management capability.
2. SHEAR Applied and Innovation (SHEAR A&I): to support a portfolio of targeted, rapid-response projects to seize opportunities to utilise emerging technologies and respond to evolving user needs in the area of knowledge and tools to support disaster preparedness and resilience, with a facility to provide knowledge management, coordination and M&E activities for SHEAR. Following the 2015 Nepal earthquake and the onset of one of the strongest El Niño events on record, the £ 2 M SHEAR A&I Response Fund was substantially drawn down to fund research in these areas and as result, DFID management agreed to replenish the fund, making an additional £ 5 M available over the remainder of the project.
3. SHEAR Applications (SHEAR Apps): partnering with the Global Facility for Disaster Reduction and Recovery (GFDRR) at the World Bank to deliver an innovative toolkit of new open data and tools to support preparedness and resilience through a competitive challenge fund (£2.5 million). This partnership leverages GFDRR’s on-the-ground expertise and networks to ensure that the outputs are demand-led and deliver value for money through building upon existing projects and delivering private sector contributions. It is delivered through a Challenge Fund (CF).

The third component, SHEAR Apps, was originally co-financed by DFID RED and CHASE (£0.5m to £2 million respectively) bringing together RED’s expertise in commissioning high quality science with CHASE’s operational experience to ensure that this science delivers tangible development impact on the ground.

SHEAR aims to leverage sizeable in-kind contributions from the private sector, including computational resources and technical expertise, and the programme is working to coordinate with other actors and donors including USAID to deliver greater collective impact.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment (A)

SHEAR’s outcome is “New high quality and relevant data and tools accessed by decision makers and applied in practice (& established processes and partnerships toward greater accessibility and availability of data and tools to support disaster resilience and preparedness in developing countries)”.
This is the third Annual review of the programme. It is still relatively early to make any authoritative assessment in terms of achieving the project outcome indicators, though the trajectory of progress against project outputs has been good, with performance exceeding expectations in some areas. Good progress has been made on SHEAR Apps, SHEAR A&I and more recently SHEAR Research, warranting an overall performance assessment of ‘A’ – outputs moderately exceeded expectations. Progress against one output area (Output 5 – Knowledge Management and Consortium Coordination) was deliberately delayed until the main research consortia were established so as to enable the consortia’s input and participation in the terms of reference and selection of the consortium coordination and knowledge broker function. This has now been completed and both are fully operational. The programme is now on a good footing to demonstrate improved performance within Output 5 in 2018, with the currently high/marginal ‘A’ outcome improving to ‘A+’.

Headline performance against each output is summarised in the table below.

Overall output score and description
SHEAR is making good progress against most of the outputs milestones for 2017 with Outputs 1, 2, and 3 awarded an ‘A+’ score (with weightings of 20%, 5%, 30% respectively) and outputs 4 awarded an A score (weighting 35%) and output 5 awarded a B score (weighting 10%). A summary is provided below. Details can be found at Section C below.

Output / (weighting)	Description	Summary narrative	Score
Output 1 / (20%)	Challenge Fund - New toolkit of demand-led, open data, tools and products for resilience, preparedness, response and recovery. / Improved capacity of the community to deliver demand-led, co-produced products that have an impact in practice. / Role of gender considered in project design and delivery.	The Challenge Fund (CF) has delivered impressive results. The first round of 15 projects targeted over 20 countries throughout Africa, South Asia, East Asia and the Pacific and delivered 15 new tools and products (13 on open platforms), ranging from flood simulation technology, to mobile app building, to weather station pilots and film production. 47 partnerships have been established with local institutions and the 15 projects have provided training to 1082 partners thus far. 13 of the projects funded were co-designed with local beneficiaries. Phase 2 of the CF has supported 7 projects to scale up or replicate their work. Two further projects not funded under Phase2 were successful in attracting $300,000 in additional funding from the government of Belgium. / Round 2 of the CF launched in August 2016, focusing on the creation, use and piloting of risk-related data and better understanding the needs of end-users. Of 84 proposals received, 3 were supported addressing 3 ‘challenge areas’: (i) Hazard Scenario Datasets; (ii) Global Open Exposure Data Repository Frameworks and; (iii) Open Vulnerability Function Datasets. These are being piloted at the national, regional and city level in Tanzania, and regionally in Ethiopia, Kenya, Uganda, Malawi and Mozambique. The three projects have held two joint workshops, including the second convened as an industry workshop,hosted by UCL at XL Catlin (a global insurance/re-insurance company) involving insurance and catastrophe risk modeling specialists..	A+
Output 2 / (5%)	Improved understanding of user needs, feasibility and roadmap for delivering more accessible and coordinated risk data and tools for developing countries.	A number of studies have been completed and published, including literature reviews, interviews, on line-surveys and 6 separate consultation exercises, including an open call for contributions. Findings are summarised in the report ‘Solving the Puzzle: Innovating to Reduce Risk’ launched in August 2016. A number of learning products have been developed: an in-depth evaluation of a CF Phase I project has been published and a learning document entitled “GFDRR Challenge Fund Phase 1 Results and Learnings” was completed in February 2017, which compiled key elements of learning to be incorporated in future Challenge Fund and similar projects. / Although not funded during Phase 2, the Floodtags project is meeting with great success with respect to the highest-level results envisioned by the SHEAR logframe. Its project, Twitter Analysis for Quick Flood Response, was used by the Philippines Red Cross in September 2017 during relief efforts after a Tropical Depression there which caused extensive flooding. It is using the Floodtags software in its operation center and credits the dashboard with making its relief operations more efficient and effective. FloodTags are also being further funded by the Dutch government to replicate their project in Mali. The project, which focuses on areas surrounding the Niger- Delta, received € 180,260.00 in funding.A number of communications events and products have been delivered, including 2 events held at the World Bank headquarters showcasing the ‘Rain Cell’ project in Burkina Faso and the FloodTags project in Tanzania. The various communication products can be found in the newly redesigned CF website. / Results from Phase 1 projects were featured in the 2016 Understanding Risk Forum session “Disruptors: Cutting Edge Technologies that are changing the way we understand risk” and there are plans to showcase the results of Phase 2 at the May 2018 Understanding Risk Forum in Mexico. / Additionally, there has been domestic and international coverage of the CF projects in the media, including in respected journals such as Science. A blog on what the team of GFDRR has learnt in managing a CFwas published. / Notably, in June 2017, the CF projects were awarded the “President’s Award for Innovation” at the World Bank Group.	A+
Output 3 / (30%)	Improved understanding of risk and more reliable predictions of hazards like floods, droughts and landslides across SA and SSA, evaluated by ‘honest broker’	The main research consortia contracted through NERC are now fully operational: 2 in Africa and 2 in Asia. Initiatives to support the better understanding of risk during the aftermath of the Nepal earthquake have also been successful, with one of the two projects in this area being scaled up at the request of DFID Nepal and the other feeding into Nepalese building codes. / SHEAR PhD Studentships (estimated 12; half from DFID priority countries) have been advertised and will be selected early in 2018. / A NERC Announcement of Opportunity has been issued for a series of smaller catalyst projects, to complement the research already being undertaken by the larger NERC co-funded consortia – outline proposals will be submitted in Jan 18, with the assessment panel in May and project to start in September 2018.	A+
Output 4 / (35%)	Better understanding of what works in getting the right knowledge and tools to the right people in the right way, demonstrated on the ground with impact	The main research projects noted above are strongly placed to deliver against this output. Additionally, first Round CF projects, combined with the scoping and surveys have already begun to deliver impact, with seven Round 1 CF projects selected for scale up and 2 more being funded by the Belgian Government. Three Round 2 CF pilot initiatives are now operational in Tanzania, Ethiopia, Kenya, Uganda and Malawi. / Work on El Niño / La Niña outlook analyses (by the University of Reading and the UK Met office) has been very successful, helping inform DFID policy and practice and reaching a wider audience of implementation partners in the humanitarian space. A review of the 15/16 El Niño humanitarian preparedness and the role of forecasts was undertaken by a consortium led by the Red Cross Red Crescent Climate Centre and covering 5 African countries. Overall the report found forecast and messaging to be timely and credible, but noted that stakeholders expressed a desire for better coordinated and audience-tailored information, withinterpretation. There is increasing demand for this type of information from within DFID and further work is underway to improve the relevance and presentation of information.	A
Output 5 / (10%)	Effective management of the research programme, including M&E of impact and value for money, and effective management of capacity building opportunities	Overall the management of the programme has functioned well, with the CF component (SHEAR Apps, managed by GFDRR) and the main Research component (SHEAR Research, managed by NERC) operating well and as expected. Originally, the design called for a knowledge management and coordination (KMC) function for the programme as a whole to be established early.However, based on more recent experience it was agreed with NERC that this should be deferred until the main research consortia were established and able to participate in both the specification of the role and the selection of the service provider. This has now been completed and both the Consortium Coordination function and the Knowledge Broker function are now operational. Likewise, it was felt that delaying the revision of the logframe so this same group could be involved was also sensible. The KB and CCT functions are both already on a good footing for improved internal and external communication of research findings and outputs, so we expect an improved score for this output in 2018.	B

Key actions
Based on the lessons listed above and the recommendations described in section C of the document below, the following set of key actions have been identified:

1. The logframe should now be reviewed and revised as soon as possible given that all key elements of the programme are in place and core participants able to input into the review process: revised LF to be agreed by end January 2018.
2. DFID and NERC, working with GFDRR and the new KB / CCT, to ensure that work under SHEAR and any new networking functions or communities of practice established through SHEAR are linked as much as possible to other work ongoing or planned in DFID as well as with existing networks or global communities of practice, to ensure their longer-term value, impact and effectiveness. An example of this is to establish a link with work on risk insurance underway in Private Sector Department, potentially alongside NERC. Ongoing.

Has the logframe been updated since the last review?
No (see above) – it is agreed that the logframe needs revision (it is currently too complex) but that it is important that the principal investigators (PIs) involved in the main research grants and representatives from the Knowledge Broker (KB) and Consortium Coordination Team (CCT) are able to engage with this process. It was therefore decided that this revision would need to take place once the newly commissioned main research programmes had completed their initial start-up and the new KB and CCT mechanism were fully established. The recommendation above is for the logframe to be reviewed and revised by end February 2018.

## C: DETAILED OUTPUT SCORING (1 page per output)
Output Title	New toolkit of demand-led, open data, tools and products for resilience, preparedness, response and recovery
Output number per LF		1		Output Score		A+
Risk:		Medium		Impact weighting (%):		20
Risk revised since last AR?		N		Impact weighting % revised since last AR?		N
Indicator(s)			Milestones (2017 or EOP)		Progress
Number of new datasets and tools developed (including in DFID priority countries)			In total, at least 10 new datasets and tools in development (50% in DFID priority countries).		Exceeded. In total 15 new tools have been developed, 10 of which were in DFID priority countries (67%). / 13 of the tools are currently available on open platforms. / Seven projects were successfully funded for Phase 2 of Round 1 and are scheduled to close by the end of February, 2018. / Round 2, aimed at developing a framework to facilitate a multi-hazard view of risk, has funded 3 projects each addressing one of the following ‘challenge areas’: (i) Hazard Scenario Datasets; (ii) Global Open Exposure Data Repository Frameworks and; (iii) Open Vulnerability Function Datasets. These are being piloted at the national, regional and city level in Tanzania, and regionally in Ethiopia, Kenya, Uganda, Malawi and Mozambique.
(a) Number of new partnerships developed across disciplines that support the development of demand-led products; existing (b) % projects with co-design and co-development approach with users			(a) 10 new partnerships developed between delivery partners (including 50% local partnership) and (b) 50% of products co-designed and co-developed with users		Exceeded. / (a) 47 partnerships were formed with local partners. / (b) 14 out of 15 (93%) projects were co-designed with well over 1,000 local beneficiaries. / 3 new partnerships developed for CF Round 2. Lead institutions are UCL London, the British Geological Survey and the Global Earthquake Model. All are engaged with a wide range of industry, academic and NGO stakeholders.
Number of project plans considering gender in risk identification, outreach and capacity development plans			All second round projects considering the role of gender in implementation		Met. Guidance for CF applications required suitable consideration of gender. Additionally, an M&E specialist worked with a number of Round 1 and 2 projects to help better address gender in the proposals. All 7 of the Phase 2 proposals were assessed as considering gender in meaningful ways with gender analyses being used in several (see GFDRR gender action plan here).
Number of targeted beneficiaries that receive training during the project			A cumulative total of 20 beneficiaries will be trained in Challenge Fund tools over the life of the project.		Exceeded. To date CF awardees have trained 1,082 beneficiaries across the range of projects.
Evidence on what works and the value of information gathered through M&E and communicated through progress and final reports			Case study evaluation of Phase 2 project completed and at least 20 M&E project-level assessments completed. Final report communicating examples of value of information for decision making.		Met. CF learning document submitted in February 2017.Case study evaluation of NIWA project completed in April 2017. Evaluation is now publicly available. Case study evaluation of IWMI’s Phase 2 project scheduled to begin in November, 2017. / 15 M&E project-level assessments from Phase 1 completed. An additional 7 M&E project-level assessments for Phase 2 are in progress and on track to be completed by end of project. / Final report communicating examples of value of information for decision making is scheduled for submission at end of Phase 2.
Leverage from private sector investment in projects (and other activities related to project)			£500,000 private sector cash and in-kind contributions by June 16 rising to $1 m by Nov 16.		Exceeded. To date, CF projects have recorded £3,890,126 cash and in-kind leverage. This is nearly four times the target for this output.

Key Points
There has been good progress against this output, exceedingexpectations against most milestones despite some initial delays during year 1 in setting up and launching the SHEAR Apps Challenge Fund (CF). The CF competition process has been well-managed and publicized. GFDRR outreach and ‘market engagement’ has been good: a dedicated webpage was set up on the GFDRR homepage for the Challenge Fund (see: here) as well as a dedicated page on the Understanding Risk (UR) website: here). Outreach was additionally promoted via GFDRR and other World Bank newsletters and social media channels, including Twitter and LinkedIn. There has been domestic and international coverage of the Challenge Fund projects in the media, including in respected journals such as Science. Also, in June 2017, the Challenge Fund team were awarded the “President’s Award for Innovation” at the World Bank Group, for their work funded through the SHEAR programme.

Learning. A blog on what the GFDRR team has learnt from managing the Challenge Fund was published and had global reach - see here. In relation to the three Round 2 projects that aim to develop a framework that facilitates a multi-hazard view of risk, GFDRR has recognized the importance of developing a data exploration and visualization tool to support the work produced by the consortia. The data exploration tool will provide developing country decision-makers with a user-friendly means to visualize and query the data emerging from the Round 2 of the Challenge Fund. To take this forward, GFDRR have published an expression of interest (EOI), and the team are in the process of selecting a winner from the technical and financial proposals received. The next step is to award the winning firm with a contract to develop the data exploration tool, which will be delivered in March 2018.

Some examples of CF projects:

Open-source mobile weather stations to reduce flood damages and increase preparedness (IWMI). This project pilots an open source mobile weather station to provide a low-cost, locally manufactured solution to provide reservoir managers with timely information on rainfall and other weather parameters via SMS to reduce flood risk in Sri Lanka. This remote weather station technology was used by the Pakistan Meteorological Department in late 2016 to implement a network of automatic weather stations (using IWMI prototype designs) to provide early warnings of floods along the Indus River. In addition, agencies from many countries used IWMI’s design to fabricate weather stations for their own use. These included: Solomon Islands (UNDP); Vanuatu (Ministry of Agriculture); Togo (Red Cross/ Red Crescent Climate Change); Haiti (Ecole Supérieure d'Infotronique d'Haïti); Sri Lanka (COSTI, NBRO, Met Department, University of Moratuwa); and Mountain Hazelnut Venture Pvt. Ltd. In Bhutan. IWMI is also planning to create an online knowledge platform to link potential users of these devices with developers.

VISUS[1] – a multi-hazard school safety assessment methodology to help policy makers decide where to focus risk reduction efforts. Working with Indonesia’s Ministry of Education school rehabilitation programme. See here for more information.
[1] Visual Inspection for Defining safety Upgrading Strategies (VISUS)
Flood tags – using social media to map flood risk - Working with local actors like the Philippine Red Cross, the project combined natural language processing and flood modeling to improve risk information via social media activity, presenting the information in standardized maps, tables and graphs, to effectively support response and preparedness procedures. See here for more information.
Web map services to improve real-time flood data in Africa. The Dartmouth Flood Observatory (DFO) has developed a set of digital products to provide decision-makers and local planners with accurate quantitative maps of long-term flood risks. Portal link here. These measure, at daily intervals, surface water extent by utilizing sensors aboard satellites launched by NASA and the European and Japanese space agencies. The development of Web Map Services through this project to improve access, query and visualization of near real time and historical global flood data was in used during the recent flooding in Texas caused by Hurricane Harvey. All major U.S. news outlets, including CNN, NYT, Wall Street Journal, as well as the Red Cross, FEMA and the White House used DFO water extent data products. The tool was also accessed by users in Bangladesh and India during the August 2017 floods. In September 2017, following significant flooding in Niger, the World Food Program requested flood extent data from DFO. This data was used to map the flooding and make decisions with respect to response operations.

Real-time urban flood risk data via cellphone network analysis.
The project provides an alternative, innovative, and affordable solution for developing countries, using mobile telecoms networks as a cost-effective alternative to weather radar. This method exploits radio waves attenuation caused by rain. Based on the loss of signal on the cellular network, rainfall can be accurately monitored throughout the network. In Africa, where the mobile phone network is dense and growing, this method offers an unprecedented potential for accurate and real-time rainfall monitoring, especially in urban areas where the network is extremely dense. With this new technique, a hydrological model was developed for Ouagadougou city to provide a Flood Early Warning System for decision makers. The team will continue investigating and developing potential collaborations to help scale the concept to other cities in the Sahel and beyond. See here for more information. This work was reported in the Economist in Sept 2017– see here. IRD’s project is currently being replicated by the cell phone company Orange in Mali (with Korean funds) and in Cameroon (with UN GPSSD funds).

Overall, this output is assessed as an ‘A+’ – moderately exceeded expectations.

Summary of responses to issues raised in previous annual reviews (where relevant)
Previous recommendations largely covered:
The need to find ways of better joining up the GFDRR funded projects, outputs and partners with the wider SHEAR work, ongoing and future, and to support the knowledge broker in this role.	This is an ongoing area of work. The SHEAR programme-wide Knowledge Broker has been appointed relatively recently as has the NERC-co-funded component consortium coordination team. Both are now fully operational and have established links with GFDRR.
The need to encourage the active consideration of gender in risk identification, outreach and capacity development plans. Although progress has been good and Phase 2 will have an increased focus on gender integration, it will be important to ensure that this issue remains a priority.	This has remained a priority for both DFID and GFDRR over the year. Both phase 1 and phase 2 projects have been scrutinised with a gender lens during the application and selection process and a number have specific gender requirements.

Recommendations

1. To ensure that the newly-instated Knowledge Broker and Consortium Coordination Team effectively enable communication between SHEAR-supported researchers and publicise this ground-breaking research externally, for example through a programme website. Ongoing.
2. To build on the GFDRR CF2 recommended risk data schema pilot study in Tanzania, through support of a number of additional ‘use cases’, to illustrate the application of open source risk data in a range of diverse locations and risk-settings, from April 2018.
3. To complete the commissioning of research projects under the ‘Disaster risk financing’ NERC Announcement of Opportunity, within a new Memorandum of Understanding between co-funders – December 2018.

Output Title	Improved understanding of user needs, feasibility and roadmap for delivering more accessible and coordinated risk data and tools for developing countries.
Output number per LF		2	Output Score	A+
Risk:		Medium	Impact weighting (%):	5
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Shared vision on the needs of users and roadmap, supportive partnerships and set of recommendations on next steps	Convene at least 3 consultation workshops leading to a working group to deliver the report. Publication of high-profile joint report with shared vision on the needs, recommendations and options by November 2015.	Exceeded. Six consultations were held over the period of December 2014 – May 2016. Scoping involved a literature review, interviews and consultations across 5 continents plus an open call for contributions launched via the Understanding Risk Community site and through the GFDRR and DFID networks which resulted in all, 26 submissions. / Furthermore, two online surveys of various government counterparts globally were conducted – the first to understand how risk information is accessed and used (22 users responded). The second survey sought to capture the risk community’s views on the value of various actions related to risk data, models, platforms, and communication (36 users and providers of risk information responded). / The findings of the consultations, written contributions and the surveys and polls was synthesized in the ‘Solving the Puzzle: Innovating to Reduce Risk publication’ (see report here. The Report was reviewed by the Disaster Risk Management Community and a final Executive Summary and Infographic were launched in August 2016.
Demonstration (pilot) activities delivered, informing the long-term roadmap	Scoping report on track to deliver recommendations on pilot projects	Met. Based on the recommendations from the Scoping Report, three pilot project activities were launched under the CF. The winning firms – British Geological Survey (BGS), the Global Earthquake Model (GEM), and University College London (UCL) – were awarded contracts in February - March 2017. / An inception workshop to bring the consortia together was held in Pavia, Italy in April 2017. This was followed by an industry workshop held in London in July 2017. / Draft data frameworks are expected to be received by mid-Nov 2017, with the final products delivered in March 2018. / A user-friendly data exploration tool will be developed to allow developing country decision-makers to visualize and query the data from the pilot projects. / A final workshop, where the data frameworks will be presented to decision-makers, will be held in Tanzania in March 20-23, 2018.

Key Points

Following the completion of the scoping report, “Solving the Puzzle: Innovating to Reduce Risk”, a competetion (referred to here as ‘Challenge Fund 2’) was run, covering four main ‘challenge areas’ prioritised in the report:

- Challenge 1: Hazard scenario datasets;
- Challenge 2: Global open exposure data repository frameworks;
- Challenge 3: Open vulnerability function datasets and;
- Challenge 4: Understanding user needs

84 proposals were received, with winners selected for the first three challenge areas. Proposals submitted to Challenge 4 failed to adequately respond to the challenge area and a decision not to fund any in this area was taken jointly with DFID. Winners were: the British Geological Survey (BGS) for Challenge 1; the Global Earthquake Model (GEM) for Challenge 2; and, University College London (UCL) for Challenge 3.

The three pilot projects were launched in Africa and South Asia, focusing on critical areas identified in the report - namely, to expand the effort to decrease disaster risk management costs and increase resilience by developing a framework that facilitates a multi-hazard view of risk. The three consortia representing leaders in risk assessment are collaboratingto develop a data framework. The initial focus is on developing detailed data for Tanzania with other efforts in countries such as Bangladesh, Kyrgyzstan, and Nepal. This work aims to develop the first-ever openly available multi-hazard risk data in data poor regions. This framework may form the foundation for future multi-hazard impact and risk assessments for example, a team in Tanzania will map densities of residential areas and assess building materials used in order to construct accurate exposure and vulnerability models for future risk assessments.

Though independently contracted, the consortia are working together to ensure that the data schemas produced are internally consistent. An inception workshop held in April 2017, provided the consortia with an opportunity to meet and discuss technical matters pertaining to the frameworks.
The consortia reconvened in July 2017 through an industry workshop organized by UCL in London at XL Catlin (global re-insurance company). The meeting provided insurance, catastrophe risk modeling specialists and NGOs involved in DRM with an opportunity to review and provide feedback on the proposed design of the data frameworks to ensure industry buy-in. Two members of the consortia – BGS and UCL – also presented their work to the Tanzania World Bank Country office during a field mission in Tanzania in September 2017.

Through internal meetings with the consortia during the London workshop, GFDRR recognized the importance of developing a data exploration and visualization tool to support the work produced by the consortia. The data exploration tool will allow developing country decision-makers with a user-friendly means to visualize and query the data emerging from Challenge Fund 2. GFDRR published an expression of interest (EOI), and the team are in the process of selecting a winner from the technical and financial proposals received. The next step is to award the winning firm with a contract to develop the data exploration tool, which will be delivered in March 2018. The results of the three pilot projects will be presented at a closing workshop targeted at decision-makers from the region in Tanzania in March 2018, which will include a capacity building workshop to use the data delivered under this program.

Overall, this output is assessed as an ‘A+’ – moderately exceeded expectations.

Summary of responses to issues raised in previous annual reviews (where relevant)

DFID management team to maintain an ongoing overview on progress with the pilot work and ensure this aspect is effectively captured in routine M&E and learning strategies etc, including in the work of the Knowledge Broker and CCT. Ensure that findings and lessons feed back in the wider SHEAR initiative and inform broader DFID and international investments on risk data and modelling, including through the new PSD risk insurance initiatives.	The DFID management team has participated in the 2nd consortium workshop held at XL Catlin and have been in regular contact with the GFDRR team. Discussions are at an advanced stage on joint work with PSD as proposed. Ensuring the active engagement of the Knowledge Broker with the GFDRR team is underway.
Strengthen links between the three SHEAR funding components. DFID, NERC and GFDRR teams to review the plans for the setup of a programme wide Knowledge Broker and Consortium Coordination Team and agree away forward by April 2017 and if possible establish a Knowledge Broker by September 2017.	KB and CCT now fully established and operational.

Recommendations

1. To ensure that the newly-instated Knowledge Broker and Consortium Coordination Team effectively enable communication between SHEAR-supported researchers and publicise this ground-breaking research externally, for example through a programme website. DFID, NERC and KB/CCT teams. Ongoing.
2. To build on the GFDRR CF2 recommended risk data schema pilot study in Tanzania, through support of a number of additional ‘use cases’, to illustrate the application of open source risk data in a range of diverse locations and risk-settings, from April 2018. DFID and GFDRR teams. Agree use case funding and approach by end December 2018.
3. To complete the commissioning of research projects under the ‘Disaster risk financing’ NERC Announcement of Opportunity, within a new Memorandum of Understanding between co-funders. DFID and NERC. By December 2018.

Output Title	Improved understanding of risk and more reliable predictions of hazards like floods, droughts and landslides across SA and SSA, evaluated by ‘honest broker’
Output number per LF		3	Output Score	A+
Risk:		Low	Impact weighting (%):	35
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Advances in risk assessment, monitoring and forecasting: new methods, more comprehensive assessments and increased robustness and reliability	5 working papers.	Met. A number of reports and publications in this area have been produced from SHEAR: / 2 peer-reviewed journal papers from the SHEAR research component, plus a number of other outputs such as conference presentations. / work commissioned on big data: a report (Climate Change Resilience in the Age of Data: Opportunities, Challenges, and Requirements ; and realising the benefits for developing countries. / Work on short to medium-term forecasting of climate events (including El Niño / La Niña) continues to progress well. This includes: continued delivery of monthly outlook analyses reports produced by the University of Reading and QA’d by the UK Met Office and DFID. / Tailored reports for DFID Ethiopia and Somalia on the possible impacts of La Niña. / A 5 country review was undertaken to assess the relevance and utilisation of the El Niño outlook analyses reports, and broader use of forecasts in the El Niño response.

		With joint funding from NERC, a rapid research commissioning exercise was completed focusing on impacts of El Nino. This resulted in 99 applications submitted from which 14 projects have been commissioned.
Improved understanding of multi-hazard risk in two regions (risk maps, multi-hazard risk assessments)	Research methodologies devised.	Met. Projects commissioned (see above) examine floods and drought in both Africa and Asia. / Work programmes are well established and operational. Assessment at this early stage suggest the work is on schedule against workplans.
Greater reliability of sub-seasonal to seasonal forecasts of drought and flood risk across two regions of Sub-Saharan Africa	Quantification of current levels of reliability.	Partially Met. The four commissioned projects were selected through a robust peer review and selection process. It is currently too early to assess progress on improving skill or provide confident assessments of reliability at this stage.
Strengthened systems to track and predict changing risk from natural disasters to enable earlier interventions in two countries	Research methodologies devised.	Met. An earlier project focused on building Nepali capability in monitoring and risk assessment of landslides is making good progress in helping Nepali authorities better assess and map risk. This project, led by the University of Durham and extended in duration and scope during 2017, is working closely with the Nepali National Reconstruction Authority (NRA), UNOPS and local NGOs. The project has developed and run bespoke training courses and events in the use of new technologies and approaches to enable better response planning and actions. / The main NERC co-funded research consortia are currently in their first full year of operations. Progress on research methods and workpackages are largely on track, though there have been some delays in 2 of the projects, related in one case to a partner in country not meeting due diligence requirements and in the other due to initial administrative delays in formal grant arrangement with a knock-on impact on setting up of formal arrangements between partners within the consortium. / A new SHEAR co-funded Disaster Risk Finance research call was issued through NERC in summer 2017, with proposals received in September and work to begin in early 2018. The goal of the work is to pair academic risk researchers with disaster risk financing organisations to deliver analysis of mutual use to both.
Developing country actively engaged in research projects and SHEAR contributing to capacity development	At least 5 developing country research institutions involved in SHEAR research consortia and AI projects.	Exceeded. The 4 SHEAR Research programmes include 13 developing country institutions of which at least 5 have a primary interest in research.

Key Points

The main research consortia competitive call was successfully concluded with 4 research consortia grants commissioned; 2 covering Africa and 2 covering Asia. Fifty eight outline proposals were submitted in response to the initial announcement of opportunity, 15 were shortlisted and invited to submit a full bid application, with 4 eventually commissioned. These (listed below) have now been funded and have started work. A kick-off meeting was held between DFID, NERC and the research leads or nominated representative of all four consortia in September 2016.

Project	Principal Investigator / institution
Citizen science for landslide risk reduction and disaster resilience building in mountain regions (Nepal)	Dr W Buytaert, Imperial College London, Civil & Environmental Engineering
Landslide Multi-Hazard Risk Assessment, Preparedness and Early Warning in South Asia: Integrating Meteorology, Landscape and Society	Professor BD Malamud, King's College London, Geography
FATHUM: Forecasts for AnTicipatory HUManitarian action (SSA)	Dr E Stephens, University of Reading, Geography and Environmental Sciences
Towards Forecast-based Preparedness Action (ForPAc): Probabilistic forecast information for defensible preparedness decision-making and action	Professor MC Todd, University of Sussex, Sch of Global Studies

Ongoing work on ‘Climate Outlooks’ – SHEAR continues to support monthly climate forecast summaries for Africa, Asia and a global outlook (with a focus on the Caribbean, MENA and Overseas Territories) – see excerpts from the October issue below. These are commissioned from the University of Reading and are quality assured by the UK Met Office Hadley Centre and CEW staff. The Climate Outlooks are issued jointly with CHASE HEWN notices (Humanitarian Early Warning Notes) which are widely distributed across DFID. This work originated from earlier responses to El Niño and La Niña, which had been successful in helping DFID better plan and respond to the impacts of these events.

In addition to the current Climate Outlooks, the programme has supported additional work to review the use of these and other advisories and to assess the relevance and utilisation of the El Nino outlook analyses reports, and broader use of forecasts in the El Nino response. The Red Cross and Red Crescent Climate Centre was commissioned to lead a 5 country review which was delivered in Jan 2017. Overall the report found forecasts and messaging to be timely and credible, but noted that stakeholders expressed a desire for more consistent and impacts-relevant information in addition toassistance with interpretation. There is increasing demand for medium-term climate/weather forecast information from within DFID and further work with the University of Reading is underway to improve the relevance and communication of information, alongside improved representation of more accurate climate models for the East Africa region. A survey of users and DFID Advisers to help feed this work is underway. Initial findings from this work are expected in December 2017 and a final report is expected in Jan 2018.

The SHEAR A&I component (through which a number of the above products were commissioned) has to date largely been operating as a ‘responsive fund’ with circumstances in year 1 being such that responding to ‘events’ (such as the Nepal earthquake and El Niño / La Niña) has meant that budget planning has been particularly difficult with demand being extremely ‘lumpy’ and highly unpredictable. It will therefore be important to establish suitable internal guidance on handling this issue so that the programme remains able to respond to priority demands in the future.

Of the 2 Projects originally commissioned in response to the 2015 Nepal earthquake, one, focused on monitoring and risk assessment of landslides has been extended and expanded with the support of DFID Nepal. This project, led by the University of Durham, is successfully engaging with the National Reconstruction Authority (NRA), UNOPS and the DFID Office to build capacity at the NRA. The programme has developed and delivered a bespoke 2 week training course for the NRA in landslide assessment, mapping and modelling and including bespoke training on satellite image access, processing, the use of UAVs, 3D terrain modelling for landslide monitoring, landslide mapping and data base analysis. This work has attracted intrest from the New Zealand Ministry of Business, Innovation and Employment in relation to incorporating learning from Nepal into a £4m Endeavour project on post-earthquake landslide risk in New Zealand. The project, is also developing links with a number of other initiatives.

Overall, this output is assessed as an ‘A’ – met expectations.

Summary of responses to issues raised in previous annual reviews (where relevant)
There were no recommendations relating to output 3.

Recommendations

1. DFID team to track progress of the current review into the utility and impact of the various El Niño related products and ensure the findings are fed back into the broader SHEAR Knowledge Broker and lesson learning system. DFID CEW. Ongoing.
2. DFID team to integrate work on forecast-based humanitarian action with ARD (WISER) and CHASE work and ensure coherence with HIEP business case on shock-responsive development. DFID CEW and ARD teams. Ongoing.

Output Title	Better understanding of what works in getting the right knowledge and tools to the right people in the right way, demonstrated on the ground with impact.
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
New understanding of risk communication and and factors determining the impact of science in disaster resilience and response	Consortia have in place strong teams to deliver new insights into risk communication. Learning from SHEAR Apps projects integrated to deliver new understanding. / .	The 4 consortia grants were commissioned through a robust NERC-managed process following astandard multi-stage research council process. The SHEAR Moderating Panel was confident that the consortia possess the right skills and capabilities to deliver project outcomes. / Of the first GFDRR managed challenge fund projects 8 have recently completed and delivered their final reports, the remainder are due by the end of the year. A learning report is currently in preparation and is due early next year.
Four pilot studies co-designing products and tools with users and demonstrating application and impact on the ground	Consortia to deliver at least four pilot projects with good coverage of regions, applications and hazards, strong partnerships and methods.	Consortia have only recently started work. However, 13 of Challenge Fund projects were co-designed with well over 100 local users and 4 pilot projects were launched in Africa and South Asia Region in August 2016 under the 2nd round of the Challenge fund, covering the following areas: hazard scenario datasets; global open exposure data frameworks; open vulnerability function datasets and; understanding user needs.
New evidence on the value of improvements in risk information and warnings for decision making	SHEAR KB and Consortia devised methods to quantify and demonstrate the value of information to decision making	Consortia research plans include work on value of information. SHEAR is also leveraging WISER research in this area.
Establishing best practice in co-design and co-production and mainstreaming this into all projects	Methods by SHEAR KB to learn from and evaluate co-production activities and implementation started with consortia.	As noted earlier a decision was taken jointly with NERC to delay the establishment of the SHEAR KB function until after the awarding of the main research projects so as to allow the leads of the 4 main research projects to be part of the decision making on the setup. KB now operational and performance will be reviewed at the end of the pilot year.

Key Points

Consortia have only very recently started work, so it is too early to make any robust assessment at this stage. However, selection was made through a robust, standard NERC research programme commissioning process, a key element of which was an assessment of the capability of the team to deliver new insights into risk communication.

Overall, this output is assessed as an ‘A’ – met expectations.

Summary of responses to issues raised in previous annual reviews (where relevant)
The recommendation from last year relates to the establishment of the SHEAR Knowledge Broker unit, which would take on the task of compiling the tools, innovations, and lessons learned from the rapid response and AI projects to ensure that these are integrated. During 2017 the KB contract was agreed (Practial Action and Red Cross/Crescent Climate Centre); their work began in July and they are already facilitating the process of knowledge exchange within the programme and externally, with a dedicated www.shear.org.uk website currently being designed.

Recommendations

1. SHEAR Knowledge Broker and Consortium Coordination Team to ensure regular communication across the broader SHEAR programme, on research results, lessons learned, etc. (ongoing) and to communicate the research programme externally, via an agreed website (early 2018). KB and CCT teams with support from DFID and GFDRR.
2. DFID to ensure SHEAR work is aligned with WISER, UPGro and FCFA, which are also conducting research closely related to this on climate services and climate change adaptation, respectively. DFID CEW. Ongoing.
3. DFID to ensure relevant results from the SHEAR programme feed into the DRR technical advisory facility funded by DFID: the Centre for Global Disaster Protection. DFID CEW. Ongoing.
4. 2015/16 El Nino projects (co-funded with NERC) to be integrated through a final programme workshop (May 2018) and for the findings of the broader programme to feed into a lesson-learning and best-practice final report, to be communicated across the DRR research community by the KB. DFID, NERC and KB teams. By end 2018.

Output Title	Effective management of the research programme, including M&E of impact and value for money, and effective management of capacity building opportunities
Output number per LF		5	Output Score	B
Risk:		Low	Impact weighting (%):	10
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of recommendations by Independent Advisory Group leading to measures taken to improve programme	This indicator is no longer relevant – see opposite.	DFID and NERC took a decision in 2016 to move to a more ad-hoc approach to advisory inputs rather than having a standing group. This was because for the SHEAR research component, advisory input is built in at early stages of the commissioning process (through the peer review and independent panel system).
Capacity of 30 users enhanced	Establish tracking system and target users.	This is a task for both the individual research projects across all components and for the SHEAR Knowledge Broker, the establishment of which occurred in July 2017. The Knowledge brokers are currently developing their capacity building strategy including an approach to M&E. However, all SHEAR projects are encouraged to focus on users and user needs as well as to work proactively to build capacity. As recorded against all outputs above, numbers of users benefiting from capacity building is substantial.
Cross-programme outreach: including briefings, stakeholder workshops	2 cross programme reports	As previously explained, DFID and NERC made a decision to hold back setting up a Knowledge Broker and consortium coordination team until the main research projects had been established. This has been completed and both the KB and the CCT have held kick-off meetings and events and have reached out to the range of actors involved across the SHEAR programme as a whole. For example, one of the SHEAR El Niño projects led by the University of Leeds has been helped to establish contact with the Red Cross projects in Malawi (and FAO) and has requested a team from the Netherlands Red Cross to be part of the advisory committee for the Catalyst project. This is a good example of how the KM is linking research and application in practice. / Research component projects have established web-sites and information / comms products aimed at stakeholders. In the case of the FATHUM project, this has resulted in Zambia’s Water Resources Management Agency (WARMA) requesting to be involved with view to applying similar methods to floods in Zambia.

Key Points
The establishment of the Knowledge Management and Consortium Coordination team is an important mechanism contributing to the achievement of this output. Now that both are established and fully operational it is expected that progress against this output will accelerate. Overall, this output is assessed as an ‘B’ – met expectations. The KB role is currently contracted for one year and will be renewed / revised based on a review of performance.

Summary of responses to issues raised in previous annual reviews (where relevant)

Previous recommendations largely covered the same issues as reported under Output 1 – the need to find ways of better joining up the GFDRR funded projects, outputs and partners with the wider SHEAR work, ongoing and future, and to support the knowledge broker in this role.	A meeting was convened during 2017, bringing together the SHEAR Knowledge Broker, NERC and GFDRR, to exchange information and details regarding work being undertaken. The KB are taking forward continued communication between the different strands of the programme. DFID RED-CEW members and NERC will meet with the KB and every 1-2 months, to track progress and to allow the KB team to highlight any concerns or potential obstacles to research progress within DFID countries.
Also to encourage the active consideration of gender in risk identification, outreach and capacity development plans.	NERC and the SHEAR Knowledge Brokers have communicated this to the consortia research teams and DFID have done so with the GFDRR and other teams.

Recommendations

For the RED-CEW team to meet regularly with the Knowledge Broker, to track progress and facilitate any relevant communication between DFID country/regional offices and the research teams, as required. DFID and KB teams. Ongoing.

For the programme website to be delivered (in early 2018) and tested for how well (and logically) it presents the research across the entirety of the SHEAR programme, also making links to relevant external stakeholders and introducing the programme and underpinning rationale for the layperson. DFID, NERC and KB teams. By early 2018 and ongoing.

The Imperial-Sussex-led NERC studentships to be agreed (in early 2018), ensuring that at least half of these are for researchers based in developing countries, with agreement in place between NERC and the supervisors, to adequately track progress. DFID, NERC and relevant PI. By early 2018.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
Key cost drivers are still seen as those identified by the Business Case. This includes all implementing activities, such as monitoring and evaluation, management and administrative costs.

VfM performance compared to the original VfM proposition in the business case
As outlined in the Business case, value for money is ensured though several processes:

- At the application stage value for money (VFM) is a stated assessment criterion in the scheme specification and applicants are required to fully cost all elements of their proposed research and provide detailed justification for each item of expenditure. Peer reviewers and panel assessors are asked to consider VFM as part of the grant assessment and panel members are asked to consider the requested costs to ensure that they are fully justified when making final funding recommendations.
- At the grant award stage all costs are subject to detailed scrutiny by DFID (if directly procured) the NERC Secretariat (for NERC co-funded components) and by GFDRR (for the World Bank led component). Any unjustified or excessive costs may be removed from the budget.
- Grants are only held by institutions which have passed RCUK or GFDRR recognition processes, which include checks on financial management and capacities. Details of the information organizations are required to provide as part of the Due Diligence process are communicated by funders prior to recognition.
- Grants are awarded with RCUK or World Bank standard T&Cs which include financial management and reporting requirements. In addition, the RCUK-wide Funding Assurance Programme conducts checks at an institutional level (see NERC’s annual report and accounts - http://www.nerc.ac.uk/latest/publications/strategycorporate/annualreport/annualreport/ ).
- Where awards have additional project delivery partners the NERC grant is with the host institution. The host institution will set up ‘sub-contracts’ with any partner organisation. The host organisation will thus take the financial responsibility of tracking partner spend and the risk of any overspend or default

Apart from immediate emergency response support following the Nepal earthquake, all funding has been awarded on a competitive basis which will drive Value for Money. NERC is also contributing £6m to the programme as well as the leveraging of NERC systems in commissioning and management of the Research, which further drives value for money. Work commissioned though the GFDRR managed Challenge Fund has also leveraged around £3,890,126 in cash and kind.

The major spending so far on project has been through GFDRR (Challenge Fund) on SHEAR Apps, through NERC on SHEAR Research and direct through DFID on the Applied and Innovation interventions. The major costs for GFDRR are on software development, multimedia, data gathering, data mining, workshops and application developments. NERC associated costs on the main Research grants are on research staff costs and travel and subsistence. The A&I costs are mainly Research staff, travel and subsistence and Equipment.

The DFID Research and Evidence Division budget covers administrative costs of managing the programme on a day-to-day basis. A separate budget line was established to cover M&E costs, including independent reviews (Mid-term if required and the End of Programme Reports and Independent Impact Review) and other M&E reports as required by the governing bodies.

Assessment of whether the programme continues to represent value for money
This programme continues to represent good vfm. The Challenge Fund commissioning was undertaken through an open global competition. The use of the robust RCUK peer review systems for competitive research calls will deliver high quality research under the SHEAR research component.

Quality of financial management
DFID has received reliable and accurate financial information from NERC over the reporting year which has allowed for stable and accurate forecasting which matches the agreed spending profile.
All planned spending on GFDRR has been completed.

Date of last narrative financial report	24 October 2017 (NERC)
Date of last audited annual statement	13 July 2017 (NERC)

E: RISK (½ page)

Overall risk rating: Moderate
Review of progress thus far suggests no change in the overall risk assessment from last year.

Overview of programme risk
The main risks identified with comments against each are noted below. Arrows indicate change from last assessment.

Risk	Probability	Impact	How risks will be minimised/mitigated	Comments
Insufficient proposals received in response to calls.	Low	Moderate	The use of a global open calls system of GFDRR Challenge Funds and of the NERC consortia rounds attracted a high level of interest and therefore competition. If, however, this process fails to yield a suitable proposal or a minimum acceptable number of proposals (for example in the NERC catalyst round), the call is normally reviewed and re-advertised.	Both initial competitive (NERC and GFDRR managed) calls elicited good responses from ‘the market’, with 58 outline proposals submitted in response to the NERC managed call. Of these 47 progressed to stage 2 and 15 of these were then selected to proceed to full proposals. 4 were eventually awarded and contracted. Given the original expectation was that there would overall be a larger number of main research grants funded, a review was undertaken and it was decided that the best approach would be to issue a call for ‘catalyst’ grants to cover the remainder of the available funding. This is currently underway, with an expected completion early next calendar year. / The GFDRR Challenge Fund round 1 call attracted substantial interest with 264 applications received from 2229 organisations covering 70 countries with 15 projects being eventually selected for funding. Round 2 of the CF resulted in 3 proposals selected. / The Disaster Risk Financing research call attracted 22 predominantly strong proposals, with funding available for approximately 9. / No change to rating.
Research proposals are of poor scientific quality, poor multi-disciplinarity or poor development relevance and impact quality	Low	Moderate	All bids will be assessed through a strict and transparent process and making use of NERC’s and GFDRR’s well-established systems. Proposals of poor scientific and development relevance or impact quality will receive a lower or no- recommendation for funding.	This has not been the experience thus far. In the case of the NERC managed call, a workshop for invited proposers was also held to both emphasise the multidisciplinary requirement and that of development impact, alongside that of research excellence. As noted in the mitigating actions, this is in addition to the standard Research Council and GFDRR competitive selection processes. / No change to rating.
Projects fail to address user needs and deliver innovation and development impact (SHEAR Apps)	Medium	Major	GFDRR (the implementing partner for SHEAR Apps), have considerable expertise in this area and have a very broad stakeholder reach. In addition, the project evaluation criteria will identify projects where user needs and delivering impact are central to the design. However, R&D and innovation can be unpredictable and risky. Regular reporting mechanisms will be used to monitor the development of the research, and if there is any indication that the stated objectives were not being met then remedial action would follow. For the GFDRR challenge fund and applied projects, projects will be numerous, small and short-term, spreading the risk and allowing DFID to learn and respond. Larger projects may also include a payment by results element.	Results to date have showed promise, though for many these are at relatively early stages in the impact pathway. As noted on the left, GFDRR have considerable expertise in this area and have performed well to date. / No change to rating.
Lack of coherence of activities or duplication across activities (including duplication with other initiatives)	Low	Moderate	The RPCs will focus on different regions so high coherence is critical and the risk of duplication is lower. / Selection process included stages which examine issues of coherence / duplication. / The KB and CCT facilities will monitor activities to identify any duplications, or potential synergies and report them to the PEC.	The Knowledge Broker and consortium coordination facilities are now in place and fully operational. Early assessment suggests that this is working well. / The NERC catalyst grants AO specified that preference would be given to proposals covering alternative regions/issues already being covered within SHEAR, to minimise the chance of duplication within the programme. / No change to rating
GFDRR does not make appropriate linkages to user communities and humanitarian community resulting in limited impact.	Medium	Major	The independent advisory group will have appropriate membership of the user and humanitarian community to mitigate this risk. In addition, the challenge fund will be phased and unsatisfactory impact in the first and second phases will result in adjustments or non-continuation.	Outputs thus far suggests that linkages are good across a range of user communities. / A small number of GFDRR risk database use cases will be supported in 2018, subject to receiving a strong proposal and we will then take stock, deciding whether to contribute further to GFDRR. / No change to rating.
A&I fund ‘demand’ has been shown to be very ‘lumpy’ making budget planning difficult.	Medium	Moderate	It will be important to establish a balance between budget planning, predictable draw-down and the ability to respond to unforeseeable priority demands in the future, the level of which cannot be predicted. Currently, the budget has been allocated pro-rata across remaining years.	Will need to keep this issue under close review. / Impact downgraded from Major to modrate, given the relative maturity of the programme and the remaining time on the programme.
Delivery chain risks, including fiduciary, governance and reputational.	Medium	Moderate	The programme has three core strands: one managed directly by DFID and the remaining two managed by different partners (NERC and GFDRR). A number of mechanisms have been put in place to ensure appropriate oversight of delivery chains (2nd tier suppliers). These include: / Ensuring appropriate due diligence of proposals at preferred bidder or equivalent stage of competition and that as part of this process a mapping exercise is undertaken; / Establishing robust governance process are in place for each component with clear reporting and accountability lines. / Robust M&E processes are in place for all sub-projects with established exception reporting procedures. / A review of this risk matrix is a formal part of the DFID annual review process.	This risk area will need to be kept under close scrutiny and will require regular engagement with partners such as NERC and GFDRR.

Outstanding actions from risk assessment
None.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The project is largely on track to the planned timeframe. The main area where there has been slippage relates to the Knowledge Broker and Consortium Coordination Team functions and fewer than expected main research grants being awarded. The KM & CCT start-up has now been addressed and both are fully operational. On the issue of main research grants, a decision was taken by NERC and DFID to utilise standard NERC smaller ‘catalyst grants’ to fill remaining gaps rather than re-run a main research project call. It is expected that a sufficient number and quality of proposals will be submitted to DFID and NERC for an independent panel assessment early in 2018.

Performance of partnership(s)
The partnerships have been performing well, though it is still relatively early stages of the programme. Both GFDRR and NERC governance and management structures and mechanisms are working well. It is still relatively early stages for the KB and CCT implementing partners, but initial signs are very positive.

Asset monitoring and control
Given the type of research it is not expected that the project will purchase significant assets, and where these are occasionally required, as in the case of one of the Nepal earthquake projects, the required assets have been borrowed from other NERC funded programmes.
The DFID project team is satisfied that both World Bank (GFDRR) and NERC asset management and monitoring procedures and rules are appropriate and being followed.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not be relevant at this stage.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
The importance of disaster resilience and early action remains unchanged since the initial design of SHEAR and the challenges are recognised in the Global Goals. If anything, recent events (El Niño/La Niña and a series of major hurricanes and flood events) have emphasised the importance of this area ofwork. It is reasonable to assume that the area of focus of the SHEAR programme will continue to grow in relevance, given both global change processes and the steady increase over time in exposure of poor people to natural hazards.

Uptake will be tracked as part of the logframe reporting over the lifetime of the programme.

The revision of the logframe with the participation of lead researchers and other parties will be completed by end January 2018. The setup and structure of the Knowledge Management and Coordination function will be finalised over the coming months. This will provide a stronger basis for ongoing M&E.

Gender Equality
SHEAR was designed before the introduction of the Gender Equality Act in 2014. However, the Business Case was clear that research and uptake strategies would need to incorporate a strong gender analysis in order to better understand the interrelationships between risk, resilience and women’s vulnerability. For example, in some natural disasters, many more women have been killed than men, underlining the differentiated vulnerability. In addition, it noted that there is some evidence that uptake can be improved through designing communications strategies that reflect potential differentiated gender roles of target beneficiaries. As a result, a strong consideration of gender equality was incorporated into the various competitive calls that have been issued through SHEAR. This is also a core role for the KB and CCT functions going forward.

GFDRR, who manage the SHEAR Apps component are guided by their 2016-2021 Gender Action Plan and have ensured gender integration is occurring in all seven Phase 2 projects. Specifically, three projects are conducting surveys which collect gender-sensitive data; one implementer is conducting a study including extensive interviews on gender dynamics as they relate to the project; and three projects are conducting gender analyses.

All four main research projects are sensitive to gender and where appropriate have integrated gender within their approaches and methods.

Monitoring progress throughout the review period

This annual review has been complied based on the following:
GFDRR annual report 2017 Vault # 207203328.
Meetings and correspondence with the GFDRR team managing the Challenge Fund.
Meetings, workshops and correspondence with the NERC team managing the SHEAR research component.
Meetings and correspondence with the SHEAR Knowledge Broker.
Ad hoc Direct and email communication with PIs of directly-procured research projects:engagement and discussion with Nepal earthquake monitoring and landslide monitoring researchers,plus discussions re continuation of the latter work with DFID Nepal; and ongoing discussion and engagement with the University of Reading led provision of monthly weather/climate forecast notes.
Downsteam partners
There have been a few changes to the Research Consortia partners during the reporting year. These are noted below.

ForPAc: Africa Population and Health Research Centre have been changed to Kenya Red Cross Society.

LANDSLIDE EVO: Dr Paul Smith, previously of Lancaster University, with expertise in probabilistic forecasting systems, will now be employed as an independent consultant on the project (this change is currently under review by NERC).