Business Case and Intervention Summary

Title: Palestinian Market Development Programme (PMDP) to Strengthen the Private Sector in the Occupied Palestinian Territories (OPTs)

Intervention Summary

What support will the UK provide?
The UK will provide a comprehensive programme to strengthen the competitiveness of the Palestinian private sector as part of its wider support to Palestinian state building efforts and the Middle East Peace Process. The Programme will provide matching grants and technical assistance to mitigate the risk associated with business development in a fragile context such as the OPTs. It will also undertake market analysis to identify and address market failures and will strengthen inward investment and transfer of ‘know how’. / The programme aims to help Palestinian firms to develop and improve 250 new products and enter 350 new markets. Over 240 companies will be expected to report improved performance on an annual basis, 96 to report increased exports and 72 to start using their own funds to develop their businesses. Overall our support will leverage a minimum of £40m of additional attributable sales by 2019. / The programme will be co-funded by the European Union for a total budget of £15.3 million over six years of which the DFID contribution will be £11 million.[1]
Why is UK support required?
What need are we trying to address? / Resolving the Israeli/Palestinian conflict is a longstanding UK international policy priority. The lack of progress on the Middle East Peace Process has exacerbated regional instability and undermined Palestinian growth prospects. In particular, movement and access restrictions imposed by the Government of Israel in the West Bank, East Jerusalem and Gaza were estimated to have cost the Palestinian economy $6.9 billion in 2010 (85% of annual GDP)[1]. / Although the Occupied Palestinian Territories’ (OPTs) real GDP growth reached 9.9% per cent in 2011[2], this was largely driven by donor supported public sector growth, and has failed to address high unemployment and high levels of poverty. Unemployment in the West Bank increased to 20.1% in the first quarter of 2012 and in Gaza, increased to 31.5 %[3] . The poverty headcount was estimated to be nearly 23% in 2009.[4]. / Sustained economic growth which helps reduce this high unemployment and poverty is a key part of Palestinian state building objectives. An economically viable Palestinian Authority (PA) is also important in political terms, so that a future Palestinian state will be a stable and effective partner for peace with Israel. Since 2007 the PA has made impressive progress with institution building, security and economic management. This has led to strong international endorsement of the PA’s institutional readiness for statehood[5]. But declining economic growth and an acute fiscal crisis could undermine these gains and public support for statebuilding. / Developing a sustainable economic base will depend largely upon the establishment of a dynamic and productive private sector. Increasing GDP will in turn increase tax revenues for the PA promoting fiscal sustainability and reducing donor dependence. However, restrictions imposed by the Government of Israel on the movement of people and access to resources, coupled with high cost and low skilled labour force has significantly reduced the competitiveness of Palestinian firms[6]. If firms are to compete successfully in domestic and international markets, they need to shift from the production of low value added, labour-intensive goods towards high value added goods and services. / This calls for the Palestinian Authority, with donor support, to create an environment that enables the private sector to flourish and innovate within (and despite) existing constraints, and which lays the ground work for a future Palestinian State. In order for aid programmes to be useful, however, Israel must take serious actions to reduce impediments to Palestinian economic development. This can only happen through political efforts by the international community that can produce lasting peace with real changes on the ground. / The UK support is needed to help firms, directly or through broader market system assistance, to raise their productivity, increase their value-added, and become more innovative and competitive. This is especially relevant to the service sector, particularly the IT-enabled, which is the least affected sector by political barriers and the most endowed given the presence of highly educated work force and entrepreneurial Palestinians. / What we will do to tackle the problem / To help increase the competiveness of the Palestinian private sector, through the PMDP, DFID will: / Provide matching grants and technical assistance to firms or consortia – under a competitive process and which specifically help firms to innovate their products/services and/or processes, and enter in to new markets. / Undertake market analysis and facilitation – to identify how specific market systems operate, what factors drive underperformance, and facilitate improved performance. This could for example include facilitating trust building between small firms and large aggregators, information exchange, access knowledge and best practice, as well as influencing a strategic demand for the matching grant component. / Provide technical assistance to key market institutions – including to the Palestinian Investment Promotion Agency (PIPA) to encourage and support foreign and local investment in the OPTs, for the establishment of a cadre of commercial representatives in key markets for Palestinian goods and services, and opportunities which help mobilize potential Diaspora investment, knowledge and technological transfer. / Alongside the PMDP, the UK will continue to help address underlying movement and access restrictions through political lobbying and additional programme work. For example, the UK is contributing technical support to the Office of the Quartet Representative (OQR) which works with the PA, the Government of Israel, international organisations and NGOs to help build the institutions and economy for a future Palestinian state. The UK has also supported the UN Access Coordination Unit (ACU) which helps improve access for humanitarian personnel and goods in the OPTs and supports international lobbying efforts aimed at improving access. / Who will implement the support we provide? / Implementation of the PMDP will be tendered to a supplier registered under DFID’s Fragile and Conflict Affected States Framework Agreement[7]. We will ensure that they deliver value for money through a set of input and output unit cost measures that will benchmark their performance against our previous project. A further contract will be awarded for programme evaluation through mini-competition under DFID’s new Global Evaluation Framework Agreement.
What are the expected results?
PMDP is expected to achieve the following Output results by March 2019: / 480 firms will have been assisted with grant or technical assistance / 350 new markets (domestic and foreign) entered in to by assisted firms / 250 new / improved products (including services) will be developed by assisted firms / 30 Business Service Providers (BSPs) will have gained recognised certification / These results will contribute to the overall outcome of improving Palestinians private sector competitiveness which will be assessed through the following indicators: / Annual number of enterprises reporting improved annual performance due to PMDP work[8] (Target: 240 by 2019) / Number of enterprises reporting increase of annual exports or first time exporters (Target: 96 by 2019); / Number of enterprises using their own funds to pay for Business Development Services (Target: 72 by 2019); / Number of net jobs directly created by PMDP (Target: 630 by 2019); / Value of additional sales attributable to PMDP (Target: £40 million by 2019) / The programme is expected to achieve wider Outcome results on the market system. These results will be identified during the inception phase of the programme and added to the Logframe and monitoring framework. / How will we determine whether the expected results have been achieved? / In addition to mid-term and final evaluations, DFID will undertake Annual Reviews and an end-term Project Completion Review (PCR) to assess progress. Reviews will assess whether targets have been achieved, confirm cost-benefit assumptions and give recommendations.
[1] The European Union agreed in principle to contribute £4.3 million to the PMDP, but formal decision is yet to be confirmed. Should the EU funding not come through; DFID will contribute the entire £15.3 million and report against the full results.
[1] “Bulletin on the economic costs of the occupation for Palestine”, A joint publication by the Ministry of National Economy and ARIJ, September 2011
[2] Ministry of Finance, Palestinian Central Bureau of Statistics and IMF estimates. - Estimates based on first three quarters of 2011 (see footnote 3 World bank Report page 39-40)
[3] IMF West Bank and Gaza – Economic Update May 2012
[4] World Bank. Coping with Conflict? Poverty and Inclusion in the West Bank and Gaza based on PCBS Palestinian Expenditure and Consumption Survey data.
[5] World Bank (September 2011). Sustaining Achievements in Palestinian Institution-Building and Economic Growth, Economic Monitoring Report to the Ad Hoc Liaison Committee
[6] World Bank, 2012 West Bank and Gaza Towards Economic Sustainability of a Future Palestinian State: Promoting Private Sector - Led Growth
[7] an arrangement that DFID has made with 41 suppliers to deliver a range of services in fragile and conflict affected states
[8] This is also a headline indicator for the Palestinian Programme Operational Plan.

Business Case

Strategic Case

A. Context and need for a DFID intervention / Political Context / The Israeli-Palestinian conflict is rooted in the 1947 plan to partition the then British Mandate Palestine into Arab and Jewish states, the subsequent establishment of the state of Israel in 1948 and the ensuing war which displaced hundreds of thousands of Palestinians as refugees. The 1967 Arab-Israeli war led to Israel’s occupation of the West Bank and Gaza Strip, and annexation of East Jerusalem. Resolving the Israeli/Palestinian conflict is a longstanding UK international policy priority. The UK strongly supports the creation, through negotiations, of a sovereign, viable and contiguous Palestinian State living in peace and security alongside a safe and secure Israel and their other neighbours in the region.[9] UK policy (in line with international law and significant international consensus) is that a two state solution should be based on 1967 borders with the Occupied Palestinian Territories (OPTs) of West Bank, Gaza, and East Jerusalem constituting the land that should form the basis for a future Palestinian state.. / DFID seeks to support UK Government policy for a successful Middle East Peace Process by helping build Palestinian institutions and promoting economic growth, so that any future state will be stable, prosperous, well-run, and an effective partner for peace with Israel. / The entrenched and highly unpredictable nature of the Israeli-Palestinian conflict and the impact of Israeli occupation mean the situation in the OPTs, and for Palestinian refugees in the region, is very fragile. There have been two violent Palestinian uprisings against the occupation, and Israel has suffered periods of bombings and rocket attacks against its cities. In recent years the internal Palestinian scene has been dominated by the conflict between the Fatah and Hamas factions, which saw Hamas taking control of Gaza by force in 2007 and the subsequent closure of Gaza by Israel. An escalation of violence in 2009 between Hamas and Israel led to significant numbers of deaths and destruction in Gaza. Another round of escalation between the same parties took place in November 2012 and left over 150 dead and more than 1,000 injured within eight days. The situation in Gaza remains extremely fragile under the recently agreed truce. The Hamas/Fatah reconciliation agreement announced in May 2011, and again in May 2012, is yet to be implemented, adding another degree of uncertainty to the internal political situation. / There have been various internationally sponsored attempts over many decades to resolve the conflict by negotiating a ‘Two-State Solution’, most notably the Oslo Accords of 1993. Most recently, the Quartet[10] have called for an immediate resumption of meaningful talks. But trust is very low between the parties, with each side accusing the other of unilateral action. The Palestinians seek recognition via the UN, and Israel continues building of illegal settlements within the OPTs and imposing movement and access restrictions that obstruct sustainable Palestinian development and economic growth. / Economic Context / There is strong international recognition of the Palestinian Authority’s readiness for statehood[11] but this readiness is threatened by an acute fiscal crisis and declining economic growth. Despite being for many years one of the highest per capita aided countries in the world, the Palestinian economy continues to suffer from major weaknesses and an increasingly unsustainable structure. The OPTs has become aid dependent and its productive sectors have been contracting. Recent signs of economic recovery and growth have been largely driven by donor supported public sector spending with few signs of robust private sector investment, except in some of the non-tradable sectors such as retail and construction. / GDP per capita in the OPTs was just $2,058 in 2010,[12] making it a lower Middle Income Country and the poorest in Middle East and North Africa region, other than Sudan and Yemen. Conflict and movement and access restrictions have led to economic stagnation, eased somewhat in the West Bank since 2007 by PA aid-supported reforms and projects. / In a recent study by the Palestinian Ministry of National Economy (MoNE) and ARIJ (2011)[13] the cost of occupation and restrictions was estimated at $6.9 bn in 2010, a staggering 85% of the total estimated Palestinian GDP. The key restriction measures in the West Bank include: / Separation Barrier: cuts the large East Jerusalem market off from the rest of the West Bank and other parts of the West Bank from each other, fragmenting the economy. The Seam Zone around the Wall limits access for farmers to agricultural land. / Area C: covers 60% of the West Bank and is entirely controlled by Israel and largely off-limits for Palestinian use. It is a significant break on economic growth, as much of the agricultural land and valuable natural resources are in Area C, especially in the Jordan Valley, and It prevents the growth of urban centres. / Internal checkpoints: these increase transport costs and uncertainty, reducing trade between urban centres. According to the UN Office for the Coordination of Humanitarian Affairs (OCHA) Movement and Access report of September 2012, there are 542 documented and mapped obstacles (checkpoints, dirt mounds, barriers, gates..etc) blocking Palestinian movement within the West Bank. / Border controls: trade between the West Bank and other countries is constrained by border controls that raise costs and cause delays, and restrictions on imports of ‘dual use[14]’ goods cost at least 5% GDP per year.[15] It is also hard for Palestinians to work in Israel and for foreign investors (particularly of Palestinian descent) to visit. / Water: Palestinians have access to only 20% of West Bank water resources, the lowest access to fresh water rate in the region.[16] / In Gaza, the key restrictions include : / Imports: in 2010 Israel moved from a list of permitted goods to a list of specific prohibited ‘dual use’ items (as for the West Bank), resulting in an increase in imports into Gaza. However, imports of construction materials are still blocked (except for humanitarian organisations) and so are having to be sourced from Egypt through Hamas-controlled tunnels. / Exports: Only a limited range of cash crops were allowed to be exported to third countries (other than Israel and the West Bank) until 2011 when Israel allowed other sectors such as garments and furniture to also export. But the ban on any transfer of goods to Israel or the West Bank continued. This is a major constraint to growth in Gaza which has traditionally exported to Israel and transferred large volumes of products to the West Bank. Exporting to third countries would require a different set of quality standards which will take a long time to develop in Gaza. / Agricultural land: since late 2008 Gazans have been prevented from accessing land up to 1,000-1,500 meters from the Green Line[17], representing 35% of Gaza’s agricultural land.[18] / Fishing: also since late 2008 Gazans have been prevented from accessing sea areas beyond 3 nautical miles from shore, representing 85% of the maritime areas they are entitled to under the Oslo Agreement[19]. / Economic conditions in the OPTs are also closely tied to political developments as a result of the ongoing conflict and occupation. Israeli movement and access restrictions in the West Bank, incursions, and its almost complete control over Area C (60% of the West Bank), East Jerusalem and the Gaza Strip act as major impediments to economic growth and private sector development[20]. In 2011, the OPTs economy grew by 9.9% due to high growth in Gaza which offset a slowing of growth in the West Bank. Without further easing of restrictions the growth will remain unsustainable, unbalanced, and with limited benefit for poor people in the OPTs. The IMF estimate that if there is significant easing of movement and access restrictions, growth in the OPTs could reach 7-10% per year for 2012-14, but if the status quo is maintained, growth will be under 4%,[21] only slightly higher than the population growth rate of 2.9%. / The PA is also facing serious budgetary uncertainty, which has the potential to become a serious threat to stability. The Palestinian Authority (PA), has very limited control over its finances, given the unpredictable nature of aid flows (39% of its recurrent budget in 2011), and the fact that 66% of its revenues (43% of its recurrent budget in 2011) are transferred to the PA via Israel, which collects them on the PA’s behalf.[22] Both sources of finance are vulnerable to actions taken by Israel. For example in response to Hamas/Fatah reconciliation, and the Palestinian statehood bid at the UN in 2011. Future Israeli actions could thus lead to either rapid deterioration or continued improvements in conditions in the OPTs. The situation in Gaza is particularly fragile and a future humanitarian crisis cannot be ruled out. / Multiple challenges thus face Palestinian development efforts, whereby economic growth must proceed under: (i) adverse conditions of conflict; (ii) intensified, systematic mobility restrictions; (iii) lack of national sovereignty; (iv) limited policy space available to the PA to manage the economy; and (v) systemic dependence on foreign aid and volatile revenue streams. The UK’s development support will need to remain flexible to respond to major changes in the political and operating environment over the course of the coming years. / Need: Supporting Economic Recovery Through Private Sector Development / Why promote the Palestinian private sector? / Within the above context, promoting the Palestinian private sector is important to achieve the DFID Palestinian programme two Operational Plan priorities: / 1. Negotiated outcome enabling a viable, contiguous and democratic Palestinian state, alongside a secure and prosperous Israel: Economic growth can help to promote the Middle East Peace Process through three routes: / Maintaining public support for the Palestinian Authority and the moderate Palestinian leadership’s commitment to non-violence and a negotiated solution to the conflict, through demonstrating tangible improvements in life on the ground / Reducing risks of instability and conflict: growth and reduced unemployment can contribute to addressing some aspects of disempowerment and anger that risk generating instability and violence in the West and Gaza both against the Israeli occupation as well as the Palestinian Authority, which would carry high human and economic costs. Recent research has found a link between unemployment and political violence, concluding that employment restrictions explain roughly one fifth of the total number of Palestinian fatalities during the Second Intifada.[23] / Reduced aid dependence of the PA: the effective functioning of the PA is key for statehood, and is threatened by a lack of fiscal sustainability due to insufficient economic growth and therefore revenues, and a heavy reliance on public sector employment. This makes the PA highly dependent on volatile aid flows. Evidence suggests that for every £1 in additional economic growth generated in the OPTs, 88 pence in additional revenues is brought in for the PA.[24] / 2. Reduced poverty and vulnerability of Palestinians in the OPTs and the region: a recent assessment of poverty in the OPTs by the World Bank[25] found that unemployment was the major cause of poverty, and that economic growth was strongly correlated with poverty reduction. There is also strong evidence that economic growth in the OPTs is strongly correlated with employment growth.[26] / As outlined earlier, economic growth in the OPTs is not sustainable because it is driven by aid, not by private sector growth. Achieving the above Impacts sustainably therefore requires promoting the Palestinian private sector, which is largely uncompetitive but highly resilient and with great potential. / Why improve the competitiveness of Palestinian firms? / There are two main issues limiting growth of the Palestinian private sector: / a) Movement and access restrictions: as outlined above, these are the most important constraints on private sector growth and investment. We therefore provide DFID secondees to the Office of Quartet Representative (OQR) to support them in lobbying the Government of Israel in easing these restrictions. In addition, our previous FNMD project played an important role in feeding evidence into the OQR work, which resulted in negotiated measures between the OQR and the Israeli government to allow exports out of Gaza. As a result, and with assistance from FNMD, the first export of non-agricultural products since the economic blockade was imposed on Gaza in 2007 took place in May of 2012[27]. Our future support to the private sector will maintain this policy focus. / b) Low competitiveness of Palestinian firms: though largely is a consequence of the movement and access restrictions, there are a number of factors which limit the competitiveness of Palestinian firms which can be addressed. The Palestinian private sector is small with comparatively high labour costs, deteriorating production capacities, and weak operational skills that lead to products being uncompetitive. Exports are resource intensive and include little value-added processing and links to global value chains. Consequently, Palestinian firms are mostly focused on local market as only 7% of manufacturing enterprises reported exporting and exports were only 11% of total sales according to PCBS’s Economic Survey of 2009. Furthermore, according to the 2007 World Bank West Bank and Gaza Investment Climate Assessment (ICA), many enterprises are risk averse and do not invest in their production and operation capacities. / Gazan firms in particular have been isolated from global markets since 2007, citing restrictions as the primary constraint to growth, followed by lack of quality electricity supply and inadequate availability of skills. / The private sector situation is most challenging for disadvantaged groups such as female entrepreneurs. Although women have the legal right to work, own land, property and access credit, female participation in the Palestinian economy is low due partly to social norms that limit female economic activity. The Palestinian Bureau of Statistics (PCBS) reports[28] that in 2010 the unemployment rate among women who have completed at least 13 years of schooling was 36.3% of the female workforce, compared to only 15.7% of the male workforce. PCBS also reports that 12% of the female workforce are self employed compared with 20% of males, and 1.4% are female employers compared to 7.4% for males. Overall, women’s labour force participation rate has been below 16% throughout the last decade, which is lower than the already low average of 26% for the Middle East and North Africa region. / How to improve the competitiveness of Palestinian firms? / We have examined eight different possible strategic options and areas that would directly or indirectly affect the competitiveness of Palestinian firms to include in the design of the PMDP. / Areas where there is not a need for a DFID intervention and which are mostly covered by other programmes and donors include the following: / 1) Business Climate: IFC’s Doing Business 2013 report[29] ranked the OPTs 135 out of 183 economies. That is the same as the year before and ranks behind Lebanon at 115th, Egypt at 109th and Jordan at 106th. USAID has a large scale ($24.9m) Investment Climate Improvement project which aims at providing support to improve the business enabling environment as well as areas of fiscal policy. / 2) Finance: In addition to the increased bank lending, there are currently five major financing facilities that provide a range of equity capital funds and loan guarantees to the private sector. These funds are: Abraaj Capital, Palestine Investment Fund Loan Guarantee Facility (focused on SMEs), Rasmala Palestine Equity Fund (focused on stocks), Siraj Palestine Fund (focused on ICT start-ups) and Sadara. / 3) Capacity to the Ministry of National Economy: There are a number of donors currently supporting capacity building for the Ministry of National Economy. These include: The World Bank, USAID and the EU. DFID will be closely coordinating with all donors to ensure complementarity and alignment. / Areas where there is a need for DFID intervention and which are the least addressed by other donors: / 4) Business Skills Development / Private sector skills development and innovation mechanisms are not highly developed. Few enterprises invest in staff training, contract business service providers to develop new or existing products or invest to enter new local and international markets. Exposure to international best practices is limited, undermining firm competitiveness. According to the 2007 ICA , less than 26% of surveyed enterprises provided any worker training and only a small proportion produced to international quality standards. / Experience with implementing the DFID funded Facility for New Market Development programme (FNMD)[30] shows that most enterprises do not value strategic business services such as market research, quality standards, marketing strategies, product development or other sophisticated business support services. / 5) Address market system failures in specific sectors / What is needed are programmes that address the underlying causes of weak market performance and which provide incentives for key market players to play an effective role in competitive and inclusive market systems. The impact of large-scale and systemic change will be maximised if it also brings benefits for the poor in their roles as employees, consumers and producers. / The Palestinian Market Development Programme (PMDP) will help address the underlying causes of weak market performance. The programme will provide incentives and facilitation to key market players seeking to stimulate private and public sector players to take on new (or adapted) functions whilst avoiding becoming an active market player itself. / One example of a market failure that was identified through FNMD was related to the low quality of the services Business Service Providers (BSPs) offer[31]. Only a handful of BSPs ended up applying for FNMD grants to upgrade their skills and services within the FNMD project. Palestinian firms have low confidence in what BSPs can offer them and therefore hesitate to invest in hiring their services, except when donors contribute towards procuring these services. The consequential lack of demand for such strategic services lead the BSPs to have limited capabilities and see no reason to upgrade them. This in turn leads to enterprises being relatively unsophisticated, experiencing problems in producing competitive quality products and services and even preparing business plans which would help in accessing bank finance or venture capital funds. BSPs also lack a body that monitors their service quality, sets standards or offers them certification. / Should BSPs upgrade the quality of their services, not only will firms be able to innovate and compete through better products and skills, but BSPs themselves can potentially become competitive enough to export their own services to other countries. This programme will address the root causes of weak BSPs through a market development approach in line with the results of the FNMD-funded research paper: Business Services Sector Market Analysis[32]. The programme will work closely with Palestinian universities to develop certification programmes that address the quality issues for the BSPs. This is in line with the latest analysis by the World Bank[33] suggesting that there is good potential for the services sector, in addition to manufacturing, to play an important role in the development of the Palestinian economy, similar to Jordan and India. / 6) Investment Promotion / The Palestinian Investment Promotion Agency (PIPA) has been struggling to effectively market investments in the OPTs[34] over the past decade for three main reasons: / The political instability and the consequent global negative perception of the OPTs as high risk. This has been a major constraint to marketing the OPTs as a destination for investment; / The weak business enabling environment compared to neighbouring countries and global emerging economies. The PA recognizes this and has made progress in some areas, such as improving the security situation. But there is still much to be done including improving regulation of land, water, energy, competition, telecom regulator, trade, and company registration; / Very weak PIPA in terms of organisational structure, resources (including IT), capacity and business experience of staff and ability to attract and look after investors, led to PIPA’s work being limited to facilitating tax exemptions to existing investors, and to organising sporadic investment events such as the Bethlehem Investment Conference of 2010. / Based on a Strategic Assessment report produced by DAI in 2010 under the FNMD project, PIPA needs to take a number of steps in order to become effective at not only looking after current investments, but also to attract new foreign direct investments (FDI). The programme will address the issues highlighted in the Strategic Assessment in order to assist PIPA become a world class and effective investment promotion agency. / 7) Palestinian Diaspora and links with the World Economy / The total number of Palestinians is around 10.9 million of whom over 73% live in the Diaspora and in Israel proper[35]. While there is a large Palestinian Diaspora, its links with the OPTs are limited. The family nature of firms often makes it difficult to create consortia and joint venture companies, further limiting technology and know-how transfers. Palestinian firms have also been isolated from international competition and markets for an extended period of time. As a result, they lack awareness of, and linkages with, potential international markets and business partners. The high risk perception and lack awareness on business opportunities is also a deterrent to investment. / As a small economy, growth in the OPTs will depend upon its integration into the world economy. Despite current restrictions in place, Palestinian enterprises would still benefit from improved productivity, expanding into new domestic and foreign markets, moving towards higher value added products and services and niche markets, and investing in new capabilities and technology. It will also be important to help prepare Palestinian enterprises to invest and upgrade their capabilities and be ready to seize market opportunities as and when further movement and access restrictions are lifted and after occupation has come to an end. This can also provide a demonstration effect – that the Palestinian economy is ready and able to grow and be a partner with other markets (including Israel) if Israel takes appropriate steps, and the parties make progress in reaching a peace agreement. / 8) Commercial representation abroad / The PA has representative political missions abroad but very few of these missions have commercial representatives to promote Palestinian products, provide export advice, promote investments or to connect with the Diaspora. The Palestinian Authority has identified the need for commercial representatives as a key policy priority under the 2011/13 Palestinian National Development Plan (PNDP) Strategic Objective: “to promote economic integration and access to external markets”[36]. / The need for commercial representation abroad has also been identified as a priority by several FNMD clients and private sector associations, such as PALTRADE. Commercial representation is needed to facilitate entering into new markets (e.g. Saudi Arabia, Sudan, and North Africa) and to institutionalise the knowledge acquired on entering such markets by specific companies and to make this knowledge available for others. The lack of qualified personnel to perform such an important role and the lack of funds to hire and train qualified staff by the PA and private sector associations are the main constraints that DFID could address building on the UKTI experience in this area of work. / Who else is working on these issues? / To date, private sector development programmes in the OPTs have provided incentives to the private sector in the form of grants and capacity building but have not addressed the root causes of specific market constraints. While some individual firms have benefited from these programmes, the impact as a whole has been limited in terms of growth, job creation and poverty reduction. In some cases, donors’ support has actually created even more dependency on donors’ funding within the Palestinian private sector and hampered innovation and risk taking[37]. In addition, donors’ support has been fragmented and poorly coordinated. / The following table provides a snapshot of main current donors and their projects: / Table 1. Donor supported PSD projects in the WB&G (excluding direct support to PA) / Donor Project Name and purpose Total Funding Timeline / AFD (French) Private Sector Development Cluster Approach. Aims at making local companies more competitive by creating networks between stakeholders belonging to the same economic sector and enhancing Public Private Partnerships. $5 million 4 years, pilot phase started July 2012 / BMZ and CIDA / GIZ Private Sector Development Program. Aims at stimulating sustainable economic growth through improving the legal and regulatory environments among SMEs and assisting trade institutions. 9.3 million EUR Ongoing (3 years) / Consulate General of France Support to firms in Bethlehem Industrial Zone to incentivise and attract enterprises. 5 million EUR grant Started in 2010- Ongoing. / Dutch Government Private Sector Investment "Plus" program (PSI-plus) & Match-Making Facility. This is a global programme to encourage foreign investors to partner with local companies and to bring Dutch expertise to assist them. Contribution of EUR 1.5 m (up to 60%) of total investment per firm Ongoing / EU Support to upgrading the Palestinian Standard Institute Quality Framework $4.5 million 2011-2013 / EU Trade Diversification/ Competitiveness Enhancement program to enhance exports through trade corridor facilitation with neighbouring Arab countries 3 million EUR July 2011-September 2013 / EU Assistance to Agriculture in the West Bank (AAWB) 5.0 million EUR 2012-2014 / Japanese International Cooperation Agency Institutional Strengthening for Industrial Park Development in the West Bank TBD End date is March 2012 / USAID COMPETE Program supporting the private sector in four sectors (Agribusiness, ICT, Stone and Marble and Tourism) $10 million/year Five year project, started May 2012 / USAID Investment Climate Improvement improve the business enabling environment as well as the areas of fiscal policy that limit the Palestinian Authority’s ability to generate revenue from domestic taxes. (Legal and regulatory reform, inventory and reviews of commercial laws, WTO compliance, Doing Business related laws, movable assets registry, Public Private dialogue $24.9 m Three year project started September 2010 / The most substantial donor PSD programme– funding wise – is the USAID COMPETE programme. It seeks to work within the four sectors (agriculture, ICT, stone and marble, and tourism) through business associations and through addressing the constraints associated with each of the four sectors. The programme does not, however, provide direct funding to firms and does not work in Gaza. / The second most substantial programme is the AFD Cluster programme. The AFD programme focuses initially on five clusters (five groups of similar companies per group) in five different geographic locations, providing capacity building through matching grants. / Non of the donor programmes currently provides matching grants to individual firms, works on investment promotion, commercial representation, or Diaspora at large, although USAID’s COMPETE programme does target the ICT Diaspora. In addition, only few donors (such as the Dutch government which support exporting carnation and strawberries from Gaza) have presence and support private sector development in Gaza. / The principles for UK intervention: / The PMDP will adhere to the following principles throughout implementation: / Systemic action – understanding where market systems are failing and acting to correct those failings through targeted incentives, but without creating dependencies; / Sustainable change - by better aligning key market functions and players with the incentives and capacity to work more effectively; / Large scale Impact - through prioritizing interventions that benefit larger numbers of poor and marginalised people, / Facilitative approach – seeking to provide a catalytic role in the market, but without displacing current market functions or players; / Entrepreneurial incentives – by sharing the risk with the private sector in a venture capitalist spirit; / Flexibility and Learning – by being flexible to adjust in response to emerging market needs and programme results. / Why UK Support is Needed? / There are three reasons for DFID to support a Market Development Programme: / Strategic fit – HMG: To help create an economically viable and stable Palestinian state living side by side with a secure Israel is a UK Government foreign policy priority. The programme will also contribute to the National Security Council’s objective to promote regional stability and remove a key driver of violent extremism. Supporting the private sector to sustain economic growth in the OPTs plays an essential role in this, and is an important political signal of the UK’s support to the peace process. Moreover, it is in the UK’s interest for poor economies, such as the OPTs, to reach emerging market status so that they not only graduate from aid dependency but also become more attractive trade and investment partners for the UK. / Strategic fit - DFID: Economic growth as the primary driver of poverty reduction is at the heart of DFID’s development agenda, it is also one of three key pillars of DFID Palestinian programme Operational Plan for 2011-2015. DFID’s new approach to working with the private sector focuses on catalysing more private sector investment and deepening private sector links in order to increase the opportunities for poor people. DFID also perceives the private sector as a key mechanism for women and men to participate in and contribute to growth. / Value added: Although other donors are providing support to the private sector in the OPTs, DFID’s approach is more focused on developing existing and new markets systems that work for poor people. DFID will draw on experience and evidence from successful market development programmes around the globe (such as Katalyst in Bangladesh and PropCom in Nigeria) which have resulted in positive impact and increased wealth for the poor. DFID, as a trusted donor in the OPTs, will also be able to influence other donors’ programmes to ensure alignment and complementarity. Without DFID’s intervention and using DFID’s extensive international knowledge and influencing capacity, there will be a missed opportunity to fill in a strategic economic niche in the Palestinian market.
B. Impact and Outcome that we expect to achieve / The Impact of the proposed Market Development Programme is: Improved private sector-led growth in the OPTs. This will be measured by the following indicators selected from the DFID Palestinian Programme Operational Plan Impact Indicators, which are based on the Palestinian National Development Plan 2011-13 (new targets beyond 2014 will be set once the new Operational Plan is agreed): / Real GDP growth: maintained at 8.2% in 2014. / Unemployment rate: falling to 17.5% in 2014. / Extent of poverty: proportion of Palestinians below the national poverty line falls to 13% in 2014. / The Outcome is: Improved competitiveness of the Palestinian private sector / More specifically, DFID’s funding is expected to deliver the following Outcome targets by March 2019 / 240 enterprises (snapshot[38]) reporting improved annual performance (e.g increased sales, reducing costs, improved processes etc.) / 96 enterprises (snapshot) reporting increase of exports or first time exporter / 72 enterprises using their own funds to pay for Business Development Services (BDS) / 630 jobs created (net) / £40m additional sales (domestic and foreign) realised / These results are estimates based on ‘central’ or medium economic rate of returns (see table 5 & 7 below). It is expected, however, that the programme will exceed these targets due to the change of behaviour that will take place among recipients and non-recipients within the market system as a result of the dissemination of success stories and awareness of good practice. These additional results will be captured within the monitoring and evaluation framework. / There are also a number of non-monetised direct and indirect benefits which the programme is likely to contribute to, and which will be assessed during evaluations. These include, but not limited to: / Influencing market development best practice among other donors; / Demonstrating British people’s solidarity and support to the wellbeing of Palestinians; / Crowding in other donors to join the programme in the future; / Creating synergy with other UK government departments and organisations (e.g. UKTI, FCO, British Counsel..etc); / Leveraging potential Islamic Development Bank funding and efforts in the OPTs. / Link between outcome and impact: / There is good evidence from the FNMD evaluation and other global research[39]&[40]that improved competitiveness of the private sector contributes to improved economic growth. / The PMDP will improve competitiveness by enabling recipient and non-recipient firms to invest in developing and producing higher quality and/or lower priced products and to better market their products and services domestically and globally. It will also enable underperforming sectors to reach their full potential and improve their productivity and quality at sector level within specific value chains. The PMDP will work to encourage Diaspora and investors to transfer knowledge and invest in the business development of firms. / Improved competitiveness will contribute to economic growth. The impact of the MDP is focused on changing the current status where by growth is predominantly linked to consumption which is directly linked to donor-dependent government spending. With private sector led growth comes also lower unemployment and lower poverty. This is especially true if private sector development is implemented in a way that ensures the participation of the poor and the marginalised. / Assumptions: / The main assumption for the outcome is that non-recipient BSPs will crowd in to provide high quality services based on evidence produced by the programme. The likelihood of this assumption to materialise in the current situation is medium to low. However, programme activities around communication, dissemination of best practice and facilitation are likely to mitigate the low probability of this assumption. The project will assess results on a quarterly basis and will adjust accordingly as necessary. / The other assumption is that the political situation remains the same or improves in order to maintain and improve the level of interest by investors, especially the Diaspora. The likelihood of this assumption is very difficult to estimate. The effective dissemination of the programme results and other success stories among potential Diaspora investors, as well as the effective work of PIPA and commercial representatives, is expected to present potential investors with robust economic opportunities within the OPTs that withstand political instability. / The impact assumptions are that movement and access restrictions remain the same or improve, and the PA finances remain viable and that the world economy does not deteriorate any further. Despite this risky nature of the assumptions, DFID’s previous FNMD shows high risks in a properly flexible programme can bring high rewards. FNMD proved that the key driver of success in risky environments is the flexible approach model which is being proposed in this Business Case.
[9] See FCO Website - http://www.fco.gov.uk/en/global-issues/mena/middle-east-peace-process1/palestinian/
[10] The Quartet is a foursome of nations and international entities involved in mediating the peace process in the Israeli-Palestinian conflict. The Quartet is the United Nations, the United States, the European Union and Russia.
[11] World Bank (September 2011). Sustaining Achievements in Palestinian Institution-Building and Economic Growth, Economic Monitoring Report to the Ad Hoc Liaison Committee
[12] IMF (March 2012) Recent experience and prospects of the economy of the West Bank and Gaza.
[13] The economic costs of the Israeli occupation for the occupied Palestinian territory. A bulletin published by the Palestinian Ministry of National Economy in cooperation with the Applied Research Institute- Jerusalem (ARIJ), September 2011
[14] “Dual Use” good s means goods that can have both civilian and military use in Israeli government assessment. Goods on the dual use list at one point included large number of items that ranged from chemical fertilisers to pasta products.
[15] USAID (January 2010) The impact of Israeli restrictions on the transfer of dual-use goods in the West Bank.
[16] World Bank (2009) Assessment of restrictions on water sector development.
[17] The line between Israel and the territories captured in the Six-Day 1967 Arab –Israeli War including the Gaza Strip.
[18] OCHA (August 2010) The humanitarian impact of Israeli-imposed restrictions on access to land and sea in the Gaza Strip.
[19] ibid.
[20] In addition to the Israeli restrictions on movement and access, the closely tied Palestinian economy with that of Israel further exacerbates the economic constraints by driving the cost structure in the OPTs to similar levels of highly developed countries. Most of the utilities (water, electricity and telecoms) are purchased from Israel at Israeli prices albeit through Palestinian subsidiaries. The Israeli security requirements for shipping goods in and out of the OPTs add significantly to the costs. Restrictions on construction outside of Areas A&B have also driven property prices in these areas to exaggerated levels due to scarcity of land in Areas A&B.
[21] IMF (March 2012) opp cit.
[22] IMF opp cit.
[23] Miaari, S., A.Zussman and N.Zussman (2011) Employment restrictions and political violence in the Israeli-Palestinian Conflict (www.meeaweb.org/pdf/Chicago_papers/Miaari_Zussman.pdf)
[24] Ministry of National Economy (2011) The economic costs of the Israeli occupation for the occupied Palestinian territory. p33 (www.met.gov.ps/pdf/ecocostsIsraeloccupationPalestinian.pdf).
[25] World Bank (July 2011) Coping with conflict? Poverty and inclusion in the West Bank and Gaza.
[26] Larudee, M. (Draft July 2012) Who shared the fruits of growth in the Palestinian economy 2006-2010?I (to be published by the Palestinian economic thinktank MAS)
[27] This relates to the first shipment of 2,000 garments from the Kamal Ashour company to JD Williams in the UK, which was facilitated by Lord Stone of Blackheath and coordinated with the Israelis by the OQR.
[28] Palestinian Central Bureau of Statistics – Women and Men in Palestine: Issues and Statistics, December 2011
[29] The World bank Doing Business 2013 assesses regulations affecting domestic firms in 185 economies and ranks the economies in 10 areas of business regulation, such as starting a business, resolving insolvency and trading across borders.
[30] The Facility for New Market Development (FNMD) project was implemented between 2008 and 2012. It focused on strengthening the Palestinian private sector by supporting 600 companies in the OPTs to develop new markets and new products (in key sectors) and improving the business environment in Gaza Strip. DFID and the World Bank have provided £7.092m, and £0.6 million respectively towards the project.
[31] Business Service Providers (BSPs) are all for profit consultancy firms, organisations and educational institutions that provide business services for the development of the private sector such as in the areas of human resource development, financial services, marketing, exports, standards..etc
[32] The ‘Business Services Sector Market analysis‘ is a DFID funded study by DAI as part of the FNMD project outputs. The study provides a detailed analysis of the nature of business services markets in the OPTs, the types of firms and main players providing the services, the opportunities and incentives for the market and the root causes that limit their impact. The study highlighted the small size of businesses, low commitment to growth, reluctance to pay for business services and the poor performance of business services as some of the reasons behind low performance of business service providers.
[33] The World Bank West Bank and Gaza, “Towards Economic Sustainability of future Palestinian state: Promoting Private Sector – Led Growth”. April 2012
[34] This is based on interviews with PIPA director and the results of the Strategic Assessment report produced by DAI on 24 March 2010
[35] PCBS, estimated Population in Diaspora, Statistical Abstract No. 9, 2008
[36] The PNDP text says: “Adopt and implement national strategies (developed jointly with private sector representative bodies) for the promotion of internal trade and overseas exports and appoint commercial attaches to represent Palestine in key export markets”.
[37] This was evident from meetings between FNMD staff and Palestinian businesses who did not participate in the FNMD project due to the 50% contribution requirement.
[38] Snapshot is not cumulative, under this indicator, we will measure the number of firms report improved performance within that year regardless when they were assisted by the programme. For example, if we over the project period assisted 480 firms, our target at the end of the programme in a snapshot measure will be 240 firms out of these assisted firms.
[39] # DCED website “How Private Sector Development leads to Pro-Poor Impacts: A Framework for Evidence”http://www.enterprise-development.org/page/EvidenceFramework
[40] # DCED website “Increased firm turnover and/or profits create economic growth”http://www.enterprise-development.org/page/framework-increased-turnover-growth

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / The Strategic Case has identified that to meet the Outcome of improving the competitiveness of Palestinian firms, there is a need for intervention in nine areas, among which the programme is proposing to intervene in five. These five areas may be grouped into three Outputs: / Output 1: Improved private sector skills and innovation: addresses the need for business skills development; / Output 2: Market system failures addressed in specific sectors: uncovers and addresses the root causes of ineffective market behaviour; / Output 3: Strengthened trade and investment linkages with international markets: addresses the need for investment promotion, supporting Palestinian diaspora and commercial representation abroad. / The design of each Output will be outlined below, drawing on extensive analysis by DFID, EU and World Bank experts and staff who have worked on the design over the past year. Where possible, design options will be outlined. The area where there is a genuine choice between feasible options, however, is in the delivery mechanism – i.e. how to finance and deliver the Inputs - where there is a choice between the following: / DFID to implement a stand-alone project fully funded by DFID / Joint DFID/EU project through a Delegation Agreement mechanism; / Joint DFID/EU/World Bank project through a multi-donor Trust Fund managed by the World Bank / Another option is to ‘do nothing’. / The overarching Theory of Change (outlined below and referred to throughout the text) remains valid regardless of which delivery option is selected out of the above three options. / Outline of Theory of Change / Output 1: Improved private sector skills and innovation / Inputs to Output: Inputs in the form of matching grants and technical assistance will be provided to encourage firms to invest in procuring business services to improve their skills and innovation. Matching grants will also encourage BSPs to invest in the quality of their services in order to compete for high value assignments and to be more responsive to firms’ needs. The programme will work with universities to also ensure that BSPs receive appropriate technical support and accreditations in order to quality assure the business services provided. / Throughout the process, PMDP will also provide technical assistance to ensure that applications from businesses are robust and of high quality. The PMDP will ensure that success stories and best practice are made available to the public and that there is better access to information and knowledge within the private sector. This is based on the assumption that firms and BSPs are willing to invest in skills improvement and innovation, and that firms are willing to share successes and best practice. / Output to Outcome: As firms improve their skills and innovation capacity they will be able to produce higher quality and/or lower cost products and services which could compete in the domestic market against imported products and even in international markets for higher value products and services. As demand for business services increase, the assumption is that client and non-client firms (including BSPs) will be crowded in to provide and market high quality services and products to the market at large. Firms will also be able to use the procured business services to develop their marketing skills which will enhance their overall competitiveness. / Design issues: / a) Grants, matching grants or loans? / The PMDP will provide targeted assistance in the form of matching grants[41] to help private sector firms address market failures. The grants will help share the financial risk associated with new ways of working and in doing so stimulate innovation, test out new models and promote replication of successful practices. The relevant risk being mitigated here is both a perceived risk of the value of procuring business services and the actual risk due to the political vulnerability of the OPTs. It will encourage diversification into new local or overseas markets, products, and processes. / Based on four years of experience with FNMD, the use of matching grants has proven to be an effective methodology of mitigating the financial risk associated with investing in developing firms. Firms are less likely to invest in purchasing business services at times of political uncertainty and without clear evidence on the value of investing in such services. The PMDP will seek to address the issue of knowledge sharing among private sector firms. Once the value of investing in businesses development services become evident, a different intervention option (such as loans or equity) could be considered. Currently there is no evidence that businesses are willing to take loans for the sake of investing in acquiring skills or becoming more innovative. Loans are largely used in the OPTs to acquire machinery and to build infrastructure. / b) Which entities to target? / The design of the matching grant scheme will ensure that changes to perceptions and practices are captured and replicated by others in the market system. The matching grant scheme will be offered to Palestinian firms, including BSPs in the West Bank and Gaza (including universities and cooperatives) and firms planning to open offices in other countries, women head of businesses, consortiums, potential investors, and businesses in remote and marginalized areas such as in Area C and in Gaza. Newly established and registered companies (i.e. start ups) with no track record in particular will be eligible to apply. Targeted outreach and media activities (radio spots, newspapers adverts, focus groups, billboards..etc) to marginalised groups will be implemented to encourage businesses to apply especially women run businesses. The matching grant will not be targeted at specific sectors. / Matching grants can also be provided to consortia through one lead representative company or through business membership organizations (BMOs). Experience from FNMD showed that Palestinian firms do not inherently work together and collaborate, despite the financial incentive of higher matching percentage (70%) offered under FNMD. BMOs can play a role to mobilize and organize firms to work together towards one objective (e.g. researching a new international market on behalf of few companies producing the same product). A small fee (up to 8%) will be paid to the BMO to cover some of the cost associated with organizing, submitting project paper work and reporting. / c) Whether to provide technical assistance to firms? / The matching grant scheme will build on the lessons learned and best practice from the FNMD project and will use the already developed grant system and database management. Based on FNMD experience and final evaluation results, the matching grants within the PMDP will be provided along with extensive technical assistance by project staff experts to ensure high quality interventions. The programme will also seek to ensure that, long term, sustainable technical assistance is provided to firms by BSPs for a fee. / d) What matching grant share? / The extent of matching grant support could include four differing scales of support as described in Figure 1. For example, 75% of activities cost associated with entering a new market with a new product/service and special categories; (ii) 50% for new market or new product/service (but not both); and (iii) 25% for old market-old product/service. Applications for consortia will also get 75% match to continue to encourage collaborative work among firms. Further elaboration of applicability and eligibility will be defined in the Programme Operations Manual. Clear criteria on applicable subsidy categories will be developed along with the selected implementing firm in order to avoid any potential accusations of favouritism as well as excessive complexity of grant processing based on experiences in other countries. Percentages will be constantly looked at to see if they are working during quarterly Steering Committee meetings and as a result of annual reviews and evaluations (See evaluation in section D for details). The overall model can therefore be adjusted based on results achieved and lessons learned during its lifetime. / There is no evidence whether such a model was used anywhere else in the world[42] as it is a creation of the local market needs in the OPTs and the result of the intensive work of experts from the EU, the World Bank and DFID over the past year. This is an innovation to the traditional model of “50% matching ratio across the board” which DFID, the World Bank and other major donors usually use. The risk associated with employing such an innovative approach is mitigated through the designed flexibility to adjust in response to market needs and results achieved as explained in the previous paragraph. The effectiveness of this innovative approach will be captured in the planned evaluations and disseminated widely within DFID for cross learning through the Private Sector Department. / Figure 1: Extent of matching grant support (%) / New 50% 75% / Old 25% 50% / Old / Markets New / e) What investments would be eligible? / A (non-exhaustive) illustrative list of specific eligible tasks could, inter alia, include (subject to further revision during inception phase with implementing firm): / The cost associated with business registration / Company expansion diagnostics / Business management and technical training, including business-related English language courses that are vital for conducting business internationally.[43] / International market research, market intelligence services, market prospection travel / Surveys and focus group assessments of same/substitute products in prospective markets / Product design and prototype development / Forming strategic alliances and subcontracting / Production and efficiency diagnostics / Software purchase, installation and related training / Product testing (internal lab and external) and certification services / Securing trademarks / Quality management systems development, inspection, testing and certification, including those related to international environmental standards / Labelling and packaging design / Market development-related travel and related expenses if part of a comprehensive marketing plan / Marketing campaigns, sales promotion materials, events and missions / Establishment of sales representation and distribution in export markets / Services associated with preparing and implementing market development plans / Setting up standard and certification training for BSPs / f) What is the ceiling for the match? / FNMD project had a ceiling of $50,000 as match contribution to any one company throughout the lifetime of the programme. This ceiling is likely to remain the same for the PMDP but final decision on the amount will be determined as part of the inception phase along with the contractor. A higher ceiling may be granted for strategic and systemic market system interventions, such as for universities’ certification programmes for business services providers. / Capital costs [e.g. machinery and equipment], and recurrent expenses [e.g. normal operating costs such as salaries, rent, advertising] are not eligible, and also cannot be counted as part of the client’s contribution to the project. Supporting recurrent costs would contribute to creating dependency on donors’ funding and lower the potential for innovation and risk taking. Private sector development experts from DFID and the World Bank also advised that the project should not support the purchase of equipment which can be financed through loans from commercial banks and other available donor programmes. Businesses usually find it less risky to get a loan to purchase a machine than to procure a business service. Banks are also more inclined to provide a loan for the former rather than the latter. This is especially true as very soon a new law (currently being processed) will allow businesses to properly register capital assets and use them as collateral against bank loans. Further details of eligibility will be specified in the Programme Operations Manual to be developed during the inception phase. / Key assumptions and evidence: / a) Firms and BSPs willing and able to invest in skills improvement and innovation: The evidence for this assumption is “Medium” given the level of average demand and repeated use by FNMD clients per the FNMD final evaluation. The evidence is mainly dependent on the FNMD experience but is supported by the latest M4P concept in support of private sector development. The FNMD evaluation revealed that FNMD clients were more reticent to invest in machinery and equipment (average 18% addition compared to 23% for non-clients), but that clients invested more into know-how and human resources (11% of profits compared to 9%). Both clients and non-clients, however, achieved similar growth of sales. This puts FNMD clients one step ahead of non-clients in terms of understanding the importance of knowledge investment by achieving similar performance improvement but with less capital investment. The design of the programme will seek to widely advertise the benefits of investing in business development through disseminating success stories and launching special events and media discussions on the issue. The programme will also specifically target BSPs to assist them improve the quality of their services and market them to the wider private sector. / b) Firms willing to share successes and best practice: There were only 23 firms at FNMD (out of total 600 assisted firms) which were willing to share their success stories with the wider business community through written articles and radio shows. The actual numbers, however, may have been much more as not all companies had been asked. The PMDP will seek to require all participating firms to agree to share some specific non-proprietary or non-confidential information about successes related to the support received through the PMDP before agreeing the matching grant. / Output 2: Market system failures addressed in specific sectors / Input to Output to Outcome: Conducting analysis of underperforming value chains or potentially high performing sectors will enable the team to identify and address the specific market failures that are hindering the development of that specific sector or value chain. Some of the issues that will be identified may only need facilitation to sort out while others may require systemic interventions to be co-funded through the matching grant scheme. DFID has proven evidence through different projects around the world where facilitation has resulted in outstanding results. One example is the Nigeria Prop Com project where one large fertiliser company was influenced to provide small fertiliser packages for small farmers to overcome the problem of low fertiliser usage by small farmers which was constrained by corruption of retailers and inability of small farmers to purchase large packages of fertilisers. / Analysis on market failures will be shared with other donors and market players, including the PA, to influence change in behaviour. PMDP experts will use the analysis to provide targeted facilitation and advice to firms, donors and other market players. Advice to other donors and market players will enable them to address areas outside the scope of the project outputs (e.g. political, institutional or other enabling environment factors). / Addressing the systemic issues that are hindering market development will enable specific value chains within certain sectors to reach their full potential and improve productivity and quality. This will enable the matching grants to be more effective and targeted and will ultimately contribute to the Outcome of Improved Competitiveness. / Design issues: / This input will aim to address issues within existing industry value chains that may be cross-sectoral or holding specific sectors from developing, scaling up or benefiting the most impoverished. Activities under this component may address packaging quality for exports, joint promotion and FDI attraction campaigns, master planning for specialized shared infrastructure, branding of regional products, joint sourcing and purchasing plans, and commercialization of academic research. The programme will also focus on conducting short value chain studies, and providing facilitation and advice to firms in targeted under-performing sectors. / It is likely that the selected sectors or sub-sectors will be linked to agribusiness, ICT and tourism although the PMDP will not be promoting one specific sector or value chain. The PNDP 2011-13 identifies agriculture, telecommunications & IT, tourism & antiquities as the priority sector of economy.[44] The sectors selected in the PNDP were also reflected by participation rates in FNMD. Under the FNMD, most clients in the West Bank were in light manufacturing, agribusiness, ICT and tourism; in Gaza they were in light manufacturing, ICT, services and agribusiness.[45] Other donors are engaging at the industry value chain level (e.g. USAID through its Compete Program, EU) while most of the sectors are not deep enough to justify a fully fledged intervention. Therefore the project will promote industry value chains’ performance but will remain cross-sectoral to the extent possible. Selection of sectors or market failures to analyse or facilitate within this component will be determined based on the field work of the team of experts and the feedback from the matching grant scheme. / The interventions will build on DFID’s Making Markets Work for the Poor (M4P[46]) concept, which targets actions to unlock the growth potential of firms while ensuring that the poor are active participants and beneficiaries. The interventions designed will be based on diagnosis, research and analysis of the underlying causes of market failure following up on information gathered from matching grant scheme applicants. The team providing the matching grants will be working with private and public sector representatives, building a dialogue around identified issues and discussing possible solutions. Any incentives to address the identified failures will be provided under the matching grant scheme only. While there are some projects funded by DFID worldwide (such as KATALYST In Bangladesh and PropCom in Nigeria) which apply the M4P principles with success, there is little evidence on how M4P principles can be applied in conjunction with a large matching grant scheme. This will be an innovative approach which will be closely assessed during annual reviews and evaluations. / Key assumptions / The main assumption for this Output is that market players are willing to adjust their behaviour as a result of the studies and to be responsive to the facilitation process provided by the team. The evidence to this assumption is Medium to Weak in the OPTs given the history of abundant donor subsidies to Palestinians, who are considered to be among the highest aided per capita in the world.[47] This, however, is a development challenge the project will address through the hiring of effective facilitators who will work with the private sector and other donors on these issues throughout the lifetime of the project. / Output 3: Strengthened trade and investment linkages with international markets / Input to Output: / The PMDP project will provide technical assistance and systems to the Palestinian Investment Promotion Agency (PIPA)[48] to develop the necessary skills to map the market and identify existing and potential business investment opportunities and enhance its aftercare services. Design of the technical assistance interventions will be based on the Strategic Assessment of PIPA conducted by DAI for DFID in March 2010. No donor support is currently provided to PIPA, The Agency has received an increased mandate under the new Investment Law and it is committed to changing its role from an agency focused on providing tax incentives to a relatively small group of large firms, to a fully fledged Investment Promotion Agency (IPA). The PMDP will not provide any funding directly to PIPA, but will provide short term experts to assist PIPA achieve its objectives and to place some enabling critical ICT systems in place. / Improving Diaspora linkages is an important area that no other donors (except USAID to a limited extent) are currently supporting in the OPTs. The PMDP will aim to mobilize the Diaspora and other potential investors through a menu of activities, including establishing a database of committed Diaspora members with a website portal, and developing a strong communications and business to business (B2B) outreach strategy. The PMDP will undertake a pre-feasibility study to establish Diaspora demands and decide on the most efficient Diaspora database hosting. Other innovative activities would include hosting start-up weekends and mentoring. The project will build on experience of the Diaspora networks such as LebNet[49] and Tech Wadi[50]. / This input will also provide support to train and place commercial representatives in ten potential international markets to promote investment, exports and to support the Diaspora in the respective countries. The proposed model is to hire and train a large pool of young Palestinian experts through a competitive and transparent process drawing on UK’s Trade and Investment (UKTI’s) training tools and consultants. This pool of experts will also be available for private sector associations and firms to hire as needed. The selected representatives will be contracted transparently by the PMDP on merit and will be managed operationally by the Ministry of National Economy, in close cooperation with the Ministry of Foreign Affairs, over three years. Once the concept has been successfully proven the Ministry of National economy can hire the same or other representatives at their own cost. / Output to Outcome: / A more effective PIPA, a mobilised Diaspora and skilled commercial representatives will result in strengthening trade and investment linkages with international markets. This will enable investors (including from the Diaspora) to transfer knowledge and invest to improve Palestinian products and services to become more competitive internationally. This is based on the evidence provided by the World Bank, EU and DFID consultants’ design work which was largely based on the specific needs of the Palestinian economy as well as international best practice. / Design issues: / Key assumptions and evidence: / There are three key assumptions for this input to achieve the desired output and outcome: / 1. PIPA and the PA have the political will to embrace change. There is medium to strong evidence that both PIPA and the PA are willing to make the necessary changes for PIPA to become more effective. This is evidenced by the recently approved new investment law which included in it recommendations to re-engineer PIPA – once resources become available - as per the recommendations of the Strategic Assessment done by DAI PIPA have since elected a new board that includes wider representation form the private sector and government ministries. The board meets on monthly basis and is fully on board regarding the implementation of the assessment key recommendations. / 2. PA and the private sector willing to hire and pay for commercial representative. There is weak evidence to this given the fragile financial situation of the PA and the pilot nature of this initiative. DFID would therefore consider sharing the financial risk associated with hiring and placing the commercial representatives for three years. The level of cost sharing will be negotiated with the PA during the inception phase. Discussions are taking place between the Ministry of National Economy and the Islamic Development Bank to secure funding for the share of this component. / 3. The main assumption at the macro level for this input is that the political situation remains the same or improves. The evidence for this assumption is weak as the political situation has been consistently fragile in the OPTs, at least for the past twelve years and this has negatively affected the interest by the Diaspora and investors to invest in the OPTs. With a more effective marketing by PIPA and better representation within the Diaspora, the project will seek to unveil the investment opportunities with the OPTs despite the political instability. The pilot nature of the interventions will also enable the programme to adjust based on new political realities. / Given the weak/medium evidence for the output assumptions and the pilot nature of the activities, the project team and contractor will ensure that results are closely monitored and evaluated against best practice and any emerging international evidence. Programme activities may be adjusted at annual reviews should enough evidence becomes available that results are not being achieved. / Feasible options for delivery of Outputs / There are not many other options in terms of activities and inputs that would achieve the desired outputs which are not covered by other donors. The DFID Wealth Creation team, supported by analysis from EU, World Bank and DFID experts agreed that the above detailed Theory of Change is the most likely to make a positive impact on the level of competitiveness for the private sector (the Outcome). There are different options, however, in the delivery mechanism of the outlined Theory of Change which the team examined. These are: / DFID to implement a stand-alone project fully funded by DFID. This option will entail DFID to follow normal procedure of tendering an implementing agency and managing the monitoring and evaluation in partnership with the Ministry of National Economy. The results will be fully attributed to DFID with no reporting requirements to other entities; / Joint DFID/EU project through a Delegation Agreement mechanism. This option will entail entering into a Delegation Agreement (DA) with the EU, where by the EU will contribute funding to the project via DFID. This DA will hold DFID liable to the EU funds and will consequently require DFID to approve all funding decisions by the project. Funding will be channelled through Crown Agents Bank which will be required to transfer payments directly to beneficiaries based on DFID approval. DFID will continue to be responsible for the tendering process and monitoring and evaluation as in option one. / Joint DFID/EU/World Bank project through a multi-donor Trust Fund managed by the World Bank. Under this option, DFID, along with other donors, will channel its funding to the project through a World Bank Trust Fund through agreeing and signing an Administrative Agreement with the World Bank. The Bank will implement the project activities on behalf of contributing donors through a non-governmental organisation (NGO) given that Trust Funds cannot be tendered to private sector consulting firms; / A fourth possibility is for DFID to do nothing and for the EU to use their funds to set up a similar programme with similar outputs. / Scale of intervention / It is proposed that under all of the above options, an appropriate total budget is around £15m. This is based on the following judgements for each output: / Output 1: a total of £9.3m, of which £5.5m will be provided in matching grants, £1.5m in technical assistance to firms, and £2.3m in administration costs. From our discussions with the contractor of FNMD, there is expected to be continued demand for a similar level of matching grants, with a risk of oversupply if more is provided. We have therefore assumed a similar level of assistance to firms as in FNMD (which provided £4,535,273 in matching grants), plus additional budget for the matching grants that will go to universities and other non-firm actors as part of the market interventions designed under Output 2. / Output 2: a total of £2m will be provided to address market failures in specific sectors, of which £1m will be provided in technical assistant, £0.5m in commencing 20 studies, and £0.5 in administration costs. These costs and the scale of this output are based on our experience and discussions with the contractor of FNMD. It is expected that four Technical Assistants will be needed to work in the field to commence studies, work with private sector and other stakeholders to identify market failures, and propose / facilitate solutions. / Output 3: a total of £3.47m will be provided to strengthen trade and investment linkages through training commercial representatives, supporting PIPA, and commencing specific activities to target investors. Under this output we are targeting specific areas and therefore the scale of intervention will be limited. The costs of this output are based on our discussions with PIPA and MoNE where £0.2m will be provided for training, £1.3m for placing 10 commercial representatives in 10 countries, £0.6m to assist PIPA’s operational capacity, £0.5m to support activities targeting investors, and £0.87m will be administration costs. / The above budget figures are best estimates based on available information at the time of the preparation of this Business Case. Adjustments to these amounts will take place once the contract has been agreed with the management entity, and the work plan has been prepared during the inception phase. / Product/Process
B. Assessing the strength of the evidence base for each feasible option / In the table below the quality of evidence (that it could bring in the desired benefits) for each option is rated as Strong, Medium or Limited. The options to be appraised will focus on the most appropriate delivery mechanism to achieve the outputs, outcome and impact. The rating of the evidence does not necessarily determine its feasibility as this would be finally determined based on the cost benefit analysis. / Table 2 / Option Evidence rating Justification / DFID to implement a stand alone project fully funded by DFID Medium DFID can deliver a stand alone project and achieve the same results whether with the EU and the World Bank or independent of them given DFID’s international experience in delivering private sector projects. This is well evidenced in the second phase of FNMD when DFID delivered excellent results as evidenced in the FNMD evaluation. Independent funding of a project provides great flexibility for DFID to design and implement the project without the need for consultation and other Head Quarter approvals. This option, however, does not provide the same level of leveraging and influencing that the third and fourth options provide. It also does not benefit from the wealth of expertise other donors bring to the table. / Joint DFID/EU project through a Delegated Agreement mechanism Limited In line with DFID guidance on working with the EU, co-financing agreements between DFID and organisations like the EU affirms the principles and good practices set out in the Paris Declaration on Aid Effectiveness. Co-financing is an effective way to: / Reduce project overhead costs and the administrative burden on partner countries. / Promote ownership and leadership of development programmes by partner countries. / Deliver aid more efficiently by sharing and maximising use of technical and management systems. / Encourage use of common monitoring, evaluation and accounting procedures to reduce number of separate donor reviews and different accounting procedures. / Despite the benefits of co-funding with the EU, the mechanism of Delegation Agreement is still unstable and some issues between DFID centre and EU are still being discussed. Evidence from around the world where a joint DFID/EU programme implemented through a Delegation Agreement has been successful is therefore limited given that only few programmes exist which have just started according to DFID’s EU Department. / Joint DFID/EU/World Bank project through a multi-donor Trust Fund managed by the World Ba Limited The benefits of using a Trust Fund are in principle the same as outlined above in terms of aid effectiveness and compliance with the Paris Declaration. Other donors also found the Trust Fund mechanism to be appealing and expressed interest to join (e.g. Netherlands and the EU). DFID, however, has done a recent systematic review of the effectiveness of Trust Funds[51] and concluded that not only a few number of Trust Funds had positive impacts on aid effectiveness, but that some even had negative impacts. Multiple studies within this Systematic review highlighted the significance and impact that political contexts have on the design and implementation of Trust Funds. There are hardly any examples around the world where Multi-Donor Trust Funds have been used for the implementation of private sector development programmes. / Do Nothing Given that few other donors are working on the areas identified in this project as explained earlier, doing nothing will mean that the Palestinian private sector will miss out on the expected outcome and impact detailed in the theory of change. / What is the likely impact (positive and negative) on climate change and environment for each feasible option? / The project is mainly concerned with providing assistance to small and medium sized enterprises rather than direct implementation. As such, the project is unlikely to lead to any direct environmental impacts. However, there are a number of potential wider environmental issues, risks and opportunities that may arise as a result of the support given. / In assessing the climate and environmental issues related to this programme, it is necessary to consider: / The potential opportunities for business and the environment in terms of improved skills and understanding of environmental standards, innovation in design etc / The direct impacts on the environment from a future increase in manufacturing, agri business development / Enterprises assisted under this programme (directly or indirectly) may include those that are potentially polluting (food and agricultural product processing and certain types of manufacturing for example). In addition there may be opportunities to improve competitiveness or market share through adoption of cleaner and more efficient production methods, certification, eco-labelling etc. / For example, providing support and help to agri-business is one area where the programme may work and where other programmes have also provided support (eg. Oxfam’s Enterprise Development Programme). Issues such as maximising efficiency in water use (where water scarcity is an issue in the OPT as outlined earlier in the business case), reducing energy in production can not only improve the environmental impact of product manufacturing but also have the potential to reduce costs of production. / Output 1 activities (matching grants) could (and will be encouraged to) include support for enterprises on developing approaches, business plans and models etc. which help meet international standards (eg. ISO14001) for environmental management systems or which help illustrate value added along the supply chain through the adoption of environmentally beneficial approaches or technologies. Meeting standards for certification (eg. energy labelling, organic produce) could also be an area the project could look at supporting. These will be of particular importance for Palestinian enterprises wanting to export and be competitive internationally. / Output 2 activities – where market analysis is being undertaken, there is the potential for the project to also look at environmental and climate related trends and opportunities for a range of enterprises in terms of positioning themselves in the value chain. This is particularly the case given the potential focus on agriculture and tourism, both of which have potential resource input (eg. water use) and impact (eg. carbon emissions) issues. The teams involved in implementing this component and in undertaking the research should have a clear environment and climate change technical adviser. / Finally, there are low direct risks to the climate and environment from implementation of the programme, mainly related to travel by team members to project-related meetings etc / Recommendations: / As the nature of the environmental issues will be different from business to business it is recommended that: / DFID’s screening requirements for the overall supplier/managing agent for the programme should include a clear statement/proposal from the supplier on how they propose to incorporate the environmental and climate related advice, support and management within their approach. Ideally they might have someone in their team who has a strong background on climate and environment and could act as their ‘champion’. / The project includes an environmental and climate change screening element when assessing applicants, to ensure that any relevant environmental and climate change issues are adequately considered when developing the package of support for the business; / The management agent in charge of programme implementation incorporates environmental and climate change issues into the project procedures taking account of the issues raised above, particularly the opportunities to raise awareness of environmental and climate change issues through the project components and / The project monitoring framework takes due regard of environmental and climate change issues and ensures they are adequately covered in the documentation and dissemination of best practice and success stories. / Where appropriate, partners will be advised that the carbon footprint of all travel should be minimised and offset where possible. All documents, reports and paper outputs funded by the programme should be printed double-sided on paper made from sustainably managed forests and/or recycled paper. / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 C B / 2 C B / 3 C B
C. What are the costs and benefits of each feasible option? / Options and Counterfactual / The appraisal is of DFID’s use of Options 1, 2 and 3 compared to the counterfactual of no DFID support. This is in order to answer the question of which of the three funding options is likely to provide the highest value for money, and whether the preferred funding option provides value for money compared to the counterfactual. If the EU does not join the project, the assumption is that they would either implement a private sector development project on their own, or that they would re-programme the funds to another sector. / Incremental costs / The project will incur incremental costs to donors, the private sector and the PA. Each of which is outlined below. / 1. Costs to donors / Costs to donor of each funding option compared to the counterfactual are as follows: / Option 1: Implement stand-alone project / Financial contribution: £15m from DFID over 6 years. Based upon our experience of FNMD, it is estimated that 25% of this will be spent on administrative costs, where this is defined as all costs other than the provision of matching grants and technical assistance to firms.[52] / Staff time: 40% of a DFID lead adviser and 40% of a DFID project officer in Jerusalem. / Option 2: Joint DFID/EU project through a Delegated Agreement / Financial contribution: £15.3m total, £11m from DFID (scaled down given the optimum project size of £15m) and £4.3m from the EU. It is estimated that 25% of this will be spent on administrative costs, as for Option 1. / Staff time: For DFID, it will require 50% of a lead adviser, 100% of one project officer and 20% of a second project officer. The full-time project officer would focus on compliance reporting to the EU and to quality assure and approval all matching grant payments, and will be charged fully to the project but hired by DFID. For the EU, it will require an estimated 10% of a lead adviser and 10% of a project officer in Jerusalem/Brussels. / Option 3: Joint DFID/World Bank/EU project through a Trust Fund / Financial contribution: £15.3m total, £11m from DFID and £4.3m from the EU. The World Bank cannot provide money to its own Trust Fund, and so is only involved in managing the project. It is estimated that 25% of this would be spent on administrative costs. This is based on the fees proposed in a World Bank project proposal, where £1.4m would be charged by the implementing NGO, and £2.4m by the World Bank. / Staff time: For DFID, it will require 30% of a lead adviser and 20% of a project officer in Jerusalem. For the EU, it will require 10% of a lead adviser and 10% of a project officer in Jerusalem or Brussels. World Bank staff costs are already incorporated as part of their administrative fee. / Putting both sets of costs together, we can compare the value for money (in terms of Economy) of the different options in terms of the share of total donor costs that are spent on ‘administration’, both for the implementing agencies and the donors themselves. This share is as follows: / Option 1: 29% / Option 2: 31% / Option 3: 28% / The differences between the three options are insignificant that in practice they may be seen to be equivalent. / The Islamic Development Bank may also potentially contribute £1.3m to the commercial attaché component of Output 3 (still under negotiations). / 2. Costs to the private sector / Under Output 1, client firms will pay their matching investment to the project matching grants. It is impossible to judge at this stage what proportion of firms will pay 25%, 50% and 75%, and so we may assume an average of 50%. The £5.5m put in by donors as matching grants will therefore by matched by £5.5m put in by firms. There may also be additional costs borne by firms as part of developing new products or entering new markets that may offset to an extent the increase in sales. However, we have no data from FNMD to estimate the size of these. It is recommended that a light-touch means of gathering information on these costs be incorporated into the monitoring and evaluation plans. / Under Output 2, the market interventions will incentivise firms to take on new activities. These will incur costs to the firms, but will be offset by the benefits. Under Output 3, the same will apply to diaspora, while the costs to investors and businesses will hopefully be reduced through the improved functioning of PIPA and the commercial representatives. / 3. Costs to the PA / The main costs will result from the need for the PA to start taking on the salary payments for the commercial attachés from 2016/17. This is estimated at a cost of £800,000 per year. Given the PA’s fiscal crisis, any such recurrent cost implication should be carefully considered. It will therefore only be done if the project-funded pilot of the attachés is demonstrated to represent value for money in terms of generating additional trade and investment. / Table 3: Incremental Costs to donors, private sector and the PA (in thousands) / Types of cost Total 2013/14 2014/15 2015/16 2016/17 2017/18 2018/19 / 1. Costs to donors / Option 1 / Donor financial contribution 15,000 3,601 3,167 2,947 2,731 2,514 400 / Donor staff costs 840 140 140 140 140 140 1400 / Total donor costs 15,840 3,741 3,307 3,087 2,871 2,654 1800 / Option 2 / Donor financial contribution 15,300 3,661 3,227 3,007 2,791 2,574 400 / Donor staff costs 1,470 245 245 245 245 245 2455 / Total donor costs 16,770 3,906 3,472 3,252 3,036 2,819 2855 / Option 3 / Donor financial contribution 15,300 3,661 3,227 3,007 2,791 2,574 400 / Donor staff costs 720 120 120 120 120 120 1200 / Total donor costs 16,020 3,781 3,347 3,127 2,911 2,694 1600 / Costs to the IsDB 1,300 217 433 433 217 - - / 2. Costs to private sector / Matching investments 5,500 1,180 1,020 1,100 1,100 1,100 - / 3. Costs to the PA / Salaries of commercial Representatives 2,000 - - - 400 800 8000 / Incremental benefits / The incremental benefits common to all funding options compared to the counterfactual are explained in detail below and summarised in Table 4. Potential differences between the options in terms of their likely effectiveness in delivering the benefits are then discussed. / Table 4: Summary of Benefits / Stage 1: Description Stage 2: Quantification Stage 3: Monetary value / 1. Higher private sector growth: Palestinian businesses will generate greater value added as their competitiveness is improved. 240 enterprises will report improved performance attributable to the project by 2018/19. / £40m in additional sales by 2018/19 attributable to the project. Total increase in value added that can be attributed to the project to 2021/22 for 3 or 4 years of impact per firm: / Low: £8.9-11.8m / Central: £29.8-39.8m / High: £63.4-84.6m / Breakeven: £16.5-22.0m / 2. Reduced unemployment: less Palestinians will be unemployed as a result of job creation by client firms as well as from the wider increase in growth. 630 net jobs directly created by the project Not applicable. / 3. Reduced poverty: the increase in employment and wider economic growth will enable Palestinians to be lifted over the national poverty line. Not possible to quantify. Not applicable. / 4. Reduced aid dependence of Palestinian Authority: increased revenues will allow the PA to reduce its dependence on volatile aid flows. PA has collected £20.7m in additional cumulative revenues by 2018/19 due to the increase in GDP attributable to the project. Annual reduced cost of aid volatility at 15% of the increase in revenue by 2021/22 for 3 or 4 years of impact per firm: / Low: £1.2-1.6m / Central: £3.9-5.2m / High: £8.3-11.2m / Breakeven: £2.2-2.9m / 5. Reduced risk of conflict and progress towards a negotiated two state solution: from the reduction in unemployment and improve fiscal sustainability of the PA. Not possible to quantify yet, although we are funding research to allow this. Not possible to monetise. / 6. Reduced risk of environmental impact and improved competitiveness through adoption of environmental management systems and cleaner/more efficient environmental technologies. Not possible to quantify Not possible to monetise. / 1. Higher private sector growth / ‘Value added’ may be defined as the value of a firm’s sales minus the cost of raw materials, and is therefore equal to the firm’s profits, wage bill and taxes. GDP is calculated by adding up the value added of all firms resident in a country, and so increasing value added contributes directly to GDP growth. / Output 1 is expected in the logframe to have improved the performance of 240 firms (50% of the 480 firms assisted). From the experience of FNMD, the vast majority of investments supported by firms were to increase value added through increasing sales rather than by cutting costs. Since the design of Output 1 is essentially the same as for FNMD (except for including matching grants to universities), we may estimate the increase in sales based upon data from FNMD, and then subtract from it the cost of intermediate inputs in order to estimate the increase in value added. The key assumptions used for this are as follows: / Table 5: Assumptions for monetising economic growth benefit of Output 1 / Assumption Value Source and justification / Assistance to consortia and universities is equivalent to assistance to firms n/a Matching grants to consortia and universities will produce additional sales data as for firms and will have at least the same average return. / Average baseline sales per firm £729,375 FNMD database. / Average annual real growth rate in sales attributable to the project High case: 10% / Central case: 4.7% / Low case: 1.4% / Breakeven case: 2.6% High case is the growth rate in additional sales calculated from the FNMD database in the FNMD final evaluation. / Central case adjusts High case with the finding from the FNMD final evaluation that on average respondent firms reported that 47% of increased sales could be attributed to the project. This represents our best estimate of the impact of the FNMD project. / Low case adjusts High case by subtracting the average growth rate of the Palestinian economy over the 2008-11 period of 8.6%. / Breakeven case is the growth rate needed with firm-level impact of 3 years for Output 1 to have a zero NPV with a 3.5% discount rate, which is 2.6%. / Number of years of impact after initial investment High case: 4 years / Low case: 3 years With FNMD there was no impact on sales within the first year, and so tracking the impact 3-4 years after is appropriate. Any longer and attribution is harder to judge. / Proportion of sales that is value added 60.4% This can be calculated per firm either by deducting the cost of intermediate inputs from total sales, or by adding together the firm’s profits and wage bill. None of this data was collected for FNMD and so an alternative approach is to just take the overall share of output that is value added from the national accounts. The value used is from PCBS for 2010. / The potential increases in value added under the different cases are given in the Summary of Benefits table above. A realistic logframe target of additional sales of £40m by 2018/19 has been selected. This is based on the Central case assumption of 4.7% annual additional sales, which is our best estimate of the impact of our previous FNMD project. It is recommended that the project monitoring system track the assumptions in the table on an annual basis in order to check that this target is on track to be met. / Output 2 will increase economic activity in particular sectors by removing key constraints to the improved functioning of markets. For instance, the intervention in the Business Development Service market will address a lack of information about the quality of Business Service Providers which limits demand and competition, through providing accreditation standards. Quantifying and monetising the benefits of market development projects is very difficult since they generally have a small impact on a large number of market agents, making it costly to gather information on impact. Furthermore, the interventions are generally designed during project implementation and so not known in advance. Since the impacts of each market intervention cannot be judged now, it is therefore recommended that the value for money criteria are used as part of the intervention selection process, drawing on best practice for market development projects (see VfM Measures below for more information) and assessed during annual reviews and evaluations. / Output 3 will increase economic growth by facilitating increased trade and investment. As for Output 2, the size of this impact cannot be quantified and monetised at this point and will need to be monitored during implementation. / 2. Reduced unemployment / Jobs will be created through the economic growth outlined above. The relationship between economic growth and employment (or the employment intensity of growth) is called the output elasticity of employment. It was 0.46 for the OPTs between 2006 and 2010, meaning that a one percent increase in GDP was associated with a 0.46% increase in employment.[53] Using the Central case above, if firms assisted under Output 1 increase their sales on average by an additional 4.7% due to the project, this can be expected on average to increase their employment by 2.2%. The logframe objective is to directly create 630 net jobs by the end of the project. / 3. Reduced poverty / Poverty will be reduced through the economic growth outlined above both increasing employment and raising wages (see the Strategic Case for the evidence regarding this in the OPTs). However, it is currently not possible to quantify this as estimates do not currently exist for the Growth Elasticity of Poverty Reduction in the OPTs. We will ensure that estimates are available by the time of the project’s evaluation. / 4. Reduced aid dependence of the PA / The economic growth outlined above will increase revenues for the Palestinian Authority, which will allow them to reduce their dependence on volatile aid flows given that improving fiscal sustainability is a major objective for the PA. This may be quantified using estimates of the growth elasticity of revenue, and the economic cost of aid volatility in reducing the PA’s ability to plan and execute its budget. / Table 6: Assumptions for monetising reduced aid dependence benefit of Output 1 / Assumption Value Source and justification / Growth elasticity of revenue 0.88 Means that a £1 increase in GDP increases the PA’s fiscal revenues by 88 pence, based on a recent study.[54] / The cost to recipient countries of aid volatility as a percentage of the value of the aid. 15% A study estimates the cost at 15-20%.[55] / The size of this benefit stream under the different cases is given in the Summary of Benefits table above. If the Logframe target for additional sales is achieved, the PA is likely to have collected an additional £20.7m in cumulative revenues by 2018/19 years due to the increase in GDP attributable to the project. / 5. Reduced risk of conflict and progress towards a negotiated two state solution: / For the role that economic growth can play see the section ‘Why support the Palestinian private sector?’ in the Strategic Case. The research finding on the link between unemployment and political violence is however contested, and so it is currently not possible to quantify and monetise this benefit. DFID Jerusalem is commissioning research to develop the evidence base for the relationship between economic conditions and conflict. / 6. Reduced risk of environmental impact and improved competitiveness / This is through the adoption of environmental management systems (and consequent reduced risks for investors) and cleaner/more efficient environmental technologies. There is evidence that compliance with environmental standards and adoption of new technologies can not only bring about environmental benefits (reduced resource consumption) but also economic benefits through reduced costs associated with use of energy, water etc. The types of benefits will vary depending on the business model involved. Evidence of the benefits that can be accrued is from a study of 31 SMEs in the UK. Certified environmental management systems delivered cost savings for the majority of firms, with an annual average saving over 2 years of £4,875 per million pounds in turnover. The costs of certifying and implementing the EMS were calculated at £1,362 per million pounds in turnover (annual average over 2 years), suggesting a payback period of 3 months for the investment.[56] It is not clear the extent to which these costs and benefits can be applied to the Palestinian context and so we cannot monetise this benefit. / Comparison of effectiveness of options in delivering the benefits / The relative advantages of Option 1 in delivering the benefits: / High flexibility: only having to comply with DFID project cycle management (PCM) requirements will enable the project to be adapted over time as lessons are learnt. At the other extreme, using a World Bank Trust Fund will allow very little flexibility over time. / High speed: only having to comply with DFID PCM requirements will enable the project to be tendered and implemented faster using FCAS accelerated procurement procedures. At the other extreme, from experience to date of exploring the World Bank Trust Fund option, it will take much longer to be tendered and implemented. / The relative advantages of Option 2 in delivering the benefits: / Medium flexibility: adding the EU’s requirements will reduce flexibility but not by as much as under the World Bank Trust Fund. This impact is very minimum as the EU is usually happy for DFID to use their funds similar to DFID funds. / Medium speed: adding the EU’s requirements will slightly slow down implementation, but not by as much as under the World Bank Trust Fund. DFID will deal with this by hiring a new programme staff member to deal with EU requirements. / Medium donor harmonisation: the positive impact of donor harmonised support to the private sector and to the PA in supporting the private sector, is slightly being reduced by the absence of the World Bank. But this will be mitigated by including the World Bank in the Steering Committee of the PMDP. / The relative advantages of Option 3 in delivering the benefits: / World Bank expertise: the World Bank would bring in its own expertise in investment promotion, market analysis and diaspora work. However, expertise of a similar quality can be obtained through hiring consultants. The relative cost of hiring consultants can be more cost efficient as / High donor harmonisation: the World Bank Trust Fund is a neutral mechanism that would attract other donors to join in in the future. And although the World Bank do not provide a large amount of support to the private sector, they are a key thought leader in the sector and are Co-Chair of the Private Sector Development Sector Working Group. / Which option has the greatest benefits therefore depends upon how flexibility and speed are weighted compared to donor harmonisation. If all are given roughly equal weight, it may be argued that Option 2 (Joint DFID/EU programme) is preferable. / Relative Disadvantages (or risks) of Options / Comparison of the relative disadvantages of the different options are set out in the table below, where for Option 3 they are higher than Options 1 and 2. The overall programme risks and mitigation are set out in detail on pages 27 to 51. / Disadvantages to achieving programme aims Mitigation Who / Option 1: DFID stand alone programme / Less effective influencing of donor alignment and harmonisation Engage other major donors in periodic meetings to ensure coordination DFID PSD adviser and project manager / Less access to EU and World Bank expertise Hire the needed experts including those used by the World Bank and EU & invite WB and EU to Steering Committee meetings DFID contractor / Option 2: Joint DFID/EU programme / Lower flexibility and speed in implementation due to EU requirements Hire additional DFID staff to look after EU requirements at project level DFID Palestinian programme via project / Option 3: Joint DFID/EU/World Bank Trust Fund / Much lower flexibility and speed in implementation due to World Bank procedures and need for consensus on major decisions Not possible to mitigate. DID project officer / Balance of benefits, costs and risks / In terms of comparing the costs, benefits and risks of the different funding options, Option 2 is the preferred option. Although it has slightly high administrative costs compared to the other options, the difference is small. In terms of the benefits, it is the only option which combines both flexibility and speed of implementation with donor harmonisation, and the risks are manageable through additional programme staff. The second preferred option is Option 1, since it carries much lower implementation risks than Option 3 in terms of speed and flexibility, and the relative advantages of Option 3 can be overcome. / In terms of whether the funding options represent value for money compared to the Do Nothing option, we can only estimate a rate of return for Output 1 for which there is relatively good evidence from FNMD and which represents 63% of the total budget. The incremental benefits and costs have been compared until 2021/22, allowing up to four years of impact on the last cohort of firms who will have made their investments supported by the project in 2017/18. The benefits and costs are discounted at two discount rates. The main discount rate used for the OPTs is 3.5%,[57] but as part of the sensitivity analysis a discount rate of 10% is also used. The results are as follows under the three cases: / Table 7: Economic rates of return for Output 1 with 3.6% discount rate / Case Net Present Value (NPV, £m) Internal Rate of Return (IRR, %) / 3.5% discount rate 10% discount rate / 3 years 4 years 3 years 4 years 3 years 4 years / Low -6.7 -4.3 -6.9 -5.2 0 0 / Central 11.7 19.8 7.5 13.2 37% 46% / High 41.2 58.5 30.7 42.8 100% 107% / Varying the expected increase in sales attributable to the project not surprisingly has a very high effect on the project’s return. Under the Low case of only an annual average increase in sales of 1.4%, Output 1 would have a negative return. Under the Central case of an annual increase of 4.7% it has a good positive return with an IRR of 37-46%, while under the High case it has a very high return. / However, we may have confidence in the Output’s value for money for two reasons. Firstly, its return breaks even (with an NPV of zero) when the annual increase in sales goes above 2.6%, which should be relatively easy to achieve. And secondly, this appraisal is an understatement of the benefits of the Output. The impact on economic growth is only the direct impact on client firms, and so does not take into account positive spillover effects on other firms. In addition, it only monetises the economic growth and reduced aid dependence benefits, and so does not take into account the additional benefits of reducing poverty and unemployment, promoting the peace process and reduced risk of environmental impact. / The value for money of Output 2 and 3 is commented on as part of the VfM Statement.
D. What measures can be used to assess Value for Money for the intervention? / The following VfM measures will be used: / 1. Economy: / Project as a whole: the share of total costs going on contracted out management. As for FNMD we will try and keep this to a maximum of 25%, which compares well with other DFID challenge fund projects outside of the OPTs, which varied between 27% and 33%.[58] / Staff salaries: the main administrative cost driver is staff costs. For local staff costs we will compare the daily fee rates proposed by the contractors with those paid by other similar projects in country including our previous FNMD project. For international consultants we will compare their daily fee rate with that paid for other DFID market development projects around the world. / 2. Efficiency: / Output 1: we will monitor the cost per market entered, and the cost per product improved/developed. It is not currently possible to divide the budget of Output 1 in order to measure this, but the project contractor will be required to do this. We will benchmark performance against FNMD, which cost £12,020 per market entered and £5,976 per product improved/developed. / Output 2: we will monitor the cost per study meeting the quality requirements in the logframe. / Output 3: we will monitor the cost per commercial attaché satisfactorily trained, linked to the logframe target of 30 attachés trained by 2014/15. / 3. Cost effectiveness: / Output 2: a set of criteria will be developed to assess the cost effectiveness of proposed market interventions, drawing on the ‘Ratings and weightings’ approach suggested by ITAD.[59] This involves scoring interventions against criteria such as Leverage/replication, Theory of Change, and Relevance and Robustness of Indicators. / Output 3: we will monitor the cost per commercial representative satisfactorily trained. Additional indicators will be developed for the work with PIPA and diaspora during project inception. / 4. Rate of return / Project as a whole: the cost-benefit analysis of Output 1 will be updated on an annual basis using the project M&E system to update the assumptions. Additional data will also be collected on the other Outputs to allow their benefits to be quantified and monetised for the independent evaluation.
E. Summary Value for Money Statement for the preferred option / The preferred option is Option 2 (Joint DFID/EU project through a Delegation Agreement mechanism). / It is preferable to the Doing Nothing option because the incremental benefits are highly likely to outweigh the incremental costs. Based on independent evaluations of our previous FNMD project and only considering its benefits in terms of economic growth and reducing aid dependence, Output 1 is extremely likely to provide a positive economic return and represents 66% of the project. Although the costs and benefits of the other two Outputs cannot at this point be quantified and monetised, there is a strong qualitative case for their value for money. Output 2 will be based on DFID’s tried-and-tested Market Development approach with processes to ensure that only those market interventions are selected which will deliver value for money. Output 3 will consist of a mix of one initiative which is low risk based on previous DFID experience (PIPA) with two higher risk initiatives given a lack of previous experience (commercial attachés and dispora). However, in all three cases there is strong buy-in from the PA, and they have a high potential if the strong synergies between them can be fully exploited. / It is preferable to the other funding options because despite slightly higher administrative costs, it is the only option which combines both flexibility and speed of implementation with donor harmonisation. Its risks can also be mitigated. / The choice of Option 2 is subject to final formal approval by the EU, which is currently being processed at EU HQ. If the EU does not provide formal approval within the next three to four months, DFID will implement a stand-alone programme (Option 1) to which the EU will be welcome to join if and when it becomes possible.
[41] Matching grants are a form of a co-financing mechanism were by a project would pay a percentage of the overall cost of a specific project while the firm (in the PMDP case) would pay the rest of the cost. IN the previous FNMD project the matching ratio between what the firm paid and what FNMD paid was 50% on average.
[42] Going through the list of private sector projects provided by the Private Sector Department does not show any project that provides matching grants to firms.
[43] Firms will be able to apply for matching grants to cover the cost of developing new products or to enter new markets which could include English language courses (e.g. offered by the British Counsel..etc).
[44] NDP 2011-13, Table 1.1, pp.17.
[45] DAI FNMD Final Evaluation Report, pp. 51 (July 2011).
[46] www.m4phub.com
[47] M.Cali (Dec 2010) Military occupation, foreign aid and the elusive quest for a viable Palestinian economy (draft unpublished, Quest 3016661).
[48] . The Palestinian Investment Promotion Agency (PIPA) was established in 1998 as an autonomous agency of the Palestinian Authority (PA), pursuant to the promulgation of the Investment Promotion Law. The law not only established PIPA, but it provided the bylaws by which PIPA would operate.
[49] LebNet is a network of Lebanese-American professionals working in the technology sector, mostly in Silicon Valley, CA. This network, which started in 1999, includes more than 200 people and is built on relationships and volunteerism.
[50] TechWadi is the leading non-profit organization building bridges between Silicon Valley and the Arab world. From its beginnings as the community of top Arab American technology professionals in Silicon Valley, TechWadi has evolved into a powerful platform for collaboration – with members and events spanning across the world.
[51] The systematic review of Trust Funds was structured around the Paris Declaration’s principles of aid effectiveness (ownership, alignment, harmonisation, managing for results and mutual accountability). It concludes; - Of the 44 studies that included an evaluation of MDTFs on ownership, 37 indicated that they had had a positive effect, and 24 demonstrated negative effects. - Only 11 of the studies directly discussed MDTF impact on alignment, with mixed results. - On harmonisation between recipients and donors/fund administering agencies, 27 studies indicated a positive impact while 26 showed a negative impact. - MDTFs historically have a poor record on managing for results, but studies demonstrate that they have improved over time. - Synthesis results on mutual accountability were inconclusive as only 25 studies mentioned this issue, with 13 indicating positive impacts and 10 showing negative impact. These conclusions were drawn from a synthesis of 57 individual studies in 24 high-quality reports. Over recent years multi-donor trust funds (MDTFs) have become standard aid financing modalities because they pool funding and expertise to enable donors to jointly deliver a set of agreed objectives more efficiently.
[52] This estimate is taken from the FNMD final evaluation, which estimated that 29% of the time of project staff was allocated to direct technical assistance to firms (p.42).
[53] Larudee, M. (Draft July 2012) Who shared the fruits of growth in the Palestinian economy 2006-2010?I (to be published by the Palestinian economic thinktank MAS)
[54] Ministry of National Economy (2011) The economic costs of the Israeli occupation for the occupied Palestinian territory. p33 (www.met.gov.ps/pdf/ecocostsIsraeloccupationPalestinian.pdf).
[55] Kharas, H. (2008) Measuring the cost of aid volatility.WolfensohnCenter for Development Working Paper No. 3 (www.brookings.edu)
[56] DEFRA (2011) – Evidence Based Study into the Benefits of EMSs for SMEs.
[57] Following HM Treasury’s Green Book, the discount rate is calculated as the Social Rate of Time Preference (SRTP), using the following formula:SRTP = (catastrophe risk + pure time preference) + elasticity of marginal utility of consumption x annual growth in per capita consumption. For the OPTs, this results in a discount rate roughly equal to that in the UK of 3.5%. Catastrophe risk may be estimated as the same as the UK at 1% since it is our best estimate of the crude death rate for the OPTs adjusted for the median age of the population. Pure time preference and elasticity are assumed to be the same as the UK at 0.5% and 1 respectively. Finally, the future long-term per capita GDP growth rate is estimated to be 1.9%, which is the mid-point between the rate over the 1968-87 period (4.4%) of relative stability, and the rate over the 1994-2010 period (-0.6) of conflict and instability .
[58] FNMD final evaluation p43.
[59] Chris Barnett, Julian Barr, Edward Hedley ‘VFM Approaches for M4P Projects’. Powerpoint presentation for M4P conference.

Commercial Case

A. Clearly state the procurement/commercial requirements for intervention / The programme total budget will be up to £15 million (from DFID funding) for six years if a stand-alone programme is implemented, or £11 million if implemented with the EU through a Delegated Agreement. The 6th year will only include evaluation activities / DFID will directly procure two different contractors (one for implementation and a second for evaluation) to manage the programme on our behalf. This will take place through Procurement Group (PrG) using the Framework Agreements (FAs). These agreements have pre-qualified contractors to undertake activities for us, having already competed through the Official Journal of the European Union (OJEU) procurement process. The first contractor will deliver and monitor the programme, and will be selected under the Fragile and Conflict Affected States Framework Agreement (FCAS). It will manage a matching grant scheme, provide technical assistance (TA) and facilitation services, commence high quality studies and manage support to PIPA, Diaspora and Commercial representation for a total of up to £14.8m. PrG confirmed that our programme can contracted through a mini competition under the FCAS. / The second contractor will evaluate the programme through annual surveys, in depth interviews, and workshops (see Evaluation Plan under section D). We will use the new Global Evaluation Framework Agreement (GEFA) to select the appropriate evaluation contractor through PrG. We estimated a budget of £200,000 over the programme period for this contract. / If option 2 - joint DFID/EU funding through Delegation Agreement (DA) - becomes feasible, the same contractors will continue to work, however the mechanism of payments will be diverted through the Crown Agents Bank (CAB ) in line with DFID’s guidance on working with the European Commission (EC)[60]. Services of CAB are paid centrally for normal transfers and management of third party donors’ funds. Under the Delegation Agreement, DFID will be the lead donor and will manage the programme and receive funds from the EU. The CAB will hold the EU’s contribution for the programme on behalf of DFID and will disperse it on projects activities on the instruction of the DFID Project Officer.
B. How does the intervention design use competition to drive commercial advantage for DFID? / We will ensure that the direct procurement of the programme will drive commercial advantage in line with DFID’s procurement guidelines. We will develop a robust and clear terms of reference for both tenders to encourage adequate competition in close consultation with DFID’s Commercial Adviser and Procurement Group. It will set out DFID’s expectations of the contractor including the anticipated deliverables. Under the Framework Agreements, which were already established under a competitive tender using EU restricted procedures, a mini-competition will be held with all contractors on the framework agreement invited to participate in the further competition. This will ensure a competitive market response, allow us to compare their technical proposals and budgets and select the appropriate contractor that will deliver best value for money.
C. How do we expect the market place will respond to this opportunity? / The ‘market’ will be limited to the 29 pre-qualified entities listed under thematic B of the Fragile and Conflict Affected States Framework Agreement. All 29 contractors on the framework will be invited to participate in the further competition. We expect that a sufficient number of contractors will be interested in this programme and will compete to win the tender. Should initial indications show only a small number of contractors are interested in participating in the further competition then it may be necessary to hold a ‘pre-bid’ meeting to explain the requirements to the framework suppliers and ensure sufficient volume of participants. While it is possible that a single contractor could mobilise the necessary expertise and have sufficient institutional depth to deliver the entire programme, we will also consider a consortium of contractors if appropriate. For the evaluation tender we will consider both options as well.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / The funds for this programme will be managed by the implementing contractor and they will be split between: 1) Programme funds and 2) admin/consultation fees. The administration costs including staffing and running costs of the programme will be a significant cost driver. To ensure the value for money (economy); as per DFID’s best practice and in comparison with other similar programme including the FNMD, these costs generally range between 27 -33% of the total costs[61]. The competitive nature of the competition will ensure that framework contractors require to demonstrate cost competitiveness and as part of the evaluation of bids a detailed assessment of the proposed fee rates, number of staff, and the administrative cost will be evaluated using the VfM measures given in the Appraisal Case. / The programme will use the unit costs developed for the delivery of relevant activities such as cost for market entered and products developed and monitor these costs during the lifetime of the programme. These will be further developed and agreed during the inception phase. / The West Bank and Gaza have relatively good infrastructure and overall transport and logistic costs are not expected to be a significant cost driver. The cost of office space in the West Bank and Gaza is not beyond the range paid elsewhere. Movement and Access restrictions are not expected to have direct significant cost on the implementation of the project since the project will not deal with assets or transfer of goods across checkpoints directly. Businesses, however, will continue to incur additional cost of transporting goods via bypass roads and delays at checkpoints and border crossings. / For the Evaluation contract, in addition to the above factors, the supplier’s methodology (surveys, interviews, geographical locations..etc) for the evaluation plan will be a key cost driver.
E. What is the intended Procurement Process to support contract award? / Procurement Process: Call-down contract under the Framework Agreements / Programme delivery and monitoring contract / DFID has a Fragile and Conflict Affected States (FCAS) Framework Agreement in place which can be used to identify a suitable contractor from a pool of pre-qualified entities to deliver this programme. PrG has confirmed that the programme could be tendered under the thematic area B of the framework agreement which covers: / B1: Engaging the private sector in accelerating economic and political recovery / B2: Sustaining/building immediate livelihoods and economic recovery, including : / A mini competition with all the contractors under thematic area B will be carried out to identify the implementing partner. The timeframe for this exercise would be approximately 10-12 weeks making it an attractive option for starting the programme within a reasonable time frame. The terms of the framework allow consortium of companies to implement the programme. The contractor once selected would then establish a programme management team to run the programme. / Under thematic B, the implementing contractor may be selected from the private sector or civil society. The successful implementing contractor must combine strong knowledge and understanding of the OPTs and the region with relevant international comparative experience in private sector development including implementing making markets work for the poor programmes. It is also important that they can identify partners to work with at the national and local level, and have the reputation and legitimacy necessary to work with a wide range of partners – from the local to the national level. / The selected contractor, within the inception phase of three months, will provide a detailed implementation and monitoring plan. The plan will be discussed with partners, quality assured, and agreed with DFID before proceeding in the implementation. / The Evaluation Contract / The evaluation contract will be awarded to a contractor registered under DFID’s new Global Evaluation Framework Agreement (GEFA). The agreement has 27 pre-qualified evaluation contractors to undertake evaluations for us. / An estimated budget of £200,000 over the programme period has been allocated to this contract. Therefore, in line with DFID PrG guidance, a mini competition under the GEFA to will be undertaken to select the appropriate contractor that will deliver the best value for money. This includes assessing their technical proposal including the evaluation implementation plan and methodology, and their budgets. / The selected contractor will provide a detailed evaluation plan that will be quality assured by DFID’s MENA Evaluation Adviser, and discussed and agreed between the programme partners and DFID before agreeing to proceed to implementation. / The process is likely to take 10-12 weeks; it will be delivered in parallel with the implementing contract.
F. How will contract & supplier performance be managed through the life of the intervention? / Both programme implementation and evaluation contractors will be procured at the same time for the entire lifetime of the project (six years). The actual implementation time for the programme, however, will be for five years, leaving the sixth year to allow for closing the programme and conduct evaluation. / The Programme contracts and contractors’ performance will be monitored and quality assured by DFID OPTs’ Project Officer and Private Sector Development Team Leader through a set of agreed key performance indicators and milestones in the contract. Performance indicators, milestones and other project deliverables will be monitored on quarterly basis by DFID staff and the Steering Committee. Unit-costs and other cost measures (such as fee rates, salaries, and travel costs) will also be monitored by DFID staff and assessed against similar costs from other DFID OPT programmes. / Payments to contractors will be paid on reimbursement basis and conditional upon quality and timely delivery of key targets and milestones.
[60] How to Note, Guidance on working with the European Commission (EC), Quest no. 2463065
[61] From FNMD evaluation document. Benchmark costs reported here relate to the food Retail Industry Challenge Fund (FRICH) and the Responsible and Accountable Garment Sector *(RAGS) Challenge Fund with total cumulative budgets of £7.4m and £3.5m respectively. These costs were obtained from DFID’s Private Sector Department.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / The programme will cost DFID up to £15 million from January 2013 to March 2019. Final allocations and spending profiles for each output will be determined during the inception phase. / As expenditure extends into 4 years beyond the current Spending Review period, FCPD have been consulted and advised that given the programme outer years value is below the threshold, the Business Case will not require HMT approval. FCPD, however, have asked to be notified once the Business Case has been approved in order to make note in their records and mention it in their periodic info to HMT[62]. / An indicative spending profile for the duration of the project is presented below. We will monitor the programme closely and realign the budget based on performance of the different programme components. / Outputs Budget (£) 2012/13 2013/14 2014/15 2015/16 2016/17 2017/18 2018/19 / Improved private sector skills 9,330,000 0 1,934,920 1776270 1,856,270 1,856,270 1,856,270 0 / Market System failure 2,000,000 0 400,000 400,000 400,000 400,000 400,000 0 / Trade and Investment 3,470,000 0 991,000 1,007,000 707,000 491,000 274,000 0 / Evaluation 200,000 40,000 30,000 30,000 30,000 30,000 40,000 / GRAND TOTAL 15,000,000 0 3,365,920 3,213,270 2,993,270 2,777,270 2,560,270 40,000 / Of which Admin Costs (25%) £3,700,000 50,000 722,500 722,500 722,500 722,500 722,500 0 / The above is based on option “1” whereby DFID will be implementing and funding the entire programme on its own. Should Option “2” become feasible (i.e. if EU co-funds the programme through a Delegation Agreement), DFID will adjust its spending down by £4m, which will be compensated through an injection of EU funding of £4.3m. The additional £0.3m will cover the cost of additional staff at DFID to manage EU corporate requirements.
B. How will it be funded: capital/programme/admin? / The funding for this programme will come from DFID OPT’s programme resource allocation.
C. How will funds be paid out? / After finalising the procurement process for both tenders, two contracts will be signed between DFID and the contractors. One covering the delivery and monitoring of the programme for 5 years, and the second will cover the evaluation element of the programme for 6 years. / The implementing contractor will submit monthly invoices to DFID and will be paid each month in arrears through DFID’s account. A project officer will be assigned to authorise payments based on achieved activities in line with the budget and action plan. For the evaluation contract, payments will be made after outputs are delivered. / However, if a delegation agreement is signed between DFID and the EU, payments will be processed through Crown Agents Bank in line with DFID’s policy and guidelines. Under the DA, DFID will manage the programme and receive funds from the EU. The CAB will hold the EU’s contribution for the programme on behalf of DFID. DFID Project Officer will authorise payments after the completion of agreed activities.
D. What is the assessment of financial risk and fraud? / The risk of financial fraud is low. During the process of establishing the Framework Agreements, PrG assess the suppliers’ financial capacity at the pre-qualification questionnaire stage to ensure that there is very low or no financial risks. Also PrG ask for the last 2 years audited accounts. / The risk of financial misappropriation/fraud will be minimised through the use of payments in arrears against the delivery of agreed outputs and conditional on receipted accounts. Contractors will be required to undergo independent audits annually. / Matching grant schemes have the potential of over invoicing services or other manipulations. Being aware of this the implementing contractor and DFID will develop safeguard measures against such manipulations including establishing a list of market prices for services similar to those implemented under the FNMD project. / As part of the inception report, the contractor will submit to DFID a detailed operational manual which will include robust internal control systems and procedures to mitigate against any financial risk or fraud. DFID, through its regional Commercial Adviser, will check the procedures to ensure adequate separation of duties and checks and balances are in place for the execution of all financial transactions. Following are some examples of procedures that DFID will ensure are in place: / project staff involved in the training of the prospective client do not participate in the approval process of projects for the same client; / all first relatives of project, DFID and EU staff involved in the project are not allowed to benefit from project funds; / separation of duties between staff who approve payments and staff who pay; / two signatures for all issued checks and transfer; / all transfers to contractor are checked by DFID project officer and approved by PSD adviser;
E. How will expenditure be monitored, reported, and accounted for? / The implementing contractor will be responsible for establishing and maintaining accounting systems for all aspects of income and expenditure related to the programme. The contractor will be required to present quarterly financial reports. They will also be required to provide forecasting information and expenditure on agreed timescale in line with DFID’s financial forecasting deadlines. / Any capital assets procured under this Intervention will be treated in accordance with DFID procedures, and declared to the DFID programme manager. Should assets remain at the end of the intervention, they will be returned to DFID OPT and will be disposed in line with DFID procedures. / Under the delegation agreement, in addition to the above arrangements the CAB will further provide financial statements on agreed timescale with the EU. / DFID will have a full time project officer at project site to monitor and quality assure all expenditures and relevant reporting.
[62] Approval from FCPD for outer years spending: Quest number 3618481

Management Case

A. What are the Management Arrangements for implementing the intervention? / Oversight / A Steering Committee will be the key structure providing policy oversight to the programme. Members will include PA Ministry of National Economy (MoNE), DFID, and the EU (if a Delegation Agreement is signed). Other entities such as the World Bank, Chambers of Commerce, PIPA, Paltrade…etc will also be invited occasionally as appropriate and upon agreement of Steering Committee members. The mandate of the Steering Committee will be to provide the programme with strategic advice and feedback on implementation, performance and results. It will also ensure complementarity with other programmes and alignment with national priorities. The Committee chair will be determined depending on the level of participation from the Ministry of National Economy, and its secretariat will be provided by the programme’s implementing partner. The Committee will meet on Quarterly basis following the release of the quarterly report to Steering Committee members. / Management / The project implementation and results will be managed by a DFID Project Officer, and quality assured by the DFID Private Sector Adviser in Jerusalem, with support from other London and Jerusalem based advisors and other staff in Jerusalem as necessary. DFID’s interface with the programme implementer will take place through regular meetings between the Programme Officer and/or DFID Private Sector Adviser and the implementing partner’s Team Leader as well as through sporadic but regular visits to the implementing organisation, beneficiary firms , and other stakeholders including PIPA and the MoNE / Figure 2 below presents the overall structure of the programme and shows how management responsibilities will be divided. Included here are the oversight bodies that will be established to provide DFID with the feedback loops it needs to review operational progress. / . / The main division of responsibilities in the management structure is envisaged as follows: / DFID Jerusalem has overall responsibility for the programme and through its standard management instruments (participation in the Steering Committee, general oversight, annual reviews and evaluations) can influence the programme’s direction; / The Steering Committee will give feedback on the programme’s progress, evaluation and on future direction. It will make sure that the programme fits with the national priorities, complements other donors’ programmes and provides good value for money; / The implementing organisation role is to manage day to day programme operations and to efficiently deliver the programme. Under the implementing organisation, a key person will be the Programme Team leader; / The Evaluation supplier will be contracted to carry out annual evaluation surveys and to undertake a full evaluation mid-term and by the end of the programme. Results of evaluations will be presented to the Steering Committee and feedback on the programme implementation for possible improvement where necessary; / Should the EU decide to co fund this programme, a Delegation Agreement will be signed which will include provision to cover the management of the EU funds. DFID will then recruit an additional B2 project officer (with cost covered by the PMDP) whose responsibility will be to provide oversight to the programme, quality assure funding decisions and disbursements for DFID approval (per EU requirement) as delegated, ensure compliance to EU/DFID corporate requirements and provide reporting. This officer will be placed in the office of the implementing organisation but will directly report to DFID project officer or team leader. / There will be other management arrangements including Memorandum of Understanding (MoU) with the MoNE and the Ministry of Planning for the overall programme and potentially with the Islamic Development Bank on the trade and investment output as discussed in the strategic/appraisal case. The MoU will stipulate roles and responsibilities of each organisation and expected results. / DFID Jerusalem / Implementing organisation / Evaluation supplier
B. What are the risks and how these will be managed? / Economic: as outlined in the Theory of Change diagram, improving the competitiveness of firms will not lead to increased economic growth if three assumptions do not hold: that Israeli movement and access restrictions should not increase; that the PA is able to continue to pay salaries; and that the world economy is growing. The risk of the PA not being able to pay salaries is the highest, but does not represent a killer risk. Mitigation measures for these risks are given in the risk matrix in the Management Case. / Environmental: further scarcity of resources crucial for some sectors development (e.g. water for agriculture and tourism) could provide significant challenges to businesses. Climate variability may have implications for the success of agricultural development and product export, as well as international markets becoming more concerned about carbon and water footprinting and therefore demanding less imported produce. Finally, there is a risk that the programme could support the development of sectors which are not sustainable in the long run in terms of their dependence on scarce resources. However, if the programme incorporates environmental and climate-related advice and support across the various components, then there is a potential to minimise these risks and maximise the environmental benefit as well as benefit to business through improving value added. / MEPP: There is a risk that a focus on the sorts of measures pursued through this intervention ultimately do not help deliver a final status peace agreement based on two-states, and with hindsight could inadvertently undermine it. Whilst economic conditions in the West Bank and Gaza could improve, this is not a substitute for real progress on final status negotiations. Indeed as time goes on, time spent on confidence-building without significant political progress the viability of the two-state solution is increasingly questionable. The UK continues to actively promote negotiations. DFID, with the Foreign and Commonwealth Office, will monitor these risks and work to ensure our support does no harm and is as conflict sensitive as possible. We will also examine the conflict sensitivity of the programme as part of the evaluation. / The OPTs country level risks are included in the DFID Palestinian programme Operational Plan (OP) and are monitored on quarterly basis. Specific risks related to this project and their mitigation are discussed below: / Risk Probability Impact Mitigation / Outcome to impact risks / Movement and access restrictions deteriorate in the West Bank and Gaza. Medium High Work closely with the OQR, UN and FCO monitoring and lobbying; using project evidence through case studies. Adjust programme design if needed to respond to emerging needs as a result of more restrictions (DFID PSD Adviser) / Gaza conflict between Israel and Hamas. High Medium (through wider oPT programme activities) Reduce militancy and address grievances by continuing with diplomatic and development efforts to improve socio-economic conditions in Gaza, including by lobbying Israel for implementation of commitments on movement and access. Should the private sector become paralysed as a result of intense conflict, programme resources will be redirected to the West Bank or for more humanitarian purposes. (DFID senior management with advice from PSD adviser) / Escalation of conflict in the OPTs Medium High / Aid flows sharply decline reducing economic growth. Low Medium Lobbying of other donors in country and outside in co-ordination with FCO. This project is designed to enable a robust economy independent of aid.(DFID/FCO ministers + OQR + PA) / Aid coordination remains weak and the proliferation of donor programmes undermines sustainable market development efforts Low Medium Support the Private Sector Working Group in providing effective donor coordination; continue leadership within the existing informal donor coordination group around PSD topics and holding donors accountable to good donorship principles through an agreed compact (DFID Wealth Creation Team Leader) / The programme introduces its own market distortions Medium Medium Direct support can cause distortions and the Palestinian market already suffers from abnormally high risk which itself creates distortions. This scheme is specifically designed to compensate for these distortions by addressing the root causes of market failures and distortions. / PMDP not sufficiently changing root causes of market failures Medium Medium PMDP alone cannot change the root causes of market failures. DFID will work very closely with the Ministry of National Economy, the EU, the World Bank and other major donors to ensure that concerted efforts are exerted to enable maximum impact. / There are no other major economic shocks, such as global economic stagnation Low Medium The programme is sufficiently flexible to work on both export oriented businesses and domestic industries and services. During economic crisis, businesses will be encouraged to focus more on improving competitiveness of local products and services to enable import substitution, rather than exports. / Outputs to outcome risks / Inadequate performance or impartiality of the Contractor’s Business Advisers, and grants managers Low Medium DFID is experienced in contracting effective managers, and there is substantial experience to be drawn upon. Staff of the selected management agency will be asked to sign a statement declaring any conflict of interest they may have with potential grantees. / Insufficient business interest in or ability to make use of the matching grant scheme Low High FNMD has demonstrated sufficient demand and more proactive measures will be taken in the PMDP to maintain and encourage more demand. (PMDP contractor) / Inappropriate (fraudulent) or ineffective use of grants provided Low High Procurement of services by the grantees will be carried out jointly by the recipient firms and the contractor in order to minimise fiduciary risk. This will result in joint accountability between the client and the programme staff on cost, value for money and quality of services. Periodic audits will be conducted / Palestinian business service providers do not provide sufficiently high quality services High Medium This issue has been identified as a market failure to be addressed in the programme. Local BSPs with certification (supported through the programme) will be included in the roster from which firms can select to provide services. / Direct/indirect financial benefit to terrorist organisations through: a) grant funds being used to help businesses with links to such organistions; .b) businesses use funds in contravention of EU/UK terrorist financing law; or c) taxing or extorting businesses for funds. Low/Medium High On a) the implementing agency will vet all recipient businesses using World Check similar to procedures used under FNMD. This procedure will prevent businesses with clear link to such organisations from receiving grants or any kind of support. On b) DFID’s contract with the implementing agency will ensure compliance with EU/UK terrorist financing law, with grant agreements with recipient companies committing them in writing to not provide direct or indirect financial benefit to terrorist organisations. On c) this is covered under b). / Measuring of PMDP results biased and not objective Medium Medium This risk will be mitigated through hiring a separate contractor to measure results throughout the lifetime of the project. These results will be compared against results produced by the implementing agency and action will be taken in case of major discrepancies. DFID staff will also conduct field visits and will verify first hand the quality of the results collated by both contractors. / The MoNE are incapable to provide support to Business representatives abroad once the project is completed Medium Medium This will be mitigated through a formal MoU signed by the PA to ensure that the PA will pick up the cost of commercial representatives after the end of the programme. This activity will also be closely assessed on an annual basis to ensure viability and results before proceeding into the next year of support. / Activities to outputs risks / The capacity of the implementing partners to deliver the programme is inadequate Low high Careful selection and screening of project partners will avoid this risk. Selection will be made on evidence of past high quality delivery experience in similar programmes. After selection, close monitoring of results and implementation quality will enable DFID staff to flag out issues early enough to enable corrective action.
C. What conditions apply (for financial aid only)? / No conditions apply.
D. How will progress and results be monitored, measured and evaluated? / Assessment of evidence base / In the Appraisal Section it was noted that there is overall medium evidence on the Market Development Project. There is medium evidence at the output level but less evidence at the outcome level. in particular around the change in behaviour among clients and non-clients, the political uncertainty and the appetite of the private sector to take risks and the level of attribution of results to the project interventions. An evaluation plan has been developed to address the gaps and is set out in the evaluation section. / Monitoring Strategy / A key requirement of the implementing partner is to collect high quality timely information on all aspects of the programme. The 2012 evaluation of the “Facility for New Market Development” highlighted a number of issues related to the monitoring and evaluation of any future similar programmes as set out below along with notes on how these are being addressed: / issues of attribution; / reliability of data; and / burden of reporting for implementing partner and for beneficiary SMEs. / To address these concerns and to ensure there is high quality monitoring and evaluation of this programme a separate company will be contracted to conduct some of the quality assurance and to evaluate the full programme. / The implementing partner will report every three months against the logframe output indicators. To enable them to do this they will develop a Management Information System (MIS) to provide this data. DFID will work closely with the implementing partner to develop this system. / The MIS system will include the following information: / All enterprises applying for support – basic information will be collected on all firms applying for support which will include size, sub-sectors, location, fields of support, gender of owners/managers/employees, the age of the firms, and the legal status of the firms. In addition, it will include description of the firm’s need for support. / Enterprises receiving support – additional information will be collected from firms which receive support as part of the application form. This will include but not be limited to: / Annual sales, divided into local sales and exports. / Employment (by age, full time/part-time) / Amount of inputs into raw materials / Investments into fixed assets / Investments made into innovation/knowledge / Sub-sector and type of products/ services offered / The firm’s current markets / Enterprises continuing to receive support – further information will continue to be collected on a quarterly basis by the implementer as they continue to work with the various enterprises. This will include both quantitative and qualitative data. / The MIS data will be used by the implementer to produce high quality quarterly progress reports. The reports will include the following information: / quantitative data on progress against logframe output indicators; / qualitative information including case studies with more detail on how the programme is working with a strong focus on beneficiary feedback from the enterprises themselves; / value for money indicators including cost per net job created and per product developed, and ratio between overhead costs and volume of grant;. / Updated risk matrix taking into account the latest situation and noting any mitigating actions which have taken place and further actions which will take place. / The diagram below summarises the logframe indicators and shows which sources of information will provide the data. / Summary Logframe with Sources and Frequency / Indicators Sources / Improved private sector-led growth in OPTs Real GDP Growth PCBS / Extent of poverty: Proportion below national poverty line PCBS Poverty and living conditions in the Palestinian Territory 2009-2010 (www.pcbs.gov.ps). / Jobs: Unemployment rate Data for OPTs as a whole from IMF reports (21% for Year 2011). Data for West Bank and Gaza from Palestinian Central Bureau of Statistics (PCBS) annual “Palestine in Figures” (www.pcbs.gov.ps). / Improved competitiveness of the Palestinian private sector Snapshot number of enterprises reporting improved annual performance due to the Palestinian Market Development Programme (PMDP) (e.g increased sales, reducing costs, improved processes etc.) Annual evaluation firm report based on annual survey / Snapshot of enterprises reporting increase of exports or first time exporter as a result of the PMDP. / Number of enterprises using own funds to pay for Business Development Services (BDS) / Estimated number of jobs directly created (net) by MDP / Value of additional sales attributable to PMDP (£m) / Improved private sector skills and innovation Number of enterprises assisted Annual project report based on MIS data / Number of new markets (domestic and foreign) entered / Number of new / improved products (including services) developed / 70% Number of Business Service Providers (BSPs) gaining recognised certification due to MDP (e.g ISO, human resources, export) / Market System failure in specific sectors addressed Number of high quality studies / scoping studies prepared to reveal market failures in selected value chains (High quality defined as: relevant topic, good use of analysis, objective, clear recommendations targeted at policy makers) Annual project report , quality assured by DFID staff / 15% Number of interventions based on the studies' recommendation taken forward (e.g facilitation, directing firms / consortiums to the matching grant scheme) / Strengthened Trade and Investment linkages with international markets Number of activities completed as part of PIPA's strategic plan (To be further developed in the inception phase of the project) Annual project report / Number of investment related activities directed at investors including diaspora (To be further developed at the inception phase of the project) / 15% Number of people trained on commercial representation abroad (To be further developed at the inception phase of the project and discussion with the MoNE) / DFID B2 Project Officer and Team Leader will review the quarterly reports. Where indicators are off track they will discuss with the implementing partner and if necessary will consider what further action is needed. / The quarterly progress reports will also be provided to the Programme Steering Committee which will meet quarterly. These meetings will include members from the Ministry of National Economy, EU, DFID, and private sector. The Committee will learn on the progress of the programme and advise on possible ways to improve the implementation and impact of the programme. This will provide feedback as the programme proceeds and that necessary action is taken early if the programme is off track. / Evaluation Plan / In addition to the monitoring carried out by the implementing contractor, a second firm will be contracted to carry out annual reviews of the programme and to undertake a full evaluation of the programme. The firm will also measure improved performance of former clients assisted by DFID through the FNMD project. This is mainly to capture the impact on clients received assistance in the last year of the FNMD (April 2011 -2012) which was difficult to measure due to business cycle. Separate Terms of Reference (TORs) will be developed and used as a basis to award a contract to a different company for the evaluation of the programme. This will ensure there is an independent evaluation. £200,000 has been set aside for this work. The TORs will be finalised and the evaluation firm will be appointed within six months of the programme being approved. / As shown in the 2012 FNMD evaluation and other research, the main methodological challenge in estimating the impact of market development programmes at the firm level involves the measurement of a counterfactual. Identifying a control group that is identical to the treatment group is difficult, as firms self-select through the application process and it is not fair to exclude some firms from applying purely for the purposes of establishing a control group. / The 2012 FNMD evaluation included an attempt to collect information from firms which were not supported by the programme but the response rate was extremely low. Firms which did not benefit from the project had little incentive to participate in answering questionnaires. / For these reasons there will not be a full impact evaluation with a control group. Rather the evaluation will focus more on qualitative information and assessments made by beneficiaries. Also we will consider further information for comparison. / The evaluation firm will be responsible for carrying out an annual survey of firms receiving support. They will collect detailed quantitative and qualitative information on the following areas: / new markets and innovation of products; / perceptions about whether the changes are due to the programme or due to other factors; / information on whether beneficiaries would buy similar services in the future without the support of the programme; / whether there have been any other effects of the support – both positive and negative. / Once the evaluation firm is contracted there will be detailed discussions with DFID and the draft annual survey will be quality assured by a DFID statistician to ensure it meets the needs of the programme. The evaluation firm will produce an annual report for DFID focussing on the following areas: / quantitative information on outcome indicators; / qualitative information on beneficiary views of the programme; / recommendations where appropriate, to adjust the project activities, logframe and theory of change. / In depth thematic report - each year, the report will include a specific theme such as value for money and gender. / monitoring the assumptions of the cost-benefit analysis, allowing an assessment of whether the project is on-track to achieve its expected return. / In addition to the five annual surveys, conducted from 2013 to 2017, the firm will also carry out a more in depth evaluation in 2018. / The in-depth evaluation will cover the five OECD/DAC evaluation criteria of Relevance, Efficiency, Effectiveness, Impact, and Sustainability. It will also look at the impact of the programme on women and will consider whether there have been any environmental impacts of the programme. The evaluation will include the following questions but not be limited to: / Relevance: / Is the project consistent with the local stakeholders’ priorities and effective market demand? / To what extent are the objectives of the project still valid? / Are programme activities, outputs, outcomes in its logical framework consistent with the overall impact? / Effectiveness: / To what extent did the programme is achieving its targets? / What internal and external factors contributing to the project results and how? / What were the effects of the programme on female headed businesses? / What would be done to make the programme more effective? / Efficiency: / To what extent the programme benefits exceeded its cost, and whether it is possible to increase benefits and / or reduce costs? / Impact: / What is the impact of the programme on its grantee firms / To what extent can these impacts be plausibly attributed to the programme? / How grantee firms perceive the effects of the programme on themselves? / To what extent the assisted firms and the programme stimulate private sector development in the OPTs? / Sustainability: / To what extent the benefits will continue without additional assistance? / Does the programme have potential for replication or scale up? / The evaluation firm will produce a more detailed evaluation plan within three months of being contracted. The evaluation plan will need to set out the detailed methodology they will use for the annual surveys as well as setting out how they will collect the other information essential for the in-depth evaluation. The methodology will need to include mechanisms for collecting quantitative and qualitative information through focus group discussions, interviews etc. The evaluation plan will also need to show how they will measure the changes to baseline data, how they will quality assure the monitoring data, how they will assess attribution, and how they will test the programme’s theory of change as it progress. / The annual evaluation reports will be submitted to the Programme Steering committee for their consideration. / The DFID Project Officer will complete annual reviews based on the quarterly progress reports from the implementing partner as well as the annual evaluation reports from the evaluation firm. The DFID wealth creation team leader will quality assures the annual reviews.
Logframe / Quest No of logframe for this intervention: 3598721