## Current Log-frame 2018
PROJECT NAME | The Queen Elizabeth Diamond Jubilee Trust - Avoidable Blindness Programme
IMPACT | Impact Indicator 1 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019 | Assumptions
Improved eye health in targeted Commonwealth countries | Number of trachoma endemic Commonwealth countries that have reached elimination targets by achieving their Ultimate Intervention Goals (UIGs) <0.1% Trachomatous trichiasis (TT) <5% Trachomatous follicular (TF) (see note 1) | Planned | Start date: April 2014 Trachoma endemic in districts in all of the Trust's countries | Proposal development and mobilisation of key partners | Trachoma endemicity mapping complete | Mass Drug Administration (MDA) distribution and surgeries on track 58% endemic targeted districts with TF < 5% in children aged 1-9 years | Antibiotic distribution and surgeries on track 81% endemic targeted districts with TF < 5% in children aged 1-9 years | Antibiotic distribution and surgeries on track 90% endemic targeted districts with TF < 5% in children aged 1-9 years | UIGs achieved in Kenya, Malawi, Uganda, Fiji, Kiribati, Solomon Islands and Vanuatu. At least 65% of surgical backlog cleared in Mozambique, Nigeria, Tanzania and Zambia. | Commonwealth Health Ministries prioritise and support health eye health programmes. Governments appreciate eye health as a critical aspect of a strengthened health system. For milestone targets on district with <5% TF - MDAs need to be delivered on time and impact surveys completed on time.
|  | Achieved |  | Proposals approved. Implementation of the SAFE strategy began in April 2014 | Mapping completed Implementation begun in all African countries. | Mass Drug Administration (MDA) distribution and surgeries on track 71% targeted districts TF < 5% | Antibiotic distribution and surgeries on track 82% targeted districts TF < 5%
Source
Global Trachoma Mapping Project (GTMP) and data from the International Coalition for Trachoma Control (ICTC), Sightsavers and local implementing partners
OUTCOME | Outcome Indicator 1 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019 | Assumptions
Increased capacity and access to quality eye health care in targeted areas of the Commonwealth for Trachoma, Diabetic Retinopathy (DR) and Retinopathy of Prematurity (ROP). | Number of people whose sight has been protected as a result of programme activities Targets are cumulative | Planned | Start date: January 2014 | Total - 20,000 Trachoma - 20,000 DR - 0 ROP - 0 | 57,012 Trachoma - 57,000 DR - n/a ROP - 12 | 71,072 68,000 2,990 82 | 83,430 77,000 6,170 260 | 100,744 90,000 10,290 454 | 107,150 95,000 11,590 560 | “Number of people whose sight has been protected as a result of programme activities,” is a sum of the population who have received TT surgery, or RoP or DR treatment. "Health professionals" includes ophthalmologists, optometrists and surgeons. Ophthalmologists can be identified who are suitable and willing to be trained.
|  | Achieved |  | Total - 18,103 Trachoma - 18,103 DR - 0 ROP - 0 | 42,947 Trachoma - 42,939 DR - n/a ROP - 8 | 69,429 Trachoma - 65,156 DR - 4,221 ROP - 52 | 87,136 Trachoma - 79,348 DR - 7,622 ROP - 166 | 92,968 Trachoma - 83,635 DR - 9,113 ROP - 220
Source
Reports from the International Coalition for Trachoma Control (ICTC) and coordinating partners (Sightsavers and Fred Hollows Foundation)
| Outcome Indicator 2 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019
| Number of eye health professionals trained/retrained and practicing in targeted Commonwealth countries Targets are cumulative | Planned | Start date: January 2014 | Total - 98 Trachoma - 96 DR - 0 ROP - 0 CEHC - 2 | 152 140 0 0 12 | 225 157 24 4 40 | 276 157 35 14 70 | 342 157 45 20 120 | 402 157 45 20 180
|  | Achieved |  | Total - 86 Trachoma - 84 DR - 0 ROP - 0 CEHC - 2 | 167 Trachoma - 147 DR - 0 ROP - 0 CEHC - 20 | 273 Trachoma - 183 DR - 23 ROP - 14 CEHC - 53 | 389 Trachoma - 198 DR - 55 ROP - 25 CEHC - 111 | 505 Trachoma - 268 DR - 55 ROP - 60 CEHC - 122
Source
Reports from ICTC, Sightsavers, PHFI, Fred Hollows Foundation and Caribbean Council for the Blind
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  | Total (£)
| 50m |  |  |  | 50m |  | 100m
INPUT (HR) | DFID (FTEs)
0.1 PM 0.3 DPM 0.05 advisory input
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019 | Assumption
Effective implementation of selected elements of the SAFE (Surgery, Antibiotics, Facial Cleanliness, Environmental Improvements) strategy | Percentage reduction in TT surgery backlog target Targets are for each year (see note 2) | Planned | Trachoma dates | April 2014 - March 2015 | April 2015 - March 2016 | April 2016 - March 2017 | April 2017 - March 2018 | April 2018 - March 2019 | Project end date: March 2019 | For the Africa Trachoma Initiative, Year One runs from April 2014 - March 2015. For the Pacific Trachoma Initiative, Year One runs from January 2015- December 2016. The indicator for the 'S' component includes: 1. People who have been operated on 2. Those who epilate having refused surgery 3. Those who have been counselled but refuse support Patients requiring TT surgery as of 2013: Kenya - 41,501 Malawi - 12,877 Nigeria (Katsina) - 29,061 Uganda - 38,600 Mozambique - 13,803 2013 Mass Drug Administration: Kenya - 2.87m people in 12 counties Malawi - 8.18m people Mass drug administration dependent on timely arrival of drugs and distribution not being compromised by insecurity For a district to benefit from behaviour change communication activities the district must have at least one of the following: social mobilization (for facial cleanliness and environmental improvements), Unilever Super School of Five, other F&E activities including development of messages and materials disseminated by health workers, schools clubs, community leader, community groups.
|  |  | Start date: April 2014 Number of TT surgeries conducted in targeted areas in 2013 (not funded by the Trust): Kenya - 6,211 Malawi - 400 (estimate) Nigeria - 15,760 Uganda - 10,738 Mozambique & Tanzania - data not available | Kenya - 22% (9,000) Malawi - 25% (1,500) Moz'que - 14% (1,000) Nigeria - 15% (2,000) Tanzania - N/A Uganda - 33% (12,500) Nigeria expansion - N/A Zambia - N/A Total - 15% (26,000) | 54% (12,000) 53% (2,500) 36% (2,000) 45% (5,000) 17% (5,000) 73% (15,000) Total - 46% (41,500) | April - Sept Oct - March 62% (3,500) 78% (6,600) 52% (750) 82% (1,750) 51% (400) 62% (800) 18% (1,500) 40% (3,500) 64% (750) 72% (2,250) 88% (1,000) 95% (2,420) Total Total 56% (7,900) 71% (17,320) | April - Sept Oct- March 80% (3,000) 88% (3,000) 100% (674) 100% (0) 80% (700) 88% (600) 34% (3,000) 57% (3,815) 92% (1,000) 100% (1,250) 90% (1,281) 93% (751) 33% (1,320) 37% (498) Total Total 80% (9,655) 71% (11,234) | April - Sept 93% (4,317) 99% (84) 99% (88) 36% (2,356) 96% (1,429) 96% (4,086) 68% (1,919) 75% (515) Total 83% (14,835) | Oct-Mar 100% 100% 100% 40% 100% 100% 100% 100% Total 93% (9,890)
|  | Achieved |  | Kenya - 24% (9,854) Malawi - 6% (368) Moz'que - 3% (235) Nigeria - 2% (345) Tanzania - N/A Uganda - 35% (13,498) Nigeria expansion - N/A Zambia - N/A Total - 12% (24,138) (see note 3) | 56% (11,173) 40% (1,934) 46% (1,033) 8% (938) 55% (1,510) 85% (8,443) Total - 48% (25,031) | 65% (5,013) 73% (3,256) 66% (1,003) 89% (891) 59% (962) 70% (928) 13% (756) 15% (502) 78% (1,001) 83% (1,380) 94% (2,165) 98% (1,489) Total 63% (10,900) 71% (8,446) | 75% (1,563) 83% (1,878) 100% (652) 98% (738) 86% (1,151) 98% (1,251) 21% (713) 29% (1,319) 87% (1,003) 91% (1,224) 90% (1,243) 83% (948) 20% (802) 37% (587) Total Total 78% (6,408) 67% (8,664) (See note 8)
Source
TT surgery registers; 6-monthly reports from the ICTC; Global Trachoma Mapping Project
| Output Indicator 1.2 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019
| % of endemic districts achieving >80% coverage of Mass Drug Administration (MDA) in the year Targets are cumulative (See note 4) | Planned | Trachoma dates | April 2014 - March 2015 | April 2015 - March 2016 | April 2016 - March 2017 | April 2017 - March 2018 | April 2018 - March 2019 | Project end date: March 2019
|  |  | Start date: April 2014 Mass Drug Administration (MDA) in 2013 (not funded by the Trust) Kenya - 2.5m Malawi - 1.6m | Kenya - 3m Malawi - 3m Pacific Islands - N/A | 5m 7.8m 0.45m | Kenya - 100% Malawi - 100% Pacific Islands - 100% | 100% 100% 100% | 100% 100% 100% | 100% N/A 100%
|  | Achieved |  | Kenya - 2.5m Malawi - 3m | 3.8m 8.7m 0.4m | Kenya - 100% Malawi - 100% Pacific Islands - n/a | 50% (insecurity in Western Kenya) 100% 100% | tbc 100% tbc
Source
Project MDA reports; 6-monthly reports from the ICTC
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019
45% (NB percentages indicative) | Number of endemic districts benefitting from behaviour change communication activities to increase facial cleanliness and environmental improvement Targets are cumulative | Planned | Trachoma dates | April 2014 - March 2015 | April 2015 - March 2016 | April 2016 - March 2017 | April 2017 - March 2018 | April 2018 - March 2019 | Project end date: March 2019
|  |  | Start date: April 2014 0 | Total - 35 Kenya - 1 Malawi - 17 Uganda - 17 Tanzania - 0 | 46 12 17 17 0 | 46 12 17 17 0 | 46 12 17 17 0 | 54 12 17 17 8 | 54 12 17 17 8
|  | Achieved |  | Total - 1 Kenya - 1 Malawi - 0 Uganda - 0 Tanzania - 0 | 34 12 17 5 0 | 35 12 17 6 0 | 54 12 17 17 8 | 54 12 17 17 8
Source
Trachoma Initiative Year One start date April 2014 Project reports; Government and WASH NGO partners reports; 6-monthly reports from the ICTC
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  | Total (£)
| 29.3m |  |  |  | 14m |  | 43.3m
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 Diabetic Retinopathy | Output Indicator 2.1 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019 | Assumptions
Increase in the number of patients with sight threatening retinopathy treated in targeted Commonwealth countries | Number of patients with diabetes screened for diabetic retinopathy annually Targets are cumulative | Planned | See 'Diabetic Retinopathy' tab | Proposal development and mobilisation of key partners | Screening commences | 17900 | 46900 | 83300 | 96300 | Year One for the DR Initiatives will run from January 2015. Change in policy will lead to greater resources for the prevention of diabetic retinopathy and for diabetic retinopathy programmes in the government health system, leading to programmes that are scalable and sustainable after Trust support ends. Governments allocate sufficient resources and budget.
|  | Achieved |  | Proposals approved. National DR Summit held and taskforce established. | 5388 | 26725 | 76951 | 91725
Source
Reporting from PHFI, The Fred Hollows Foundation and The Fred Hollows Foundation NZ. India - Community Health Centre Records, District Hospital records. Pacific - Monthly reports from clinic administration staff and World Health Organisation (WHO) Tool to Assess Diabetes and Diabetic Retinopathy Services (TADDS)
| Output Indicator 2.2 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019
| Number of screened patients with diabetes treated for diabetic retinopathy annually Targets are cumulative | Planned | See 'Diabetic Retinopathy' tab | Proposal development and mobilisation of key partners | Treatment commences | 2990 | 6170 | 10290 | 11590
|  | Achieved |  | Proposals approved. National DR Summit held and taskforce established. | 1503 | 4221 | 7622 | 9113
Source
India - reporting from PHFI, Community Health Centre Records and District Hospital records. Pacific - measures of DR severity by BIO / direct ophthalmoscope or PEEK collected during outreaches and screenings.
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019
15 | At least one example from each partner of how they have influenced national health policy with respect to integrating diabetic retinopathy models of care into the public health system | Planned |  | Proposal development and mobilisation of key partners | India - States identified | Public Health Foundation of India (PHFI) - Meetings held with all state governments where diabetic retinopathy screening is planned Caribbean Council for the Blind (CCB) - Start-up consultation meetings completed in all 4 countries with partners and Ministries of Health Fred Hollows Foundation (FHF) - Diabetic retinopathy eye screening integrated into government health systems in project locations | PHFI - Operational guidelines for screening and treatment adopted by the government FHF - Diabetic Retinopathy Coordinators recruited and employed in each country | PHFI - Health ministries in all 10 program states sign MoUs supporting the program FHF - National health strategies developed with eye health embedded in all 4 countries | PHFI - Government directives issued supporting DR model of care
|  | Achieved |  | Proposals approved. National DR Summit held and taskforce established. | India - States identified | PHFI - Meetings held with all state governments where diabetic retinopathy screening is planned. PHFI - Special issue of Indian Journal of Endocrinology published focusing on DR. CCB - Start-up consultation meetings completed in all 4 countries with partners and Ministries of Health FHF - Diabetic retinopathy eye screening integrated into government health systems in project locations | PHFI - Second draft of operational guidelines reviewed by Technical Expert Group and due for printing FHF - DR Coordinators recruited and employed in each country Bangladesh – A national DR taskforce, chaired by the Ministry of health, has been established | PHFI - Health ministries in 10 program states have signed MoUs supporting the program
|  | Source | [7 empty] | RISK RATING
|  | India - reporting from PHFI Pacific, Bangladesh and Pakistan - reports from the Fred Hollows Foundation. Caribbean - reports from the Caribbean Council for the Blind | [7 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  | Total (£)
| 4.5m |  |  |  | 3.3m |  | 7.8m
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 Retinopathy of Prematurity | Output Indicator 3.1 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019 | Assumptions
Increase in the number of infants treated for retinopathy of prematurity (ROP) | Number of infants screened for ROP in Special New-born Care Units (SCNUs) in quality improvement programme area annually Targets are cumulative | Planned | 0 | Proposal development and mobilisation of key partners | 150 | 1960 | 6360 | 10000 | 12420 | Year One of the ROP Initiative will run from Q1 2015. The absolute number of instances of ROP in India is likely to rise during the Trust's lifetime due to the increased survival rate of premature infants. Assuming 4%-8% of pre-term infants <2,000 grams develop ROP that requires treatment (based on existing evidence). In 2018, data from the programme showed that 2% of pre-term infants <2,000 grams develop ROP that requires treatment (See note 6) Based on the programme working in 5 states with 4 SNCUs in each state. As of 2018 the programme is working in 4 states in 18 SNCUs in total. (See note 7) Change in policy will lead to greater resources for the prevention of ROP and for ROP programmes in the government health system, leading to programmes that are scalable and sustainable after Trust support ends.
|  | Achieved |  | Proposal approved. National ROP Summit held and taskforce established. | 175 | 2146 | 5777 | 7715
Source
Retinopathy of Prematurity Year One start date January 2015 Data to be taken from existing UICEF databases and reporting from state level Special New-born Care Unit (SNCU) Co-ordinators
| Output Indicator 3.2 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019
| Number of infants treated for ROP in Special New-born Care Units (SCNUs) in quality improvement programme area annually Targets are cumulative | Planned | 0 | Proposal development and mobilisation of key partners | 12 Obtain baseline rates of ROP requiring treatment from first year of implementation | 82 | 260 | 200 | 250
|  | Achieved |  | Proposal approved. National ROP Summit held and taskforce established. | 8 Baseline rates secured | 52 | 166 | 220
Source
Retinopathy of Prematurity Year One start date January 2015 Data to be taken from existing UICEF databases and reporting from state level Special New-born Care Unit (SNCU) Co-ordinators
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019
5 | At least two examples of how the Public Health Foundation of India (PHFI) have influenced national health policy with respect to integrating retinopathy of prematurity models of care into the public health system | Planned | Start date: Jan 2015 States identified in 2015 | Proposal development and mobilisation of key partners | Baseline data collected for chosen states. | National Operational Guidelines for ROP adopted by the Ministry of Health ROP is included in the Government’s online database for neonatal intensive care units | Ministries of Health in non-Trust States issue advice that government neonatal care providers initiate ROP screening and treatment State Ministries of Health issue documents advising that government eye care service providers initiate ROP screening and treatment of ROP | 5 programs, not funded by the Trust, for screening and treating ROP established in neonatal care units >75% of identified ophthalmologists in program areas trained in ROP screening | Control of ROP is a specific priority in the National Programme for the Control of Blindness, with budgetary provision for screening and treatment Joint National Neonatology Forum (NNF) and All India Ophthalmological Society (AIOS) National Guidelines for ROP formally adopted by the Ministry of Health.
|  | Achieved |  | Proposal approved. National ROP Summit held and taskforce established. | Situational analyses completed and training begun | National Operational Guidelines for ROP adopted by the Ministry of Health in May Special edition of Journal of Indian Paediatrics focusing on ROP published | Operational guidelines for prevention of blindness from ROP have been developed and are being shared with the Trust states and pilot units. National Ministry of Health programme has included all components of the operational guidelines into National guidelines for prevention of childhood blindness. | 23 programes, not funded by the Trust, for screening and treating ROP established in neonatal care units. (15 in Maharashtra, 4 in Telangana, 4 in Madhya Pradesh).
|  | Source | [7 empty] | RISK RATING
|  | Retinopathy of Prematurity Year One start date January 2015 Reporting from PHFI - Data to be taken from existing UICEF databases and reporting from state level SNCU Co-ordinators | [7 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  | Total (£)
| 0.9m |  |  |  | 2.6m |  | 3.5m
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 Fellowships, Research and Technology | Output Indicator 4.1 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019 | Assumptions
Strengthened eye health systems in lower and middle income Commonwealth countries in three key areas of people, knowledge and tools | Number of health care professionals trained Targets are cumulative | Planned | Start date: June 2014 0 | Total - 2 MSc students - 0 Clinical Fellowships - 2 PhD Fellowships - 0 | Total - 12 5 7 0 | Total - 40 10 30 0 | Total - 70 15 55 0 | Total - 120 20 100 8 | Total - 180 30 140 10 | Enough quality candidates apply for the Masters, Clinical Fellowships and PhDs Clinical fellowships include both short-term 3 month fellowships and long-term 1 year fellowships. Yearly figures for short and long-term clinical fellowships are indicative and may change slightly over time. This will depend on the number of suitable applicants and available places at teaching institutions. Countries involved in the DR LINKS network are at different stages of development and will agree and implement their national frameworks at different rates.
|  | Achieved |  | Total - 2 Clinical Fellowships - 2 | Total - 18 MSc students - 5 Clinical Fellowships - 15 PhD Fellowships - 0 | 53 8 45 0 | 111 13 98 0 | 122 13 109 0
Source
Commonwealth Eye Health Consortium Year One start date June 2014 MSc course directors, clinical fellowships committees, host training institution records, research fellowship working group reports
| Output Indicator 4.2 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019
| Number of countries with domestic institutions that have agreed and implemented national frameworks for diabetic retinopathy screening and treatment | Planned | Start date: June 2014 No partners in DR network and no national framework for DR | 8 countries in DR network and 2 countries agree DR framework with their National Prevention of Blindness Committees (NPBCs) | 6 countries establishing national DR framework with their NPBCs. National frameworks in place in 2 countries. | 2 countries agree national DR framework 2 countries establishing their MoH DR framework 4 countries working towards a national DR framework | 4 countries agree national DR framework 2 countries establishing their DR framework 2 countries working towards national DR framework | 6 countries agree national DR framework 2 countries establishing their DR framework | 8 countries have their MoH DR framework in place and integrated into MoH services
|  | Achieved |  | DR Network established. Training for all participants held in London | DR framework agreed and in place in Botswana and Zambia. Development underway in Tanzania | DR frameworks agreed in Botswana and Zambia. DR frameworks being established in Kenya and Tanzania. Jamaica, Malawi, Nigeria and Uganda working towards their national DR frameworks. | 9 countries agreed national DR framework. 3 countries with DR framework in place. | 9 countries agreed national DR framework. 5 countries with DR framework in place.
Source
Commonwealth Eye Health Consortium Year One start date June 2014 DR Training Network Meeting report; VISION 2020 LINKS Programme records; signed agreements for each country; biannual VISION 2020 LINKS Steering Committee minutes
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019
25 | New eye care technologies developed | Planned | Start date: June 2014 Applications and hardware not available for smartphone and Electronic Patient Records System not yet available for use in lower and middle income countries | Consortium assembled and ready to implement project streams | Development and studies underway | Completion of validation studies Public release of Peek Acuity (smartphone app) | Public release of Peek Retina (smartphone attachment) Community trial for Peek screening underway | Community trial for Peek screening completed Botswana school screening trial commences (note 5) | Botswana school screening trial underway
|  | Achieved |  | Consortium plan developed and proposal approved | Peek studies on usability, DR, malaria retinopathy and school children completed. mRAAB and further school studies planned | Validation studies completed Public release of Peek Acuity (smartphone app) Paediatric visual acuity tablet app Peekaboo released | Peek Retina (smartphone attachment) publically released (April 2017) Community trial for Peek screening underway Preparations for Botswana school screening trial underway | Community trial for Peek screening completed in Kenya
|  | Source | [7 empty] | RISK RATING
|  | Commonwealth Eye Health Consortium Year One start date June 2014 Reports from Peek and OpenEyes teams and combined technology working group | [7 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  | Total (£)
| 10m |  |  |  | 1.7m |  | 11.7m
INPUTS (HR) | DFID (FTEs)
OUTPUT 5 The Trust | Output Indicator 5.1 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019 | Assumptions
A robust, responsive and supportive Trust | Unqualified audit of accounts received and annual results reporting aligned to common indicators presented in a manner consistent with results-based management principles | Planned | Start date: Jan 2014 n/a | Compliant accounts and reporting. Clear lines of communication | Compliant accounts and reporting. Clear lines of communication | Compliant accounts and reporting. Clear lines of communication | Compliant accounts and reporting. Clear lines of communication | Compliant accounts and reporting. Clear lines of communication | Compliant accounts and reporting. Clear lines of communication | Trust working effectively and managing programme and financial risks necessary for effective programming and therefore for results on the ground.
|  | Achieved |  | Thorough good clean audit. Annual report and accounts approved by Board of Trustees | Thorough good clean audit. Annual report and accounts approved by Board of Trustees. | Thorough good clean audit. Annual report and accounts approved by Board of Trustees. | Thorough good clean audit. Annual report and accounts approved by Board of Trustees.
Source
Trust's reporting; DFID annual review; audit check
| Output Indicator 5.2 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019
| Proportion of grantees satisfied by implementation and value added by the Trust | Planned | Start date: Jan 2014 Draft procedures, agreements, governance structures and reporting still being finalised | Grantee responses to satisfaction question included in reporting to the Trust | Grantee responses to satisfaction question included in reporting to the Trust | Grantee responses to satisfaction question included in reporting to the Trust | 90% positive grantee responses to satisfaction question included in reporting to the Trust | 90% positive grantee responses to satisfaction question included in reporting to the Trust | 90% positive grantee responses to satisfaction question included in reporting to the Trust
|  | Achieved |  | Relationship with Trust "has been very good," (CEHC Aug 2014) "very fruitful" (CEHC Jan 2015) and "extremely enabling" (ICTC Nov 2014) | Relationship with Trust "has been extremely enabling" (ICTC May 2015) and "very positive" (CEHC August 2015) | The Trust has "been immensely helpful and supportive" (CEHC Aug 2016) "The Foundation is very pleased with the relationship with the Trust" (FHF Aug 2016) | 100% positive grantee responses to satisfaction question included in reporting to the Trust
Source
Surveys conducted annually as part of grantees' reporting process. Reporting from coordinating partners.
IMPACT WEIGHTING (%) | Output Indicator 5.3 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019
10 | Development of monitoring indicators and evaluation reports showing capacity building and lessons learned | Planned | Start date: Jan 2014 n/a | M&E Strategy completed, key monitoring indicators agreed with implementation partners |  | Mid-term evaluations completed | Mid-term evaluation findings implemented | End-term evaluations underway and on track | Evaluations completed
|  | Achieved |  | M&E Strategy completed. Monitoring indicators agreed with LSHTM (for Fellowships, Research and Technology) ICTC (for African Trachoma) and PHFI (for ROP) | Reporting indicators agreed with all major partners. Inception report completed for Commonwealth Eye Health Consortium evaluation | Mid-term evaluations completed | Findings from mid-term evaluations implemented Summaries of mid-term evaluations published on Trust's website
Source
Trust's reporting to the board and to DFID; audited financial statements
| Output Indicator 5.4 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019
| At least two examples of how the Trust has influenced global policy and/or have leverage with respect to scaling up preventable blindness programmes | Planned | Start date: Jan 2014 n/a |  |  | Diabetic Retinopathy partners to be brought together in October to produce a declaration for the 2017 Commonwealth Health Ministers meeting Trust support of Commonwealth Health Hub with the Commonwealth Secretariat to produce a policy brief on eye health services and health systems strengthening for Commonwealth governments | Avoidable blindness to be included for the Commonwealth Health Ministers meeting 2017 The Trust contributes to a side event at the World Health Assembly 2017 | Commission and disseminate study on return on investment in avoidable blindness Commonwealth Heads of Government Meeting conclusions cover the ending of avoidable blindness Facilitate Vision for the Commonwealth coalition to lay the groundwork for meeting the commitments on vision in the CHOGM 2018 communique | May 2019 CHMM increases the momentum for meeting the commitments on vision in the CHOGM 2018 communique Lead the Vision for the Commonwealth coalition to lay the groundwork for a meaningful outcome on vision at the 2020 CHOGM. Joint evaluation with DFID completed on trachoma and findings disseminated at GET2020 meeting
|  | Achieved |  |  | Funding leveraged from END Fund and Hilton Foundation to support Trachoma elimination in Tanzania. 'Time to See' exhibition showcasing the Trust's word show to leaders at CHOGM in Malta | Diabetic Retinopathy partners brought together in October and produced a manifesto for the 2017 Commonwealth Health Ministers meeting Trust support of Commonwealth Health Hub with the Commonwealth Secretariat Trust information hub held at the Commonwealth Health Ministers Meeting in Geneva (May) Events held in Nigeria (April) and Tanzania (July) with DFID and senior Ministry of Health officials to promote the Trachoma Initiative | Avoidable blindness included in the Commonwealth Health Ministers meeting 2017 The Trust contributed to a side event at the World Health Assembly 2017 on avoidable blindness The Trust funded a brief on avoidable blindness in the Commonwealth, conducted in coordination with the Commonwealth Secretariat The Trust has form a coalition of eye health organisations (A Vision for the Commonwealth) to effectively lobby on issues related to blindness at CHOGM 2018 | Study on return on investment in avoidable blindness completed by PwC and disseminated at CHOGM Commonwealth Heads of Government Meeting communique included avoidable blindness and the Trust Coordinated successful effort in advance of CHOGM to secure £20m investment in trachoma elimination
|  | Source | [7 empty] | RISK RATING
|  | Trust's reporting to the board and to DFID; audited financial statements | [7 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) |  | Other (£) |  | Total (£)
| 5m |  |  |  | 5.6m |  | 10.6m
INPUTS (HR) | DFID (FTEs)
Notes
1) £0.3m from DFID funding supports other Fellowships, Research and Technology grants
2) Funding from other sources also supports the Trust's Youth programme (not shown in this log-frame)

## Diabetic Retinopathy
OUTPUT 2 Diabetic Retinopathy | Output Indicator 2.1 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019
Increase in the number of patients with sight threatening retinopathy treated in targeted Commonwealth countries | Number of patients with diabetes screened for diabetic retinopathy annually Targets are cumulative | Planned | India - 0 | Proposal development and mobilisation of key partners | Implementation due to being in 2016 | 2200 | 10000 | 24000 | 37000
|  |  | Bangladesh - 800 |  | n/a | 1000 | 4600 | 8000 | n/a
|  |  | Pakistan - 0 |  | n/a | 0 | 2000 | 4600 | n/a
|  |  | Belize - 1,000 (nationwide) |  | Screening begins | 2000 | 4500 | 7500 | n/a
|  |  | Dominica - 0 |  |  | 500 | 1000 | 1500 | n/a
|  |  | Jamaica - 0 |  |  | 1000 | 2500 | 4000 | n/a
|  |  | St. Lucia - 0 |  |  | 600 | 1400 | 2200 | n/a
|  |  | Fiji - 6,000 (nationwide) |  | Targets identified | 7750 | 11750 | 16200 | n/a
|  |  | Kiribati - 0 |  |  | 250 | 750 | 1500 | n/a
|  |  | Samoa - 0 |  |  | 200 | 800 | 1800 | n/a
|  |  | Solomon Islands - 0 |  |  | 1400 | 4800 | 6800 | n/a
|  |  | Tonga - 1,500 (nationwide) |  |  | 500 | 1500 | 3000 | n/a
|  |  | Vanuatu - 0 |  |  | 500 | 1300 | 2200 | n/a
|  | Achieved |  | Proposals approved. National DR Summit held and taskforce established. | India - More time spent on state-level advocacy | 5742 | 32200 | 42350
[5 empty] | Bangladesh - n/a | 3686 | 8018 | 9046
[5 empty] | Pakistan - n/a | 0 | 8822 | 12418
[5 empty] | Belize - 543 | 2584 | 2584 | 2584
[5 empty] | Dominica - 0 | 929 | 929 | 929
[5 empty] | Jamaica - 0 | 1779 | 1779 | 1779
[5 empty] | St. Lucia - 0 | 211 | 211 | 211
[5 empty] | Fiji - 4,231 | 8117 | 12460 | 12460
[5 empty] | Kiribati - 0 | 250 | 1293 | 1293
[5 empty] | Samoa - n/a | 495 | 2676 | 2676
[5 empty] | Solomon Islands - 572 | 2457 | 4488 | 4488
[5 empty] | Tonga - n/a | 0 | 653 | 653
[5 empty] | Vanuatu - 42 | 475 | 838 | 838
Source
Reporting from PHFI, The Fred Hollows Foundation and The Fred Hollows Foundation NZ. India - Community Health Centre Records, District Hospital records. Pacific - Monthly reports from clinic administration staff and World Health Organisation (WHO) Tool to Assess Diabetes and Diabetic Retinopathy Services (TADDS)
| Output Indicator 2.2 |  | Baseline | Year One: Dec 2014 | Year Two: Dec 2015 | Year Three: Dec 2016 | Year Four: Dec 2017 | Year Five: Dec 2018 | Final Year: June 2019
| Number of screened patients with diabetes treated for diabetic retinopathy annually Targets are cumulative | Planned | India - 0 | Proposal development and mobilisation of key partners | Targets identified | 220 | 1000 | 2400 | 3700
|  |  | Bangladesh - 450 |  | n/a | 500 | 1000 | 1620 | n/a
|  |  | Pakistan - 0 |  | n/a | 0 | 420 | 800 | n/a
|  |  | Belize - 241 (nationwide) |  | Treatment begins | 120 | 240 | 360 | n/a
|  |  | Dominica - 0 |  |  | 50 | 100 | 150 | n/a
|  |  | Jamaica - 0 |  |  | 80 | 170 | 300 | n/a
|  |  | St. Lucia - 0 |  |  | 20 | 40 | 60 | n/a
|  |  | Fiji - 2,500 (nationwide) |  | Targets identified | 1800 | 2700 | 3800 | n/a
|  |  | Kiribati - 0 |  |  | 50 | 100 | 150 | n/a
|  |  | Samoa - 0 |  |  | 0 | 50 | 100 | n/a
|  |  | Solomon Islands - 0 |  |  | 100 | 200 | 300 | n/a
|  |  | Tonga - 50 (nationwide) |  |  | 0 | 50 | 100 | n/a
|  |  | Vanuatu - 0 |  |  | 50 | 100 | 150 | n/a
|  | Achieved |  | Proposals approved. National DR Summit held and taskforce established. | India - Situational analyses completed | 273 | 1236 | 2613
[5 empty] | Bangladesh - n/a | 427 | 548 | 571
[5 empty] | Pakistan - n/a | 0 | 474 | 565
[5 empty] | Belize - 71 | 448 | 448 | 448
[5 empty] | Dominica - 0 | 28 | 28 | 28
[5 empty] | Jamaica - 0 | 52 | 52 | 52
[5 empty] | St. Lucia - 0 | 5 | 5 | 5
[5 empty] | Fiji - 1,334 | 2494 | 3631 | 3631
[5 empty] | Kiribati - 0 | 22 | 82 | 82
[5 empty] | Samoa - n/a | 68 | 227 | 227
[5 empty] | Solomon Islands - 81 | 353 | 614 | 614
[5 empty] | Tonga - n/a | 0 | 50 | 50
[5 empty] | Vanuatu - 17 | 51 | 227 | 227
Source
India - reporting from PHFI, Community Health Centre Records and District Hospital records. Pacific - measures of DR severity by BIO / direct ophthalmoscope or PEEK collected during outreaches and screenings.

## Notes
Notes
1 | "% endemic targeted districts with TF < 5% in children aged 1-9 years" shows the district level progress towards elimination made by countries. Impact Assessments are conducted after rounds of Mass Drug Administration (MDA) to assess the level of trachoma (TF) in children aged 1-9 years and if further rounds of antibiotics are required. If TF<5% then no further MDA is needed.
2 | The number of people who have had their trichiasis managed (e.g. received surgery) provided in brackets for context. Figures have been rounded to the nearest 500
3 | New data has shown a lower prevalence of trachoma than anticipated and therefore the total number of surgeries required to achieve elimination has reduced
4 | The previous indicator on antibiotics was: "Number of people treated with antibiotics in endemic target communities in Kenya, Malawi and Pacific Islands."
5 | The Botswana school screening programme was approved by the Trust in September 2017. The programme will work in coordination with the national Government to test the vision of every school child in the country and provide treatment to all those who need it. The programme aims to reach every school child by the end of 2020. Peek will train teachers to use smartphone technology to administer eye tests to their students. The health management information systems will then use the data upload from the mobile app to manage the patient pathway of children who require treatment.
6 | Assumption in log-frame: Assuming 4%-8% of pre-term infants <2,000 grams develop ROP that requires treatment (based on existing evidence). Evidence from programme: Evidence from the programme has shown that 2% of infants eligible for screening require treatment. • 10,529 eligible for screening up to March 2018 • 240 recommended for treatment up to March 2018 • 240/10,59 = 2.3% Targets for treatment in 2018 and 2019 have been revised accordingly
7 | Assumption in log-frame: Based on the programme working in 5 states with 4 Special Neonatal Care Units in each state. (20 units in total) Evidence from programme: Due to the coordinating partner’s licence to receive foreign funds being suspended, work was not able to start in the 5th state, Rajasthan. Screening and treatment is underway in 4 states in 18 units. Therefore, the ROP programme is underway in 18 units, rather than 20. (i.e. 90% of the assumption). Targets for screening in 2018 and 2019 have been revised accordingly.
8 | As of 2018 the Trachoma Initiative expanded programme activities in Nigeria, Uganda and started activities in Zambia. The percentage targets have been adjusted as the denominator (number of people to be treated) have increased. This has resulted in some percentage targets being reduced accordingly. The overall number of people to be treated by the Trachoma Initiative over 5 years has remained the same. Targets are updated every 6 months in response to new data to ensure that the programme is effectively utilising resources to locate people in need to treatment.

## Log-frame changes
Calendar Years
All programmes run on different programme years. Trachoma Africa: April - March DR and ROP: January - December Fellowships, research and technology: June - May To aid reporting, milestones and targets for Outcome Indicators 1 and 2 are by calendar year. Milestones and targets for Outputs 2,3,4 and 5 are also by calendar year.
Cumulative targets
All quantitative indicators have cumulative targets and results, except for Output Indicator 1.1, which shows the overall % reduction in surgery backlog and the yearly outputs in brackets.
Final Year
The Trust's agreement with DFID ends in June 2019. An additional column has been added to the log-frame to show the targets for the first six months of 2019. Several programme conclude at the end of 2018 and therefore do not have targets for 2019.
Output Indicator 1
Mid-year targets have been added, as suggested in the 2015 DFID annual review.
Outcome Indicator 2
This outcome now specifies "Number of eye health professionals trained," as it refers to eye surgeons and ophthalmologists
The numbers now should the number of eye health professionals trained each year. The previous version of the log-frame kept a cumulative running total over the years.
Trachoma
Output indicator has been revised "% of endemic districts achieving >80% coverage of MDA in the year", rather than "the absolute number of antibiotic doses distributed". Interrupting the transmission of trachoma requires >80% coverage, so this figure is more significant than the number of people who have received antibiotics.
Output indicators will be revised to better reflect the impact of F&E improvements. The Trust and the ICTC are well underway in developing this.
The Trust
To monitor and acknowledge the Trust’s global policy leverage, outcome indicator 5.4 has been added “At least two examples of how the Trust has influenced global policy and/or have leverage with respect to scaling up preventable blindness programmes”.
Diabetic Retinopathy
The Diabetic Retinopathy Initiative focuses on ensuring that diabetic retinopathy models of care can be integrated into the public health system. This has involved more time spent on advocacy with government health officials to ensure that the public system has sufficient buy-in. Success for the Diabetic Retinopathy Initiative would be the incorporation and adoption, by public health systems, of the models of care piloted by our partners.
We have changed output indicator 2.3 to be: “At least one example from each partner of how they have influenced national health policy with respect to integrating diabetic retinopathy models of care into the public health system.” This indicator would provide the opportunity to include important activities such as national summits, meetings with state health officials, and signing of agreements between the government and health care providers.
The previous output indicator 2.3 (the number of health professionals trained) has been removed, as this information will still be captured in Outcome indicator 2 (that sums the total of health professionals trained from all of the initiatives).
Retinopathy of Prematurity
Output indicator 3.3 has been removed (the number of health professionals trained) as this information will still be captured in Outcome indicator 2 (that sums the total of health professionals trained from all of the initiatives).
As with the Diabetic Retinopathy Initiative, output indicator 3.3 will now represent the advocacy work being conducted by the Public Health Foundation of India to incorporate retinopathy of prematurity models of care into the public health care system. The new output indicator 3.3 will be: “At least two examples of how PHFI have influenced national health policy with respect to integrating retinopathy of prematurity models of care into the public health system.”