Business Case and Intervention Summary
Nepal: Rural Access Programme (RAP)
Intervention Summary
What support will the UK provide?
RAP will increase the economic opportunities available to the poorest and most vulnerable people in seven of the remotest Districts in Nepal. Firstly, by providing employment for the poor maintaining rural roads and constructing economic infrastructure. Secondly, by developing agricultural and other small businesses to put in place the foundations for sustainable economic growth in the area. / The £36.5 million RAP programme will last for 4 years and will consist of 5 components: / Maintenance and upgrading of roads, £18.7m - to sustain and improve existing roads, trails and bridges; / Economic Infrastructure, £7.35m – Trails, trail bridges, markets, irrigation and other investments to stimulate economic activity; / Technical Assistance, £5.5m – cash crop and enterprise training (£2.5m), government capacity development (£1.5m) and ensuring corruption free implementation (£1.5m); / Rural Employment Guarantee Programme Support £3.6m – support to improve the delivery of the Karnali Employment Programme and the design of a National Rural Employment Guarantee Scheme programme; and / Results, Evaluation and policy support, £1.35m – support for third party monitoring, research and independent evaluation.
Why is UK support required?
High levels of chronic poverty make Nepal the 16th poorest country in the world[1], and one of the most unequal. Economic growth is hampered by geography and lack of investment, with Nepal having the lowest road access levels in South Asia. The poor in Nepal are also highly vulnerable to natural, economic, social and political shocks that trap them on or near the poverty line. In Nepal, all of these indicators are worse in the Mid and Far Western regions. The government’s capacity is limited to address these issues, so DFID support is required to provide direct support, develop government and private sector capacity, and stimulate economic growth in the poorest area of Nepal.UK support is therefore required now to: / Give the poorest access to work, to escape debt and start investing; / Train poor farmers and help them invest in higher value crops and access markets; / Ensure physical access to markets is maintained throughout the year; and / Focus enough support on one geographic area to develop sufficient production in high value products to sustain private sector markets.
What are the expected results?
RAP is expected to deliver the following high level results: / No of people lifted out of poverty – 20,000 (short term) / No of days of employment generated – 7.5m days / Roads maintained 2,400 Km years (i.e. 600 Km per year for 4 years) / Population benefitting from improved access - 800,000 / Increase 40,000 farmer’s incomes from cash crops by£130 p.a.
[1] Based on GNI/Capita

ABBREVIATIONS
ADB	Asian Development Bank
ARMP	Annual Road Maintenance Plan
CBS	Central Bureau of Statistics
DANIDA	Danish Aid Agency
DDC	District Development Committee
DDF	District Development Fund
DFID	Department for International Development
DoLIDAR	Department of Local Infrastructure Development and Agricultural Roads
DTMP	District Transport Master Plan
DTO	District Technical Office
FRA	Fiduciary Risk Assessment
FWDR	Far West Development Region
GoN	Government of Nepal
LEP	Labour-based, Environment-friendly, Participatory
LGCDP	Local Governance and Community Development Programme
LRN	Local Road Network
LRUC	Local Road Users Committee
MoLD	Ministry of Local Development
MWDR	Mid West Development Region
NLSS	Nepal Living Standard Survey
OP	Operational Plan
RMUG	Road Maintenance Users Group
SED	Safe and Effective Development
SDC	Swiss Development Cooperation
SP	Service Provider
SRN	Strategic Road Network
SWAp	Sector Wide Approach
VDC	Village Development Committee
WB	World Bank

Strategic Case

General context / High levels of chronic poverty make Nepal the 16th poorest country in the world[2]. Social exclusion and geographical isolation are the underlying causes, exacerbated by poor economic growth, and weak governance. For many, chronic poverty is compounded by climatic conditions – rain, floods, landslides, and drought[3] and social factors that worsen the outcomes for women, children and excluded groups[4]. / Gender inequality[5] is a key development challenge in Nepal, with significant gender gaps in education, and high levels of gender based violence. Lack of economic empowerment for women reinforces their position as second-class citizens. / Access levels are the lowest in South Asia, 10 million people live more than two hours walk from the nearest road and in the hills and mountains, more than 30% of the population live more than four hours walk from a road[6]. / All of these indicators are worse in the Mid and Far Western development regions, which have been left behind[7], and have consistently worse poverty rankings across all dimensions of poverty[8], leading to high levels of food insecurity and out-migration.[9] / [10] / The Western regions have the lowest densities of roads[11], with only a third of the national average. Two of the seven district headquarters are not connected to the national road network by a motorable road[12]. Not only does this constrain economic development but also access to government services e.g. health[13] and education. / Poor management of local government resources[14] has opened space for competition and political opportunism[15], which can potentially lead to local conflict. There is limited local government attention to economic issues, which leads to poor targeting, and tracking of resources, so that allocations for women, children, poor and excluded groups are often misused. / Economic opportunities exist[1] in many areas, e.g. niche agricultural products, tourism and hydropower, with large markets in India and China next door. These sectors can be developed, if access[2] can be established and maintained and economic development programmes supported. / Maintenance is largely absent leading to half of rural roads being unusable[16]. This situation denies the poor the access they need to markets and government services. Recent studies show that of the roughly £50m spent on rural roads every year only £1-2 m is spent on maintenance, a third of the 10% required. This represents a significant waste of resources with around £40m of rural road investments being literally ‘washed away’ every year due to a lack of maintenance. / Climate change and earthquakes pose additional risks. Infrastructure investments are at threat from natural disasters and if poorly built will substantially increase these risks. Future investments must be more resilient, including investments in agriculture that must recognise that increasingly erratic weather patterns are more likely. / Why is UK support required? / Nepal remains poor, unequal and fragile, conditions that fuelled the conflict. It is no coincidence that the Maoist insurgency had strong support in the Mid and Far West where the highest levels of absolute poverty and most severe challenges in terms of access and economic opportunity are found. Regional equalities are likely to become more important in the context of a move to federalism, and could fuel the re-emergence of conflict. Conflict that would result in the reversal of the overall poverty reduction gains of the last decade. As a result, the challenge of supporting peace building and stability on the one hand and accelerated, private sector led, economic development on the other, is at the core of DFID Nepal’s Operational Plan 2011-14 (OP). / This business case responds to strong demand[17] from the poorest people of Nepal for roads and economic opportunities and is well aligned with the Government of Nepal’s development priorities. RAP will deliver DFID Nepal’s Operational Plan results in short term jobs, access to markets and private sector led growth. It will contribute to DFID’s corporate results in rural road construction and maintenance, job creation and poverty reduction. It will support delivery of DFID’s Structural Reform Plan commitment to ‘Make British international development policy more focused on boosting economic growth and wealth creation’ and in addition will contribute to DFID’s results in gender and climate results by ensuring that women benefit disproportionately and that all investments are climate and disaster resilient. RAP will also contribute to the UK’s wider Prosperity agenda by supporting private sector led growth in Nepal and is fully consistent with the joint HMG strategy for Nepal. / This Business Case appraises the options for delivery of these results. It also assesses which options are most likely to ensure that results are sustainable and stimulate longer term, private sector investment in the RAP project area. It recognises that DFID is not the only agency working in rural infrastructure and private sector development. The Asian Development Bank (ADB), World Bank (WB) and Swiss Development Corporation (SDC) and most recently DANIDA also work in these sectors. These donors have traditionally focused on new construction and have performed poorly in supporting the necessary complementary activities required to ensure road investments lead to wider economic growth and institutional change. To fill this gap DFID have led the analysis of the needs of the sector and piloting of pro-poor approaches to infrastructure development and maintenancexix. DFID is also leading the way in implementing private sector led market development programmes in Nepal and will use the’ Making Markets Work for the Poor’ approach’ in RAP implementation. / Despite the number of donors, the requirements for support remain huge, and by no means met by current government and donor programmes. The Rural Transport Mid Term Expenditure Framework (MTEF) assessment indicated that a resource gap of around $1 billion exists in the rural transport sector over the next 7 years or around $130 – $140 million per year[18] if the government’s rural access targets are to be met[19]. To meet this shortfall and respond to demand, the Government has increased central allocations to the Ministry of Local Development (MoLD) from 8% to 12% of the national budget over the past 5 years. Approximately 40% of this goes to rural roads. Combined with rural road funding from other sources the rural road sector receives around 6% of the Government Budget.[20] According to MoLD regulations, 10% of this amount should be spent on maintenance. However, a survey carried out under the current phase of RAP found that maintenance is officially around 4% of rural road spending. The survey also showed that much of this funding is reallocated to rehabilitation and upgrading, and even new construction, whilst still being reported as maintenance. Actual allocations to maintenance are therefore lower still and can be estimated to represent just 2-3% of rural road sector funding, far below the amount required to maintain the rapidly growing rural road network. Consequently, over 50% of the rural road network is no longer motorable, representing an average loss of assets of £40 million per year. / Lessons Learned / Having established that there is a significant need in the sector the RAP design also recognises that there is significant experience in the sector to inform the design of the next phase of DFID support, not least the ten years of RAP implementation[21] [22] [23], see box below. / Key Lessons from RAP / 1. Labour-based works programmes are effective in reaching the poorest. Wages lifted 12,000 people directly out of poverty, in the last phase of RAP; / 2. Labour availability is highest in the West of Nepal, reflecting the limited alternatives available to the poor in the area; / 3. Simple targeting is effective at reaching the poorest, 100% of RAP workers were living below the poverty line before they started work on RAP; / 4. Direct targeting of Women is necessary to ensure they benefit disproportionately. RAP has had to enforce quotas to ensure women do not lose out. / 5. Savings groups, literacy training and income generation training schemes are all effective in giving workers access to increased economic opportunities. / 6. Market Development support needs to be extended to include traders and agricultural input suppliers if production is going to scale up significantly and sustainably. / 7. Government Support for Maintenance is available if the systems and incentives are in place to support its allocation and implementation. / 8. Institutional Development is required not just for government but also for the private sector and community groups. / 9. Climate change and disaster resilience can be integrated into RAP relatively easily, improving infrastructure and increasing the awareness of communities. / 10. Delivering safely and securely is possible as long as ‘safe and effective development’ approaches are used to resolve disputes over resources quickly. / 11. Third party anti-corruption measures that provide oversight at all levels of implementation do improve accountability, but do not replace the need for improved government and private sector led and owned anti-corruption measures.
B. Impacts and Outcomes / RAP is expected to deliver the following results: / No of people lifted out of poverty – 20,000 (short term) / No of days of employment generated – 7.5m days / Roads maintained 2,400 Km years (i.e. 600 Km per year for 4 years) / Population benefitting from improved access - 800,000 / Transport costs reduced by 50% in 6 RAP Districts / 40,000 farmers with increased incomes of at least £130 p.a. / Increased trade in RAP Districts / Capacity/Policy Results / Seven DDCs implementing co-funded rural road maintenance plans / 100 Community Road Committees receiving government budget for maintenance / 50% increase the uptake of the Karnali Employment Program by the poorest in pilots / National rural employment guarantee scheme based on RAP experience and pilots
[2] Based on GNI/Capita
[3] Nepal Vulnerability Assessment, Practical Action, 2010
[4] Multi-dimensional poverty assessment, WB, 2010
[5] NLSS 3, CBS, 2011
[6] Rural Transport Infrastructure Strategy, DFID, 2008
[7] Chronic poverty and Vulnerability Study 2011, DFID/HTPSE
[8] Population Census Preliminary Report, CBS, 2011
[9] Initial Effects on Household Economy and Labour Migration, RAP Study for DFID, 2010
[10] Source: Central Bureau of Statistics, National Planning Commission Secretariat, Government of Nepal. Preliminary Results of National Population Census 2011, Population of Nepal at a Glance, Sept. 2011.
[11] Rural Road Record Update, DoLIDAR, 2010/2011
[12] Study on Transport Constraints in Western Nepal (Karnali Highway Transport Corridor), Farhad Ahmed & Punya Prasad Regmi, December 2009, for DFID and WFP
[13] Mobility & Health, Case Study for Nepal Practical Action 2008. ‘Maintenance of the existing transport links must be prioritized and carried out through local community based management systems to ensure access to health facilities’
[14] Local Road Network Governance Assessment World bank and DFID, 2011
[15] Transparency and accountability in Construction (Nepal) March 2009, IT Transport for DFID
[1] Nepal Growth Diagnostic, ADB, DFID and ILO, 2009
[2] More than roads: using markets to feed the Hungry in Nepal, WFP 2010
[16] Estimates from the recent WB/DFID local road network assessment, 2011
[17] The Nationwide Public Opinion Survey On Contemporary Political Issues, World Bank, 2012, ranked lack access to road as their most important problem at the local level.
[18] Rural Transport Infrastructure SWAp Medium Term Expenditure Framework, GoN, 2009
[19] These targets are; all Districts headquarters reachable by road; all people in the hills and mountains within 4 hours of improved access; and all people in the Terai (plains) within 2 hours of a road.
[20] It is important to note, however, that not all rural road sector funding forms part of this national budget, with approximately 20% coming from local level.
[21] RAP 1 Impact study, WSP 2011.
[22] Preliminary findings of the Koshi Hills Impact study (DFID 2012, unpublished)
[23] RAP 2 Maintenance Pilots

Appraisal Case
A. What are the feasible options that address the needs set out in the Strategic case? / Theory of Change / Based on the identified needs and evidence from previous interventions a theory of change was developed, that enabled the necessary components of support to be defined. / Rural Access Programme: Theory of Change / RAP's theory of change relies on the core narrative set out below. This is well supported by the available evidence, which is elaborated further in the evidence section: / Context: The rural poor in Nepal lack access to capital to invest in economic activities, and access to markets to sell their produce, locking them in chronic poverty. This is supported by recent analysis in the Mid and Far Westvi of Nepal that shows that lack of access to productive assets and remoteness are key determinants of poverty. / Inputs – RAP will provide employment, transport infrastructure and income training. Previous phases of RAP have proven DFID’s ability to deliver these inputs effectively[24]. / Outputs – RAP inputs generate savings that can be invested in cash crop production combined with increased access to markets provided by improved infrastructure. RAP1 studies and the international literature[25] show that rural infrastructure investments stimulate local economic activity. / Outcome – Increased investment and private sector income generation. Both RAP 1XXII and DFID agriculture programesXXXI show that investments in higher value crops lead to sustainably higher earnings and reinvestment in increased production. / Impact – Increased growth and poverty reduction in RAP Districts. As noted in DFID’s recent literature review ‘A huge body of literature reported a causal link between road development and poverty reduction’[26]. / This theory of change allowed the inputs required to achieve the desired results to be identified. These include the investments required in road maintained, economic infrastructure and short-term jobs and the institutional support for the government and private sector required to sustain improvements in the longer term. These inputs were then costed and grouped into components so that the appraisals could assess how well they would be delivered by the three identified implementation options. / Mid and Far West Implementation Area of RAP / RAP components / It is intended that the £36.5m programme will build on the proven labour-based approach developed by RAP and focus on 7 Districts in the Mid and Far West of Nepal. The 7 Districts were selected based of their poverty levels and the MoLD’s preference for support to a coherent ‘cluster’ to improve implementation efficiency and impact. This is seen is as a model for future support in the sector with development partners each agreeing to support a ‘cluster’ of Districts based on increasingly harmonised technical approaches (albeit with different funding modalities). / To support the theory of change set out above 5 components were identified; / Maintenance and upgrading, £18.7m - to sustain and improve existing roads, and bridges. / Economic Infrastructure, £7.35m– trails, trail bridges, markets, irrigation and other investments to stimulate economic activity. / Technical Assistance, £5.5m, including: - Cash crop, market development and enterprise training (£2.5m); - Government capacity support (£1.5m); and - Implementation support (£1.5m). / Rural Employment Guarantee Programme Support £3.6m – support to improve the delivery of the Karnali employment programme and the design of a national employment programme. / Results, Evaluation and policy support, £1.35m – to conduct third party monitoring, research and lesson learning to ensure implementation (including corruption) is independently monitored and RAP lessons are fully captured. / 1. Maintenance and upgrading, £18.7m The programme will mobilise Road Maintenance Groups (RMGs) drawn from communities alongside existing roads in the RAP Districts. Priority for employment will be given to the poorest, women and vulnerable members of communities. These groups will be paid to maintain and upgrade existing roads. RMGs will also be used as the focal point for training in agriculture, marketing, savings and social empowerment, using the approaches successfully implemented in RAP 1 and 2. / 2. Economic Infrastructure, £7.35m Previous RAP experience has shown that additional economic infrastructure is required to maximise the impact of improved access. Consequently, trails, trail bridges, markets, irrigation and other investments to stimulate economic activity, will be provided under RAP. This will also allow the programme to ‘reach out’ beyond the road corridors in the seven Districts. / 3. Technical Assistance, £5.5m – / Substantial technical assistance is required to: / Support Private Sector Development (£2.5m) / Provide training to 40,000 farmers on income generation activities e.g. developing markets for local high value resources, agricultural processing, tourism etc. based on local market assessments. This component will draw on the DFID Nepal market development programme for technical support; / Develop government and private sector capacity to plan and implement economic development activities; / Government capacity support (£1.5m) / Training, policy and institutional support with a focus on: / Providing incentives for good performance; / Piloting Output based maintenance systems i.e. providing limited funds to government on a reimbursement basis; / Developing government financial management and procurement capacity; and / Supporting local government develop economic plans and capacity to work with the private sector. / Ensure implementation support (£1.5m); / Support RMGs, to develop their institutional capacity drawing on lessons from other DFID community development and local governance programs; and / Support implementation to ensure that RAP is delivered effectively and the misuse of funds and conflict over resources is prevented. / 4. Rural Employment Guarantee Programme Support £3.6m This component will improve the effectiveness of the Government’s Karnali Employment Program (KEP) in the Mid and Far West of Nepal. Technical assistance will be provided in two pilot districts and at the national level. Support will focus on improving targeting and awareness, wage payment systems, registration, planning and monitoring, transparency, capacity and coordination with local government. The TA will also ensure that lessons learned from RAP pilots inform the roll out of a National Employment Guarantee Scheme, and the development of Nepal’s wider social protection framework. / 5. Results, Evaluation and policy support, £1.35m To provide DFID with assurances that implementation is being delivered effectively RAP will contract a third party to undertake continuous monitoring of the programme including financial and administrative arrangements overseen by DFIDN. DFIDN will also undertake an independent evaluation. This component will also ensure that separate studies can be conducted to capture lessons on specific issues specified by the RAP Steering Committee and used to inform the design of future donor and government programmes. / Longer Term Strategy / This phase of RAP continues to focus on delivery but with support to build government and private sector capacity so that subsequent stages can rely less on direct DFID implementation. It recognises that the required institutional changes to make this happen will take time and in the current context may not be possible to complete during this phase. For these reasons a four year implementation period is recommended, after which Nepal’s political direction and approach to Federalism may be clearer and a new phase of support can be designed which can reflect the new context and political scenario. / Options Appraised / The appraisals assess which delivery options are most likely to support the delivery of the Theory of Change and the RAP results set out the Operational Plan most effectively. Three options were identified which were appraised against their ability to deliver the programme i.e. a rural infrastructure and private sector development programme in the West of Nepal: / Direct implementation: Contract a service provider to implement the programme and provide technical assistance to central and local government. / Through Government: Provide financial aid to government for implementation with technical assistance contracted separately to support implementation. / Through a Multilateral Development Bank (MDB): Develop a joint programme with the World Bank or Asian Development Bank, who both have programmes in the sector. / Counterfactual / If DFID were not to support RAP, a number of direct and indirect effects would result. / Impact / 20,000 people would remain in poverty in one of the poorest areas of Nepal; / Access levels in the Mid-far West would remain the lowest in Nepal; / Significant investments in rural roads would be wasted; / Infrastructure foundations for development would not be put in place in 7 Districts; and / The environment for the private sector to develop in the Mid-Far West would remain limited. / Institutional / Rural road maintenance budgets and capacity would remain largely absent; and / Public Financial Management reforms in MoLD would be slower. / Sector influence / Policies on rural infrastructure particularly for labour based approaches and maintenance would remain unrealistic and unimplemented; / Results based financing would not be adopted by donors working in the sector; and / The next generation of government employment schemes would be less effective in reaching the vulnerable. / In addition, DFID is currently leading policy development in the sector, especially in maintenance and support for the next generation of government employment schemes and social protection policy. Not providing support would leave a vacuum that is unlikely to be filled by the other donors, leading to the continued fragmentation of support for these areas and the significant levels of wasted investment continuing. For example, the £40m p.a. loss of rural road assets and the large targeting and corruption loses in Nepal’s employment schemes would continue. / Summary of Appraisals / Political and Institutional Appraisal / RAP is a well-designed programme from a political, institutional, private sector and counter fraud perspective; however, the programme faces major challenges in achieving its institutional and counter-fraud goals (including a lack of political will; major financial management weaknesses in government and; a sector facing high levels of corruption). / In particular, RAP will need to actively promote debate on the pro-poor labour-based construction methodology that RAP 2 promoted and that RAP will continue to support. This approach is very much welcomed by the poor, but not by political leaders who prefer the speed by which roads can be constructed through machinery (and who can make money through machinery based contracts). This risk is partly mitigated in RAP by the focus on maintenance (which is inherently more labour-based). However the programme will need to actively work to promote understanding of pro-poor, labour based approaches in the sector, and assess the political economy risk relating to pressures for machinery use during implementation, hence the importance of the institutional and policy component and the strong linkage to Karnali Employment Programme and its national successor. / In addition, past rural road and local governance programmes have shown that local government can improve its accountability and performance[27] but this is a slow and challenging process in Nepal’s fragile, political environment. Consequently, the RAP staged approach that recognises that local government institutions can only improve slowly, incrementally and with the right incentives is appropriate. Finally, the appraisal notes the need to ensure lessons from the Maintenance pilot, which is still under implementation, are continuously fed into RAP implementation.[28] / These issues have been clearly identified in the design and viable methods to track improvements and inform decisions as to when and how to move towards greater use of government systems e.g. the possible move to performance/output- approaches included. / RAP is also designed to cope with the changing political context. Both national and local level elections are expected over the period of the programme and these will bring disruption to local authorities. The flexible approach allows the programme to accommodate these changes, with a faster transition to government systems should elections by completed early, and state effectiveness improve, and the ability to remain in ‘bi-lateral mode’ should the situation deteriorate. / The move to Federalism remains a significant issue and one, which may affect the project in the outer years. The main implication would be the need to redesign the capacity building elements to support federal structures and possibly revise the geographic area for implementation. Again, a phased and adaptable approach to programme implementation will allow the programme to evolve to these changes, albeit requiring continuous and close project management from DFID to ensure the programme remains appropriate to the uncertain context. / Conflict Appraisal / Selection of where roads and other infrastructure will be built or maintained, of the technical approach adopted (manual or mechanised), of contractors, and of individuals for employment (maintenance groups and programme staff) will all be subject to contestation and potential political and criminal distortion. To avoid this, the systems of decision-making will need to be transparent and accountable, and seen by the public to be so. To avoid further frustration at the perceived slow pace of peace dividend delivery, the programme must deliver jobs quickly and visibly. Payment demands by criminal/political groups will require good use of Safe and Effective Development (SED) approaches and the Basic Operating Guidelines (BOGS). Payments for enforced purchase of land or compensation for damage must be handled fairly and sensitively, and potential public perception of programme corruption minimised through strict financial systems, third party monitoring and use of public audits. / The importance of public perception relating to these risks cannot be over-emphasized. If it is negative, even if unfairly so, the programme will exacerbate conflict dynamics. As such, an effective communications strategy will be essential, both locally and nationally, as will strong SED practice at all times. / It is recognised that any option not through government may reinforce a public perception that the state is either unable or unwilling to provide assistance. However, this risk is considered subservient to the need to manage the other identified conflict risks. Nonetheless, everything possible must be done to publicly demonstrate a sense of partnership between the programme and government. This is addressed in the design by embedding the project in DoLIDAR centrally and in District offices, and ensuring project management decisions are led by a joint DFID and government Steering Committee. / Technical Appraisal / To date rural road maintenance has been constrained by complicated planning and institutional arrangements, underfunding and limited institutional capacity[29]. Therefore improvements, particularly simplification and streamlining, in the existing procedures and additional resources provide great opportunities to demonstrate that much needed maintenance of rural transport infrastructure can be delivered simply and cost effectively. / The on-going RAP 2 Pilots have developed a feasible approach to rural road maintenance and how to sustain long term funding. This approach includes technical capacity building in local government, reliable road condition surveys and the development of annual road maintenance plans (ARMPs) using a common Government approved format. The economic infrastructure component is relatively straightforward, will be based on existing VDC plans, and will be delivered using labour-based approaches. RAP will also ensure that this infrastructure is climate and disaster resilient. / The support to private sector development in agriculture will use the DFID Making Markets Work for the Poor approach. This has already been successful in supporting the vegetable and dairy sectors in Nepal[30]. RAP will adopt a similar approach based on rapid market assessments in the Project Districts, to identify the critical constraints to agricultural business development in the area and then provide support to address them. / Fiduciary Appraisal / As noted in the Rural transport Infrastructure Fiduciary Risk Assessment 2012[31] and in the World Bank Transport Sector PER 2011, the risks in the sector are high, see table below. / Details Risk Ratings / Government / Public Financial Management System High / Risk of Corruption High / Assessment of Reform Credibility Partially credible / Short term FMS proposed for RTI Pilot maintenance works Moderate/substantial / MOLD PEFA and FRRAP reforms- March 2012-2015 Partially credible / 14 out of the 15 FRA risk factors assessed by the FRA are rated as high[32]. In particular, the infrastructure sector is prone to corruption. Multiple small contracts are let with limited supervision and control, which in totality add up to significant amounts of money being at risk (6% of all Government spending in Nepal). / Project risk mitigation measures therefore include: / Very limited use of government systems: / External oversight at three levels; - Beneficiary through public audits; - Permanent District staff to monitor implementation; and - Programme level through third party monitoring / Integrated (technical and physical) audits and spot checks. / Payment based on results. / The RAP service provider will also be required to fully own and implement DFID’s anticorruption strategy and ensure that sub-contracted organisations are fully aware of DFID’s anti-corruption requirements. / Economic Appraisal / The economic appraisal focuses on quantifying and monetising the returns to maintenance associated with reduction in transport costs and the additional income generation associated with increased market access (mainly with vegetable and livestock) for each kilometre kept open. The appraisal is summarised in table below. / The economic appraisal is based on the following assumptions: / Benefits ceasing one year after the investment stops; / Maintaining the road allows it to open for an additional 50% of the year – based on evidence that where roads are not maintained 50% of roads are inaccessible in Nepal; / A 50% reduction in transport costs, a conservative estimate other interventions associated with new roads produce estimates closer to 95%[33]; / Additional income generation of £13,500/km/year from increased agricultural and livestock production, based on past RAP and DFID agriculture programmes evidence[34] / In addition each options was assigned an assumed ‘probability of delivery’ based on the experience of delivery in Nepal. These assumptions are summarised in the table below and were applied to the net benefit streams for each option. / Options and Probabilities of Delivery[35] / Option Probability of Delivery Justification / 1: Direct 90% Based on previous RAP experience of successful delivery / 2: Government 50% Based on current experience of the government managed rural road network where that 50% of the rural road network not passable and evidence of misuse of funds / 3: Multilateral 80% Based on performance of such instruments in Nepal and assumes a delay in effective start-up based on recent experiences / A standard cost benefit analysis was then conducted based on these assumptions and gave the following results. This analysis shows the option of direct delivery as having the highest returns followed by the multilateral and then government implementation option. This is primarily due to the probability of success weightings assigned to each option. This is a relatively crude way of evaluating the options but is valid given that the weightings are based on actual project delivery experience of similar projects in Nepal. / Summary of the Economic Appraisal / Option Net Present Value @ 3.5% Discount Rate Net Present Value @ 12% Discount Rate Internal Rate of Return Benefit/Cost Ratio @ 3.5% / 1: Direct £16.26 million £9.98 million 52% 1.49 / 2: Government -£5.71 million -£6.61 million -12% 0.83 / 3: Multilateral £12.84 million £3.05 million 5% 1.04 / Option 1 – direct implementation shows large positive returns. This is consistent with other maintenance-focused projects around the world[36], and is due to the relatively small amounts of maintenance finance required to preserve relatively costly road assets that ensure that access benefits are sustained year round. It is based on based on a 90% probability of successful delivery of the net benefits. This high rating is based upon the performance of previous interventions (from RAP 1 and RAP 2) delivered through this approach. The through government option has far lower returns because of its lower probability of success (50% for government delivery). It is also far more risky from many other perspectives e.g. corruption. Option 3 has the second lowest returns mainly due to a slightly lower probability of delivery and delays in the realisation of benefits. This is based on experience in Nepal on the ADB managed RRRSDP programme. / The ecomonic appraisal therefore recommends that option 1 / Sensitivity analysis of the Preferred Option: Option 1 Direct Implementation / Sensitivity analysis was conducted on option 1 to calculate the switching values at a 3.5% discount rate point of the main benefit variables (the costs having largely been fixed). These were found to make the project unviable if: / The probability of successful delivery fell from 90% to 60% / The number of months the roads are kept open fell to 3.9 months from 6 months / The income generation benefits fell by 40% i.e. from £13,500/Km to £8,444/Km / These indicate that the project is reasonably robust, i.e.: even if the underlying delivery environment (which determines the probabilities of success) deteriorates, the intervention can still be justified. However these levels of deterioration are possible, and turn the net benefits negative. / Consequently the economic viability of the project is dependent on ensuring the full benefits are realised. For example, the sensitivity analysis shows that the number of months the roads are kept open cannot fall below 3.9 months if the investment is to be economically justified. Similar results are true for the production values and the probability of delivery success, which all become negative if the expected benefits drop by more than 30%. This reinforces the selection of the management option with the highest probability of successful delivery and the need for close management of the project during implementation. / Social Appraisal / The RAP approach has proven its effectiveness by linking a labour based approach to infrastructure development with improved access, economic growth and poverty reduction. In the new design, greater emphasis will be placed on sustainability through maintenance, private sector development and an intensive geographic focus in some of the poorest districts of Nepal. This design presents a number of opportunities to mainstream approaches, in areas of institutional development and planning capacity as well as delivery systems for private sector led development. / The regional focus on the Mid and Far West is strongly supported, because of its high incidence of chronic poverty. The shift to a maintenance approach offers potential to set in place a national sustainable employment generation programme, but does require greater attention to the institutional development aspects of the project. There are also a number of opportunities to strengthen the evidence underpinning the theory of change and strengthen our understanding of links between employment and access, and sustainable poverty alleviation and vulnerability reduction. RAP also presents the opportunity to work on Nepal’s employment guarantee policy, which RAP will support in two districts to improve implementation of the Karnali Employment Program and influence the proposed national programme. / The project has a good track record in achieving Gender Equality and Social Inclusion (GESI), that will be strengthened in the following areas: / Application of equal wages for workers, and removal of local distortions in wage rates for women, elderly and disabled groups; / Development of more robust methods of identifying the poor, through a combination of community based and proxy means testing; / Support for landless and extreme poor groups, to mitigate risks of ‘capture’ of benefits; / Household level poverty analysis to explore the impact of employment opportunities and constraints to sustainable chronic poverty alleviation; and / Links to VDC and Ward Citizen Forums to increase local voice and accountability. / Environment, Climate and Disaster Resilience Appraisal / This programme is rated category ‘B’ in DFID’s Climate and Environment Assessment (CEA) methodology, as a result a separate Climate and Environment Assessment was carried out.[37] The CEA notes that there are significant environmental and climate risks and opportunities for this programme. Maintenance of roads is challenging in the already climate vulnerable steep and dynamic slopes of the Mid and Far Western Region that are prone to earthquakes and landslides. There are opportunities too. If early actions are taken to integrate climate and environment into road maintenance activities, the programme can develop innovations and skills in adaptation and climate proofing of roads. / The appraisal however recognises that the works in the phase of RAP will have less environmental impact than the new road construction undertaken in RAP 2. However, the labour based, environmentally sensitive approach and techniques adopted in RAP 2 will remain appropriate and should be continued. / The key environmental issues that will be addressed in the programme are: / Increased environmental risks due to poor construction management, e.g.: damage to water courses and increased risks of landslides; / High Climate and disaster vulnerability e.g. Drought, floods and landslides; / Low adaptive capacity of the population due to poverty and lack of alternative livelihoods; / Low levels of awareness on climate and environmental issues; / Very weak institutions to implement and enforce environmental regulations; / The need to ensure increased access does not lead to increased deforestation; / Opportunities to introduce of bio-engineering, limiting the amount of material use and spoil and other environmentally sensitive approaches; / Opportunities for raising climate awareness; / Opportunities for increasing the capacity of local level government agencies on environmental issues; and / Opportunities to work in close collaboration with existing environmental and climate programmes i.e. Himali, MSFP, PPCR and NCCSP. / Options Analysis / Option 1 - Direct implementation through a service provider / The Social appraisal supports the selection of Option one, implementation through an external service provider with a view to mainstreaming implementation over time, with due note of the challenges of the delivery environment in the Mid and Far West. Similarly, the Environmental appraisal ranks option one as the most appropriate due to the higher degree of scrutiny and higher possibility of continuous monitoring/capacity building/community involvement in environmental risk mitigation for infrastructure works. Option 1 also presents opportunities for the integration and technology transfer of CC/DRR issues into the programme working closely with the DFID supported Nepal Climate Change Support Programme. From a fiduciary risk perspective, Option 1 also provides the best safeguards and can introduce incentives for good performance. The TA and the pilot funding modality approach will also support strengthening of government systems. Option 1 also performs best from an economic perspective, because of the increased likelihood of timely and effective delivery of outcomes. This is linked to the technical appraisal that provides clear evidence that direct implementation delivers better than government or WB/ADB implementation. It is also more likely to deliver better private sector development outcomes than the two alternatives. The exception to this is on the institutional appraisal where the direct implementation nature of the programme will reduce its ability to deliver state building outcomes. This has been mitigated to an extent by rewarding government capacity improvements and supporting them with TA but it still means that option 1 is ranked 2nd. In addition, the conflict appraisal recognises that RAP will not be able to support government capacity building as effectively as Option 2 but recognises that it will be able to prevent political capture of resources and fully implement SED approaches. / Option 2 – Through Government implementation using financial aid / Institutionally the through government option is preferred as it will lead to the greatest development of state capacity. However, the high corruption risks and slow delivery rates would undermine the projects ability to deliver, making it the worse option from a fiduciary risk perspective. These factors also make it the third ranked option from both a technical and environmental perspective, mainly due to the limited capacity of local government to monitor works effectively. Limited government capacity, also leads to a lower probability of effective delivery making it a less attractive economic option. From a social perspective, implementation through government is ranked second, as the important opportunities for mainstreaming approaches are limited by the current weak capacity of local administration to implement directly. The conflict appraisal also highlights the need for RAP to support government capacity building but recognises the government’s weak delivery and corruption control capacity is unlikely to prevent local resources capture and therefore will be a source of local level conflict. Hence, it is the least preferred option. / Option 3 - Through a Multilateral Development Bank (MDB): / Experience from previous programmes implemented through the Multilateral Development Banks has shown that implementation is technically likely to be slower and of lower quality than through direct implementation but better than Government implementation. The same is true in terms of fiduciary risks and environmental concerns. The economic appraisal ranks the MDB option second due to its slow and slightly lower probability of delivery. Although nominally implemented by the Government previous programmes focusing on delivery have also been the weakest in terms of supporting institutional development. From a conflict perspective the MDB option will have some capacity to reduce conflict risk in particular by improving the transparency of resource allocation but a full safe and effective development approach is unlikely to be adopted resulting in this option being ranked second. Implementation through donor partners is also ranked third due to a lack of mainstreaming of social needs in the MDBs approaches e.g. in monitoring, planning and implementation. / The table below presents the design team’s ranking of the options in each of the appraisal areas. / Option Tech. Social Inst/Pol Fiduciary Conflict Environ. Econ. Total / Direct 1 1 2 1 1 1 1 8 / GoN 3 2 1 3 3 2 3 17 / WB/ADB 2 3 3 2 2 3 2 17 / The recommended implementation approach based on the above appraisals is Option 1, direct implementation through a competitively procured service provider. / It should be noted that this assessment places a premium on immediate direct delivery, as required to support the peace process, the demand for tangible evidence of increased economic opportunities and to support the development of the private sector. The weaker assessment of Options 1’s ability to address longer capacity building needs is however of concern and the programme will need to be aware of the need to build systems and capacity in government and with the private sector. / B. Assessing the strength of the evidence base for each feasible option / Option Evidence rating / 1 Strong (medium at the wider impact level) / 2 Medium/Strong / 3 Medium/Strong / The evidence of impact is strong throughout the theory of change, apart from evidence of wider attribution at the impact level[38]. / The international evidence is strong on the impacts of rural roads on rural poverty reduction, the World Bank[39] and IFPRI[40] both concluding that physical access to markets is a necessary, but not sufficient requirement for poverty reduction in rural areas. In simple terms the global evidence shows that communities without roads are poorer that those with roads (after controlling for other factors)xxvii. This is confirmed by a number of studies conducted in Nepal where remoteness (measured as the time taken to the nearest road head) is highly correlated with poverty, most notably in the recent DFID Chronic poverty and Vulnerability Study based on Nepal Living Standard Survey Data from 2010. In addition, several studies quantify the reduction in transport costs associated with moving from porters to road transport, i.e. up to 90% reduction in transport costs per tonne/KmXIX after road opening. This lays the foundation of the evidence base for RAP i.e. that improved access is fundamental to stimulating economic growth. / In addition, the theory that employment is effective in reducing short-term poverty is supported by the evidence from RAP where the average household incomes of those working on the roads increased by 220%. This was enough to lift all workers above the poverty line whilst being employed by RAP, reducing debt levels and increasing investment in income generating activities. RAP experience also shows that it is possible to target benefits effectively; women made up 51% of RAP beneficiaries and 54% were from socially excluded groups. / The evidence that savings from wages increases farmers likelihood to invest in cash crop production is also strong. Only 20% of the rural poor have access to formal credit[41] making them reliant on money-lenders who charge 40% or more for credit, discouraging any risk taking with borrowed money. Evidence from RAP impact studies shows that RAP’s approach of generating savings from wages and then lending them out through savings groups reduces interest rates to below 15%, making investment in cash crop production from loans far more attractive. Here the evidence from RAP shows that farmers are willing to invest if access to finance, skills training, and markets are available. For example in RAP 1, farmers earned an additional £50 - £280 per year[42] from cash crop production, based on a RAP survey of 1,544 Households. These returns are similar to those found in the recently completed Market Access to Smallholder Farmer Project supported by DFID[43] that showed an average income increase of around £130 per farmer per year. The area where the evidence is weaker is on the wider impact on the ‘road influence area’, defined as within 2 hours walk of the road. RAP impact work has, so far; only able to measure that 70% of poor households in the road influence area experienced an increase in food security as a result of RAP.[44] This lack of evidence is currently being addressed through the Koshi Hills Impact Study. / The assessment of delivery options performance (in particular to inform the economic analysis) is all also based on strong evidence from recent rural road programme performance in Nepal. Evidence of direct delivery is based on the experience gained in RAP 1 and 2. Evidence of MDB delivery is based on experience from the Rural Reconstruction and Rehabilitation Sector Development Programme (RRRSDP) an ADB financed project managed by the Ministry of Local Development (MoLD) and co-financed by DFID. Evidence of government delivery is based on experience from the Local Government and Community Development Programme (LGCDP) working with MoLD[45] and Fiduciary Risk Assessments completed in early 2012. / What is the likely impact (positive and negative) on climate change and environment for each feasible option? (See Environmental Appraisal Section for justification) / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 B B / 2 A B / 3 D D / A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation / C. What are the costs and benefits of each feasible option? / As detailed above, the economic appraisal for RAP was run for all costs and the main benefits which could be quantified and monetised; all three feasible options were assessed. The direct implementation option generated the highest returns (with an IRR of 52% and net present value of £16.3 million at a 3.5% discount rate). The multi-lateral option was less viable with an internal rate of return of only 5% and a net present value at 3.5% of £12.8m. This is mainly due to the delays in implementation expected when working through the WB and ADB (based on project experience in Nepal[46]) which delay the accrual of benefits. / The through Government option has the lowest returns, largely due to the far higher delivery and fiduciary risks. In addition the private sector, social and environmental risks are also higher implying that this option is neither viable nor desirable. / The economic appraisal therefore indicates that Option one is the most beneficial. In addition, the economic assessment is based on a number of other conservative assumptions, the most significant being that benefits will return to pre-project levels one year after completion. This reinforces the importance of investing in institutional change and capacity development in the government and private sector to ensure sustainability and long-term project viability. / This is a reasonably robust outcome that demonstrates that the RAP programme, directly delivered, will achieve value for money even if costs increase or benefits decrease by around 30%. This analysis does however note the need for close project management to ensure timely and effective delivery of project outputs to ensure the project outcomes and overall impacts are achieved. How the programme will be managed to ensure delivery is addressed in the following sections.
D. What measures can be used to assess Value for Money for the intervention? / Value for money in RAP can be assessed across all ‘three E’ indicators of Economy, Efficiency and Effectiveness. Economy indicators will ensure that supervision costs as a percentage of works costs remain the same or lower. Efficiency indicators will track planned versus actual delivery of outputs to pinpoint where progress is delayed or delivery costs are rising. Effectiveness indicators will track the programme’s impacts on private sector growth, income generation and poverty alleviation in the RAP area. The detail on each of these areas is set out below. / Economy indicators: Technical assistance will remain below 15% of the total cost. Pre-financing costs of the less than 2% of works costs. / Efficiency Indicators: 60% of the funding will be paid as wages to the poorest and most vulnerable people; the average cost of maintenance/km of road will be less than NRs 80,000/Km; and the use of an entirely output based contract with the main contractor with payments linked to the delivery of logframe results, will all ensure delivery efficiency. / Effectiveness Indicators: The programme monitoring and impact evaluation system will ensure that DFID can monitor delivery of the RAP outcome and impact results i.e. poverty reduction for 20,000 people, maintenance of 600 km of roads every year for four years, improved access for over 800,000 people and £130 annual increase in cash crop incomes for 40,000 farmers. / In addition, The emphasis on sustainability and in particular, climate resilience, which is embedded in the project design, will also ensure RAP contributes to a significant, sustainable increase in the value of roads and therefore overall effectiveness. Similarly, the technical assistance support for the Government, the Private Sector and the Karnali Employment Program will increase the effectiveness of RAP by increasing the impact beyond RAP implementation e.g. by influencing the design of the Government’s National Rural Employment Guarantee Scheme.
E. Summary Value for Money Statement for the preferred option / Based on the assessments above Option 1 should be selected to deliver maximum benefits and value for money. / Option 1 provides the highest likelihood of successful delivery and impact on poverty reduction. This is based on the experience of the previous phases of RAP that have delivered direct impacts efficiently, with more than 60% of the resources being paid out in wages to poor and vulnerable people. / As noted in the economic appraisal sustainability has a significant impact on the overall effectiveness of RAP; particularly whether maintenance and production of higher value crops continue beyond the project period. Evidence from the RAP maintenance pilots shows that resources are available at the District level for maintenance if the systems are in place to use them. Similarly, evidence from the DFID funded Market Access For Smallholder Farmers programme show that a private sector led approach provides all involved with the incentives to continue production beyond the end of the project, with average annual incomes increasing by around £130 per farmer for an investment of under £70 per farmer. / It should be noted that that technical assistance costs of £5.5m (roughly 15%) are high. However, these are justified due to the need for close project support and monitoring in the weak capacity and high fiduciary risk environment that RAP will be working in and the need to provide adequate private sector development support to ensure ‘market take-off’.
[24] RAP 1 project Completion report, DFID 2009
[25] Khandker S R, Bakht Z and Koolwal G B, 2006, The poverty Impact of Rural Roads: Evidence from Bangladesh (Policy Research Working Paper 3875), World Bank, Washington DC Fan S and Chan-Kang C, 2005, Road Development, Economic Growth, and Poverty Reduction in China (Research Report 138), International Food Policy Research Institute, Washington D. C. Deolalikar A B, 2001, The Spatial Distribution of Public Spending on Roads in Vietnam and its Implication Dercon S, Gilligan D O, Hoddinott J and Woldehanna T, 2007, The Impact of Roads and Agriculture Extension on Consumption Growth and Poverty in Fifteen Ethiopian Villages (CSAE WPS/200701), University of Oxford
[26] Poverty Related Impacts of Investments in Road Sector, DFID literature review 2012.
[27] For example RAP 1 has put in place the MoLD maintenance directives and RAP 2 has supported their implementation, initially in RAP 2 districts and now in 7 non-RAP 2 districts working with other donors
[28] These include the need for strong relationships to be built with the MoF (and FCGO) to ensure a separate budget line is set up for maintenance
[29] Nepal Road Sector Assessment, DFID/WB/SDC,2012.
[30] MASFP and APPSP project Completion Reports, DFID
[31] Rural Transport Infrastructure Fiduciary Risk Assessment, Keith Cornish for DFID, 2012
[32] Economic Analysis of Local Government Investments in Rural Roads, Dr. Govind P. Koirala for UNDP 2010
[33] Reduction in transport costs of 50% calculated by per kg cost difference between porter/foot transport (£0.50/km) i.e. a reduction of £0.25 per km, multiplied by the demand (or requirements for all households) for freight transport within the zone of influence of the road giving an estimated total cost saving of £1875/km/yr. This is then multiplied by the number of additional Km of road open each year. This is very conservative assumption – ‘new’ or upgraded roads have been found to generate savings of up to 95% based on current porter charges.
[34] Increase in income generating activities calculated by increased incomes from savings and investments from road construction labour payments invested in vegetable and livestock production, £80 of vegetables per year and £40 per year of livestock. Based on data from RAP1 and 2, the Market Access for Smallholder Farmers and the population in the Road Impact Area (RIA) for the next phase of RAP. This is estimated at £13,500/km/yr which is multiplied by the additional number of kilometres of road kept open each year.
[35] These estimates are based on evidence from the current programmes in Nepal, RAP 2, RRRSDP and RAIDP and LGCDP and the Karnali Employment Programme.
[36] Economic evaluation of Rural Transport 3, World Bank, 2007
[37] Rural Access Programme - Environmental and Climate Assessment, Dr. Toran Sharma, 2012.
[38] To address this acknowledged gap RAP 2 is conducting a long term (30 year) impact study of the Koshi Hills where the UK as has invested over £200m, more than half on roads. This is due to complete in September 2012.
[39] Rural Roads and Poor Area Development in Vietnam, Ren Mu &Dominique van de Walle, World Bank, 2007
[40] Analysing the impact of public investment on rural development, Fenggan Shan Et AL. IFPRI 2005
[41] Asian Development Bank (Rural Finance Sector Analysis 2012, unpublished)
[42] RAP 1 Impact study, WSP 2011.
[43] Market Access for Small-holder Farmers, Project Completion Report, DFID Nepal June 2012
[44] RAP 1 Impact study, WSP 2011.
[45] Economic Analysis of Local Government Investments in Rural Roads, Dr. Govind P. Koirala for UNDP 2010
[46] The ADB managed RRRSDP programme co-funded by DFID is running approximately two years behind the current phase of RAP, but started at the same time.

Commercial Case
Direct procurement
A. Clearly state the procurement/commercial requirements for the intervention / RAP has four procurement requirements: / Firstly, the option chosen requires the procurement of a service provider to manage the main implementation contract for the project and provide accompanying capacity building and institutional development support. This will require the contract to be competitively procured under OJEU rules managed by Procurement Group. / Secondly, the implementation service provider will be responsible for the competitive sub-contracting of national organisations; for works supervision, social mobilisation and private sector development consultants. The competitive sub-contracting arrangements will be overseen by a steering committee headed by Government and DFID. The sub-contracting process will identify appropriate and highly qualified suppliers who can best deliver the milestones and achieve the best value for money and following procurement best practice. / Thirdly, DFID Nepal will be responsible for competitively recruiting the third party monitoring agency, and potentially employment programme technical assistance. / Fourthly, an evaluation contract will be procured through the DFID procurement framework.
B. How does the intervention design use competition to drive commercial advantage for DFID? / In discussion with Procurement Group, and in order to ensure the maximum competition it was decided to open up the main procurement process to the OJEU restricted procurement procedure rather than run a ‘mini’ competition under the new DFID framework arrangements. This is based on the limited response from bidders (2 bids) from a previous framework agreement bidding exercise under RAP 2. / The main service provider contract will include provisions limiting fee rates for international and local consultants and exposure to exchange rate and inflation risks. These provisions will be included in a fully performance/output based contract. Local contracts will also be competitively procured and requests for proposals will clearly specify milestones/deliverables against which payments will be made. The local tender process will use competition to drive down fee rates from sub-contractors and partners. The service provider’s procurement policies and capacities will be reviewed at the bid evaluation stage.
C. How do we expect the market place will respond to this opportunity? / As noted above the response to similar opportunities has been weak. As a result, the full OJEU restricted procedure has been used to maximise the field of potential bidders. In addition the Terms of Reference for the service provider have been designed to be as attractive to bidders as possible, e.g. reduction of the service providers exposure to fiduciary risks. / To test the market Procurement Group have already asked for Expressions of Interest from interested suppliers, based on a draft terms of reference for RAP implementation. Three suppliers responded, indicating that although interest is limited, competition is still worthwhile to stimulate innovation and improve value for money in delivery of the programme. In addition, experience from RAP 2 shows the need for the service provider to work closely with the local consultancy, contractors and social mobilisation organisations to develop their capacity to effectively bid for and implement works effectively.
D. What are the key cost elements that affect overall price? How is value added and how will we measure and improve this? / Wage costs for labour-based works (60%) are the most significant cost factor, but one which the project aims to maximise by using labour-based approaches. To do this the service provider will be pushed to ensure maximum cost effectiveness by minimising the costs in other areas by: / Keeping the technical assistance component cost to below 15% by streamlining implementation and keeping service provider charges to a minimum; / Early and bulk procurement of materials to reduce inflation risks, benefit from economies of scale and ensure materials are available on site and do not affect delivery; / Keeping the pre-financing fee charged by the service provider as low as possible, i.e. under 2%; and / Closely monitoring TA costs against set deliverables and progress.
E. What is the intended Procurement Process to support contract award? / OJEU restricted procedure for the main service provider contract. Following approval of the Confirmation of Scope Business Case an OJEU notice was placed and expressions of interest received. The full tender invitation process will start immediately after approval of this Business Case. / In addition, local (National) procurement for third party monitoring, supervision and employment programme consultants will also be undertaken. / An impact evaluation contact will also be awarded through the DFID evaluation framework arrangement.
F. How will contract & supplier performance be managed through the life of the intervention? / The contracts will be output based. Supplier performance will be monitored monthly against submitted invoices and progress reports. Joint Trimesterly (every 4 months) Steering Committee meetings will formally assess progress against major milestones and agree on the management actions required to be taken by the service providers over the next 4 months. This will provide the opportunity to agree additional milestones and payment criteria with the service providers, as the project develops and issues arise. / The supplier will also be responsible for closely monitoring the performance of sub-contracted agencies (government, private sector and civil society). This will be made easier by the output/performance based funding system that will be adopted by RAP. DFID and MLD led reviews and field visits for verification of works and delivery on the ground will ensure supplier performance is well managed.

Financial Case

A. What are the costs, how are they profiled and how will you ensure accurate forecasting? / The cost of the programme is £36.5m over a period of 4 years[47]. DFID Nepal has adequate funds allocated in the operational plan to fund this programme. The expected allocation and annual spend estimates for the four sub-components are set out below: / The selection of the preferred Option 1 for implementation will provide the most control over disbursement. Financial management capacity will be a key selection criteria for the service provider and a task embedded in the implementation ToRs. Good communication with the service provider will ensure forecasting accuracy and as shown by RAP 2 the ability to ‘take on additional work, and spend it well’ if the needs arises. This is why the ToR and contract used for the OJEU procurement procedure will allow for an increase in overall programme value and the possibility of a cost extension. / RAP Components Spend 2012/13 Spend 2013/14 Spend 2014/15 Spend 2015/16 Total (£m) / Programme budget (Maintenance and upgrading) 3.74 5.61 5.61 3.74 18.7 / Economic infrastructure 1.10 2.95 2.20 1.10 7.35 / Technical Assistance 1.00 1.50 1.50 1.50 5.5 / Employment Programme 0.36 1.08 1.08 1.08 3.6 / Monitoring, Evaluation and Policy 0.40 0.20 0.20 0.55 1.35 / Total 6.6 11.33 10.59 7.98 36.5 / The above table shows the provisional budget breakdown between the main components of the programme. These are indicative, and are expected to be changed to respond to changing implementation needs. In turn, any changes will be carefully monitored, forecasted and updated to maintain accuracy following ARIES forecasting procedures.
B. How will it be funded: capital/programme/admin? / The components of the project are allocated as follows: / All infrastructure works e.g. maintenance and upgrading and economic infrastructure are capital spends, CDEL / Karnali Employment Programme spend treated as RDEL / Technical assistance as programme spend, RDEL / Monitoring and evaluation, future studies and policy work, RDEL / Based on the component allocations the split of spend is as follows: / £26.0 m (70% approx.) CDEL / £10.5 m (30% approx.) RDEL / During the inception phase the detailed forecasts and RDEL/CDEL allocations will be updated based on more accurate cost projections to ensure accurate forecasting.
C. How will funds be paid out? / Implementation payments will be pre-financed by the service provider and reimbursed by DFID on a monthly basis, based on proof of delivery and expenditure. At the peak of implementation, this will require the service provider to advance up to £1.5m per month, for which it is expected that a pre-financing fee will be charged. / GoN will continue to exempt the UK government, DFID and its service providers from any taxes, fees, Value Added Tax, import or customs duties imposed directly or indirectly by GoN on all goods and services provided.
D. What is the assessment of financial risk and fraud? / The fiduciary risk assessment for Government systems in rural infrastructure is High on all but one of the 15 DFID assessment criteria. Even after significant risk mitigation measures are introduced the risk rating remains Moderate to Substantial e.g. in the initial RAP 2 maintenance pilots. / The primary measure to reduce these risks is the selection of the direct funded, private sector implemented, funding modality that removes the risks of fraud and corruption using government systems. This does not eliminate the risk of loss or misuse of funds. To protect taxpayers money further the RAP service provider will paid on a purely reimbursable basis and be made liable for any losses, as part of the contract. They will also be responsible for ensuring their sub-contractors are aware of DFID’s anti-corruption policies and be responsible for enforcing these policies. In addition, RAP will introduce improved payment systems for workers e.g. mobile banking and payments to saving and credit accounts, where practical, to ensure wages reach the poor directly and risks of theft are reduced. / To provide incentives for improved performance within the government system the programme will also pilot output based/Programme for Results (PforR) based funding at the District level. This will also be disbursed by the service provider, based on agreed rates for maintenance of roads and supplementary infrastructure and evidence of delivery. This will protect UK taxpayer’s money from misuse. The pilots will test whether this approach can be used as an effective incentive to reward good local government performance and accountability and control corruption. This work will be undertaken in close collaboration with the WB and ADB who are both considering similar mechanisms in the next generation of their rural infrastructure work. / More broadly, the programme will analyse the best way to support the implementation of the emerging local government accountability mechanisms such as the Ward Citizen Forums. To do this RAP will also use DFID Nepal’s PFM ‘call down’ contract, to provide the DFID team and RAP partners with expert advice on fiduciary and corruption risk control. This will enable RAP to develop and strengthen reform interventions including third party oversight, the implementation of the MoLD fiduciary risk action plan and introduce a local version of the construction sector transparency initiative. / Disbursement of funds / DFID’s funds will be fully reflected in the annual budget (White Book) of the GoN and the budgets of the seven implementing Districts. / Funds will be allocated and agreed by the project steering Committee and flow directly from the service provider to the implementing groups after evidence of expenditure and delivery and has been provided. DFID will in turn reimburse the service provider based on the consolidated evidence of expenditure. / Where the funds flow through the government, i.e. payment for results, the service provider will reimburse the DDF/Sub-account on a monthly basis for eligible payments for the agreed maintenance and economic infrastructure works carried out. The DDC will forward a monthly statement of expenditure accounting for these funds. While replenishing the amount, the Service Provider will oversee that the DDC has fulfilled its commitments and obligations in accordance with the agreed provisions and deliverables. Once payments have been made, the service provider will seek reimbursement from DFID based on the consolidated evidence of expenditure in the same way as for direct implementation. / In summary, the fiduciary risks are high according to the 2012 assessment[48] of the government system in Rural Infrastructure. These can be reduced to medium/substantial with appropriate mitigation measures that increase the level of oversight and accountability, particularly of payments and procurement, but they cannot be completely removed. Direct implementation risks are however judged to be medium. RAP 2 has had instances of fraud and wage theft and although some funds have been recovered, some is still being pursued. Overall losses however represent less than 0.1% of RAP 2 funds. / Based on this evidence RAP will use direct funding for the majority of funds and only move to output based funding through government systems if sufficient capacity and evidence of delivery are developed. In addition, anti-corruption and fraud safeguards are embedded in the programme and the responsibilities of the Service Provider for their implementation are explicitly part of the Terms of Reference, including the responsibility to ensure subcontractor compliance. Adherence to these agreed safeguards will be closely monitored by DFID.
E. How will expenditure be monitored, reported, and accounted for? / The service provider will prepare monthly invoices and accompanying progress reports, detailing progress on key outputs on which to base DFID’s reimbursements. / The service provider will also prepare more detailed progress and financial reports on a trimester basis. The report will include progress on individual district activities, expenditure, updated cost projections, and progress against the log frame indicators, including gender, environmental and climate change indicators. A formal presentation of the Trimester Report to the RAP Steering Committee will provide an opportunity to assess with government overall progress and resolve issues requiring actions from DoLIDAR or MLD. The actions agreed will then be used by DFID as additional delivery indicators against which to base payments. / In addition, public audits will be conducted to verify wage payments made to the RMGs and contractors. Any funds allocated to the DDCs will also be subject to the annual audit conducted by the Auditor General’s Office. In addition, the TA Team will conduct an annual audit to verify that allocated funds are only used on approved projects. ToRs of such audits and audit firm’s capacity will be quality assured by DFID and GoN. To assure that the user groups do not misuse funds and to encourage accountability of DDCs, public audits will be carried out before the final payments are made. Interim payment requests will also be checked against actual physical progress before payments are released. Copies of all Audit reports will be submitted to DFID and GoN and held by the project service provider. / In addition, RAP will adopt a third party monitoring component as part of the overall M and E system, which will be independent from the implementation arm and will report simultaneously to the donor (DFID) and the Ministry of Local Development. This third party agency will undertake a regular sampled field check to validate project M and E reporting, undertake spot checks on process and technical quality, and carry out thematic assessments as required. The third party monitoring agency will be funded directly by DFID initially, with a view to transferring management to the Government, in line with the emerging MoLD practice supported by LGCDP. / The Karnali Employment Programme Component will conduct a Public Expenditure Tracking Survey and will develop systems of social audit and beneficiary monitoring to enhance the performance and feedback on the use of government funds in the KEP.
[47] The programme is expected to be complete by July 2015. This is to align the programme with the GoN financial year and allow a third full building season (October to June) to be included. As such, the implementation period is only 3 year but as this cuts across DFID financial years it will appear on DFID systems for 4 years.
[48] Rural Transport Infrastructure Fiduciary Risk Assessment, Keith Cornish for DFID, 2012

Management Case
A. What are the Management Arrangements for implementing the intervention? / A. Oversight / DFID Nepal will manage the RAP programme. The infrastructure adviser will be responsible for overall management and technical oversight. The IWCT programme officer will be responsible for ensuring compliance with DFID Programme Cycle Management procedures, backed up by the IWCT programme manager. This core team will draw in technical support where required on social, governance, conflict and economic issues, backed up by the Inclusive Wealth Creation Team Leader. / Externally the Ministry of Local Development (MLD) has established a Joint Steering Committee for Rural Infrastructure with participation from seven key ministries and agencies and the donor partners involved in rural infrastructure to take forward broader policy and sector harmonisation work. Under this umbrella the government has formed a RAP project steering committee with MLD, MoF, NPC, Districts and DFID representatives to manage project related issues, performance tracking and ensure good communication on implementation. / B. Management / Through an OJEU competitive bidding process, DFID will contract a service provider to manage the RAP programme. The service provider will also provide training on technical aspects, implementation and financial management, to develop government and private sector capacity. District based NGOs and private sector consultants and contractors will be contracted and managed by the service provider to take on the additional social mobilisation and infrastructure activities included in RAP. / DFID Nepal will closely monitor the progress of the programme, both technical and financial and will meet regularly service provider. Progress assessments will be supplemented by steering committee meetings and DFID Annual Reviews. The contract with the service provider will also include the management of a Technical Co-operation Fund to allow flexible needs based support to be provided. / A tri-partite agreement will be signed by RAP DDCs, DoLIDAR and RAP to engage the local users groups or, for more technically complicated works, contractors to carry out the infrastructure works. / A comprehensive exit strategy involving handover to government and the private sector will be formulated during project inception. The strategy will be flexible enough to be updated during the implementation phase as local conditions change. This strategy will be linked to wider DFID and donor thinking on support to local development and private sector support to ensure that the impacts of DFID support are sustainable.
B. What are the risks and how these will be managed? / The overall delivery risk is medium, after mitigation measures. / Technical – The main technical challenges are to develop an effective approach to maintenance. In particular the choice of technology to upgrade and rehabilitate roads and protect infrastructure from climatic and earthquakes risks cost effectively. In addition, the development of sustainable markets in the RAP districts (and beyond) will require a sound private sector development approach. / Mitigation – RAP will draw on pilot experience and worldwide research to establish a sound methodology for maintenance work and draw on the Climate Change and DRR team to ensure that works are climate and earthquake resilient. Similarly, RAP will draw on DFID’s technical expertise to develop a sound market development approach. The technical risks are therefore rated as low/medium after mitigation. / Social – despite a track record of relatively inclusive performance in RAP 2, RAP still risks elite capture and exclusion unless it proactively promotes inclusion. In particular equal access to employment opportunities and economic infrastructure and training for poor and excluded groups and equal pay for women and provision of childcare on construction sites. / Mitigation – RAP will build on and improve the methodology for the selection of beneficiaries used in RAP 2, and will pay particular attention to the roles of disadvantaged groups in decision-making positions e.g. in RMGs, and road user and VDC planning committees, where RAP 2 performed less well. The social risks are therefore rated as medium after mitigation. / Institutional - The main challenge is to institutionalise an effective approach to maintenance and the evidence based allocation of resources to maximise their impacts. For example establishing and supporting sustainable Road Maintenance Groups to effectively deliver maintenance and upgrading works and linking them to sustainable District level funding. / Mitigation – The approach will be threefold. Firstly demonstrating within RAP that effective maintenance is both possible and affordable. Secondly supporting Local Government capacity and systems; and thirdly rewarding good performance. However, as noted in the institutional appraisal institutional change is likely to take time and it is highly likely that further support will be required beyond RAP to fully institutionalise these changes nationwide. The institutional risks are therefore rated as medium/High after mitigation. / Political – Political interference in resource allocation and project selection, political selection of workers and demands for political donations will remain significant risks to the project. In addition, the labour based approach which favours the poor over the elites (who make money from machinery-based contracts) all pose substantial risks. / Mitigation – The transparent, SED approaches will be continued into RAP, ensuring that community support for pro-poor projects acts as a counter balance to political/elite capture. This should be easier in RAP as lower value maintenance work is by its nature less likely to be attractive to politicians but that does not mean that RAP can afford to be complacent. Political economy analysis will be carried out during implementation to analyse the acceptance and sustainability of the approach for road maintenance. The political risks are rated as medium after mitigation. / Fiduciary – as noted the fiduciary risks related to the use of government systems in the sector are High. Corruption, poor budget execution, lack of capacity and poor audit and accountability all make the current government systems without considerable safeguards unacceptable. / Mitigation – The approach will be twofold. Firstly, using non-government systems until more effective government funding systems are developed. Secondly, only moving to highly ring-fenced, output based, use of government systems if sufficient capacity has been demonstrated to give government systems credibility. Based on this approach the overall fiduciary risks are rated as medium. / Conflict – Two major conflict risks exists. Firstly, that conflict disrupts the ability of RAP to deliver due to security risks, Bandhs etc. Secondly, that the project will create conflict by being perceived as favouring one group. / Mitigation –As with RAP 2, RAP will address the first risk by advance purchase of materials, ensuring that enough are available at site to continue work. It should also be noted that RAP is less vulnerable to this risk than RAP 2 because of its maintenance focus that requires less externally sourced materials, workers and expertise. The second risk will be addressed by ensuring strict adherence to SED approaches. Overall, the conflict risks are rated as medium. / Environmental – The main climate and environmental risks are that the work leads to landslides and other environmental damage and the infrastructure works are not built to withstand climatic and earthquake shocks and are therefore liable to be destroyed. / Mitigation –As with RAP 2, RAP will address these risks by adopting the proven environmental mitigation measure adopted in RAP 2 and ensuring disaster and climate resilient design principles are applied. If these measures are effectively enforced the climate and environment risks are rated as medium. / Economic – the main economic risks are that the improved road access and economic infrastructure do not lead to an increase in economic activity in the Districts. In addition, significant cost increases would significantly reduce the cost effectiveness of the intervention. / Mitigation – RAP will continue the approach successfully adopted in RAP 2 to train farmers along the road corridor in high value cash crop production. This approach combined with reliable access has consistently increased production of market crops and incomes. / Costs in RAP are primarily driven by labour rates, introducing a dilemma into the management of cost risks. Increasing wage costs directly benefit the poorest and ensures maximum participation, albeit at higher overall costs. As with RAP 2, RAP will need to constantly monitor wages, labour availability and delivery rates to ensure the appropriate balance without exploiting the poor people that RAP aims to help. Overall, the economic risks are rated as medium.
C. What conditions apply (for financial aid only)? / All funds for this programme will be advanced by the supplier and reimbursed by DFID. / At a later stage some funds may be managed by government in essence closely monitored, output based financial aid. As a result, the programme has undertaken a fiduciary risk assessment, which found the overall risks to be high. Mitigation measures are currently being designed to reduce risks to an acceptable level and produce a baseline against which improvements in financial management and corruption performance can be assessed. Acceptance of these mitigation measures (TA oversight of procurement and payments, quality assurance of outputs and withholding of payments where procedures have not been followed or in adequate evidence of delivery can be produced) will be pre-conditions for moving to use of government systems, on an output based basis. / If these pre-conditions are met, i.e. fiduciary risks have been reduced to medium at the most; a further submission will be made to the Head of Office making the case for limited use of output based financial aid.
D. How will progress and results be monitored, measured and evaluated? / RAP will use the management information system developed under RAP 2 that monitors inputs and outputs on a monthly basis e.g. physical progress on works, numbers of people employed (and who they are), costs and training provided. / Every 4 months (as per Nepal government practice) the service provider will provide DFID and GoN with Trimester Progress Reports. The reports will include progress on individual Districts and sub-projects, updated expenditure statements, accurate cost projections and progress against all relevant log frame indicators. This work will be complemented by data collected from social audits and third party monitoring reports to triangulate information and ensure accountability and rigour in data collection. DFID Nepal will also conduct formal reviews and undertake joint reviews of RAP with MLD/DoLIDAR and other donors involved in the rural infrastructure sector at least twice a year. This system will ensure effective measurement of inputs, outputs and some lower level outcomes. An internal Project Completion Report will be completed in the last year of implementation. / An independent evaluation will be carried out to assess the overall impact and effectiveness of the programme i.e. its delivery of higher-level results and outcomes (poverty levels, increase in incomes and District ‘GDP’). Budget has been set aside for this contract, which will be contracted separately through the DFID framework agreement as soon as the project has been approved, so that baseline information can be collected during project inception. Importantly the evaluation will continue to monitor indicators from the previous phases of RAP so that a consistent time series can be collected allowing assessment of the cumulative impacts of three phases of RAP to be made. The baseline will include comparative data from two similar non-RAP Districts. At the end of the project, this baseline data will be used to independently assess the overall impact of the programme. The evaluation design will also draw on the data and analysis produced by two on-going studies funded by DFID. The first, the Mid and Far West Chronic poverty and Vulnerability Study that provides in depth analysis of the causes of poverty and constraints to its removal in the RAP project area. The second, the 40 year Koshi Hills Impact study, that although not analysing the RAP project area does have important lessons on the long term development trends in Nepal and how best to measure these longer term changes based on the data available. For example, the Koshi Hills study has developed the methodology for measuring ‘District GDP’ which will be used as one of the two higher level indicators for RAP, to capture the economic growth in the District that RAP will be contributing to. / The independent evaluation will take place 6 months after overall project completion to enable a better assessment of the sustainability of the project interventions to be made. This will include an assessment of the institutional changes in both government and the private sector. This will draw on a variety of sources such as, household and market surveys; fiduciary risk assessments; expenditure tracking surveys; and beneficiary score cards, to provide an evidence based assessment of RAP’s impact on private sector capacity and government institutions and policy.
Logframe - See attached logframe. / Quest No of logframe for this intervention:

References: