PROJECT NAME		State Partnership for Accountability, Responsiveness and Capability (SPARC), Nigeria (2008 – 2015)
STATE		Programme level – all states (Type A, B and C)[1]

GOAL[2]	Indicator		Baseline					Milestone (end 2013)					Target (2015)
Nigeria’s own resources used efficiently and effectively to achieve MDGs	Improvements in progress towards MDGs		See endnote i					n/a					See endnote i for 2015 targets
			Source
			Annual MDG reports of the Office of the Senior Special Adviser to the President, MDGs (OSSAP-MDGs) and the National Planning Commission
	Indicator		Sub-Indicator	Baseline					Milestone 2 (end 2013)					Target (2015)
	Improvements in citizens’ access to, use of and satisfaction with basic services
			NER (%) / Primary/Secondary	ENU		JIG		KAD		KAN		LAG					ENU		JIG		KAD		KAN		LAG
				80/61		28/14		66/42		47/27		82/70					88/67		56/28		83/53		71/41		90/77
				ANA		KAT		NIG		YOB		ZAM					ANA		KAT		NIG		YOB		ZAM
				TBC		TBC		TBC		TBC		TBC					TBC		TBC		TBC		TBC		TBC
			Completion Rate (%) Primary/Secondary	ENU		JIG		KAD		KAN		LAG					ENU		JIG		KAD		KAN		LAG
				89/59		24/10		62/37		46/24		95/76					98/74		48/25		78/56		69/42		100/84
				ANA		KAT		NIG		YOB		ZAM					ANA		KAT		NIG		YOB		ZAM
				TBC		TBC		TBC		TBC		TBC
			Gender Parity Index Primary/Secondary	ENU		JIG		KAD		KAN		LAG					ENU		JIG		KAD		KAN		LAG
				0.9/1.1		0.7/0.4		0.9/0.8		0.8/0.8		0.9/1.1					1/1.1		0.9/0.6		0.9/0.9		0.9/0.9		1/1
				ANA		KAT		NIG		YOB		ZAM					ANA		KAT		NIG		YOB		ZAM
				TBC		TBC		TBC		TBC		TBC					TBC		TBC		TBC		TBC		TBC
			Satisfaction / Primary/Secondary	ENU		JIG		KAD		KAN		LAG			ENU		JIG		KAD		KAN		LAG		ENU		JIG		KAD		KAN		LAG
				61/46		49/44		60/60		51/55		73/65			71/57		60/56		70/70		61/65		81/75		75/62		65/61		75/75		66/70		85/79
				ANA		KAT		NIG		YOB		ZAM			ANA		KAT		NIG		YOB		ZAM		ANA		KAT		NIG		YOB		ZAM
				TBC		TBC		TBC		TBC		TBC			TBC		TBC		TBC		TBC		TBC		TBC		TBC		TBC		TBC		TBC
			National under 5s mortality rate (boys)	175 (per 1000 live births)					103 (per 1000 live births)					86 (per 1000 live births)
			National under 5s mortality rate (girls)	166 (per 1000 live births)					98 (per 1000 live births)					81 (per 1000 live births)
			Source
			Education Indicators: Baseline = 2006 QWIQ (Interim), Milestones = 2010 NEDS and 2014 NEDS / Health Indicators: Mortality Rate Baseline = 2008 NDHS , Milestones = NDHS; TB rate Baseline & Milestones = NTBLCP Annual Report / Satisfaction Indicators: Baseline = 2006 QWIQ (Interim), Milestones = QWIQ
	Indicator		Sub-Indicator	Baseline (August 2010)					Milestone (end 2013)					Target (2015)
	Improvements in Citizens perceptions of State Government performance[3]			ENU	JIG	KAD	KAN	LAG	ANA	KAT	NIG	YOB	ZAM		ENU	JIG	KAD	KAN	LAG	ANA	KAT	NIG	YOB	ZAM	ENU	JIG	KAD	KAN	LAG	ANA	KAT	NIG	YOB	ZAM
			Capability						Baseline will be established in late 2012.										To be developed after baseline is established.										To be developed after baseline is established.
			Accountability																							
			Responsiveness																							
			Source
			Cross-SLP Survey on the Perceptions of Service Delivery and Governance at State level.
[1] See SPARC Consolidation and Expansion Strategy for details on typology of State approaches. In summary: 2 x Type A (Going with the Grain): Jigawa and Lagos; 4 x Type B (Consolidated Approach): Enugu, Kaduna, Kano and Yobe; 4 x Type C (Building Foundations): Anambra, Katsina, Niger and Zamfara.
[2] Goal level baseline and milestone data for additional SPARC states of Anambra, Katsina, Niger, Yobe and Zamfara is being compiled.
[3]  On Track,  Off Track,  Severely Off Track,  Improving,  Staying the Same,  Declining

PURPOSE	Outcome Indicator 1	Type	Baseline (2011)	Milestone (end 2013)	Target (2015)	Assumptions
The efficiency and effectiveness of selected state level governments’ use of public resources is enhanced	Effectiveness of policies and strategies and consistency of Medium-Term Plans and Budgets with policies and resource envelopes.	A (2):	State Develop Plan well established in Jigawa and at advanced draft state in Lagos. MTSSs have been developed for priority sectors but require improvement.	In all States: The State Development Plan and MTSSs of priority sectors are adequately reflected in the 2014-2016 budget.	In all States: The State Development Plan and MTSSs/sector plans of at least 75% of sectors are adequately reflected in the 2015-2017 budget.	Political will to sustain the reform agenda is maintained beyond the lifetime of SPARC / State governments continue to prioritise the MDGs in the allocation and use of public resources / Levels and fluctuations in oil revenues do not unduly undermine fiscal stability / SAVI achieves sustainable improvements in State Government inclusivity and responsiveness to citizens’ rights and demands / Sectoral SLPs achieve sustainable improvements in sector performance / .
		B (4):	State development plans exist but Government plans to replace in Kano and Kaduna. MTSSs are in place within priority sectors, but are of variable quality and are not adequately reflected in the budget.	In at least one State: (a) A new/revised State Development Plan (SDP) has been approved and published, and (b) within priority sectors, MTSS goals and objectives are consistent with the SDP and can be linked to the 2014-2016 budget.	In at least one State: The State Development Plan and MTSSs of priority sectors are adequately reflected in the 2015-2017 budget.
		C (4):	There are no comprehensive State Development Plans, though the foundations exist in some states (e.g. Zamfara Vision 2020). There are no recognised MTSSs, though some sectors (e.g. Health) have Sector Plans.	In at least two States: A process for preparing a State Development Plan has been agreed.	In at least two States: (a) Draft State Development Plan prepared, ready for ExCo approval, and (b) In at least one sector, the MTSS/Sector Plan is realistic and reflected in the 2015-2017 budget.
		Source
		(a) SEAT Reports, (b) Annual SG Performance Review Reports, (c) State Development Plans, (d) MTSSs, (e) Annual SG budgets, and (e) PFM factsheets.
	Outcome Indicator 2	Type	Baseline (2011)	Milestone (end 2013)	Target (2015)
	Realism and predictability of multi-year capital and recurrent budgets.	A (2):	Expenditure budget variance was between 11-35% over 2007-2010. Budgets are prepared on a medium-term basis and at an aggregate level are broadly consistent with revenue forecasts. There are strong links between forecasts and annual budget ceilings in Lagos but not Jigawa. Cash forecasting is weak and budget releases are centrally controlled and not predictable. There are more effective expenditure approval processes in Lagos than Jigawa, but in both cases, payment areas are experienced for non-salary/routine expenditure. Rudimentary cash forecasting is in place in Lagos but not Jigawa.	In all States: (a) Variance between 2014-2016 budget and medium-term revenue forecasts is less than 15-25% (depending on State), (b) Expenditure budget variance is below 15-25% (depending on State), and (c) Annual cash forecasts prepared by STO/Treasury are used as the basis for cash management and disbursement in priority sectors.	In all States: (a) Variance between 2015-2017 budget and medium-term revenue forecasts is less than 10-15% (depending on State), (b) Expenditure budget variance is below 15% (depending on State), and (c) Quarterly cash forecasts prepared by STO/Treasury are used as the basis for cash management and disbursement in priority sectors.
		B (4):	Expenditure budget variance was between 5-57% over 2007-2011. Revenue forecasting tools are being used, though not fully institutionalised, including to provide sector ceilings for planning in some cases. Budgets are prepared on a medium-term basis, but are not yet consistent with revenue forecasts and sector ceilings. Cash forecasting is weak or non-existent and budget releases are centrally controlled and not predictable.	In at least one State: (a) Variance between 2014-2016 budget and medium-term revenue forecasts is less than 20-35% (depending on State), and (b) Expenditure budget variance is below 20-35% (depending on state).	In at least one State: (a) Variance between 2015-2017 budget and medium-term revenue forecasts is less than 15-25% (depending on State), (b) Expenditure budget variance is below 15-25% (depending on State), and (c) Annual cash forecasts prepared by Treasury are used as the basis for cash management and disbursement in priority sectors.
		C (4):	Expenditure budget variance was between 25-44% over 2006-2010. In some cases, the budget is not prepared in a multi-year fiscal framework and where it is, there are consistent over forecasts of revenue. No reliable estimates of cash flow are available and MDAs do not receive information on availability of funds for budget execution.	In at least two States: (a) Expenditure budget variance is below 25-35% (depending on State), and (b) The Budget Call Circular is used to guide 2014-2016 budget preparation.	In at least two States: (a) Expenditure Budget variance is below 20-25% (depending on State), (b) A Budget Policy Statement is used to guide the annual budget process, and (c) Annual cash forecasts prepared by Treasury are used as the basis for cash management and disbursement in the Health sector.
		Source
		(a) PEFA reports, (b) Annual SG Performance Review Reports, (c) Budget Call Circular, (d) Revenue forecasting model forecasts, (e) Sector spending ceilings, (f) State Development Plans, (g) Annual SG budgets (h) Annual Accounts/Financial Statements, and (i) PFM factsheets.

PURPOSE (Cont.)	Outcome Indicator 3	Type	Baseline (2011)			Milestone (end 2013)			Target (2015)
	Effectiveness of core[4] MDA support for government planning, finance and human resources performance management and service delivery mechanisms.	A (2):	Mandates have been compiled and reviewed but rationalisation has not yet begun. HRM polices and processes have been accepted in principle in Lagos but require improvement in Jigawa. There are no formal establishment and workforce planning processes in place. Service Charters are being developed in priority sectors, but there is a need for a standardised and formal performance management process.			In all States: (a) Agreed procedures and responsibilities for routine review of mandates are being implemented, (b) Reorganisation is underway in priority central MDAs, (c) A modern G&SI sensitive HRM Policy and improvement Strategy have been agreed, (d) a G&SI sensitive workforce planning Policy and Strategy have been agreed, and (e) G&SI sensitive Service Charters/Standards for pilot MDAs have been published.			In all States: (a) Mandate compendium has been updated, (b) Reorganisation has been completed in priority central and is underway in additional sector MDAs, (c) Selected HRM processes have been reformed in line with the State HRM Policy, (d) Establishment and workforce plans are being implemented in priority central MDAs, and (e) Performance against Service Charters/Standards for pilot MDAs has been published.
		B (4):	Mandates have been documented but still require rationalisation. The level of implementation of corporate planning varies between states, but is taking place in central MDAs in most states. HRM policies and processes are not comprehensive or up-to-date and are non-functional in some critical areas. There are no established functions for establishment or workforce planning. Service Charters have been developed in Enugu and a Performance Management Framework in under development in Kaduna.			In at least one State: (a) Mandates have been documented across government, (b) Reorganisation is underway in priority central MDAs and (in some states) selected sector MDAs, (c) A modern G&SI sensitive HRM Policy and improvement Strategy/Action Plan have been agreed, (d) Establishment and workforce plans, taking into account G&SI issues, have been agreed in priority central MDAs and (in some states) selected sector MDAs, and (e) G&SI sensitive Service Charters for pilot MDAs have been published.			In at least one State: (a) Mandates are being rationalised in line with recommendations to improve organisational effectiveness, (b) Reorganisation has been completed in priority central MDAs and (in some states) selected sector MDAs and is underway in additional central/sector MDAs, (c) Selected HRM processes have been reformed in line with the State HRM Policy, (d) Establishment and workforce plans are being implemented in priority central MDAs and (in some states) selected sector MDAs, and (e) Performance against Service Charters for pilot MDAs has been published.
		C (4):	The structures and functions of MDAs are generally not well documented or aligned with service delivery targets and there is no process for their review. HRM policies and processes are not comprehensive or up-to-date and are non-functional in some critical areas. There are no systematic processes for establishment or workforce planning.			In at least two States: (a) A corporate improvement plan is being used to guide reorganisation in the central planning MDA, (b) A G&SI sensitive HRM improvement plan has been agreed, and (c) A strategy for government-wide establishment and workforce planning has been agreed.			In at least two States: (a) The central planning MDA corporate improvement plan has been implemented, and implementation is underway in at least one sector MDA, (b) the HRM improvement plan is being implemented in at least one sector, and (c) Establishment and workforce planning is being implemented in the central planning MDA and workforce planning is being used in at least one sector.
		Source
		(a) SEAT Reports, (b) Annual SG Performance Review Reports, (c) Mandate descriptions and rationalisation reports, (d) Corporate planning implementation reports, (e) HRM policy and improvement plan reports, (f) Performance management reports and Service Charters, and (g) Workforce analysis reports.
	Outcome Indicator 4	Type	Baseline (2011)			Milestone (end 2013)			Target (2015)
	% of PEFA/SEAT Dimensions improving by at least one rating.	A (2):	See 2011 SEAT/PEFA			N/A			In all States: 25%
		B (4):	See 2011 SEAT/PEFA			N/A			In at least one State: 20%
		C (4):	See 2011 SEAT/PEFA			N/A			In at least two States: 15%
		Source
		State Government PEFA/SEAT Self Assessments, validated by external M&E Contractor.
INPUTS (£)	DFID (£)	Govt (£)		Other (£)			Total (£)				DFID SHARE (%)
	DFID to complete	DFID to Complete
INPUTS (HR)	DFID (FTEs)
	DFID to complete
[4] Core MDAs refers to central “Apex” MDAs which, depending on the state, may include: a) Office of the HoS, b) Ministry of Finance, c) Ministry of Economic Planning or d) State Economic Planning Commission.

OUTPUT 1	Output Indicator 1.1	Type	Baseline (2011)	Milestone (end 2013)					Target (2015)			Assumptions
Policy and strategy development, monitoring and evaluation improved.	Extent to which policy and strategy making processes meet good practice standards.	A (2):	See State logframes.	In all states: The 2013 milestone has been achieved.					In all states: The 2015 target has been achieved.			Citizens’ ability to claim rights and hold government accountable increased. / Civil society and State and Federal Government are, and remain, committed to the MDGs. / Changes in political leadership do not undermine State Government support for agreed governance reforms in State Development Plans/Change Plans/SPARC intervention plans. / Changes in senior positions (e.g. HoS, Commissioners) do not undermine State Government support for key initiatives (e.g. Corporate Planning, State Development Plans, and MTSS). / State Government is committed to implementing institutional change actions detailed in agreed State Development Plans/Change Plans/SPARC intervention plans. / State Government is committed to mainstreaming governance reforms within the State Development Plan. / Constitutional reform do not have negative effects on inter-government relations. / HIV/AIDS, malaria and TB incidence do not prevent improvements in efficient and effective use of funds.
		B (4):	See State logframes.	In at least one state: The 2013 milestone has been achieved.					In at least one state: The 2015 target has been achieved.
		C (4):	See State logframes.	In at least two states: The 2013 milestone has been achieved.					In at least two states: The 2015 target has been achieved.
		Source
		(a) SPARC quarterly and annual progress reports, (b) SPARC M&E MIS, (c) SPARC Annual Evaluation Study, and (d) Annual SG Performance Review Reports.
	Output Indicator 1.2	Type	Baseline (2011)	Milestone (end 2013)					Target (2015)
	Quality and comprehensiveness of policies and strategies.	A (2):	See State logframes.	In all states: The 2013 milestone has been achieved.					In all states: The 2015 target has been achieved.
		B (4):	See State logframes.	In at least one state: The 2013 milestone has been achieved.					In at least one state: The 2015 target has been achieved.
		C (4):	See State logframes.	In at least two states: The 2013 milestone has been achieved.					In at least two states: The 2015 target has been achieved.
		Source
		(a) SPARC quarterly and annual progress reports, (b) SPARC M&E MIS, (c) SPARC Annual Evaluation Study, and (d) Annual SG Performance Review Reports.
	Output Indicator 1.3	Type	Baseline (2011)	Milestone (end 2013)					Target (2015)
	Extent to which results frameworks are comprehensive and measured.	A (2):	See State logframes.	In all states: The 2013 milestone has been achieved.					In all states: The 2015 target has been achieved.
		B (4):	See State logframes.	In at least one state: The 2013 milestone has been achieved.					In at least one state: The 2015 target has been achieved.
		C (4):	See State logframes.	In at least two states: The 2013 milestone has been achieved.					In at least two states: The 2015 target has been achieved.
		Source
		(a) SPARC quarterly and annual progress reports, (b) SPARC M&E MIS, (c) SPARC Annual Evaluation Study, and (d) Annual SG Performance Review Reports.
Impact Weighting	Output Indicator 1.4	Type	Baseline (2011)	Milestone (end 2013)					Target (2015)
20%	Extent to which performance management processes are being used.	A (2):	See State logframes.	In all states: The 2013 milestone has been achieved.					In all states: The 2015 target has been achieved.
		B (4):	See State logframes.	In at least one state: The 2013 milestone has been achieved.					In at least one state: The 2015 target has been achieved.
		C (4):	See State logframes.	In at least two states: The 2013 milestone has been achieved.					In at least two states: The 2015 target has been achieved.
		Source
		(a) SPARC quarterly and annual progress reports, (b) SPARC M&E MIS, (c) SPARC Annual Evaluation Study, and (d) Annual SG Performance Review Reports.
Inputs (£)	DFID (£)	Govt (£)			Other (£)		Total (£)			DFID Share (%)		Risk Rating
	DFID to complete	DFID to Complete										High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 2	Output Indicator 2.1	Type	Baseline (2011)	Milestone (end 2013)					Target (2015)			Assumptions
State public financial management improved.	Extent to which the budget is credible and policy based.	A (2):	See State logframes.	In all states: The 2013 milestone has been achieved.					In all states: The 2015 target has been achieved.			As above.
		B (4):	See State logframes.	In at least one state: The 2013 milestone has been achieved.					In at least one state: The 2015 target has been achieved.
		C (4):	See State logframes.	In at least two states: The 2013 milestone has been achieved.					In at least two states: The 2015 target has been achieved.
		Source
		(a) SPARC quarterly and annual progress reports, (b) SPARC M&E MIS, (c) SPARC Annual Evaluation Study, and (d) Annual SG Performance Review Reports.
	Output Indicator 2.2	Type	Baseline (2011)	Milestone (end 2013)					Target (2015)
	Extent to which the budget is comprehensive and transparent.	A (2):	See State logframes.	In all states: The 2013 milestone has been achieved.					In all states: The 2015 target has been achieved.
		B (4):	See State logframes.	In at least one state: The 2013 milestone has been achieved.					In at least one state: The 2015 target has been achieved.
		C (4):	See State logframes.	In at least two states: The 2013 milestone has been achieved.					In at least two states: The 2015 target has been achieved.
		Source
		(a) SPARC quarterly and annual progress reports, (b) SPARC M&E MIS, (c) SPARC Annual Evaluation Study, and (d) Annual SG Performance Review Reports.
	Output Indicator 2.3	Type	Baseline (2011)	Milestone (end 2013)					Target (2015)
	Level of predictability and control in budget execution.	A (2):	See State logframes.	In all states: The 2013 milestone has been achieved.					In all states: The 2015 target has been achieved.
		B (4):	See State logframes.	In at least one state: The 2013 milestone has been achieved.					In at least one state: The 2015 target has been achieved.
		C (4):	See State logframes.	In at least two states: The 2013 milestone has been achieved.					In at least two states: The 2015 target has been achieved.
		Source
		(a) SPARC quarterly and annual progress reports, (b) SPARC M&E MIS, (c) SPARC Annual Evaluation Study, and (d) Annual SG Performance Review Reports.
	Output Indicator 2.4	Type	Baseline (2011)	Milestone (end 2013)					Target (2015)
	Quality of accounting, recording and reporting.	A (2):	See State logframes.	In all states: The 2013 milestone has been achieved.					In all states: The 2015 target has been achieved.
		B (4):	See State logframes.	In at least one state: The 2013 milestone has been achieved.					In at least one state: The 2015 target has been achieved.
		C (4):	See State logframes.	In at least two states: The 2013 milestone has been achieved.					In at least two states: The 2015 target has been achieved.
		Source
		(a) SPARC quarterly and annual progress reports, (b) SPARC M&E MIS, (c) SPARC Annual Evaluation Study, and (d) Annual SG Performance Review Reports.
Impact Weighting	Output Indicator 2.5	Type	Baseline (2011)	Milestone (end 2013)					Target (2015)
40%	Extent and quality of external scrutiny and audit.	A (2):	See State logframes.	In all states: The 2013 milestone has been achieved.					In all states: The 2015 target has been achieved.
		B (4):	See State logframes.	In at least one state: The 2013 milestone has been achieved.					In at least one state: The 2015 target has been achieved.
		C (4):	See State logframes.	In at least two states: The 2013 milestone has been achieved.					In at least two states: The 2015 target has been achieved.
		Source
		(a) SPARC quarterly and annual progress reports, (b) SPARC M&E MIS, (c) SPARC Annual Evaluation Study, and (d) Annual SG Performance Review Reports.
Inputs (£)	DFID (£)	Govt (£)			Other (£)		Total (£)			DFID Share (%)		Risk Rating
	DFID to complete	DFID to Complete										High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 3	Output Indicator 3.1	Type	Baseline (2011)	Milestone (end 2013)					Target (2015)			Assumptions
State civil service performance improved.	Clarity and appropriateness of public service organisation and operational management.	A (2):	See State logframes.	In all states: The 2013 milestone has been achieved.					In all states: The 2015 target has been achieved.			As above.
		B (4):	See State logframes.	In at least one state: The 2013 milestone has been achieved.					In at least one state: The 2015 target has been achieved.
		C (4):	See State logframes.	In at least two states: The 2013 milestone has been achieved.					In at least two states: The 2015 target has been achieved.
		Source
		(a) SPARC quarterly and annual progress reports, (b) SPARC M&E MIS, (c) SPARC Annual Evaluation Study, and (d) Annual SG Performance Review Reports.
	Output Indicator 3.2	Type	Baseline (2011)	Milestone (end 2013)					Target (2015)
	Extent to which HRM policies and organisation are in place.	A (2):	See State logframes.	In all states: The 2013 milestone has been achieved.					In all states: The 2015 target has been achieved.
		B (4):	See State logframes.	In at least one state: The 2013 milestone has been achieved.					In at least one state: The 2015 target has been achieved.
		C (4):	See State logframes.	In at least two states: The 2013 milestone has been achieved.					In at least two states: The 2015 target has been achieved.
		Source
		(a) SPARC quarterly and annual progress reports, (b) SPARC M&E MIS, (c) SPARC Annual Evaluation Study, and (d) Annual SG Performance Review Reports.
	Output Indicator 3.3	Type	Baseline (2011)	Milestone (end 2013)					Target (2015)
	Extent to which establishment planning and workforce planning, management and development is in place.	A (2):	See State logframes.	In all states: The 2013 milestone has been achieved.					In all states: The 2015 target has been achieved.
		B (4):	See State logframes.	In at least one state: The 2013 milestone has been achieved.					In at least one state: The 2015 target has been achieved.
		C (4):	See State logframes.	In at least two states: The 2013 milestone has been achieved.					In at least two states: The 2015 target has been achieved.
		Source
		(a) SPARC quarterly and annual progress reports, (b) SPARC M&E MIS, (c) SPARC Annual Evaluation Study, and (d) Annual SG Performance Review Reports.
Impact Weighting	Output Indicator 3.4	Type	Baseline (2011)	Milestone (end 2013)					Target (2015)
20%	Extent to which MDA performance management policies and procedures are in place.	A (2):	See State logframes.	In all states: The 2013 milestone has been achieved.					In all states: The 2015 target has been achieved.
		B (4):	See State logframes.	In at least one state: The 2013 milestone has been achieved.					In at least one state: The 2015 target has been achieved.
		C (4):	See State logframes.	In at least two states: The 2013 milestone has been achieved.					In at least two states: The 2015 target has been achieved.
		Source
		(a) SPARC quarterly and annual progress reports, (b) SPARC M&E MIS, (c) SPARC Annual Evaluation Study, and (d) Annual SG Performance Review Reports.
Inputs (£)	DFID (£)	Govt (£)			Other (£)		Total (£)			DFID Share (%)		Risk Rating
	DFID to complete	DFID to Complete										High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 4	Output Indicator 4.1	Baseline (2011)		Milestone (end 2013)				Target (2015)			Assumptions
Federal support to state governance improved.	Effectiveness of National mechanisms for improving state governance.	An SPRM mechanism has been designed and launched. State level CGS is operational and the LG-CGS has been launched. The Nigerian Governors Forum (NGF) Secretariat has been reinvigorated in recent years and a strategy developed to guide its work. However, the NGFS is currently under resourced.		(a) The SPRM mechanism has been piloted and reviewed, (b) State level CGS is reviewed and adjusted, (c) LG-CGS is fully operational, and (d) the NGFS strategic plan has been updated and implementation started.				(a) Recommendations for adjusting the SPRM mechanism agreed in response to lessons learned and the SPRM mechanism adjusted in response, (b) a transition strategy for the MDG-CGS scheme post 2015 has been prepared, and (c) the NGFS structure and number/skills mix of staff is consistent with its mandate and strategic objectives.			Government still committed to achieving MDGs / Governors’ interest in PRM sustained
		Source
		(a) SPRM State Self Assessment Report and State Plan of Action, (b) State surveys on progress of implementation, (c) Circulars and memos emanating from the NCE, (d) NGF Strategic Plan document; NGF databases and records, (e) SPRM CMS held in the Nigeria Governors Forum, (f) State Plans of Action from the SPRM exercise, (g) Press reports on SPRM Quarterly progress reports from the CGS team, (h) Reports from the Presidential Committee on MDGs, and (i) CGS evaluation Reports.
	Output Indicator 4.2	Baseline (2011)		Milestone (end 2013)				Target (2015)
	Responsiveness and success of State Governments to National initiatives to improve state performance.	The SPRM is being piloted in 4 states, the State level CGS is in operation in all states and the LG level CGS has been launched and has begun operation in 113 LGAs. Currently, the State level CGS experiences a 90% completion rate.		(a) At least 10 states have submitted SPRM State Self Assessment Report (SSAR) and State Plan of Action (SPoA), and (b) all states continue to access State level CGS and maintain a 90% completion rate.				At least 18 states have submitted their SPRM SSAR and SPoA.
		Source
		(a) SPARC consultancy reports, (b) OSSAP-MDGs project monitoring reports, (c) CGS Base line studies and NEEDS assessment reports, and (d) OSSAP-Nigeria MDGs Information System
Impact Weighting	Output Indicator 4.3	Baseline (2011)		Milestone (end 2013)				Target (2015)
20%	State governments have a mechanism for accessing and sharing lessons through appropriate Federal organisations	NGF CMS commissioned and functioning as a repository and tool for state information.		SPARC state level lessons have been collated and made available to all non-SPARC states.				SPARC state level lessons have been promoted to all non-SPARC states.
		Source
		(a) NGF CMS, (b) SPARC M&E MIS, (c) SPARC Share Fair Reports, (d) SPARC resource centre, (e) Targeted SG surveys on adoption of initiatives.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID Share (%)	Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

PROJECT NAME	State Partnership for Accountability, Responsiveness and Capability (SPARC), Nigeria (2008 – 2015)
STATE	Anambra (Type C Approach)

Logframe to be developed during State programme inception over August-October 2012.

PROJECT NAME	State Partnership for Accountability, Responsiveness and Capability (SPARC), Nigeria (2008 – 2015)
STATE	Enugu (Type B Approach)

GOAL	Impact Indicator 1	Baseline	Milestone (end 2013)	Target (2015)
Nigeria’s own resources used efficiently and effectively to achieve MDGs	Improvements in progress towards MDGs	See Programme Logframe for baseline and milestones.
	Impact Indicator 2	Baseline	Milestone (end 2013)	Target (2015)
	Improvements in citizens’ access to, use of and satisfaction with basic services	See Programme Logframe for baseline and milestones.
	Impact Indicator 3	Baseline (August 2010)	Milestone (end 2013)	Target (2015)
	Improvements in Citizens perceptions of State Government performance	See Programme Logframe for baseline and milestones.

PURPOSE	Outcome Indicator 1	Baseline (2011)		Milestone (2013)				Target (2015)			Assumptions
The efficiency and effectiveness of selected state level governments’ use of public resources is enhanced	Effectiveness of policies and strategies and consistency of Medium-Term Plans and Budgets with policies and resource envelopes.	Enugu Medium Term Implementation Plan approved, along with four draft MTSSs, but reflection in budgets is poor.		(a) A revised ENVMTIP has been approved and published, and (b) within priority sectors, MTSS goals and objectives are consistent with the SDP and can be linked to the 2014-2016 budget.				The ENVMTIP and MTSSs of priority sectors are adequately reflected in the 2015-2017 budget.			Political will to sustain the reform agenda is maintained beyond the lifetime of SPARC / State governments continue to prioritise the MDGs in the allocation and use of public resources / Levels and fluctuations in oil revenues do not unduly undermine fiscal stability / SAVI achieves sustainable improvements in State Government inclusivity and responsiveness to citizens’ rights and demands / Sectoral SLPs achieve sustainable improvements in sector performance / .
		Source
		(a) Enugu Medium Term Implementation Plan, (b) MTSSs, (c) Draft Budgets, and (d) SPARC Evaluation Reviews.
	Outcome Indicator 2	Baseline (2011)		Milestone (2013)				Target (2015)
	Realism and predictability of multi-year capital and recurrent budgets.	Actual expenditure deviated from budgeted expenditure by 31%, 27% and 22% 2008-2010 respectively. Budget preparation is undertaken on a medium-term basis however there is no evident link between the multi-year estimates and the annual budget ceilings. Budgets are therefore generally unrealistic and outturns demonstrate significant variance from budget. Cash forecasting is weak and budget implementation is not based on realistic work plans. Commitments and contractor arrears are not effectively tracked, giving rise to cash rationing.		(a) Variance between 2014-2016 budget and medium-term revenue forecasts is less than 20%, and (b) Expenditure budget variance is below 20%.				(a) Variance between 2015-2017 budget and medium-term revenue forecasts is less than 15%, (b) Expenditure budget variance is below 15%, and (c) Annual cash forecasts prepared by Treasury are used as the basis for cash management and disbursement in priority sectors.
		Source
		(a) PEFA reports, (b) Budget Call Circular, (c) Revenue forecasting model forecasts, (d) Sector spending ceilings, (e) SDP, (f) Annual SG budgets, (g) Annual Accounts/ Financial Statements, and (h) PFM factsheets.
	Outcome Indicator 3	Baseline (2011)		Milestone (2013)				Target (2015)
	Effectiveness of core MDA support for government planning, finance and human resources performance management and service delivery mechanisms.	While public service mandates are clear, necessary rationalisation is yet to be completed. ESEPC has commenced reorganisation, but other central MDAs are not so advanced. Recent efforts to improve HRMIS constitute a first step towards strengthening human resources management, including workforce planning. A SERVICOM office has been established, and service charters are being developed in seven pilot MDAs.		(a) Mandates have been documented across government and proposals for rationalisation presented to ExCo, (b) A modern G&SI sensitive HRM Policy and improvement Action Plan have been agreed, (c) Establishment and workforce plans, taking into account G&SI issues, have been agreed in OHoS, and (d) SERVICOM office operational and G&SI sensitive Service Charters for seven pilot MDAs have been published.				(a) Mandates are being rationalised in line with recommendations to improve organisational effectiveness, (b) Reorganisation has been completed in the OHoS, (c) Selected HRM processes (including establishment and workforce planning) are being reformed in line with the State HRM Policy, (d) Establishment and workforce plans are being implemented in OHoS, and (e) Performance against Service Charters for seven pilot MDAs has been published.
		Source
		(a) Mandate rationalisation reports, (b) corporate planning implementation reports, (c) HRM policy and action plan, and (d) service charters and service review reports.
	Outcome Indicator 4	Baseline (2011)		Milestone (2013)				Target (2015)
	% of PEFA/SEAT Dimensions improving by at least one rating.	See 2011 SEAT/PEFA		N/A				20%
		Source
		State Government PEFA/SEAT Self Assessments, validated by external M&E Contractor.
INPUTS (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID SHARE (%)
	DFID to complete	DFID to Complete
INPUTS (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 1	Output Indicator 1.1	Baseline (2011)		Milestone (2013)				Target (2015)			Assumptions
Policy and strategy development, monitoring and evaluation improved.	Extent to which policy and strategy making processes meet good practice standards.	ESEPC has been providing some support but this needs to be strengthened. There is now a conflicting responsibility between the new MoPB and the ESEPC which needs to be resolved. (Milestones refer to "central planning agency", but this is pending a resolution.)		(a) Appropriate tools (e.g. guidelines) related to policy, strategy and M&E provided to all policy makers and MDAs by the Central Planning Agency, (b) Three new strategy making processes, consistent with the quality guides being promoted by the CPA, and (c) 2 new policy making processes, consistent with the guides, being promoted by the CPA.				(a) Priority MTSS sectors have implemented selected strategy and M&E processes which meet good practice standards, and (b) Selected policy making processes being used which meet good practice standards.			Citizens’ ability to claim rights and hold government accountable increased. / Civil society and State and Federal Government are, and remain, committed to the MDGs. / Changes in political leadership do not undermine State Government support for agreed change plans. / Changes in senior positions (e.g. HoS, Commissioners) do not undermine State Government support for key initiatives (e.g. Corporate Planning, State Development Plans, and MTSS). / State Government is committed to implementing institutional change actions detailed in agreed change plans. / State Government is committed to mainstreaming governance reforms within the State Development Plan. / Constitutional reform do not have negative effects on inter-government relations. / HIV/AIDS, malaria and TB incidence do not prevent improvements in efficient and effective use of funds.
		Source
		(a) SEAT Reports, (b) ENVMTIP and Sector Performance Reports, and (c) MTSS, Policy and M&E Guidelines.
	Output Indicator 1.2	Baseline (2011)		Milestone (2013)				Target (2015)
	Quality and comprehensiveness of policies and strategies.	Medium Term Implementation Plan (ENVMTIP) 2010-2013 has been completed and signed on for implementation by the Executive Governor. The ENVMTIP was reviewed in January with improved results framework, but a revised draft is still being awaited. Four sectors have developed first generation MTSSs, but their quality needs improvements.		(a) ENVMTIP better meets Policy standards, and (b) 2014-2016 MTSS for priority sectors better meet MTSS standards.				2015-2017 MTSS of priority sectors are consistent with good practice as indicated in MTSS Guidelines.
		Source
		(a) SEAT Reports, (b) MTSSs and ENVMTIP, (c) Fiscal Projections, and (d) MTSS and ENVMTIP and Sector Performance Reports.
	Output Indicator 1.3	Baseline (2011)		Milestone (2013)				Target (2015)
	Extent to which results frameworks are comprehensive and measured.	The ENVMTIP was reviewed in January with improved results framework (not yet comprehensive). Incoherent KPIs presently exist and were fine-tuned in May 2012 for incorporation in the MTSSs of the priority sectors.		The ENVMTIP and MTSSs in at least 2 priority sectors include comprehensive results frameworks with relevant KPIs.				(a) KPI MIS generating reports for measurement of results frameworks in the ENVMTIP and MTSSs of at least 2 priority sectors, and (b) M&E scorecards prepared by at least 2 priority MTSS sectors.
		Source
		(a) SEAT Reports, (b) ENVMTIP and MTSSs, (c) Annual ENVMTIP and Sector Performance Reports, (d) KPI MIS reports, and (e) MDA M&E Scorecards.
Impact Weighting	Output Indicator 1.4	Baseline (2011)		Milestone (2013)				Target (2015)
25%	Extent to which performance management processes are being used.	The Annual Performance Evaluation template agreed and sent out by the Enugu State Economic Planning Commission to guide all MDAs in documenting their Annual Performance Reviews.		The Central Planning Agency has the capacity to support sectors in implementing annual sector performance reviews, which incorporate a G&SI focus.				(a) The Central Planning Agency conducts an ENVMTIP annual performance review, in line with the ENVMTIP M&E framework, which incorporates a G&SI focus, and (b) at least 2 MTSS sectors have held MTSS annual performance reviews which incorporate a G&SI focus.
		Source
		(a) SEAT Reports, (b) Corporate Planning progress reports, (c) Annual ENVMTIP and Sector Performance Review Reports, and (d) ENVMTIP and MTSSs.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)			DFID Share (%)		Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 2	Output Indicator 2.1	Baseline (2011)		Milestone (2013)			Target (2015)			Assumptions
State public financial management improved.	Extent to which the budget is credible and policy based.	Budget preparation is undertaken on a medium-term basis. However, ENS PFM factsheets & the 2012 PEFA Repeat Self-Assessment indicate that state budgets are generally unrealistic and out-turns demonstrate significant variance from budgets.		(a) A Budget Policy Statement is used to determine and guide on realistic forecasting of aggregate resources, (b) Annual call circulars prepared which include aggregate and sector ceilings, and (c) guidance provided on determining the costing, justification and inclusion of capital/development projects into the budget process.			State Government is using medium-term revenue forecasts and sector spending ceilings to prepare the 2015-2017 budget.			As above.
		Source
		(a) PEFA Reports, (b) Budget calendar, (c) Budget Call Circular, (d) Revenue forecasting model forecasts, (e) Sector spending ceilings, (f) Budget policy statement, (g) Annual SG budgets, and (h) PFM factsheets.
	Output Indicator 2.2	Baseline (2011)		Milestone (2013)			Target (2015)
	Extent to which the budget is comprehensive and transparent.	The State has a Budget Manual and new BC & COA have been designed and agreed, but is yet to be implemented. However, the Budget execution is still poor and the processes detailed in the budget manual are not being strictly implemented.		The 2014 budget process is consistent with the budget manual.			Implementation of the new BC&COA has commenced.
		Source
		(a) PEFA Reports, (b) PFM Factsheets, (c) Audit reports, (d) State BC & COA, (e) State Budget Manual, (f) Annual SF budgets, and (g) ENS Website.
	Output Indicator 2.3	Baseline (2011)		Milestone (2013)			Target (2015)
	Level of predictability and control in budget execution.	Cash forecasting is weak and budget implementation is not based on realistic work plans. IGR is approximately 13% of total revenue. Commitments and contractor arrears are not effectively tracked, giving rise to cash rationing.		(a) The Accountant Generals Office has the capacity to prepare quarterly cash plans based on budget profiles, and (b) strategy is developed for improving IGR.			(a) a basic cash forecasting model is being operated within the Treasury, and (b ) Implementation of the Strategy for improving IGR has commenced.
		Source
		(a) PEFA Reports, (b) Quarterly Work plans, (c) Cash budgets, (d) Revenue profile of BIR, (e) PFM factsheets, and (f) IGR strategy.
	Output Indicator 2.4	Baseline (2011)		Milestone (2013)			Target (2015)
	Quality of accounting, recording and reporting.	Final Accounts have been prepared up to 2010. Bank reconciliation is weak and accounting is done manually. Attempt at computerizing the accounting system has not succeeded. However, the State has acquired an HR Database linked to the Payroll which is due to be tested with the payment of April 2012 salaries; and an initial savings of N100million had been reportedly made from the first month of test-run. Exco has approved the report of the consultants but, final clean-up is being planned in order to conclude the process and the database moved permanently to the OHoS.		(a) A Final Accounts Procedures Manual prepared and accounts staff trained, (b) Central MDAs begin to prepare Asset register using new template, (c) Staff trained in debt management procedures and processes, and (d) Procurement manual produced and associated staff training provided.			(a) Office of the Accountant General is using revised procedures for final accounts preparation, and (b) Implementation of the accounts computerisation action plan has started.
		Source
		(a) PEFA Reports, (b) Book keeping records, (c) Management and Financial Reports, (d) debt management procedures, (e) procurement manual, and (f) PFM factsheets.
Impact Weighting	Output Indicator 2.5	Baseline (2011)		Milestone (2013)			Target (2015)
50%	Extent and quality of external scrutiny and audit.	A new Auditor-General was recently appointed by EnSG after the retirement of the former A-G. The HoA / PAC lacks the capacity for effective scrutiny of financial statements/ Audit Reports. Audit Procedures Manual has been prepared but this needs to be revised and updated. The audit of final accounts is usually delayed.		The State's Audit Procedures Manual is revised and audit staff trained.			(a) Final accounts audited in line with revised Audit Procedures Manual and published within 6 months of submission, and (b) SHoA/PAC has the capacity to scrutinise financial statements/ Audit Reports.
		Source
		(a) PEFA Reports, (b) Audit Procedures Manual, (c) Audit Reports, and (d) PFM factsheets.
Inputs (£)	DFID (£)	Govt (£)	Other (£)		Total (£)				DFID Share (%)	Risk Rating
	DFID to complete	DFID to Complete								High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 3	Output Indicator 3.1	Baseline (2011)			Milestone (2013)			Target (2015)			Assumptions
State civil service performance improved.	Clarity and appropriateness of public service organisation and operational management.	There is clarity of mandates, structures, organisations and functions for all organisations from the reviews done which were approved by the ESG in 2012. The rationalisation of mandates in line with recommendations has not yet made measurable progress. Although ESEPC has made significant progress with implementing corporate planning recommendations, other central MDAs are not so advanced.			(a) Reorganisation of OHoS is in progress; in line with the corporate plan, (b) OHoS has the capacity to support MDAs to conduct corporate planning, and (c) recommendations for rationalising mandates between MoPB and ESEPC have been presented to ESG.			Reorganisation of MDAs in at least three sectors is in progress; in line with corporate plans.			As above.
		Source
		(a) Corporate Plans, (b) Mandate reviews reports, and (c) organograms.
	Output Indicator 3.2	Baseline (2011)			Milestone (2013)			Target (2015)
	Extent to which HRM policies and organisation are in place.	ESG is guided by laws and regulations that are provided by State circulars and the Federal Civil Service Rules which need to be updated and modernised.			(a) G&SI-sensitive ESG HRM policy developed, and (b) action plan to improve HRM prepared.			(a) HRM policy adopted, and (b) action plan being used to reform selected HRM processes.
		Source
		(a) Establishment Circulars, (b) Federal and State Civil Service Rules, and (c) HRM Policy Documents.
	Output Indicator 3.3	Baseline (2011)			Milestone (2013)			Target (2015)
	Extent to which establishment planning and workforce planning, management and development is in place.	ESG does not have systematic workforce planning process. Recent initiatives to strengthen the HRMIS should yield improved workforce information but implementation is at an early stage.			(a) Establishment Plan and Workforce Plan prepared in OHoS, and (b) ESG-wide workforce planning approach paper prepared.			(a) Agreed establishment and workforce planning process being used in OHoS, and (b) action plan to introduce workforce planning agreed.
		Source
		(a) OHOS Workforce plan and progress reports, and (b) workforce planning action plan.
Impact Weighting	Output Indicator 3.4	Baseline (2011)			Milestone (2013)			Target (2015)
25%	Extent to which MDA performance management policies and procedures are in place.	The Governor’s decision to refocus ESG on service delivery resulted in establishing a SERVICOM office in his Office. A Service Charter policy has been designed. Service Charters are being developed in seven MTSSs MDAs as the first phase (Ministries of Health, Education, Environment, Agriculture, Works, Water and Transport).			(a) SERVICOM office has the capacity to support MDAs to prepare service charters, and (b) the seven pilot MDAs have completed preparation of service charters which include a G&SI focus.			(a) SERVICOM office has the capacity to support MDAs to conduct annual reviews against service charters, and (b) at least three of the seven pilot MDAs have conducted annual reviews against service charters.
		Source
		(a) SEAT reports, (b) Service Charters, (c) Service Charter Performance Reports, and (d) MDA Quarterly Performance Reports.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID Share (%)	Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

PROJECT NAME	State Partnership for Accountability, Responsiveness and Capability (SPARC), Nigeria (2008 – 2015)
STATE	Jigawa (Type A Approach)

GOAL	Impact Indicator 1	Baseline	Milestone (end 2013)	Target (2015)
Nigeria’s own resources used efficiently and effectively to achieve MDGs	Improvements in progress towards MDGs	See Programme Logframe for baseline and milestones.
	Impact Indicator 2	Baseline	Milestone (end 2013)	Target (2015)
	Improvements in citizens’ access to, use of and satisfaction with basic services	See Programme Logframe for baseline and milestones.
	Impact Indicator 3	Baseline (August 2010)	Milestone (end 2013)	Target (2015)
	Improvements in Citizens perceptions of State Government performance	See Programme Logframe for baseline and milestones.

PURPOSE	Outcome Indicator 1	Baseline (2011)			Milestone (2013)			Target (2015)			Assumptions
The efficiency and effectiveness of selected state level governments’ use of public resources is enhanced	Effectiveness of policies and strategies and consistency of Medium-Term Plans and Budgets with policies and resource envelopes.	Comprehensive Development Framework in place and being used to guide MTSS and budget development.			The CDF and MTSSs of priority sectors are adequately reflected in the 2014-2016 budget.			The CDF and MTSSs/sector plans of at least 75% of sectors are adequately reflected in the 2015-2017 budget.			Political will to sustain the reform agenda is maintained beyond the lifetime of SPARC / State governments continue to prioritise the MDGs in the allocation and use of public resources / Levels and fluctuations in oil revenues do not unduly undermine fiscal stability / SAVI achieves sustainable improvements in State Government inclusivity and responsiveness to citizens’ rights and demands / Sectoral SLPs achieve sustainable improvements in sector performance / .
		Source
		(a) Revised CDF, (b) Revised MTSSs, (c) State Budgets, and (d) SPARC Evaluation Reviews.
	Outcome Indicator 2	Baseline (2011)			Milestone (2013)			Target (2015)
	Realism and predictability of multi-year capital and recurrent budgets.	The 2011 PEFA identified that actual expenditure deviated for budgeted expenditure by 49%, 15% and 35% respectively between 2007 and 2009. Budgets are prepared using multi-year forecasts of fiscal aggregates on a three year rolling basis while recurrent expenditure aggregates are forecast annually. However there are no clear links with subsequent setting of annual budget ceilings. Whilst monthly releases for salaries and routine overhead expenditure to MDAs are predictable, approvals and payments of non-routine recurrent overhead and capital expenditures are not predictable as they are determined by estimates of availability of funds by the Treasury and prioritization of releases by the Governor. Annual cash flow forecast for the fiscal year and monthly updates are not prepared.			(a) Variance between 2014-2016 budget and medium-term revenue forecasts is less than 25%, (b) Expenditure budget variance is below 25%, and (c) Annual cash forecasts prepared by Treasury are used as the basis for cash management and disbursement in priority sectors.			(a) Variance between 2015-2017 budget and medium-term revenue forecasts is less than 15%, (b) Expenditure budget variance is below 15%, and (c) Quarterly cash forecasts prepared by Treasury are used as the basis for cash management and disbursement in priority sectors.
		Source
		(a) PEFA reports, (b) Budget Call Circular, (c) Revenue forecasting model forecasts, (d) Sector spending ceilings, (e) SDP, (f) Annual SG budgets, (g) Annual Accounts/ Financial Statements, and (h) PFM factsheets.
	Outcome Indicator 3	Baseline (2011)			Milestone (2013)			Target (2015)
	Effectiveness of core MDA support for government planning, finance and human resources performance management and service delivery mechanisms.	MDA Mandate descriptions are yet to be adopted by JSG and mandate rationalisation has not begun. HRM policies and processes, including establishment and workforce planning, require improvement. While there are Service Charters in Health, Education and Water, there is no standardised central process for performance management or service delivery.			(a) Agreed procedures and responsibilities for routine review of mandates are being implemented, (b) Reorganisation is underway in 50% of central MDAs, (c) A modern G&SI sensitive HRM Policy and improvement Strategy have been agreed, (d) a G&SI sensitive workforce planning Policy and Strategy have been agreed (including succession planning), and (e) G&SI sensitive Service Charters for pilot MDAs have been published, alongside establishment of a unit to support this process.			(a) Mandate compendium has been updated, (b) Reorganisation has been completed in 50% of central MDAs and is underway in the MDAs of at least two priority sectors, (c) Selected HRM processes have been reformed in line with the State HRM Policy, (d) Establishment and workforce plans are being implemented in priority central MDAs, and (e) Performance against Service Charters for pilot MDAs has been published.
		Source
		(a) Mandate descriptions and rationalisation reports, (b) corporate planning implementation reports, (c) HRM policy and improvement strategy, (d) service charters (performance management reports, and (e) workforce audit reports.
	Outcome Indicator 4	Baseline (2011)			Milestone (2013)			Target (2015)
	% of PEFA/SEAT Dimensions improving by at least one rating.	See 2011 SEAT/PEFA			N/A			25%
		Source
		State Government PEFA/SEAT Self Assessments, validated by external M&E Contractor.
INPUTS (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID SHARE (%)
	DFID to complete	DFID to Complete
INPUTS (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 1	Output Indicator 1.1	Baseline (2011)		Milestone (2013)				Target (2015)			Assumptions
Policy and strategy development, monitoring and evaluation improved.	Extent to which policy and strategy making processes meet good practice standards.	Limited technical support is available; BEPD has been able to provide technical support for development of the CDF. Some data collection tools have been developed and circulated to MDAs; Sector Desk Officers also provide limited support on MTSS development. guidelines for Sector Planning Teams developed and circulated.		Provision to all MDAs and policy makers by BEPD of appropriate tools (e.g. guidelines) related to policy, strategy and M&E, with priority placed on selected specific process standards (see guides).				(a) Health, Education, Agriculture and Water sectors are using strategy and M&E processes which meet good practice standards, and (b) Policy makers using selected improved standards in making development plans (see guides).			Citizens’ ability to claim rights and hold government accountable increased. / Civil society and State and Federal Government are, and remain, committed to the MDGs. / Changes in political leadership do not undermine State Government support for State Development Plan governance reforms. / Changes in senior positions (e.g. HoS, Commissioners) do not undermine State Government support for key initiatives (e.g. Corporate Planning, State Development Plans, and MTSS). / State Government is committed to implementing institutional change actions detailed in the State Development Plan. / Constitutional reform do not have negative effects on inter-government relations. / HIV/AIDS, malaria and TB incidence do not prevent improvements in efficient and effective use of funds.
		Source
		(a) SEAT Reports, (b) CDF and Sector Performance Reports, and (c) MTSS, Policy and M&E Guidelines.
	Output Indicator 1.2	Baseline (2011)		Milestone (2013)				Target (2015)
	Quality and comprehensiveness of policies and strategies.	There is a state policy document (Comprehensive Development Framework - CDF) in place, which was used as a basis for the development of MTSS in 4 sectors and Medium Term Plans in all the other sectors.		(a) CDF better meets content Policy standards, and (b) 2014-2016 MTSS of priority sectors (Health, Education, Agriculture and Water) better meet content MTSS standards.				(a) 2015-2017 MTSS of priority sectors (Health, Education, Agriculture and Water) are consistent with good practice as indicated in MTSS Guidelines, and (b) other sectors demonstrate improved content standards in medium term plans.
		Source
		(a) SEAT Reports, (b) CDF, (c) Fiscal Projections, and (d) MTSS and CDF and Sector Performance Reports.
	Output Indicator 1.3	Baseline (2011)		Milestone (2013)				Target (2015)
	Extent to which results frameworks are comprehensive and measured.	Reliable data is lacking in most sectors; this has resulted in slow and unreliable sector performance reviews - which is required for MTSS development and roll-over. The Statistics unit requires strengthening, and no M&E Unit exists.		KPI MIS in place within BEPD, incorporating CDF KPIs and the data required to measure them.				(a) KPI MIS producing performance reports against CDF KPIs and being used to prepare policy/strategy analysis for priority sectors, and (b) M&E scorecards prepared by at least 3 priority MTSS sectors.
		Source
		(a) SEAT Reports, (b) CDF and MTSSs, (c) Annual CDF and Sector Performance Reports, (d) KPI MIS reports, and (e) MDA M&E Scorecards.
Impact Weighting	Output Indicator 1.4	Baseline (2011)		Milestone (2013)				Target (2015)
25%	Extent to which performance management processes are being used.	Key Performance Indicators are incorporated in the CDF, but there is a challenge with data availability to allow for effective measurement; conversely, there is no effective result from performance measurement process to support decision making.		(a) CDF adjusted, with stakeholder involvement, and (b) BEPD have the capacity to support sectors in implementing annual sector performance reviews which incorporate a G&SI focus.				(a) MEPB conducts CDF annual performance review, in line with the CDF M&E framework, which incorporates a G&SI focus, and (b) Health, Education, Agriculture and Water MTSS annual performance reviews better meet performance review standards.
		Source
		(a) SEAT Reports, (b) Corporate Planning progress reports, (c) Annual CDF and Sector Performance Review Reports, and (d) CDF and MTSSs.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)			DFID Share (%)		Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 2	Output Indicator 2.1	Baseline (2011)			Milestone (2013)				Target (2015)		Assumptions
State public financial management improved.	Extent to which the budget is credible and policy based.	Actual expenditure deviated for budgeted expenditure by more than 15% of budgeted expenditure, as well as expenditure composition variance exceeded by 15% - both for 2007 -2009. Actual IGR against budget shows significant variance. On the average Federal transfers constitute 91% of the total revenue of the State Government over the period, indicating high dependence mainly on Federal transfers to fund its aggregate expenditure. The forecast of internally generated revenue is inadequate; the credibility of both the revenue and expenditure budgets is low. Work planned to strengthen the BC&CoA in conjunction with the CGS/ Federal MDG office is planned.			(a) Approved 2014-2016 budget has been developed using medium-term revenue forecasts, and (b) BC&CoA reviewed in conjunction with CGS/ federal MDG Office (subject to Federal level approvals) to include MDG and G&SI classifications where appropriate.				(a) State Government is using medium-term revenue forecasts and sector spending ceilings to prepare the 2015-2017 budget, and (b) BC&CoA strengthened to include MDG and G&SI classifications.		As above.
		Source
		(a) PEFA reports, (b) PFM Factsheets, and (c) revenue forecasting model.
	Output Indicator 2.2	Baseline (2011)			Milestone (2013)				Target (2015)
	Extent to which the budget is comprehensive and transparent.	Documentation provided to the SHoA with Budget proposals in inadequate, data on extra-budgetary expenditure are not included in fiscal reports. Transparency on inter-governmental relation is not good, as there is no consolidated overview of the transfers of revenue from the Federation Account and from State to LGs.			(a) Annual budget documentation better meets PEFA standards, including macroeconomic assumptions and deficit financing and composition, and (b) a process for the publication of budget allocations to LGs is prepared.				(a) Annual budget documentation better meets PEFA standards, including prior year budget outturn and details of debt stock, and (b) State and LGs/ LCDAs publish what they receive annually.
		Source
		(a) PEFA reports, (b) LG budget preparation guidelines, (c) LG budgets, and (d) Assessment of consistency between LG budget guidelines and actual LG budgets.
	Output Indicator 2.3	Baseline (2011)			Milestone (2013)				Target (2015)
	Level of predictability and control in budget execution.	Annual cash flow forecasts for the fiscal year and monthly updates are not prepared. There are predictable monthly releases for salaries and routine overhead expenditure to MDAs. Approvals and payments of non-routine recurrent overhead and capital expenditures are not predictable. Annual cash flow forecast for the fiscal year and monthly updates are not prepared. There are also weakness in the procurement system.			(a) Annual cash forecasts prepared, incorporating budget profile information for key sectors (Health, Education, Agriculture and Water), (b) Procurement Unit procedures which comply with good practice are prepared, and (c) strategy developed for improved IGR.				(a) Quarterly cash forecasts prepared by Treasury, incorporating budget profile information for original 4 and additional two sectors, (b) MDAs are operating in line with procurement procedures, and (c) elements of strategy for improved IGR being implemented.
		Source
		(a) PEFA reports, (b) Procurement and Fiscal Responsibility Laws, (c) Minutes of ExCo meetings, (d) Cash forecasting model reports, and (e) PFM Factsheets.
	Output Indicator 2.4	Baseline (2011)			Milestone (2013)				Target (2015)
	Quality of accounting, recording and reporting.	Financial statements are prepared annually but do not contain complete and accurate information as well as the consolidated activities of parastatals and Local Governments, resulting in the need to revise the accounts before they are audited. Debt data is not comprehensive and does not show the principal, accrued interest and debt service for both external and domestic debt.			(a) MDA League Log reports demonstrate improved quality of standardised accounting, (b) Reports generated from IFMIS on a timely basis demonstrate improved recording and reporting from MDAs, and (c) Debt records are improved.				(a) Accounts of autonomous MDAs are included in annual financial reports, and (b) Final accounts produced and reports submitted for audit within 6 months of the next accounting year.
		Source
		(a) PEFA reports, (b) MDA league logs, (c) IFMIS reports, and (d) Final Accounts Reports.
Impact Weighting	Output Indicator 2.5	Baseline (2011)			Milestone (2013)				Target (2015)
50%	Extent and quality of external scrutiny and audit.	A wide range of financial audits are performed, focusing on significant and systemic issues. Formal responses are made by MDAs to audit issues raised but there is no evidence of follow up.			(a) Auditing techniques appropriate for computerised system are being used, and (b) Procedures to ensure monitoring of audit issues and recommendation are developed.				Procedure for monitoring implementation of agreed Audit report recommendations is in place.
		Source
		(a) PEFA reports, (b) PAC meeting minutes, and (c) SHoA Annual Audit Reports.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID Share (%)	Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 3	Output Indicator 3.1	Baseline (2011)			Milestone (2013)			Target (2015)			Assumptions
State civil service performance improved.	Clarity and appropriateness of public service organisation and operational management.	There is clarity in the legal authority and specific responsibilities of most of the MDAs but these are not centrally stored or easily accessible; functional definitions need to be documented and accessible and there needs to be a clear mechanism for resolving overlaps. Functional relationships between the various tiers of Government need to be managed better.			(a) Mandates descriptions adopted by JSG and a process for rationalising mandates is in place, (b) At least 50% of central MDAs have completed the first phase of corporate plan implementation, (c) Technical support teams have the capacity to support MDAs to prepare and implement corporate plans, and (d) an action plan to modernise Registry delivered.			Corporate plans are being implemented in at least 2 out of 4 priority sectors (Health, Education, Agriculture and Water).			As above.
		Source
		(a) SEAT reports, (b) Mandate Reports, (c) Corporate plans, (d) Registry reports, and (e) MDA Quarterly Reports.
	Output Indicator 3.2	Baseline (2011)			Milestone (2013)			Target (2015)
	Extent to which HRM policies and organisation are in place.	Jigawa State is guided by the laws and regulations that are provided in the State/Federal Civil service Rules and Circulars. The laws and rules are not strictly enforced nor are there effective sanctions imposed in all cases of default.			State-wide G&SI-sensitive HRM policy and strategy for improving HRM processes developed.			(a) HRM policy framework and systems reflect good practice, and (b) process of realigning HRM structures and processes with policy has started.
		Source
		(a) SEAT Reports, (b) HRM Policy Document, (c) HRM policy committee minutes, and (d) establishment circulars.
	Output Indicator 3.3	Baseline (2011)			Milestone (2013)			Target (2015)
	Extent to which establishment planning and workforce planning, management and development is in place.	There are schemes of service and a grading structure which are published and accessible to all public servants but there is no clear method to check whether the workforce structure suits the functional requirements of the public service. Aside from the MDAs supported by SPARC in Finance, BEPD, SSGs Office and OHOS and other DFID partnerships (ESSPIN & PATHS2) in Education and Health respectively; Jigawa State has no clear system of establishment planning.			(a) Draft establishment plans and workforce plans completed for central MDAs, and (b) Workforce planning policy and strategy developed, incorporating succession planning, and reflecting G&SI issues.			(a) Draft establishment plans and workforce plans being developed for remaining MDAs, (b) JSG workforce audit, incorporating a G&SI focus, undertaken, and (c) Potential HR cost savings presented to SG.
		Source
		(a) SEAT Reports, (b) Establishment Plans, (c) Workforce plans, and (d) MDA Quarterly Reports.
Impact Weighting	Output Indicator 3.4	Baseline (2011)			Milestone (2013)			Target (2015)
25%	Extent to which MDA performance management policies and procedures are in place.	Service Charters exist in Health, Education and Water. None in Central MDAs. No standard setting process. No performance Agreements			(a) A relevant unit has been identified and has the capacity to support MDAs to prepare service charters, (b) central ministries have developed G&SI-sensitive service charters with performance statements, and (c) Performance Management model agreed.			(a) Performance against service standards (including equity of access) is measured for Central MDAs and four sector MDAs, and (b) the Performance Management model has been piloted in at least two MDAs.
		Source
		(a) SEAT Reports, (b) Service Charters, (c) Service Charter Performance Reports, and (d) performance management model reports.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID Share (%)	Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

PROJECT NAME	State Partnership for Accountability, Responsiveness and Capability (SPARC), Nigeria (2008 – 2015)
STATE	Kaduna (Type B Approach)

GOAL	Impact Indicator 1	Baseline	Milestone (end 2013)	Target (2015)
Nigeria’s own resources used efficiently and effectively to achieve MDGs	Improvements in progress towards MDGs	See Programme Logframe for baseline and milestones.
	Impact Indicator 2	Baseline	Milestone (end 2013)	Target (2015)
	Improvements in citizens’ access to, use of and satisfaction with basic services	See Programme Logframe for baseline and milestones.
	Impact Indicator 3	Baseline (August 2010)	Milestone (end 2013)	Target (2015)
	Improvements in Citizens perceptions of State Government performance	See Programme Logframe for baseline and milestones.

PURPOSE	Outcome Indicator 1	Baseline (2011)		Milestone (2013)				Target (2015)			Assumptions
The efficiency and effectiveness of selected state level governments’ use of public resources is enhanced	Effectiveness of policies and strategies and consistency of Medium-Term Plans and Budgets with policies and resource envelopes.	No state development plan approved. Four priority MTSSs devised but quality is poor and they are not reflected in the budget.		(a) A new SDP has been approved and published, and (b) within the four priority sectors, MTSS goals and objectives are consistent with the SDP and can be linked to the 2014-2016 budget.				The SDP and MTSSs of the four priority sectors are adequately reflected in the 2015-2017 budget.			Political will to sustain the reform agenda is maintained beyond the lifetime of SPARC / State governments continue to prioritise the MDGs in the allocation and use of public resources / Levels and fluctuations in oil revenues do not unduly undermine fiscal stability / SAVI achieves sustainable improvements in State Government inclusivity and responsiveness to citizens’ rights and demands / Sectoral SLPs achieve sustainable improvements in sector performance / .
		Source
		(a) State Development Plan, (b) MTSSs, (c) State Budgets, and (d) SPARC Evaluation Reviews.
	Outcome Indicator 2	Baseline (2011)		Milestone (2013)				Target (2015)
	Realism and predictability of multi-year capital and recurrent budgets.	Unrealistically high budgets continue to be set. Progress against this score deteriorated significantly over time fluctuating from 44% in 2009, 57% in 2010 and 55% in 2011. Multi-year forecasts are now made for revenue, and allocation of revenue funds between sectors/ministries. However there is no clear link between the multi-year fiscal forecasts and the eventual approved budget. An effective cash management and planning system is not in place, with releases being controlled centrally with no predictability of funds being available to MDAs for budget implementation.		(a) Variance between 2014-2016 budget and medium-term revenue forecasts is less than 35%, and (b) Expenditure budget variance is below 35%.				(a) Variance between 2015-2017 budget and medium-term revenue forecasts is less than 25%, (b) Expenditure budget variance is below 25%, and (c) Annual cash forecasts prepared by Treasury are used as the basis for cash management and disbursement in priority sectors.
		Source
		(a) PEFA reports, (b) Budget Call Circular, (c) Revenue forecasting model forecasts, (d) Sector spending ceilings, (e) SDP, (f) Annual SG budgets, (g) Annual Accounts/ Financial Statements, and (h) PFM factsheets.
	Outcome Indicator 3	Baseline (2011)		Milestone (2013)				Target (2015)
	Effectiveness of core MDA support for government planning, finance and human resources performance management and service delivery mechanisms.	Mandates have been documented and BEMST has been designated to maintain mandates in future. Three MDAs are implementing corporate plans, and two others are partway through the process. A new HRD policy has been validated but HRM policies and systems need updating. Establishment planning exercises are underway in four central MDAs, but there is no general establishment or workforce planning function. A new performance management framework is under development.		(a) Mandates have been documented across government, (b) Corporate Planning is being systematically rolled out across all sectors, (c) A modern G&SI sensitive HRM Policy and improvement Strategy/Action Plan have been agreed, (d) Establishment and workforce plans, taking into account G&SI issues, have been agreed in priority central MDAs, and (e) G&SI sensitive Service Charters have been published and a Performance Management model implemented in two pilot MDAs.				(a) Mandates are being rationalised in line with recommendations to improve organisational effectiveness, (b) Corporate Planning is being implemented in at least 50% of sectors, (c) Selected HRM processes (including posting of trained HR Managers within OHoS and priority MDAs) are being reformed in line with the State HRM Policy, (d) Establishment and workforce plans are being implemented in priority central MDAs, (e) government-wide workforce analysis has been completed, and (f) Performance information against Service Charters and from Performance Management systems has been published for two pilot MDAs.
		Source
		(a) Mandate descriptions and rationalisation reports, (b) corporate planning implementation reports, (c) HRM policy and improvement plan reports, (d) performance management reports, and (e) workforce analysis reports.
	Outcome Indicator 4	Baseline (2011)		Milestone (2013)				Target (2015)
	% of PEFA/SEAT Dimensions improving by at least one rating.	See 2011 SEAT/PEFA		N/A				20%
		Source
		State Government PEFA/SEAT Self Assessments, validated by external M&E Contractor.
INPUTS (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID SHARE (%)
	DFID to complete	DFID to Complete
INPUTS (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 1	Output Indicator 1.1	Baseline (2011)			Milestone (2013)			Target (2015)			Assumptions
Policy and strategy development, monitoring and evaluation improved.	Extent to which policy and strategy making processes meet good practice standards.	The Ministry of Economic Planning is able adequately to provide support in only three of the 12 areas identified in the guide to sector MDAs. The MoEP's capacity to provide necessary advice and support to MDAs faces a number of constraints, but it includes gaps in relevant technical knowledge base. Technical guidance and support functions have been established within MoEP incorporating the themes of MTSS development. A draft guide on policy making has been developed and shared with the Commissioner for Economic Planning.			(a) Provision to all MDAs by MoEP appropriate tools (e.g. guidelines) related to strategy making and M&E, and (b) Policy and Development Plan making guidelines localised and used to raise awareness of policy makers about their policy making role in Government.			(a) Policy and strategy advice is being provided to ExCo based on sound analysis which incorporates the views of appropriate stakeholders, and (b) standards of advice from MoEP to MDAs as compared with the guidance provided are good on more of the recommended processes.			Citizens’ ability to claim rights and hold government accountable increased. / Civil society and State and Federal Government are, and remain, committed to the MDGs. / Changes in political leadership do not undermine State Government support for agreed change plans. / Changes in senior positions (e.g. HoS, Commissioners) do not undermine State Government support for key initiatives (e.g. Corporate Planning, State Development Plans, and MTSS). / State Government is committed to implementing institutional change actions detailed in agreed change plans. / State Government is committed to mainstreaming governance reforms within the State Development Plan. / Constitutional reform do not have negative effects on inter-government relations. / HIV/AIDS, malaria and TB incidence do not prevent improvements in efficient and effective use of funds.
		Source
		(a) SEAT Reports, (b) SDP and Sector Performance Reports, and (c) MTSS, Policy and M&E Guidelines.
	Output Indicator 1.2	Baseline (2011)			Milestone (2013)			Target (2015)
	Quality and comprehensiveness of policies and strategies.	A State Development Plan was developed in 2010 in line with government's eleven points development agenda. The plan was never published and was never implemented. With a change in administration, a new policy agenda was formulated which has kick started a process of developing a new State Development Plan. Four MTSSs have been developed, but their quality and alignment with realistic ceilings, and with policy direction (owing in part to its absence) is poor.			(a) A financially feasible State Development Plan (SDP) has been developed, and (b) 2014-2016 MTSS of priority sectors (Health, Education, Agriculture) better meet MTSS standards.			2015-2017 MTSS of priority sectors (Health, Education, Agriculture) are consistent with good practice as indicated in MTSS Guidelines.
		Source
		(a) SEAT Reports, (b) MTSSs and SDP, (c) Fiscal Projections, and (d) MTSS and SDP and Sector Performance Reports.
	Output Indicator 1.3	Baseline (2011)			Milestone (2013)			Target (2015)
	Extent to which results frameworks are comprehensive and measured.	There is a dearth of reliable and up-to-date data in the State, although there has been improvement in the availability of baseline information. Most sectors do not have reliable baseline information. Inter-agency data sharing is limited and demographic data is not available to develop SMART outcome targets. The majority of MDAs do not have access to research findings or statistics that sufficiently support strategic analysis or targeted planning.			The SDP and MTSSs in at least 3 priority sectors include comprehensive results frameworks with relevant KPIs.			(a) Results frameworks in the SDP and MTSSs of at least 3 priority sectors include both targets and actual values for all KPIs, and (b) M&E scorecards prepared by at least 3 priority MTSS sectors.
		Source
		(a) SEAT Reports, (b) SDP and MTSSs, (c) Annual SDP and Sector Performance Reports, and (d) MDA M&E Scorecards.
Impact Weighting	Output Indicator 1.4	Baseline (2011)			Milestone (2013)			Target (2015)
25%	Extent to which performance management processes are being used.	Good progress has been made in setting up systems for monitoring progress against work plans, budget and capital works implementation. Limited regular evidence of performance assessments and impact reviews are being used to adjust policies, strategies and programmes.			MoEP have the capacity to support sectors in implementing annual sector performance reviews which incorporate a G&SI focus.			(a) MoEP conducts SDP annual performance review, in line with the SDP M&E framework, which incorporates a G&SI focus, and (b) priority sectors (Health, Education, Agriculture) have held MTSS annual performance reviews which incorporate a G&SI focus.
		Source
		(a) SEAT Reports, (b) Corporate Planning progress reports, (c) Annual SDP and Sector Performance Review Reports, and (d) SDP and MTSSs.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)			DFID Share (%)		Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 2	Output Indicator 2.1	Baseline (2011)			Milestone (2013)			Target (2015)			Assumptions
State public financial management improved.	Extent to which the budget is credible and policy based.	The trend in budget performance is very poor. PEFA PI-3 scored ‘D’ in 2008 and in February 2012 a D indicating that throughout the period, KDSG has continued to set unrealistically high budgets. Progress against this score deteriorated significantly over time fluctuating from 44% in 2009, 57% in 2010 and 55% in 2011. Actual expenditure was lower than the original budget by more than 15% in all three years assessed. There is no adopted State Development Plan.			Medium term revenue projections updated using updated revenue model.			The 2015-2017 budget call circular contains guidance which is consistent with goals and objectives of SDP and priority MTSS sectors (Health, Education, Agriculture).			As above.
		Source
		(a) PEFA reports, (b) Budget calendar, (c) Budget Call Circular, (d) Revenue forecasting model forecasts, (e) Sector spending ceilings, (f) Budget policy statement (g) Annual SG budgets, and (h) PFM factsheets.
	Output Indicator 2.2	Baseline (2011)			Milestone (2013)			Target (2015)
	Extent to which the budget is comprehensive and transparent.	Information included in budget documentation is not comprehensive enough. Only four of the nine elements prescribed by PEFA are included in the budget and these include a) Deficit financing, describing anticipated composition b) Financial Assets, including details at least for the beginning of the current year c) Current year’s budget (either the revised budget or the estimated outturn), presented in the same format as the budget proposal and d) Summarized budget data for both revenue and expenditure according to the main heads of the classifications used (ref. PI-5), including data for the current and previous year.			Annual budget documentation better meets PEFA standards, including macro-economic assumptions and the state debt profile.			Annual budget documentation better meets PEFA standards, including prior year’s budget outturn, information on the fiscal deficit and explanation of budget implications of new policy initiatives.
		Source
		(a) PEFA reports, (b) Annual budget documentation, (c) Annual SG budgets, and (d) PFM factsheets.
Impact Weighting	Output Indicator 2.3	Baseline (2011)			Milestone (2013)			Target (2015)
50%	Level of predictability and control in budget execution.	The cash management system in Kaduna is heavily centralised. Despite the existence of plans and budgets, funds are only made available subsequent to requests for cash release, which are subject to a long passage with several queues and many delays. In effect, a cash management and planning system is not in place, MDAs have no effective power to make their projections against the plans they made, and there is no predictability of cash availability to implement plans. Allocation decisions are taken centrally on a case by case basis with no reference to policies or budgets. DMD plans to move its data to the CS-DRMS system, with the assistance of Crown Agents.			(a) Annual budgets for Health sector MDAs are profiled, and (b) Staff trained on the use of new CS-DRMS.			(a) A basic cash forecasting model is being operated within the Treasury, and (b) Health sector MDA cash releases are consistent with the profiled budget.
		Source
		(a) PEFA Reports, (b) Annual SG budgets, (c) Cash forecasting model forecasts, (d) Cash budgets, and (e) PFM factsheets.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID Share (%)	Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 3	Output Indicator 3.1	Baseline (2011)			Milestone (2013)			Target (2015)			Assumptions
State civil service performance improved.	Clarity and appropriateness of public service organisation and operational management.	There is an unpublished mandate report which presents MDA mandate summaries, core functions, organograms, intergovernmental linkages including associated parastatals. BEMST is agreed as the central agency responsible for mandates but it is unclear about its role. Three MDAs (OHoS, MoEP and Education) have completed corporate plans to the functional review stage and are implementing the results. Two others (Health and Agriculture) are part way along the line.			(a) A system and guidelines to support the publication and review of mandates has been developed, and (b) A system and guidelines to support the roll out of Corporate Planning to other MDAs is being used.			(a) The system and guidelines to support the publication and review of mandates is in use, and (b) The system and guidelines for supporting MDA Corporate Planning have been adjusted in response to lessons learned.			As above.
		Source
		(a) Mandates clarification report of MDAs, and (b) Corporate planning reports (OHoS, MoEP, Health and Education).
	Output Indicator 3.2	Baseline (2011)			Milestone (2013)			Target (2015)
	Extent to which HRM policies and organisation are in place.	Central HRM functions are the responsibility of OHOS (BEMST and PSO) but these are weakly understood and implemented. After years of under funding and neglect of HRD, a Human Resource Development Policy has been prepared and validated by PSs. The policy provides the basis for new HRD plans. An individual annual performance management system (APER) is operating but is largely discredited. Government is initiating efforts to revamp it.			(a) A state-wide G&SI-sensitive HRM improvement plan and a workforce strategy have been developed, (b) individual annual performance management system (APER) has been revised, and (c) HRD personnel are better able to operate HRD system.			(a) HRM policy framework and systems better reflect good practice, (b) process of realigning HRM systems with policies has started, and (c) trained HRM managers are in place in OHoS/BEMST and priority MDAs.
		Source
		(a) HRM Policy report and improvement plan, (b) PSM Self Assessment 2012, (c) HRM progress reports, and (d) establishment circulars.
	Output Indicator 3.3	Baseline (2011)			Milestone (2013)			Target (2015)
	Extent to which establishment planning and workforce planning, management and development is in place.	Establishment planning in past years has fallen away with the decline of BEMST but is being restored through establishment planning exercises in BPSR, BEMST, MoEP and PSO. There is no effective workforce planning function linking human resource requirements to service plans.			(a) Workforce development plans, based on new establishment plans have been developed for BEMST, PSO and MoEP, and (b) G&SI-sensitive strategy for KdSG-wide workforce planning and audit developed.			(a) Roll out of establishment and workforce planning has been reviewed and lessons learnt as the basis for institutionalisation, and (b) workforce analysis identifies skills gaps, gender issues etc. and estimates potential for HR cost savings.
		Source
		(a) PSM Self Assessment 2012, and (b) Establishment and workforce planning reports (BPSR, BEMST and MoEP).
Impact Weighting	Output Indicator 3.4	Baseline (2011)			Milestone (2013)			Target (2015)
25%	Extent to which MDA performance management policies and procedures are in place.	There is very little monitoring and evaluation of service delivery performance and little appreciation of the Service Charter concept. There are no public service agreements of any kind to ensure the public service is accountable to the public. Components of Performance management (MDA outputs, outcomes, MDA organisation) have been identified and are at various stages of development. Overarching performance management responsibilities are in the process of being agreed between OHOS, CSC and MoEP.			(a) A Performance Management model (including sector, organisational and individual performance) agreed and being piloted in selected MDAs, (b) Service Charter concept agreed, emphasising equity of access, and piloted in two MDAs, and (c) relevant units have the capacity to support MDAs performance management efforts.			Sector, organisational and individual performance review information is measured and reported for scrutiny by SHoA and State Government.
		Source
		(a) PSM Self Assessment 2012, (b) Annual Sector Performance Review Guideline, and (c) Performance review reports.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID Share (%)	Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

PROJECT NAME	State Partnership for Accountability, Responsiveness and Capability (SPARC), Nigeria (2008 – 2015)
STATE	Kano (Type B Approach)

GOAL	Impact Indicator 1	Baseline	Milestone (end 2013)	Target (2015)
Nigeria’s own resources used efficiently and effectively to achieve MDGs	Improvements in progress towards MDGs	See Programme Logframe for baseline and milestones.
	Impact Indicator 2	Baseline	Milestone (end 2013)	Target (2015)
	Improvements in citizens’ access to, use of and satisfaction with basic services	See Programme Logframe for baseline and milestones.
	Impact Indicator 3	Baseline (August 2010)	Milestone (end 2013)	Target (2015)
	Improvements in Citizens perceptions of State Government performance	See Programme Logframe for baseline and milestones.

PURPOSE	Outcome Indicator 1	Baseline (2011)		Milestone (2013)				Target (2015)			Assumptions
The efficiency and effectiveness of selected state level governments’ use of public resources is enhanced	Effectiveness of policies and strategies and consistency of Medium-Term Plans and Budgets with policies and resource envelopes.	Existing State Plan jettisoned. MTSSs not properly costed and no longer reflect SDP.		(a) A new SDP has been approved and published, and (b) within the two priority sectors, MTSS goals and objectives are consistent with the SDP and can be linked to the 2014-2016 budget.				The SDP and MTSSs of the two priority sectors are adequately reflected in the 2015-2017 budget.			Political will to sustain the reform agenda is maintained beyond the lifetime of SPARC / State governments continue to prioritise the MDGs in the allocation and use of public resources / Levels and fluctuations in oil revenues do not unduly undermine fiscal stability / SAVI achieves sustainable improvements in State Government inclusivity and responsiveness to citizens’ rights and demands / Sectoral SLPs achieve sustainable improvements in sector performance / .
		Source
		(a) State Development Plan, (b) MTSSs, (c) State Budgets, and (d) SPARC Evaluation Reviews.
	Outcome Indicator 2	Baseline (2011)		Milestone (2013)				Target (2015)
	Realism and predictability of multi-year capital and recurrent budgets.	During the period 2007-9 there was significant budget variance: expenditure out-turns compared to the approved budget averaged 51.7%. No forward cash flow planning and monitoring was undertaken and information to MDAs on cash availability was non-existent.		(a) Variance between 2014-2016 budget and medium-term revenue forecasts is less than 35%, and (b) Expenditure budget variance is below 35%.				(a) Variance between 2015-2017 budget and medium-term revenue forecasts is less than 25%, (b) Expenditure budget variance is below 25%, and (c) Annual cash forecasts prepared by Treasury are used as the basis for cash management and disbursement in priority sectors.
		Source
		(a) PEFA reports, (b) Budget Call Circular, (c) Revenue forecasting model forecasts, (d) Sector spending ceilings, (e) SDP, (f) Annual SG budgets, (g) Annual Accounts/ Financial Statements, and (h) PFM factsheets.
	Outcome Indicator 3	Baseline (2011)		Milestone (2013)				Target (2015)
	Effectiveness of core MDA support for government planning, finance and human resources performance management and service delivery mechanisms.	Mandates have been documented, but not yet approved by state government, and mandate rationalisation is still required. Corporate planning processes have begun in some MDAs, but implementation has not started. Apart from civil service rules, which are neither published nor readily accessible, there is no comprehensive HRM policy in place. There are no formal procedures for establishment or workforce planning, and no electronic HRM database exists. No performance management or service delivery policies or procedures appear to be in operation.		(a) Mandates have been documented across government, (b) Reorganisation is underway in priority central MDAs, (c) A modern G&SI sensitive HRM Policy and improvement Strategy have been agreed, (d) Establishment and workforce plans, taking into account G&SI issues, have been agreed in priority central MDAs and selected sector MDAs, and (e) G&SI sensitive Service Charters for pilot MDAs in two sectors have been published and a Service Charter unit established.				(a) Mandates are being rationalised in line with recommendations to improve organisational effectiveness, (b) Reorganisation has been completed in priority central MDAs and is underway in selected MDAs of at least two sectors, (c) Selected HRM processes are being reformed in line with the State HRM Policy, (d) Establishment and workforce plans are being implemented in priority central MDAs and selected sector MDAs, (e) Performance against Service Charters for pilot MDAs in two sectors has been published, and (f) a Performance management concept and implementation plan agreed.
		Source
		(a) Mandate rationalisation reports, (b) corporate planning implementation reports, (c) HRM policy and improvement strategy and implementation reports, (d) service charter reports, and (e) Performance Management Model.
	Outcome Indicator 4	Baseline (2011)		Milestone (2013)				Target (2015)
	% of PEFA/SEAT Dimensions improving by at least one rating.	See 2011 SEAT/PEFA		N/A				20%
		Source
		State Government PEFA/SEAT Self Assessments, validated by external M&E Contractor.
INPUTS (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID SHARE (%)
	DFID to complete	DFID to Complete
INPUTS (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 1	Output Indicator 1.1	Baseline (2011)		Milestone (2013)				Target (2015)			Assumptions
Policy and strategy development, monitoring and evaluation improved.	Extent to which policy and strategy making processes meet good practice standards.	Capacity in the central planning MDAs for supporting MDAs strategy development functions as well as M&E requires further strengthening. Apart from guidance that is contained in the Annual Budget Call Circular, little other guidance is provided to MDAs from the central planning MDAs towards policy and strategy development as well as for the state-wide M&E function. Whilst there is a localised Guide to MTSS Development, capacity to use it within MoPB remains limited.		(a) Provision to all MDAs by MoPB of appropriate tools (e.g. guidelines) related to strategy and M&E, and (b) generic policy making guide is adapted for local use and plan agreed for how to use it with policy makers.				(a) Policy and strategy advice is being provided to ExCo based on sound analysis which incorporates the views of appropriate stakeholders, and (b) a process, consistent with good standards, for the annual roll over of the SDP and existing MTSSs has been agreed.			Citizens’ ability to claim rights and hold government accountable increased. / Civil society and State and Federal Government are, and remain, committed to the MDGs. / Changes in political leadership do not undermine State Government support for agreed change plans. / Changes in senior positions (e.g. HoS, Commissioners) do not undermine State Government support for key initiatives (e.g. Corporate Planning, State Development Plans, and MTSS). / State Government is committed to implementing institutional change actions detailed in agreed change plans. / State Government is committed to mainstreaming governance reforms within the State Development Plan. / Constitutional reform do not have negative effects on inter-government relations. / HIV/AIDS, malaria and TB incidence do not prevent improvements in efficient and effective use of funds.
		Source
		(a) SEAT Reports, (b) M&E information needs survey report, (c) SDP and Sector Performance Reports, and (d) MTSS, Policy and M&E Guidelines.
	Output Indicator 1.2	Baseline (2011)		Milestone (2013)				Target (2015)
	Quality and comprehensiveness of policies and strategies.	The last State Development Plan (KSRD) has been suspended by the new administration that came into office in 2011. Consequently the 2012 Budget was not based on any high-level strategic document but on some 'priorities' determined by the government. Existing MTSSs now need to be revised in order to be fully aligned to a re-worked SDP.		(a) A State Development Plan (SDP) has been developed, and (b) At least 2 MTSSs prepared, consistent with SDP goals and objectives and exhibiting selected standards according to the localised guides.				2015-2017 MTSS of 2 existing and 2 additional sectors better meet good practice as indicated in MTSS Guidelines.
		Source
		(a) SEAT Reports, (b) MTSSs and SDP, (c) Fiscal Projections and (d) MTSS and SDP and Sector Performance Reports.
	Output Indicator 1.3	Baseline (2011)		Milestone (2013)				Target (2015)
	Extent to which results frameworks are comprehensive and measured.	A State Statistical Master Plan (SSMP) has been domesticated from the Federal NBSs' one. It has not yet been approved by KnSG therefore implementation of an SSMP is yet to commence. The Statistics Department of the MoPB is poorly resourced with majority of staff needing capacity development for producing robust statistical and research products.		(a) MoPB provides information needed to guide strategic planning in accordance with client MDA needs, and (b) the SDP and MTSSs in at least 2 priority sectors include comprehensive results frameworks with relevant KPIs.				(a) State-wide KPI MIS generating reports for measurement of results frameworks in the SDP and MTSSs of at least 2 priority sectors, and (b) M&E scorecards prepared by at least 2 priority MTSS sectors.
		Source
		(a) SEAT Reports, (b) SDP and MTSSs, (c) Annual SDP and Sector Performance Reports, (d) KPI MIS reports, and (e) MDA M&E Scorecards.
Impact Weighting	Output Indicator 1.4	Baseline (2011)		Milestone (2013)				Target (2015)
25%	Extent to which performance management processes are being used.	Annual performance assessments have been carried out in a limited number of key sectors in Kano. Project Monitoring Directorate (PMD) requires capacity development of staff and systems for effective M&E. There is still a need to develop a framework for undertaking state-wide M&E.		MoPB have the capacity to support sectors in implementing annual sector performance reviews which incorporate a G&SI focus.				(a) MoPB conducts SDP annual performance review, in line with the SDP M&E framework, which incorporates a G&SI focus, and (b) at least 2 MTSS sectors have held MTSS annual performance reviews which incorporate a G&SI focus.
		Source
		(a) SEAT Reports, (b) Corporate Planning progress reports, (c) Annual SDP and Sector Performance Review Reports, and (d) SDP and MTSSs.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)			DFID Share (%)		Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 2	Output Indicator 2.1	Baseline (2011)		Milestone (2013)					Target (2015)	Assumptions
State public financial management improved.	Extent to which the budget is credible and policy based.	The State Development Plan (KSRD) was suspended by the new administration in 2011 therefore 2012 budget is not based on any high state-level policy document. There were some variances between aggregate revenue out-turn and budget approved over the period 2007-2009 and there are also no costed sector strategies.		(a) The 2014-2016 budget call circular contains guidance which is consistent with SDP goals and objectives, (b) medium term revenue projections updated using updated revenue model, and (c) BC&CoA strengthened to reflect sectoral changes.					Medium-term revenue forecasts and sector spending ceilings have been used to prepare the 2015-2017 budget.	As above.
		Source
		(a) PEFA reports, (b) Budget Call Circular, (c) Revenue forecasting model forecasts, (d) Sector spending ceilings, (e) SDP, (f) Annual SG budgets, and (g) PFM factsheets.
	Output Indicator 2.2	Baseline (2011)		Milestone (2013)					Target (2015)
	Extent to which the budget is comprehensive and transparent.	There is a highly developed chart of accounts used for budget formulation but it is not used for budget execution or reporting. Some Autonomous Government Agencies (AGAs) and Public Enterprises (PEs) had their accounts and audit up to date in Fiscal 2009, but that needs to be extended across the entire government of Kano State.		(a) Consolidated Audit reports are produced, and (b) a strategy for upgrading the IFMIS has been prepared.					An action plan for IFMIS upgrading has been agreed and implementation has started.
		Source
		(a) PEFA reports, (b) Budget review reports, (c) Annual audit report, (d) Revised BC and COA, and (e) PFM factsheets.
	Output Indicator 2.3	Baseline (2011)		Milestone (2013)					Target (2015)
	Level of predictability and control in budget execution.	During the period covered by the 2011 PEFA, no forward cash flow planning and monitoring was reported while information to MDAs on cash availability was non-existent. Also, frequent but non-transparent in-year budget adjustments were reported. This unpredictability in the resource flow to MDAs denied them the ability to plan and utilise resources effectively and efficiently. A capital projects database has been supported but requires ongoing support. There is no consolidation of cash balances nor a system for contracting loans and issuing guarantees. Domestic debt records may not be complete.		(a) Annual cash forecasts are prepared, based on profiled budgets, using a basic cash forecasting model, (b) Strategy developed for improving IGR, (c) Policies and controls developed to strengthen debt management and recording (d) support for capital project database - data capture and training and (e) Treasury Management processes and procedures improved and documented.					(a) Health and Education sector MDA cash releases are consistent with the profiled budget, and (b) elements of strategy for improved IGR being implemented.
		Source
		(a) PEFA reports, (b) Cash forecast reports, (c) IFMIS cash management and debt management reports, (d) PFM factsheets, and (e) IGR Improvement strategy.
	Output Indicator 2.4	Baseline (2011)		Milestone (2013)					Target (2015)
	Quality of accounting, recording and reporting.	Monthly bank reconciliations are done within four weeks of month end and explains all major issues, while monthly imprests are retired within two weeks. Resource availability to service delivery units are not tracked. No in-year reports aimed at 'bringing-in' the budget. Consolidated accounts cover all aspects of government but several significant issues affect their completeness while submission of accounts for audit averaged 14 months.		(a) Treasury has the capacity to improve bank reconciliation systems and procedures, and (b) In year budget performance reports are produced and made available.					Final accounts produced and reports submitted for audit within 6 months of the next accounting year.
		Source
		(a) PEFA reports, (b) Final Accounts reports, (c) Accountant General minutes/memos, and (d) PFM factsheets.
Impact Weighting	Output Indicator 2.5	Baseline (2011)		Milestone (2013)					Target (2015)
50%	Extent and quality of external scrutiny and audit.	Systems and financial audits cover 83% of government expenditure with 2009 audit report completed within one month of receipt. Recurrence of important issues suggest a lack of follow-up on queries raised. SHoA scrutinises detailed revenue and expenditure proposals with Appropriation Committee and other specialised select House Committees negotiating with MDAs.Fiscal policy is not scrutinised and while rules exist to govern in-year budget amendments, such rules are not adhered to. Annual Audit Reports are produced with recommendations and scrutinised by the SHoA but not always implemented.		SHoA has the capacity to scrutinise annual revenue and expenditure proposals.					A procedure for monitoring implementation of agreed Audit report recommendations is in place.
		Source
		(a) PEFA reports, and (b) minutes/report of PAC, SHoA on Final Accounts.
Inputs (£)	DFID (£)	Govt (£)	Other (£)		Total (£)			DFID Share (%)		Risk Rating
	DFID to complete	DFID to Complete								High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 3	Output Indicator 3.1	Baseline (2011)			Milestone (2013)			Target (2015)			Assumptions
State civil service performance improved.	Clarity and appropriateness of public service organisation and operational management.	Aspects of Corporate Planning - mandate clarification, vision, mission, organisational objectives - undertaken in some sections of the Kano State public service but reorganisation in line with these has not started. Organisational mandates have not been approved by the KnSG, and some overlapping mandates still require negotiation and resolution.			(a) Clear organisational mandates, missions and objectives are understood by all staff and being used to guide the work of key central MDAs, and (b) implementation plans for reorganisation of key central MDAs have been prepared.			(a) Senior managers have the capacity to implement reorganisation plans in key central MDAs, and (b) Implementation plans for reorganisation of selected MDAs from at least 2 MTSS sectors have been prepared.			As above.
		Source
		(a) SEAT reports, (b) Corporate Plans, and (c) MDA Quarterly Reports.
	Output Indicator 3.2	Baseline (2011)			Milestone (2013)			Target (2015)
	Extent to which HRM policies and organisation are in place.	Currently existing HRM Policies contained in the Civil Service Rules is not comprehensive while the Civil Service Rules are neither published nor readily accessible to staff. Staff reported not always being aware of its contents and had not had any induction (last staff induction was conducted 10 years ago).			State-wide G&SI-sensitive HRM policy developed and strategy for improving HRM processes prepared.			HRM Policy adopted and HRM improvement strategy being used to reform selected HRM processes.
		Source
		(a) SEAT Reports, (b) State HRM Policy and Improvement Plan, and (c) establishment circulars.
	Output Indicator 3.3	Baseline (2011)			Milestone (2013)			Target (2015)
	Extent to which establishment planning and workforce planning, management and development is in place.	Civil servants do not have individual job descriptions . Existing procedures for workforce are not comprehensive while formal reviews of resource needs of the service have yet to be undertaken. There is no electronic HRM database in place to facilitate workforce planning.			G&SI-sensitive establishment and workforce plans have been prepared in central planning MDAs and selected MDAs from at least 2 MTSS sectors.			Senior managers have the capacity to implement workforce and establishment plans in central planning MDAs and selected MDAs from at least 2 MTSS sectors.
		Source
		(a) SEAT Reports, and (b) Establishment and workforce plans.
Impact Weighting	Output Indicator 3.4	Baseline (2011)			Milestone (2013)			Target (2015)
25%	Extent to which MDA performance management policies and procedures are in place.	No service charters or service-type minimum service standards have been established for any sectors across government in the state.			(a) A relevant unit has been identified and has the capacity to support MDAs to prepare service charters, and (b) the MDAs in at least 2 MTSS sectors have developed service charters with performance statements.			(a) Performance against service standards is measured for Central MDAs and selected MDAs of at least 2 MTSS sectors, and (b) a Performance Management model prepared and an action plan for its implementation developed.
		Source
		(a) SEAT Reports, (b) Service Charters, and (c) Service Charter Performance Reports.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID Share (%)	Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

PROJECT NAME	State Partnership for Accountability, Responsiveness and Capability (SPARC), Nigeria (2008 – 2015)
STATE	Katsina (Type C Approach)

GOAL	Impact Indicator 1	Baseline	Milestone (end 2013)	Target (2015)
Nigeria’s own resources used efficiently and effectively to achieve MDGs	Improvements in progress towards MDGs	See Programme Logframe for baseline and milestones.
	Impact Indicator 2	Baseline	Milestone (end 2013)	Target (2015)
	Improvements in citizens’ access to, use of and satisfaction with basic services	See Programme Logframe for baseline and milestones.
	Impact Indicator 3	Baseline (August 2010)	Milestone (end 2013)	Target (2015)
	Improvements in Citizens perceptions of State Government performance	See Programme Logframe for baseline and milestones.

PURPOSE	Outcome Indicator 1	Baseline (2011)		Milestone (2013)				Target (2015)			Assumptions
The efficiency and effectiveness of selected state level governments’ use of public resources is enhanced	Effectiveness of policies and strategies and consistency of Medium-Term Plans and Budgets with policies and resource envelopes.	Health sector plan exists but of poor quality; Some Community Development Plans have been developed, but there is no State Plan.		A process for preparing a State Development Plan has been agreed.				(a) Draft State Development Plan prepared, ready for ExCo approval, and (b) In the Health sector, the MTSS/Sector Plan is realistic and reflected in the 2015-2017 budget.			Political will to sustain the reform agenda is maintained beyond the lifetime of SPARC / State governments continue to prioritise the MDGs in the allocation and use of public resources / Levels and fluctuations in oil revenues do not unduly undermine fiscal stability / SAVI achieves sustainable improvements in State Government inclusivity and responsiveness to citizens’ rights and demands / Sectoral SLPs achieve sustainable improvements in sector performance / .
		Source
		(a) State Development Plan action plan, (b) State Development Plan, (c) Health Sector Plan, and (d) SPARC Evaluation Reviews.
	Outcome Indicator 2	Baseline (2011)		Milestone (2013)				Target (2015)
	Realism and predictability of multi-year capital and recurrent budgets.	Actual expenditure deviated from budgeted expenditure by 26%, 33% and 25% between 2006 and 2008 respectively. The budget is not prepared in a multiyear fiscal framework and no forward aggregates are prepared. Whilst the PFM system exercises tight controls during budget execution. Forward estimates of cash flow are not prepared. MDAs do not receive information on availability of funds for budget execution.		(a) Expenditure budget variance is below 25%, and (b) The Budget Call Circular is used to guide 2014-2016 budget preparation.				(a) Expenditure Budget variance is below 20%, (b) A Budget Policy Statement is used to guide the annual budget process, and (c) Annual cash forecasts prepared by Treasury are used as the basis for cash management and disbursement in the Health sector.
		Source
		(a) PEFA reports, (b) Budget Call Circular, (c) Revenue forecasting model forecasts, (d) Sector spending ceilings, (e) SDP, (f) Annual SG budgets, (g) Annual Accounts/ Financial Statements, and (h) PFM factsheets.
	Outcome Indicator 3	Baseline (2011)		Milestone (2013)				Target (2015)
	Effectiveness of core MDA support for government planning, finance and human resources performance management and service delivery mechanisms.	Although the state government is relatively lean and mandates are relatively clear, there is no formal process by which the structure is documented or regularly reviewed. MoFBEP structures and processes require strengthening to support improved planning and financial management. Apart from civil service rules and laws, Katsina's HRM policies are not comprehensive and not up-to-date. There is no systematic process of establishment or workforce planning.		(a) A corporate improvement plan is being used to guide reorganisation in MoFBEP, (b) A Health sector G&SI sensitive HRM improvement plan has been developed, and (c) A strategy for government-wide establishment and workforce planning has been developed.				(a) The MoFBEP corporate improvement plan has been implemented, and implementation is underway in at least one health sector MDA, (b) the HRM improvement plan is being implemented in the Health sector, and (c) Establishment and workforce plans are being implemented in MoFBEP and workforce plans are being used in the Health sector.
		Source
		(a) MoFBEP corporate improvement plan reports, (b) Health sector HRM policy and HRM reform implementation reports, (c) proposed establishment and workforce planning approach, (d) service charters and service review reports, and (e) Health sector MDA corporate improvement plan reports.
	Outcome Indicator 4	Baseline (2011)		Milestone (2013)				Target (2015)
	% of PEFA/SEAT Dimensions improving by at least one rating.	See 2011 SEAT/PEFA		N/A				15%
		Source
		State Government PEFA/SEAT Self Assessments, validated by external M&E Contractor.
INPUTS (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID SHARE (%)
	DFID to complete	DFID to Complete
INPUTS (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 1	Output Indicator 1.1	Baseline (2011)		Milestone (2013)				Target (2015)			Assumptions
Policy and strategy development, monitoring and evaluation improved.	Extent to which policy and strategy making processes meet good practice standards.	MoFBEP provides limited support to MDAs in form of budget call circulars and information on some state and federal policies.		(a) Guidance for preparing MTSS, alongside definition of sector MTSS support roles (mandates) within MoFBEP, has been localised, (b) this is used to guide Health sector plan improvement, and (c) the policy guide is localised and ways of using this to build CDCs into a state development plan have been considered.				(a) MoFBEP provides sustained and improved support for preparing and reviewing/adjusting sector plans in Health and other selected sectors, (b) sector planning process in Health exhibits use of a greater number of process standards than before, and (c) a decision is made to proceed with development of a State Development Plan.			Citizens’ ability to claim rights and hold government accountable increased. / Civil society and State and Federal Government are, and remain, committed to the MDGs. / Changes in political leadership do not undermine State Government support for agreed SPARC intervention plan. / Changes in senior positions (e.g. HoS, Commissioners) do not undermine State Government support for key initiatives (e.g. Corporate Planning, State Development Plans, and MTSS). / State Government is committed to implementing institutional change actions supported under the SPARC intervention plan. / Constitutional reform do not have negative effects on inter-government relations. / HIV/AIDS, malaria and TB incidence do not prevent improvements in efficient and effective use of funds.
		Source
		(a) SEAT Reports, (b) SG MTSS guidelines, (c) MoFBEP Corporate Improvement Plans, and (d) MoFBEP quarterly work plan progress reports.
	Output Indicator 1.2	Baseline (2011)		Milestone (2013)				Target (2015)
	Quality and comprehensiveness of policies and strategies.	There is no particular document acknowledged as the development agenda of the state. Some MDAs have developed sectoral plans including the Strategic Health Development Plan, but there is no MTSS in the state.		Sector Plan in Health demonstrates better standards against the guide, than in the current health sector plan.				(a) Health Sector Plan is financially feasible (consistent with 2015-2017 fiscal projections), and exhibits improved content standards over earlier version, and (b) some CDCs have been developed into the basis for a State Development Plan.
		Source
		(a) SEAT Reports, (b) Framework for State Development Plan, (c) Health Sector Performance Review Reports, (d) Health MTSS, and (f) Fiscal Projections.
Impact Weighting	Output Indicator 1.3	Baseline (2011)		Milestone (2013)				Target (2015)
25%	Extent to which results frameworks are comprehensive and measured.	Some MDAs like Health and Education conduct surveys and have integrated M&E as part of their planning process. However, there is no deliberate framework for data management and institutionalisation of M&E across MDAs and at state level		The Community Development Committee (CDC) reports and Health Sector Plan include results frameworks with relevant KPIs.				Results frameworks in the Community Development Committee (CDC) reports and Health Sector Plan include both targets and actual values for all KPIs.
		Source
		(a) SEAT Reports, (b) Health MTSS, and (c) Health Sector Performance Reports.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)			DFID Share (%)		Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 2	Output Indicator 2.1	Baseline (2011)		Milestone (2013)			Target (2015)			Assumptions
State public financial management improved.	Extent to which the budget is credible and policy based.	The budget preparation process uses flexible rather than fixed budget calendars. There is little political guidance during budget preparation, the budget is not prepared in a multiyear fiscal framework .No forward aggregates are prepared and there are no sector strategies.		(a) A fixed budget calendar is used to guide the 2014-2016 budget process, and (b) The Budget Call Circular includes sector ceilings and is used to guide 2014-2016 budget preparation using realistic revenue forecasts.			A detailed Budget Policy Statement is used to guide: (a) drafting of annual call circulars which include accurate and justified aggregate and sector ceilings, and (b) determining, costing and including capital/development projects into the budget process.			As above.
		Source
		(a) PEFA Reports, (b) Budget calendar, (c) Budget Call Circular, (d) Revenue forecasting model forecasts, (e) Sector spending ceilings, (f) Budget policy statement, and (g) Annual SG budgets.
	Output Indicator 2.2	Baseline (2011)		Milestone (2013)			Target (2015)
	Extent to which the budget is comprehensive and transparent.	Within the BC&COA there is no relationship between current and capital codes; the current code tracks the personnel and overhead spending for all, but cannot track their capital spending. The current BC&COA does not comply with international standards (COFOG and GFS). Budget documentation presented to the Legislature includes only one of the listed nine items identified in the PEFA assessment PI 6 – current year’s budget outturn.		(a) Proposals made to MoFBEP for revised Budget Classification and Chart of Accounts, and (b) Annual budget documentation better meets PEFA standards.			(a) Revised BC&COA is consistent with international best practice and standards, including GFS compliance, and (b) Annual budget documentation better meets PEFA standards.
		Source
		(a) PEFA Reports, (b) MoFBEP Guidance document on revision of BC&COA, (c) Budget Classification and Chart of Accounts, (d) Annual SG budgets, and (e) Budget performance reports.
	Output Indicator 2.3	Baseline (2011)		Milestone (2013)			Target (2015)
	Level of predictability and control in budget execution.	The PFM system exercises tight controls during budget execution. Forward estimates of cash flow are not prepared. MDAs do not receive information on expenditure commitment ceilings. The project approval and payment authorization process entails frequent budget adjustments not involving MDAs. The controls are through a process of obligatory top executive authorization for capital and overhead expenditures already approved in the budget. MDAs including Health have little control over decisions on what projects to implement or information on availability of funds for budget execution.		(a) A simple cash forecasting model is developed, and (b) Health Sector has the capacity to profile Health Sector budgets.			(a) A basic cash forecasting model is being operated within the Treasury, and (b) Annual budgets for Health sector MDAs are profiled.
		Source
		(a) PEFA Reports, (b) Annual SG budgets, (c) Cash forecasting model forecasts, and (d) profiled budgets.
	Output Indicator 2.4	Baseline (2011)		Milestone (2013)			Target (2015)
	Quality of accounting, recording and reporting.	No in year budget monitoring reports are produced.		Proposed formats for budget monitoring and reporting are presented.			Improved budget performance reports are produced.
		Source
		(a) Budget monitoring report formats, and (b) budget monitoring reports.
Impact Weighting	Output Indicator 2.5	Baseline (2011)		Milestone (2013)			Target (2015)
50%	Extent and quality of external scrutiny and audit.	Limited time is devoted to the review and scrutiny of budget proposal by the legislature before approval. Audit comprises manly transactions level checking; very little systems audit is in place. The Legislature does not hold public hearings or issue recommendations on audit findings.		An enlightenment programme is designed for SHOA including key PFM principles and the scrutiny of budget proposals and statutory reports.			Enlightenment programmes delivered in conjunction with SAVI and extended to Civil Society and the media.
		Source
		(a) State Auditor-General's Reports, (b) SHoA and Public Accounts Committee Meeting minutes, (c) SAVI/civil society groups PFM knowledge survey, and (d) Technical papers/reports on engagement with SAVI/civil society groups on PFM.
Inputs (£)	DFID (£)	Govt (£)	Other (£)		Total (£)				DFID Share (%)	Risk Rating
	DFID to complete	DFID to Complete								High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 3	Output Indicator 3.1	Baseline (2011)			Milestone (2013)			Target (2015)			Assumptions
State civil service performance improved.	Clarity and appropriateness of public service organisation and operational management.	The macro-structure of the State government is relatively lean. As a result of this lean structure, Katsina State Government appears to suffer from less confusion and duplication of mandates. However, there is no formal process by which the structure is documented, or regularly reviewed. MoFBEP structures and processes require strengthening.			MoFBEP Corporate Improvement Plan developed.			Corporate Improvement Plan developed for at least one Health Sector MDA.			As above.
		Source
		(a) SEAT Reports, (b) MoFBEP and Health MDA Corporate Improvement Plans, and (c ) MoFBEP and Health sector quarterly work plan progress reports.
	Output Indicator 3.2	Baseline (2011)			Milestone (2013)			Target (2015)
	Extent to which HRM policies and organisation are in place.	The Federal civil service rules, laws and guidelines on HRM have been translated into Katsina’s own guidelines. Although HRM policies exist, they are not comprehensive and not up to date.			Revised G&SI-sensitive Health HRM Policy developed and used to define HRM structures and functions in the sector.			HRM policies agreed and improvements to HRM functions and structures across Government have begun.
		Source
		(a) SEAT Reports, (b) Health HRM Policy and Implementation Plan, and (c) Health sector quarterly work plan progress reports.
Impact Weighting	Output Indicator 3.3	Baseline (2011)			Milestone (2013)			Target (2015)
25%	Extent to which establishment planning and workforce planning, management and development is in place.	Although Katsina SG has periodically addressed workforce issues, there is no systematic process of establishment or workforce planning in place.			G&SI-sensitive establishment and workforce planning strategy developed.			(a) An establishment and workforce planning process is being used within MoFBEP, and (b) A workforce planning process is being used in the Health Sector (including recruitment, retention, deployment processes).
		Source
		(a) SEAT Reports, (b) MoFBEP reports, (c) Workforce Planning reports, and (d) Health sector quarterly work plan progress reports.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID Share (%)	Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

PROJECT NAME	State Partnership for Accountability, Responsiveness and Capability (SPARC), Nigeria (2008 – 2015)
STATE	Lagos (Type A Approach)

GOAL	Impact Indicator 1	Baseline	Milestone (end 2013)	Target (2015)
Nigeria’s own resources used efficiently and effectively to achieve MDGs	Improvements in progress towards MDGs	See Programme Logframe for baseline and milestones.
	Impact Indicator 2	Baseline	Milestone (end 2013)	Target (2015)
	Improvements in citizens’ access to, use of and satisfaction with basic services	See Programme Logframe for baseline and milestones.
	Impact Indicator 3	Baseline (August 2010)	Milestone (end 2013)	Target (2015)
	Improvements in Citizens perceptions of State Government performance	See Programme Logframe for baseline and milestones.

PURPOSE	Outcome Indicator 1	Baseline (2011)		Milestone (2013)				Target (2015)			Assumptions
The efficiency and effectiveness of selected state level governments’ use of public resources is enhanced	Effectiveness of policies and strategies and consistency of Medium-Term Plans and Budgets with policies and resource envelopes.	No SDP since LA-SEEDS. Some draft MTSSs exist but have not been used at budgeting stage.		The SDP and MTSSs of priority sectors are adequately reflected in the 2014-2016 budget.				The SDP and MTSSs/sector plans of at least 75% of sectors are adequately reflected in the 2015-2017 budget.			Political will to sustain the reform agenda is maintained beyond the lifetime of SPARC / State governments continue to prioritise the MDGs in the allocation and use of public resources / Levels and fluctuations in oil revenues do not unduly undermine fiscal stability / SAVI achieves sustainable improvements in State Government inclusivity and responsiveness to citizens’ rights and demands / Sectoral SLPs achieve sustainable improvements in sector performance / .
		Source
		(a) Lagos State Development Plan, (b) MTSSs, (c) State Budgets, and (d) SPARC Evaluation Reviews.
	Outcome Indicator 2	Baseline (2011)		Milestone (2013)				Target (2015)
	Realism and predictability of multi-year capital and recurrent budgets.	The expenditure budget deviations (in absolute terms) were 34.9%, 24.5%, and 11.1% in 2008, 2009, and 2010 respectively. Medium term fiscal forecasts guide budget ceiling setting, within which MDA (rather than sector) strategies are prepared. Expenditure approval procedures are not consistently followed or based on realistic cash forecasting, resulting in payment arrears. Rudimentary cash forecasting is in place and new tools including budget profiling, capital projects work planning and Treasury Single Account are being introduced.		(a) Variance between 2014-2016 budget and medium-term revenue forecasts as set out in the Budget Policy Statement is less than 15%, (b) Expenditure budget variance is below 15%, and (c) Annual cash forecasts prepared by the STO are used as the basis for cash management and disbursement in priority sectors.				(a) Variance between 2015-2017 budget and medium-term revenue forecasts is less than 10%, (b) Expenditure budget variance is below 15%, (c) The Treasury Single Account (TSA) is operationalised, and (d) Quarterly cash forecasts prepared by the STO are used as the basis for cash management and disbursement in priority sectors.
		Source
		(a) PEFA reports, (b) Budget Call Circular, (c) Revenue forecasting model forecasts, (d) Sector spending ceilings, (e) SDP, (f) Annual SG budgets, (g) Annual Accounts/ Financial Statements, and (h) PFM factsheets.
	Outcome Indicator 3	Baseline (2011)		Milestone (2013)				Target (2015)
	Effectiveness of core MDA support for government planning, finance and human resources performance management and service delivery mechanisms.	Although mandates have been compiled and reviewed in 2011, role clarification is still to be implemented between the central HRM/HRD MDAs. An HRM policy portfolio has been accepted in principle and an HRM transition plan , including piloting improved HRM processes, is in place. There is no formal government-wide establishment planning or workforce planning, and this is now a government priority. A Service Charter policy has been in place since 2010 and a first phase of rollout is now underway. HE Governor and EXCO are introducing a first phase of Performance Agreements.		(a) Agreed procedures and responsibilities for routine review of mandates are being implemented, (b) Reorganisation is underway in the three central HRM Ministries, (c) A modern G&SI sensitive HRM Policy and improvement Strategy have been agreed (including proposals for establishing HRM cadre), (d) a G&SI sensitive workforce planning Policy and Strategy have been agreed, and (e) G&SI sensitive Service Standards and performance against Performance Agreements for pilot MDAs have been published.				(a) Mandate compendium has been updated, (b) Reorganisation has been completed in the three central HRM Ministries and is underway across all MDAs (supported by OoT), (c) Selected HRM processes (including posting of partially qualified staff into HRM units of at least 25% of MDAs) have been reformed in line with the State HRM Policy, (d) Establishment and workforce plans are being implemented in priority central MDAs, and (e) Performance against Service Standards for pilot MDAs has been published.
		Source
		(a) Mandate review reports, (b) corporate planning implementation reports, (c) HRM reorganisation reports, (d) performance management reports, and (e) workforce analysis reports.
	Outcome Indicator 4	Baseline (2011)		Milestone (2013)				Target (2015)
	% of PEFA/SEAT Dimensions improving by at least one rating.	See 2011 SEAT/PEFA		N/A				25%
		Source
		State Government PEFA/SEAT Self Assessments, validated by external M&E Contractor.
INPUTS (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID SHARE (%)
	DFID to complete	DFID to Complete
INPUTS (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 1	Output Indicator 1.1	Baseline (2011)		Milestone (2013)				Target (2015)			Assumptions
Policy and strategy development, monitoring and evaluation improved.	Extent to which policy and strategy making processes meet good practice standards.	MEPB support to MDAs primarily limited to procedural and technical guidance in preparing MTSS and annual budgets. Although there is an appetite for policy making and development of a Lagos State Plan at the political level, there is negligible support provided for this process by the MEPB. Nor is it clear to what extent politicians understand their role in policy making and its place in the business of government.		(a) Provision to all MDAs by MEPB of appropriate tools (e.g. guidelines) related to policy, strategy and M&E, (b) At least two good standard processes are being used in Policy making (see Policy Making guide for process standards), (c) At least three good standard processes in sector strategy are in use in the majority of the sectors adopting MTSS, and (d) process for consolidating Ministry strategies into MTSSs agreed and implementation begun				(a) Policy and strategy advice is being provided to ExCo (and via SAVI to the SHoA) based on sound analysis which incorporates the views of appropriate stakeholders, (b) At least 3 good standard processes being used in policy making, and (c) At least five good standard processes in sector strategy making being used in the majority of sectors adopting MTSS.			Citizens’ ability to claim rights and hold government accountable increased. / Civil society and State and Federal Government are, and remain, committed to the MDGs. / Changes in political leadership do not undermine State Government support for State Development Plan governance reforms. / Changes in senior positions (e.g. HoS, Commissioners) do not undermine State Government support for key initiatives (e.g. Corporate Planning, State Development Plans, and MTSS). / State Government is committed to implementing institutional change actions detailed in the State Development Plan. / Constitutional reform do not have negative effects on inter-government relations. / HIV/AIDS, malaria and TB incidence do not prevent improvements in efficient and effective use of funds.
		Source
		(a) LASG MTSS Guide, (b) MEPB Corporate Plans, (c) MEPB quarterly work plan progress reports, (d) Minutes of MEPB Strategic Management Meetings/Retreats, (e) SEATs, and (f) Policy document (LSDP) and sector strategy documents.
	Output Indicator 1.2	Baseline (2011)		Milestone (2013)				Target (2015)
	Quality and comprehensiveness of policies and strategies.	MEPB support to MDAs primarily limited to procedural and technical guidance in preparing MTSS and annual budgets. Although there is an appetite for policy making and development of a Lagos State Plan at the political level, there is negligible support provided for this process by the MEPB. Nor is it clear to what extent politicians understand their role in policy making and its place in the business of government.		(a) New State Development Plan agreed and meets 30 percent of good quality content standards including demonstration of general fiscal realism and G&SI content, (b) Ten sector strategies agreed which meet 30 percent of content quality standards				(a) Consolidated MTSSs consistent with SDP goals and objectives and incorporate gender and social inclusion measures, (b) State Development Plan improved and meets 50 percent of good content quality standards, and (c) Ten sector strategies now meet 50 percent of content quality standards.
		Source
		(a) Sector Performance Review Reports, (b) Sector MTSS, (c) SDP, and (d) Fiscal Projections Models.
	Output Indicator 1.3	Baseline (2011)		Milestone (2013)				Target (2015)
	Extent to which results frameworks are comprehensive and measured.	Data management centre established and equipped. Developing MIS to provide routine data for policy and planning.		KPI MIS in place within MEPB, incorporating SDP KPIs and the data required to measure them.				(a) KPI MIS producing performance reports against SDP KPIs and being used to prepare policy/strategy analysis for priority sectors, and (b) M&E scorecards prepared by priority MTSS sectors.
		Source
		(a) State KPI database management reports and statistics, (b) SDP, (c) Sector MTSS, and (d) Policy Briefs and Reviews.
Impact Weighting	Output Indicator 1.4	Baseline (2011)		Milestone (2013)				Target (2015)
25%	Extent to which performance management processes are being used.	Performance Management processes, including reporting, currently piloted in Health, Education and Environment.		MEPB have the capacity to support sectors in implementing annual sector performance reviews which incorporate a G&SI focus.				(a) MEPB conducts SDP annual performance review, in line with the SDP M&E framework, which incorporates a G&SI focus, and (b) MTSS annual performance reviews in priority sectors better meet performance review standards.
		Source
		(a) SEAT Reports, (b) Corporate Planning progress reports, (c) Annual SDP and Sector Performance Review Reports, and (d) SDP and MTSSs.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)			DFID Share (%)		Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 2	Output Indicator 2.1	Baseline (2011)	Milestone (2013)	Target (2015)	Assumptions
State public financial management improved.	Extent to which the budget is credible and policy based.	The cabinet provides guidance before issuing of the budget call circular however budget approval is not consistent with the budget calendar; Medium term fiscal forecasts guide budget ceilings; MDA rather than sector strategies exist, and are not properly costed - capital and current budgets remain separate activities with no link.	(a) Budgets prepared in adherence to an agreed budget call circular, and (b) The Budget Policy Statement contains revenue envelopes which are consistent with the revenue model.	(a) Approved 2015-2017 budget is consistent with the goals and objectives of priority MTSS sectors, within realistic sector spending ceilings, and (b) Recurrent expenditure implications are clearly linked to capital projects within MTSSs.	As above.
		Source
		(a) Budget calendar, (b) Budget Call Circular, (c) Revenue forecasting model forecasts, (d) Budget Policy Statement, (e) Sector spending ceilings, (f) Budget policy statement, and (g) Annual SG budgets.
	Output Indicator 2.2	Baseline (2011)	Milestone (2013)	Target (2015)
	Extent to which the budget is comprehensive and transparent.	Support has been provided to revise and update the Budget Classification and Chart of Accounts (BC&COA). The Oracle system will be updated to incorporate the revised BC&COA, and the new system will be rolled out for the 2013 budget preparation and subsequent budget execution. The transparency of intergovernmental fiscal relationship achieves poor PEFA scores as Lagos State Government does not provide Local Governments (LGs) and Local Council Development Areas (LCDAs) with advance information on expected annual budgetary allocations.	(a)The STO has the capacity to introduce and support the revised BC&COA, and (b) a process for the publication of budget allocations to LGs/ LCDAs prepared.	(a) Revised BC&COA is adopted, and (b) State and LGs/ LCDAs publish what they receive annually.
		Source
		(a) Minutes of JAAC meetings, (b) Budget Call Circular, and (c) Minutes of Ministerial Budget Session with MEPB.
	Output Indicator 2.3	Baseline (2011)	Milestone (2013)	Target (2015)
	Level of predictability and control in budget execution.	Lagos state use rudimentary cash forecasting. MDAs do not receive information on resources available for commitment. MDAs have commenced budget profiling and a Capital Projects work plan is being developed to record quarterly expenditure requirements for capital projects. Expenditure approval procedures are not consistently followed or based on realistic cash forecasting, resulting in payment arrears. Support has been provided to design and implement a Treasury Single Account (TSA) system. A comprehensive internal revenue assessment is planned to determine potential revenue sources. The internal audit function is not sufficiently professional and an assessment of the CIAD is planned to determine the degree to which the Agency has been able to meet its mission and mandate. Support has been provided to implementing Procurement legislation and strengthening procurement systems and institutions.	(a) A simple cash forecasting model is developed and piloted using sample cash flow data, (b) a strategy for improving IGR has been prepared, (c) an action plan to implement recommendations from the CIAD assessment has been prepared, and (d) Procurement staff trained and procurement decentralisation action plan prepared.	(a) The Treasury Single Account (TSA) procedures are being implemented according to an agreed plan, (b) the cash forecasting model is being used in the STO, (c) Implementation of the IGR improvement strategy has commenced, and (d) implementation of recommendations from the CIAD assessment has commenced.
		Source
		(a) Cash forecasting model, (b) Work Plan for TSA, (c) Relevant SG (e.g. SSC or EXCO) Minutes of meeting, (d) Quarterly budget performance reports by MEPB, (e) cash forecasting model, (f) Capital Work plan database, (g) IGR strategy, (h) CIAD Assessment Report and Implementation Plan, (i) procurement training plan, and (j) procurement decentralisation action plan.
	Output Indicator 2.4	Baseline (2011)	Milestone (2013)	Target (2015)
	Quality of accounting, recording and reporting.	Support has been provided for scoping and designing a Treasury Single Account (TSA) system which will involve changes in bank accounting and reconciliation procedures. In year budget reports captures only releases to MDA; quarterly reports issued within month following end of quarter; data quality issues arise from difference between fund releases, payments, and actual expenditure commitment.	(a) Procedures for bank reconciliation within the Treasury Single Account (TSA) framework are documented and piloted, and (b) improvements for budget performance reporting formats (actual + commitments against budget) prepared.	(a) Procedures for bank reconciliation within the TSA framework are operating, and (b) improved budget performance reports are produced.
		Source
		(a) MEPB Quarterly Budget Reports (b) Published Accounts (c) Oracle reports (d) TSA procedures

Impact Weighting	Output Indicator 2.5	Baseline (2011)		Milestone (2013)				Target (2015)
50%	Extent and quality of external scrutiny and audit.	Public hearings by SHOA are not held on the SAG's Annual Audit Report. There is no procedure for responding to, and monitoring audit recommendations. OSAG has limited capacity and expertise in modern audit techniques.		(a) PAC/ SHoA has the capacity to scrutinise and follow up on Annual Audit Reports, and (b) OASG has the capacity to use improved procedures and techniques.				A procedure for monitoring implementation of agreed Audit report recommendations is in place.
		Source
		(a) State Auditor-General's Reports, (b) Legislative Public Accounts Committee Meeting minutes, and (c) OSAG Auditing Manuals.
Inputs (£)	DFID (£)	Govt (£)	Other (£)		Total (£)				DFID Share (%)	Risk Rating
	DFID to complete	DFID to Complete								High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 3	Output Indicator 3.1	Baseline (2011)			Milestone (2013)			Target (2015)			Assumptions
State civil service performance improved.	Clarity and appropriateness of public service organisation and operational management.	Most agencies and parastatals are backed by law or regulation. Mandates were captured, reported and reviewed by the Body of Permanent Secretaries in 2011; some minor adjustments were made and a compilation of MDA mandates produced but not widely disseminated. There are overlaps and lack of role/ function clarity between the 3 central ‘HRM&D’ MDAs. Operational management identified as a priority [at the SEAT]			(a) Restructuring plan developed for the 3 central HRM ministries, based on approved recommendations for rationalising/clarifying mandates, structure and functions, and (b) OoT plan for cyclical review of MDA mandates developed.			(a) The mandates, structure and functions of the 3 central HRM ministries reflect corporate plan recommendations, and (c) OoT have the capacity to support MDAs to prepare and implement corporate plans.			As above.
		Source
		(a) SEAT Reports, (b) Mandate review reports, (c) SG Gazette of Mandates, and (d) Central HRM corporate improvement plans.
	Output Indicator 3.2	Baseline (2011)			Milestone (2013)			Target (2015)
	Extent to which HRM policies and organisation are in place.	HRM transition plan and governance in place. HR policy portfolio accepted in principle. MDAs Pilot HRM.			(a) G&SI-sensitive HRM policies developed, (b) HRM unit structure agreed, and (c) HRM cadre proposal presented for EXCO decision.			(a) Process of realigning HRM systems with policy has started, and (b) HRM Units staffed by at least partly qualified HR staff in 4 priority MDAs.
		Source
		(a) State HRM structures and policies, (b) Minutes of meetings of HR Champions/Core Group, and (c) HOS/PSO Circular on HR Cadre.
	Output Indicator 3.3	Baseline (2011)			Milestone (2013)			Target (2015)
	Extent to which establishment planning and workforce planning, management and development is in place.	Workforce forecasting and planning do not exist and now seen as critical. A Training and Development policy is in draft awaiting ratification by EXCO. There is no succession planning, talent management, career development or concept of merit based progression in place. Grade drift is common and many posts do not have clear job descriptions.			(a) Training plan in operation, (b) strategy for workforce planning and audit agreed, and (c) skills and capability gaps and age/gender/diversity issues analysed.			(a) Establishment and workforce planning process agreed and being used in priority MDAs, (b) succession planning policy being used and (c) proposed HR cost savings plan presented to LSG.
		Source
		(a) Action Plan on establishment and workforce planning, (b) Capacity building plan for establishment and workforce planning, and (c) Report of HRM Pilots.
Impact Weighting	Output Indicator 3.4	Baseline (2011)			Milestone (2013)			Target (2015)
25%	Extent to which MDA performance management policies and procedures are in place.	Service Charter policy and guidance in place since 2010 and made operational in first phase of 6 CP MDAs and 6 nominated Agencies in July 2012. HE Governor and EXCO have agreed to phase1 Performance Agreements			(a) Service Delivery Units in MDAs in the first phase have the capacity to establish service standards including equity of access and support development of service improvement plans, and (b) Commissioners in the first phase have the capacity to review and report performance against performance agreements.			(a) Performance against service standards (including equity of access) is measured for pilot MDAs, and (b) Performance against performance agreements has been measured.
		Source
		(a) SEAT reports, (b) Service Charter policy and guidance, (c) Service Charter Implementation Committee TOR and action plan, and (d) Service Charters and Performance Agreements.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID Share (%)	Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

PROJECT NAME	State Partnership for Accountability, Responsiveness and Capability (SPARC), Nigeria (2008 – 2015)
STATE	Niger (Type C Approach)

Logframe to be developed during State programme inception over August-October 2012.

PROJECT NAME	State Partnership for Accountability, Responsiveness and Capability (SPARC), Nigeria (2008 – 2015)
STATE	Yobe (Type B Approach)

GOAL	Impact Indicator 1	Baseline	Milestone (end 2013)	Target (2015)
Nigeria’s own resources used efficiently and effectively to achieve MDGs	Improvements in progress towards MDGs	See Programme Logframe for baseline and milestones.
	Impact Indicator 2	Baseline	Milestone (end 2013)	Target (2015)
	Improvements in citizens’ access to, use of and satisfaction with basic services	See Programme Logframe for baseline and milestones.
	Impact Indicator 3	Baseline (August 2010)	Milestone (end 2013)	Target (2015)
	Improvements in Citizens perceptions of State Government performance	See Programme Logframe for baseline and milestones.

PURPOSE	Outcome Indicator 1	Baseline (2011)		Milestone (2013)				Target (2015)			Assumptions
The efficiency and effectiveness of selected state level governments’ use of public resources is enhanced	Effectiveness of policies and strategies and consistency of Medium-Term Plans and Budgets with policies and resource envelopes.	YOSERA 2 is the State Development Plan. Needs up dating and improving. Health sector strategy approved.		(a) A revised YOSERA has been approved and published, and (b) within the Health sector, MTSS goals and objectives are consistent with the SDP and can be linked to the 2014-2016 budget.				The YOSERA and MTSSs of two priority sectors are adequately reflected in the 2015-2017 budget.			Political will to sustain the reform agenda is maintained beyond the lifetime of SPARC / State governments continue to prioritise the MDGs in the allocation and use of public resources / Levels and fluctuations in oil revenues do not unduly undermine fiscal stability / SAVI achieves sustainable improvements in State Government inclusivity and responsiveness to citizens’ rights and demands / Sectoral SLPs achieve sustainable improvements in sector performance / .
		Source
		(a) YOSERA 3, (b) Health MTSS, (c) State Budgets, and (d) SPARC Evaluation Reviews.
	Outcome Indicator 2	Baseline (2011)		Milestone (2013)				Target (2015)
	Realism and predictability of multi-year capital and recurrent budgets.	Aggregate primary expenditure outturn deviated from the original primary budget by more than 43% and 38% in 2007 and 2008 respectively, but by only 5.1 percent in 2009. Medium term budget frameworks were used for 2010-13, and updated in 2011. Revenue forecasting tools have recently been adopted but are not yet fully institutionalised. Medium term frameworks and tools to determine aggregate spending limits and sector spending ceilings are not established. There is no forward-looking cash flow planning and monitoring. No reliable information is provided to MDAs on cash availability and cash releases are not predictable.		(a) Variance between 2014-2016 budget and medium-term revenue forecasts is less than 25%, and (b) Expenditure budget variance is below 25%.				(a) Variance between 2015-2017 budget and medium-term revenue forecasts is less than 20%, (b) Expenditure budget variance is below 20%, and (c) Annual cash forecasts prepared by Treasury are used as the basis for cash management and disbursement in priority sectors.
		Source
		(a) PEFA reports, (b) Budget Call Circular, (c) Revenue forecasting model forecasts, (d) Sector spending ceilings, (e) SDP, (f) Annual SG budgets, (g) Annual Accounts/ Financial Statements, and (h) PFM factsheets.
	Outcome Indicator 3	Baseline (2011)		Milestone (2013)				Target (2015)
	Effectiveness of core MDA support for government planning, finance and human resources performance management and service delivery mechanisms.	Although the organisational structure of government is fairly lean, some mandates overlap. MDAs do not have objectives which reflect mandates or sectoral strategies, and MDA functions, structures, processes and workforce are not aligned. Current HRM policies and procedures are limited to basic personnel administration, and lack of capacity in the workforce is a major issue. Health sector workforce audit has identified important gaps. The health sector human resource information system is partly established.		(a) Mandates have been documented across government, (b) Reorganisation plans agreed in at least one central MDA and two Health Sector MDAs in line with corporate planning recommendations, (c) A modern G&SI sensitive HRM Policy and improvement Action Plan have been agreed, (d) Workforce plans, taking into account G&SI issues, have been agreed in Health sector MDAs, and (e) Civil service Staff Audit is underway, including disaggregation by gender and other social factors.				(a) Mandates are being rationalised in line with recommendations to improve organisational effectiveness, (b) Selected HRM processes (including plans to create a unified personnel database) are being reformed in line with the State HRM Policy, and (c) The workforce plan is being implemented in Health sector MDAs.
		Source
		(a) Mandate and mandate rationalisation reports, (b) corporate planning implementation reports, (c) HRM improvement strategy and implementation reports, (d) unified personnel database reports, and (e) workforce audit and health service workforce planning reports.
	Outcome Indicator 4	Baseline (2011)		Milestone (2013)				Target (2015)
	% of PEFA/SEAT Dimensions improving by at least one rating.	See 2011 SEAT/PEFA		N/A				20%
		Source
		State Government PEFA/SEAT Self Assessments, validated by external M&E Contractor.
INPUTS (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID SHARE (%)
	DFID to complete	DFID to Complete
INPUTS (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 1	Output Indicator 1.1	Baseline (2011)		Milestone (2013)				Target (2015)			Assumptions
Policy and strategy development, monitoring and evaluation improved.	Extent to which policy and strategy making processes meet good practice standards.	MoBEP support to MDAs primarily limited to procedural and technical guidance in preparing annual budgets.		(a) Guidance for preparing MTSS, alongside definition of sector MTSS support roles within MoBEP, have been used to guide Health sector MTSS preparation, and (b) localised policy making guidelines developed and used to support production of YOSERA 3.				MoBEP demonstrates the capacity to support Health and other selected sectors in preparing and reviewing/adjusting MTSS, and the State in developing policy, as evidenced through growth in the number and standards of processes being used for sector and policy development.			Citizens’ ability to claim rights and hold government accountable increased. / Civil society and State and Federal Government are, and remain, committed to the MDGs. / Changes in political leadership do not undermine State Government support for agreed change plans. / Changes in senior positions (e.g. HoS, Commissioners) do not undermine State Government support for key initiatives (e.g. Corporate Planning, State Development Plans, and MTSS). / State Government is committed to implementing institutional change actions detailed in agreed change plans. / State Government is committed to mainstreaming governance reforms within the State Development Plan. / Constitutional reform do not have negative effects on inter-government relations. / HIV/AIDS, malaria and TB incidence do not prevent improvements in efficient and effective use of funds.
		Source
		(a) SEAT Reports, (b) SG MTSS guidelines, (c) MoBEP Corporate Improvement Plans, and (d) MoBEP quarterly work plan progress reports.
	Output Indicator 1.2	Baseline (2011)		Milestone (2013)				Target (2015)
	Quality and comprehensiveness of policies and strategies.	A Health Sector plan has been developed. Currently developing a comprehensive Strategic Sector Development Plan, as a basis for an MTSS. There is a State Development Plan called YOSERA 2, and the state says it wants to develop a YOSERA 3 and is seeking assistance.		(a) Revised YOSERA 3 completed which demonstrates improved content against the Policy Guide Standards as compared with YOSERA 2, and it is being used to guide Health MTSS development, and (b) Health first version MTSS developed and reflects some of the standards established in the localised MTSS Guide.				YOSERA 3 and Health MTSS: (a) better meet policy and strategy standards, and (b) at least one other first version MTSS developed.
		Source
		(a) SEAT Reports, (b) Health Sector Performance Review Reports, (c) Health MTSS, (d) YOSERA, and (e) Fiscal Projections.
Impact Weighting	Output Indicator 1.3	Baseline (2011)		Milestone (2013)				Target (2015)
25%	Extent to which results frameworks are comprehensive and measured.	Data management centre established but not equipped and with no clear objectives. General lack of reliable data except in some specific sectors.		YOSERA and Health MTSS include results frameworks with relevant KPIs.				Results frameworks in YOSERA and Health MTSS include both targets and actual values for all KPIs.
		Source
		(a) SEAT Reports, (b) YOSERA and Health MTSS, and (c) YOSERA and Health Sector Performance Reports.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)			DFID Share (%)		Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 2	Output Indicator 2.1	Baseline (2011)			Milestone (2013)			Target (2015)			Assumptions
State public financial management improved.	Extent to which the budget is credible and policy based.	The budget calendar is flexible and dates are not respected. The state commenced the use of medium term budget frameworks for 2010-13, and updated these in 2011. Revenue forecasting tools have recently been adopted through SPARC support but are not yet fully institutionalised. Medium term frameworks and tools to determine aggregate spending limits and sector spending ceilings are not established.			(a) A budget calendar is used to guide the 2014-2016 budget process, and (b) The Budget Call Circular contains sector budget allocations derived from a realistic Revenue Model.			A Budget Policy Statement is used to guide: (a) drafting of annual call circulars which include accurate and justified aggregate and sector ceilings, and (b) determining, costing and including capital/development projects into the budget process.			As above.
		Source
		(a) PEFA Reports, (b) Budget calendar, (c) Budget Call Circular, (d) Revenue forecasting model forecasts, (e) Sector spending ceilings, (f) Budget policy statement, and (g) Annual SG budgets.
	Output Indicator 2.2	Baseline (2011)			Milestone (2013)			Target (2015)
	Extent to which the budget is comprehensive and transparent.	Information included in budget documentation is not comprehensive. Only one (budget format presentation) of the nine elements prescribed by PEFA are included in the budget documentation.			Annual budget documentation better meets PEFA standards.			Annual budget documentation better meets PEFA standards.
		Source
		(a) PEFA Reports, and (b) budget documentation.
	Output Indicator 2.3	Baseline (2011)			Milestone (2013)			Target (2015)
	Level of predictability and control in budget execution.	There is no forward-looking cash flow planning and monitoring; no reliable information is provided to MDAs on actual availability. Cash releases to the health sector are not predictable. Health sector plans do not appear to be costed or profiled.			(a) A simple cash forecasting model is developed, and (b) Health Sector has the capacity to profile Health Sector budgets.			(a) Annual budgets for Health sector MDAs are profiled, and (b) A basic cash forecasting model is being operated within the Treasury.
		Source
		(a) PEFA Reports, (b) Annual SG budgets, and (c) Cash forecasting model forecasts.
	Output Indicator 2.4	Baseline (2011)			Milestone (2013)			Target (2015)
	Quality of accounting, recording and reporting.	In-year reports compare estimates to actual along main administrative headings, but it is not clear whether ‘actual’ represents releases, payments, or commitments.			Improvements for budget performance reporting formats (actual + commitments against budget) prepared.			Improved budget performance reports are produced.
		Source
		(a) Budget monitoring report formats, and (b) budget monitoring reports.
Impact Weighting	Output Indicator 2.5	Baseline (2011)			Milestone (2013)			Target (2015)
50%	Extent and quality of external scrutiny and audit.	The House scrutinizes detailed revenue and expenditure proposals, but not underlying fiscal policy or framework. Evidence suggests no legislature hearings take place to examine audit reports and no recommendations issued.			An enlightenment programme is designed for SHOA including key PFM principles and the scrutiny of budget proposals and statutory reports.			Enlightenment programmes delivered in conjunction with SAVI and extended to Civil Society and the media.
		Source
		(a) State Auditor-General's Reports, (b) SHoA and Public Accounts Committee Meeting minutes, (c) SAVI/civil society groups PFM knowledge survey, and (d) Technical papers/reports on engagement with SAVI/civil society groups on PFM.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID Share (%)	Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 3	Output Indicator 3.1	Baseline (2011)			Milestone (2013)			Target (2015)			Assumptions
State civil service performance improved.	Clarity and appropriateness of public service organisation and operational management.	Organisational structure is stable and fairly lean. Some mandates overlap. MDAs do not have objectives which reflect mandates and sectoral strategies. MDA functions structures, processes and workforce are not aligned. Ministry of Health has been partly restructured, and PHCMB created.			(a) Critical mandates documented across Government, and (b) Corporate planning process underway in at least one central MDA and two key health sector MDAs.			(a) Documented mandates have been accepted, (b) process for rationalising mandates agreed and implementation started, and (c) reorganisation underway in at least one central and one Health MDA.			As above.
		Source
		(a) Mandate review reports, (b) Mandates reference document, (c) Central and Health sector corporate improvement plans, and (c) Central and Health sector quarterly work plan progress reports.
	Output Indicator 3.2	Baseline (2011)			Milestone (2013)			Target (2015)
	Extent to which HRM policies and organisation are in place.	Current HRM and HRD policies and systems are limited to basic personnel administration. The basic essentials for workforce planning are not yet in place. Lack of capacity in the workforce is a major issue.			(a) State-wide G&SI-sensitive HRM strategy for improving HRM processes has been prepared, and (b) gender-disaggregated personnel records data sources identified and action plan for consolidation prepared.			(a) Unified personnel database has been developed and an implementation plan agreed, and (b) HRM improvement strategy is being used to reform selected HRM processes.
		Source
		(a) SEAT Reports, (b) HRM and HRD Policies and Implementation Plans, and (c) Relevant MDA quarterly work plan progress reports.
Impact Weighting	Output Indicator 3.3	Baseline (2011)			Milestone (2013)			Target (2015)
25%	Extent to which establishment planning and workforce planning, management and development is in place.	Health sector workforce audit has identified important gaps in the workforce. HRIS is partly established, and HR Forum for Health has been created.			(a) Process for updating civil service staff audit has started, and (b) workforce planning approach for the Health sector agreed, incorporating a G&SI focus.			Agreed workforce planning process being used in the Health sector, incorporating succession planning and human resources development.
		Source
		(a) SEAT Reports, and (b) Health sector quarterly work plan progress reports.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID Share (%)	Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

PROJECT NAME	State Partnership for Accountability, Responsiveness and Capability (SPARC), Nigeria (2008 – 2015)
STATE	Zamfara (Type C Approach)

GOAL	Impact Indicator 1	Baseline	Milestone (end 2013)	Target (2015)
Nigeria’s own resources used efficiently and effectively to achieve MDGs	Improvements in progress towards MDGs	See Programme Logframe for baseline and milestones.
	Impact Indicator 2	Baseline	Milestone (end 2013)	Target (2015)
	Improvements in citizens’ access to, use of and satisfaction with basic services	See Programme Logframe for baseline and milestones.
	Impact Indicator 3	Baseline (August 2010)	Milestone (end 2013)	Target (2015)
	Improvements in Citizens perceptions of State Government performance	See Programme Logframe for baseline and milestones.

PURPOSE	Outcome Indicator 1	Baseline (2011)		Milestone (2013)				Target (2015)			Assumptions
The efficiency and effectiveness of selected state level governments’ use of public resources is enhanced	Effectiveness of policies and strategies and consistency of Medium-Term Plans and Budgets with policies and resource envelopes.	2020 vision is the only plan document, and it is insufficiently developed to constitute the basis of a plan. Sector plan for health not wholly consistent with envelopes, though it is partially reflected in the budget.		A process for preparing a State Development Plan has been agreed.				(a) Draft State Development Plan prepared, ready for ExCo approval, and (b) In the Health sector, the MTSS/Sector Plan is realistic and reflected in the 2015-2017 budget.			Political will to sustain the reform agenda is maintained beyond the lifetime of SPARC / State governments continue to prioritise the MDGs in the allocation and use of public resources / Levels and fluctuations in oil revenues do not unduly undermine fiscal stability / SAVI achieves sustainable improvements in State Government inclusivity and responsiveness to citizens’ rights and demands / Sectoral SLPs achieve sustainable improvements in sector performance / .
		Source
		(a) State Development Plan, (b) Health sector plan, (c) State budgets, and (d) SPARC Evaluation Reviews.
	Outcome Indicator 2	Baseline (2011)		Milestone (2013)				Target (2015)
	Realism and predictability of multi-year capital and recurrent budgets.	Expenditure deviations from the budget 2008-10 were 43%, 44% and 37% respectively. Over the PEFA assessment period (2008-10) there were consistent over forecasts of revenue and under estimates of IGR resulting in unrealistic budgets being set. The annual budget represents the only Unrealistic) cash forecast, and it is not converted to a quarterly or monthly cash plan. No reliable information is provided to MDAs or the Governor’s Office on the availability of cash for commitment of expenditure. Funds for execution are determined largely by central cash rationing rather than budget allocations.		(a) Expenditure budget variance is below 35%, and (b) The Budget Call Circular is used to guide 2014-2016 budget preparation.				(a) Expenditure Budget variance is below 25%, (b) A Budget Policy Statement is used to guide the annual budget process, and (c) Annual cash forecasts prepared by Treasury are used as the basis for cash management and disbursement in the Health sector.
		Source
		(a) PEFA reports, (b) Budget Call Circular, (c) Revenue forecasting model forecasts, (d) Sector spending ceilings, (e) SDP, (f) Annual SG budgets ,(g) Annual Accounts/ Financial Statements, and (h) PFM factsheets.
	Outcome Indicator 3	Baseline (2011)		Milestone (2013)				Target (2015)
	Effectiveness of core MDA support for government planning, finance and human resources performance management and service delivery mechanisms.	The structures and functions of MDAs are not aligned with sectoral or other service delivery targets. MoBEP structures and processes require strengthening to improve planning and financial management. HRM policies and processes are not comprehensive and critical elements are non-functional. The workforce is large in proportion to the size of the state and the personnel database is out of date. Human resource information systems and human resource development systems are non-functional.		(a) Government mandates, structure and staffing has been documented, (b) A corporate improvement plan is being used to guide reorganisation in MoBEP, (b) A government-wide G&SI sensitive HRM improvement plan has been developed, and (c) A strategy for government-wide establishment and workforce planning has been developed.				(a) The MoBEP corporate improvement plan has been implemented and implementation is underway in at least one health sector MDA, (b) the HRM improvement plan is being implemented in the Health sector, and (c) Establishment and workforce plans are being implemented in MoBEP and workforce plans are being used in the Health sector.
		Source
		(a) Mandate and mandate rationalisation reports, (b) MoBEP corporate improvement plan reports, (c) Health sector MDA corporate improvement plan reports, (d) HRM improvement plan implementation reports, and (e) establishment and workforce planning reports.
	Outcome Indicator 4	Baseline (2011)		Milestone (2013)				Target (2015)
	% of PEFA/SEAT Dimensions improving by at least one rating.	See 2011 SEAT/PEFA		N/A				15%
		Source
		State Government PEFA/SEAT Self Assessments, validated by external M&E Contractor.
INPUTS (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID SHARE (%)
	DFID to complete	DFID to Complete
INPUTS (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 1	Output Indicator 1.1	Baseline (2011)		Milestone (2013)				Target (2015)			Assumptions
Policy and strategy development, monitoring and evaluation improved.	Extent to which policy and strategy making processes meet good practice standards.	MoBEP support to MDAs primarily limited to procedural and technical guidance in preparing annual budgets.		Guidance for preparing MTSS, alongside definition of sector MTSS support roles within MoBEP, have been developed (localised from the generic model) and used by the core team to guide Health sector strategy team.				(a) MoBEP provides sustained and improved support for preparing and reviewing/adjusting sector strategy in Health, and (b) A guide and proposals have been developed for providing advice to policy makers and an action plan for the development of a State Development Plan agreed.			Citizens’ ability to claim rights and hold government accountable increased. / Civil society and State and Federal Government are, and remain, committed to the MDGs. / Changes in political leadership do not undermine State Government support for agreed SPARC intervention plan. / Changes in senior positions (e.g. HoS, Commissioners) do not undermine State Government support for key initiatives (e.g. Corporate Planning, State Development Plans, and MTSS). / State Government is committed to implementing institutional change actions supported under the SPARC intervention plan. / Constitutional reform do not have negative effects on inter-government relations. / HIV/AIDS, malaria and TB incidence do not prevent improvements in efficient and effective use of funds.
		Source
		(a) SEAT Reports, (b) SG MTSS guidelines, (c) MoBEP Corporate Improvement Plans, and (d) MoBEP quarterly work plan progress reports.
	Output Indicator 1.2	Baseline (2011)		Milestone (2013)				Target (2015)
	Quality and comprehensiveness of policies and strategies.	Zamfara Vision 2020 prepared but not sufficiently results-oriented. Health has developed a Strategic Plan but its quality against guidance standards remains poor, and there is limited evidence of the plan being reflected in the budget or actual expenditure. MoBEP has capacity at a senior level has potential.		MoBEP localised guidelines have been used and are evident in the content (improved standard) of the Health sector strategy 2014-2016.				Health sector strategy: (a) is financially feasible and consistent with 2015-2017 fiscal projections, (b) has comprehensive results frameworks that incorporate better content standards; and (c) outline development plan drafted.
		Source
		(a) SEAT Reports, (b) Health sector MTSS action plan, (c) Health MTSS, (d) Zamfara Vision 2020, (e) Fiscal Projections, and (f) MoBEP and Health Sector quarterly work plan progress reports.
Impact Weighting	Output Indicator 1.3	Baseline (2011)		Milestone (2013)				Target (2015)
25%	Extent to which results frameworks are comprehensive and measured.	No general evidence of strong availability or use of research and statistics across government		The upgraded Vision 2020 and Health Strategic Plan include results frameworks with relevant KPIs.				Results frameworks in the upgraded Vision 2020 and Health Strategic Plan include both targets and actual values for all KPIs.
		Source
		(a) SEAT Reports, (b) Vision 2020 and Health Strategic Plan, and (c) Vision 2020 and Health Sector Performance Reports.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)			DFID Share (%)		Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 2	Output Indicator 2.1	Baseline (2011)		Milestone (2013)				Target (2015)			Assumptions
State public financial management improved.	Extent to which the budget is credible and policy based.	There is no published budget calendar resulting in a call circular not being issued until September, giving MDAs approximately 2 weeks to prepare budgets. Budget approval is often well into the year of execution. The call circular contains no expenditure ceilings and no EXCO guidance on strategic resource allocations.		(a) A fixed budget calendar is used to guide the 2014-2016 budget process and (b) The Budget Call Circular includes contains sector ceilings based on realistic revenue forecasts.				A Budget Policy Statement is used to guide: (a) drafting of annual call circulars which include accurate and justified aggregate and sector ceilings, and (b) determining, costing and including capital/development projects into the budget process.			As above.
		Source
		(a) PEFA Reports, (b) Budget calendar, (c) Budget Call Circular, (d) Revenue forecasting model forecasts, (e) Sector spending ceilings, (f) Budget policy statement, and (g) Annual SG budgets.
	Output Indicator 2.2	Baseline (2011)		Milestone (2013)				Target (2015)
	Extent to which the budget is comprehensive and transparent.	The State’ budget classification is documented only in the budget and in the Accountant General’s report. There are inconsistencies in the application of some of the codes. The economic and functional classifications are incomplete, and are not applied uniformly across recurrent and capital expenditure. It is therefore not fully GFS- compatible.		Proposals made to MoFBEP for revised Budget Classification and Chart of Accounts.				Revised BC&COA is consistent with international best practice and standards, including GFS compliance.
		Source
		(a) PEFA Reports, (b) Budget Classification and Chart of Accounts, (c) Annual SG budgets, and (d) Budget performance reports.
	Output Indicator 2.3	Baseline (2011)		Milestone (2013)				Target (2015)
	Level of predictability and control in budget execution.	The annual budget represents the only cash forecast, and it is not converted to a quarterly or monthly cash plan. No reliable information is provided to MDAs or the Governor’s Office on the availability of cash for commitment of expenditure.		A basic cash forecasting model is designed.				(a) Capacity to profile annual budgets is established in at least one key sectors, and (b) A basic cash forecasting model is being operated within the Treasury.
		Source
		(a) PEFA Reports, (b) Annual SG budgets (c) Cash forecasting model forecasts (d) profiled budgets.
	Output Indicator 2.4	Baseline (2011)		Milestone (2013)				Target (2015)
	Quality of accounting, recording and reporting.	No in year budget reports are produced. However, the basic systems are in place to enable comparison of actual results against budget at the year end, and they could be used to prepare quarterly financial reports.		Proposed formats and processes for preparing budget monitoring reports are presented.				Improved budget performance reports are produced.
		Source
		(a) Budget monitoring report formats, and (b) budget monitoring reports.
Impact Weighting	Output Indicator 2.5	Baseline (2011)		Milestone (2013)				Target (2015)
50%	Extent and quality of external scrutiny and audit.	Audit reports are submitted to the legislature more than 12 months after the end of the period covered.		Proposals for more timely preparation and submission of audit reports presented.				Time to submit audit reports to the legislature reduced.
		Source
		(a) Audit reports, and (b) ShoA minutes.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID Share (%)	Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

OUTPUT 3	Output Indicator 3.1	Baseline (2011)		Milestone (2013)				Target (2015)			Assumptions
State civil service performance improved.	Clarity and appropriateness of public service organisation and operational management.	Structure and functions of MDAs are not aligned with any sector or other service delivery. MoBEP structures and processes require strengthening.		(a) Current cross-Government public service organisation clarified, including staffing structure, organisational and reporting arrangements, cost structure & basic mandates and (b) MoBEP Corporate Improvement Plan developed.				(a) Rationalisation of MDA mandates in progress in central MDAs, (b) Corporate Improvement Plan implemented in MoBEP and (c) Corporate Improvement Plan developed for at least one Health Sector MDA.			As above.
		Source
		(a) SEAT Reports, (b) Mandate review reports, (c) Mandates reference document, (d) MoBEP and Health sector corporate improvement plans, and (e) MoBEP and Health sector quarterly work plan progress reports.
	Output Indicator 3.2	Baseline (2011)		Milestone (2013)				Target (2015)
	Extent to which HRM policies and organisation are in place.	HRM policies and processes are not comprehensive and critical elements are non-functional.		HRM arrangements reviewed and G&SI-sensitive improvement plan prepared.				Implementation of HRM improvement plan begun in the health sector.
		Source
		(a) SEAT Reports, (b) HRM review reports, (c) HRM improvement plan, and (d) quarterly work plan progress reports.
Impact Weighting	Output Indicator 3.3	Baseline (2011)		Milestone (2013)				Target (2015)
25%	Extent to which establishment planning and workforce planning, management and development is in place.	The workforce is large in proportion to the size of the state. Personnel database is out of date and HRIS and HRD systems are non-functional.		(a) Health sector workforce planning approach agreed and (b) G&SI-sensitive strategy for ZSG-wide workforce planning and audit agreed.				(a) An establishment and workforce planning process is being used in MoBEP, (b) A workforce planning process is being used in the Health Sector (including recruitment, retention, deployment processes), and (c) Workforce analysis identifies issues and potential HR cost savings.
		Source
		(a) SEAT Reports, (b) workforce planning strategy, (c) workforce review reports, and (d) MoBEP and Health sector quarterly work plan progress reports.
Inputs (£)	DFID (£)	Govt (£)	Other (£)			Total (£)				DFID Share (%)	Risk Rating
	DFID to complete	DFID to Complete									High
Inputs (HR)	DFID (FTEs)
	DFID to complete

## Logframe Endnote i: MDG attainment 1990 – 2009
Goal	1990	2000	2005	2009	Target 2015
1. Eradicate extreme poverty and hunger
1.A – Halve, between 1990 and 2015, the proportion of people whose income is less than one dollar a day
Proportion of the population living on less than $1 (PPP) per day (%)	-	-	51.55 2004	-	21.4
Poverty gap ratio	32.1	-	29.6	-	-
Share of poorest quintile in national consumption (%)	5	5	5.1 2004	-	-
1.C – Halve, between 1990 and 2015, the proportion of people who suffer from hunger
Prevalence of underweight children under five years of age (%)	35.7	31 1996	30 2004	23.1 2008	19.96
Proportion of population below minimum level of dietary energy consumption (consuming 2,900 calories or less daily) (%)	39	29	35	32.83 est.	14.5
2. Achieve universal primary education
2.A – Ensure that, by 2015, children everywhere, boys and girls alike, will be able to complete a full course of primary schooling
Net enrolment ratio in primary education (%)	68	95	84.6	88.8 2008	100
Proportion of pupils starting Primary 1 who reach Primary 5 (%)	67	97	74	72.3 2008	100
Primary 6 completion rate	58	76.7	69.2	67.5 2007	100
Literacy rate of 15-24 year olds, women and men	-	64.1	76.2	80.0 2008	100
3. Promote gender equality and empower women
3.A – Eliminate gender disparity in primary and secondary education preferably by 2005 and to all levels of education no later than 2015
Ratio of girls to boys in primary education (girls per 100 boys)	76	78	81	85.4 2008	100
Ratio of girls to boys in secondary education (girls per 100 boys)	75	81	80.6	79.9 2008	100
Ratio of girls to boys in tertiary education (girls per 100 boys)	46	66	70.1	66.8 2008	100
Share of women in wage employment in the non agricultural sector (%)	66.3	-	79	-	-
Proportion of seats held by women in the National Parliament (%)	1.0	3.1	3.1	7.5	30
4. Reduce child mortality
4.A – Reduce by two-thirds, between 1990 and 2015, the under-five mortality rate
Under-five mortality rate (per live 1,000 births)	191	183.75	201	157 2008	63.7
Infant mortality rate (per 1,000 live births)	91	81.38	100	75 2008	30.3
Percentage of one-year olds fully immunised against measles	46	32.8	60	74.3	100
5. Improve maternal health
5.A – Reduce by three quarters, between 1990 and 2015, the maternal mortality ratio
Maternal mortality rate (per 100,000 live births)	1000	704	800	545 2008	250
Proportion of births attended by skilled health personnel (%)	45	42	43.5	38.9 2008	100
5.B – Achieve by 2015, universal access to reproductive health
Contraceptive prevalence rate (%)	-	-	12	14.6 2008	-
Adolescent birth rate (%)	-	-	25 2004	-	-
Antenatal care coverage: At least one visit (%)	-	-	59	54.5 2008	-
Antenatal care coverage: At least four visits (%)	-	-	47 2004	44.8 2008	-
Unmet need for family planning (%)	-	-	17 2004	20.2 2008	-
6. Combat HIV/AIDS, malaria and other diseases
6.A – Have halted by 2015 and begun to reverse the spread of HIV/AIDS
HIV prevalence among pregnant young women aged 15-24 (%)	-	5.4 2001	4.3	4.2 2008	To be halted
Young people aged 15-24 reporting the use of a condom during sexual intercourse with a non-regular sexual partner (%)	-	-	63.8	63.8 2007	100
Proportion of population aged 15-24 years with comprehensive correct knowledge of HIV/AIDS (%)	-	-	25.9	25.9 2007	100
Ratio of school attendance of orphans to school attendance of non-orphans aged 10-14 years	-	-	-	1.2 2009	-
Children orphaned by HIV/AIDS (million)	-	-	1.97	1.97 2007	-
6.C – Have halted by 2015 and begun to reverse the incidence of malaria and other major diseases
Malaria prevalence / (per 100,000)	-	2024	1157	1157 2007	-
Deaths (per 100,000)	-	0.23	0.16	0.16 2007	-
Proportion of children under 5 / sleeping under insecticide-treated / bed nets (%)	-	-	2.2 2003	10.9	-
Tuberculosis prevalence / (per 100,000)	-	15.74	7.07	7.07 2007	-
Deaths (per 100,000)	-	1.57	1.50	1.50 2007	-
7. Ensure environmental sustainability
7.A – Integrate the principles of sustainable development into country policies and programmes and reverse the loss of environmental resources
Proportion of land area covered by forest (%)	18.9	14.4	12.2	9.9	15
7.C – Halve, by 2015, the proportion of people without sustainable access to safe drinking water and basic sanitation
Proportion of population using an improved drinking water source (%)	54	54	60	58.9	77
Proportion of population using an improved sanitation facility (%)	39	42.9	33	51.6	70
8. Develop a global partnership for development
8.D – Deal comprehensively with the debt problems of developing countries
Per capita ODA to Nigeria (US$)	3.0	1.47	48.94	81.67 2006	-
Debt service as a percentage of exports of goods and services	22.3	8.2	15.2	0.5 2008	-
8.F – In cooperation with the private sector, make available the benefits of new technologies, especially information and communications technology
Telephone lines per 100 people	0.3	0.44	0.87	0.86 2008	-
Cellular subscribers per / 100 people	0	0.02	13.19	41.66 2008	-
Internet users per 100 people	0	0.06	3.55	15.86 2008	-
Teledensity	-	-	16.27	45.93	-

Source: Nigerian Government 2010 MDG Report