Business Case

Summary Sheet

Title: / Responding to the Nutrition Crisis in Yemen
Programme Summary: / This programme is part of a wider UK Government objective to avert famine in Yemen. / The Department for International Development (DFID) will fund a 3 year programme in Yemen built around a life-cycle approach that aims to address the immediate and underlying causes of undernutrition. It will address critical nutrition, health, water and sanitation needs, and improve the technical analysis and evidence informing the response. / This programme is in line with the International Development (Gender Equality) Act 2014. The needs and perspectives of girls, boys, women and men have been considered and integrated into programme activities.
Programme Value: Up to £96.5 million		Country/ Region: Yemen
Programme Code:	Start Date: / October 2018	End Date: / September 2021
Overall programme risk rating:	Major
Vault Number:	36022579

Intervention Summary (2 pages max)
What support will the UK provide?
This programme is part of a wider UK Government objective to avert famine in Yemen. DFID will provide up to £96.5 million over 3 years to address critical nutrition, health, water and sanitation needs in Yemen, while also improving evidence informing the response[1].Hazard and risk analysis and early warning
[1] Including drawing DFID framework agreements: Expert Advisory Call-Down Service (EACDS) on Strengthening Resilience and Response to Crises; and the Maximising Quality of Scaling Up Nutrition (MQSUN),initiative.
- Effective response to protracted crises – solving chronic needs
- Tackling long-term stresses
- Anticipating and mitigating shocks – preparing for recurrent or seasonal shocks
- Responding to shock – building back better
- Financing risk – contingency and risk financing, insurance and private sector
What are the main programme activities?
DFID investments will be structured across three main output areas identified below. These will use the lifesaving approach to immediate and remedial needs as well as improve the contextual understanding of the causes and consequences of malnutrition. The programme will respond flexibly and adapt to changes in needs and access.
1. Immediate Actions - providing lifesaving and improved quality nutrition, health, water, sanitation and hygiene (WASH) service delivery for affected populations. DFID will approach health and wash through a nutrition lens and complement these with a focus on protection for the most vulnerable.
2. Remedial Actions – maintain and strengthen systems delivering nutrition, health and water and sanitation services at a sub-national level. It will manage risk through planning and financing to improve the efficiency and effectiveness of the response.
3. Increase contextual understanding - addressing the information and data gaps that exist in Yemen by focusing on improving the knowledge and evidence base to improve our understanding of the context (i.e. under 5 mortality), analytical products necessary for decision making (i.e. nutrition surveys). Hazard and risk analysis and early warning
- Effective response to protracted crises – solving chronic needs
- Tackling long-term stresses
- Anticipating and mitigating shocks – preparing for recurrent or seasonal shocks
- Responding to shock – building back better
- Financing risk – contingency and risk financing, insurance and private sector
Does the programme fit with DFID’s strategic architecture: the UK Aid Strategy, Single Departmental Plan, International Development Act and the department’s Business Plan?
Yes this programme delivers against the UK Aid Strategy, in particular, strategic objective 2 (Resilience and Response) and 4 (Poverty); the Departmental Plan, Her Majesty’s Government (HMG) Humanitarian Reform Policy, and the DFID Yemen Business Plan. In addition it contributes to manifesto commitments[2] and contributes to the UK’s ambition to deliver against the Sustainable Development Goals, in particular on ending hunger.
[2] Manifesto commitment: To address nutrition needs to children under 5, pregnant women (of childbearing age) and adolescent girls and provide sustainable access to water.
What percentage of DFID’s Single Departmental Plan results target does this programme represent? Could the programme be adjusted in scope or scale to deliver SDP results?
This programme will contribute to the single department plan results related to leading humanitarian responses, delivering on DFID’s global nutrition strategy and putting disability at the heart of what we do.
Is the programme coherent with the wider international community and partner government response? Has the programme set out a sustainable exit strategy?
The programme aims to shift the international humanitarian response model in Yemen to a protracted crisis approach (HMG Humanitarian Policy Objective), capable of delivering lifesaving assistance while maintaining the foundation necessary for future sustained development. The exit strategy is dependent on a significant change in the operating environment that allows the Government of Yemen to deliver these critical services.
Has the programme considered working with HMG Departments and accessing cross-HMG funds?
Yes, the programme will look to engage with other Government departments and UK investments (e.g. UK International Climate Finance and Green Climate Fund).
How does the programme relate to other UK aid within the specific sector, including multilateral, bilateral and centrally managed programmes?
DFID Yemen’s business plan prioritises urgent humanitarian and protection needs: i) food security; ii) multi-sectoral approach to the treatment and prevention of malnutrition; iii) to support the needs of the most vulnerable. This programme will specifically address the second element and complements the DFID Yemen investments in the other areas.

The programme further complements UK multilateral and centrally managed investments, including but not limited to World Bank International Development Assistance, Global Alliance for Vaccines and Immunisation (GAVI), and DFID core funding to UNICEF.
Is there sufficient flexibility to learn and adjust to changes in the context? What level of flexibility is there to shift this and future commitments?
Yes, the programme is designed around a model that can flex and shift approaches to changes in the context – including either a deterioration or improvement. The risk management component in output 2 will specifically aim to improve the quality of the risk analysis, planning, and subsequent resourcing. It will aim to improve the overall understanding of the context and anticipate where it might be necessary to adapt or flex.
Does the proposed level of risk to be taken fit with DFID’s risk appetite for this portfolio?
Yes. While a major risk programme, DFID is partnering with an established UN organisation with a strong track record in country and a partner of DFID since 2011. Independent monitoring of the previous programme has shown that UNICEF was largely equipped to manage risks in a complex and challenging context.
Is there a clear communications strategy to reinforce our objectives? Will the programme be branded with the UK aid logo and recognise UK Government funding – and, if not, why not?
We will proactively communicate our support for UNICEF for this programme to the UK public and internationally. We however consider the security risks to UNICEF staff to be too significant to require UKAID branding within Yemen.
Has the programme been quality assured? How confident are we that the skills, capability, resources and political will exist to deliver the programme?
Politically, this programme addresses a UK National Security Council priority to avert famine in Yemen. This business case has undergone a peer based quality assurance process involving DFID leads on nutrition, conflict and Yemen specific experts on results, value for money (VFM), and commercial delivery. DFID has a strong track record in nutrition programming in Yemen and are confident that the programme can be delivered with available resources.
Does the SRO and team have the capability and resources to deliver this programme?
Yes, the senior responsible owner (SRO) and programme manager are experienced and will draw upon expertise in the DFID Yemen team for contextual knowledge as well as other expertise across DFID on nutrition, health and wash.

Strategic Case
Why Yemen?
1. The humanitarian crisis in Yemen is widely acknowledged as the worst in the world. Last year’s cholera outbreak was the largest ever recorded in a single year. An estimated 22 million Yemenis, roughly 75% of the population, are in need of humanitarian assistance or protection assistance, including 11 million people who are severely in need. Of these, some 8.4 million people are severely food insecure and at risk of starvation, a 24% increase over the last year.
2. Approximately a third of the districts in the country - 107 of 333 districts - are now facing a heightened risk of sliding into famine, an increase of 13% since April 2017. The majority of the 10.4 million individuals living in these 107 districts do not know where their next meal will come from; lack access to safe water for drinking and basic sanitation and hygiene facilities; adequate access to health care; and require nutrition assistance. The situation is further worsened by the current resource shortfalls, capacities of partners, and access challenges. The institutions providing basic essential services are on the brink of collapse, with salaries having not been paid for over 18 months.
3. At least one child dies every ten minutes in Yemen because of preventable diseases.[3] Beyond the direct casualties of the armed conflict, there are ‘silent deaths’ that go largely unnoticed and unrecorded. Girls, boys, women and men are dying of hunger and diseases that are easily preventable and treatable such as diarrhoea, malnutrition and respiratory tract infections. People with chronic diseases, including high blood pressure and diabetes, who are not receiving life-sustaining treatment due to medical shortages are slowly dying. Yemen’s rates of maternal mortality were already the highest in the Middle East as well as having the lowest levels of antenatal coverage. As a result many women suffer from anaemia, infections, and/or obstetric fistula.[4] [5] This is further compounded by access restrictions for populations seeking care, and lack of service providers, food commodities, fuel, and medicines.
  [3] ERC statement https://www.unocha.org/story/yemen-child-under-age-five-dies-every-10-minutes-preventable-causes-un-humanitarian-chief
  [4] UNICEF – With maternal mortality at 148 deaths per 100,000 live births and antenatal coverage at 60%, and only 45% of births are attended by skilled health staff
  [5] UNICEF - https://www.unicef.org/media/media_93868.html
4. Nutrition - 7.5 million Yemenis, 25% of the entire population, are malnourished. At least 1.8 million children and 1.1 million pregnant or breastfeeding women are acutely malnourished, including over 400,000 children under five who are suffering from severe acute malnutrition. Nutrition surveys conducted during the first half of 2018 confirm alarming rates of Global Acute Malnutrition (GAM) which have soared above 20 percent in two governorates, are between 15 and 20 percent in two others and between 10 and 15 percent in four governorates[6]. Half of all children in Yemen are stunted; five have levels above 60 percent, and 13 governorates have stunting levels of 40 percent. Surveys confirm that stunting is increasing by as much as 1.7% annually.
  [6] Based on WHO criteria, when a population’s Global Acute Malnutrition (GAM) rates exceed 10%, this is regarded as a “serious” emergency; when GAM rates exceed 15%, this indicates a “critical” emergency.
5. Health - Only 50% of all health facilities are fully functional and an estimated 16 million Yemenis require support to obtain healthcare, 9.3 million of whom are in acute need. Access to healthcare is paramount for people whose lives are at risk due to illness or injury. According to a health cluster analysis, the main causes of avoidable deaths in Yemen are communicable diseases and maternal, perinatal, and nutritional conditions, which together account for 50% of mortality, and non- communicable diseases, which account for 39% of mortality[7]. The latest cholera and diphtheria outbreaks have underscored the detrimental impact of the failing health system[8].
  [7] WHO. Cholera Situation Update Yemen. Geneva; 2017.
  [8] OCHA; Yemen - Humanitarian Needs Overview 2018;
Health and Nutrition facility functionality[9].
[9] OCHA. Humanitarian Response Plan Yemen 2018. New York; 2018.

1. Water, sanitation and hygiene (WASH) - An estimated 16 million people require assistance to access safe drinking water and sanitation, including 11.6 million in acute need. The country has experienced two major outbreaks of cholera; the first began in October 2016 and the second began at the end of April 2017. The outbreak has resulted in over 1.1 million suspected cases and over 2,100 related deaths[10]. Collapsing urban water and sanitation systems, deteriorating water and sanitation conditions in rural areas, and a lack of means to maintain personal hygiene and to purchase safe drinking water all contribute to an increased risk of mortality and morbidity. As of December 2017, water, sanitation, and garbage disposal systems have all deteriorated or ceased functioning across much of the country. The lack of functioning WASH services coupled with inadequate hygiene practices are thought to have contributed heavily to the cholera epidemic in the country. [11]
  [10] WHO - Yemen – Cholera Response; weekly epidemiological bulletin: week 29 - 2018
  [11] WHO. Cholera Situation Update Yemen. Geneva; 2017.
2. Access – A volatile security situation, restricted access to some parts of the country, fuel shortages and damaged road infrastructure are all factors that put a strain on affected populations and organisations responding to the crisis[12].
  [12] OCHA. Humanitarian Response Plan Yemen 2018. New York; 2018.
  1. Vulnerable populations – The conflict is making it harder for civilians to move freely. This is particularly the case for women seeking reproductive health services, or children seeking treatment for severe acute malnutrition. Additionally, the intensification of the conflict, and restrictions of movement in active conflict areas, disconnects and disrupts the formal market systems resulting in scarcity and escalation of prices of essential food and non-food commodities.[13]
    [13] OCHA. Humanitarian Response Plan Yemen 2018. New York; 2018.
  2. Humanitarian access - Access restrictions by all parties to the conflict continue to hamper humanitarian reach. With 22.2 million people in need of some kind of humanitarian assistance and, approximately 1.5 million people living in districts with the high access constraints, Yemen is one of the largest and most logistically complex emergency responses. Of particular concern are the bureaucratic obstacles, such as visa restrictions, travel permits, registration and approval procedures, and checkpoints; interference in the implementation of humanitarian activities, including through demanding fees, restricting importation of critical supplies, diverting aid; and security constraints such as ongoing fighting and violence against humanitarian workers.
Related to both groups is the communication and collection of information and data which remains an ongoing challenge within Yemen. The conflict, bureaucratic impediments and security concerns continue to prevent populations from communicating their needs, and their ability to seek information as well as humanitarian actors from being able to carry out surveys, and assessments to analyse and inform the response.
Nutrition of children and women / Key Findings from the last national survey (2013)[14] / Almost half of children under-5 (47 percent) are stunted (short for their age), / 16% are wasted (thin for their height), / 39% percent are underweight (thin for their age). / Almost all children (97%) are breastfed at some time; however, only 10% of children 0 to 6 months are exclusively breastfed. / Only 15% of children 6-23 months are fed in accordance with all three infant and young child feeding (IYCF) practices. / Almost nine in ten children (86 percent) age 6-59 months are anaemic. / Seven in ten women age 15-49 are anaemic.
[14] Yemen National Demographic Health Survey 2013

Why Nutrition in Yemen?
Malnutrition is endemic in Yemen. In 2013, prior to the current conflict Yemen met the criteria of a country experiencing a critical nutrition emergency. According to the Yemen National Demographic and Health Survey (YNDHS), Yemen’s malnutrition levels were critical. 16%[15] of Yemeni children under-5 were acutely malnourished and 47% chronically malnourished or stunted[16]. Just 59% of households had access to improved sources of drinking water whilst 45% of households accessed improved sanitation facilities. Wide geographic disparities were prevalent in service/access and nutrition and health services.[17]
[15] Based on WHO criteria, when a population’s Global Acute Malnutrition (GAM) rates exceed 10%, this is regarded as a “serious” emergency; when GAM rates exceed 15%, this indicates a “critical” emergency.
[16] Stunted is defined by reduced height for age
[17] Maximising Quality for Scaling Up Nutrition; An Updated Contextual Analysis of Nutrition Situation in Yemen; January 2018

Acute Malnutrition
1. Acute malnutrition or wasting can result in death if left untreated. In children aged under five years it is internationally diagnosed three ways, being too thin for a given height[18] and/or having a left arm circumference less than a given threshold (i.e. measuring how fat or thin the mid upper arm circumference is), and/or having swollen feet (known as bilateral pitting or malnutrition oedema).
  [18] Severe acute malnutrition (SAM): weight-for-height ratio z-score (WHZ) of <-3 (also termed “severe wasting”) or MUAC < 115 mm, or the presence of bilateral pitting oedema, or both. Moderate acute malnutrition (MAM): WHZ between -2 and -3 (“moderate to severe wasting”) or mid-upper arm circumference (MUAC) of 115-125 mm (WHO definitions).
2. As mentioned above, access constraints have led to a lack of data to analyse the context. The figure below presents the most up-to-date and statistically representative data available for acute malnutrition given by the Global Acute Malnutrition (GAM) prevalence at the governorate level. Where Standardised Monitoring and Assessment of Relief and Transitions (SMART) surveys with statistically representative data at the governorate level were available, these were used[19].
  [19] The 2004 census information on governorate population was used in combination with prevalence estimates to calculate the approximate percentage of the national burden of wasting in each governorate.

Figure 1: Comparison of GAM prevalence and percentage of national GAM burden by governorate.[20]
[20] Population estimates for governorates are taken from the 2004 census. Prevalence estimates for global acute malnutrition are taken from the 2013 Yemen National Health and Demographic Survey, except where more recent Standardised Monitoring and Assessment of Relief and Transitions (SMART) surveys with representative data at the national level were available Note: GAM, global acute malnutrition. Source Maximising Quality for Scaling Up Nutrition; An Updated Contextual Analysis of Nutrition Situation in Yemen; January 2018
1. The national prevalence of GAM amongst children aged 6 to 59 months was above the 15% critical emergency threshold, in 11 governorates and above 20% in the four governorates of Hodeidah, Shabwa, Hajja, and Abyan (based on findings from 2013).
2. Due to the challenges around data, we are only able to use estimates of the GAM to assess the context. However all indications are that not much has changed since the last nationally representative survey was carried out, with still much of the country considered in a critical state (see map below).

Map 1 Latest estimated of Global Acute Malnutrition (GAM)
Chronic Malnutrition
1. Chronic malnutrition or stunting is a result of prolonged or repeated episodes of undernutrition starting before birth and can result in reduced height and cognitive ability[21]. It is defined by a reduced height for age.
  [21] Vinicius J. B. Martins, Telma M. M. Toledo Florêncio, Luciane P. Grillo, Maria do Carmo P. Franco, Paula A. Martins, Ana Paula G. Clemente, Carla D. L. Santos, Maria de Fatima A. Vieira, Ana Lydia Sawaya Long-Lasting Effects of Undernutrition Int J Environ Res Public Health. 2011 Jun; 8(6): 1817–1846. Published online 2011 May 26. doi: 10.3390/ijerph8061817 https://www.ncbi.nlm.nih.gov/pmc/articles/PMC3137999/
2. Similar to acute malnutrition, there have been challenges with gathering data on chronic malnutrition or stunting. The figure below presents the most up-to-date and statistically representative data available for stunting prevalence at the governorate level. The governorates that accounted for the highest burden of stunting in the country were Hodeidah (12% of national burden) and Taiz (12% of national burden); together they accounted for almost a quarter of all stunting in the country. Prevalence was also extremely high in both governorates at 49% and 46% in Hodeidah (2013 YNHDS) and Taiz (2017 SMART), respectively.

Figure 2: Comparison of stunting prevalence and percentage of national burden by governorate.
Malnutrition has serious consequences
1. The combined influence of wasting and stunting make children 12 times more likely to die from diseases. If left unchecked this could trigger the declaration of a famine[22] which combines indicators related to food insecurity, malnutrition and mortality.
  [22] A famine declaration is triggered if all three of the following indicators are breached: - At least one in five households faces an extreme lack of food - More than 30 percent of children under 5 are suffering from acute malnutrition (wasting) - At least two people out of every 10,000 are dying each day
2. Good nutrition is fundamental for optimal health and growth. Through its effect on health and cognitive development it is also vital for academic performance and productivity, and therefore for healthy economies and socioeconomic development. It is widely acknowledged that the children who survive do less well at school, have 10% lower lifetime earnings, and are more likely to have undernourished children themselves. Additionally, the economic consequences of undernutrition in affected countries represent losses of national GDP of 10% year-on-year[23]. Addressing malnutrition would therefore help children of Yemen to be healthy, learn, and contribute to the economy and society and improve Yemen’s future development prospects.
  [23] Saving lives, investing in future generations and building prosperity – the UK’s Global Nutrition Position Paper; October 2017 Global Nutrition Report 2015
The Drivers of Malnutrition in Yemen
1. In Yemen, the food and nutrition crisis has been exacerbated by the conflict and subsequent collapse of the economy. The disruption of formal markets, fluctuation in the currency, escalation of prices of basic goods and diminished purchasing power mean that Yemenis can buy less with the money they have. Around 80% of Yemenis are estimated to be in debt. The interruption of the payment of salaries for 1.25 million public sector workers continues, undermining public systems. Half of all health facilities in the country are closed or not fully functional. A quarter of all children are not attending school.[24]
  [24] Maximising Quality for Scaling Up Nutrition; An Updated Contextual Analysis of Nutrition Situation in Yemen; January 2018
2. The root causes of malnutrition and the factors leading to it are complex and multidimensional. Conflict, poverty, underdevelopment, and low socioeconomic status are major contributors, along with other social determinants. Malnutrition is often aggravated by poor feeding and care practices for infants and young children, as well as poor sanitation and hygiene. A lack of access to education, quality health systems, and safe drinking water can also have a negative effect, along with infectious disease and the ingestion of harmful contaminants.
3. In recent years progress has been made in developing knowledge and understanding of the magnitude and scope of nutritional challenges, the increasing contribution of non-communicable diseases, and the complex web of factors that can influence nutrition. A greater understanding has developed regarding the importance of nutrition at different stages of the life course and the effect of poor nutrition across generations (see illustration below). An intergenerational cycle of malnutrition exists whereby a woman who has anaemia or has a low body mass index, for example, is likely to have a baby with a reduced birth weight. Low birthweight babies are more likely to be wasted or stunted and to have a higher risk of morbidity and mortality and of developing non-communicable diseases later in life. Conversely, if the mother is obese when she starts her pregnancy she is also at increased risk of complications during pregnancy or delivery, which could result in premature delivery—and, therefore, a low birth weight for her baby. Alternatively, if she carries the baby to full term, her baby is more likely to have a higher birth weight and a higher risk of child and adolescent obesity.[25]
  [25] Branca, Francesco; Piwoz, Ellen; Schultink, Werner; Sullivan; Lucy Martinez; “Nutrition and health in women, children, and adolescent girls”; BMJ 2015;351:h4173: https://doi.org/10.1136/bmj.h4173 (Published 14 September 2015)
[26]
[26] Branca, Francesco; Piwoz, Ellen; Schultink, Werner; Sullivan; Lucy Martinez; “Nutrition and health in women, children, and adolescent girls”; BMJ 2015;351:h4173: https://doi.org/10.1136/bmj.h4173 (Published 14 September 2015)
1. Similarly, there is now much greater awareness that effective responses need to come from beyond the health sector and that this must involve other sectors, such as those related to water and sanitation, education, trade, and social protection. Crucially, a radical transformation is needed so that food systems can ensure that everyone has access to a sustainable, balanced, and healthy diet.[27]
  [27] Branca, Francesco; Piwoz, Ellen; Schultink, Werner; Sullivan; Lucy Martinez; “Nutrition and health in women, children, and adolescent girls”; BMJ 2015;351:h4173: https://doi.org/10.1136/bmj.h4173 (Published 14 September 2015)
2. For Yemen, there are unique differences as to how malnutrition presents itself, including differences related to age, gender, mother’s status and physical location that appear to have a bearing on a child’s likely nutritional status. This is illustrated below with specifics about the Yemen context highlighted[28]:
  [28] Maximising Quality for Scaling Up Nutrition; An Updated Contextual Analysis of Nutrition Situation in Yemen; January 2018
Scale
  - 7.5 million Yemenis, 25% of the entire population, are acutely malnourished and almost half (46%) of all children under 5 in Yemen are stunted. At least 1.8 million children and 1.1 million pregnant or breastfeeding women are acutely malnourished, including over 400,000 children under age five who are suffering from severe acute malnutrition[29].
    [29] OCHA. Humanitarian Response Plan Yemen 2018. New York; 2018.
Drivers of Malnutrition in Yemen[30]
[30] Maximising Quality for Scaling Up Nutrition; An Updated Contextual Analysis of Nutrition Situation in Yemen; January 2018
  - Feeding practices – While 97% of children were assessed to have been breastfed at some stage with average duration being 18 months, exclusive breastfeeding is extremely low amongst children 0 to 6 months at 10%. Additionally, only 15% of children aged 6 to 23 months were fed in accordance with all three of the recommended safe feeding[31] practices for non-breastfed children.
    [31] Nonbreastfed children age 6-23 months: they receive other milk or milk products at least twice a day; receive the minimum meal frequency of solid or semisolid food or milk feeds at least four times a day; and receive solid or semisolid foods from at least four food groups not including the milk or milk products food group.
  - Women affected by undernutrition and without access to sexual reproductive health were more likely to give birth to small babies or have children that are stunted - An estimated 30% of children are born with low birth weights (< 2.5 kg) closely tied to economic status, with increasing prevalence amongst poorer households. Additionally, children born within a birth interval of less than 24 months after the previous sibling were 65% more likely to be stunted compared to firstborn children.
  - The governorate in which a child lived was found to be an important determinant of child wasting. There appears to be large disparities in the percentage of children wasted across governorates, ranging from 10.9% in Ibb to 26.2% in Hodeidah even after adjusting for other variables. A total of seven governorates were found to have significantly higher odds of wasting when compared to those who lived in Ibb, the governorate with the lowest percentage of wasted children in the country.
  - Continued efforts to maintain access to clean water is essential, with a priority on rehabilitating piped water systems. Even after adjusting for other variables, children who lived in households that accessed drinking water from a tanker truck were at a significantly decreased risk of wasting compared to those that used the government piped network. Similarly, children in households that accessed water from a tube well were also at a significantly decreased risk of wasting compared to those that used the government piped network. This is likely due to high levels of pollution in the government piped water network, which has been associated with increased child morbidities in the past.
  - Behaviour change and hygiene promotion efforts need to go beyond distributing hygiene kits to meaningfully changing behaviours. Children in households with soap visible at the place where they washed their hands did not have decreased odds of wasting.
  - Food security and purchasing power are essential - There are currently 1.4 million households (approximately 22%) that suffer from food shortages or go a whole day without food and are 16 to 38% more likely to be malnourished.

See Annex A for a summary of the statistical analysis underpinning this business case context.

DFID intervention rationale - Tackling the drivers of malnutrition in Yemen
1. Nutrition-specific interventions are essential to help prevent malnutrition and save lives. But evidence shows that this package on its own will only have marginal gains, such as reduced stunting rates by 20%. As such, DFID will increasingly prioritise nutrition-sensitive interventions that address the underlying and root causes of malnutrition[32].
  [32] Saving lives, investing in future generations and building prosperity – the UK’s Global Nutrition Position Paper; October 2017
2. This business case will support a 3 year programme built around a life-cycle approach that employs a range of strategies to address the immediate and underlying causes of undernutrition (explained below).
Why a life-cycle approach?
Improving women’s, children’s, and adolescents’ nutrition requires a range of policies, programmes, and interventions at different stages of life. And, since we know that malnourished women give birth to malnourished children, it is possible to take action to improve nutrition across generations. The figure below illustrates some of the essential interventions that address nutrition vulnerability. [33]
[33] Branca, Francesco; Piwoz, Ellen; Schultink, Werner; Sullivan; Lucy Martinez; “Nutrition and health in women, children, and adolescent girls”; BMJ 2015;351:h4173: https://doi.org/10.1136/bmj.h4173 (Published 14 September 2015)

1. By taking a life-cycle approach, the programme aims to shift the international humanitarian response model in Yemen to a protracted crisis approach (HMG Humanitarian Policy Objective), capable of delivering critical lifesaving assistance while attempting to maintain the foundation necessary for future development.
2. This is an ambitious but necessary objective in order to retain flexibility over the course of the programme delivery. Contextualising the approach in Yemen means that we will need to focus on the lifesaving interventions and build on these where possible to maintain and increase the capacity and resilience of the systems involved. It will be an ongoing exercise, consistently delivering critical lifesaving assistance while also scaling longer term systems strengthening efforts where access becomes permissible.
Impact and Outcomes
The expected impact of the programme is:
Nutrition caseloads in Yemen decrease; across the life course we see an improved Nutrition status among infants, children adolescents, adults and pregnant women.
Outcome 1: Girls, boys and their mothers living in humanitarian conditions have access to critical life-saving interventions through convergent life-saving nutrition, health, water, sanitation and hygiene services
Indicative indicators
- Reduction in Under five morbidity and mortality due to preventable causes
- Over 2.5 million people with Increased access to improved water supply sources, basic sanitation and hygiene supplies
Outcome 2: Nutrition, health, water, sanitation systems and hygiene promotion are preserved and strengthened to deliver services and manage risk.
Indicative indicators
- Increased access to health care facilities and mobile clinics for at least 5 million children
- Timely response to all identified and known hazards as measured by a scaled response to an early warning
Outcome 3: The international and national systems in Yemen are better able to use knowledge and evidence to make critical decisions
Indicative indicators
- Increased access to analysis and evidence with at least one substantive report produced per year
- An annual analysis of cross cutting performance highlighting success and indicating gaps specifically for integrated programming, gender, disability and protection
Lessons Learned
Key lessons learned from nutrition, health water, sanitation and hygiene promotion programming in Yemen include:
Programmes need to consider the operational challenges of delivering an integrated programme in a live conflict setting. The challenge for DFID moving forward to ‘shock proof’ the programme, considering carefully ways to build better risk management to anticipate, prepare for and respond to acute changes in the security environment which will have potential negative impact on civilian populations living in Yemen.
  1. This business case has integrated the shock response component as part of the risk management element and will continue to assess the theory of change as part of the annual review.
Further integration of services should be considered, including providing sexual and reproductive health services, mental health and psycho-social support, inclusivity programmes and programming addressing Gender, GBV and safeguarding.
  1. This is being integrated throughout the programme as part of ensuring standards are applied across the programme, psychosocial and early child development support to particularly vulnerable cases and a protection focused case management referral system.
Strengthened conflict sensitivity, including robust and consistent community consultation procedures and feedback loops need to be included.
  1. This element will be integrated as part of the system strengthening and risk management elements.
Consistency of data presented and made available regarding malnutrition and other health indicators has been an issue. DFID should explore ways it can access data directly, and then modify reporting to produce a higher level strategic report to DFID twice a year.
  1. This is being taken on board as part of the management of the business case.
Collaboration needs to be strengthened around the delivery of services for both SAM and MAM cases. DFID should explore ways it can facilitate the continued collaboration between key nutrition actors (UNICEF, WFP and WHO)
  1. DFID is looking to establish a common action plan between key nutrition actors in Yemen and potentially launching this at a United Nations General Assembly event.
Gender Equality
1. This programme is in line with the International Development (Gender Equality) Act 2014. The needs and perspectives of girls, boys, women and men have been considered and integrated into programme activities.
2. Yemen ranks last out of 144 countries on the World Economic Forum's Global Gender Gap Index.38 Women and girls continue to face entrenched gender inequalities which result from prevailing social norms that limit their access to services, livelihoods and other opportunities. The conflict has only served to exacerbate the specific vulnerabilities and the limitations they face.[34] Further to this, the levels of responsibilities that women have to take on have significantly increased with women having to seek employment in addition to their other responsibilities.
  [34] OCHA. Humanitarian Response Plan Yemen 2018. New York; 2018.
3. As families face the loss of male family members due to conflict-related death or injury or loss of traditional livelihoods, the level of economic hardship increases. This increasingly leads families to resort to negative coping strategies. Child marriage rates have increased, rising from 52% of Yemeni girls under the age of 18 marrying in 2016 to close to 66 per cent in 2017. A UNICEF Knowledge, Attitude and Practices (KAP) survey (2017) revealed that in governorates with high numbers of IDPs, such as Hajjah, Al Hudaydah and Ibb, 44% of all marriages involve girls under the age of 15.[35] Studies have suggested that pregnancy and child birth in adolescent girls will cease the mother’s growth and increase the risks of low birth weight, neonatal mortality, and obstetric difficulties.39
  [35] OCHA. Humanitarian Response Plan Yemen 2018. New York; 2018.
4. Women and girls bear the disproportionate brunt of obstacles caused by protracted displacement, including lack of access to services and civil documentation. An estimated 76 per cent of IDPs and IDP returnees are women and children. Among female-headed IDP and host community households, nearly 21 per cent are headed by females below the age of 18. [36]
  [36] OCHA. Humanitarian Response Plan Yemen 2018. New York; 2018.
5. Escalating conflict and forced movement of populations continue to create risks and instances of sexual and gender-based violence (GBV), including sexual exploitation and abuse. Focus group discussions have shown that women report psychological distress due to violence, fear for family members and fear of arrest or detention, whilst men report distress due to loss of livelihoods, restricted mobility and being forced to perform “women-specific roles”. These kinds of stresses can contribute to increased levels of domestic violence, placing more women at risk. [37]
  [37] OCHA. Humanitarian Response Plan Yemen 2018. New York; 2018.
6. Despite social norms which discourage reporting, there was still a 36 per cent rise in GBV access to services reported in 2017. According to the GBV Information Management System (IMS), up to September 2017, 37 per cent of these services related to psychological abuse, 27 per cent to physical assault, 24 per cent to denial of resources, 9 per cent to child marriage and 2 per cent to rape. Most cases (46 per cent) were reported by victims aged 26-40 years, with 21 per cent related to those under 18 years of age.[38]
  [38] OCHA. Humanitarian Response Plan Yemen 2018. New York; 2018.
7. While women and girls are by large more disadvantaged within Yemen, boys seem to suffer from a significantly high prevalence of acute malnutrition (wasting) and chronic malnutrition (stunting). Girls were also more likely than boys to be fed in accordance with recommended infant and young child safe feeding practices. More recently, as part of DFID third party monitoring female admissions were found to be higher than male admissions by 12%, with this differential holding across almost all Health Facilities, districts and governorates studied. As we would expect boys to be higher, this raises concerns that boys are going untreated. It is not entirely clear why this appears to be the case and so any programming will need to include a continued gender analysis and flexibility to respond to unique gendered needs.
Disability
The prevalence of disabilities as measured by the Yemen National Demographic Health Survey (2013) was three percent of household members, with mobility impairments and visual disorders being the most common disabilities. There is no difference between urban and rural areas; however, males are slightly more likely to have any disability than females (4% versus 3%). As expected, the reported prevalence of disability increases with age and reaches a maximum of 20% among people age 70 and older.
Figure 3: Distribution of Disabilities across Age groups

The figures from 2013, are the most recent, they estimate that approximately 885,000 people had some form of disability. However, this pre-dated the 2014 Washington Group Questions[39], and means Yemen does not have any disability statistics based on the latest new international best practices guidelines. Since the conflict started in 2015, this figure is likely to have risen. ICRC estimate 6,000 people have been left disabled – most as a result of a blast, mine, or gunshot wounds. According to the UN’s Humanitarian Needs Overview for 2018, Persons with Disabilities:
[39] The Washington Group (WG) Short Set is a set of questions designed to identify (in a census or survey format) people with a disability. http://www.washingtongroup-disability.com/washington-group-question-sets/short-set-of-disability-questions/
- Are more likely to risk losing access to health services
- Are more likely to have to pay someone to fetch water for them
- Are more likely to need protection services if they are already part of another vulnerable group (e.g. IDPs)
- Are less likely to have the right to basic and secondary education met.
This business case aims to improve the access to critical services for people with disabilities. This is likely to take the form of a regular assessment of services based on the Washington Group questions.
Conflict Sensitivity
1. Since late 2014, Yemen has been experiencing active conflict. The civil conflict began when the Houthis mounted a coup against Yemen’s transitional government in September 2014. It became internationalised in March 2015 when a Saudi-led Coalition (SLC) intervened in support of the Government of Yemen (GoY) to counter the alliance between the Houthis and forces loyal to former president Saleh. The Houthi-Saleh alliance broke down in early December 2017 following the assassination of former President Saleh by Houthi forces. Political talks are currently stalled, though the UN Special Envoy plans to reconvene the parties in September 2018. Short ceasefires have repeatedly broken down. Only a political solution will end the conflict. The UN reports that at least 5,200 civilians have been killed since March 2015. Overall (including combatants), 16,432 casualties have been reported and verified by UN OHCHR between 26 March 2015 and 10 May 2018.
2. Additionally, in Yemen, conflict over dwindling water supplies dates back decades, even before the ongoing civil war[40]. Today, Yemen is one of the most water-stressed countries in the world. Conditions are expected to worsen with factors including continuing mismanagement of water supply resources, poor choices in agriculture (e.g., water-intensive cultivation of the stimulant qat), and population growth[41] [42]. Given the wartime breakdown of the central state, water management is less effective or not enforced42. Water scarcity is also due in part to a shift from traditional rain harvesting to pumping groundwater. In 2009, a UN Food and Agriculture Organisation (FAO) report forecast that Yemen could be the first country to lose its groundwater resources completely; others predict that Sana’a, Yemen’s largest city, could run out of water within the decade[43] [44].
  [40] Douglas, Collin. 2016. A Storm Without Rain: Yemen, Water, Climate Change, and Conflict. The Center for Climate and Security. Accessed Aug. 23, 2017. https://climateandsecurity.org/2016/08/03/a-storm-without-rain-yemen-water-climate-change-and-conflict/.
  [41] Lichtenthaeler, Gerhard. 2010. “Water Conflict and Cooperation in Yemen.” Running Dry, Middle East Report. Accessed Oct. 27, 2017. Middle East Research and Information Project, Inc. http://www.jstor.org/stable/40660903.
  [42] Hettle, Natalie. “Water Wars in Yemen.” The Middle East Center Blog. Nov. 15, 2016. Accessed Aug. 23, 2017. https://mesc.osu.edu/blog/water-wars-yemen.
  [43] Whitehead, Fredericka. 2015. “Water scarcity in Yemen: the country's forgotten conflict.” The Guardian. Apr. 2. Accessed Aug. 23, 2017. https://www.theguardian.com/global-development-professionals-network/2015/apr/02/water-scarcity-yemen-conflict.
  [44] Abd Almohsen, Rehab. 2015. “Thousands Die in Yemen in Fights Over Water.” SciDevNet. Jun. 25. Accessed Aug. 23, 2017. http://www.scidev.net/index.cfm?originalUrl=global/water/news/water-death-yemen-conflict.html.
3. The current conflict has made the situation even worse; approximately 16 million people in Yemen lack clean drinking water with water scarcity rising rapidly throughout the country, caused by the mismanagement of water resources. Many of the public municipal water services no longer operate as public sector workers have not been paid salaries since the summer of 2016. Where they do, the water is not potable, increasing the reliance on unregulated, unsustainable and inefficient water trucking[45].
  [45] Humanitarian Response Plan 2018
4. Programming in this area must have a conflict sensitivity element in order to ensure activities do no inadvertently increase the levels of conflict at either a local or national level.
Terrorism and terrorist financing and fraud and corruption
There is a risk of terrorism and terrorist financing in Yemen as well as fraud and corruption. DFID will work so that the selected partners for this business case have in place robust policies and monitoring systems to detect report and mitigate the risks. Terrorist groups including Al-Qaeda in the Arab Peninsula and Daesh-Yemen are active in Yemen. Partners and all downstream partners are expected to make themselves aware of, and partners to sign compliance with, the relevant counter terrorist financing legislation. Due diligence and delivery chain mapping is undertaken on all partners to reduce risk and provide further assurance over the use of UK funds.

Appraisal Case
Options appraisal
Prior to the current crisis, the capacity of all partners delivering social services (government, development agencies, NGOs) in Yemen was limited and did not reach all parts of the country. The current political and conflict dynamics have exacerbated this problem with government health systems affected and only a limited number of humanitarian organisations still operational. Delivery of an ambitious programme in Yemen therefore requires working with a range of delivery partners. In addition, DFID Yemen’s experience to date, working with a number of NGO consortia and UN agencies, has provided valuable insights into the benefits of different delivery options.
In this appraisal, four delivery options have been considered:
Option 1: Do nothing on nutrition (counterfactual)
Option 2: Partnership with a coalition of NGOs
Option 3: Joint partnership with UNICEF, and WHO
Option 4: Partnership with UNICEF
Key criteria considered in assessing the strength of evidence for each option:
- Operational resilience
- Geographical reach and scale
- Sustainability and ability to work with government
- Proven delivery ability
- Efficiency of DFID programme management
	Option 1: Do nothing (base case):	Option 2: Partnership with consortium of NGOs	Option 3: / Partnership with UNICEF, WFP, and WHO	Option 4: Partnership with UNICEF
COSTS
Direct Costs	0	Up to £96 million	Up to £96 million	Up to £96 million
Indirect Costs	0	4 Full time staff	2 Full time staff	1.5 Full time staff
BENEFITS
Operational resilience	0	3	4	4
Geographical reach and scale	0	2	5	4
Sustainability and ability to work with government	0	2	4	4
Proven ability to deliver an integrated programme	0	2	2	4
Efficiency of DFID programme management	0	2	3	5
Total	0	11	18	21
The advantages and disadvantages are summarised against the 5 criteria in the table (scoring 1 – poor to 5- excellent).

Strength of evidence for each option:
Option 1: Do nothing on nutrition (counterfactual)
This case would see humanitarian needs increase related to a decline in nutrition, health and WASH service delivery and malnutrition grow. The likelihood of a significant deterioration including an increase of already high levels of malnutrition and an increased risk of famine would be higher.
Option 2: Partnership with a coalition of NGOs
DFID would fund a coalition of NGOs to deliver at a similar scale and ambition. This would require a competitive bid and for NGOs to either expand current consortiums or form new ones.
Advantages:
- Direct implementers with closer access to beneficiaries.
- Capitalise on the specific strengths of each partner and activities coordinated. Facilitate learning and innovation if sufficient time investment in this is possible.
- Reduce management costs at the programme level (compared with the UN), although this would have to be balanced against significantly increased administrative costs for DFID.
Disadvantages:
- The scale and reach of NGOs still operational in Yemen is relatively limited. They do not have the long-standing partnership with government systems and few are able to provide the scale of integrated health, nutrition and WASH needed for this programme.
- The NGOs do not have the same economies of scale as the UN.
- Increased administrative burden for DFID compared with partnering with a single agency. Partnership management and coordination would be complex and beyond current operating resources available.
- Requires a complex monitoring strategy, a particular challenge given the lack of a DFID presence in Yemen.
- Not an easy time to set up new partnerships particularly without DFID Yemen presence in Sana’a; this process would take time and cause delays in implementation at a time of critical need.
- Would potentially require a newly formed consortium which would take time to formulate with complex governance arrangements to be agreed by all partners.
Option 3: UNICEF, WFP, and WHO
DFID would engage partners in a multi-agency partnership with shared indicators of performance. We would incentivise agencies towards a coalition approach. For an active humanitarian response this would be the first time this has been done and an ambitious undertaking.

Advantages:
- Complementarity between agencies would allow advantages of specific strengths of each.
- Strong partnerships with government.
- Incentivise UN coordination.
- Expand the potential range of nutrition, health, food security, and WASH interventions.
- DFID already has a food security programme with WFP (food and cash/voucher support). Incentives could be placed within both programmes to stimulate collaboration.
Disadvantages
- Would increase the administrative burden for DFID compared with partnering with a single agency.
- The most direct nutrition-related health interventions can be delivered by UNICEF alone i.e. without an additional relationship with WHO.
- Will take a long time to set up and cause delays in implementation at a time of critical need.
- Not an easy time to set up new collaborative partnerships particularly without DFID Yemen presence in Sana’a.
Option 4: Partnership with UNICEF
DFID would continue to work bilaterally with UNICEF while incentivising the collaboration among other delivery partners. This would build upon the partnership that has existed since 2011.
Advantages:
- UNICEF is an established humanitarian and development actor with a track record in Yemen and the only agency able to operate at scale in the treatment of SAM in challenging circumstances.
- UNICEF has a strong partnership with the Ministry of Health and Population (MoPHP) in both Sana’a and Aden and record of supporting government health systems; it also works closely with NGOs to deliver services in hard to reach areas.
- UNICEF has close working relationships with WFP and WHO, as well as the MoPHP and has worked with them to establish a scale up plan for the Community based Management of Acute Malnutrition (CMAM) and to ensure coordination between the agencies.
- UNICEF has a mandate to protect children who are the group most vulnerable to malnutrition and to work across health, nutrition and WASH and the ability to deliver an integrated programme and provide coherence of approach.
- UNICEF has received large contributions from both the World Bank and the Kingdom of Saudi Arabia which we plan to strategically complement.
- Relationship with a single agency reduces the administrative burden placed on DFID Yemen.
- UNICEF has in place a third party monitoring programme which also monitors activities implemented through local government.
- Working through a single umbrella agency allows efficiencies in procurement, including for Ready to Use Therapeutic Food (RUTF) for under-nutrition treatment.
Disadvantages
- This approach means DFID is less closely linked to NGOs involved in implementing the programme.
- There is a UNICEF in country management cost of 11% and a board approved indirect cost of 8%.
Conclusion of options appraisal
Option 4 is considered the best and most appropriate option at the current time.
1. As humanitarian needs continue to escalate, with deterioration of social service delivery and rising malnutrition, Option 1 of taking no action is deemed inappropriate.
2. Option 2 has been rejected as there is limited evidence to suggest a consortium of NGOs could alone provide the specific integrated programme we are looking for at the speed, reach and scale needed.
3. The unproven delivery record of a collaborative programme between UNICEF, WHO and WFP, and the coordination already in place between the agencies on nutrition could lead to over complicating coordination and higher admin and management costs. There is therefore no added value of Option 3 over Option 4.
4. UNICEF have the ability to deliver nutrition, health, and WASH humanitarian service delivery nationwide; implement a more intensive community based approach to tackle malnutrition where there is greatest need; support institutional and system strengthening to support recovery and longer term improvements; and contribute to the generation of knowledge to improve programming.
Theory of Change of Option 4
1. This programme is part of a wider UK Government objective to avert famine in Yemen. DFID will provide up to £96.5 million over 3 years to address critical nutrition, health, water and sanitation needs while also improving the technical analysis and evidence informing the response[46].
  [46] Including the Maximising Quality of Scaling Up Nutrition (MQSUN), and Expert Advisory Call-Down Service (EACDS) on Strengthening Resilience and Response to Crises
2. DFID investments will be structured across three main outputs. These will use the lifesaving approach to immediate, and remedial needs as well as increase contextual understanding of the causes and consequences of malnutrition. The programme will maintain the ability to respond flexibly and adapt to changes in needs, access, and available funding:
- Immediate Actions - Critical Nutrition, Health, Water, Sanitation and Hygiene service delivery – providing lifesaving and improved quality of nutrition, health and wash services for affected populations. DFID will approach health and wash through a nutrition lens and complement these with a focus on protection for the most vulnerable.
- Remedial Actions - System strengthening and risk management – maintain and strengthening systems delivering nutrition, health and water and sanitation services at a sub-national level. It will also focus on managing risk better within planning and financing to improve the efficiency and effectiveness of the response.
- Increase contextual understanding - Knowledge and evidence generation – addressing the information and data gaps that exist in Yemen by focusing on improving the knowledge and evidence base to improve our understanding of the context (i.e. under 5 mortality), analytical products necessary for decision making (i.e. nutrition surveys). Hazard and risk analysis and early warning
1. The programme will primarily target the 107 high-priority districts considered at heightened risk of famine, as identified jointly by the WASH, Nutrition, Health, and Food Security and Agriculture clusters. As the situation in Yemen is rapidly evolving and uncertain, the programme will also maintain flexibility to work in any of the 333 districts for emergency response if/when the situation arises.
2. The exit strategy for this business case is dependent on a significant change in the operating environment such that peace allows the Government of Yemen to deliver these critical services.
Theory of Change– Integrated Nutrition programme adopting a life-cycle approach

1. Access to intervention locations remains open for UNICEF, partners and beneficiaries.
2. Coordination between social welfare and health sectors maintained
3. Supplies prices remain stable and supply importing remain viable.
4. Local authorities continue support to nutrition, health and WASH assistance both at national and sub-national levels.
5. UNICEF continues to have access and additional funding to maintain incentives for health workers
6. Local authorities granted the access to implement the nutrition assessments
Assumptions
The three outputs involve critical service delivery related to nutrition, health, water, sanitation and hygiene promotion with additional complementary vouchers and protection interventions related to access to treatment, case management of the most vulnerable and psychosocial support. Across these three outputs DFID would invest in the delivery of the following activities essential to maintaining services in Yemen.

Output 1: The first output focuses on critical nutrition, health, water, and sanitation service delivery, providing lifesaving and improved quality services for affected populations with a focus on the most vulnerable.
Output 1 - Critical Nutrition, Health, and WASH service delivery
Nutrition Services	Immediate Life-saving and core emergency programmes / Treatment of Malnutrition (wasting) – support the continued scale up of the treatment of Severe Acute Malnutrition (SAM) and the Community based Management of Acute Malnutrition (CMAM). / Increase the collaboration in the delivery of services with the World Food Programme (focused on the treatment of Moderate Acute Malnutrition) and World Health Organisation (focused on for delivery of health services). / Infant and Young child feeding – support for healthy child feeding practices, phasing in as part of this support Early Child Development activities in the management of malnutrition and infant feeding. / Prevention and building resilience / Pilot an adolescent nutrition anaemia prevention program through weekly Iron and Folic Acid supplementation.
Health services	Immediate Life-saving / Immunisation - support and facilitate routine immunisation and supplementary vaccination (campaigns), providing urgent support for cold chains. / Infectious disease control - Screening and treatment of childhood illness and remain responsive to significant disease outbreaks. / Reproductive health services in primary health care facilities (Minimum Initial Service Package (MISP) – Including family planning, antenatal, delivery, postnatal care, and support for midwives. / Emergency new born care at all levels of health system (community to tertiary care). / Expand mental health services support to the most affected populations – link to protection. / Prevention and building resilience / Scale the provision of mobile health teams to provide additional coverage. / Provision of the Minimum primary health care package in primary health care facilities.
Water, Sanitation, and Hygiene services	Immediate Life-saving – averting and mitigating mortality and morbidity / Urgent provision of hygiene supplies, such as soap, water treatment and menstrual hygiene items targeted based on risks related to malnutrition and disease outbreaks. / Urgent short-term water supply (e.g. via water trucking) with a focus on the most vulnerable, (IDPs and conflict affected). / Urgent water and sanitation system maintenance. / Hygiene promotion / behaviour change including focus on menstrual hygiene. / Increase the accessibility of services for disabled populations. / Prevention and building resilience / Explore market solutions for access to water, sanitation and hygiene supplies. / Support of innovative approach for rural areas (solar systems). / Water, sanitation and hygiene services in rural Schools. / Work with authorities to encourage sustainable water management.
Social protection	Immediate Life-saving / Voucher system to encourage health seeking behaviour, enable access and ensure accessibility to those with disabilities – vouchers would be prioritised for severe acute malnourished (SAM) cases, sexual reproductive health needs, and protection cases (including people with disabilities, and cases of gender based violence).
Protection	Immediate Life-saving / Psychosocial support provided to children suffering from SAM cases complements mental health support provided. / Across all areas support and assess interventions against conflict sensitivity and critical protection guidelines (protection, gender based violence, child protection and persons with disabilities).

1. The two new elements to this programme are the social protection and protection elements. The former focused on securing access for SAM treatment and protection cases, based on a voucher system currently operating for pregnant women for antenatal, delivery and postnatal access. The latter, protection element is focused on improving the case management and psychosocial wellbeing of SAM cases while they receive treatment.
2. Output 2: The second output relates to the strengthening of services, systems, and risk management. The strengthening of service delivery will build upon the investments DFID has made to date in Yemen. Increasing the quality and services related to nutrition, health, water, sanitation, and hygiene at a sub-national level (planning, prioritisation and governance of services with a strong focus on training). Additionally, it will include a focus on managing risk better within planning and financing to improve the efficiency and effectiveness of the response.

Output 2 - System Strengthening and Risk Management
Systems Strengthening	Core service delivery / Nutrition, Health and WASH / Increase the quality of care for management of acute malnutrition, management of common childhood illnesses, for routine and supplemental vaccination and maternal and new-born care both at community and facility levels. / Supply and Logistics: Improve the supply and logistics management capacities at health facility, district, governorate and central level. Introduce mechanism for end user monitoring of supply items. / Monitoring and managing water and sanitation service delivery to the most vulnerable including Water quality safety.
	Preserving service delivery / Capacity strengthening – focusing on the management, supervision and monitoring capacities of the district and governorate health authorities, General Authority of Rural Water Supply, local water corporations and civil society. / Ensure availability of a critical mass of trainers at central, governorate and district level for the key programmes to bolster and maintain availability of adequate numbers of service providers. / Establish a career path for Community Health Volunteers, Community Health Workers, Supervisors and various cadres of health facility based workers. / Improve the capacity of local government and civil society partners to effectively implement behaviour change interventions. / Ensure the quality of care received via health facilities participating in the voucher system. / Improve case management and referrals ensuring the full integration of services for the most vulnerable.(severe acute malnutrition, reproductive health, and protection cases) across sectors (nutrition, health and wash) and referrals to other services (e.g. food distribution)
Systems Strengthening (continued)	Coordination, information management, supervision and monitoring / Management Information System: Support timely flow of high quality data from service delivery levels to district and governorates levels. Equip facility, district and governorate levels in use of data for action and decision making. / Increase the capacity, quality of the data and analysis of the UNICEF led clusters (WASH and Nutrition) and offer additional support to the health cluster. / With the health cluster - improve data collection and analytical capacity of public health information management systems. / Support the Scaling Up Nutrition (SUN) activities in Yemen – ensuring that the development related nutrition interventions are supported in the country.
Risk Management	Managing risk better / Managing risk better means that UNICEF will work with other key stakeholders to identify risks, formulate joint plans and identify investments that improve the efficiency and effectiveness of the response. / To do this they will need to improve the quality of the risk analysis underpinning decision making. / Convene and support through clusters key partners to identify enabling investments to increase the efficiency and effectiveness of the response. / Provide an analysis detailing the benefits and costs of investments that mitigate risk or improve the efficiency of the response. / Explore and identify funding sources for these investments (i.e. Green climate fund).

1. The risk management element is an entirely new, but necessary area of focus. Yemen is considered a protracted crisis where it is essential partners maintain lifesaving services and where possible increase their capacity. However it is also essential that within planning, they anticipate future risks that could create new or exacerbate needs and hinder services and seek financing for these. As such DFID will leverage its funding in order to secure additional, complementary funding from other sources by incentivising agencies to collaborate, improving the quality of plans and getting them to identify additional funding sources for investments.
2. DFID has already been engaged in this area with UNICEF, with the threat of cholera and a potential third wave outbreak DFID sought to provide partners in country with risk assessments that they could use to plan against (see text box below).

Cholera Response 2018 / Yemen suffered the worst cholera outbreak in living memory in 2017 with over 1.1 million suspected cases and over 2,300 associated deaths. / Timing of response is crucial. Early prevention, detection and treatment substantially reduce case fatality rates. With regard to prevention measures, to make a substantial difference to the course of an epidemic, the response needs to be ahead of the epidemic curve. / Ahead of the 2018 raining season, DFID worked with partners to refine the risk context by facilitating the access to risk assessments and forecasts. DFID is working with international partners - including the Met Office, the University of West Virginia, the University of Maryland and NASA – in an attempt to save lives by predicting likely cholera hotspots. These assessments are shared with UN humanitarian agencies on the ground in Yemen so that they can respond in advance to cholera surges.. / Map 1: June 2018 Map 2: July 2018 / Responding quickly enough to every new outbreak in every new location is very difficult – and can only be achieved through agile and mobile rapid response teams with a very high level of organisation, using recently gathered data, risk assessment and forecasting as a basis for targeted interventions. Preparedness is crucial to effective response – without having such systems, roles and capacities pre-established, the response is always likely to lag behind the epidemic curve. [47]
[47] Source UNICEF Real Time evaluation Yemen Cholera Response 2017 (unpublished)

Output 3: The third output is part of a wider DFID effort to increase the quality of the data and analysis underpinning the response. As mentioned above the data and analysis is largely out of date, where Yemen is often cited as one of the responses where data and analysis prevents us from knowing if the interventions we are pursuing are having the desired effect. This output’s primary objective is to focus on improving the knowledge and evidence base that improves our understanding of the context (i.e. under 5 mortality), and analytical products necessary for decision making (i.e. nutrition surveys).

Output 3 - Knowledge and evidence generation
Knowledge and evidence generation	Strategic information, analysis, data and reports generated to assess and adapt strategies, including: / Continued implementation of Standardised Monitoring of Relief and Transition (SMART) surveys to monitor changes in levels of under-nutrition. / Coverage surveys to look at the status of service delivery. / Knowledge Attitude and Practice Surveys to monitor changes in behaviour, and vaccine confidence. / Mortality monitoring – assess U5 mortality and work with WHO on population estimates. / Analysis of disability access to services using the Washington group questions. / Analysis of medium to long term risks – i.e. water security.

 Indicative expected results
  1. 2,972,000 under-five children screened and 70,000 treated for malnutrition
  2. 3.25 million under-five children treated for childhood illnesses
  3. 1,373,400 individuals in urban settings, 186,391 in rural settings and 818,154 internally displaced persons (IDPs) and host communities benefitting from improved water and sanitation services
  4. 818,154 affected individuals with access to emergency WASH (clean water, basic sanitation and hygiene materials)
  5. 800,000 supported with sexual reproductive health programming including 302,800 family planning, 292,000 antenatal check-ups, 117,200 deliveries, and 88,000 postnatal visits
  6. 500,000 children between 9-18 years benefit from targeted anaemia prevention
  7. 108,000 vulnerable children, women and including 21,600 people with disabilities reached through health access voucher programme
  8. 125,000 of girls and boys received psychosocial services in health facilities and its catchment areas
  9. 70,000 provided with early children development support

Integration with other programmes and support
DFID Yemen bilateral portfolio
These interventions do not happen in isolation however and rely significantly on a portfolio approach with other DFID investments. In particular, this business case will complement DFID programming with the following partners:
1. World Food Programme - Food security, blanket supplementary feeding, targeted supplementary feeding (treatment for moderate acute malnutrition and services for pregnant and lactating women, and cash programming)
2. NGOs – Providing critical support in targeted areas including areas related to this business case, nutrition, health, WASH, and cash programming
3. UNHCR / IOM – displacement, and protection monitoring and providing overall coordination for protection actors in country
4. Social Fund for Development – providing long term development support to Yemen including small scale construction such as wells
5. Pooled fund – providing funding for nutrition and related sectors
6. OCHA – overall inter-cluster coordination and coordination of humanitarian action in Yemen
All business cases complement one another, each serving their own purpose and ensuring DFID Yemen can meet its Business Plan objectives.
Wider DFID investment
1. World Bank made a significant International Development Assistance contribution to Yemen totalling 1.3 billion USD in 2016 with a specific focus on delivering basic services through supporting the maintenance and development of state service providers. Whilst some portion of this funding is channelled through the Yemen Humanitarian Pooled Fund, a majority is delivered outside of it. The flagship programme with an explicit nutrition focus is the Emergency Health and Nutrition Project delivered through UNICEF and the World Health Organisation.
2. At a higher level it draws on DFID’s donor influence within the World Bank board, Central Emergency Response Fund (CERF) and significant contributions to GAVI (25% of vaccines) to prioritise Yemen.
How DFID’s funding complements UNICEF’s current funding
1. UNICEF receives funding from a diverse range of donors, including the World Bank, GAVI, ECHO, EU, OFDA, Japan and several others. Despite this UNICEF’s Humanitarian Action for Children (HAC) appeal for 2018 is only 55% funded. The overall work plan for 2018 is funded at a slightly lower level, as it includes ‘humanitarian-plus’ elements as well. There is a clear need for DFID support, with DFID having been and continuing to be one of the most important partners to work in these sectors in Yemen.
2. Other funding sources that UNICEF is operating with are earmarked as follows:
- World Bank funds under the original Emergency Health and Nutrition Project (EHNP) are dedicated to ‘system preservation’ efforts including support to over 2000 health facilities for operational costs, HR support, furniture, equipment supplies for provision of the minimum service package (MSP), support to District and Governorates Health offices (DHOs and GHOs) for integrated supportive supervisions, etc. It does have flexibility to be used for other activities when funding gaps exist.
  - World Bank funds under “Additional Financing 1” are for support to food distribution and acute malnutrition.
  - World Bank funds under “Additional Financing 2” are earmarked for Cholera response activities.
- GAVI funds are marked for procurement of new and underutilised vaccines and health system strengthening (HSS) initiatives linked to Immunisation, i.e. cold chain equipment optimisation and other activities needed to maintain immunisation coverage.
- EU funds are earmarked for establishment of a CHWs network.
- ECHO and OFDA funds contribute only to the humanitarian response.
DFID’s funding would complement these funding sources. We would aim to leverage our funding to increase the quality and capacity of UNICEF to deliver at scale.
Achieving Value for Money (VfM)
DFID uses the ‘4 Es’ framework (economy, efficiency, effectiveness and equity) to ensure that UK aid maximises its impact. The assessment (below) shows that the proposed option demonstrates Value for Money. The programme’s complexity requires ongoing monitoring and analysis of how change is being achieved.
Economy - Inputs of the appropriate quality at the right price
1. DFID’s contribution will include an indirect cost recovery charge of 8% (a standard board approved rate). A further 11.7% in country management cost will be applied which covers operations (6.5%), M&E (1.3%), emergency and field operations (0.9%) and security costs (2.5%). In addition direct staff costs total 6.86% of the total budget. The key cost drivers are supplies, field logistics and human resources. UNICEF will be required to report back on cost drivers and VFM indicators at quarterly meetings and country management costs will remain under review to ensure they remain appropriate in an evolving context.
2. Where DFID utilises additional framework agreements to bolster the analytical capacity of the response, we will use the pre-agreed / approved rates. These will be short and focused pieces of work aimed at improving the overall contextual understanding.
Efficiency - How well are inputs converted into outputs?
Effectiveness - How well are outputs having the intended effect?
DFID Yemen’s previous funding to UNICEF spanned important periods of escalation of the conflict and deterioration of health and nutrition in Yemen, including the beginning of the cholera outbreak and the international attention to the risk of famine. As such implementation throughout this turbulent period, has contributed to significant lessons about the effectiveness of the programme in a complex emergency context. The following lessons will be taken forward in this new programme to ensure effectiveness throughout this intervention:
- Investment in preventive services as well as traditional development-context health and nutrition interventions, rather than limiting the support to the emergency/humanitarian response only.
- Integration and multi-sectoral programmes and interventions at both community and health facility levels. This includes the importance of expanding availability of integrated health and nutrition services in the second and third level of coverage through several modalities, including Community Health Volunteers (CHV), Community Health Workers (CHW), mobile teams and integrated outreach services, to reach vulnerable and rural populations that cannot access health facilities due to high transportation costs and social exclusion considerations. This also includes ensuring Internally Displaced People (IDPs) and other conflict-affected populations have access to essential routine health and nutrition services, in addition to humanitarian support.
- Strengthening monitoring and reporting systems at a sub-national level plays an important role in improving quality of services and performance indicators. Centrally-led monitoring and reporting are not sufficient, especially as project interventions move to more decentralised levels.
- All donors supporting Yemen must work together to support the maintenance and strengthening of the health and nutrition systems in Yemen and prevent their collapse. It is critical to support a combination of public-sector actors, civil society organisations, and local NGOs; and for international NGOs and UN agencies to focus their efforts on building the capacity of those who will remain in Yemen when the crisis ends and international support declines. While there are some risks associated with this approach, many mechanisms have been established to control and mitigate these risks, and there is proof that this approach is feasible within the current context. In the long-run this approach will be the most effective towards ensuring sustainability through consistent and continuously maintained national and local systems.

Equity
UNICEF works to benefit all Yemenis. As a UN agency, UNICEF has no political affiliation and has consolidated its reputation as a development agency working to benefit all vulnerable individuals and communities irrespective of their political, territorial or sectarian affiliations. Beneficiary needs are the guiding factors for responses. UNICEF interventions will also target youth and women since women and girls in conflict affected areas are the most vulnerable group. This business case also aims to improve the access to critical services for people with disabilities. This is likely to take the form of a regular assessment of services based on the Washington Group questions.

Summary Value for Money Statement for the preferred option

The deteriorating political, economic and security context in Yemen has had a significant impact on the nature of VFM considerations. Over the life of the project we expect that UNICEF operations will continue to experience rising input costs. However we judge that it is VfM to act now, as this programme will help to build resilience in the face of the humanitarian crisis.

Going forward we will continue to monitor VFM through the 4E’s framework as part of the project cycle management processes. Drawing from DFID’s guidance, VfM should be measured at all points in the results chain from input level up to outcome and impact. In order to monitor value for money for the programme, UNICEF will report on the following details, alongside log frame reporting.

Value for money indicators	Benchmark (as at 31 December 2017)	VFM If	Source
Economy
Cost of Community based Management of Acute Malnutrition (CMAM) training course, per attendee	$540	Does not increase more than cost of fuel and other key inputs.	UNICEF budget
Unit cost of plumpynut (brand name for a Ready-to Use Therapeutic Food or RUTF)	£37.12 per carton for treatment of one child	Does not increase more than market rate (procured internationally)	UNICEF
Cost of hygiene kit	Basic hygiene kit: $ 50 / Consumable hygiene kit: $ 6	Does not increase more than market rate (procured locally)	UNICEF budget
Cost of water tank	$203	Does not increase more than the market rate	UNICEF budget
Efficiency
Administration costs to total number of beneficiaries	Total ‘administration costs’ (ie recovery cost to date) = USD 3,291,105 (GBP 2,511,843). Total number of beneficiaries = 4,886,708	Low and kept low
Number of days to deliver health and nutrition supplies from Djibouti to Yemen	10 days from Djibouti to Hodeidah / 9 days from Djibouti to Aden	Does not increase	UNICEF
Availability of plumpynut at facility level (stockouts)	All health facilities have (TBC) days/volume supplies in store		Collected from health facilities through monthly CMAM report, SMS, TPM and field visits.
Cost Effectiveness – cost per beneficiary
Cost of delivering CMAM per beneficiary	£151	No more than 10% increase	From cluster
Cost per beneficiary of providing a package of child, maternal health and nutrition interventions through the integrated outreach.	£7.23	No more than 10% increase	UNICEF budget
Cost of CLTS in one village (includes CLTS and water supply incentive to villages achieving open-defecation-free status)	$14,000	No more than 10% increase	UNICEF budget
Cost of Misoprostol for treatment of post-partum haemorrhage	$ 4.90 per woman	Does not increase more than market rate	UNICEF

In addition to regular monitoring of the above indicators UNICEF water, sanitation and hygiene promotion will engage in a return on investment analysis to determine VfM and efficiency of significant investments (such as solar-powered water supply systems).
Commercial Case
1. We will formulise our funding through a Contribution Arrangement with UNICEF. The arrangement is governed by the framework agreement between DFID and UNICEF. This funding will be used for supplies, commodities, sub activities and staff related costs relating to the outputs above. Examples include micronutrient supplementation, support to vaccine and cold chain logistic systems (procurement and transportation), rehabilitation and installation of solar-powered water supply systems, procurement and distribution of essential WASH supplies, provision of psychosocial support to children, specialist and other personnel related costs etc. A detailed logframe with clear results and a budget with full breakdown of costs will be submitted by UNICEF before a funding arrangement is put in place.
2. In addition, there will be an option through this business case to draw down on DFID framework agreements to seek expertise to complement the overall understanding of the context and assess the appropriateness of the strategy being employed.
3. To ensure the sustainability of this programme, and deliver on our Grand Bargain commitments, UNICEF will work through existing health systems where possible. UK funding will not go through government or defacto authority systems. UNICEF will partner with subnational level health systems such as the Ministry of Public Health Governorate Health Offices (GHOs), General Authority of Rural Water Supply Projects (GARWSP), Ministry of Planning and Internal Cooperation (MoPIC). No UK funds will be put through these organisations. Instead UNICEF will provide incentive payments to health care workers so that there are medical staff to deliver services (most healthcare workers have not received their public sector salaries in well over 18 months). UNICEF will also provide supplies such as Ready to Use Therapeutic Food and medicines. UNICEF will also contract suppliers for the provision of fuel so that generators can pump clean water.
4. At every stage in the process UNICEF will be responsible for carrying out the necessary due diligence requirements to ensure funds or resources are not misused or diverted. Each organisation, including GHOs, will have an individual micro-assessment which assesses the controls in place to deliver the required activities and monitored through the harmonised approach to cash transfers (para 124). UNICEF has a robust system of controls which has been reviewed by DFID, and we will continue to work closely with UNICEF to ensure the controls remain viable in an evolving context. Accountability would fall to UNICEF for systematic monitoring, and obtaining beneficiary feedback while DFID will use its third party monitoring to carry out spot checks.
5. Given the changing situation in Yemen including the access restrictions in certain districts, there will be a need to ensure we can adapt and that flexibility is built into the approach to ensure funds can be reassigned to other priority districts if needed. The Contribution Arrangement will include wording to ensure adaptability and flexibility of the programme. Requested changes to the programme will be considered and approved by the SRO to ensure need remains prioritised and ensure the changes remain within the scope of the programme.
UNICEF’s capability and capacity to deliver
1. UNICEF has been an important partner for DFID in Yemen over recent years and has a wealth of experience working in Yemen in the areas of nutrition, health, water and sanitation. UNICEF is the cluster lead for Education, Nutrition, WASH and Child Protection further demonstrating the importance of their role in the country.
2. Our previous integrated nutrition, health and WASH programme with UNICEF ended on 31 March 2018. The project completion review scored an A confirming that the programme met expectations.
3. During our previous programme an independent monitoring study concluded in early 2018. This study verified results reported under UNICEF’s work on severely acute malnourished children and water and sanitation. The study found a number of positives but also some areas needing improvement including accuracy of record keeping on SAM, availability of supplies, beneficiary targeting to ensure girls are sufficiently included in SAM treatment and ensuring methodology is comparable with other implementing partners, frequency of WASH interventions and other household level interventions, quality of WASH interventions, and sustainability of WASH projects over life span of programme.  We will continue to work with UNICEF on the findings of this study and ensure through this new programme actions are in place to address these issues. We will consider funding options should UNICEF fail to implement improvements. (See Lessons learned section para 42 above).
4. A due diligence assessment in 2016 on UNICEF Yemen made a number of recommendations including on risk, reporting of aid diversion, staffing/resources, third party monitoring and results reporting, warehouse management and downstream partners. UNICEF has made a number of improvements to address the recommendations from this due diligence assessment including ensuring that the issue of misuse of funds, aid diversion and fraud is discussed at quarterly meetings and ensuring on-going fraud and corruption training is taking place. These practices along with other areas identified in the due diligence assessment will continue to be reviewed and discussed with UNICEF on a regular basis. Where fraud is reported, these reports will be expedited and investigated by both the DFID Yemen team and DFID fraud unit.
5. This programme will provide funding for three UNICEF international staff based in Sana’a and one based in Ibb and a further 33 national staff across a number of field offices. The table below sets out staffing numbers broken down by sector.
Position	International / National	Location	Qty
Health and Nutrition
Health and nutrition Chief (P5)	International	Sanaa	1
Health and Nutrition Specialist (P3)	National	Ibb	1
Health Officer	National	Field Offices	3
Health Officer	National	Central/Sana’a	1
MNH Officer	National	Central/Sana’a	1
Nutrition Specialist	National	Sanaa	1
Health and Nutrition Officer	National	Field Offices	3
Health and Nutrition Specialist	National	Field Offices	3
Health and Nutrition Officer	National	Field Offices	5
WASH
WASH Specialist (P3)	International	Sanaa	1
WASH Officers	National	Field Offices	3
Child Protection
NOC	National	Sanaa	1
NOB	National	Field Offices	5
C4D
C4D Officer	National	Field Offices	5
C4D Officer	National	Sanaa	1
C4D Specialist	International	Sanaa	1

1. Staffing numbers based in Yemen gives DFID confidence that they have the resources to deliver, but this continues to be kept under review to ensure any reduction in staff numbers due to the evolving security situation does not significantly impact on the delivery of the programme.
2. UNICEF Yemen has a business continuity plan in place, which provides guidance on how to keep operations running if international staffing presence in Yemen reduces due to a deteriorating security situation. If international staff left Yemen, they would still continue working remotely, and each staff member would have a designated in-charge national member of staff to cover for in-country needs.
Procurement capability
1. Procurement of all goods and services associated with the programme will be done by UNICEF. UNICEF has a strong track record of delivery, consistently being assessed by DFID Yemen as A and A+ in annual reviews. It has a good field presence in Yemen, including during the current conflict where its delivery has included a £46 million DFID programme between 2016-2018. UNICEF delivered a £56.7 million humanitarian/development programme for DFID between 2012-2016 and a £6 million humanitarian programme in 2011. These provided a multi-sectoral response across water and sanitation (WASH), nutrition, health, education and child protection, meeting targets as planned.
2. There are checks and balances built into the system; an international member of staff heads the supply unit in each country, including Yemen. There is an audit every two to three years and an internal committee, headed by the Operations Chief, oversees procurement. UNICEF uses the following three types of procurement:
Procurement of supplies (e.g. Ready to Use Therapeutic Food (RUTF), medicines, supplements, medical kits and WASH products)
1. All essential supplies will be procured either internationally through UNICEF’s supply division in Copenhagen, regionally through UNICEF’s office in Amman or through local procurement services as per the globally agreed international standards and transparent rules and regulations. All transactions will be done in the ‘SAP system’[48], which all donors will have full access to.
  [48] Accounting software - SAP is an ERP (Enterprise Resource Planning) software by the same name of the company.
2. UNICEF will facilitate all related logistics and will ensure timely delivery to all beneficiaries’ sites through the government MoPHP (at a sub-national level) and NGOs partners’ logistic and warehousing network, or as a last resort during emergencies, UNICEF’s own logistic system. Consumable supplies such as therapeutic feeding, medicines, and hygiene kits will be monitored closely through UNICEF field offices, implementing partners’ reports as well as joint and spot check field visits to ensure appropriate utilisation and no disruption in the supply pipeline.
3. Once programme supplies arrive at the port of entry (usually Hodeidah and Aden seaports, or to the airport), UNICEF will facilitate the release, distribution and/ or emergency pre-positioning of these supplies through Long-term Arrangements (LTAs) with local contractors who have been selected through competitive bidding. Then programme staff in collaboration with the respective technical counterparts in the government and NGO partners will develop the distribution plan and will oversee the distribution process until these supplies reach the beneficiary sites.
Institutional contracts supply of fuel to Local Water Corporations and Cleaning Funds
As part of UNICEF’s urban WASH work they have a tripartite agreement between UNICEF, Local Water Cooperation / Cleaning Funds and Yemen Petroleum Company. This agreement has carried forward from the old programme and has enabled the procurement of fuel at official rates (YR140/litre in 2015) compared to unofficial market rates (up to YR500/litre in 2015). The fuel supplies Local Water Corporations and Cleaning Funds for water supply systems and solid waste management. Furthermore, UNICEF also has a service level agreement (SLA) with WFP which provides procurement and logistic support on fuel delivery (also DFID funded). This modality addresses the risk mitigation, particularly for large scale procurement as well at the time of the import restrictions in 2017 based on our learnings and other similar incidents.
Procurement of services to support programme implementation (e.g. technical assistance and expertise related to programme operations, research, monitoring and evaluation)

These services will be procured through a competitive process in accordance with UNICEF standard procurement principles and procedures. On the basis of previous procurement of these types of services, UNICEF report there is capacity to respond to this demand, and that local firms can offer good value for money. However, UNICEF will recruit individuals and firms internationally where required.
Procurement through NGOs
As part of UNICEF’s procurement guidelines, procurement can be carried out through micro-assessed (low risk) NGOs, provided they have the capacity to deliver goods and services within the quality required by UNICEF. Furthermore, NGOs can conduct procurement through Programme Cooperation Agreements (PCA). NGOs’ procurement policies are checked by UNICEF. However, NGOs are not allowed to undertake any procurement for nutrition or health supplies given the sensitivity of those items and to ensure a consistent standard of quality. They may procure WASH supplies through PCAs if needed, but it is anticipated these will be lower value supplies (i.e. under $2000). However, for some international NGO’s with whom UNICEF have a global agreement, such a ceiling does not apply on procurement of supplies e.g. Oxfam.
Procurement through government channels
UNICEF procures goods and services from government agencies when there is a strong cost effectiveness argument to do so, for example access to government networks and infrastructure which enables UNICEF to reach more beneficiaries over a wider coverage. As set out above, UNICEF entered into a tripartite agreement with the Local Water Corporation and Yemen Petroleum Company following the start of the crisis in 2015. The Yemen Petroleum Company were the only organisation who could provide and deliver fuel at governorate and district levels to ensure the provision of water to the greatest proportion of the population. UNICEF technical teams participate in all stages to oversee the quality of the services as per agreed standard specifications.
Administration costs
1. UNICEF’s direct management cost in Yemen is 11.7% which covers operations, monitoring and evaluation, emergency and field operations, external communications and security costs. In addition, direct staffing costs total 6.86% of the budget. A further 8% indirect cost recovery rate is applied for the UNICEF HQ in New York. This cost is agreed through the framework agreement between DFID and UNICEF. This indirect cost covers the coordination of partners; procurement of services; payments to contractors; monitoring, review and oversight; and financial reporting and audits and is comparable to costs in other countries with similar security situations.
2. DFID will monitor direct management cost with a view to identifying any potential reductions. The current security situation in Yemen results in a higher than normal management cost for operations. We will also work with UNICEF to determine if there are other areas of the intervention where costs could be reduced.

Monitoring Progress
1. DFID will monitor progress against the outputs of this intervention through regular reviews of the logframe which accompanies this business case. Access to a donor portal providing real-time data will help to conduct these reviews. DFID will also hold regular discussions (monthly) as well as formal progress meetings (quarterly progress checks and programme reviews twice a year) to discuss progress and challenge any areas of under-performance.
2. UNICEF monitors progress of delivery partners through the Harmonised Approach to Cash Transfers to Implementing Partners (IPs). Assurance activities help to determine where funds transferred to partners were used for the intended purpose and in accordance with the agreed work plan. The level of checks undertaken on IPs is determined by the outcome of micro-assessments undertaken on each IP. Micro-assessments are completed by an independent body on any partner spending over $100,000 of UNICEF funds. The assessment includes a review the partners’ financial management capacity. Assurance activities on each IP include programmatic visits to obtain evidence on the status of programme implementation and review progress, spot checks to review financial records and obtain reasonable assurance that amounts reported by IPs are accurate and audits for all IPs receiving over $500,000 with a special audit being conducted where signification issues/concerns are found. DFID will also have access to UNICEF third party monitoring reports. We will review these reports and raise any concerns with UNICEF to ensure they are being addressed.
Visibility throughout supply chain and managing risk
1. We will work with UNICEF to ensure a detailed and up to date delivery chain map is maintained, which clearly sets out which partners UNICEF will engage and how much funds are provided to each partner. This delivery chain will help to clarify the different roles of partners in Nutrition, Health, water, sanitation, and hygiene promotion interventions etc. It will also be used as a tool to identify risks including potential fraud weak spots to ensure the control environment remains adequate.
2. DFID will work with UNICEF to put in place a system that manages how funds would be utilised. This would involve delivering resources or supplies to points of need within the system and being able to track them down to beneficiaries. Accountability would fall to UNICEF for systematic monitoring, and obtaining beneficiary feedback while DFID will use its third party monitoring to carry out spot checks.
3. DFID will continue to work with UNICEF throughout this intervention to ensure greater collaboration in humanitarian efforts across the various UN partners and beyond ensuring greater efficiency in delivery of humanitarian assistance in Yemen.
Financial Case
Overview of costs
1. DFID will provide up to £96.5 million to UNICEF to deliver this programme over the next three years. £78 million will be planned and budgeted over three years, with an additional £500,000 for drawing down on DFID framework agreements: Expert Advisory Call-Down Service (EACDS) on Strengthening Resilience and Response to Crises; and the Maximising Quality of Scaling Up Nutrition (MQSUN), initiative. A further £18 million flexibility built in to enable DFID Yemen and UNICEF to scale up and respond rapidly to anticipated spikes in need eg outbreaks in disease. All funds will come from DFID Yemen’s resource allocation (RDEL). DFID Yemen will explore whether CDEL budget should be used from the UK International Climate Finance and the Green Climate Fund. 100% of funding for this programme will be ODA eligible.
2. The initial contribution agreement will be for £78m over three years. Flexible funding will be activated on a needs only basis. After discussions with DFID, UNICEF will present DFID with an immediate response proposal. This will be reviewed by the SRO and assessed based on critical need, the wider humanitarian response, and to ensure that the activities fit within the scope of this business case. The SRO will seek financial assurances this can be funded by DFID’s resource allocation, either through a reprioritisation within our existing allocation or additional crisis reserve funds if applicable. On agreement with the Head of Office and the Finance Manager that funds can be reprioritised, the Contribution Agreement will be amended to accommodate the agreed flexible funding. Building in flexibility follows DFID’s best practice and is also a crucial risk mitigation factor in managing DFID Yemen’s humanitarian portfolio.
3. DFID may additionally utilise framework agreements in order to purchase up to £500k of analytical capacity to complement the overall understanding of the context and assess the appropriateness of the strategy being employed.
4. To deliver this programme DFID will require 50% of a full time programme manager and 50% of a full time humanitarian advisor. The programme team will also draw on expertise from cross cutting advisers in DFID Yemen and health and nutrition specialists in DFID. These costs will come from DFID’s total operating costs and have been factored into the workforce planning and budgets.
Programme cost profiling
Year	2018/19 / (£m)		2019/20 / (£m)				2020/21 / (£m)	2021/22 / (£m)	Total / (£m)
Quarter	Q3	Q4	Q1	Q2	Q3	Q4	Q1-4	Q1-2
Pre-planned activities	14	14	5	5	5	5	20	10	78
Flexible response to spikes in need / (estimate)	-	-	7				7	4	18
Analytical contracts		0.1	0.2				0.1	0.1	0.5
Total	14	14.1	5	5	12.2	5	27.1	14.1	96.5

1. It is expected that DFID will make three prepayments to UNICEF per year to cover activities and supply purchases for the following four month period. Payments will be made where there is a clear need and evidence provided that the previous disbursal has been largely utilised – see reporting.
2. UNICEF has requested the immediate disbursal of year one’s allocation, £28 million, in order to facilitate timely procurement of services and supplies for the interventions included in the business case. The procurement of pre-qualified/ high quality medical products, nutrition supplements, and water and sanitation supplies is imperative for ensuring both an effective humanitarian response that saves lives and the ability to continue to scale to address malnutrition. As procurement of these supplies and arrival in country may take time due to the complex situation in Yemen, UNICEF needs to start this process at the earliest stage of the programme implementation.
3. £28m will be disbursed to UNICEF in 2018/19 with the remainder expected to be disbursed evenly over the remaining two and half years, in line with need. The flexible £18m will be drawn upon as described above and is estimated based on analysis of passed trends.
Monitoring, reporting & accounting for funds
1. Financial reports will be submitted with each payment request setting out contributions made as well as expenditure against these contributions and any unspent balance from the previous contribution. Forecasts will be submitted with each payment request setting out expected expenditure at a minimum for the next four month period. Each payment request will be reviewed alongside forecasts and the expenditure reports to ensure funding is not paid in advance of need.
2. In addition, UNICEF will be expected to submit Third Party Monitoring reports along with payment requests which will provide additional reassurance on progress as well as set out challenges faced. Audit provisions for UNICEF are set out in the overarching framework agreement between DFID and UNICEF. UNICEF will provide audit reports under the principles of UN’s single audit framework, which provides a sufficient level of general assurance. DFID will scrutinise these reports ensuring accuracy and any issues will be raised with UNICEF
3. In accordance with the framework agreement between DFID and UNICEF, payments will be made in UK pounds sterling. UNICEF accepts the risks associated with exchange rate fluctuations. As set out by the framework agreement, at the end of the programme, UNICEF will return any uncommitted funds to DFID.
4. The programme components will be reported through DFIDs aid management platform under the following sectors. This will be reviewed during the programme to ensure it remains relevant.
Component 1 - Responding to the Nutrition Crisis in Yemen
Funding Type: 105 – Humanitarian Assistance
Benefiting Country: Yemen
	Input Sector	Input Sector Code	Percentage Allocation
1	Material Relief Assistance and Services	72010	100%
Component 2- Analytical support
Funding Type: 105 – Humanitarian Assistance
Benefiting Country: Yemen
	Input Sector	Input Sector Code	Percentage Allocation
1	Material Relief Assistance and Services	72010	100%

Flow of funds
1. DFID will ensure that no UK aid funds support any other objective than the delivery of critical services outlined in this business case. DFID funding for this programme will be paid directly to UNICEF and through any selected partner via a DFID approved framework agreement.
2. UNICEF will retain responsibility for the onward disbursement of funds. UNICEF would share a regularly updated partner mapping and have in place a system that monitors how funds would be utilised. This would involve delivering resources or supplies to points at need within the system and being able to track them down to beneficiaries. Accountability would fall to UNICEF for systematic monitoring, obtaining beneficiary feedback while DFID will use its third party monitoring to carry out spot checks.
3. In delivering this programme, UNICEF will work with a number of different partners including the local level health systems, national and international NGOs, fuel supplier and an independent monitor. Downstream partner mapping will be updated on the Aid Management Platform and will be continuously reviewed with changes made where necessary. Funding will be provided to downstream partners based on their comparative advantage and a risk assessment to deliver against the key results agreed in the logframe.
4. As illustrated above this programme entails many downstream partners, all of which will attach a management cost for their inputs. These costs will be monitored through the delivery chain map and challenged where deemed appropriate. The large number of downstream partners will increase financial and fraud risk. To manage this risk UNICEF will follow the Harmonised Approach to Cash Transfers (HACT) as detailed on the next page and the commercial case.
5. This UNICEF integrated programme is also funded by the World Bank, GAVI. the Vaccine Alliance, European Commission’s Humanitarian Aid and Civil Protection Department (ECHO), the European Union, The Office of U.S. Foreign Disaster Assistance (OFDA) and Japan through separate funding arrangements. UNICEF will provide financial reports which set out DFID funding and expenditure and balances against our contribution, and clear attribution of DFID funded results.
Financial and Fraud risk assessment
1. Residual fraud risk has been assessed as major. The risks in Yemen, given the lack of salary payments alone mean that all partners will need to remain alert to this risk. There are a large number of downstream partners on this programme which increases the financial and fraud risk.
2. UNICEF’s approach to transferring funds to implementing partners helps to mitigate the risk of fraud occurring. UNICEF will apply the Harmonised Approach to Cash Transfers (HACT), which includes assessment and strengthening of partner financial systems, spot checks, micro-assessments, audits, programmatic visits and scrutiny of use of funds. UNICEF is also increasingly using smaller disbursements, advances and reimbursements to reduce risk. Third party monitoring is increasing the frequency of programme visits, particularly to areas not possible to reach by UNICEF staff. Capacity building, monitoring and financial regulations such as limits on overhead costs help to limit mismanagement of funds. The HACT approach consists of:
- Micro-assessments - conducted at least once per programme cycle (every five years) for all partners who receive at least USD 100,000 per year. UNICEF hires an accounting firm (Moore Stephens) to conduct the assessments. These assessments determine the Implementing Partners (IPs) financial management capacity. Moreover, the risk rating of the IP, along with other available information, is also taken into consideration when selecting the appropriate cash transfer modality for the IP, and the appropriate type and frequency of assurance activities.
- Audits - a more systematic examination of data, financial statements and performance, and are conducted on UNICEF’s behalf by KPMG. Audits are undertaken at least once per programme cycle (at least once every five years) for implementing partners who have received at least USD 500,000 per programme cycle. The primary objective of an audit is to provide the UNICEF country office with a reasonable reassurance on the appropriate use of funds provided to the IP in accordance with the programme document or work plan.
- Spot checks - a review of financial records to obtain reasonable assurance that the amounts reported as spent on Financial Authorisation and Certificate of Expenditure (FACE) forms are accurate. FACE forms are required to be submitted before a new tranche of funding can be transmitted to a partner. Spot checks are conducted in the offices of the implementing partner where financial records are kept, and, as above, the frequency of the checks is also determined by the level of risk, determined by UNICEF, and amount of cash distributed to the partner.
1. UNICEF undergoes regular audit conducted by the Office of the Investigation and Audit (OIA). Any suspected fraud and corruption are reported to them, and will be reported to DFID without undue delay, in accordance with the Framework Agreement. In addition UNICEF has a whistler-blower policy for notification of any fraud and corruption.
2. UNICEF ensures that all staff completes the UNICEF ethics training course within one month of joining the organisation, and is looking at conducting additional training for IPs on HACT, as well as the possibility of incorporating clauses in contracts to recover any losses.
3. In addition, DFID has made clear to UNICEF their obligation to inform DFID of any misuse of funds by downstream partners. DFID will discuss the issues and agree appropriate action with UNICEF e.g. termination of downstream partner agreement, agreement on future use of funds whereby downstream partner will no longer receive DFID funding
Asset Management
1. UNICEF will maintain an asset register for this project detailing any equipment and supplies purchased from DFID funds in line with our asset management guidance i.e. life span of more than one year and assets including “attractive” assets (e.g. mobile phones, laptops etc) in excess of £500. UNICEF will also be responsible for the maintenance of any assets purchased. UNICEF will provide updates, at least annually, alongside standard reporting.
2. At the end of the programme, the SRO will consider VFM in the disposal of any remaining equipment and assets (including medical supplies purchased with DFID funds), ensuring that a clear record of decisions are kept detailing whether assets will be sold, ownership transferred to aid recipient or UNICEF. This decision will take into consideration criteria e.g. future use, maintenance etc. At the end of the programme approval from the Head of Office will be requested on any decision the SRO makes in disposal of assets. Any transfer of assets to a recipient will be agreed in writing with UNICEF and signed by the Head of Office.
Management Case
Management Arrangements for Implementing this Intervention
1. Funding to this programme will be governed by a contribution arrangement between UNICEF and DFID. The DFID Senior Responsible Owner and Lead Adviser for this programme is the A2 Humanitarian Adviser. The programme will be managed by this person and the A2L Senior Programme Manager, who will provide monitoring and evaluation, information management, and spend and forecasting oversight.
2. Within DFID, the United Nations and Commonwealth Department (UNCD) is responsible for the UK’s institutional relationship with UNICEF. DFID’s New York Office (UKRep NY) will facilitate the UK’s partnership with UNICEF and lead on issues where direct contact is involved. The UK is a member of the UNICEF Executive Board, which provides an oversight function.
3. DFID Yemen will work closely with UKRep NY and UNCD to ensure consistency with the wider objectives of UK core funding. In addition, the DFID programme team will meet with UNICEF monthly to discuss progress (including financial spend), changes in context and need, risk, aid diversion and conflict sensitivity. If progress is off track DFID will work with UNICEF to put in place a Performance Improvement Plan which would include an action plan as well as monthly progress meetings.
Beneficiary Representation
1. Beneficiaries are represented in the governance of this intervention through ensuring participation in both programme planning and implementation through focus group discussions and sensitisation sessions at the community level.
2. A beneficiary feedback mechanism is in place which is linked to field monitoring visits. Gender sensitive water, sanitation, and hygiene promotion committees will be established and trained for local governance of solar-powered water supply systems and will also lead the water safety planning process.
3. As part of ongoing Communication for Development (C4D) work on systematic Accountability to Affected Populations (AAP), UNICEF are conceptualising community engagement and feedback mechanisms to more robustly involve communities in programming. It is expected that a local NGO will lead on this work.
4. Finally UNICEF’s child protection work will seek feedback from mothers whose children receive support from trained heath works and the case managers. In addition, the community based child protection committees will organise regular orientation/discussion sessions for community members to promote their participation and seek their feedback on how to better provide support to children.
Monitoring of Intervention
1. High level strategic reports will be submitted from UNICEF to DFID twice a year. In addition, DFID will have access to real time data through a donor portal increasing data availability and transparency allowing for closer up to date tracking of results. These reports and results will be reviewed during monthly update, quarterly progress check and bi-annual programme review meetings. DFID will agree a reporting template with UNICEF and it will include a summary of progress and key results over the previous six month period and an update of risk and mitigating actions against the programme’s risk register.
2. The SRO and Programme Manager for this programme will monitor progress against the outputs through regular reviews of the logframe which accompanies this business case. The logframe has been designed to cover the delivery of a range of critical services, strengthening systems, risk management and knowledge generation activities. It includes a set of output, outcome and impact indicators which aim to capture the key steps in the theory of change.
3. Outputs will be monitored on an on-going basis with data from routine monitoring as well as through the donor portal, and used to score the programme annually. Progress against Outcomes will also be assessed annually. The SRO will oversee the logframe and review accordingly. All results will be disaggregated by sex and disability where appropriate and formally assessed through an annual review.
4. DFID will also hold regular discussions as well as formal quarterly meetings to discuss progress, context, needs, risk and aid diversion. Should progress go off track, DFID Yemen will work with UNICEF to put in place a Performance Improvement Plan which would include an action plan as well as monthly progress meetings.
5. This programme will also be subject to independent monitoring funded from DFID Yemen’s own independent monitoring programme. In addition a due diligence refresh will be completed in 2019 with the scope of this assessment being agreed with the SRO in due course.
6. UNICEF monitors progress of delivery partners through the Harmonised Approach to Cash Transfers to Implementing Partners (IPs). Data verification is done by UNICEF staff, third-party monitoring, as well as zonal and district governmental monitors who have been trained on integrated monitoring and provided with the essential tools. Assurance activities help to determine where funds transferred to partners were used for the intended purpose and in accordance with the agreed work plan. Monitoring costs incurred for this programme will be covered by UNICEF’s indirect cost recovery charge and direct management budget. See financial case for more details.
7. Should this programme cease to represent good VfM then an action plan in consultation with UNICEF will be put in place to seek improvements. If no or little improvement is made then DFID will consider ending this programme early.
Evaluation
DFID Yemen intends to carry out a portfolio level evaluation where this programme will feature. There are no formal plans to evaluate this programme independently. There is strong evidence from DFID’s prior partnership with UNICEF that UNICEF’s approach can deliver results in the current context. Conducting an impact evaluation will involve large-scale data collection which will be difficult to do due to the security constraints. The high cost associated with doing an impact evaluation in Yemen cannot be justified. In addition, the collection of medical data on malnourished non-beneficiaries would not be ethical.
Risks
1. The risks of working in Yemen are significant, given it is an active conflict zone, and needs to be weighed against the high return of providing life-saving support to people in desperate need. Each UN agency has its own risk management system and will use this to inform decision making. As part of DFID’s regular meetings with UNICEF, discussions will cover progress, context, needs and risk. These meetings will highlight any changes to the key risks and will consider the need for any additional mitigating actions.
2. To contextualise the programme approach for Yemen, a complex context with an active conflict means that we will need to focus on the lifesaving interventions and build on these where possible to maintain and increase the capacity and resilience of the systems involved. This will be an ongoing exercise, assessing the programme criticality of elements where delivery begins to be a challenge or scaling efforts were access become permissible.

Risk	Mitigating actions	Residual risk
External context - Security situation deteriorates and UNICEF and partners draw down staff with a negative impact on humanitarian operations.	UNICEF is working with other agencies and UNDSS to find ways to implement the Security Management System Policy on how “to stay and deliver” humanitarian support for a community in need while also strengthening remote programming by placing staff in Amman or other alternative locations. / Provision of UNHAS also allows for regular and reliable access for humanitarian staff. / Any threat of an assault, will lead UNICEF to considering various options including temporarily putting staff on administrative leave with only critical staff remaining and will closely monitor the situation.	Major
External context /Delivery – / Lack of humanitarian access. UNICEF and partners cannot access certain areas of the country due to violence, insecurity and lack of fuel and programming suffers	Establishment of an Access Monitoring Working Group to articulate access constraints and support negotiation processes. / DFID’s support to coordination structures covers this and surge deployments also offer a route to ensure that sufficient security and coordination functions are in place. / UNICEF is increasingly decentralising with field offices in Sana’a, Aden, Hodeidah and managing the inter-agency operational hubs in Ibb and Sa’ada, strengthening their operational capacity and reach and are undertaking their own local level access negotiation. / Presence in Mukalla being established. / UNICEF’s extensive network of partners including local NGOs and CBOs gives diverse delivery options. / UNICEF’s support to the government and NGO partners to extend health and nutrition services in order to improve access and utilisation of health and nutrition interventions through Integrated outreach services throughout the country especially in remote areas where normal health services are lacking/non-existing, and also through the Mobile teams in inaccessible/insecure areas and IDPs settlements. / UNICEF has special local arrangements with Yemen Petroleum Company to supply fuel e.g. for urban water, sanitation systems and a close relationship with the logistics cluster and private suppliers of fuel. They are also using solar and other energy saving measures. / To improve community access and acceptance of UNICEF-supported programmes, UNICEF is implementing a community engagement and outreach C4D interventions including mapping and engagement with influential and key decision makers. / UNICEF annual perception surveys will help to highlight how the organisation is perceived and gives an insight into how reputation and local popularity can improve access. / UNICEF also conducted an access mapping exercise in early January 2018, and found that access has overall improved in the past year, resulting in more programme visits by UNICEF and reduced reliance on third party monitoring. As the conflict lines are fluid, UNICEF is shifting its operational support taking account accessibility. For example, Al Mokha in Taizz Governorate is now supported from Aden rather than from Ibb, the original hub geographical area of responsibility, and so will be soon the southern districts of Hodeidah.	Major
External context/ Delivery - / Banking sector fragility/failure - / Lack of imports, shrinking of commercial activity, devaluation of Yemeni Rial. Deterioration/collapse of banking services and no hard currency in the market.	Payments to INGOs to international accounts, opening of additional UNICEF accounts throughout Yemen (North/south). / UNICEF has identified alternative modalities, to transfer funds to partners. / Negotiate rates with banking sector, and possibly establish alternative payment modality with more than one bank/other financial institutes such as money transfer companies. / UNICEF also has the option to make use of a Standard Operating Procedure on money transfers through money suppliers rather than using banks.	Major
Operational - Dysfunctional telecommunications systems and unreliable electricity	Use of satellite phones and radios to manage programme. Use of solar and fuel for generators if no mains electricity. / Use of solar and fuel powered generators. / Advocacy is on-going to facilitate the import of telecommunications equipment. / UNICEF maintains up to date business continuity plans for all its offices, and conducts regular reviews and simulations of critical telecommunication systems, and checks its back-up system.	Moderate
External context - Divided leadership in public health policy and access – / Programme delivery will occur in areas outside of the control of the legitimate Government of Yemen.	UNICEF increasingly working at the decentralised level; ensuring its approach to programming is conflict-sensitive; working at technical level, non-political level with line ministries (with policy work on hold), and different de facto technical authorities and local civil society depending on location.	Severe
Conflict Sensitivity – UNICEF programming could unintentionally exacerbate conflict at a local level.	UNICEF programmes will continue to target the most vulnerable children, and provide clear communication to stakeholders and beneficiaries about the rationale for targeting. It will also factor in political sensitivities and changing control of geographic areas, adapting its approach to maximise access and minimise risks. / UNICEF is taking steps to strengthen its application of conflict sensitivity; including developing a national conflict sensitive planning manual with MOPIC and developing its work on Accountability to Affected Populations for improved community feedback. DFID will work with UNICEF to ensure that its draws on the support of the new conflict sensitivity facility that is due to be established in the Autumn to further strengthen its conflict sensitivity capacity and practice. / UNICEF’s field presence and third party monitoring (TPM) also help monitoring and ensuring the equal access by all to the government and NGOs services supported by UNICEF. / UNICEF uses the common UN HACT modality to monitor partners and the new CSO procedures include a declaration on political affiliation and HQ/CO check. / The Strategic Reflection (SR) process will also help to enhance programming and operational support in Yemen. The SR took into consideration the new political, security, economic, social and human rights situation and working environment. As a result of this process UNICEF developed a strategic way forward to guide work and contribution over the next two years (2018-19) as well as in subsequent strategic planning frameworks i.e. UNDAF and CPD.	Major
Delivery/ Operational -Decreased capacity of implementing partners both NGOs and government, including brain drain	Humanitarian Coordinator advocates to NGOs to support and maintain their presence. / Advocacy to maintain government health worker salaries and provision of staff training. / Small scale funding agreements with multiple partners, technical support and capacity building to local NGOs and sharing of technical support between agencies. / Prioritisation of work plan activities and scale based on the emerging needs and operational capacity. / UNICEF continues to work to build the capacity of all partners, both NGO and government.	Major
Delivery - Inadequate field monitoring and implementation of third party monitoring means results not captured and use of funds (including through government) not monitored.	UNICEF has contracted a national organisation (Prodigy) to conduct third party monitoring nationally with a focus on areas they cannot reach themselves. / UNICEF is increasingly relying on staff monitoring delivery as opposed to remote monitoring through a third party / DFID’s own independent monitoring project will also conduct a verification study during the programme.	Major
External context / Delivery -Supply pipelines to and inside the country are interrupted and local markets collapse	UNICEF Yemen to ensure preposition stock to sufficiently cover needs / UNICEF increase of its warehouse capacity locations and additional new warehouse will help to store more stock. / UNICEF uses multiple suppliers (except for medicines, vaccines and nutrition supplies) and a combination of local and offshore suppliers (including procurement through neighbouring countries Jordan, Oman, Djibouti). They have set up a supply hub in Djibouti, including contingency stocks, and use multiple ports of entry in the north and south in coordination with the logistics cluster and work to pre-position supplies in strategic locations. The supply pipeline is kept agile with the ability to use smaller non-traditional entry ports.	Major
Fiduciary - Aid diversion/ Collateral Damage	Supplies held in decentralised storage and as far as possible secure locations to minimise risk. / Global insurance covers any loss or damage at UNICEF warehouses. / Where necessary and possible access will be negotiated with parties to the conflict. / To lessen the risk of collateral damage occurring during transportation of aid, prior to transportation of supplies, security clearance requests are submitted from the de-confliction cell in Riyadh and the Ministry of Interior in Sana’a by providing the details on number of trucks, routing, road maps from warehouse to point of destination with their coordinates, details of contact person at receiving end. Trucks only move once all clearances have been received. / UNICEF will continue to enhance cooperation with logistics cluster and various authorities on the ground to ensure safe delivery.	Major
Fiduciary -Mismanagement of funds	The common UN Harmonised Approach to Cash Transfers (HACT) includes assessment and strengthening of partners’ financial systems, spot checks, micro-assessments and scrutiny of use of transferred funds. / UNICEF is increasingly using smaller disbursements, advances and reimbursements to reduce risk. / Third party monitoring is increasing the frequency of programme visits, particularly to areas not possible to reach by UNICEF staff. / UNICEF undergoes regular audit conducted by the Office of the Investigation and Audit (OIA). Any suspected fraud and corruption are reported to them, and will be reported to DFID without undue delay, in accordance with the Framework Agreement. / UNICEF whistler-blower policy for notification of any fraud and corruption. / UNICEF staff complete the UNICEF ethics training course within one month of joining the organisation, and is looking at conducting additional training for implementing partners on HACT, as well as the possibility of incorporating clauses in contracts to recover any losses. / UNICEF will need to assure DFID that it has carried out the necessary fiduciary risk assessments on its delivery chain and partners	Major
External context/ Delivery - Threats to staff and operations from state / non-state actors	Office premises are Minimum Operational Safety Standards (MOSS) compliant. / Movement in armoured vehicles. / Appropriate communications equipment for staff and Armoured Vehicles. / Coordinate closely with the United Nations Department of Safety and Security. / Update the relevant governments entities on the UNICEF mandate and role in the country and activities accomplished. / Regular meetings held with the concerned government entities to update on the changing circumstances. / Partner with local NGOs, who may have better access and networks than international partners. / Conduct perception survey to assess UNICEF's image and neutrality in Yemen. / Make greater use of Arabic 'UNICEF' logo.	Major
Reputational -UNICEF ensures partners’ approach to programming is conflict-sensitive and avoids unintended negative impact	Strategic Reflection (SR) process helps to enhance programming and operational support in Yemen. The SR took into consideration the new political, security, economic, social and human rights situation and working environment. As a result of this process UNICEF developed a strategic way forward to guide work and contribution over the next two years (2018-19) as well as in subsequent strategic planning frameworks i.e. the United National Development Assistance Framework. / UNICEF’s support will extend to all geographical locations including conflict and non-conflict areas as guided by a two year rolling work plan for 2018/19. / UNICEF’s humanitarian responses guided by the Yemen Humanitarian Response Plan (YHRP), itself based on the inter-agency Humanitarian Needs Overview (HNO). / Partners mapping of NGOs by health, nutrition and WASH clusters help and guide UNICEF’s support based on needs on the ground. / UNICEF supports health nutrition, WASH and C4D interventions through several short and long term Programme Cooperation Agreements (PCA) in difficult and inaccessible areas. / UNICEF’s field presence and third party monitoring (TPM) also help monitoring and ensuring the equal access by all to the government and NGOs services supported by UNICEF. / UNICEF uses the common UN HACT modality to monitor partners and the new CSO procedures include a declaration on political affiliation and HQ/CO check. / Whilst the organisation does not have a unified approach to conflict-sensitive programming (but has guidance on conflict analysis), UNICEF Yemen is working with MoPIC to develop a national conflict-sensitive planning manual, and updates its own Emergency Risk Management matrix on a regular basis. / UNICEF does not have a formal conflict sensitivity matrix, but programmes will continue to target the most vulnerable children, and programmes are therefore adapted as needed to address changing conflict sensitivities such as political control of certain areas.	Moderate

Partnership Principles and other conditions
Funding through the programme will be made directly to UNICEF. As such we will not be providing direct support for the government. Nevertheless, part of the delivery chain includes critical elements of the health system at a sub-national level.. We will work with UNICEF to identify which principles (if any) are most appropriate in this intervention.

Definitions:[49]
[49] Tull, K. (2018). Simplified protocol to treat severe and moderate acute malnutrition in Yemen. K4D Helpdesk Report 340. Brighton, UK: Institute of Development Studies.
Acute malnutrition or Wasting: Acute malnutrition can result in death if left untreated. Acute malnutrition in children aged under five years is internationally defined by
- Being too thin for a given height, and/or
- Having a left arm circumference less than a given threshold (i.e. measuring how fat or thin the mid upper arm circumference is), and/or
- Having swollen feet (known as bilateral pitting or malnutrition oedema).
Chronic malnutrition or stunting is defined by a reduced height for age. It is a result of prolonged or repeated episodes of undernutrition starting before birth and can result in reduced height and cognitive ability.
Community health worker (CHW): CHWs are known by many different names in different countries.
The umbrella term “CHW” embraces a variety of community health aides selected, trained and working in the communities from which they come. CHWs are trained to carry out one or more functions related to health care. A widely accepted definition was proposed by WHO: Community health workers should be members of the communities where they work, should be selected by the communities, should be answerable to the communities for their activities, should be supported by the health system but not necessarily a part of its organisation, and have shorter training than professional workers.
Community-based Management of Acute Malnutrition (CMAM): Evidence suggests that large numbers of children with severe acute malnutrition can be treated in their communities without being admitted to a health facility or a therapeutic feeding centre. The community-based approach involves timely detection of severe acute malnutrition in the community and provision of treatment for those without medical complications with ready-to-use therapeutic foods or other nutrient-dense foods at home. If properly combined with a facility-based approach for those malnourished children with medical complications and implemented on a large scale, community-based management of severe acute malnutrition could prevent the deaths of hundreds of thousands of children. CMAM evolved from Community-Based Therapeutic Care (CTC), which is a community-based approach for the management of acute malnutrition in emergency settings. Although CMAM was developed in the emergency context, its decentralised nature has been shown to lend itself to integration into existing services at the primary health care level in the longer term and in non-emergency contexts.
Complementary feeding: The child receives both breastmilk or a breastmilk substitute and solid (semi-solid or soft) foods. The process starts at six months when breastmilk alone is no longer sufficient to meet the nutritional requirements of infants, and therefore other foods and liquids are needed, along with breastmilk. The target age range for complementary feeding is generally taken to be 6 to 24 months of age. It is not recommended to provide any complementary foods to children less than six months old.
Complementary food: Any food, whether manufactured or locally prepared, used as a complement to breastmilk or to a breastmilk substitute.
Exclusive breastfeeding: Infant receives only breastmilk (including breastmilk that has been expressed or from a wet nurse) and nothing else, except for Oral Rehydration Salts (ORS), medicines and vitamins and minerals.
Global Acute Malnutrition (GAM): Is the measure of the combined presence of both moderate acute malnutrition and severe acute malnutrition in a population.
Infant: A child from birth to 12 months of age.
Infant and young child feeding (IYCF): Describes the adequate nutrition required during infancy and early childhood that is essential to ensure the growth, health, and development of children to their full potential.
Low birth weight (LBW): An infant weighing less than 2.5 kg at birth.
Moderate Acute Malnutrition (MAM): Children with moderate malnutrition have a risk of mortality. If some of these moderately malnourished children do not receive adequate support, they may progress towards severe acute malnutrition (severe wasting and/or oedema) or severe stunting (low height-for-age), both life-threatening conditions.
Mid Upper Arm Circumference (MUAC): MUAC is a quick and simple way to determine whether or not a child is malnourished using a coloured plastic strip. MUAC is suitable to use on children from the age of 12 months up to the age of 59 months. However, it can also be used for children over six months with length above 65 cm.
Severe Acute Malnutrition (SAM): Children with severe malnutrition have an increased risk of mortality. Is defined by a very low weight for height scores against the WHO growth standards, MUAC less than 115 mm, by visible severe wasting, or by the presence of nutritional oedema.
Undernourished: A classification that indicates undernutrition such as stunting, underweight, or wasting.
Undernutrition: A consequence of a deficiency in nutrient intake and/or absorption in the body. The different forms of undernutrition that can appear isolated or in combination are acute malnutrition (bilateral pitting edema and/or wasting), chronic malnutrition (stunting), underweight (combined form of wasting and stunting), and micronutrient deficiencies.

Underweight: A composite form of undernutrition including elements of stunting and wasting and is defined by a weight-for-age z-score (WAZ) below 2 standard deviations of the median (WHO standards). This indicator is commonly used in growth monitoring and promotion (GMP) and child health and nutrition programmes aimed at the prevention and treatment of undernutrition.
Value for Money (VfM): Value for Money (VfM) in UK funded programmes is about maximising the impact of each pound spent to improve poor people’s lives.

 Annex A
Statistical analysis of the context
This section describes the prevalence of acute and chronic malnutrition in Yemen carried out as part of a report compiled by the Maximising Quality in Scaling up Nutrition initiative. The recently updated context analysis informs much of the business cases, includes estimates from three national surveys, from 2011, 2013 and 2016. It also utilises the latest available SMART surveys wherever possible. DFID has also drawn upon a multivariate regression analysis of the 2013 YNHDS to determine the associated drivers of malnutrition in Yemen[50]. This information while dated represents the latest and best information we have on the nutritional context. The gap in data and critical indicators will be discussed later in this business case as part of one of the output focus areas.
[50] The multivariate analysis carried out as part of a 2018 MQSUN report was the first of its kinds to be carried out on the 2013 data. Methods available in the MQSUN report. 2011 (Comprehensive Food Security Survey), 2013 (Yemen National Demographic and Health Survey), 2016 (Emergency Food Security and Nutrition Assessment)
Levels and trends in Key Anthropometric[51] indicators (Acute, Chronic)
[51] Anthropometric measurements are used to assess the size, shape and composition of the human body.
Acute Malnutrition (Wasting)
  1. Prevalence of wasting was highest amongst children aged 6 to 8 months (28.4%). This age group also had a Severe Acute Malnutrition rate (11.0%) that far exceeded the national average (5.2%). Male children were significantly[52] more likely than female children to be wasted (17.8% and 14.7%, respectively).
    [52] P < .001
  2. Wasting rates were highest amongst children whose mothers also exhibited signs of undernutrition. 24.6% of children whose mothers measured “thin” according to their Body Mass Index (BMI) were wasted, compared to 16.1% of children whose mothers had normal BMIs.
  3. Size at birth, as reported by the child’s mother, was found to have a strong association with a child’s odds of wasting. The odds of wasting were 1.58 times[53] higher amongst children who were classed as being smaller than average at birth.
    [53] 58% more likely
  4. The governorate in which a child lived was found to be an important determinant of child wasting. There were large disparities in the percentage of children wasted across governorates, ranging from 10.9% in Ibb to 26.2% in Hodeidah even after adjusting for other variables. A total of seven governorates were found to have significantly higher odds of wasting when compared to those who lived in Ibb, the governorate with the lowest percentage of wasted children in the country.
  5. Continued efforts to maintain access to clean water is essential, with a priority needed on the rehabilitating the piped water systems. Even before the conflict and after adjusting for other variables, children who lived in households that accessed drinking water from a tanker truck were at a significantly decreased risk of wasting compared to those that used the government piped network. Similarly, children in households that accessed water from a tube well were also at a significantly decreased risk of wasting compared to those that used the government piped network. This is likely due to high levels of pollution in the government piped water network, which has been associated with increased child morbidities in the past.
  6. Behaviour change and hygiene proportion efforts need to go beyond distributing hygiene kits to meaningfully changing behaviours. After adjusting for other variables, children in households with soap visible at the place where they washed their hands were not found to have significantly decreased odds of wasting.
Chronic Malnutrition (stunted)
  1. Prior to the current conflict, in 2013, almost half (46.5%) of all children under the age of 5 years were stunted. Almost half of all stunted children (23.0% of all children under the age of 5 years) were severely stunted. There was also a significant divide between urban and rural areas in the rate of stunting, at 33.7% and 51.4%, respectively. Almost six out of every ten children from the lowest wealth quintile (59.2%) and second-lowest quintile (55.2%) were stunted, compared with one child out of every four children (25.9%) from the highest wealth quintile.
  2. The prevalence of stunting increased substantially with age, children aged 18 to 59 months had stunting rates (49.8% to 57.8%) that exceeded the national average. Children aged 36 to 47 months had a rate of stunting (57.8%) that was more than three times the stunting rate observed amongst children under the age of 6 months (19.2%).
  3. Similar to wasting, there were significant prevalence variation based on gender, residence, mothers characteristics and size at birth.
    1. Prevalence was found to be significantly higher[54] in boys (47.6%) than girls (45.4%).
      [54] P value = 0.26
    2. The governorate in which the child was resident was associated with increased odds of being stunted where out of the 21 governorates surveyed, 14[55] had a prevalence of stunting above the World Health Organisation critical threshold of 40%[56].
      [55] Amran, Al Dale, Al Jawf, Al Mahra, Dhamar, Hajja, Houdeaidah, Ibb, Lahj, Mareb, Rayma, Sana’a, Sadaa, and Taiz
      [56] Only 4 out of the 21 governorates (Shabwa, Al-Mrah, Abyan, and Aden) had a prevalence of stunting lower than 30%. The only governorate with a stunting level below the 20% WHO “acceptable” threshold was Aden.
    3. Children whose biological mothers were “thin” (BMI < 18.5 kg/m2) were much more likely than other children to be stunted[57].
      [57] 52.7%, compared with 47.2% amongst children with “normal BMI” mothers and 35.8% amongst children whose mothers were overweight/obese
    4. Mothers who reported their children as being smaller than average at birth were 35% more likely to be stunted.

  1. Analysis also showed a strong and significant association between household wealth. Children in the poorest households were at an increased risk of being stunted compared to those from the wealthiest.
  2. Birth spacing and access to sexual reproductive health was found to be critical - Children born within a birth interval of less than 24 months after the previous sibling were 65% more likely to be stunted compared to firstborn children[58].
    [58] The odds of stunting were also elevated amongst children born within an interval between 24 and 47 months after the previous sibling (27%) compared to firstborn children.
  3. As would be expected in households that suffered from food shortages went a whole day without food were 16 – 38 times more likely to be stunted.