The Country Representative / UNICEF Zambia / Lusaka	PO Box 50050 / 15101 Ridgeway / Lusaka / Zambia
	Tel: / Fax: / Email:
	21st November 2011

### AMENDMENT OF THE MEMORANDUM OF UNDERSTANDING FOR TACKLING MATERNAL AND CHILD MALNUTRITION PROJECT IN ZAMBIA – DFID CODE NO. 201927-102
1. I refer to the Memorandum of Understanding (MOU) for the above project signed by DFID and UNICEF on 27th May 2011 and 1st June 2011 respectively. Following recent discussions, DFID proposes to change the project end date and increase the amount made available to UNICEF by £935,000 (Nine Hundred Thirty-Five Thousand Pounds Only). The amendments will cover support for the Child Health Weeks (CHWs) activities as set out in the attached DFID Business Case on Tackling Maternal and Child Undernutrition in Zambia (Annex 1).
2. I, therefore, propose that the figures and words "£150,000 (One Hundred and Fifty Thousand Pounds Sterling)" in paragraph 1 of the original MOU be replaced by the figures and words “£1,085,000 (One Million Eighty-Five Thousand Pounds Only)”. The schedule of payment for the revised amount is provided at Annex 2.
3. I further propose that the end date of 31st December 2012 in paragraph 5 of the original MOU be replaced by 31st December 2015.
4. This letter of amendment will place on record our common understanding of the above changes and will come into operation on the date you sign your confirmation below. This note will be known as Amendment No. 1 2011.
5. Please sign both copies of this letter: return one to me and retain the other for your own records.
Signed for DFID:	Confirmed by UNICEF:
Name:	Name:
Position: Head of Office	Position: Country Representative
Date:	Date: