Type of Review: Annual Review

Project Title: Climate Investment Funds (formerly the Environmental Transformation Fund)

Date started:	24 Feb 2009	Date review undertaken: 1 June 2012

## Introduction and Context

Regular and effective monitoring, reviewing and lesson learning are key to how DFID measures the results of its projects and demonstrates Value for Money. Carrying out an annual review is part of this process. The annual review looks at progress over the last year against the intended outputs identified at the start of the project. It also looks at progress against results, risk, and value for money. This is the third annual review of DFID and other Government Department (DECC) contributions to the Climate Investment Funds and two other related climate funds.

The Climate Investment Funds (CIFs) are a pair of funds to help developing countries pilot low-emissions and climate-resilient development. With CIF support, 46 developing countries are piloting transformations in clean technology, sustainable management of forests, increased energy access through renewable energy, and climate-resilient development.

What support is the UK providing?

Funding through the Climate Investment Funds has been approved at two points, from two distinct UK climate finance instruments and from two Comprehensive Spending Review periods:
- 2009 - Environmental Transformation Fund (ETF) of £800m;
- November 2011 – up to 285m from the International Climate Fund (ICF).

ETF
The £800m ETF funding was provided to the Climate Investment Funds (CIFs), Congo Basin Forest Fund (CBFF), and Forest Carbon Partnership Facility (FCPF). This was split as follows: £735m for the CIFs; £50m for CBFF; £15m for FCPF. Funds were equally provided by DFID and DECC.

The £735m contribution to the CIFs was split across the CIFs as follows:

CIF Trust Fund/Programme	Total Funds/£m
Clean Technology Fund (CTF)	385
Pilot Programme for Climate Resilience (PPCR)	225
Forest Investment Programme (FIP)	75[1]
Scaling-up Renewable Energy Programme (SREP)	50
[1] The UK pledged £100m in total to the FIP. In March 2011 DECC deposited an additional £25m to make good our full pledge on the FIP.

ICF
A further £285m from the ICF was approved in 2011/12 and was just to the CIFs. This was split between CIF programmes and UK Government (DFID &DECC) departments as follows.

Programme	DECC Spend (£m)	DFID Spend (£m)	HMG Total (£m)
CTF	£106	£44	£150
PPCR	£0	£85	£85
SREP	£25	£25	£50
Totals	£131	£154	£285

What are the expected results?

The 2009 project memorandum for the first contribution of £800m set out some expected results and also a logframe with outcomes and outputs, against which this annual review has been conducted.
The outcome statement is to Transform energy supply and demand, and forest use, and increase resilience to climate change in developing countries.

There are eight agreed outputs, with associated indicators, however, no milestones or targets have been set for these as the CIFs own results frameworks have not set these yet (this is discussed further within the annual review). The agreed outputs were:

1. CIFs investment plans and development strategies that integrate low carbon pathways and climate resilience;
2. Infrastructure, capacity and financing for low carbon development and climate resilience;
3. Learning about piloting, demonstration, replication and transformation captured and shared in countries and across countries;
4. Learning about piloting, demonstration, replication and transformation captured and shared across projects, programmes and funds;
5. Learning about piloting, demonstration, replication and transformation captured and shared globally;
6. CIFs governed with legitimacy and inclusion;
7. FCPF Readiness Fund assists developing countries to reach a capacity level at which they will be ready to participate in a future system for positive incentives for REDD+; and Carbon Fund tests and evaluates incentive payments for REDD+ in approximately five developing countries;
8. The Congo Basin Forest Fund (CBFF) alleviates poverty and addresses climate change through reducing the rate of deforestation of the forests of the Congo Basin, with effective participation of Congo Basin countries in climate change initiatives deriving sufficient benefits for conservation of resources and enhancing livelihoods of populations living in the forest.

The project memo set out the following expected results, which provide some specific targets to help assess progress against the above outcomes, especially outcome 1, in the absence of agreed milestones and targets:

Up to 15 countries will be provided with additional finance to support the development and deployment of clean technologies, helping these countries onto a low carbon development path.

Up to 11 countries or regions will be provided with support to develop a climate resilient development plan and additional finance to support the implementation of this plan, thereby building climate resilience. Funds through the Climate Investment Funds will be complementary to existing development plans in recipient countries.

Between five and ten countries will be given support to implement national strategies for reducing emissions from avoided deforestation and degradation.

A further five to ten low income countries will be given support to increase energy access and their low carbon development growth potential by developing new renewable energy sources.

By piloting approaches to climate financing mechanisms, the funds will also provide lessons and knowledge to inform discussions on the future financing of climate change, including the negotiations under the UNFCCC.

The business case in 2011 for the second approved contribution set out the following expected results:

The CIFs provide funding to pilot climate interventions at scale. Before the Green Climate Fund is up and running the CIFs will provide important lessons for implementing adaptation, low carbon development and programmes to tackle deforestation. As pilot programmes in a limited number of countries they have the ability to demonstrate that transformation is possible. The financing will directly avoid greenhouse gases emission, increase access to energy for poor women and men, increase the integration of resilience to climate change and climate variability into country development strategies, and ensure regulatory frameworks support sustainable management of forests and protect the rights of local communities and indigenous peoples.

The results from the CIFs will be measured (in part) by[2] the following indicators – these are specifically intended to be comparable to the Key Performance Indicators (KPIs) being used to measure results from the UK’s investments through the International Climate Fund (ICF):
[2] These are a subset of the proposed core indicators across the CIFs. For the full document see: http://www.climateinvestmentfunds.org/cif/sites/climateinvestmentfunds.org/files/Joint%20Inf%202%20%20Implementation%20CIF%20results%20framework.pdf

- The tonnes of CO2 avoided.
- The number of households, in areas of risk, whose livelihoods have improved.
- The number of people with access to climate resilient housing and shelter.
- The numbers of jobs created by CIF funding in low carbon development.
- The electricity generated from renewable energy.
- The number of households with access to electricity.
- The amount of private and other sources of funding increases through leverage.

Specifically, UK funding will contribute to the following expected results. Examples have also been provided to demonstrate what type of result this will deliver under each CIF programme, and in some cases, the initial anticipated results achieved from UK support:

- Increased renewable energy, transport, and energy efficiency infrastructure, e.g. CTF investment in energy efficiency in India will accelerate the deployment of super-efficient fans by 2014/15 avoiding up to 98 million tonnes of CO2 per annum; investment in renewable energy in India will scale up the installation of concentrated solar power, delivering up to 20GW of energy by 2022; and investment in Nigeria will support 300 retrofitted and new high efficiency buses in Lagos, reducing carbon emissions by 13.5 MtCO2e over the lifetime of the project.
- Increased renewable energy services in low income countries, e.g. additional SREP investment in Kenya will enable the construction of a geothermal plant and enable this to be connected to the grid to increase Kenya’s renewable energy supply by 32%. By connecting this 200MW power plant to the grid by 2015, it will demonstrate a model for replication to enable a potential 5000MW to be generated by geothermal power in Kenya by 2030.
- Increased knowledge and awareness of climate variability and climate change among government, private sector and civil society will improve planning processes e.g. increased investment in Tajikistan would allow the PPCR to scale up in agriculture and land management, focusing on districts with high food insecurity and high likelihood of climate change impacts. Examples from plans approved so far include Bangladesh’s Investment Plan, where results include income opportunities generated for 10,000 women, 250 km of roads improved to climate resilient standards, 87,000 hectares of land benefiting from improved water management, increasing crop yields for 440,000 people and average travel time for households to access desired markets halved.
- Increased Multilateral Development Bank (MDB) finance for climate change and renewable energy.
- Continuous improvement in the operation of the CIFs.

The last of these outputs directly responds to the outcome of the Multilateral Aid Review (MAR) carried out in 2010 on the CIFs. This found that the CIFs provided good value for money, in providing a critical gap in delivering the UK Government’s climate change outcomes and delivering finance at scale, and that they are also important in delivering the Millennium Development Goals and wealth creation. While recognising that the CIFs were a new instrument, the MAR did identify a number of areas where improvements could be made, including:
- clearer development impact;
- improved country ownership and greater transparency;
- greater innovation and effective working with the private sector;
- being able to demonstrate results; and
- ensuring effective communication of lessons learnt.

These areas of improvement are being closely monitored as part of monitoring progress against the above outputs (e.g. outputs 3 to 6 below) and as highlighted in the evidence and evaluation section below.

What is the context in which UK support is provided?

The original Programme Memo (2009) – against which the first two annual reviews were carried out - set out the context as follows:

The impacts of climate change on development are potentially great. Even if mitigation targets are met, the need to deal with the projected impact of climate change will require additional finance and capacity in developing countries. Negotiations under the UN Framework Convention on Climate Change (UNFCCC) are underway. These aim to agree and set in place a new global deal that includes financing mechanisms for climate change adaptation and mitigation beyond 2012. However, the pace of climate change means developing countries cannot wait until then to start investing in adaptation and mitigation. We need to start spending at scale now in order to build experience to understand how best to support developing countries in responding to climate change and to inform UNFCCC negotiations and the creation of financing mechanisms created under the UNFCCC.

There is a short window of opportunity to help set the global response on the right track. The current set of international institutions and financial instruments is geared towards ‘business as usual’ high carbon growth and is ill-equipped for facilitating climate resilient investments. There has been a proliferation of new, often bilateral, mechanisms to help developing countries tackle climate change. Not only have these been uncoordinated, but they are of insufficient scale.

Through its support for the Climate Investment Funds, the ETF aims to address this knowledge gap by testing approaches to delivering climate change finance. In recognition of the need to avoid pre-empting outcomes of negotiations for a new global deal on climate change, the CIFs are subject to a sunset clause, and are due to be completed by 2012 (although funding will probably be disbursed until around 2014).

Since then, the Climate Investment Funds have been established and recognised as a multilateral fund able to provide finance at scale to address the above needs, alongside other international climate funds, such as the Global Environment Facility (GEF) and the Adaptation Fund, though these have different roles, such as providing capacity building and technical support for planning. Progress has also been made on developing a new financing mechanism, the Green Climate Fund, that was approved in Durban in December 2011. While the CIFs sunset clauses remain, it is unlikely that the Green Climate Fund will be designed and ready to disburse finance in 2012. As such the CIFs remain the only currently viable fund to deliver climate finance at scale until the GCF is designed, ready to receive contributions and implement.

## Section A: Detailed Output Scoring

The 8 outputs have been scored against the 5 scale scoring system as follows:

A++	Outputs substantially exceed expectation
A+	Outputs moderately exceeded expectation
A	Outputs met expectation
B	Outputs moderately did not meet expectation
C	Outputs substantially did not meet expectation

Output 1: CIFs investment plans and development strategies that integrate low carbon pathways and climate resilience.
Output 1 score and performance description: / A+ - Outputs moderately exceeded expectation
Progress against expected results: / The indicator for this output was The number of plans/strategies approved that integrate low carbon/climate resilient development. / In the extant outputs for the ETF, detailed milestones or targets were not set. As highlighted in previous annual reviews this was because the results frameworks have not yet identified baselines, milestones or targets (this is discussed further in the results section below). As such progress is measured against the expected results from the original ETF project memo as set out above. Since the last annual review significant progress has been made, which in some cases (PPCR and SREP) exceed the expected results set out in the original ETF programme memorandum (hence the score of A+): / A total of 20 countries (against a target of 15 countries) will receive support for deployment of clean technologies. 15 country and one regional (5 countries) CTF Investment Plans have now been approved (over the last year India was approved in 2011, and Chile was approved in 2012). Twenty-six CTF projects (within the Investment Plans) have been approved for $1.9 billion. At the time of the 2011 report 13 country and one regional Investment Plan, with 20 projects, had been approved. / A total of 18 countries – 9 within two regional programmes (from a target of 11 countries) - are being supported to develop climate resilient development plans. For PPCR 15 Strategic Programmes for Climate Resilience (SPCRs) have been endorsed, encompassing all of the pilot country programmes, with only 3 countries within the regional tracks still to be endorsed (Haiti, Jamaica and Papua New Guinea). In addition at seven projects have been approved for $120.9m focussed on climate forecasting, capacity development, community action in climate resilient agriculture, and disaster risk management. In 2011 5 SPCRs and just 1 project had been approved. / A total of 8 countries (against a target of 5-10) will be given support to implement national strategies for reducing emissions from avoided deforestation and degradation. For FIP 5 Investment Plans have been endorsed in the last year out of the 8 pilots, and one project for $42m has been approved. No Investment Plans had been endorsed in 2011 at the time of the last review. / A total of 12 countries (against a target of 5-10) have been identified for support to increase energy access and their low carbon development growth potential. For SREP 5 Investment Plans (from 6 pilots) have been endorsed in the last year, with one project approved for $25m. One further country (Tanzania) has been told there are funds for projects when it develops an Investment Plan and a further 5 countries have been given the go ahead to develop Investment Plans. By March 2011 at the time of the last review there were no approved Investment Plans as the programme was still in the scoping mission stage. / The above represents very good progress over the year in moving to approve all remaining Investment Plans at the country pilot level as well as approve new plans where there are available resources. Progress has also been made in the quality of the Investment Plans (early Investment Plans had a number of issues, such as poor results frameworks). Below the country level, the development and approval of projects is only really taking place within CTF and to some extent PPCR – this is largely to be expected given that the over-arching Investment Plans are only now being approved. There has recently been debate between contributors and the CIF Admin Unit and MDBs on the pace of the CIFs in terms of design and approval of projects, disbursement and ultimate implementation. This issue is not captured by the current wording of this output, and so is not directly reflected in the assessment and score. / Recommendations: / As part of the business case for the new contribution to the CIFs it was proposed to develop a new logframe for the UK’s financial contribution (this is further discussed under ‘Results’ below). The implications for this output is that it will be updated to reflect clearer output results consistent with the new business case, and have milestones and targets commensurate with the progress expected over the lifetime of this project. For example the current output only goes as far as measuring progress in terms of Investment Plans produced rather than approval of projects, disbursement of funds or actual implementation. A new output and set of targets should consider results in the areas set out above (tonnes of CO2 avoided etc) and could consider issues of Investment Plan quality. / Impact Weighting (%): 25% / Revised since last Annual Review? Y Increased due to changes to the forestry programme weighting – see output 5 for explanation. / Risk: Low / Revised since last Annual Review? Y / Against the current wording of this output there is now a low risk that the output will not be met, most of the expected results have already been achieved or exceeded as the majority of Investment Plans have now been produced and endorsed by the Trust Fund Committees – the risk around disbursement and implementation of projects will need to be picked up in the risks against the new logframe (more discussion of this under risks below).

Output 2: Infrastructure, capacity and financing for low carbon development and climate resilience
Output 2 score and performance description: / B – Outputs moderately did not meet expectation
Progress against expected results: / The indicator for the output is ‘Summation of CTF, SREP, FIP and PPCR outputs with respect to infrastructure provided, capacity developed and financing provided’. It is acknowledged that there are issues with this as an output indicator as there were no milestones or targets set due to the lack of targets or milestones in the respective CIF programme results frameworks. As such against the original output, where there was no time limit for the infrastructure etc to be provided, it is hard to judge whether performance is above or below that expected. However, as judged by the number of CTF projects that are on track in the approval process through the CIF Trust Fund Committee and MDB Boards – a precursor to implementation and putting infrastructure in place – there are indications that this is taking longer than expected. Out of 63 projects in the pipeline (i.e. not including those already approved and being implemented) 59 are now behind schedule. Hence the score of B. / Against the measures set out in the new business case for the CIFs it is increasingly apparent that funding through the CIFs will deliver some very significant results on tonnes of CO2 reduced or avoided.. / Reduced or avoided emissions / Tonnes of CO2 equivalent reduced or avoided – CTF / The overall expected carbon savings produced on completion of all CTF are estimated at 1.6 billion tCO2, this figure was derived mainly from the 13 CTF investment plans endorsed before November 2010 (Phase I)[3]. The estimated overall savings are impressive, and will need to be closely monitored and quality assured by DECC economists; the savings figures may be more fluid in some investment plans than in others, depending on the specificity of the expected investment activities. The CIF admin unit is also compiling the estimated CO2 reduction from each project or program when these are submitted for funding approval. Comparing these figures with the endorsed investment plans reveals some discrepancies (i.e. shortfalls), but the projected CO2 reductions are largely on track so far. / The latest summary of CTF approved projects (March 2012) and their corresponding CO2 emissions reduction projections (MtCO2), shows that the CTF currently has 28 projects approved for lending USD 1.92 billion with reduction potential of 441 MtCO2 on completion of these projects. 18 of these projects are categorized private sector and 10 projects are categorized public sector. / Tonnes of CO2 equivalent reduced or avoided – FIP / The FIP program is not as advanced as the CTF program and the analysis of reduction projections or potential is still based on investment plans (not approved projects). Figures are likely to change when detailed project designs are finalized. Preliminary data for projects is only available for the Lao PDR project in Democratic Republic of Congo and one project in Brazil; therefore it is still too early to determine progress against expected results. / Volume of public and private climate finance mobilized / The current levels of leveraging funds are based on figures provided in the investment plans or SPCRs. The table below provides a summary. The projections are indicative and final figures will only be available when projects are proposed for Executive Board approval. Hence, figures need to be handled with caution because private sector projects usually consist of several sub-projects, which may not materialize or are different to the original proposal. / Projected Co-financing - April 2012 / (in USDm) / GOVERNMENT PRIVATE SECTOR MDBs OTHERS TOTAL / CTF1 6,958.6 9,981.5 11,822.3 5,036.6 33,799.0 / PPCR2 192.9 14.0 892.5 315.3 1,414.7 / FIP3 789.0 / SREP2 584.7 185.1 1,053.2 865.2 2,688.2 / TOTAL 7,736.2 10,180.6 13,768.0 6,217.1 38,690.9 / Note: Leveraged funds for projects yet to be approved are highly indicative. Amounts above are from endorsed IPs/SPCRs only. / 1 Based on actual leveraged funds for approved projects and projected co-financing for projects yet to be approved by the Trust Fund Committee. / 2 Based on SPCR/IP figures. / 3 Breakdown is still for confirmation with the MDBs. / Recommendations: / As with Output 1, this output target / description should be changed to provide the ability to obtain more specific results for each programme in line with Key Performance Indicators (KPIs) of the UK’s International Climate Fund (ICF). Defining what results will be measured, with clearly defined baselines, milestones and targets, has been a significant problem for the regular monitoring of progress of UK financing to the CIFs and is something the UK has been consistently pressing for. We will continue to press and will revise the indicators accordingly. / Some of the CIFs are further ahead than others, for example there remains limited information on the expected results under the Forest Investment Plan. We will take a tougher line with Country Investment Plans to ensure they make every effort to quantify – where possible – the impact of their proposed investments, particularly with relation to GHG mitigation which is the core objective of the FIP. The November 2012 CIF (and specifically FIP) meetings will provide an opportunity to push for and ensure robust and measurable results frameworks are in place. / Impact Weighting (%): 25% / Revised since last Annual Review? Y Increased due to changes to the forestry programme weighting – see output 5 for explanation / Risk: Medium / Revised since last Annual Review? N
[3] http://www.climateinvestmentfunds.org/cif/sites/climateinvestmentfunds.org/files/CIF_AR_2011_year_in_review.pdf

Output 3: Learning about piloting, demonstration, replication and transformation captured and shared in countries and across countries. / Output 4: Learning about piloting and implementation captured and shared across projects, programmes and funds. / Output 5: Learning about climate financing models captured and shared globally.
Output scores and performance descriptions: / Output 3: A – Outputs met expectation
Output 4: A+ - Outputs moderately exceeded expectation / Output 5: B – Outputs moderately did not meet expectation / Progress against expected results: / Indicators for each of these outputs were the same: Number of knowledge assets created; Frequency of use of knowledge assets; Level of client satisfaction with knowledge assets and, as such, have been considered in this review together. / Knowledge assets created / Over the year, the most significant knowledge asset to move forward was the Independent Evaluation of the CIFs. The evaluation is discussed further in under the results section below. / Strengthening lesson learning, knowledge management and communication: The UK presented a short paper on suggested measures to improve the operations of the CIFs to the CTF/SCF Committee meeting in June 2011, supported by other donors and recipients alike. The CIF AU subsequently produced a set of proposed improvement measures, which included the UK’s suggestions. This included a section on strengthening lesson learning, knowledge management and communication. We stated that the CIFs need to provide and effectively communicate a strong evidence base of results and lessons on climate financing that is transformative, innovative and goes beyond business as usual, highlighting that this would be particularly important as the Green Climate Fund is being designed through the Transitional Committee. / Specifically, we suggested that the CIF AU develop a much more accessible website, which includes communication products available by theme, and project data. Progress has been made on the web redesign, for example there is the facility to find documents by theme/programme/country/fund, and project data is readily accessible. The fully revamped website is expected to be up and running by summer 2012. / We also suggested that a social networking platform for knowledge sharing be developed. The CIF AU has responded by working on promoting further country and regional exchanges and sharing of experiences, through a Global Support Programme known as CIFNet – an on-line forum for pilot countries, other interested countries, stakeholder groups, including civil society, women’s groups, the private sector etc. It aims to build a community of practice between pilot countries and facilitate South-South learning. The knowledge sharing platform will, when complete, also include an M&E sourcebook and toolkit, which will enable users to download and share methods, tools, methodologies for design, implementation and reporting on projects. Users will be able to exchange views and experiences about the different indicators, tools, methodologies. CIFNet is under continuous development. / A significant product, arising from the UK’s ‘improvement paper’ was a Communication Strategy, which was presented at the May 2012 committee meetings. / See: Communication Strategy / Programmatic learning products for 2012 Partnership Forum. The CIF AU is developing the following learning products, with the SREP product having been completed: / CTF: Tools and approaches used to engage the private sector / FIP: Experience gained in collaboration and engagement at the country level with REDD+ stakeholders / PPCR: Sustaining national dialogue on the PPCR implementation process / SREP: How SREP can be used to prioritise energy sector interventions (completed) / The CIF website has further details of other learning products developed, including pilot country meetings for pilot countries to share experiences, and presentations at the UNFCCC meetings in Durban in December 2011. / See: http://www.climateinvestmentfunds.org/cif/content/knowledge-and-learning / Frequency of use: We are not aware that the CIF AU monitors the use of learning projects. We will recommend that this now happens within the different areas of the revamped website, and to request feedback from clients on usefulness – this should be used to inform continuous improvement of the learning and communications tool. / Level of client satisfaction: the new website has been developed in response to demands from recipient (and donor) countries to assist on particular challenges relating to lesson-learning, knowledge sharing and M&E. As above, we should request detailed assessments of levels of satisfaction with the final product when it has been fully functioning for some months (eg to report to the November 2012 meetings). The SREP learning product was a workshop, which took place at the Pilot Country meeting in Nairobi, Kenya in March 2012. The post-workshop evaluation highlighted that workshops, with a highly practical emphasis, are very useful to pilot countries. When asked whether a learning workshop was a useful and effective modality for sharing lessons learned in SREP, 100% of participants answered yes. Over two thirds of participants said that the CIFs should organise this type of in-depth workshop in the future, and integrate the focus on lesson sharing at the Pilot Country meetings as a whole. / The CIF Annual Report, beginning with the 2011 edition, is to be used as a global knowledge product, with each report going forward focusing on one aspect of learning that has been significant to CIF countries. The 2011 report looks at global renewable energy; the MDBs have focused on the renewables perspectives for their countries and regions. / Recommendations: / Independent Evaluation: we should continue to work with the Evaluation Oversight Committee (EOC) and the CIF Admin Unit to ensure that products / outputs generated from the independent evaluation can effectively influence the design of the Green Climate Fund. As stated above, we submitted comments pressing for action on timing to ensure that the evaluation is useful to the GCF design and establishment – at the same time highlighting that the quality, independence and credibility of the evaluation should not be compromised. We should continue to work with the EOC on our suggestion that the evaluation approach paper considers phasing the evaluation, in particular focusing primarily on the process aspects the GCF Board itself will be considering first, so that early evaluation findings can be helpful to the GCF design. / Measures to improve the operations of the CIFs – we should take into account the progress update at the next Committee meeting and press for action as necessary. / Web-learning: we should ensure that the CIF Admin Unit monitors CIFNet – both in terms of level of use and usefulness and act upon feedback. / 2012 learning products: all centred on useful themes (set out above), but we should ensure that they are practical and relevant, and that countries will be facilitated to implement lessons, in order that lesson learning in the CIFs is as effective as possible and meets the needs of pilot countries. We should discuss with the AU how it intends to use the learning products at the November 2012 Partnership Forum, if possible this should be through a series of workshops around the different learning themes, rather than presenting the documents, as feedback has highlighted that workshops are more useful learning tools. (There are, of course, cost implications for holding workshops, but this could be justified if the results would be practical lesson-learning and enhanced country level management of CIF funding.) / We should ensure that the CIF AU draws out cross-thematic lessons from the four different learning products and that these lessons feed in to the design of the Green Climate Fund. It is also important that the lessons from previous learning exercises feed in to the design of the 2012 learning products themselves, so we should liaise with the CIF AU to ensure stakeholders are able to comment on them. / DFID will commission an independent review on the effectiveness of the various national institutional arrangements put in place under the PPCR, in order to compare these and learn lessons for the design of the GCF. / Impact Weighting (%): 27% / Revised since last Annual Review? Y Output 3 is an amalgamation of the previous outputs 3,4 & 5. These were so similar that it was decided to merge them into one output – the previous weightings were 9% for each, equalling in total the new 27%. / Risk: Medium / Revised since last Annual Review? N (While there are some concerns about the lessons from the Independent Evaluation being available for the design of the Green Climate Fund, in other areas, there has been good progress over the year in the number of learning products developed and improvements in the way these have been used. On balance this doesn’t indicate the need to change the risk rating).

Output 6: CIFs governed with legitimacy and inclusion
Output 6 score and performance description: / A – Outputs met expectation
Progress against expected results: / The indicator for this output was ‘level of stakeholder satisfaction with CIF Governance’. / In terms of CIF governance the UK has been clear in setting out a number of reforms it would like to see under the Measures to improve the operations of the CIFs. In the June 2011 CIF meetings in Cape Town, the UK, reflecting on experience to date, highlighted five areas where the CIFs could be strengthened, and suggested some tangible indicators of progress by December 2011, one of the five was: / Country ownership and transparency: While at the global level and in global level consultations the CIFs have been strong, partnership behaviour at country level has been mixed. Progress partly depends on a range of measures being taken across the MDBs more generally, such as greater decentralisation. Specifically the CIFs should: / Engage with private sector associations and civil society in the development of all investment plans and, unless justified otherwise, projects. This engagement should be explicitly set out in each plan or project, along with clear plans for continuing stakeholder involvement in monitoring and evaluation / Improved transparency by eliminating closed executive sessions under the CTF. / Make the CIFs compliant with the International Aid Transparency Initiative. / At the CIF committee meetings in Washington on 3 November 2011, the joint committee of the CTF and SCF agreed UK proposals on a number of points which built on the UK paper, including those areas above. Examples of the UK’s indicators and agreed recommendations are set out in annex A2 of the CIF Business Case. / Progress was made at the Trust Fund Committee meetings in May 2012 on country ownership and transparency, for example how to further strengthen country-level partnerships among the MDBs, and to improve in-country collaboration amongst stakeholders operating at the country level. Full details can be found in the co-chairs summary of the Joint CTF-SCF committee meeting in May 2012. / At the November 2011 Joint CTF-SCF committee meeting it was agreed to eliminate closed sessions under the CTF – see Measures to Improve the operations of the CIFs / On IATI compliance the CIF AU provided a progress report to the joint committee in May 2012 advising of additional polices and next steps which may be necessary to ensure compliance. / NGOs / While NGOs remain concerned with issues on the policies and investments by the CIFs, comments on the governance of the CIFs by stakeholders is limited. There has also been good progress over the year to improve the transparency and inclusiveness of CIF governance. / NGOs have active observer status at the CIF Committee meetings, meaning that they can table questions. On governance issues, there was a request at the May 2012 Committee meeting within the FIP from an observer NGO for civil society observers to be treated as organizations rather than individuals, and for more than one individual from an elected observer organization to attend meetings. As this would have potential cost implications for NGOs not based in Washington the CIF AU was asked by the sub-committee to come back in November with implications across the CIFs. / On policy issues, some NGOs have consistently raised concerns through campaigns around the PPCR’s provision of both loan and grant funding, rather than solely grant funding. They have welcomed the fact that the majority of our new contribution to the PPCR is being provided as grant funding rather than as concessional loans, but are still concerned about the provision of loans to countries which they regard as being highly debt distressed. / The UK Government has responded to these concerns by setting out the distinct benefits of the different types of financing, by highlighting the country-demand for them, and by clarifying the PPCR approach to debt distressed countries. Loans, equity and guarantees maximise the total amounts of money available for developing countries, and can serve to mobilise further private sector money. Grants are put towards aspects of low carbon, climate resilient development where necessary expenditure may generate low or no financial returns. UK climate finance is a combination of capital and resource allocation to support the provision of both loans and grants, and to try to avoid distortion of competition in the private sector by providing undue subsidies. We have also clarified that the PPCR uses the World Bank’s Debt Sustainability Framework (DSF) to ensure that loans are not available to low income pilot countries who cannot afford to repay them, and that the PPCR does not apply the DSF to middle income pilot countries, who are entitled to request both grants and highly concessional loan financing under the pilot programme. The UK played an important role in ensuring that the PPCR sub-committee addressed this issue. / Two UK-based NGO reports have been issued in the last twelve months which have criticised separate CTF projects for not benefitting local populations. We provided responses via our press office. / Recommendations: / The UK should continue to use its seat on the Committees to ensure that the CIFs are governed with inclusiveness and transparency. We should closely follow implementation of the decisions from the May 2012 committee meetings on country ownership and IATI. / We should also ensure CIFs meet both climate and development objectives, providing broader benefits for local populations. This includes poverty alleviation, access to renewable energy, improved air and water quality, and local industrial development potential. / We welcome NGO views and scrutiny and will continue to ask for their views as appropriate. / Impact Weighting (%): 9% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 7: FCPF Readiness Fund assists developing countries to reach a capacity level at which they will be ready to participate in a future system for positive incentives for REDD+; and Carbon Fund tests and evaluates incentive payments for REDD+ in approximately five developing countries.
Output 7 score and performance description: / B – Outputs moderately did not meet expectations
Progress against expected results: / The indicators for this output were: Number and quality of REDD+ readiness preparation plans supported; Knowledge generated and disseminated by the FCPF including country advisory services; and Number and Quality of REDD+ Emission Reduction Programmes Supported. / The Forest Carbon Partnership Facility (FCPF) was established in 2008. Total contributions to the Readiness Fund now stand at US$230 million committed or pledged by 15 public donors. The Readiness Fund provides participating countries with support to prepare itself for REDD+, focused around Readiness Preparation Proposals (RPPs). / The Readiness Fund aims to assist developing countries to reach a capacity level at which they will be ready to participate in a future system for positive incentives to REDD. To date thirty-seven developing countries (14 in Africa, 15 in Latin America and the Caribbean, and eight in Asia-Pacific) have signed up to the programme. Of these, 23 countries have submitted RPPs for assessment, but only five have received grants to implement these proposals. / The engagement of 37 countries in the Readiness Fund points towards some success in the objective of assisting developing countries to build capacity for REDD+, with this being largely achieved through the raising of awareness and the sharing of experience through regular partnership committee meetings. / However, the low level of grant approvals is disappointing and points to some difficulties with the programme. All of the approved grants have been issued within the past year, which suggests a gradual improvement in performance. This should be closely monitored in the coming year. Difficulties appear to stem from cumbersome governance and decision-making, as well as fairly onerous requirements attached to the disbursement of relatively small grants (e.g. in the order of US$3.6m). / The Carbon Fund aims to deliver payments for verified emissions reductions in up to five countries. The Carbon Fund has become operational in the past year, and is currently working on methodological issues relating to the registration of emissions reductions programmes and the verification of avoided emissions. / The World Bank’s Independent Evaluation Group is currently undertaking a review of the implementation of the Bank’s 2002 forest strategy. DFID staff have contributed to this review. The scope of the review will encompass the FCPF and will help to inform future UK engagement with the FCPF. It is due to be published later in 2012. / Recommendations: / Monitor the Readiness Fund for improvement to the rate of uptake in grants. / Use the shared UK-Netherlands seat on the partnership board to encourage an acceleration of the programme. (Corrective interventions need to recognise the constraints which the FCPF’s broad-based multilateral decision-making place on the scope for individual donors to advocate changes from current practice). / Draw on IEG findings to inform future UK position on the FCPF. / Impact Weighting (%): 5% / Revised since last Annual Review? Y Since the increase in funding to other parts of the CIFs in 2011/12 the input to these funds has decreased as a proportion of the overall contribution, as a result we recommend reducing the weighting to 5% from 12% (FCPF and the readiness fund account for less that 2% of overall CIF (ETF) project funding from the UK. / Risk: Medium / Revised since last Annual Review? N

Output 8: The Congo Basin Forest Fund (CBFF) alleviates poverty and addresses climate change through reducing the rate of deforestation of the forests of the Congo Basin, with effective participation of Congo Basin countries in climate change initiatives deriving sufficient benefits for conservation of resources and enhancing livelihoods of populations living in the forest.
Output 8 score and performance description: / B – Outputs moderately did not meet expectation.
Progress against expected results: / The indicators for this output were: To reduce the average rate of deforestation in the Congo Basin region from 0.19 to 0.10% and increase the forestry sector contribution to GDP from 15-20% by 2018 (sunset date for CBFF). / The CBFF is managed as a special fund by the African Development Bank (AfDB). An external operational effectiveness review was recently commissioned by the CBFF secretariat. The review has highlighted that whist the CBFF is very relevant and supporting some innovative and transformational projects (particularly in the DRC), project management has not been as effective as we would expect. This has been primarily due to difficulty in working with existing AfDB fiduciary and project management procedures, and the limited capacity of some grantees to comply with these complex procedures. We are currently working with the CBFF secretariat, AfDB and other CBFF donors to ensure that the review recommendations are acted upon and lead to an improvement in fund performance. / No milestones or targets have been set for this output; as such progress below is not being measured against expected results or baselines. However, with a portfolio of 41 projects amounting to €84 million, the CBFF is becoming an important mechanism in the fight against deforestation, forest degradation and poverty and a major partner in fostering REDD activities in the Congo Basin region. / The majority of existing CBFF projects focus on sustainable forest management practices (approximately 37% of portfolio value) and livelihoods development (36%). REDD pilot projects represent 14% of the portfolio and headway has also been made in supporting monitoring, assessment and verification (MRV), as well as benefits from carbon markets. / For example, the CBFF approved 6 projects to the Ministry of Environment, Conservation of Nature and Tourism in DRC in support of 5 pilot REDD projects and a training and capacity building project within the REDD framework for Government and civil society. Together these projects will contribute to the development and implementation of a national REDD strategy for DRC. A regional project in support of developing harmonised national MRV systems for REDD across the region has also been supported by the CBFF. / During 2011/12, the main focus was to improve the performance of the fund and to ensure the current portfolio of projects were operational. To this effect: 25 projects were appraised, 19 were approved by AfDB management, 13 grant agreements were signed, and total disbursements amounted to €4.28 million compared to €1.36 million in 2010. / A fund management agent (FMA) was recruited at the end of 2010/11 and is now responsible for grant disbursement, monitoring, reporting, and evaluation (in place of the CBFF Secretariat) for all projects under a threshold value of €2,500,000. During 2011/12, the FMA developed simplified operational procedures for reviewing projects and organized training workshops for grant recipients on the Bank’s rules and procedures for procurement and disbursement. This has facilitated good project management and improved disbursement rates. The FMA has also been working to develop simplified procedures for procurement and disbursements which should further improve performance in 2012. / Recommendations: / The UK will follow up as part of the CBFF governing council to ensure: / Overall disbursement of funds to projects and implementation of project activities has been lower than expected. The CBFF must therefore continue to focus on improving the management and performance of the existing portfolio. / The CBFF’s monitoring and evaluation framework requires strengthening (there is currently no SRF), especially reporting the cumulative impact of individual CBFF projects. Revision of the current CBFF logframe and the development of a monitoring and evaluation framework should be a priority for the CBFF in 2012. / An external operational effectiveness review was carried from January to May 2012. The review has made a number of specific recommendations on how fund operations, performance and its strategic focus can be improved. The CBFF governing council (GC) should ensure that the recommendations made in the operational effectiveness review are considered and acted upon at the next GC meeting, due to take place in London on 27th June 2012. / Impact Weighting (%): 9% / Revised since last Annual Review? Y As with output 5 - since the increase in funding to other parts of the CIFs in 2011/12 the weighting to these funds has decreased as a proportion of the overall contribution, as a result we recommend reducing the weighting to 9% from 12% / Risk: Medium / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? Y / At the last review it was proposed that the CIFs, CBFF and FCPF be reviewed separately through producing separate logframes (or results frameworks). This recommendation is still being actioned as set out below: / CIFs: With the new contribution to the CIFs in the last year, it was proposed to develop a new logframe covering just the CIF outputs and outcomes. This logframe is still under development, mainly for the same reasons as the previous ETF logframe was not fully developed with milestones and targets. This is because, at the level of the individual CIF projects, the 4 results frameworks for the CTF, PPCR, FIP and SREP have not as yet produced aggregate milestones and targets for the identified outputs. The intention was always to build these up from the constituent investment plans and projects. / Over the last year a new issue has emerged that further delays finalisation of the CIF results frameworks, but ultimately will make them more manageable and able to report clear results: In June 2011 the UK suggested, as part of its proposed improvements, that MDBs identify 3-5 core indicators for each programme. In response, the MDBs and recipient countries have fed back that the Trust Fund Committee endorsed results frameworks as a whole are unworkable given the large number and level of indicators. As a consequence, starting with SREP, but also underway with the other CIF programmes the results frameworks are now being revised and simplified to identify 5 to 10 core indicators (this is similar in approach to the UK’s Key Performance Indicators being developed for the International Climate Fund). This is still work in progress. The first simplified results framework for SREP was approved at the May 2012 SCF Trust Fund Committee. The simplified PPCR and CTF results frameworks will be approved at the November 2012 committee meetings. The FIP results framework will be approved at the May 2013 sub-committee meeting. / CBFF: The CBFF log frame has not been revised since the last review. However, an external evaluation of the CBFF is on-going and will make recommendations for how the logframe should be revised. Revising the logframe, updating the CBFF operational strategy and developing a monitoring framework will all be completed in 2012. / FCPF: The FCPF is included within the ETF logframe. It has not been updated since the last review. An independent review of the World Bank’s forest strategy is ongoing and will encompass FCPF. This will help to inform future UK objectives around this programme. / 1.2 Overall Output Score and Description: / A (Outputs met expectations)
1.3 Summary of overall progress / Overall, there has been mixed progress against the outputs (1-8 above) though the majority of programmes are meeting expectations and some are exceeding them. Highlights over the year include: / Good progress by the CIF Admin Unit and MDBs on improvements to the CIFs arising from the UK’s paper from June 2011. This is despite limited staff resources within the Admin Unit; / Significant progress over the year for the Programmes under the Strategic Climate Fund (SCF) i.e. PPCR, SREP and FIP, in endorsing the remaining Investment Plans, which goes beyond the initial numbers envisaged when the UK’s ETF funds were approved. / Increasing acceptance of the value of the CIFs as demonstrated by a succession of approaches by recipient countries to receive funds under the CIFs and continuing contributions from new and existing donors; / As part of the CIF improvements, CIFs are getting better at learning lessons, and sharing information and best practice at the country and programme level; / Effectively mobilising a significant amount of additional finance for low carbon, climate resilient development. / 1.4 Key challenges / However there are a number of risks and weaknesses that still remain, that will require engagement by the UK over the coming year and action by the CIF governance and MDBs: / Slow progress on establishing results frameworks. Results reporting (as set out above) is a significant problem to enable regular monitoring of progress of UK financing to the CIFs and an area the UK is continually prioritising in engagement with the CIF Admin Unit, MDBs and CIF Trust Fund Committees; / Slow speed of disbursement and project approval from initial Investment Plan endorsement; / Variable quality of some Investment Plans and projects; / Lack of a risk management framework that the Trust Fund Committees can annually review. This has led to a lack of discussion over the low ambition of project proposals, which means the CIFs are not necessarily being sufficiently innovative which – in turn – may weaken additionality of CIF funding (there are some clearly highly transformational investments in the portfolio but also some weaker ones); / While the CIFs AU and MDBs have aimed to do more with the private sector, so far engagement and therefore leverage of private sector finance, has been limited; / Lack of fund and programme level lesson learning to inform the future climate architecture. While having a credible Independent Evaluation of the CIFs is important, there is a risk that some lessons from this may be too late to effectively influence the design of GCF; / There remains lack of clarity over future of CIFs and implications for the potential funding gap should the GCF not be up and running quickly (this in part is due to waiting for the GCF board to meet, which will give an indication of how long the CIFs need to provide climate finance over an interim period before the GCF starts).
1.5 Annual Outcome milestone assessment / The outcome statement, as used in previous annual reviews was to Transform energy supply and demand, and forest use, and increase resilience to climate change in developing countries. / Previous annual reviews have indicated that milestones and baselines for the CIF results frameworks are still under development as these need to be linked to the individual projects that are funded. This is still the case as has been discussed above. As such it is premature to make detailed assessments of whether the outcome, as currently drafted, will be achieved at this stage. / Again as discussed above with the new contribution to the CIFs in the last year it is proposed to fully revise the logframe. This, however, will follow the finalisation of the CIF results frameworks and as such the outcome statement will change in the new logframe. This outcome statement will need to have detailed baselines, indicators and targets. Ideally these will be comparable to the Key Performance Indicators (KPIs) that are being developed for the International Climate Fund (ICF).

2. Spending profile and timescale
2.1 Is the spend profile detailed in the Business Case being followed: Y / The spend profile is as planned. Up to March 31 DFID has deposited six promissory notes out of a total of eight. These promissory notes (PNs) are encashed annually under terms and a schedule agreed between DFID and the Trustee. Details of the PN deposits and encashments are described in the tables below. / DFID Contribution – all figures in UK £m / DFID Promissory Note Deposits / Actual (and planned for 2013 & 2014) / DFID 03 2009 05 2009 04 2010 11 2010 01 2012 03 2012 03 2013 03 2014 / PN1 PN2 PN3 PN4 PN5 PN6 PN7 PN8 / PPCR 197.50 8.75 2.75 - 101.00 - 57.00 15.00 13.00 / CTF 220.00 30.00 85.00 77.50 27.50 - - - / PROV 16.50 - - 16.50 - - - / FCPF 1.75 1.25 0.50 - - - - - - / CF/FCPF 5.75 - 0.75 - 5.00 - - - - / CBF 25.00 1.50 6.00 17.50 - - - - / FIP 37.50 6.00 - - 31.50 - - - - / SREP 25.00 2.50 5.00 - 17.50 - - - - / Total 529.00 50 100 95 155 44 57 15 13 / Encashments against promissory notes / 2009 to date, and future projections for 2013,14 & 15 / DFID 08 2009 01 2010 01 2011 01 2012 01 2013 01 2014 01 2015 Total / PPCR 3.00 - 24.79 26.26 54.80 75.65 13.00 197.50 / CTF 29.00 70.08 42.42 44.93 25.87 7.71 - 220 / PROV - - - - - - 16.49 16 / FCPF 1.75 - - - - - - 2 / CF/FCPF 0.75 - 5.00 - - - - 6 / CBF 7.50 - 17.50 - - - - 25 / FIP 1.55 - 8.26 8.75 11.60 7.33 - 38 / SREP 2.00 - 5.10 5.84 7.73 3.92 - 25 / Total 45.55 70 103 86 100.00 94.62 29.49 529 / DECC Contributions - all figures in UK £m / Promissory Notes deposited / DECC 03 2009 05 2009 04 2010 11 2010 2011 12 2011 03 2012 / PN1 PN2 PN3 PN4 PN5 PN6 PN7 / PPCR 112.50 8.75 2.75 - 101.00 - / CTF 298.42 30.00 85.00 77.50 106 - / PROV - - - - - / FCPF 1.75 1.25 0.50 - - - - / CF/FCPF 5.75 - 0.75 - 5.00 - - / CBF 25.00 1.50 6.00 17.50 - - / FIP 62.50 6.00 - - 31.50 5.00 - - / SREP 50.00 2.50 5.00 - 17.50 - 25.00 / Total 555.92 50 100 95 155 5 106 25 / Encashments against promissory notes / 2009 to date, and future projections for 2013,14 & 15 / DECC 08 2009 01 2010 01 2011 01 2012 01 2013 01 2014 01 2015 Total / PPCR 3.00 - 24.79 26.26 34.80 23.65 - 112.50 / CTF 29.00 70.08 42.42 44.93 44.87 35.20 31.92 298.42 / PROV - - - - - - - - / FCPF 1.75 - - - - - - 1.75 / CF/FCPF 0.75 - 5.00 - - - - 5.75 / CBF 7.50 - 17.50 - - - - 25.00 / FIP 1.55 - 8.26 15.00 17.85 13.58 6.25 62.50 / SREP 2.00 - 5.51 5.84 11.66 19.00 6.00 50.00 / Total 45.55 70 103 86 109.17 91.44 44.17 555.92 / 2.2 Does the review of the cash balance position raise any concerns around payment in advance of need: No / When setting up the encashment schedules for the additional funds in December 2011 DFID questioned the CIFs liquidity needs, including the Trustee’s cash balance position. The Trustee responded with sufficient assurance that current encashments were based on their actual needs. The new encashment schedule was agreed on the basis that liquidity needs would be looked at again in 2012 as part of an ongoing assessment of need. This will be done in time for the January 2013 encashment to ensure no payments in advance of need are taking place. / 2.3 Have additional payments linked to good performance been triggered: Not Applicable / N/A.

3. Evidence and Evaluation
3.1 Assess any changes in evidence / Below is a brief assessment on further evidence we have since the Multilateral Aid Review (MAR) of the CIFs was published. The CIF MAR included a number of areas of weakness and where reforms were needed. This led to the June 2011 paper (as discussed above) that the UK set out areas where the CIFs should seek improvements. Below is an update of evidence we have against each of these areas: / Development impact, including gender: CIF AU have agreed that indicators of development and poverty reduction impacts will be included in all proposals submitted for CIF funding from FY2013. In the interim, it has been agreed that all proposals submitted should integrate and describe – either quantitatively or qualitatively - the development impacts. The progress on gender has been slow – but the gender impact assessment is now expected to be completed for the end of 2012. / Country ownership and transparency: / Country ownership: CIF AU has devised a set of detailed measures to strengthen country coordination which were agreed at the May 2012 meeting, and will take on board civil society feedback on clearer articulation of the need to engage with a range of organisations including private sector at country level. / Transparency: progress has been made on CIF compliance with IATI which will move forward with wider World Bank IATI compliance, as the CIFs are not a separate signatory themselves. In addition to the availability of programmes and projects on-line, Committee comments are now routinely published.. / Innovation, private sector and additionality: a paper setting out proposals for additional tools and instruments to enhance private sector investments in the CIFs was agreed at the May 2012 meetings, with amendments - the finalised version is yet to be circulated. We will comment when it is. We want CIFs to develop, in parallel: a robust risk management framework; specific operational guidelines for financial instruments currently permissible under the CIF where such guidelines would help promote more diversity in instruments used in the CIF portfolio; and a detailed proposal as to how to facilitate the use of local currencies in CIF funded projects and programmes. (It is proposed that the Independent Evaluation considers the additionality issue.) / Results: RFs for CTF, PPCR & FIP are still under development. A simplified SREP RF was presented to the May 2012 meetings and approved. CIF AU has promised draft RFs for all programmes for the November 2012 meetings. They are also working on the development of clear tools and guidelines as to how the results framework cascades to the country investment plan and project level; developing a web-based monitoring and evaluation platform; and the indicators of development or poverty reduction for each CIF funded project or program. / Lesson learning: refer to output 3 on lesson learning. / Other areas of updated evidence include on admin costs and progress by the MDBs against MAR criteria: / Admin costs: the CIF FY13 Business Plan and Budget was presented and discussed at the May 2012 CIF Committee meetings. This shows that total administrative costs will, by end FY14, have amounted to 7.5% on cumulative project funding for the SCF, 1.3% for the CTF, and 3.1% for the CIF as a whole. The 7.5% ratio for the SCF is 1.4% higher than last year, reflecting the impact of an expected 30% increase in the number of SCF projects. These administration costs are higher than those anticipated in the CIF business case and will be kept under review. / MDB progress / Results: Following the example of the Asian Development Bank (AsDB), most Multilateral Development Banks are making good progress on measuring and reporting their results. The World Bank has adopted an institution-wide Corporate Scorecard for measuring progress, to be presented annually to Governors. The African Development Bank (AfDB) published its first Annual Development Effectiveness Review in the summer of 2011. / Cost and value for money: Among Multilateral Development Banks, the AsDB committed to a 2% annual productivity improvement in 2012 and the AfDB identified efficiency savings in its 2012 administrative budget. The World Bank remains committed to a flat real administrative budget and its Corporate Scorecard tracks the time required to prepare projects and the costs associated with project preparation. / Transparency and accountability: AfDB and IADB signed up to IATI in 2011 (IDA and the AsDB had already signed up to IATI). / Gender: The World Bank gave gender issues prominence internationally with its 2012 World Development Report on Gender Equality and Development and adoption of gender as the focus for the 2011 Annual Meetings. The Bank also committed to hold itself accountable against gender mainstreaming targets that assess the impacts on girls and women of any Bank action. / 3.2 Where an evaluation is planned what progress has been made? / As set out in the governance frameworks of the CTF and SCF, there will be an Independent Evaluation of the CIFs, carried out by the MDBs’ evaluation departments. The two principle objectives of this evaluation are: / to assess how effectively the CIFs are designed and operating to achieve transformative change in the areas of climate adaption, climate mitigation, and forestry; and / to draw lessons from the experience of the CIFs to inform future climate finance. It is currently scheduled to issue its final report in November 2013. / At the May 2012 CIF Committee Meetings, the UK, and other Committee members, pressed for the timeframe of the Independent Evaluation of the CIFs to be sequenced so that early lessons from the Independent Evaluation - particularly on Institutional Arrangements & Governance - could feed into the development of the Green Climate Fund. The UK has also sent detailed written comments to the CIF Admin Unit following the meeting, and engaged in VCs with the Evaluation Oversight Committee (EOC), to highlight that to ensure the evaluation is of use, and is used, findings from the evaluation need to be available soon so as to be valuable in the development of the Green Climate Fund. / The evaluation will be formative rather than summative, focusing on the process aspects of programme design, governance, management and the general establishment of the CIFs, rather than looking for higher level outcomes or impact at this stage. The UK commented to the CIF AU that this will be most helpful as lesson learning for the design of the future climate financing i.e. the Green Climate Fund, but we also said that it would be useful if some early outputs and outcomes were considered so as to provide a trajectory to impacts. / The UK highlighted the need to put in place a mechanism to further strengthen the independence of the evaluation and this was supported by others at the joint committee meeting in May 2012: the Committee requested that the EOC present a proposal for establishing an international reference group of eminent people, with a balance between experts from developing and developed countries, to advise the oversight committee in order to ensure credibility and independence. / We should continue to work with the Evaluation Oversight Committee (EOC) and the CIF Admin Unit to ensure that products / outputs generated from the independent evaluation can effectively influence the design of the Green Climate Fund. As stated above, we submitted comments pressing for action on timing to ensure that the evaluation is useful to the GCF design and establishment – at the same time highlighting that the quality, independence and credibility of the evaluation should not be compromised. We should continue to work with the EOC on our suggestion that the evaluation approach paper considers phasing the evaluation, in particular focusing primarily on the process aspects the GCF Board itself will be considering first, so that early evaluation findings can be helpful to the GCF design.

4. Risk
4.1 Output Risk Rating: Medium / 4.2 Assessment of the risk level / The last update of the risk register was carried out by the Cross-Whitehall group in March 2012 and it focused upon the following issues: / Speed of disbursement: (Amber) – risk level decreasing. / Following UK highlighting this as an area for improvement in June 2011, the MDBs proposed in November 2011 setting targets for submitting project proposals for approval of CIF funding after endorsement of an investment plan and for beginning disbursement after MDB approval of CIF funded projects. These proposals were discussed at the May 2012 committee meetings. This could see funds released from stalled or slow moving projects. The Trust Fund Committee also approved more ambitious targets to drive more rapid release of funds. / Mitigation: The Cross-Whitehall team is going to undertake an analysis of both the operational and reputational risks around disbursement and the risk register will be updated following the results of this analysis. This will enable us to clarify how best to mitigate against the assessed level of risk. / NGO / recipient / other stakeholders’ negativity: (Red/Amber) The risk level is decreasing. / Other donors have recently pledged further funding to the CIFs (e.g. Canada, Norway). / With regard to NGOs, the UK will continue to advocate for the participation of NGOs in CIF meetings so that they are connected and exposed to the views of developing countries. The UK welcomes NGO feedback and policy scrutiny. As appropriate, we will continue to ask for their views (eg they have previously fed-in to feedback to the CIF AU on lesson-learning), this inclusivity means that the CIFs benefit from value-add of civil society knowledge. / With regard to developing countries, requests to be considered for funding for programmes have been received by the CIF Admin Unit (eg DRC, Ethiopia, Mauritania). However, in the case of PPCR the decision by the sub-committee not to open it up to new countries may increase the risk of negativity from those countries, and there is also a risk that the process to allocate new funding to existing countries, including through a competitive window, may be controversial and cause some negativity. / Regarding other stakeholders at the May 2012 CTF/SCF committee meeting, EIB, KfW and AfD all requested to be considered as implementing agencies. This would indicate a decrease in this risk. / Mitigation: These issues and risk will need to be kept under review. / HR: (Amber/Green) – risk level decreasing. The Cross-Whitehall group has set out roles and responsibilities on the CIF portfolio in a Management and Accountability document and we are satisfied that HMG resources are adequate to effectively engage and manage the CIFs. / Mitigation: The Cross-Whitehall group are assessing whether the arrangements for DECC assurances for adaptation spend under the PPCR need to be strengthened for future spend. / Capturing lessons: (Red/Amber) – risk level increasing. The Cross-Whitehall group voiced concerns that lessons for the UNFCCC – principally the design of the Green Climate Fund – are not currently being captured in a coherent and strategic manner and noted that this is a high risk. There is also a risk that timing of the Independent Evaluation Risk does not fit well with feeding in to the design of the GCF. / Mitigation: CIF AU will present to the November committee meetings on the GCF – we should feed in early views to this paper. We are also in contact with the EOC regarding the timing of the evaluation and the need for early findings to be made available so as to be useful to the GCF. / Pledges: (Amber/Green) – risk level decreasing. It was agreed that although contributions from other donors are forthcoming (see above for detail), there are still some risks around whether/when the pledges from the US will be met. Plus, we are entering a period of uncertainty over future international climate architecture which may reduce the number of future pledges to the CIFs. / Mitigation: we plan to hold a strategic discussion on the future of the CIFs at the November 2012 Committee meetings to decide on their role, if any, in the future climate architecture. / Results: (Red) – risk level increasing. It was agreed that this continues to be a high level risk, as results frameworks, baselines, indicators and targets have yet to be finalised. / Mitigation: actions discussed included UK continuing to work on international consensus building on monitoring and evaluation (M&E) and the possibility of using portion of ICF M&E budget to target CIFs. / Carbon savings: (Red) – [new risk]. The Cross-Whitehall group added a risk around the Clean Development Mechanism (CDM) and the potential lack of additionality on carbon savings. / Mitigation: UK ideas for approaching the CDM issues include strengthening CTF investment criteria to avoid overlap between IPs and the CDM, and undertake a screening of current projects to check for any overlap. DECC is taking forward this piece of work.
Risk of funds not being used as intended / The World Bank serves as the Trustee for the CIFs and follows World Bank policies and procedures for the funds it administers. The Bank (as highlighted in the MAR) has strong internal controls, fiduciary management and audit compliance. / As mentioned in section 2.2 above, the encashment schedule was set up to ensure funds were not being provided in advance of need. However, this will be reviewed with the Trustee for the 2013 encashment. / As highlighted under key challenges the lack of a risk management framework that the Trust Fund Committees can review is a concern to the UK. This is being addressed as requested by the UK at the May 2012 CIF Committee meetings. / 4.4 Climate and Environment Risk / The Multilateral Aid Review assessment of 2011 did not highlight any concerns for the CIFs and the climate and environment assessment in the last business case the Environmental Screening Note –(ESN) prepared for the UK’s first contribution to the CIFs did not identify improvements, but rather set out areas for monitoring. Now that most investment plans have been endorsed and projects are coming to the CIF committees for approval, the most relevant section of the ESN are set out below, as a marker over the coming year for us to ensure that they are considered: / Programme-level administration / Although country selection criteria include preparedness for actions, the capacity of many Least Developed countries to transform their development policy and planning to accommodate climate resilience, fund programmes, large-scale adaptation projects and climate information will be weak – and especially in the ability to predict secondary environmental effects. / Country investment plan and project selection / Environmental Impact Assessments will be mandatory for large-scale energy and infrastructure projects or for the cumulative impacts of smaller scale developments. It is the responsibility of implementing agencies to undertake environmental impact assessments, using national systems where appropriate. / Design questions and indicators for national implementation plans and project proposals include: / Number of proposals screened at concept stage / Number of environmental appraisals undertaken / National policy adaptation and amendments / Term recruitment/secondment of environmental advisers / Baseline climate data publication / Reduced emissions and degradation indicators / Adaptation and resilience measures in place / The World Bank, as lead partner, is responsible for producing performance frameworks/logframes for the CIFs as a whole and the various elements within the CIFs, which are at different stages of development. We will work closely with the Bank and other donors to ensure that these actions are captured in the performance frameworks. / We are working closely with the CIF AU on the development of the CIF results frameworks; although we have consistently pressed the CIF AU for the development of comprehensive Results Frameworks Progress has been slow; RFs with baselines, indicators and targets are yet to be finalised.

5. Value for Money
5.1 Performance on VfM measures / The following sets out value for money measures against each of the CIF programmes. As very few projects are yet to deliver tangible results, performance on VfM measures is based on expected results. In some instances, expected results cannot be given across all funds / programmes. An explanation is provided where this is the case. An update on financial leverage of the CIFs is also provided: / CTF / Expected emission savings for CTF: 1.6 billion tonnes of CO2e from Phase I investment plans[4]. DECC economists will need to quality assured these expected emissions savings to assess methodological consistency with the ICF, in particular with regards to attribution and accounting for the sale of carbon credits for compliance purposes. / Expected job creation for CTF / Expected increase in energy access for CTF / Expected increase in Capacity for CTF / Cost-effectiveness of abatement for CTF: HMG has not calculated these figures as the projections made at present are likely to be inaccurate and it will be more appropriate to wait for the CIF results frameworks to set these out once finalised. / SREP / Please note that all of the SREP calculations have been made using the investment plans of Kenya, Ethiopia, Honduras, Nepal, Mail, Maldives and that they do not take into account the £50million reserve. / Expected emission savings for SREP: 102 MtCO2e / Expected job creation for SREP: No aggregate figures available yet. / Expected increase in energy access for SREP: number of people with increased access to energy: 3.2 million. / Expected increase in Installed capacity for SREP: 867 MW of renewable energy on completion of all projects. / Cost-effectiveness [of abatement] for SREP: 24.7 $/TCO2e (total cost/TCO2 ($) – NB this is the capital investment cost per tonne, not the marginal abatement cost). / PPCR / The PPCR stresses the role of catalysing complementary forms of investment (not always financial) in communities, markets, communications, governmental institutions and physical infrastructure that together provide a foundation for adaptation. The investment projects also focus on bringing about additionality to identified development efforts. By doing so, the projects tend to be focused not only on priority sectors, but aligned with priority initiatives. From a cost effectiveness perspective, for example, the Cambodia PPCR investment plan estimates that $1 of PPCR funding results in $4 of development investment being made climate resilient. Care is also taken to elicit a clear overview of regulatory and communication challenges with resilience activities and projects must include institutional engagement and knowledge management activities. While most national programmes have now been approved under the PPCR, detailed project preparation work remains underway and as such the availability of detailed results frameworks and logframes is limited. There are a number of indicators used for each project, but these tend to be output based (i.e. number of people benefiting from some from of resilience), and not fully monetised in any form of formal cost benefit assessment. / Examples of expected PPCR results from Cambodia (their Strategic Programme for Climate Resilience funding is US $86m): / 30% reduction on the number of households with an income lower than the poverty line; / 40% reduction on the number of households with insufficient rice production for year-round consumption; / 30% average income increase in PPCR target areas; / installed drip irrigation system and other water saving technologies for 20,000ha of crop farms; / installed all-weather post harvesting facilities for 20,000ha of crop farms. / FIP / One of the core objectives of the FIP is GHG mitigation. We are continuing to work with the CIF Admin Unit to try to ensure that country investment plans quantify, as far as possible, the impact of investments, especially regarding GHG mitigation. The FIP programme is not as advanced as the CTF/SREP/PPCR programmes, and the analysis of reduction projections or potential is still based on investment plans (not approved projects). Figures are likely to change when detailed project designs are finalized. / Examples of expected FIP results / Some preliminary expected results from FIP funding in the Democratic Republic of Congo: 14.9Mt CO2e expected GHG emission reduction (DRC’s FIP Investment Plan funding is US $60m). In Laos, the expected outcome is: 5.3MtCO2e expected GHG emission reduction (Laos’ FIP Investment Plan funding is US $30m). / Co-financing across CIFs / The CIF Admin Unit provided the following leveraging data in April 2012, based on figures provided in endorsed investment plans and a combination of approved projects, and those in the pipeline for approval. It highlighted that projections are indicative, should be handled with caution, and that private sector projects usually consist of several sub-projects which, ultimately, may not materialise, or may be different to those originally proposed. / The figure for the FIP is based on endorsed IPs and is not broken down in categories (government, private sector, MDBs, others). / CIF / Projected Cofinancing- (April 2012) / (in $ million) / GOVERNMENT PRIVATE SECTOR MDBs OTHERS TOTAL / CTF1 6,958.6 9,981.5 11,822.3 5,036.6 33,799.0 / PPCR2 192.9 14.0 892.5 315.3 1,414.7 / FIP3 789.0 / SREP2 584.7 185.1 1,053.2 865.2 2,688.2 / TOTAL 7,736.2 10,180.6 13,768.0 6,217.1 38,690.9 / Note: Leveraged funds for projects yet to be approved are highly indicative. Amounts above are from endorsed IPs/SPCRs only. / 1 Based on actual leveraged funds for approved projects and projected cofinancing for projects yet to be approved by the Trust Fund Committee. / 2 Based on SPCR/IP figures. / 3 Breakdown is still for confirmation with the MDBs. / CTF specific co-financing and leverage / Below is some CTF specific data on co-financing and leverage at the project level. / Expected co-financing leverage ratio for CTF[5]: 7.4. This new ratio is based on better information from 33 individual projects approved by the Trust Fund Committee (TFC) as of March 2012 with a total value of $1.92bn. This is higher than the estimated ratio of 6.5 in the November report update but lower than the 2011 Annual Report estimated ratio of 8.4. / The following caveats around leverage should be taken into account: / The indicator currently reflects expected future levels of finance – this will change as more projects are approved and developed and it will be some years before actual flows are realised and can be monitored, reported and verified. / Leverage implies causality - whilst analysis will take into account the likelihood of crowding in additional funds - in some instances the ratio just reflects co-financing rather than finance that has been crowded in by CIF funds. / Leverage ratios across projects and countries are not comparable – a ‘good’ leverage ratio is dependent on the context, in particular the expected project risk and reward. / Levels of finance are ‘a means to the end’ - the effectiveness of climate finance will depend on the achievement of results (i.e. emission reductions). Other core indicators once available will provide supportive evidence in future. / Carbon market co-financing / We, along with other members of the joint CTF/SCF Trust Fund Committee, have asked the CIFs to prepare a paper on carbon markets for the 2012 November Committee meetings. This paper will examine the interactions between CIF financing and the carbon markets, including the current and expected scale of carbon market co-financing in the CIF pipeline. The paper is expected to discuss the advantages and disadvantages associated with these interactions based on views of Committee members, observers, and other stakeholders. / HMG project cost / The CIF Programme is managed by a DFID A2 (G7) deputy head of team, with inputs from two B1 policy officers and the four policy leads for SREP, PPCR, CTF and FIP. FTE = SCS G5 0.05 / A1 0.1 / A2 0.7 / B1 x2 0.5 each / A2 Policy Leads x4 0.25 each. / While DFID is the lead Department on management of the CIFs, the following DECC resources are also allocated to the management of the CIFs: 0.33 FTE HEO; 0.15 FTE G7; 0.05 FTE SCS (PB1). These staff are based within the International Climate Policy and Finance team. / 5.2 Commercial Improvement and Value for Money / CIF programmes are implemented by MDBs and therefore follow the MDBs’ procurement policies and procedures. MAR findings related to the relevant MDB’s approach to procurement, in terms of whether procurement is driven by cost control, targets for procurement savings, and monitoring and reporting on prices, are summarised below. / Overall, the MDB approach to procurement aims to ensure open and fair competition in all tenders, to procure high quality goods and services at the lowest cost. Procurement of goods and services goes through International Competitive Bidding (with limited exceptions). The MAR, however, notes that these procurement procedures are criticised by recipients and donors for their imposition of high transaction costs, delays, and uncompetitive prices. / Measures are being taken by the MDBs to address concerns, for example, the World Bank has begun a review of its procurement policies and practices and to better align procurement with the World Bank’s development objectives. The UK is engaging fully with the World Bank to ensure that this review addresses the issues about which we are concerned. This includes the possibilities of using country systems to lower transactions costs and avoid duplications, which is dependent upon robust, rigorous systems that meet international standards being in place. / The World Bank remains committed to a flat real administrative budget and its Corporate Scorecard tracks the time required to prepare projects and the costs associated with project preparation. The AsDB committed to a 2% annual productivity improvement in 2012. / In December 2012, there will also be a review of procurement and fiduciary processes in fragile and conflict states to speed up implementation. In addition, the Operations Policy and Country Services Vice-Presidency has recently set-up an informal team to help operations teams quickly resolve procurement problems. The MDBs work together on procurement rules and standards, and use systems in similar ways. Therefore the recommendations from the World Bank study will be adopted by all the banks. / African Development Bank (AfDB) / AfDB procurement rules use international competitive bidding, but there are no targets for procurement savings. Prices are monitored where there have been concerns about high unit costs, and this is fed into guidance for staff on contract negotiation. Annual reports on corporate and operational procurement, including data on savings, are produced for the Board of Directors and published on the AfDB website. / Asian Development Bank (AsDB) / AsDB has restrictions on procurement from non-member countries; this constrains its ability somewhat to pursue economy and efficiency. Procurement procedures are criticised by recipients and donors for imposing high transaction costs, delays and uncompetitive prices. / European Bank for Reconstruction and Development (EBRD) / The EBRD’s approach to procurement is driven by VFM. It has procurement policies and rules consistent with its objectives of appropriate use of funds and efficiency of operations. The EBRD places no restriction upon the procurement of goods and services from any country, and generally requires the use of international competitive tendering for public contracts. Private sector operations may follow other established commercial practices in addition to formal open tendering. / Inter American Development Bank (IADB) / The IADB also has restrictions on procurement from non-member countries which constrain its ability to pursue economy and efficiency. Procurement rules use international competitive bidding. IADB is criticised by recipients and donors for high transaction costs, delays and elevated contract prices for Bank projects. However, in June 2010, the Executive Board approved a Strategy for Strengthening the Use of Country Procurement Systems. This creates the possibility to use country systems or sub-systems for the procurement of goods and services which should increase the scope for cost efficiency gains from local procurement. / World Bank Group / World Bank procurement policy is driven by “economy and efficiency” as outlined by their Articles of Agreement. In IDA, international competitive bidding is used for all contracts (with exceptions only if the nature of the procured goods or services, or the size of the country, justifies them). There is anecdotal evidence that IDA contract prices are higher than contracts elsewhere, but IDA does not monitor the impact of its procurement on local market prices. In the IFC, competitive procurement is mandatory for all operational procurement above $50K and must be advertised. In order to further assure value for money, certain steps are required for procurement above specified threshold values. IFC is implementing a new, mandatory, web-based procurement tool (eConsultant2), which will further ensure compliance. IFC has also introduced a number of sustainability measures into its procurement policy, such as green office design criteria for country office construction. / There is considerable oversight and scrutiny of World Bank procurement operations; around 5% of procurement operations are reviewed internally and a smaller amount of operations go to external review every year. The World Bank has begun a review of its procurement policies and practices to address concerns and better align procurement with the World Bank’s development objectives.
6. Conclusions and actions
Overall conclusion: / This annual review scored the outputs as an A i.e. outputs met expectations, but neither exceeding nor not meeting expectations. This is a fair reflection over the course of the year, where some significant progress has been made. Particular highlights have been the significant effort by the CIF Admin Unit and MDBs to address areas of improvements that were first discussed in the June 2011 Trust Fund Committee meetings, and endorsement of the majority of the remaining country investment plans. This now provides the basis for the CIFs to move to the next step of implementation i.e. approval and implementation of projects within investment plans. / The score for the annual review over the course of the year is not higher (i.e. not A+ or A++) as there remains a number of areas where there is need for significant improvements. The main areas are: putting in place results frameworks with a sensible and limited number of core indicators to demonstrate progress at the Programme (i.e. CTF, PPCR, SREP, FIP) level; putting in place a risk management framework to enable the Trust Fund Committees to annually review risks within the CIFs; and in looking forward to the establishment of the Green Climate Fund ensuring lessons from the CIFs – ideally through the Independent Evaluation – are taken on board in GCF design and clarifying the place of the CIFs within a new global climate financing architecture. / The balance between the progress made and the remaining concerns means that the risk remains at medium. / Key recommendations: / The top level recommendations from this annual review are: / With the finalisation of the CIF results frameworks, which include clear targets, the UK’s logical framework for this funding should be updated in time for the next annual review so that outputs can better measure the actual results being delivered by the CIFs. The UK needs to continue to push the CIF AU and MDBs to finalise the results frameworks to enable this improved monitoring of results. / The UK Cross-Whitehall team will continue to review the UK’s risk register on a monthly basis. However, it is imperative that we push for a risk management framework to be agreed and then used by the CIF Trust Fund Committee. / The UK should continue to engage with the Evaluation Oversight Committee of the Independent Evaluation to ensure that an independent and credible evaluation is produced and overseen by an international reference group. Close attention is needed to ensure lessons from the evaluation can be and are used in the design of the Green Climate Fund. / While good progress has been made on the measures to improve the CIFs, we should continue to watch implementation, for example on gender and development, and transparency. / By the next annual review there should be clearly separated logical frameworks for CIFs, CBFF and FCPF. / The areas for monitoring the CIFs as identified within the Environmental Screening Note should be followed up.
[4] http://www.climateinvestmentfunds.org/cif/sites/climateinvestmentfunds.org/files/CIF_AR_2011_year_in_review.pdf
[5] The figures on co-financing and leverage reflect the detail in the Climate Investment Funds ‘Semi-Annual Report on CTF Operations’ published 16 April 2012 and presented to the May 2012 CTF Trust Fund Committee (TFC).

7. Review Process
This review was conducted within DFID. / The first draft was completed by the CIF Programme lead, with more information then added by policy leads and policy officers for each of the ETF projects. / The CIF admin unit was consulted on the review and specifically asked for inputs relating to output 2. These were provided and drawn on for the review. / As the ETF programme is jointly funded by DECC, the International Climate Change team in DECC were widely consulted throughout the review and provided substantial inputs which are reflected in the final review. / Principle documentation that was examined as part of this review includes: / Strengthening the CIFs – learning from experience (HMG doc) / HMG Management and Accountability Framework (HMG doc) / CIF Business Case (HMG doc) / Multilateral Aid Review (HMG doc) / Progress Against MAR Reform Priorities 2011 (HMG doc) / Progress Report on the CIF 2012 Learning Products (CIF doc) / CIF 2011 Annual Report (CIF doc) / Proposed Measures to improve the operations of the CIFs (CIF doc) / Progress Report on Measures to improve the operations of the CIFs (CIF doc) / Co-Chair summary of CTF/SCF Committee May 2012 (CIF doc) / CIF FY13 Business Plan and Budget (CIF doc) / CTF Semi-Annual Reports (May & November 2011 & April 2012) / CIF Results Frameworks (CIF docs) / Note on the Independent Evaluation of the CIFs (CIF doc) / Independent Evaluation of the CIFs (CIF doc)