## A1 Goal, Purpose, Risk
Annual Review
ARIES Project Code | 108745
ARIES Project Description | GENDER JUSTICE AND PROTECTION PROJECT (GJP)
A1: Goal, Purpose, Risk
Goal
Goal statement | To bring about a sustainable reduction in violence against women in accordance with the government’s policy commitments
Indicator 1
Milestone for this review (if any)
What progress has been made in the period covered by this review? | Given the multiple facets of VAW and the scale of the problem in Pakistan, GJP is very small intervention; however it is contributing to achieve the goal.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
What evidence is there of progress made in the period covered by this review towards the Goal-level Target(s)? | A) GJP has influenced a larger population in 42 districts of Pakistan through various interventions. B) GJP has produced a number of professionals as well as established mechanisms which provide rehabilitation services to VAW survivors. C) GJP has enabled government and civil society organizations to work together to combat VAW.
Goal Recommendation 1
Goal Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Goal Recommendation 2
Goal Recommendation 3
Goal Action Point 2
Goal Action Point 3
Purpose
Project Purpose | Mechanisms in place to support a sustainable reduction in Violence Against Women (VAW) in Pakistan
Indicator 1 | X% of increased reporting of VAW cases in Pakistan
Milestone for this review (if any)
What progress has been made in the period covered by this review? | 1. Anti karo kari cells by Sindh Police Department has increased access of VAW survivors to the reporting system/ points. 2. Following services have facilitated and encouraged women to report VAW cases: a) Counselling and referral services are provided in Chakwal, Vehari, Lahore, Jehlum, Norowal and Khushab districts of Punjab; Hyderabad, Sukkur, Larkana, Ghotki, Noshehro Feroz and Khairpur Mirs districts of Sindh; Charsada, Noshehra, Peshawar, Bannu and Haripur districts of NWFP. b) 13 Helplines for victim support are working in Chakwal, Norowal, Vehari and Faisalabad districts of Punjab; Hyderabad, Sukkur, Larkana, Ghotki, Noshehro Feroz and Karachi districts of Sindh; and Charsada district of NWFP. c) Legal aid, by nine GJP partners, is being provided in Hyderabad, Sukkur, Larkana, Ghotki, Noshehro Feroz and Khairpur Mirs districts of Sindh, Bannun, Peshawar, Haripur and Charsada districts of NWFP, Norowal, Chakwal, Vehari, Faisalabad and Khushab districts of Punjab.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Y No. of government initiatives supporting reduction of VAW
Milestone for this review (if any)
What progress has been made in the period covered by this review? | 7 government initiatives/ projects under implementation to reduce VAW. 1. Anti karo kari cells established by Sindh Police Department in 4 districts. 2. Punjab Police department is in process of establishing Gender Crime cells. 3. Balochistan Police Department is in process of establishing Anti Honour Killing cells. 4. Legal aid provided by Regional Directorate of human Rights (RDHR) in NWFP. 5. Awareness raising and advocacy carried out by District Government Mardan. 6. One window counter is being established by City District Government Rawalpindi. 7. A national research on establishing relationship between VAW and substance abuse is being carried out by Ministry of Narcotics Control.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | No. of new or revised government policies, procedures and systems incorporating good practices on VAW
Milestone for this review (if any)
What progress has been made in the period covered by this review? | 1. Notification of seven female parole officers (probation officers) in Peshawar, Mardan, Kohat, Dera Ismail Khan, Abbotabad, Bannu and Sawat districts of NWFP. 2. Support in the form of consultation and legal feedback for the passage of Sexual Harrasment Bill. 3. Anti karo kari units established by Sindh Police Department in Sukkur, Larkana, Ghotki and Noshehro Feroz districts of Sindh.
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4 | No. of women benefiting from GJP initiatives
Milestone for this review (if any)
What progress has been made in the period covered by this review? | 1. Capacity building for 1187 women and awareness raising for 15,745 women undertaken. Capacity building events and modules focused on CEDAW, Inheritance rights, karo kari specific policing, Operationalization of Section 174-A of Code of Criminal Procedure, legal aid, gender sensitization and rights in a marriage contract. 2. A large number of women benefited from radio programmes and IEC material in all 42 districts accross Pakistan. 3. 676 women received legal aid and 4,990 women received counselling and referral services. GJP's partner organizations, which are focusing on rehabilitation services, for VAW survivors have dedicated staff and resources to provide counselling and legal services. These organizations have engaged psychologists and lawyers (mostly volunteers) to facilitate/ ensure quick, cheap and adequate redressal response for VAW survivors.
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5 | Strengthened service provision mechanism in place for victims of VAW
Milestone for this review (if any)
What progress has been made in the period covered by this review? | 1. Four anti karo kari units established by Sindh Police Department. 2. Legal aid, counselling and referral services are provided at 20 centres/points. 3. Strengthening of an Acid burn victims treatment centre by supporting legal follow-up of acid burn victims.
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project?
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | Although the scale and financing of the project is limited, it is contributing to the realization of the Goal. The following evidences indicate the degree of achievement of the purpose and its contribution towards the goal: 1. The mechanisms established by partner government organizations through GJP include anti karo kari units by Sindh Police Department and legal aid by Regional Directorate of Human Rights NWFP. The mechanisms are successfully rendering services to VAW survivors in mitigating their sufferings. Legal aid centres, counselling & referral centres, help lines and community support groups established by partner CSOs are also providing services to VAW survivors. These mechanisms provide enabling environment to report cases of VAW and seek justice. 2. Also, these mechanisms are educating the surrounding communities through awareness raising activities. These activities are meant to motivate men, women and youth to pledge "No to VAW" and thus prevent VAW on sustainable basis.
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | All the outputs are directly linked to the purpose, however, Output 2 and 4 are more focused on establishing and strengthening of mechnisms to combat VAW. Output 2 is about capacity building of government and civil society partners to undertake VAW related work which is helping in strengthening mechanisms. Output 4 is directly linked to the purpose. The sub projects initiated under output 4 are establishing mechanisms to combat VAW. Following is the evidence to these outputs which are directly influencing the purpose. a) 13 baseline studies conducted by the partner organizations, b) 1187 women and 1992 men trained on CEDAW, Inheritance rights, karo kari specific policing, Operationalization of Section 174-A, legal aid, gender sensitization and rights in marriage contract, c) 15,745 women and 18,579 men made aware on social disapproval of VAW, d) large number of IEC material produced to spread the word against VAW, legal provisions and available rehabilitation services e) Establishment of VAW helplines, counselling and legal aid centres.
Purpose Recommendation 1 | Revise log frame, should ensure baseline to reflect number of VAW cases reported. To access the progress quantitatively.
Purpose Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2
Purpose Recommendation 3
Purpose Action Point 2
Purpose Action Point 3
Project Purpose Score | 2 | 1.6
Purpose Justification
Risk
Project Risk Rating or latest Overall Risk Score. | High
Based on the review, does the Project Risk Rating need revision? | Yes
If Yes, why is this? | Priorities/concerns of the government such as terrorism, governance, security, energy and food crisis is relegating the issue of VAW to the background. The inflationary pressures will also have a qualitative impact on sub-project deliverables by the closing period.
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks?
Risk Recommendation 1 | Consideration of future funding to GJP should be focused on Government priorities and commitments around VAW to leverage existing government ownership and priorities.
Risk Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Risk Action Point 2
Risk Action Point 3
Logframe, DSOs, Cross-Cutting Markers
Logframe revised/needs revision? | Yes
If Yes, why was/is this? | The log frame needs to be revised according to new DFID fromat.
Logframe Recommendation 1 | Goal level indicators to be incorporated.
Logframe Action Point 1 | Revision of LFA is required.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Logframe Recommendation 2 | The purpose should be amended to capture the verity of interventions to combat VAW.
Logframe Recommendation 3 | Outputs need review for further appropriation and also to incorporate a few recommendations such as inclusion of national level baseline on VAW.
Logframe Action Point 2 | Revision of LFA is required.
Logframe Action Point 3 | Revision of LFA is required.
DSOs revised/need revision?
If Yes, why was/is this?
DSO Recommendation 1
DSO Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision? | No
If Yes, why was/is this?
CCM Recommendation 1
CCM Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | External Resource Pool responsive to supporting proposals that aim to address VAW
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | The external resource pool can not be substantially influenced directly and the output needs revision thereof.
Original or Revised Impact Weight (%) | 10%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.2
DFID Share revised/needs revision?
If Yes, why was/is this? |  | 1
Original or Revised DFID Share |  | 2
3
Indicator 1 | No. of VAW proposals from GJP implementing partners funded by external resource pools. | 4
Is this a Standard Indicator? | Yes | 5
Milestone for this review (if any) |  | 0
What progress has been made in the period covered by this review? | 16 GJP partners submitted 36 proposals to different donors. Four of the GJP partners i.e. Bedari, Acid Survivors Foundation (ASF), Rahnuma-FPAP and Basic Integrated Rural Development Society (BIRDS) received funding. Bedari received funding from Unifem, WISE and EC; ASF received funding from Zurich Foundation; FPAP received funding from IPPS and BIRDS received funding from Unifem.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | No. of joint events by GJP to develop linkages between implementing partners and ERP.
Is this a Standard Indicator? | Yes
Milestone for this review (if any)
What progress has been made in the period covered by this review? | GJP has been sharing partners' work with potentail ERPs. GJP also invited partners to attend an event on VAW conducted by GJP to provide them the opportunity to connect with donors. However, additional steps need to be taken and GJP has planned a dedicated event in Islamabad to link its partner organizations with potential ERPs where these partner organizations will try to attract funding for further scaling-up of their VAW related work.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | No. of proposals submitted by GJP implementing partners to external resource pools
Is this a Standard Indicator? | Yes
Milestone for this review (if any)
What progress has been made in the period covered by this review? | 16 GJP partners submitted 36 proposals to different ERP/ donors. Four of the GJP partners i.e. Bedari, Acid Survivors Foundation (ASF), Rahnuma-FPAP and Basic Integrated Rural Development Society (BIRDS) received funding. Bedari received funding from Unifem, WISE and EC; ASF received funding from Zurich Foundation; FPAP received funding from IPPS and BIRDS received funding from Unifem.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 | No. of hits on GJP website to access information
Is this a Standard Indicator? | Yes
Milestone for this review (if any)
What progress has been made in the period covered by this review? | 166,761 hits on GJP website. www.gjp.org.pk
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 1 | 4 | 0.25
Impact Weighted Score | 2.5 | 0.025
Justification for the Score | The external resource pools have their own priorities.
Output 1 Recommendation 1 | GJP should connect implementing partners with ERPs and provide examples of good initatives that could be replicated and/or scaled up with external funding.
Output 1 Action Point 1 | In next workplan, organise event with all other ERPs on VAW to share GJP best practices/well performing projects.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2
Output 1 Recommendation 3
Output 1 Action Point 2
Output 1 Action Point 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Government and CSOs capacity strengthened to access and effectively utilize funds from resource pools for initiatives to reduce VAW
Impact Weight revised/needs revision? | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 10%
Risk revised/needs revision? | Yes
If Yes, why was/is this? | Lack of ownership towards implementation by the GoP; Changing priorities of government agencies due to law and order situation.
Original or Revised Risk | High | 1
0.1
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 | X %of Government and CSOs partnerships implementing VAW projects
Is this a Standard Indicator? | Yes
Milestone for this review (if any)
What progress has been made in the period covered by this review? | 1. Regional Directorate of human Rights (RDHR) has partnered with Dost Foundation and Aurat Foundation in social rehabilitation of women prisioners in Peshawar and Haripur. 2. Community Development Programme (CDP) has signed an MoU with Bannu (NWFP) Police for facilitation and capacity enhancement of the Gender Justice Committess and Musallahati Committees.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | No. of government officials (female/male) actively engaged in projects funded by GJP
Is this a Standard Indicator? | Yes
Milestone for this review (if any)
What progress has been made in the period covered by this review? | Approximately 64 government officials i.e. health, education, police department staff, women crisis centre staff are involved in various projects. This includes one national (Ministry of Narcotics Control) and four provincial level (Sindh, Balochistan and Punjab Police departments; and Regional Directorate of Human Rights NWFP) officials whereas remaining belong to the target districts.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | No. of capacity building events held by GJP for implementing partners
Is this a Standard Indicator? | Yes
Milestone for this review (if any)
What progress has been made in the period covered by this review? | GJP has conducted a capacity building workshop for its partner organizations. The workshop covered the topics of monitoring, communication and reporting.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 | No. of implementing partners’ staff (men/women) whose capacity was built by GJP initiatives.
Is this a Standard Indicator? | Yes
Milestone for this review (if any)
What progress has been made in the period covered by this review? | 1. 32 participants (11 women, 21 men) from 27 partner organizations trained directly in monitoring, communication and reporting. 2. Continious backstopping/ capacity building input is being provided to 52 (20 women, 32 men) staff members of partner organizations.
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 | %age of utilization of funds by implementing partners
Is this a Standard Indicator? | Yes
Milestone for this review (if any)
What progress has been made in the period covered by this review? | 37 % funds committed have been utilised by the GJP partners.
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 2 | 2 | 0.75
Impact Weighted Score | 7.5 | 0.075
Justification for the Score | Timely response to VAW survivors, Improved knoweldge base regarding VAW issues, Bifurcated and timely information supply, quality of the IEC material and degree of meeting reporting requirements of partner organizations indicate significant positive attainment on capacity ladder.
Output 2 Recommendation 1 | More capacity building events are required to achieve the output.
Output 2 Action Point 1 | Capacity building events to be included in the Annual work plan.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2
Output 2 Recommendation 3
Output 2 Action Point 2
Output 2 Action Point 3
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Good Practices in Prevention and Protection Embedded in Government Policy and Processes on VAW
Impact Weight revised/needs revision? | Yes
If Yes, why was/is this? | Embedding good practices in government policies has limited achievement posibilities.
Original or Revised Impact Weight (%) | 10%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.2
DFID Share revised/needs revision? | Yes
If Yes, why was/is this? | Lack of Ownership, commitment and low priority on government's agenda
Original or Revised DFID Share
Indicator 1 | Lessons from good practices used to initiate and upscale number of VAW initiatives by government agencies
Is this a Standard Indicator? | Yes
Milestone for this review (if any)
What progress has been made in the period covered by this review? | Majority of GJP supported projects initiated in mid 2009 and it was too early to have lessons/ best practices drawn from these projects during 2009.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | No. of researches published and disseminated
Is this a Standard Indicator? | Yes
Milestone for this review (if any)
What progress has been made in the period covered by this review? | 13 district level baseline/research studies conducted through GJP supported initiatives.These reports were basically conducted to support the organization's work in their target area and two of the reports were printed. District level baselines/ studies broadly researched on forms and magnitude of VAW practices, coping mechanisms, rehabilitation facilities, other VAW mitigating initiatives etc in relation to specific VAW themes.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | No. of good practices documented and disseminated by GJP
Is this a Standard Indicator? | Yes
Milestone for this review (if any)
What progress has been made in the period covered by this review? | Planned for 2010.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 | No. of training curricula of Government institutions incorporating VAW concerns
Is this a Standard Indicator? | Yes
Milestone for this review (if any)
What progress has been made in the period covered by this review? | It is too early a time in the course of project implementation to gain ample manoeuvrability towards curricula.
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 | • No. of Advocacy events held by GJP
Is this a Standard Indicator? | Yes
Milestone for this review (if any)
What progress has been made in the period covered by this review? | GJP has convened screening of a documentary (prepared by a GJP implementing partner) which was followed by a pannel discussion of gender experts.
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 3 | 3 | 0.5
Impact Weighted Score | 5 | 0.05
Justification for the Score | Due to prevailing law and order situation and economic downturn,VAW is not a high priority area for the government.
Output 3 Recommendation 1 | GJP should determine areas where GoP has shown some level of commitment in embedding in policies/practices, such as sexual harassment, domestic violence, acid survivors bills, and engage specifically in those areas.
Output 3 Action Point 1 | GJP to organise event with GoP around legislation that protects women, in context of next round of proposals being focused specifically in this area.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2
Output 3 Recommendation 3
Output 3 Action Point 2
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4 | Projects from CSOs and Government approved by GJP fund addressing VAW concerns
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 70%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | Low | 3
2.1
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 | No. of proposals by CSOs and government agencies approved by FMC
Is this a Standard Indicator? | Yes
Milestone for this review (if any)
What progress has been made in the period covered by this review? | 22 proposals of CSOs and 9 from government agencies approved
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 | No. of Districts covered by the sub projects
Is this a Standard Indicator? | Yes
Milestone for this review (if any)
What progress has been made in the period covered by this review? | 42 districts covered directly which include seven from NWFP, eight from Sindh, six from Balochistan, 17 from Punjab and four from AJK. Areas covered by research projects are additional to this.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 | No. and types of awareness raising events held
Is this a Standard Indicator? | Yes
Milestone for this review (if any)
What progress has been made in the period covered by this review? | 502 events held. a) 92 theatre/ puppet performances/ shows b) 389 awareness raising seminars, celebration of women day and 16 days of activism, debate competition, public/ community meetings, consultative dialogues, discussions forums, awareness raising sessions c) 21 radio programmes • 13,129 women and 16,711 men benefited directly from theatre/ puppet and awareness raising programmes. • Awareness raising programmes targeted general masses, girls and boys in schools, factory workers, media, women labourers, youth groups, Bar association, community leaders • Beneficiaries of radio programmes and IEC material are additional. • Awareness raising programmes focussed on forms and impacts of VAW, national and international commitments regarding VAW, concerning laws, available mechanisms for redressal/ rehabilitation, role of community in combating VAW and Engaging Men for Ending Violence against Women.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 | No. and types of communication material produced and No. of Researches conducted by GJP implementing partners
Is this a Standard Indicator? | No
Milestone for this review (if any)
What progress has been made in the period covered by this review? | • 50,500 posters, 7500 stickers, 23 broachers/ flyers, 6 booklets, 2 IEC kits printed and disseminated. • Six GJP partners published and disseminated News letters • Acid Survivors Foundation has prepared promotional/ advocacy documentary • 13 studies at district level. District level studies broadly researched on forms and magnitude of VAW practices, coping mechanisms, rehabilitation facilities, other VAW mitigating initiatives etc in relation to specific VAW themes.
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 | No. of capacity building events held by implementing partners and No. of stakeholders capacitated (men & women) by implementing partners
Is this a Standard Indicator? | No
Milestone for this review (if any)
What progress has been made in the period covered by this review? | No. of Events: 113, No. of Modules: 15 • 1205 women and 1983 men benefitted • The capacity building events targeted community leaders, respective health and education department staff, women crisis centre staff, lawyers, media and locally elected representatives. • Capacity building events and modules focused on CEDAW, Inheritance rights, karo kari specific policing, Operationalization of Section 174-A, legal aid, gender sensitization and rights in marriage contract.
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 | No. of women provided legal aid, counselling, referral services
Is this a Standard Indicator? | Yes
Milestone for this review (if any)
What progress has been made in the period covered by this review? | • 676 women received legal aid (through court and informal justice system) • 4,990 women received counselling and referral services
Output Performance for Output 4 | 1 | 1
Impact Weighted Score | 70 | 0.7
Justification for the Score
Output 4 Recommendation 1 | Best practices need to be documented highlighting how support has helped to address VAW concerns.
Output 4 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
Output 4 Action Point 2
Output 4 Action Point 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 5 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 5 Recommendation 1
Output 5 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6
Is this a Standard Indicator?
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 2010-03-18
Impact Weighting (must = 100) | 100%
Total Impact Score | 85 | 0.85
Output Risk | Low | 2.6
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems | X
Quantitative data from project/programme study | X
Government assessment
Joint donor review
Independent consultant review
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner
National non-Government partner
Independent consultant
Donor partners
DFID staff | X
Donor partners
Comment here on the Method of Scoring and Scoring Responsibility. | Robust and innovative scoring methodology.
Scoring Recommendation 1
Scoring Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | Partner organizations need capacity building on advocacy around VAW.
Working with Partners Recommendation 1 | It is clear that more capacity building events are required for partners. It may be useful to circulate a questionnaire among the partners seeking their specific capacity building needs and organise training around the areas identified.
Working with Partners Action Point 1 | Devise a capacity building/training needs questionnaire and organise trainings/events around that in the next workplan.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2
Working with Partners Recommendation 3
Working with Partners Action Point 2
Working with Partners Action Point 3
2. Best Practice / Innovation | GJP has brought in a variety of partners from government and civil society organizations which are working on innovative ideas and mechanisms. which include: 1. Establishment of Honour Killing units in Sukkur, Larkana, Ghotki and Noshehro Feroz districts of Sindh by Sindh Police Department. The experience of establishing dedicated institutional structures is being replicated by Punjab Police and Balochistan Police Departments. 2. Training of stakeholders on operationalization of Cr.PC 174-A by Rahnuma-FPAP in Muzaffarabad, Bagh, Mirpur and Bhimber (AJK), Mansehra (NWFP) and Sialkot, Gujranwala and Gujrat (Punjab) districts. 3. Development of anti VAW related supplementary material for religious seminaries by Al-Mubarak Welfare Society (organization linked with semanaries) in religiously conservative area of district Charsada, NWFP 4. Awareness raising on women rights provided in the marriage contract by Farmers Development Organization in district Lodhran, Punjab. 5. A national level study on investigating and mainstreaming community solutions and strategies for combating VAW by Sustainable Development Policy Institute. 6. Conducting a national research on women with substance abuse problem in relation to VAW and building capacity of drug treatment staff / centres to deliver quality treatment services for women by Ministry of Narcotics Control.
Best Practice / Innovation Recommendation 1
Best Practice / Innovation Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | Projects with government counterparts need inception phase which should be calculated at the time of project designing before approval.
Project Management Recommendation 1
Project Management Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved.
Key issues, points of information or additional comments that may be useful for this or other project teams. | Since the government counterparts have other pressing priorities, the gender related work is less of of a priority. Hiring a dedicated project officer for the sub-projets boost the project efficiency and makes it more likely to yield the desired results.
Other Recommendation 1
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
Evidence Recommendation 1
Evidence Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions?
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project. | 1. The structures/ systems established in partnership with government i.e. Anti karo kari units by Sindh Police Department are expected to be sustainable in nature. 2. The material produced such as training modules and booklets, trainers produced and research studies conducted are valuable assets which will keep benefitting gender and VAW related work even after the project concludes.
Sustainability Recommendation 1 | A great deal of time and inverstment has been put into establishing the GJP as a key Fund tackling violence against women. In order to have increased sustainability, the project work may be linked with an established institution where it keeps on providing technical backstopping to NGOs, if not funding, and act as a resource centre.
Sustainability Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2
Sustainability Recommendation 3
Sustainability Action Point 2
Sustainability Action Point 3

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | 0
R2 | 0
R3 | 0
A1: Purpose
R1 | Revise log frame, should ensure baseline to reflect number of VAW cases reported. To access the progress quantitatively.
R2 | 0
R3 | 0
A1: Risk
R1 | Consideration of future funding to GJP should be focused on Government priorities and commitments around VAW to leverage existing government ownership and priorities.
R2 | 0
R3 | 0
A1: Logframe
R1 | Goal level indicators to be incorporated.
R2 | The purpose should be amended to capture the verity of interventions to combat VAW.
R3 | Outputs need review for further appropriation and also to incorporate a few recommendations such as inclusion of national level baseline on VAW.
A1: DSOs
R1 | 0
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | 0
R2 | 0
R3 | 0
A2: Outputs
R1.1 | GJP should connect implementing partners with ERPs and provide examples of good initatives that could be replicated and/or scaled up with external funding.
R1.2 | 0
R1.3 | 0
R2.1 | More capacity building events are required to achieve the output.
R2.2 | 0
R2.3 | 0
R3.1 | GJP should determine areas where GoP has shown some level of commitment in embedding in policies/practices, such as sexual harassment, domestic violence, acid survivors bills, and engage specifically in those areas.
R3.2 | 0
R3.3 | 0
R4.1 | Best practices need to be documented highlighting how support has helped to address VAW concerns.
R4.2 | 0
R4.3 | 0
R5.1 | 0
R5.2 | 0
R5.3 | 0
R6.1 | 0
R6.2 | 0
R6.3 | 0
R7.1 | 0
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | 0
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | It is clear that more capacity building events are required for partners. It may be useful to circulate a questionnaire among the partners seeking their specific capacity building needs and organise training around the areas identified.
R2 | 0
R3 | 0
Best Practice / Innovation
R1 | 0
R2 | 0
R3 | 0
Project Management
R1 | 0
R2 | 0
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | 0
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | A great deal of time and inverstment has been put into establishing the GJP as a key Fund tackling violence against women. In order to have increased sustainability, the project work may be linked with an established institution where it keeps on providing technical backstopping to NGOs, if not funding, and act as a resource centre.
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Purpose
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Risk
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Logframe
AP1.1 | Revision of LFA is required.
AP1.2 | Revision of LFA is required.
AP1.3 | Revision of LFA is required.
A1: DSOs
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Cross-Cutting Markers
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | In next workplan, organise event with all other ERPs on VAW to share GJP best practices/well performing projects.
AP1.2 | 0
AP1.3 | 0
AP2.1 | Capacity building events to be included in the Annual work plan.
AP2.2 | 0
AP2.3 | 0
AP3.1 | GJP to organise event with GoP around legislation that protects women, in context of next round of proposals being focused specifically in this area.
AP3.2 | 0
AP3.3 | 0
AP4.1 | 0
AP4.2 | 0
AP4.3 | 0
AP5.1 | 0
AP5.2 | 0
AP5.3 | 0
AP6.1 | 0
AP6.2 | 0
AP6.3 | 0
AP7.1 | 0
AP7.2 | 0
AP7.3 | 0
AP8.1 | 0
AP8.2 | 0
AP8.3 | 0
AP9.1 | 0
AP9.2 | 0
AP9.3 | 0
AP10.1 | 0
AP10.2 | 0
AP10.3 | 0
B: Scoring
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | Devise a capacity building/training needs questionnaire and organise trainings/events around that in the next workplan.
AP1.2 | 0
AP1.3 | 0
Best Practice / Innovation
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
Additional Action Points arising
AP1.1
AP1.2
AP1.3