## A1 Goal, Purpose, Risk
Annual Review (reviewed Feburary 2011)
ARIES Project Code | 108745
ARIES Project Description | Gender Justice & Protection Project (GJP)
A1: Goal, Purpose, Risk
Goal
Goal statement | To bring about sustainable reduction in violence against women in accordance with the Government of Pakistan's policy commitments.
Indicator 1 | Gender Empowerment Measure (GEM)
Milestone for this review (if any) | Percentage change from 0.377 of base line in 2006 to 0.386 in 2009.
Indicator 2 | Gender Development Index (GDI)
Milestone for this review (if any) | Percentage change from 0.513 of base line in 2006 to 0.532 in 2009.
What evidence is there of progress made in the period covered by this review towards the Goal-level Target(s)? | The GJP worked without any baseline at the project or sub-project levels. In the absence of baseline data, it is difficult to measure project's contribution towards the Goal-level target (s). Any attempt to judge progress or even attrition towards GDI & GEM is further compounded with difficulties as neither the project nor the government of Pakistan generate this report. The percentage based break up at the Goal level indicators has no ratinale to it and GJP had no instrumnet to monitor, measure & report on it. As per UNDP's Human Development Report Pakistan has slipped from its 124th position to 141st on GDI. Nevertheless there is an evidence that the project has created conditions i.e. (a) increased social awareness on the issue of VAW at the institutional and community level; (b) the presence of critical mass of activists at the community level who have the will and commitment to work to end violence against women; (c) enhanced capacity of small NGOs to work on the issues of VAW and (d) the provision of legal aid
and counselling services to the survivors of violence that had facilitated many women to exit violent situations together contribute to the project goal of sustainable reduction in violence against women.
Goal Recommendation 1 | Goal settings have to be realistic with some qualitative attribution based indicator. It would be useful to highlight the amendments/ repeal of certain number of discriminatory laws could be an indicator for GJP as majority of its partners are working on advocacy and policy change.
Goal Action Point 1 | In next phase of project, if any, the goal indicators need to be nationally grounded and qualified. They should focus on effectiveness and sustainability of initiatives and be targeted on certain policies and pockets of VAW i.e. geographically and by governmental institutions.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Goal Recommendation 2
Goal Recommendation 3
Goal Action Point 2
Goal Action Point 3
Purpose
Project Purpose | Better support and protection against violence and abuse for women and girls in Pakistan.
Indicator 1 | 90% of all proposals funded achieve their objectives.
Milestone for this review (if any) | Zero at baseline in 2006 and 100% of total GJP funded (GBP 1.86 million) allocated for first, second, third and fourth round of projects
What progress has been made in the period covered by this review? | Three round of proposals held. Total Funds available were $ 4,515,108 and expenditure till Dec. 2010 is approximately $2,769,100. It is pertinent to note that the project design and objective are macro and broad in nature. The corresponding indicators of the logframe are not designed to capture quality and impact but are geared towards tracking of activities. Evidence indicates that the project has made substantial progress towards completion of designed project activities as stated in the sub-project logframe against the objectives.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Legislation, policies, implementation and support system to address VAW in place and operational.
Milestone for this review (if any) | Baseline states to have discriminatory laws, policies & procedures such as Hudood Ordinance, Qanoon-e-Shahadat etc.and by 2009, GJP initiatives support and implement at least 2 affirmative polices.
What progress has been made in the period covered by this review? | GJP partners played an active role in advocating implementation of the Sexual Harassment Act 2010 and legislation on Acid Control & Crime Protection Bill. The sub projects also contributed to advocacy for domestic violence bill. Police and government mechanisms were sensitised to implement protective measures for VAW victims through orientation of Police on legislation in Sindh and establishment of a One-Window support counter in Rawalpindi. One sub project with maulvis has prevented 32 women from being exchanged for blood money - swara - which is illegal, and also forbidden in the Quran. GJP support to legislation, policies and implemention systems has been through its partners. 3 projects focused on providing legal aid to survivors, 18 on awareness raising and advocacy and 16 in Capacity building. The project has 12 projects extending legal aid through regular court cases within the itegrated components. Project activitives were geared to create an environment that influences the State to take necessary steps towards policy/ legislation development and implementation. The indicator set to
measure the same is unrealistic for a Challenge Fund. However the project, through its partners, has contributed to the development of policies, legislation and/or implementation.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | Victim of VAW are better able to access redressal mechanism by CSO and the government
Milestone for this review (if any) | Base line 2006 stated to have inadequate procedures in place for dealing with victims of VAW (treatment at police stations, courts, health and counselling). 2010 target was victims of VAW have better access to mechanism & support services in at least 40 districts.
What progress has been made in the period covered by this review? | Again the indicator is ambitious and overlaps with indicator No.2. The direct beneficiaries of the project, who received legal aid, counselling and rehabilitation support, are estimated at 30,711 in total, but each partner uses a different formula to arrive at the number of indirect beneficiaries which means the numbers are not reliable. The outreach of the project is currently in 93 districts which is a thin spread. The number of district will increase due to the Sindh Police project which is expected to expand to 23 district in Sindh (from 4). The number of districts has been calculated in some cases on a single event and cannot be assumed to have covered the needs of the district as a whole. The project has been able to touch upon the three elements of redressal i.e. Protection, Prevention and Support for VAW through its sub project activities by supporting them through Police stations and court cases.
Are Purpose Assumptions being realized? If so, to what degree, and what has been the effect on the project? | Purpose level assumptions are being realized to some extent as 2007-2009 was a period where government did exhibit some positive responses towards discriminatory laws and the Sexual Harassment law was passed. 2010 has been a bad year due to blasphemy cases and related fall out. The project has been able to focus on implementation of the sexual harassment act through its partners. The partner government agencies though remained appreciative of the project work; however they need to be pushed to convert the ongoing project support into institutional framework and to absorb the work at government ends. Communities have benefitted most and are better informed, with the potential to be harbingers of change and advocates for reform.
What evidence is there that achieving the Purpose is contributing to the realization of the Goal? If it is doing so, to what degree? | The purpose level indicator have no connect with the realization of Goal as Goal is an international indicator towards which even the "State" has no contribution. Therefore Purpose indicator has no contribution and or alignment with realization of Goal.
The socio-cultural, economic and political environment in the country continues to produce gender disparities and women’s vulnerabilities despite the government’s national and international commitments. Increasing militarization, radicalization and deterioration in the law and order situation in the country has given rise to violence against women (VAW). Protective legislative framework and supportive mechanisms for the victims remain weak. Therefore, the focus of the GJP is extremely relevant.
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | The purpose indicators are qualitative in nature except the one that focuses on 100% expenditure of the GJP fund through four rounds. The fourth round is yet to be launched and $545,967 is available for this. The achievement of purpose cannot be fully attributed as influencing governmental support and legal aid redressal systems has not been the key focus of the project. However output based activities have been mostly achieved.
The project’s integrated framework with its preventative-protective-supportive elements, is appropriate to address issues of VAW. The project’s four priority areas i.e. advocacy and awareness raising; capacity building; action oriented research and documentation and legal aid are also appropriate.
Purpose Recommendation 1 | The purpose level indicators should be more quantified and less ambitious. Indicators at all levels should be refreshed and be made more relevant to what a Challenge Fund project of this nature can hope to achieve. Challenge fund arrangements should be based on clearly defined project framework with targeted areas of intervention so that the activities of various project partners can have an aggregated impact.
Purpose Action Point 1 | Revisit the logframe after the review and develop new indicators where necessary, better to reflect the nature and ambitions of the activities to allow the PMU to play a more effective role.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2 | The spread of GJP sub projects across Preventative (awareness raising) Protective (legislation) and Supportive (support services legal aid, counselling, rehabilitation serviced to survivors of violence), should be strategically grouped, balanced and managed in terms of resource allocatio, coverage of thematic areas and advocacy.
Purpose Action Point 2 | Hold workshops with project partners to develop activity groupings and advocacy messages; consider teaming up with other organisations working on similar themes but not funded through GJP. Align with the government for relevant policies and use the same focus for advocacy work.
Purpose Recommendation 3 | M&E should have larger budgetary allocation and should be part of programme cost, in order to develop clear, evidence based messages for influencing.
Purpose Action Point 3 | Strengthen the M&E system and use the information to plan a two pronged support by working with aligning with government on advocacy for relevant policies, whilst at the same time communicating messages to citizens.
Project Purpose Score | 2 | 1.7
Purpose Justification | The need for such support for VAW is critical in Pakistan and GJP has been able to raise awareness and change behaviour across a range of groups. Work direct with government has been limited, but some sub projects have had significant impact in relation to protection of women at local level that has potential for replication. Future GJP activities should focus on sustainability of the achievements and broadening of awareness of the negative impacts of VAW.
Risk
Project Risk Rating or latest Overall Risk Score. | High
Based on the review, does the Project Risk Rating need revision? | Yes
If Yes, why is this? | Project has been working mostly at grass root level where communal non-acceptance is more a risk then attitude of the government. Earlier risk level has been assigned more from governmental perspective.
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks?
Risk Recommendation 1
Risk Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Risk Action Point 2
Risk Action Point 3
Log frame, DSOs, Cross-Cutting Markers
Log frame revised/needs revision? | No
If Yes, why was/is this?
Log frame Recommendation 1
Log frame Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Log frame Recommendation 2
Log frame Recommendation 3
Log frame Action Point 2
Logframe Action Point 3
DSOs revised/need revision?
If Yes, why was/is this?
DSO Recommendation 1
DSO Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision?
If Yes, why was/is this?
CCM Recommendation 1
CCM Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 | Strengthened CSO/citizen voices on legislation, policy and implementation to prevent VAW (Activity: fund CSOs to talk to and influence legislation)
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 30%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | Low | 3
0.9
DFID Share revised/needs revision? | No
If Yes, why was/is this? |  | 1
Original or Revised DFID Share |  | 2
3
Indicator 1 (leave blank if standard indicator) | Increased number of Bills/ policies/ Acts considered by the parliament and the government on VAW. | 4
Is this a Standard Indicator? | No | 5
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Baseline of 2006 stated that Discriminatory laws, policies and procedures such as Hudood Ordinance, Qanoon-e-Shahadat etc exist (i.e. no legislation in place on sexual harassment, acid crime and domestic violence). By 2010,GJP initiatives have influenced implementation or enactment at least five key legislations / policies on VAW. | 0
Progress made in the period covered by this review, including numbers. | Sub project activities have led to the strengthening of voices in support of the approval and implementation of the Sexual Harassment Act (SHA) by supporting Alliance Against Sexual Harassment Act (AASHA)'s partner organizations such as Bedari. Project support has also facilitated government to establish one window VAW reporting counter that has potential to grow institutionally. The project has also strengthened the capacity of four districts of Sindh Police, and they are now handling VAW cases sensitively as crimes against Human Rights. The Acid Crime bill is being actively pursued by Acid Survivor Foundation with GJP support and the bill is progressing in the NA. Less conventional 'policy' work is the initiative by the Mubarrak NGO in KPK where Maulvis are disseminating interpretations of Islam that challenge the practice of Swara or using women as payment for blood-money. To date 32 women have been saved from being exchanged in Swara payments. Several organisations are working on making policies work at local level - eg. Bedari supports women in registering VAW cases at local police stations and getting upkeep from fathers for children. Attribution is based on based on monitoring data showing increased levels of awareness & access to information of direct beneficiaries of the project on legal rights relating to VAW, and the fact that beneficiaries in some sub projects are becoming active in advocacy to reduce VAW.
Indicator 2 (leave blank if standard indicator) | Number of CSO proposals funded to work on legislation and policy achieving their objectives
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Starting with a zero baseline, at least 8 policy advocacy projects from CSOs achieving objectives.
Progress made in the period covered by this review, including numbers | 18 projects of GJP have advocacy against VAW as primary objective and almost all the project (41) one way or the other touch upon awareness raising and information dissemination. Most of them have been effective in their activities, although not all are finished yet. Policy advocacy has not been the direct topic of sub projects, but 2 policy research proposals are in the pipeline that will have the option of producing policy briefs.
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 1 | 2 | 0.75
Impact Weighted Score | 22.5 | 0.225
Justification for the Score | Sub projects have worked proactively on the reform and approval of legislation (AASHA was a particular success) and strengthened the voices of communities and beneficiaries to be aware of VAW and to demand implementation of policies addressing VAW. CSO capacity has been strengthened to work toward policy advocacy.
Output 1 Recommendation 1 | Advocacy & awareness raising should be linked to a process where one-off activities are built upon/aggregated to create more impact.
Output 1 Action Point 1 | PMU/UNDP (UN Women) to discuss ways to maximise impact of GJP sub projects.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2
Output 1 Recommendation 3
Output 1 Action Point 2
Output 1 Action Point 3
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Strengthened government and CSOs capacity to implement laws and policies against VAW (Activity: fund CSOs and government to ensure effective implementation of policy, laws and systems.
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 30%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.6
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator) | % of GJP funded CSOs projects contribute to implementation of policies, laws and systems.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | From a zero base line to 40% of the projects work towards attainment of the indicator.
Progress made in the period covered by this review, including numbers | Most of the project activities are geared to contribute to engage government related agencies/departments for sensitization and/or support implementation of policies & laws especially through sensitization and capacity building of police and lawyers. These activities have provided entry points to work with government agencies. However the M&E is insufficient in relation to measurement against the indicator.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | % of GJP funded government projects contribute to implementation of policies, laws and systems.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | From a zero base line to 20% of the projects work towards attainment of the indicator.
Progress made in the period covered by this review, including numbers | This is a difficult and slow moving area. There has been alignment with the government to sensitize & train police staff in 4 districts of Sindh which under 3rd round is expected to cover 23 districts and has an option of up scaling and replication in Baluchistan.The One-Window help desk under Rawalpindi government though at nascent stage has the potential to deliver if properly institutionalized and managed.
Sindh Police Department has established Anti Karo Kari Cells in four districts of Sindh, which are positively impacting the culture of police stations. The project provided an opportunity to the Sindh Police Department to fill the gap in information on human rights and VAW amongst police officials, as traditionally these are neither a priority nor a part of police training. The pool of 140 police officials trained as master trainers are playing a strong outreach role in sensitising and improving the professional capacity of police officials in registering and handling cases of VAW. The Sindh Police Department intends to scale up the project to cover all districts in the province and is also making efforts to integrate VAW in regular on-going training courses.
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 2 | 3 | 0.5
Impact Weighted Score | 15 | 0.15
Justification for the Score | Government departments do not usually bid for projects and are generally reluctant to accept donor support in sensitive areas. Hence the overall number of projects with government is small, but where there are projects progress is slow but appreciable
Output 2 Recommendation 1 | Replication of Police sensitization and capacity building should be pursued
Output 2 Action Point 1 | Explore possibilities for replication of this work through other sub projects and/or through an extension of the work with Sindh police and/or in Baluchistan.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2 | Sub-projects should develop a strengthened focus on effective evidence-based advocacy in order to influence implementation of laws, policies and systems.
Output 2 Action Point 2 | Develop a more robust monitoring system; group sub projects working in similar thematic areas and aggregate lessons from M&E for stronger messages and greater impact.
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 | Increased awareness and knowledge of communities on combating violence and abuse against women and girls (Activity: fund government and CSOs to work with/talk to/train communities and CBOs).
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%) | 40%
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk | Medium | 2
0.8
DFID Share revised/needs revision? | No
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator) | Percentage of funded proposals which have enabled communities to engage with Government departments, Police and CSOs to report VAW and prevent violence and abuse.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Baseline zero to 40%
Progress made in the period covered by this review, including numbers | This target has been met due to advocacy & awareness raising efforts under Outputs 1 & 2, as each of the sub project has either a legal aid/counselling component and/or helping communities to better understand and take recourse, and develop redressal systems. Most of the beneficiaries were enthusiastic and there are examples of both women and men becoming advocates of reducing VAW and spreading improved information.There is little direct evidence of violence rates being reduced.13. GJP has supported and strengthened CSO advocacy efforts for policy, implementation and protective legislation. The Acid Survivor Foundation (ASF) has carried out affective advocacy with stakeholders and parliamentarians on the Acid Control and Crime Prevention Bill (ACCPB).
The advocacy efforts of the NGO led the Chief Justice of The advocacy efforts of the NGO led the Chief Justice of Pakistan to take suo moto action and order the government to pass legislation on acid violence and provide free medical services and legal aid to victims of acid violence. The advocacy of ASF led to the first Acid Control and Crime Prevention Bill as a private member bill – this was tabled in 2010. Although the ACCPB has not been passed as yet there is a likelihood that it will be passed by the parliament within the project period. The project partners also supported the implementation process of the law passed on Sexual Harassment and contributed to the advocacy efforts on the Domestic Violence Bill
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) | Number of CSO proposals funded to work on community sensitization which are achieving their objectives.
Is this a Standard Indicator? | No
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any) | Baseline zero to 40%
Progress made in the period covered by this review, including numbers | 100% of the funded projects have a sensitization and information dissemination support role.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 3 | 2 | 0.75
Impact Weighted Score | 30 | 0.3
Justification for the Score
Output 3 Recommendation 1 | Targeted support can consolidate advocacy and sustainable activism: monitoring should be strengthened and clear messages developed to help communities be successful in advocating to reduce VAW in all forms.
Output 3 Action Point 1 | Strengthen monitoring system as above and develop targeted advocacy messages across sub-projects which are relevant for local audiences as well as policy makers.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2 | Data on changes in VAW rates at local levels is needed. If numbers are not available, perception surveys should be set up
Output 3 Action Point 2 | PMU and UNDP to agree how data will be collected
Output 3 Action Point 2
Output 3 Action Point 3
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 4 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 4 Recommendation 1
Output 4 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
Output 4 Action Point 2
Output 4 Action Point 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list | 2. Number of classrooms constructed or rehabilitated | 0
Milestone for this review (including number, if any) | what you started out to achieve - target for that year
Progress made in the period covered by this review, including numbers | quantity actually delivered
Output Performance for Output 5 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 5 Recommendation 1
Output 5 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## B Project Scoring
B: Project Scoring
Review Date (dd/mm/yyyy) | 2011-02-08
Impact Weighting (must = 100) | 100%
Total Impact Score | 67.5 | 0.675
Output Risk | Medium | 2.3
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems
Quantitative data from project/programme study | X
Government assessment | X
Joint donor review | X
Independent consultant review | X
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner
National non-Government partner
Independent consultant | X
Donor partners
DFID staff
Donor partners
Comment here on the Method of Scoring and Scoring Responsibility.
Scoring Recommendation 1
Scoring Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | GJP has managed to work with range of CSO and Government partner each having its own strength and weaknesses. However, the sub-project partners required more technical support than was envisaged.The networking and sharing of resources remains weak and at an informal level. The partners have not capitalised on each others strengths and GJP has not yet been able to extend support as partners to both widen and deepen the impact of the activities.
Working with Partners Recommendation 1 | Possibilities for consolidating the work of GJP partner into a VAW network be explored.
Working with Partners Action Point 1 | Develop a final Call for Proposals focusing on the development of one network, based on but not limited to the work of the GJP sub-projects.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2 | Care technical appraisals of local partners' capacities should be carried out in advance of commencement of sub-project activity
Working with Partners Recommendation 3
Working with Partners Action Point 2 | Identify any needs for TA in existing sub-projects and ensure that future project partners are carefully appraised
Working with Partners Action Point 3
2. Best Practice / Innovation | Best practice has been engagement with Sindh Police department to sensitize the police station staff to take VAW as 'a crime', prioritize and take an aware method to handle it.
Best Practice / Innovation Recommendation 1 | Technical support should be offered to the government department for institutionalization of this practice.
Best Practice / Innovation Action Point 1 | Hold meetings/workshops with relevant departments to agree how to take forward.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | Project Management had 3 layers i.e. Execution Agency UNDP, Implementing Agency UNOPS and Project Management Unit (PMU). Additionally, the Funds Management Committee is responsible for the allocation of Challenge Fund sub projects, with DFID in a support role. PMU has been servicing all the 'bosses' and has been administratively bogged down, without having required technical M&E and gender skills in-house. DFID's shifting goal posts through Logframe revision has also had a negative effect on project management and the latest iteration is yet to be formally approved.
The prime lesson learnt is that when a project of such nature is designed which is expected to be integrated to wider programme umbrella (GSP in this case) with multi Agencies (UNDP & UNOPS) responsible for its execution and implementation, all partners should agree to clear roles and responsibilities, formalised in MoUs etc, and technically reflected in the Project Document.
Project Management Recommendation 1 | DFID should consider a structure based on a technically empowered PMU an implementing/execution agency which could be UNOPS, with technical support from UN Women being offered through UNDP
Project Management Action Point 1 | In view of the winding down of GSP & Gender Unit of UNDP and the presence of UNOPS in Pakistan, it is suggested that DFID should clarify the contractual roles, responsibilities and nature of support of both UNDP and UNOPS to GJP for enhanced understanding on following lines: i) technical and gender advice and support to the PMU: DFID to discuss with UNDP possible sources of gender support and facilitate the greater involvement of UN Women. (The DAO agenda should enable this). ii) Discuss transfer of funds from UNDP to support UN Women’s greater involvement iii) Continue use of UNOPS for programme management and the standardization of the asset management function of GJP. iv) Strengthen the budgetary allocation to M&E and ensure that strong M&E capacity exists in the PMU
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved. | 1.The project framework has been stretched to relate to range of priorities of government and donors, and has had to work within different institutional structures. The project design is based on an "interlocutor" model that related to GOP, DFID, UNDP initiatives under the GSP umbrella and CSOs. It has many 'owners' but responsibility rests with a administratively under-empowered PMU with constant staff turnover, and an FMC that lacks both substantive technical expertise on gender or VAW and the wherewithal for backward integration of GJP sub-projects with the GOP reform agenda. UNDP, UNOPS and DFID have not provided or shared responsibility for technical backstopping to GJP, although DFID was of the understanding that the 7.5% contribution to UNDP covered TA backstopping from UNDP
2. GJP efforts to create synergies within its CSO partners have been limited to an annual get together, and CSOs and government partners have not been able to develop this into public-private partnership. Similarly, few synergies have been created with other GSP projects, the UNDP gender portfolio or the DFID portfolio. UNDP's Gender Unit has been disbanded
Key issues, points of information or additional comments that may be useful for this or other project teams. | 1. GJP has been subjected to a continuous revision of the log frame by DFID from March 2007 to March 2009 to November 2010. This has been taxing on the project. The last version of log frame is yet to be approved by Funds Management Committee (FMC). The roles of the GJP team and the FMC in log frame based target setting has been secondary has been driven by the DFID system requirements and changes in the way that DFID monitors and values its programmes.
2. GJP has been working without a useable baseline. In the absence of benchmarks established through a baseline at the beginning of the project, it is difficult to assess the impact of the project and attribute any impact and/or changes in the VAW spectrum to the project activities. Despite this, the sub-projects have had a wide range of local level impacts. The challenge now is to scale these up to have broader significance.
Other Recommendation 1
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
966875 | GJP Programme Memorandum
2981924 | GJP Revised Logical Framework
GJP sub projects 41 project documents, log frames & financials
GJP 13 research reports
910836 | MOU between DFID & UNDP
1835427, 1844433 | Multi donor review of GSP 2008
1567556 | Desk review 2008 of GJP
Information/ advocacy material of CSOs
Evidence Recommendation 1
Evidence Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions? | No
If Yes, what was the cause?
Date Suspended (dd/mm/yyyy)?
What were the consequences?
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project. | 1. VAW as subject, as of now, can only be measured in qualitative terms. The project has made significant contribution in sensitization and awareness raising however, its policy specific inputs have been less significant.
2. GJP has been working through grass root CSOs and Government departments, which is commendable. Further targeted support is needed tp provide a connecting forum between the two bodies for lasting development and extended outreach. GJP partnership with the Government has the potential for longer term sustainability by encouraging the government to become part of the process moving forward.
3. GJP has created a social capital at the community and institutional level through awareness raising and sensitization that has a potential to be sustained in the post-project period.
4. The project has strengthened indigenous capacity of smaller NGOs to work on VAW at district level, which has generated positive response and is an impetus for them to continue to work on VAW even without funding support from the GJP.
5. The project has created a sustainable knowledge pool on VAW through grass root situation analysis, pipeline research studies and range of IEC material i.e. booklets, documentaries and posters, which will continue to be used and reproduced.
6. Support services, legal aid, counselling, rehabilitation support and help lines are unlikely to be sustained by the NGOs after the expiry of the project life. However if the same are linked with UN Women and Aurat Foundation’s GEP initiatives focusing VAW, it has the possibility of sustenance.
Sustainability Recommendation 1 | Continue support to reduction of VAW efforts of the CSOs for positive influence on policy formulation and elimination of discriminatory laws leading to VAW
Sustainability Action Point 1 | The DFID future support to VAW should be: a. designed within the structural approach. The structural form of violence, poverty, social exclusion, patriarchal traditions and cultures are deeply connected with direct forms of violence against women. b. target those legislative and policy areas that dent and undermines structures of power which breeds gender violence. c. designed in a manner not only to support practical needs but also the strategic interests of survivors of violence. d. DFID should consider taking lead in supporting and strengthening the voices of civil society on VAW and helping them to mobilize external resource pool.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2 | M&E should be strengthened and aggregated between sub-projects where feasible, in order to provide robust data to underpin future policies
Sustainability Action Point 2 | PMU and UNDP/UN Women to agree activities

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | Goal settings have to be realistic with some qualitative attribution based indicator. It would be useful to highlight the amendments/ repeal of certain number of discriminatory laws could be an indicator for GJP as majority of its partners are working on advocacy and policy change. | DFID/UNDP/PMU
R2 | 0
R3 | 0
A1: Purpose
R1 | The purpose level indicators should be more quantified and less ambitious. Indicators at all levels should be refreshed and be made more relevant to what a Challenge Fund project of this nature can hope to achieve. Challenge fund arrangements should be based on clearly defined project framework with targeted areas of intervention so that the activities of various project partners can have an aggregated impact. | DFID/UNDP/PMU
R2 | The spread of GJP sub projects across Preventative (awareness raising) Protective (legislation) and Supportive (support services legal aid, counselling, rehabilitation serviced to survivors of violence), should be strategically grouped, balanced and managed in terms of resource allocatio, coverage of thematic areas and advocacy. | UNDP/PMU
R3 | M&E should have larger budgetary allocation and should be part of programme cost, in order to develop clear, evidence based messages for influencing. | DFID/UNDP/PMU
A1: Risk
R1 | 0
R2 | 0
R3 | 0
A1: Logframe
R1 | 0
R2 | 0
R3 | 0
A1: DSOs
R1 | 0
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | 0
R2 | 0
R3 | 0
A2: Outputs
R1.1 | Advocacy & awareness raising should be linked to a process where one-off activities are built upon/aggregated to create more impact. | UNDP/PMU
R1.2 | 0
R1.3 | 0
R2.1 | Replication of Police sensitization and capacity building should be pursued | UNDP/PMU
R2.2 | Sub-projects should develop a strengthened focus on effective evidence-based advocacy in order to influence implementation of laws, policies and systems.
R2.3 | Develop a more robust monitoring system; group sub projects working in similar thematic areas and aggregate lessons from M&E for stronger messages and greater impact. | UNDP/PMU
R3.1 | Targeted support can consolidate advocacy and sustainable activism: monitoring should be strengthened and clear messages developed to help communities be successful in advocating to reduce VAW in all forms. | UNDP/PMU
R3.2 | Data on changes in VAW rates at local levels is needed. If numbers are not available, perception surveys should be set up | UNDP/PMU
R3.3 | PMU and UNDP to agree how data will be collected
R4.1 | 0
R4.2 | 0
R4.3 | 0
R5.1 | 0
R5.2 | 0
R5.3 | 0
R6.1 | 0
R6.2 | 0
R6.3 | 0
R7.1 | 0
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | 0
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | Possibilities for consolidating the work of GJP partner into a VAW network be explored.
R2 | Care technical appraisals of local partners' capacities should be carried out in advance of commencement of sub-project activity
R3 | 0
Best Practice / Innovation
R1 | Technical support should be offered to the government department for institutionalization of this practice.
R2 | 0
R3 | 0
Project Management
R1 | DFID should consider a structure based on a technically empowered PMU an implementing/execution agency which could be UNOPS, with technical support from UN Women being offered through UNDP
R2 | 0
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | 0
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | Continue support to reduction of VAW efforts of the CSOs for positive influence on policy formulation and elimination of discriminatory laws leading to VAW
R2 | M&E should be strengthened and aggregated between sub-projects where feasible, in order to provide robust data to underpin future policies
R3 | PMU and UNDP/UN Women to agree activities
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | In next phase of project, if any, the goal indicators need to be nationally grounded and qualified. They should focus on effectiveness and sustainability of initiatives and be targeted on certain policies and pockets of VAW i.e. geographically and by governmental institutions.
AP1.2 | 0
AP1.3 | 0
A1: Purpose
AP1.1 | Revisit the logframe after the review and develop new indicators where necessary, better to reflect the nature and ambitions of the activities to allow the PMU to play a more effective role.
AP1.2 | Hold workshops with project partners to develop activity groupings and advocacy messages; consider teaming up with other organisations working on similar themes but not funded through GJP. Align with the government for relevant policies and use the same focus for advocacy work.
AP1.3 | Strengthen the M&E system and use the information to plan a two pronged support by working with aligning with government on advocacy for relevant policies, whilst at the same time communicating messages to citizens.
A1: Risk
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Logframe
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: DSOs
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Cross-Cutting Markers
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | PMU/UNDP (UN Women) to discuss ways to maximise impact of GJP sub projects.
AP1.2 | 0
AP1.3 | 0
AP2.1 | Explore possibilities for replication of this work through other sub projects and/or through an extension of the work with Sindh police and/or in Baluchistan.
AP2.2 | Explore possibilities for replication of this work through other sub projects and/or through an extension of the work with Sindh police and/or in Baluchistan.
AP2.3 | Develop a more robust monitoring system; group sub projects working in similar thematic areas and aggregate lessons from M&E for stronger messages and greater impact.
AP3.1 | Strengthen monitoring system as above and develop targeted advocacy messages across sub-projects which are relevant for local audiences as well as policy makers.
AP3.2 | 0
AP3.3 | 0
AP4.1 | 0
AP4.2 | 0
AP4.3 | 0
AP5.1 | 0
AP5.2 | 0
AP5.3 | 0
AP6.1 | 0
AP6.2 | 0
AP6.3 | 0
AP7.1 | 0
AP7.2 | 0
AP7.3 | 0
AP8.1 | 0
AP8.2 | 0
AP8.3 | 0
AP9.1 | 0
AP9.2 | 0
AP9.3 | 0
AP10.1 | 0
AP10.2 | 0
AP10.3 | 0
B: Scoring
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | Develop a final Call for Proposals focusing on the development of one network, based on but not limited to the work of the GJP sub-projects.
AP1.2 | Identify any needs for TA in existing sub-projects and ensure that future project partners are carefully appraised
AP1.3 | 0
Best Practice / Innovation
AP1.1 | Hold meetings/workshops with relevant departments to agree how to take forward.
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | In view of the winding down of GSP & Gender Unit of UNDP and the presence of UNOPS in Pakistan, it is suggested that DFID should clarify the contractual roles, responsibilities and nature of support of both UNDP and UNOPS to GJP for enhanced understanding on following lines: i) technical and gender advice and support to the PMU: DFID to discuss with UNDP possible sources of gender support and facilitate the greater involvement of UN Women. (The DAO agenda should enable this). ii) Discuss transfer of funds from UNDP to support UN Women’s greater involvement iii) Continue use of UNOPS for programme management and the standardization of the asset management function of GJP. iv) Strengthen the budgetary allocation to M&E and ensure that strong M&E capacity exists in the PMU
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | The DFID future support to VAW should be: a. designed within the structural approach. The structural form of violence, poverty, social exclusion, patriarchal traditions and cultures are deeply connected with direct forms of violence against women. b. target those legislative and policy areas that dent and undermines structures of power which breeds gender violence. c. designed in a manner not only to support practical needs but also the strategic interests of survivors of violence. d. DFID should consider taking lead in supporting and strengthening the voices of civil society on VAW and helping them to mobilize external resource pool.
AP1.2
AP1.3
Additional Action Points arising
AP1.1
AP1.2
AP1.3