## Logframe
PROJECT NAME | Gender Justice & Protection Project (GJP), Pakistan - 108745
IMPACT | Impact Indicator 1 |  | Baseline (2008) | Milestone 1 | Milestone 2 | Target 2012
Increased gender equality in Pakistan | Gender Inequality Index | Planned | 0.721 |  |  | 0.681
Achieved
Source: Media
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target 2012
| Gender Empowerment Measure (GEM) |  | 0.377 |  |  | 0.41
Achieved
Source
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Target 2012 | Assumptions
Reduction in violence against women and girls in project areas | Increased mobility and access to services (education, health, financial services etc) for women and girls in project areas |  |  |  |  | 20% increase in women's mobility and access to services in project areas | All segments of society and government effectively resist anti gender equality ideologies.
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Target 2012
| Incidents of violence against women and girls | Planned |  |  |  | 30% reduction in the incidents of VAW as reported in the media and project progress reports
Achieved
Source
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Target 2012 | Assumption
Necessary policies, laws and enforcement mechanisms established to protect women and girls from violence within the scope of GJP sub projects | Number and types of policies, bills, acts and mechanisms formulated and tabled at relevant forums | Planned | No legislation in place on sexual harassment, acid crime and domestic violence |  |  | Domestic Violence Bill, Acid Control and Crime Prevention Bill, Sexual Harassment Bill | 1. Government remains committed to gender equality, 2. Legislative processes are not interrupted by abrupt changes in government and political instability
Achieved
Source
Parliamentary records (provincial and national assemblies and senate), partner reports, GJP reports, media
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Target 2012
| Number and types of policies, bills, acts and mechanisms approved and promulgated | Planned | No legislation in place on sexual harassment, acid crime and domestic violence |  |  | Domestic Violence Bill, Acid Control and Crime Prevention Bill, Sexual Harassment Bill
Achieved
Source
Copies of approved laws, acts and bills etc
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Target 2012
20% |  | Planned
Achieved
|  | Source |  |  |  |  | RISK RATING
Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Target 2012 | Assumptions
Strengthened government and CSOs capacities to provide necessary supportive and rehabilitative services to victims of VAW, within the scope of GJP sub projects | Access to and quality of supportive and rehabilitative services being provided by public sector entities to women and girls | Planned |  |  |  | 15% increase in access to services which meet minimum international standards | 1. Government remains committed to gender equality, 2. Committed and capable CSOs come forward to implement project components
Achieved
Source
Partner reports, GJP reports, Media coverage, Sample Survey
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Target 2012
| Number of Anti Karo Kari cells institutionalized within the administrative structures of police stations in Sindh | Planned | zero |  |  | 20
Achieved
Source
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 | Milestone 2 | Target 2012
35% | Access to and quality of supportive and rehabilitative services being provided by CSOs to women and girls | Planned |  |  |  | 30% increase in access to services which meet minimum international standards
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | Partner reports, GJP reports, Media coverage, Sample Survey |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Target 2012 | Assumptions
Increased awareness among citizens to prevent and reduce VAW and support victims of VAW, within the scope of GJP sub projects. | % of men and boys who oppose violence against women and girls | Planned |  |  |  | 30% men and boys oppose violence against women and girls | All segments of society and government effectively resist anti gender equality ideologies and succeed in containing and reversing their spread
Achieved
Source
Sample Survey
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Target 2012
| % of men and boys who actively advocate for ending VAW | Planned |  |  |  | 15% men and boys actively advocate to end violence against women and girls
Achieved
Source
Sample Survey
IMPACT WEIGHTING (%)
35%
RISK RATING
Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 | Milestone 2 | Target 2012 | Assumptions
A national alliance to collectively raise voice against VAW and pursue systemic reforms is created | Institutional and organizational status of National Alliance | Planned |  |  |  | A fully functional alliance with clear strategic plan and provincial chapters. The strategic plan will define the long term roadmap and governance structure. | Suitable and capable organization(s) come forward to lead this effort
Achieved
Source
GJP progress report, Details of financial and human resources available to the alliance, Copy of alliance Strategic Plan
| Output Indicator 4.2 |  | Baseline | Milestone 1 | Milestone 2 | Target 2012
| Number of active CSO members | Planned |  |  |  | 40 CSOs with sufficient representation from all parts and regions of the country
Achieved
Source
IMPACT WEIGHTING (%)
10%
RISK RATING
Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)

## Acitivites log
Activities Log
OUTPUT 1 | ACTIVITY 1.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer
Necessary policies, laws and enforcement mechanisms established to protect women and girls from violence | Support initiatives to strengthen policies, laws and mechanisms | Formulation and tabling of Acid bill (National and Baluchistan) | Enforcement of sexual harassment act | Enforcement of marriage contract, government's minimum wage award and Cr. PC 174 |  | Kashif Noon/ Zishan Ahmad
| ACTIVITY 1.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
Monitoring Officer
OUTPUT 2 | ACTIVITY 2.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer
Strengthened government and CSOs capacities to provide necessary supportive and rehabilitative services to victims of VAW, within the scope of GJP sub projects | Support public sector services | Appointment of female parole officers in KPK | Mobilizing counter trafficking task force in KPK | Instituting gender crime cells |  | Kashif Noon/ Zishan Ahmad
|  | Milestone 4 | Milestone 5 | Milestone 6
|  | Successful modeling of family justice center | Improve substance abuse rehabilitation services | Trained government officials |  | Kashif Noon/ Zishan Ahmad
| ACTIVITY 2.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| Support SPD in establishing anti karo kari cells | Establishment of anti karo kari cells in 4 districts | Establishment of anti karo kari cells in 20 districts | Trained police officials |  | Kashif Noon/ Zishan Ahmad
| ACTIVITY 2.3 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| Support CSOs to address access to and quality of protective and rehabilitative services | Mobilize complaint services | Establish referral systems | Provision of legal aid to women |  | Zishan Ahmad/ Shameela Ahmad
OUTPUT 3 | ACTIVITY 3.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer
Increased awareness among citizens to prevent and reduce VAW and support victims of VAW, within the scope of GJP sub projects. | Educate men and boys to disapprove VAW | 10% boys and men disapprove VAW | 20% boys and men disapprove VAW | 30% boys and men disapprove VAW |  | Zishan Ahmad/ Leena Maqsood
| ACTIVITY 3.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| Mobilize men and boys to advocate for ending VAW | 5% men and boys advocate ending VAW | 10% men and boys advocate ending VAW | 15% men and boys advocate ending VAW |  | Zishan Ahmad/ Leena Maqsood
Monitoring Officer
OUTPUT 4 | ACTIVITY 4.1 | Milestone 1 | Milestone 2 | Milestone 3 | Risks | Monitoring Officer
A National Alliance to collectively raise voice against VAW and pursue systemic reforms is created | Activation of National Alliance | Shared conception of National Alliance | Strategic planning for National Alliance | Fully functional national alliance with necessary human and financial resources |  | Zishan Ahmad
| ACTIVITY 4.2 | Milestone 1 | Milestone 2 | Milestone 3 |  | Monitoring Officer
| Mobilization and strengthening of National Alliance | 20 active CSO members | 40 active CSO members | Trained CSO leaders |  | Zishan Ahmad
Monitoring Officer