## Template
Please refer to the Smart Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE | Low Energy Inclusive Appliances (LEIA)
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022) | Assumptions
Improved access to reliable energy services, leading to better well-being for poor people and livelihood opportunities. | People with improved energy access through more efficient appliances. Measured by sales, market size and presence of LEIA appliances, including: a) Refrigeration b) TVs c) fans d) SWPs, agri-processors (businesses metric tbc) | Planned | [5 empty] | a) 300,000 b) 1.2 million c) 1 million d) TBD | Assumes UK Government funding continues. Definitions: No. sales = sales of LEIA supported appliances (all near market, and horizon technologies as it becomes possible/appropriate). Market definition = global market (although acknowledging focus on specific regions countries, where appropriate). Business energy access (d) will be monitored through sales of specific business related products, such as SWP, agri-processors and other products. Baseline activities: In January 2019, we will obtain appliance specific data from GOGLA market research data for refrigeration (a), TVs (b) and fans (c). SWPs, agriprocessors and other business related products (d) methods will be defined further during year 2.
Achieved
Source
Sales, market size and presence of LEIA appliances: How measured: Using GOGLA market research data and other approaches (e.g. to monitor GOGLA non-affiliate sales). In future, when data collection methods allow, the indicator will also split between (i) new energy access, defined as appliances taken up by those who previously did not have energy access and (ii) higher tier those who have energy access, who are adding new appliances. Initial target numbers sourced from modelling done to inform the LEIA Business Case. These may be updated in future as improved data becomes available.
| Impact Indicator 2 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022) | Assumptions
| Income and livelihoods, measured by: a) Number of jobs b) i) household savings due to LEIA appliances ii) total income generated by businesses due to LEIA appliances | Planned | [5 empty] | a) 490 | Influenced by the types of appliances supported through LEIA outputs and market activities. Definitions: Jobs - focus on use-related jobs. Longer term Target: 9300 jobs by 2030 Baseline activities: Use existing data A6:C18from GOGLA surveys for 2018 (income based metric from after sales surveys). Investigate approaches for non-GOGLA affiliated appliances. Conduct a review of other published methods and data
Achieved
Source
How measured: Market research (follow up surveys with appliance purchasers – e.g. GOGLA surveys) to obtain an understanding of for a) additional income resulting from use of appliances, and b) impact of LEIA appliances on household finances, including i) household savings - initially estimates will be derived from data available through Global LEAP and GOGLA. The methodology will be further developed in year 2 as we gather more data through consumer research projects. ii) income generated from income generating activities, enabled by LEIA appliances. The GOGLA and Global LEAP RBF surveys asks questions which enable a financial estimate from common income generating activities stemming from LEIA appliance use.
| Impact Indicator 3 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022) | Assumptions
| Environmental impact, measured by: GHG emissions avoided | Planned | tbc |  |  |  |  | tbc | Influenced by the types of appliances supported through LEIA outputs and market activities. Definitions: Develop a modelling based method, with a clear set of assumptions (TBD) Baseline activities: Review possible methods used for a modelled approach. Use to set a baseline for this year if a sensible method can be determined. Different approaches for some appliances (e.g. solar water pumps) will be required. A research project to investigate LEIA influence on e-waste will be undertaken during year 1.
Achieved
Source
How measured: A modelling approach, informed by a literature review and assessment of existing approaches (tbc during year 1).
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022) | Assumptions
Halve the cost and double the efficiency of a range of Low Energy Inclusive Appliances in Least Developed Countries | Cost reductions in the average retail price of at least four LEIA appliances, including: a) refrigeration ($/m2) b) TVs ($/in2) c) fans ($/in) d) SWPs (metric tbc) | Planned | a) refrigeration i) refrigerators: $18.49 ii) refrigerator-freezer combination units: $14.72 b) TV : $0.93 c) Fans: $2.60 | a) refrigeration i) refrigerators: $17.57 ii) refrigerator-freezer combination units: $14.28 b) TV : $0.88 c) Fans: $2.47 | a) refrigeration i) refrigerators: $15.72 ii) refrigerator-freezer combination units: $13.25 b) TV : $0.79 c) Fans: $2.21 | a) refrigeration i) refrigerators: $12.94 ii) refrigerator-freezer combination units: $12.51 b) TV : $0.65 c) Fans: $1.82 | a) refrigeration i) refrigerators: $11.09 ii) refrigerator-freezer combination units: $11.78 b) TV : $0.56 c) Fans: $1.56 | a) refrigeration i) refrigerators: $9.25 (50% reduction) ii) refrigerator-freezer combination units: $10.30 (30% reduction) b) TV : $0.47 (50% reduction) c) Fans: $1.30 (50% reduction) | Focus on near term products for 2018 and 2019. Key definitions: For both cost and energy efficiency; ‘Best-in-Class’ – defined as the average value of top 20% of the market, based on the products tested through the LEIA program, in terms of cost or energy efficiency. ‘Average’ – defined as the average value of the market, based on the products tested through the LEIA program, in terms of cost or energy efficiency. See associated methods note for details on energy efficiency metrics definitions and methods for measuring indicators (note - for fans the baseline and targets are based on pedestal and table fans as limited data is available for ceiling fans). It is found that the energy efficiency and price are seen to correlate with the product size. To enable comparison of products across various sizes, we define the efficiency and cost metrics as EEI per unit of product size or cost per unit of product size. For each appliance type, product size is defined as following. 1. Refrigerators: Surface area (m2) is used instead of volume (m3) to enable more accurate comparison of refrigerators and refrigerator-freezers of various sizes. Refrigerator heat gain is dictated by the surface area and not volume. The surface area is calculated as volume to the power 0.67. 2. Fan: Fan size is the measurement of diameter of the cycle traced out by the tips of the fan blades, measured in inch (in). 3. TV: Viewable screen area of the television in square inch (in2).
Achieved
Source
Global leap data platform market testing data. Costs data sourced from best available data, including product purchase data (see detailed methods note for further details).
| Outcome Indicator 2 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022)
| Efficiency improvements in the average energy efficiency values of at least four LEIA appliances, including: a) refrigeration (m2/kWh/day) b) TVs (In2/W) c) fans (m3/min/W) d) SWPs (metric tbc) | Planned | a) refrigeration i) refrigerators: 45.66 ii) refrigerator-freezer combination units: 25.74 b) TV : 12.88 c) Fans: 2.44 | a) refrigeration i) refrigerators: 50.23 ii) refrigerator-freezer combination units: 27.03 b) TV : 13.52 c) Fans: 2.51 | a) refrigeration i) refrigerators: 54.79 ii) refrigerator-freezer combination units: 29.60 b) TV : 14.81 c) Fans: 2.56 | a) refrigeration i) refrigerators: 59.36 ii) refrigerator-freezer combination units: 32.18 b) TV : 16.74 c) Fans: 2.68 | a) refrigeration i) refrigerators: 66.21 ii) refrigerator-freezer combination units: 33.46 b) TV : 18.03 c) Fans: 2.81 | a) refrigeration i) refrigerators: 73.06 (60% EE increase) ii) refrigerator-freezer combination units: 36.04 (40% EE increase) b) TV : 19.32 (50% EE increase) c) Fans: 2.93 (20% EE increase)
Achieved
Source
Global leap data platform market testing data. Costs data sourced from best available data, including product purchase data (see detailed methods note for further details).
| Outcome Indicator 3 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022) | Assumptions
| Evidence of increased market ecosystem strength, and alignment, measured by: a) number of companies active in LEIA appliances b) number of active users of EforA database per month | Planned | a) 80 b) n/a (database will be launched in October 2018) | a) 90 b) 500 | a) 105 b) 800 | a) 120 b) 1000 | a) 135 b) 1200 | a) 150 b) 1400 | Definitions: Availability of market data and evidence of ecosystem strength – The quantitative data that will be collected to track these output indicators will be complemented with a qualitative assessment of market stakeholders by a third party evaluator. Baseline activities: The number of companies active in LEIA appliances includes both manufacturers and distributors of off-grid fans, televisions, refrigerators, and solar water pumps. This includes companies that have participated in Global LEAP Awards competitions, companies whose products were identified from market scoping, and information received from GOGLA on their members that manufacture and/or distribute appliances. No work was done in the baseline to distinguish companies that manufacture low energy appliances from standard appliances. OI 3 b) No data was available on the baseline because the database will be launched in October. The targets were created by looking at the web traffic for related websites (e.g. CLASP S&L policy database and Global LEAP)
Achieved
Source
a) Companies that have participated in awards competitions, product testing, technical working groups. Information was also received from GOGLA and verified using companies websites b) E4A database web analytics capability will be built into the database to track usage.
| Outcome Indicator 4 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022) | Assumptions
| Matching public and private investment a) E4A members how much funding allocated to further the goals of doubling the efficiency and halving the cost of efficient appliances. b) Private investment activity to support LEIA appliances | Planned | a) £ 31.7 million b) 0 |  |  |  |  | a) £ 100 million b) £ 6 million | OI 3a: Defined as EforA Coalition members that allocate funds to further the goals of doubling the efficiency and halving the cost of efficient appliances. OI 3b: Defined as co-funding for R&D co-investment activities.
Achieved
Source
OI 4: Co-funding is dependent on funding availability from partners. Measured by: (a) funding allocated to further the goals of doubling the efficiency and halving the cost of efficient appliances from public/philanthropic sources. (b) Private investment is matching funds for R&D investment estimates from workstream 5 activities.
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
| 18m |  |  | 31.7m | 49.7m |  |  | 36%
INPUTS (HR) | DFID (FTEs)
0.3
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022) | Assumptions
Market Stimulation & Incentives | Engagement and communications, including: a) number of stakeholders consulted to scope and design competitions b) number of partner organizations engaged to promote participation in competitions c) number of partner organizations engaged to promote results of competition | Planned | 0 | a) 30 b) 0 c) 0 | a) 60 b) 10 c) 10 | a) 60 b) 20 c) 20 | a) 60 b) 20 c) 20 | a) 60 b) 20 c) 20 | Indicator 1.1: Stakeholders and partner organisations engaged is influenced by the state of the market for each appliance group (link to Output 4) Indicator 1.2: Interest and applications from firms/products applying remains high i.e. quality and quantity. Directly influenced by output indicator 1.1. 1.2 e) research teams are likely to be University departments applying, or other types of organisations (which are not firms). Indicator 1.3: DESCO Buyers Clubs are established / efficient. Note, this indicator will be further developed, pending the outcome of the buyers club concept note.
Achieved
Source
Outreach tracker and CRM
| Output Indicator 1.2 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022)
| Market participation in efficient appliance awards (Global LEAP, including awards, design challenges, innovation prizes) including: a) number of competition designs and test methods b) number of competitions c) number of firms applying d) number of products applying e) number of research teams applying | Planned | None | a) tbc b) 0 c) 0 d) 0 e) 0 | a) tbc b) 2 c) 15 d) 40 e) 15 | a) tbc b) 4 c) 15+ d) 40+ e) 20 | a) tbc b) 4 c) 15+ d) 40+ e) 25 | a) tbc b) 4 c) 45 d) 70 e) 30
Achieved
Source
Efficiency for Access Website
| Output Indicator 1.3 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022)
| Buyer's clubs, including: a) number of stakeholders consulted to develop concept note for a buyer's club b) Buyers' club concept note submitted c) tbc if Buyers Club goes ahead. | Planned |  | a) 15 b) 1 | a) 15 b) 1 | a) 15 b) 1 | a) 15 b) 1 | a) 15 b) 1
Achieved
IMPACT WEIGHTING (%) |  | Source | [6 empty] | RISK RATING
6% |  | Outreach tracker; Inception Report | [6 empty] | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
| 1m |  |  | 2.9m | 3.9m |  |  | 25.6%
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022) | Assumptions
LEIA Appliance Product Testing & Quality Assurance | Product testing, including: a) number of markets/countries and LEIA product categories surveyed b) LEIA products tested (category split tbc), data consolidated and released. | Planned | None | a) 6 markets / 3 products b) 60 | a) 7 markets / 4 products b) 100 | a) 8 markets / 5 products b) 180 | a) 9 markets / 5 products b) 220 | a) 10 markets / 6 products b) 250 | Output indicator 2.1: Initial products focused on TVs, fans, and refrigerators. Market scoping focused in 6 markets -- Kenya, Tanzania, Uganda, India, Pakistan, and Sierra Leone. Product testing activities are dependent on availability of products coming to the market. Output indicator 2.2: Quality assurance framework, defined as setting up a process for sampling, testing, certification, and communicating the results. LEIA program will align the product priorities with EforA Coalition members, such as Lighting Global. Initial appliance category focus is on TVs and fans, followed by SWP, refrigeration, and potentially one other productive use to be defined. Market support activities are defined as financing/ procurement programs (e.g. RBF), business support services (e.g. IFC country business development service for distributors), etc. Quality assurance frameworks development is influenced by interest / appropriateness of target markets to use them. Output indicator 2.3: A capacity building and technical support is defined as training provided to test labs to use off-grid appliance test methods, templates, and trouble-shooting technical issues come up during testing. Support for test labs and methods is dependent interest/ capacity from labs and target users of methods. Output indicator 2.4: Stakeholders are defined as companies, partner organizations (e.g. Energy Access Practitioner Network, GOGLA, renewable associations, etc.), academia whom LEIA program conduct outreach to for promoting the Data Platform. Engagement is defined as direct outreach via emails, phone calls, meetings, events, and webinars to generate interest and raise awareness about the Data Platform.
Achieved
Source
Surveys documentation, data platform
| Output Indicator 2.2 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022)
| Quality assurance frameworks, including: a) number of stakeholders consulted to scope and design QA frameworks for appliances b) number of appliance categories for which quality assurance frameworks are developed to inform market support activities | Planned | None | a) 10 b) 0 | a) 15 b) 1 | a) 20 b) 2 | a) 25 b) 3 | a) 30 b) 3
Achieved
Source
CRM, stakeholders consultation documentation
| Output Indicator 2.3 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022)
| Testing, including: a) number of test laboratories and facilities that received capacity building and technical support on LEIA product testing b) test methods defined for Solar Water Pumps and two additional LEIA product/technology categories | Planned | 0 | a) 4 b) 0 | a) 5 b) 1 | a) 5 b) 2 | a) 6 b) 3 | a) 6 b) 3
Achieved
Source
Quarterly Report; Test methods published
| Output Indicator 2.4 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022)
| Number of stakeholders engaged to promote the use of the test data and the platform | Planned | 0 | 30 | 50 | 60 | 70 | 80
Achieved
IMPACT WEIGHTING (%) |  | Source | [6 empty] | RISK RATING
22% |  | CRM | [6 empty] | Low/Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
| 4m |  |  | 8m | 12m |  |  | 33%
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022) | Assumptions
Marketplace Education, Comms & Coordination | EforA and coordination, including: a) number of EforA coalition meetings/ calls conducted b) number of EforA coalition donor roundtable partners c) number of joint activities between coalition partners promoted d) number of countries/ regions and appliances/ technologies that Coalition members focus on (with relevance to efficient appliances for energy access) | Planned | 0 | a) 4 calls/meetings b) 8 members c) 5 d) 15 appliances (8 LEIA priorities; and 25 countries with all major regions covered) | a) 8 calls/ meetings b) 10 members c) 10 d) 15+ appliances, 25+ countries | a) 12 calls/ meetings b) 12 members c) 15 d) 15+ appliances, 25+ countries | a) 16 calls/ meetings b) 14 members c) 20 d) 15+ appliances, 25+ countries | a) 20 calls/ meetings b) 15+ members c) 25+ d) 20+ appliances, 30+ countries | Output indicator 3.1: b) EforA Coalition ecosystem consists of the following: Donor Roundtable Members/Partners, with decision making and co-funding power; Program Partners, with collaborations/ implementation but no funding power; and Industry Partners. Here we refer only to Donor Roundtable Partners. 'Indicator. c) 'Joint activities' may not represent necessarily co-funding. Collaboration between two coalition partners on a project by sharing knowledge and insights and/or co-writing reports will count for this indicator. Output indicator 3.2: a) For country specific campaigns, Initial campaign strategy developed for one 'low hanging' and one 'challenge' country by milestone 4. Priority themes are currently agricultural technology, productive uses, health, cooling, gender differentials & mainstreaming, and disability inclusion, and may be subject to revision in future years per industry needs. c) The team will explore viability and value-add of an additional social media channel in 2019, with relevant metrics added for future years. d) Visits are disaggregated as unique: average 20 per month and repeat visits: average 50 per month each year Output indicator 3.3: a) A policy primer is defined as short, comprehensive good practice updates/summaries on specific policy topics. This will synthesise data and information from other programmatic outputs that are most relevant to policymakers. b) The findings of the policy makers may be disseminated in workshops, webinars, or through organizations more directly involved in policy advocacy (e.g. GOGLA, AMDA). Output indicator 3.4: Evaluation reports are planned to be undertaken before August 2019 and August 2021.
Achieved
Source
EforA coalition calls, bilateral interviews, and partner activities matrix development with yearly updates
| Output Indicator 3.2 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022)
| External communications, including: a) market stakeholder communication campaigns (focused on countries and/or priority themes) conducted b) Number of newsletters published, with consistent subscriber growth and above average open & click through rates c) social media engagement, with growing number of Twitter followers, an increased engagement rate and steady impressions, and exploring feasibility of another social media channel (i.e. Instagram or LinkedIn) d) Growing website traffic following the launch of phases 2 & 3 of the EforA website, with consistent unique and repeat visits, and average time spent on a page | Planned | a) 0 b) 0 c) <100 twitter followers d) 0 | a) 0 b) 2 issues, 1500 subscribers, open rate >20%, click through rate >7% c) 400 Twitter followers, average of 12K impressions per month, engagement rate of 1% d) 0 (website not launched until Sept 2018) | a) 2 priority theme campaigns b) 6 newsletters total, 1750 total subscribers, open rate above 20%, click through rate above 7% c) 500 total Twitter followers, average of 20K impressions per month, engagement rate of 1% d) 1000 visits total, time spent on a page 1-2 minutes on average | a) 1 priority theme campaign + 1 "low-hanging" country campaign (4 total) b) 10 newsletters total, 2000 total subscribers, open rate > 20%, click through rate > 7% c) 600 total Twitter followers, average of 25K impressions per month, engagement rate of 2% d) 1500 visits total, time spent on a page 1-2 minutes on average | a) 1 priority theme campaign + 1 "challenge" country campaign (6 total) b) 14 newsletters total, 2500 total subscribers, open rate > 20%, click through rate > 7% c) 700 total Twitter followers, average of 30K impressions per month, engagement rate of 2% d) 2000 visits total, time spent on a page 1-2 minutes on average | a) 2 priority theme campaigns, total of 6 priority theme campaigns and 2 country campaigns b) 20+ newsletters total, 3000+ total subscribers, open rate > 20%, click through rate > 7% c) 750+ Twitter followers total, average of 40K+ impressions per month, engagement rate 2-3% d) 2500+ visits total, time spent on a page 1-2 minutes on average
Achieved
Source
Zoho Campaigns newsletter analytics, Twitter analytics, Google analytics
| Output Indicator 3.3 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022)
| Policy briefs: a) Number of briefs that provide policy relevant data analysis. These will be published and we will work with partners to disseminate to relevant policymakers. b) Number of countries/regional associations in which findings from policy briefs are disseminated to policymakers, standards bodies, and other relevant stakeholders. | Planned | a) 0 b) 0 | a) 0 b) 0 | a) 2 b) 4 | a) 3 b) 10 | a) 5 b) 15 | a) 7 b) 20
Achieved
Source
Quarterly Reports (reporting published briefs)
| Output Indicator 3.4 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022)
| Number of independent evaluation reports, assessing programme contribution to outcomes and impacts, generating learnings for future improvement. | Planned | 0 | 0 | 1 | 1 | 2 | 2
Achieved
IMPACT WEIGHTING (%) |  | Source | [6 empty] | RISK RATING
11% |  | Quarterly Reports (reporting published briefs) | [6 empty] | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
| 2m |  |  | 10.4m | 12.4m |  |  | 16%
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022) | Assumptions
Market Intelligence & Technology Road Mapping | Industry roundtables, including: a) hold industry roundtables to inform research agenda and R&D road mapping b) number of organizations that attend industry roundtables | Planned | None | a) 2 b) 30 | a) 2 b) 30 | a) 4 b) 60 | a) 4 b) 60 | a) 4 b) 60 | Report outputs are peer reviewed prior to release. Output indicator 4.1: Industry roundtables are organized for priority LEIA technologies to uncover and identify the challenges and opportunities facing these markets. These priorities then inform the broader research agenda and provide a group of stakeholders that can be utilized to vet assumptions and steer programmatic work. Output indicator 4.2: Little data is publically available on the needs and preferences of potential and existing LEIA technology consumers. When possible the research will focus on consumer in DFID priority countries and will be done in close consultation to industry partners to ensure that outputs are useful and research methods are replicable. Output indicator 4.3: For milestone 1 a report will be published that synthesizes results to date from market surveys and testing, this will be augmented by additional desk research. For the milestones that follow, LEIA will collaborate with partners (e.g. Lighting Global and GOGLA) to develop global market trends reports that look at both household and productive use technologies. We anticipate to also publish shorter market snapshot/insight reports for single technologies and priority countries. The publication timeline and strategy for these reports will be developed early in year 2. Output indicator 4.4: The first R&D roadmaps that will be published are for solar water pumps, refrigerators, and interoperability. The roadmaps in later years will focus on horizon technologies. The development of a useful roadmap is dependent on participation and buy-in of market players. It is envisioned that industry will be willing to participate because the roadmaps will identify focus areas for R&D investments. Output indicator 4.5: The first year of the program will focus on collecting data to develop a baseline for impacts and then these impacts will be measured in years 2-5. These research findings will inform the broader market and coalition members, but also be used in tracking programmatic outcomes and impacts. Whenever possible impacts will be disaggregated by gender and will look at impacts on marginalised populations, including the disabled and children.
Achieved
Source
RSVPs and attendee lists
| Output Indicator 4.2 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022)
| Peer reviewed reports published covering new areas of Consumer Research on LEIA appliance use and preferences in Low Income Countries a) number of consumer research projects initiated b) number of consumer research projects completed and reports published | Planned | None | a) 1 | a) 3 b) 1 | a) 4 b) 3 | a) 5 b)4 | a) 5 b) 5
Achieved
Source
Efficiency for Access Website
| Output Indicator 4.3 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022)
| Publish market trends reports for LEIA appliances | Planned | None | 1 | 2 | 3 | 4 | 5
Achieved
Source
Efficiency for Access Website
| Output Indicator 4.4 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022)
| Publish R&D roadmaps for LEIA technologies 1) Hold technical working group meetings to draft roadmap 2) Publish roadmap | Planned |  | 1) 2 b) 0 | a) 10 b) 3 | a) 14 b) 4 | a) 16 b) 5 | 5
Achieved
Efficiency for Access Website
| Output Indicator 4.5 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022)
| Peer reviewed reports published that measure the impacts (e.g. socioeconomic, inclusivity, gender mainstreaming) from LEIA appliances. a) number of research projects initiated b) number of research projects completed and reports published. | Planned |  | a) 1 b) 0 | a) 3 b) 2 | a) 4 b) 3 | a) 4 b) 4 | a) 4 b) 4
Achieved
IMPACT WEIGHTING (%) |  | Source | [6 empty] | RISK RATING
28% |  | Efficiency for Access Website | [6 empty] | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
| 5m |  |  | 10.4m | 15.4m |  |  | 32%
INPUTS (HR) | DFID (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022) | Assumptions
R&D Partnerships & Co-Investment | a) Terms of reference for future/ongoing RD&D partnerships drafted b) Initial draft of the R&D partnerships and co-investment strategy submitted | Planned | None | a) 1 b) 1 | a) 1 b) 1 | a) 1 b) 1 | a) 1 b) 1 | a) 1 b) 1 | Strategy on R&D partnerships and co-investment to be put in place by September 2018, which will inform setting of milestones and targets for indicators 5.1 and 5.2. M&E to also include qualitative exploration with R&D partners and co-investors to help inform outcomes and impacts.
Achieved
Source
Quarterly Report
| Output Indicator 5.2 |  | Baseline | Milestone 1 (Aug 2018) | Milestone 2 (Aug 2019) | Milestone 3 (Aug 2020) | Milestone 4 (Aug 2021) | Target (2022)
| Firms and technologies supported, including: a) number of LEIA horizon technologies supported through open call b) number of Innovative firms supported c) new LEIA partnerships stimulated/ supported though open call d) new LEIA strategic partnerships stimulated/ supported directly | Planned |  | a) 0 b) 0 c) 0 d) 0 | a) 2 b) tbc in year 2 c) 1 d) 1 | a) 4 b) tbc in year 2 c) 2 d) 2 | a) 6 b) tbc in year 2 c) 3 d) 3 | a) 8 b) tbc in year 2 c) 3 d) 4
Achieved
IMPACT WEIGHTING (%) |  | Source | [6 empty] | RISK RATING
33% |  | Quarterly Report | [6 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) |  |  | DFID SHARE (%)
| 6m |  | 0 | 0 | 6m |  |  | 100%
INPUTS (HR) | DFID (FTEs)

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
DFID’s Approach to Value for Money (Smart Guide) provides further advice on ensuring VfM.