Annual Review – Summary Sheet
Title: Forest Governance Markets and Climate (FGMC)
Programme Value £ for full 10 year life: £250 million		Review Date: July 2018 (due date 10 August 2018)
Programme Code: 201724	Start Date: / August 2011	End Date: / August 2021

Summary of Programme Performance
Year	2012	2013	2014	2015	2016	2017	2018
Programme Score	A	A	A	A	A+	A	A
Risk Rating	M	M	M	M	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-201724/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-201724/documents

A. Summary and Overview (1-2 pages)
ACRONYMS USED IN THIS REVIEW
EFI	European Forest Institute an international organisation that hosts a multi-donor TA facility for developing countries
EUTR	EU Timber Regulation that requires due diligence in supply chains
FGMC	Forest Governance Markets and Climate programme
FLEGT	Forest Law Enforcement Governance and Trade (as used throughout refers to EU and Member State policy)
ICF KPI	International Climate Finance, Key Performance Indicator
NDC	Nationally Determined Contributions to Climate Change Agreement (National Plans)
PMST	Programme Management Support Team supporting FGMC and supplied under contract by KPMG
REDD+	Reduced Emissions from forest Degradation and Deforestation
VPA	Voluntary Partnership Agreement: bilateral trade treaty between EU and timber producing country

Description of programme (1/2 page)
FGMC supports reform of the global timber market to: tackle illegal logging; promote legal timber trade; support community engagement in management of and benefit from forest resources; and broadly promote policies, incentives and business standards that protect livelihoods linked to the forest sector; thereby promoting growth and reducing deforestation.
FGMC is based on the premise that transparent and accountable forest management is essential to stop deforestation and promote sustainable growth. It is designed to work with demand and supply side measures, influencing consumer markets and supporting producer countries to improve forest governance. It follows principles agreed through the European Union (EU)’s Forest Law Enforcement Governance and Trade Action Plan (FLEGT). The FLEGT aims to close EU markets to illegal trade and assist developing countries to comply with the requirements for legal and sustainable timber trade. This in turn enables them to develop exports for EU and other international markets.
In line with the FLEGT, 16 countries have engaged with the EU to form Voluntary Partnership Agreements (VPA): a legally-binding trade treaty that secures market access for timber products in the EU, coupled with nationally negotiated reforms to improve governance of the forest sector and combat illegal logging.
Through the FGMC, the UK leads support to 6 VPA countries (Indonesia, Ghana, Guyana, Liberia, Republic of Congo and Burma) to assist the forest sector reform process. In addition, FGMC supports the European Forest Institute’s FLEGT Facility, FAO’s FLEGT programme and international civil society organisations (CSOs) supporting reforms.
The UK plans to transfer the FLEGT approach to UK law and policy after leaving the EU in 2019. FGMC is well positioned to support this transition.
FGMC works at the international level to shift global norms: providing dedicated support to help China review its role as market and investor, providing evidence to help develop strategies that halt illegal timber imports and to foster responsible business standards. It applies lessons from working with the timber trade to other commodity supply chains. The map above illustrates FGMC’s footprint.
This programme plays a significant role in shaping and delivering HMG’s aims and objectives around forests and climate change. It supports and informs the development of environment and trade policy in the context of the UK leaving the EU and is responding to HMG commitments to address both illegal timber and illegal wildlife trade. UK leadership on this issue has shaped the agenda internationally, within the EU and domestically.
FGMC deploys a variety of delivery mechanisms, organisations and service providers (see Annex1).

Summary supporting narrative for the overall score in this review
FGMC is as a 10 year programme executed in phases. The year in review ends the second phase. FGMC delivered good progress with most milestones being achieved or exceeded. Highlights include:

Strengthened public policies and business practices to tackle illegal timber trade. Strong progress on policy and legal reform in a number of key producer countries
- In Indonesia, FGMC has enabled strong national stakeholder engagement leading to remarkable transformation in forest sector reform. Thanks to this, the country has just completed its first year of export licensing of forest products worth £1.3bn, whilst expanding the focus of legal regulation from a limited number of timber products for export to the EU, to certification for 194 types of forest product with combined value of nearly £23 billion for export across 195 countries.
- Indonesia’s progress encourages others: Ghana is close to licensing its timber products, with progress in this direction across other partner countries such as Republic of Congo, Guyana and Vietnam over the current AR period.
- Narrative reports point to significant improvements in the business environment for the private sector, through reduced transaction costs and risks, clear legal obligations and the creation of transparent and efficient licensing procedures that FGMC interventions have helped to support[1].
  [1] Evidence from the UK timber trade field missions, from FGMC Facilitators and EFI experts Annex: FGMC Partners and Instruments operating during the Annual Review period #	Organisation Name	Countries & Arenas	End date of current agreement Facilities (MOUs) 1	European Forest Institute FLEGT and REDD Facility	Global	December 2019 2	FAO FLEGT Programme	Global	December 2018 3	Ghana Forestry Commission	Ghana	September 2018 Delegated Cooperation (MOUs) 1	Agence Française de Développement : DFID’s contributes through AFD	ROC	December 2018 2	EU contributes through DFID for joint VPA support	Liberia	October 2018 3	Norway (NORAD) contributes through DFID for joint VPA support)	Guyana	January 2018 Service Contracts 1	DAI : VPA Support Unit: capacity building all actors	Liberia	September 2018 2	SGS : establishing Legality Verification Dept and control system	Liberia	October 2018 3	Coffey Intl : Africa Facilitation Services	Ghana, Liberia, CdI, ROC, DRC	December 2017 4	Coffey Intl: Guyana Facilitation –stakeholder support fund	Guyana	January 2018 5	Palladium: Facilitation; TA and stakeholder support fund	Burma/Myanmar	May 2019 6	LTS Intl/OPM : Multi-stakeholder Forest Programme , phase 3	Indonesia	February 2018 7	LTS Intl: InFIT, overseas investor guidelines, market measures	China, Global	March 2018 8	ITAD & Tripleline : Independent Review and MTR	Global	December 2017 9	Ecometrica: Forest hectares KPI monitoring methods	Global	September 2018 10	KPMG, Programme Management Support Team (PMST)	Global	April 2021 11	AECOM: Solar Power supply and IT procurement	Ghana	December 2018 12	IPA procurement for SGS related equipment)	Liberia	October 2018 13	Palladium : Multi-stakeholder Forest Programme , phase 4	Indonesia	August 2021 Accountable Grants 1	Instituto BVRio	Ghana, Liberia, Cameroon, CdI, Brazil, UK, EU, China	March 2018 2	ClientEarth	Ghana, Liberia, ROC, Gabon, CdI, Global	March 2018 3	Chatham House	UK, China, Global	March 2018 4	Environmental Investigation Agency (EIA)	Burma/Myanmar, Indonesia, Global	March 2018 5	Fern	Ghana, Liberia, Cameroon, Global	March 2018 6	Forest Peoples Programme	Guyana, Indonesia, Cameroon, DRC, Global	March 2018 7	Forest Trends	Burma/Myanmar, Vietnam, China, Global	March 2018 8	Global Canopy Programme (GCP)	Global	March 2018 9	Global Witness	Global	December 2017 10	International Alert	Burma/Myanmar	March 2018 11	Intl Institute for Environment and Development (IIED)	Cameroon, DRC, China, Global	March 2018 12	NEPCon (Nature Economy and People Connected)	Global	March 2018 13	Proforest Initiative	Ghana, Liberia, Cameroon, CdI, Global	March 2018 14	Rainforest Action Network (RAN)	Indonesia, Global	March 2018 15a	Rainforest Foundation UK – Mapping	DRC, Cameroon, Congo Basin	March 2018 15B	Rainforest Foundation UK – Monitoring	Ghana, Cameroon, DRC, Global	March 2018 16	Rights & Resources Initiative (RRI)	Global	March 2018 17	Traffic International	Cameroon, China	March 2018 18	UK Timber Trade Federation (UKTTF)	Ghana, Cameroon, UK, Global	March 2018 19	Well Grounded	Cameroon, DRC, ROC	March 2018 20	World Resources Institute (WRI)	Global	March 2018
Good progress has also been made toward shifting demand in consumer countries
- In China, a critical market, FGMC partners produced tools and evidence to document the impact of Chinese investments on forests. This has influenced policy. In 2017 China publicly committed to a regulatory approach to addressing illegal timber trade.
- More broadly, FGMC has supported development and testing of a system to verify the legality of imports; development of a global standard for sustainable natural rubber, and the development of country guidelines for responsible investment in the forest sector in Cameroon, Guyana and Gabon.
- In November, the UK prosecutor brought the first action against a UK company importing timber from Cameroon with insufficient evidence of legality which sent an important signal to UK business and demonstrated the “teeth” of UK action under EUTR.

Improved mechanisms for forest governance. FGMC is supporting significant improvements in:
- Accountability: with progress to establish auditing mechanisms to verify compliance with new export legislation across most partner countries.
- Transparency: with progress in all focus countries to establish the laws, information management and data sharing systems needed to ensure transparency in the timber trade and related tax collection; most notably in Indonesia, Vietnam, Ghana and Liberia.
- Rights: strengthening land and forest rights for forest dependent communities and indigenous peoples across a number of countries, e.g. security community rights over customary forests in Indonesia and Amerindian land rights in Guyana.
Gender and inclusion: FGMC has enabled women and marginalised groups to influence policy making and FGMC partner Fern is building evidence to support inclusive legal reform processes.

Increased knowledge and momentum to inform international policy processes and shift global business norms. In this review period FGMC partners continued to:
- Contribute to a global evidence base informing international and regional forest policy, notably in the Congo Basin and East Asia.
- Inform research into EU policy options to address deforestation.
- Support law enforcement around legal timber trade.
- Provide guidance to protect women’s and community land rights.

Coherence with other global processes to safeguard forests and combat deforestation. FGMC partners have produced tools and evidence that help document the impact on forests of global investments in commodities. Innovative platforms such as the Forest 500 index developed by the Global Canopy Project, or the Rainforest Action Network’s forestsandfinance.org, have evidenced the risks of deforestation and help build pressure on investors and businesses to understand their supply chains and promote the sustainable use of forest resources. For instance:
- Illegal Deforestation Monitor’ website - www.bad-ag.info developed by Fern has received growing attention and interest from key stakeholders. The Norwegian state pension fund decided to divest from JBS based on investigation showing “an unacceptable risk” that a company is “contributing to or is itself responsible for gross corruption”.
- The Forest 500 tool enables companies to be screened for weak deforestation policies; and has now been improved to identify financial institutions providing loans or investments to those companies.
- With FGMC support, Chatham House and World Resources Institute launched new tools to support transparency and traceability across commodity supply chains.

Recommendations for the year ahead
1. Timely procurement of key service contracts for the final years of the programme to pre-empt operational risks.
2. The PMST and FGMC team should further develop tools to measure, report and disseminate FGMC impact, as well as demonstrating its contribution to meeting Key Performance indicators (KPIs) of International Climate Finance (ICF).
3. FGMC team / PMST should propose a strategy for addressing displacement in the trade of illegally produced timber. Evidence suggests that within regulated markets there is increasing compliance with legal standards for timber trade. However, illegal timber continues to be traded globally, and is increasingly going to markets with little or no import controls (such as India, Nigeria).
4. PMST and DFID communications experts should work to effectively package key lessons from the programme and disseminate these across DFID and the wider development community.
5. The FGMC team should adapt the programme focus as needed to support the development of new HMG policy and partnerships in preparation for the UK departing from the EU.
6. FGMC engagement in Burma should be reviewed in light of the current political context.
B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Legal, legitimate and credible mechanisms of forest sector governance and management are in place in producer countries
Output number per LF		1	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s)	Progress
1.1 Inclusive public policy: / No. of countries with deliberative multi-stakeholder decision making with adequate incentives and capacity to engage effectively	Mechanisms functioning in 6 focal countries: Ghana, Liberia, ROC, Guyana, Indonesia, Burma. / Progress in 10 further countries	A: Significant positive change scored in 5 out of 6 focal countries; positive change reported for 8 of the 10 other VPA countries.
1.2 Effective facilitation of VPA processes / Brokering dialogue and a constructive dynamic between stakeholder interests.	Sustained in focal countries : Indonesia, Ghana, Liberia, ROC, / Guyana , Burma, as well as DRC and Cote d’Ivoire	A+: Excellent results in all 8 countries.
1.3 Progress in the design, development and full operation of a Legality Assurance System (LAS)[1]	Key milestones (reflecting country specific status): design; develop; / test; roll-out; operate; licensing[2] of reformed systems	A: Excellent progress in Indonesia and Ghana reflecting significant sector transformation; / Progress is on track in 8 /11 other countries building a LAS.
1.4 Progress in monitoring and transparency mechanisms / Country specific commitments on transparency cover 3 aspects: (a) legal compliance and forest crime; (b) public information; (c) impacts.	By country, key milestone for transparency and monitoring efforts: designed, piloted; tested; operational [3]	A: Monitoring and information sharing advanced in all 6 focal countries
[1] The LAS put governance reforms into practice, introducing clarity to requirements, systematic application of controls and independent scrutiny or audits in supply chains
[2] Country specific milestones are captured in annual VPA workplans, the FGMC country specific Theory of Change and logframe. Key expectation highlighted here. The PMST Annual Progress Report captures results too detailed to report here
[3] Country specific milestones are captured in annual VPA workplans, the FGMC Theory of Change and logframe. Key expectations highlighted here. The PMST Annual Progress Report captures results, including from CSO grants, too detailed to report here

Provide supporting narrative for the score
FGMC actions under this output are guided by each country specific Theory of Change and priorities established by stakeholders engaged with country specific Voluntary Partnership Agreements in annual work-plans. The indicators record progress across a range of countries.

  1. Inclusive public policy: FGMC supports national stakeholders to contribute to policy making and resolve contested issues around forest governance. This requires a national platform and political space, informed and organised stakeholder positions and capacity to engage effectively. Progress has been varied across contexts; with good progress in 5 out of 6 focus countries. In Guyana, FGMC support to stakeholder consultations was crucial to addressing Amerindian rights claims. In Liberia, FGMC support to a multi-stakeholder Forum and community engagement secured strong and coherent policy messages, convincing a sceptical new administration to move ahead with forest sector reforms. However, progress slowed in Burma due to
  2. wider political challenges. In 8 of the 10 other countries engaged in a VPA process, FGMC support is helping to facilitate reforms. VPA processes remain stagnant in Gabon and Malaysia (EFI reports).

1.2 Effective facilitation of VPA processes: Facilitation support helped maintain a dynamic, quality process through significant political change or uncertainty in Liberia, Republic of Congo and Ghana this year. In the Democratic Republic on Congo (DRC), support from the FGMC facilitator helped revive strong local interest in forest governance reforms. Through effective facilitation, FGMC support in the Republic of Congo helped secure interest (and co-finance) of the Ministry of Finance and Planning for a stock taking exercise and installation of a mechanism to monitor legal compliance with timber regulations.
1.3 Progress in design, development and operation of Legality Assurance Systems (LAS): The LAS put governance reforms for legal timber licensing into practice, introducing clear requirements, systematic application of controls and independent scrutiny or audits in supply chains. Expected milestones are defined in country VPA work-plans.

In Indonesia this year 100% of exports to the EU were licensed. Indonesia issued more than 39,000 FLEGT licences for a value of USD 1.3 billion to operators for trade with all 28 EU Member States. Beyond the EU licenses all exports no matter the destination were checked by independent audits of factories and forests: about 23 million ha of forests and 3000 factories. In Ghana, roll-out of the LAS across all forest districts is complete, the system is now operational; a shipment test using ‘mock licences’ destined for the Netherlands, Germany and Spain is completed; 6 audit cycles were completed across the country and with 162 companies. This is yielding efficiency in business processes and greater accountability for community benefit sharing. In Liberia, LAS field testing is completed and the roll-out and transfer of operations is completed in 3 out of 4 Districts, although progress was slower than planned. In Republic of Congo, testing is completed with strong backing from the private sector and significant leadership and co-financing from the Ministry of Finance and World Bank, and roll out has started.

In Guyana, Parliament adopted new forest regulations and new Codes of Practice and Guidelines for Wood Tracking Systems were approved. The development of the LAS is on track building from a robust existing system. In Burma, international market pressure is influencing the Government to revamp controls and transparency. In other VPA countries, there was good progress in meeting annual expectations, except in Cameroon where technical challenges and lack of political steerage continue to hamper progress and in Central African Republic where civil unrest continues.

1.4 Monitoring and transparency: VPAs entail investments in monitoring to improve accountability, benefits, and impact. FGMC supports governments and CSOs to establish the agreed accountability measures. This includes:
(a) Legal compliance: monitoring mechanisms, independent audits and whistleblowing and independent CSO-led monitoring are established.
System wide monitoring is operational in Indonesia, Ghana, Rep.of Congo; being piloted in Liberia and the principles and design agreed in Guyana and Vietnam. CSO-led monitoring of forest operations and the implementation of agreements with communities is operational in Indonesia, Cameroon, DRC and Rep of Congo and piloted in Ghana and Liberia, tracking benefit sharing with communities, social responsibility agreements, community monitoring of forest crime. There was limited progress in Guyana.

(b) Transparency and information sharing mechanisms established to meet international market and local stakeholder demands. FGMC has supported NGO and government efforts to improve transparency. Mechanisms for this have been established in Cameroon, Rep of Congo, Ghana and Indonesia. But in Indonesia, more work is required to improve data management. With extensive inputs from civil society and FGMC partner Client Earth, new legislation in Ghana requires publication of key sector information. The Ghana Forestry Commission is teaming up with NGOs to make legal compliance data available in real-time. Information sharing policies are designed in Guyana, Central Africa Republic, Vietnam and framed in the VPA and they are being tested in Liberia.

(c) Impact monitoring systems have been designed and agreed in Ghana, but implementation is slow.

Lessons identified this year, and recommendations for the year ahead

1. Ensure that country-specific Theory of Change and milestones are updated to reflect priorities of FGMC Phase 3 as well as stakeholder priorities framed by Joint Implementation Committees.
2. Analysis should be commissioned on the relationship between market incentives and shifts in governance, employment and business practices, to better understand impacts and improve FGMC communications on working with market measures to influence governance reform.
3. PMST should support EFI on impact monitoring work.
4. The PMST should work with FGMC partners to identify incentives for different segments of the timber industry to engage in governance reforms and changes to business practices.
5. FGMC should increase communications and lesson sharing across HMG on VPAs and the opportunities post-Brexit to develop new partnerships that promote trade and sustainable development.

Output Title	Public policies and private business standards that tackle trade in illegal timber
Output number per LF		2	Output Score	A+
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicators	Milestone(s)	Progress
2.1 EU Timber Regulation (EUTR) Compliance Understanding by operators, suppliers, and monitoring organisations, third-party certification schemes, and trade federations	EU operator awareness / Consistency in guidance & tools / Market shift towards low risk sourcing. / EU trade federations with relevant purchasing policies.	A+: Achieved (exceeded end programme milestones)
2.2 EUTR Enforcement: Competent Authorities (CA) awareness of EUTR enforcement roles and responsibilities	Reports by CA on EUTR compliance; / Successful enforcement action; / CA enforcement across all EU member states	A+: Achieved (exceeded end programme milestones)
2.3 Market measures in other consumer markets: / other countries, notably China implement measures to reduce trade in illegal timber	Coherence in measures across countries. / Market and investment measures for China / Other consumer countries adopt measures to favour legal timber	A: On track with positive signals from China, particularly its private sector and increased coordination between consumer markets
2.4 Financial institution (FI) policies and practices adapted to mitigate risks of illegality in timber and other commodity supply chains, including forest land conversion rights	FI understand risks in timber supply chains, adopt policies to address these risks. / increased transparency on how FI manage risks of illegality in timber supply chains.	A: on track

Narrative to support the score
FGMC posits that public policies and regulation coupled with private business initiatives can stop illegal timber reaching consumers. This year, there has been significant progress with EUTR implementation as well as further moves from Japan and China towards blocking out illegal timber. Progress with policies and practices of financial institutions has been supported by the newly published EU Action Plan on Sustainable Finance which was heavily informed by FGMC actors. These shifts have been driven by the knowledge and intelligence sharing, new tools, greater coordination between private sector actors as well as between enforcement agencies.

Major consumer countries such as the US and Australia use similar regulatory approaches to the EU, although without the link to licensing. However, other important markets such as China, Japan and Korea are less stringent. FGMC seeks, through international dialogue and policy engagement to promote new and stronger regulations in partner countries, and to coordinate and align enforcement efforts.

2.1 EU Timber Regulation (EUTR) Compliance: Due diligence practices have improved with support from FGMC partners and grantees, and there is evidence that EUTR is influencing sourcing and purchasing policies:
- FGMC partners and grantees have improved understanding and due diligence practices to exclude illegal products from supply chains across the EU and beyond, through: new tools for business; coordination; country specific information and data on supply chain risks.
- Industry developed tools supported by FGMC with Nepcon and World Resources Institute help inform company due diligence and risk management, while the responsible trading platform established by BVRio has greatly exceeded expectations with exchanges of nearly 20 million m3 of timber product sales that meet all due diligence requirements.
- There is a sense amongst traders that EUTR is starting to bite, and is influencing sourcing of importers and exporters in the EU. Businesses and trade associations are improving purchasing policies and investing in greater intelligence gathering.

2.2 EUTR Enforcement: Enforcement has been demonstrated in all 28 EU countries, with appropriate enforcement and legal actions taken where concerns have been raised
- European Commission’s scoreboard indicates enforcement across all 28 EU countries (with necessary legislation, authorities and monitoring checks in place). Concerns raised by FGMC partners over unequal penalty regimes and inadequate enforcement have yielded EC and country action (in Belgium and Slovakia).
- Landmark court cases informed by substantiated concerns from a number of FGMC’s grantees are contributing to shift business sourcing along the entire supply chain.
- Enforcement action in Italy, UK, Germany, NL, Denmark and Sweden has drawn from intelligence and investigations of FGMC actors; success of the first UK enforcement case.
- Forest Trends fosters more harmonised implementation of market regulations globally and improves enforcement capacity.

2.3 Market measures in other consumer markets: Other consumer markets, notably China and Japan, have been actively working with FGMC to improve investment guidelines, sourcing policies, and legality verification systems:
- Guidance for Chinese businesses on supply chains in developing countries (notably for Cameroon, Gabon, Guyana): investment guidelines for timber, rubber, palm oil completed and adopted by Chinese trade associations. Rubber guidelines are being actively promoted as a global sustainability standard.
- Chinese Legality Verification system for imports continues to be tested with 10 companies and promoted by their trade federation. China has indicated that it will adopt a regulatory approach to lock out illegal timber imports; currently the policies drafted for this purpose are promoted as voluntary measures.
- Information sharing with importer associations, exporters, investors, banks and Customs is encouraging businesses to focus on risks of illegality in supply chains.
- Other consumer markets have adopted measures to stop trade in illegal timber, e.g. those of US, Switzerland and Australia are similar to the EU, while New Zealand, Korea and Japan use a voluntary approach. FGMC partners are working with authorities and NGOs in Japan to share global experience on due diligence standards. Japan has strengthened its sourcing policies for the 2020 Olympics as a result of FGMC information sharing. Across consumer countries, FGMC initiatives are improving coordination between authorities and companies to foster a consistent approach to market checks on legal compliance.

2.4 Financial institution policies and practices adapted: FGMC partners have positively influenced EU financial regulation, and there has been good appetite from investors for the new tools developed to increase investor information on deforestation risks:
- Three complementary approaches are being implemented to promote best practice within Finance Institutions: advocacy, evidence gathering and innovative tools to monitor their commitments.
- FGMC partners, Fern and Rainforest Action Network, have influenced EU financial regulation to encourage banks and investors to take account of deforestation and social risks, notably in the new EU Sustainable Finance Action Plan (March 2018); an exciting development to hold investors to account on environmental impacts.
- New tools are developed to inform Finance Institutions on risks. A Rainforest Action Network platform reveals the links to tropical forest loss in SE Asia and targets investors in the EU, Japan and Indonesia. As a result they report shifts in risk assessment and policies of banks. However, Global Canopy Programme report disappointing results in their efforts to secure their public commitments, but the Forest Disclosure programme continues to attract investors (656 investors with USD 87 billion) who are keen to learn how to better identify risks in their portfolio and act to mitigate them.

Lessons identified this year, and recommendations for the year ahead

1. PMST should commission work alongside research and analysis of FGMC grantees, to deepen understanding of the “proof of concept” of FLEGT i.e. that market levers are influencing governance reforms and changes to business practices that safeguard forests.
2. PMST should invest time and resources to sustain our engagement with China in advance of DFID securing a new contract to advance UK-China partnership on forests and international trade.
3. PMST working with DFID and the FCO to update the FGMC engagement strategy with China based on recent government changes that impact decision making for a national regulation on timber imports and furthering UK-China partnership on sustainable trade of timber and other commodities. The possible role of the newly established Chinese cooperation agency should be considered.

Output Title	Increased knowledge and momentum for change
Output number per LF		3	Output Score	A+
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator	Milestone(s)	Progress
3.1 Availability and effective use of evidence on governance, market and tenure reform	Evidence is relevant and accessible	A+: Exceeded expectations with evidence leading to significant policy change. / FGMC Products Report shows scale & scope of new evidence
3.2 Size, diversity and influence of communities of practice	Increase in size and diversity of community of practice	A+: Significant growth in communities of practice influencing policy and business norms
3.3 Communication and engagement to sustain political momentum globally.	Increase in effectiveness of communication and engagement with influential political decision-makers	A: On track and yielding policy results

Provide supporting narrative for the score
To sustain momentum for change, FGMC links communities of practice from national to regional and global. It is ideas, knowledge and people that bridge the political arenas, allowing adaptation to changing markets, and building international pressure for change. This has supported the shift of attention solely from the European market to encompass other major consumers, Australia and the USA, together with fuelling emerging interests from China, Korea and Japan. The Communities of Practice amplify results and link them into different policy arenas creating increased momentum for change. FGMC results are a consequence of the effectiveness of networking, capacity building and evidence used to influence and advocate for change. With the transition from phase 2 of the FGMC programme, 2017 has seen a consolidation of stock taking and lesson learning that helped to shape the focus of Phase 3 as well as influencing the shape of future EU action.
Amongst other platforms, with FGMC support EFI has created a one-stop information centre (FLEGT.org) where members can access and share news, research, training materials and many other resources. The PMST has established a FGMC page on this portal to facilitate coordination and lesson learning.
3.1 Availability and effective use of evidence: Innovative forest and land-use monitoring tools developed by FGMC partners are contributing to a global evidence base on: governance, tenure, gender, livelihoods, forest cover, forest crime, investment policies, commodity trade and supply chains, illegal deforestation:
- World Resources Institute’s Global Forest Watch tracks tree cover loss on a daily basis that is widely used to inform international policy-making and investment decisions of international organisations and provides 16 governments with core data on the state of their forests.
- Rights and Resources Institute’s land tenure research has informed international companies on community-to-company land negotiations and findings on indigenous and rural women’s rights and is informing the integration of gender-sensitive protection for women in legal frameworks (includes information on 59 countries).
- Forest Trends analysis of Chinese trade flows informed decision making in China.
- FGMC partners continue to investigate and expose bad practice and crime that in turn creates the evidence and momentum for change. Examples this year include investigations by Global Witness in Papua New Guinea that resulted in changes in sourcing practiced by US and Chinese supply chains; investigations on the illegal trade between Vietnam and Cambodia (Environmental Investigation Agency) resulted in policy change in Vietnam; Fern’s investigations of illegal deforestation shifted Norwegian Pension Fund investment decisions; investigations by Rainforest Action Network informed Indonesia’s finance and investment policies and anti-corruption work.

3.2 Size, diversity and influence of communities of practice; Significant developments in establishing new local and global communities of practice, including practitioners, experts, policymakers, NGOs, community groups and companies:
- Chatham House convened an annual experts meeting in June 2017, bringing together over 200 experts, practitioners, and policy makers from 42 countries to exchange on results of FLEGT and future policy directions.
- More specific communities of practice formed this year include Fern’s community rights network, Proforest’s ‘Africa Practitioners Network’; Rainforest Foundation’s practice on CSO-led monitoring who are building a standard on independent forest monitoring, a coalition of practitioners on tenure and land titling and FAOs work with private sector trade associations.

3.3 Communication and engagement to sustain political momentum globally; Communities of practice have provided entry points for engagement in various political arena, contributing to policy development:
- The EU NGO Coalition (with significant representation from FGMC actors) significantly contributed to the future direction of EU FLEGT policies contributing evidence to evaluations. The same coalition has been instrumental in engaging with an EU feasibility study on Deforestation.
- In the UK, practitioners from business and NGOs have worked together to advocate for UK’s sustained engagement in FLEGT policies after the UK’s exit from the EU. Research by Chatham House identifies opportunities to integrate sustainability into the UK’s future trade relationships drawing lessons from the FLEGT policy domain.
.
Lessons identified this year, and recommendations for the year ahead linked to this output
1. PMST should work with the contracted Independent Monitor to assess how the wealth of information and networks are influencing transformations on the ground and in global markets.
2. Working with the DFID team the PMST should tailor FGMC learning to inform HMG policy, particularly related to the opportunities of linking future trade, environment and development policy.
3. Building from the FGMC Media Summary, the PMST should integrate this information into the regular programme updates and reporting prepared for DFID.
4. FGMC should invest in developing an approach to measure the overall impact of the momentum created by a community of practice.

Output Title	Coherence with other global processes aiming to safeguard forests and combat deforestation
Output number per LF		4	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s)	Progress
4.1 Policy alignment between international processes promoting responsible forestry and land use: REDD+, FLEGT alignment	Focal country REDD+ programmes integrate governance; FLEGT cross learning in at least 3 countries. / Synergies and cross learning between FLEGT and other processes such as CITES, EITI	A: Good progress with expanding links to other policy domain
4.2 FLEGT practice informing measures to reduce the risk to forests from other commodities	Research and analysis informs trade and investment measures for commodities that may put forests at risk	A: Good progress on influencing demand side policy and business standards, but more attention required to supply side actions
4.3 Business standards, legal compliance and investor behaviour to reduce deforestation	Changes in business standards, compliance of investors in relation to reducing deforestation	A: increased evidence and tools but limited evidence to demonstrate change in business practice and standards

Provide supporting narrative for the score
The threat to forests is not just from illegal logging but, increasingly, from illegal forest clearance. An estimated 49 per cent of total tropical deforestation between 2000 and 2012 was due to illegal conversion for commercial agriculture. These threats are well recognised and addressed through international processes and private sector commitments in various international Fora. However these initiatives need strong sector governance to deliver results on the ground. FGMC promotes national stakeholder-led policy making to address underlying conflicts of interest and to build legitimacy for legal and institutional reform. This year FGMC actors have continued to work with established processes, such as REDD+ and CITES, and are engaging with new processes linked to commodity supply chains.
4.1 Policy alignment between international processes promoting responsible forestry and land use: Effective lesson learning and coordination between initiatives has been established in all FGMC focal countries:
- FGMC has supported lesson sharing between REDD+ and FLEGT communities in DRC, Cote d’Ivoire, Liberia and Vietnam leading to effective coordination. Governance considerations are now integrated into REDD+ strategies in Congo Basin (into World Bank investment strategies and Norway-led policy dialogues).
- The Extractive Industries Initiative (EITI) in Liberia and the Republic of Congo include forest sector revenue drawing from evidence supported by FGMC partners; Burma and Guyana will do so as well.
- FGMC grantees worked with the Convention on International Trade in Endangered Species (CITES) to successfully integrate more of the threatened Hongmu tree species for protection and provided intelligence to assist with follow up enforcement action on the international rosewood trade.
- FGMC actors shared experience on enforcement action with those working on the Illegal Wildlife Trade exploring opportunities for policy synergy.

  1. FLEGT practice informing measures to reduce the risk to forests from other commodities: Growing evidence and tools are informing policy and regulation as well as business practices in consumer countries and in West Africa producers are working to develop strategy to encourage sustainable investments in palm oil and cocoa:
- On the demand side (regulations and policy): substantive advances in the generation of evidence, analysis and guidance are informing policy. This includes development of Chinese rubber commodity guide; analysis of international Human Rights framework relating to land rights integrated into investors guidance; evidence by FGMC partners have informed European Parliament resolutions on commodities and deforestation raising political attention to this domain.
- On the demand side (tools): an exciting number of new tools have been developed to assess the risks posed to forests and for businesses to better understand their forest footprint. Chatham House launched a Resource Trade Database and World Resources Institute launched a new Commodities partnership to increase transparency in commodity supply chains.
- On the supply side, with support from FGMC, six Governments are building from their commitments on sustainable palm oil and considering extension to other commodities such as cocoa. Supported by Proforest, a partnership between small holders and companies is developing new tools to support sustainable production (this work is closely coordinated with DFID’s Partnership for Forests programme.
- However, product-focused advocacy in consumer markets, such as against palm oil, is raising concerns of protectionism in producer countries that may limit, rather than increase, opportunities for FGMC work in focal countries.

4.3 Business standards, legal compliance and investor behaviour to reduce deforestation; An established base of publicly available evidence, convening and inclusive policy making has increased transparency, and the pressure on businesses to source responsibly with a clear understanding of the risks:
- Tools and evidence for business: Rights and Resources Initiative is facilitating a network of business leaders to leverage action to secure community land rights, in 2017 they developed practical guidance for businesses on challenges related to tenure risks.
- Monitoring tools for accountability: the Global Canopy Programme’s Forest 500 is the world’s first rainforest rating agency, ranking the most influential companies, financial institutions, and governments in the race towards a deforestation-free global economy. Increasing numbers of are disclosing forest footprint data.
Lessons identified this year, and recommendations for the year ahead linked to this output
1. FGMC and other donors have supported the development of innovative tools to monitor progress in private sector-led initiatives in addressing deforestation in their supply chains. There is a need to ensure coherence in the demands placed on industry leaders. PMST should encourage a community of practice to test and streamline tools focused on assessing risks and performance.
2. PMST should work with the facilitators in focal countries to identify new opportunities to build links between the governance reforms supported by VPA and other initiatives combatting deforestation, the illegal wildlife trade and with NDCs.
3. PMST should work with FGMC partners to dedicate more attention to work with producer countries on measures to address forest risk commodities, building on work with Proforest in Africa.
4. FGMC should look at investing in opportunities to work with the Illegal Wildlife Trade community to ensure synergies are realised, particularly in the context of the China trade.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

FGMC is based on the assumption that trade and other incentives can drive transformative change in markets, governance, forest management and business practices, and that these changes will bring economic, environmental and social benefits that ultimately promote economic growth, reduce poverty, secure ecological goods and services, and build stronger, fairer and safer societies. The theory of change for the programme is summarised in the figure below:

Key aspects of the programme design include the following considerations, which underpin the broader theory of change:
- Global nature of the programme: The programme is designed to work on both demand-side and supply-side measures, with a presence and influence in producer countries as well as European markets. The multi-level nature of the programme is designed to provide unique opportunities for linking, synergy and coherence and to use field-level evidence to drive and inform international and national policies in a coordinated manner.
- Using trade as a lever for governance and wider development objectives: Trade is an entry point and incentive for triggering in-country forest governance reforms. These governance reforms are essential preconditions for wider objectives of climate change mitigation, sustainable livelihoods and more equitable trade.
- In-country legitimacy: National-level processes are designed to ensure local-level ownership through multi-stakeholder deliberation. Furthermore, support provided by DFID to producer countries is designed to be tailored to local needs, rather than a one-size-fits-all approach.
- Legal basis: The outcomes of in-country deliberation and resolutions are designed to be codified in domestic law and reinforced by consumer-country laws regulating trade in timber and timber products. The programme is further designed to support the continuum of policy development through to implementation.
- Long-term support: The programme builds on earlier work by DFID to improve forest governance, which started in the 1990s, and is framed as a 10-year investment.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead
The programme is on track to meet expected outcomes as indicated by the External Review of Phase 2. However, innovative methods for analysing the impact in markets and governance are required. A number of FGMC partners, such as Chatham House, World Resources Institute and Rights and Resources Initiative will contribute to this analysis. In addition, PMST will contract policy impact monitoring expertise to assist in framing this monitoring.
Explain major changes to the logframe in the past year (1/2 page)
There have been no major changes to the logframe this year. The Business Case addendum that was approved in October 2017 [https://devtracker.dfid.gov.uk/projects/GB-1-201724/documents ] sets out the priority results for the final programme phase and priorities for the coming year.

Describe any planned changes to the logframe as a result of this review (1/2 page)
The logframe will be adjusted to more clearly frame the priorities for the final programme period (2018-21) as set out in the Business Case addendum.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)
The VfM case in the Business Case is based on high level cost benefit analysis for the full 10-year programme, and projected impacts on deforestation and government revenues up to 2035. The economic analysis estimated an extremely high benefit-cost ratio of £38 for every £1 invested in the intervention (38:1), and an internal rate of return (IRR) of 218%. These very high returns reflected estimations of changes in land use especially with regard to oil palm plantations in Indonesia. The massive shifts in land use globally, together with FGMC experience provide the basis to revisit this model based on evidence generated over this period. Other critical assumptions, such as the forest area protected as a result of changes in trade and policy may be lower than in the Business Case, resulting in a lower IRR. A number of studies (Ecometrica and IFPRI) have been commissioned to assess forest impact and changes to global trade and these, together with data gathered by World Resources Institute, Global Forest Watch and the International Tropical Timber Trade Organisation’s independent market monitor will feed into the revised economic analysis. The PMST will update this analysis in FY 2018-19.
The Business Case was also predicated on the assumption that FGMC would result in improved livelihoods for forest dependent people. This is more difficult to assess. Although there are already improvements to legal rights in many countries, this does not necessarily translate into benefits for those, often very poor people, who depend on the sale of forest products for their livelihoods. Country efforts to achieve FLEGT licencing for legal timber include strengthening monitoring systems. This includes analysis of winners and losers from the Legality Assurance Systems developed to strengthen legal compliance. The purpose is to ensure safeguards for local communities; but the information gathered will also provide data for recalculating the cost benefit analysis.
Assessment of whether the programme continues to represent value for money
The programme continues to represent value for money (VfM), both through supporting processes which are having transformative effects on sector governance and international markets, and by providing immediate, tangible demonstrations of VfM at the level of specific project activities and by partner organisations as described under Section B of this review.
FGMC is successfully adapting to meet new challenges and deliver additional results, for example through the current initiative integrating activities tackling the Illegal Wildlife Trade into existing grants.
FGMC delivers important benefits for girls and women. Girls and women in forest-dependent communities are frequently excluded from property rights, rarely own land, or have secure access to forest resources. Discrimination, lack of rights and security, and limited opportunities keep women in a cycle of vulnerability and poverty. FGMC grants help tackle this through reform of tenure and laws. Actions include support to build the capacity of civil society on gender issues, research to better understand the human rights implications of customary law for women, legal action to address violations of the rights of women and girls, and support to encourage inclusive national processes that involve women in policy and legal advocacy work. The PMST has placed renewed focus on gender in the framing of the 2018-21 grants, revised the gender strategy and incorporated it more clearly into the revised reporting templates.[4]
[4] FGMC Gender Strategy and Action Plan (PMST, 2017)
The 2015-2018 grants were all completed by 28 February 2018, with an overall underspend of £148,265 relative to the value of grants awarded (0.4% variance). Areas where efficiencies and economies were achieved in the grants programme included:
- Organisations actively collaborating to make the best use of common resources (e.g. Global Witness and Rainforest Foundation UK sharing forest monitors in DRC) or jointly organising events to maximise impact and audience reach, and economise on venue costs (e.g. Fern, the Environmental Investigation Agency and Client Earth in Republic of Congo).
- Carrying forward learning and training resources from previous projects into current projects, reducing the need for new expenditure (e.g. Client Earth legal analysis and training materials for workshops in Ghana).
- Global Witness and Forest Trends each increased their internal staffing capacity for data analysis, report production and communications work, reducing their reliance on more expensive external consultants.
The five contracts which ended in the past year – MFP3 (Indonesia), Africa VPA Facilitation, InFIT (China), Guyana VPA support and Independent Programme Monitoring – were each successfully completed within or under agreed budgets, primarily due to savings on expenses. The cumulative saving over the full life of these contracts was over £200,000.
In line with the DFID Supplier Review, complete cost transparency is being rolled out in all new contracts and contract amendments issued under the programme. In the recently concluded 2018-21 grants round, managed by the PMST, equivalent rigorous standards in budgeting and cost transparency have been introduced for grant applicants.
The size, breadth and complexity of FGMC necessitate the outsourcing of some of the management functions. Programme management support and independent monitoring accounted for 4.5% of total programme spend in the past year. These services were provided diligently, to a high standard and allowed a more efficient and effective use of DFID staff time.
Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)
As a ten-year programme that remains on track in its 7th year, projected future returns on our investments are high. FLEGT licensing is now a reality for Indonesia, Ghana is very close, and the pace of change in other VPA countries such as Republic of Congo, Guyana and Vietnam has stepped up. Once established and delivering to international markets, FLEGT licenses and the governance that they require will be self-sustaining beyond project completions. Perhaps even more significant is the greatly improving prospect of transformative impact if China effectively regulates its import market. Engagement with China is undertaken primarily to address the risk of leakage of illegal timber flows to less discerning markets, which in turn reduces leverage for reform in those countries with which China trades (and which are the focus of DFID support). The value for money in demand-side measures can be seen from the counterfactual – failure to address these issues would reduce FGMC’s effectiveness significantly. FGMC therefore remains on track to deliver results with major global trade consequences.
Global trade reforms represent both an end and a means. Trade is used as a lever for country level reforms. Results vary from country to country, and require time to ensure that reforms are backed by a social and political legitimacy that is critical to enforce rights, improve management and adopt simpler more transparent legal trading practices. Even in deeply divided countries where licensing will continue to be challenging, reforms continue to emerge from the inclusive decision making processes that have been established. Transformational changes that result from FGMC investments go well beyond forest outcomes and represent significant VfM. For example, in Ghana, the inclusive policy making is informing approaches to link sustainable cocao productions to international markets, in Guyana Forest People’s programme inspired by the VPA process have helped to establish a formal land rights settlement process in South Rununi District with the Ministry of Indigenous People’s Affairs.
FGMC advocates that countries such as Liberia or Guyana, with less capacity, weak governance and poor rule of law should not be excluded from international efforts that leverage trade. Often these countries are important in terms of their forest assets (with high value tropical woods) and may be the target of illegal loggers who capture revenue and subvert community efforts. Although these countries often need significant time and investment to secure reforms, benefits are likely to be significant, especially for poorer people dependent on the forests.
FGMC is playing a critical role in both shaping and delivering HMG’s aims and objectives around forests and climate change. It supports and informs the development of environment and trade policy in light of the UK’s departure from the EU and related sustainability provisions and delivery of the UK’s 25-Year Environment Action Plan; and most recently in responding to HMG commitments to address both illegal timber and illegal wildlife trade. UK’s leadership on this issue has shaped the agenda internationally, within the EU and domestically. It has shaped HMG policy interest in this area of work, particularly in reflecting on strategies as the UK departs from the EU.
FGMC remains relevant to, and aligned with, DFID policy and is providing the practical experience and networks that contribute to wider HMG policy development. In particular FGMC’s experience on working with FLEGT policy and VPAs is helping to guide HMG in the development of equivalent partnerships in preparation for our departure from the EU: the aim is for the UK to move seamlessly to equivalent agreements that mirror the EU/producer country VPA and that would allow UK businesses and authorities to accept FLEGT licenses. The programme aligns well with and supports DFID’s new Economic Development Strategy,[5] the DFID Governance Strategy, the DFID Building Stability Framework and the 2017 World Development Report,[6] which focused specifically on governance, the importance of being “politically smart” and “locally led”, two hallmarks of the FGMC programme”. In the final phase, FGMC has strengthened its focus on transparency in the allocation of new grants and in support of the Transparency and Accountability Agenda.
[5] DFID. 2017. Economic Development Strategy: prosperity, poverty and meeting global challenges. London, UK.
[6] World Bank. 2017. World Development Report 2017: Governance and the Law. Washington, DC: World Bank.

E: RISK (½ to 1 page)
Overall risk rating:  Moderate, but increasing
The programme risk register was updated in June 2018 in line with DFID’s risk management framework and is reviewed quarterly or more frequently if there is a specific change in context or delivery.
Contextual risks are moderate and increasing. Shifts in global demand, such as a reduction in the relative importance of trade to the EU when compared to Asia (as in the case of Cameroon where the importance of the EU as a market share has more than halved over the past 5 years) may reduce the potential leverage of EU related trade measures. As some countries improve controls within their own forests, this may displace illegality to neighbouring countries or increase “laundering” across borders. Of particular concern are Vietnam and its neighbours in the Mekong (as exposed in the recent Environmental Investigation Report report), Ghana and neighbours in West Africa and the Congo Basin to Asia. To mitigate these risks we work through FGMC partners to encourage regional cooperation in intelligence sharing and independent monitoring.
In specific focal countries, risks relate to national politics or insecurity as is the case in Liberia, DRC and Burma. These challenges are addressed at the programme level by supporting a range of pro-reform partners from civil society, the private sector and government, and by the use of facilitators in focus countries to provide intelligence, identify bottlenecks and facilitate stakeholder interactions.  The option to exit from high risk countries is built into contracts to enable early termination if necessary.
Delivery risks, failure by FGMC partners either in their direct delivery or in their coordination with others, remains moderate and unchanged. Delivery chains span a number of countries, and multiple partners in government, the private sector and civil society.  FGMC has developed a thorough delivery chain mapping that traces and analyses how funds flow through international CSOs down to final beneficiaries and partners. Mitigation of these risks is an on-going priority, implemented through strong management by the DFID team coupled with the coordination, due diligence, monitoring and lesson learning provided by PMST. DFID country offices are actively engaged in oversight, particularly in China and Indonesia.
Overall reputational risk remains relatively low because of the broad base of support for the programme and consensus between business and CSOs.  However some partners are working to directly challenge on issues such as illegality, corruption, poor human rights, a lack of transparency, environmental crimes, poor corporate responsibility and standards. As such they may criticise actions by governments with whom HMG has a good relationship, or challenge HMG. Reputational risk is mitigated through: regular monitoring of grantee actions by the PMST and DFID officials, with established protocols for handling sensitive reports and findings; accountable grant contracts include a mandatory requirement to comply with all relevant UK legislation, including the Anti-lobbying act; and may be terminated if activities pose a reputational risk to DFID; and due diligence audits to identify any areas of concern.
There is a significant and growing operational risk of disruption to on-going reforms as a result of delays in mobilising Phase 3 (April 2018-21) of the programme. All grant projects as well as Technical assistance contracts ended by early 2018, but mobilisation of new grants and supplier contracts have been delayed by changes to internal DFID procedure.  In the interim, the FGMC team has secured transitional support to sustain critical reforms through international organisations, other donors and implementing partners in Liberia, Guyana, Ghana, Republic of Congo and Indonesia. The PMST has worked extremely efficiently to secure a new set of grants in early July 2018. However, on-going DFID procurement procedures for new Supplier contracts in Liberia, Ghana, Guyana, Republic of Congo, and China pose a risk to delivery in 2018 and 2019.
Fiduciary risk is considered to be low with strong oversight from a KPMG management support team. Where FGMC works in challenging countries, funds are managed by commercial suppliers with strong performance records and robust corporate governance. Grant applicants are subject to prior due diligence assessments and close monitoring by KPMG. The programme exercises a robust process of due diligence that goes beyond a review of financial management capacity, and extends to wider governance arrangements and any potential for conflict of interests. All programme partners assume full financial responsibility for all sub-grantees, as well as demonstrating robust internal due diligence processes over the full chain of their implementing partners.
Safeguarding risks are considered low. FGMC partners do not work directly with children or vulnerable adults. Each of the directly funded partners has confirmed they have whistle-blowing and anti-harassment policies, and understands their responsibility to take all reasonable steps to prevent sexual exploitation, abuse and harassment by either their employees or a downstream partner, and to report any incidents immediately. Due diligence prior to contract issuance has checked safeguarding policies.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)
Overall FGMC spend in the past financial year was £28.9 million (£1.6 million lower than 2016/17) . By funding modality the largest portion, 48%, was spent by not-for-profit organisations receiving grants managed by the PMST. 23% was spent through grants managed directly by DFID under Memoranda of Understanding. The remaining 29% was spent through the 12 contracts that were active in 2017/18.   All spending is fully compliant with the SMART rules. Delivery chain mapping provides a comprehensive picture of downstream partners, and suppliers are aware of their obligation to take fiduciary responsibility for those partners. Performance of contracted suppliers in 2017/18 was generally good, with delivery in line with planned schedules.  One exception however was the contract for procurement and installation of IT and solar power equipment, necessary for full reliable operation of the Ghana Timber Legality Assurance System across multiples sites. Factors such as poor communication, late changes to specifications, and unclear roles and responsibilities delayed the ordering of goods consignments, resulting in £2 million of slippage between 2017/18 and 2018/19. The causes of delays were partly, but not wholly, outside the supplier’s control. Communications and coordination between DFID, the supplier, their sub-contractors and the beneficiaries have been much improved in 2018 and the delivery and installation is now on track to be completed in 2018.
PMST management of grant recipients has been diligent. In addition to ensuring that grantee quarterly narrative reporting was timely and of good quality, PMST provides a grantee help desk function for day to day queries and have continued with its rolling programme of strategic “grantee conversations” (which are joined by the FGMC SRO whenever possible) . These conversations enable in-depth discussions of progress, highlights and challenges from each project, and for the PMST to share latest thinking on the FGMC theory of change and direction, feedback on project proposals, reporting, and other grant management issues. These meetings are generally held over a half day and can result in a range of actions, for example changes to the programme of work, or the structure of reporting, which are subsequently tracked. FGMC partners have continued to actively support the FGMC community of practice through lesson learning events and the dissemination of publications.
FGMC partners have responded positively and efficiently to information requests (for example on safeguarding policies) and to our rigorous expectations of supplier performance and financial management.
Capital assets such as office equipment, furniture and vehicles represent less than 1% of FGMC expenditure to date. Wherever applicable grant holders and service providers maintain up to date asset registers. The solar power and IT goods being purchased for the Ghana Forestry Commission are not included in this figure, since ownership (and liability for loss or damage) passes to the Forestry Commission, as the end beneficiary, immediately upon delivery. A number of contracts and grants came to an end in 2017/18, or are due to end shortly, and in each case asset disposal arrangements have been or are being agreed.
In the second half of the reporting year PMST put high levels of time and effort into establishing the grants portfolio for the final 2018-21 phase. In addition to proposals being strong on their own merit, a portfolio of complementary and mutually reinforcing grants needed to be developed, covering key areas of the FGMC Theory of Change. As of July 2018, 21 shortlisted proposals have progressed through the concept note, proposal review and due diligence processes. 15 of these grants have been awarded and the remaining 6 are awaiting finalisation.
The PMST has introduced an Annual Compliance Statement, requiring grantees to explicitly report compliance with a range of DFID policies (e.g. on gender and disability)
This is a complex transitional period for FGMC, requiring intensive management by DFID and the PMST and placing pressure on management resources. Twelve separate funding arrangements (held by DFID, plus 21 grants held by the PMST, either ended during the reporting year or are due to expire soon. The PMST has consolidated management information and results in a “project completion report” for the 2015-18 phase of FGMC. Arrangements for 5 new service contracts, one contract extension, four new Memoranda of Understanding need to progress as fast as processes allow, and the remaining new grant awards need to be concluded by PMST. Recruitment and funding for a China Programme Coordinator based in the British Embassy is also critical to realising our ambitious objectives there. As indicated in section E above, there is a high risk that delays in starting new work will result in slippage in the 2018/19 budget, and add to demands on the 2019/20 budget.

Date of last narrative financial report(s)	Varies for each MOU and service contract. / All reports due have been received.
Date of last audited annual statement (s)	Varies for each MOU and service contract. / All reports due have been received.

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

FGMC continues to work to and be guided by the original Business Case and logframe. Over the past year we have reviewed and refined FGMC’s strategy and theory of change and developed focused country specific theories of change to guide progress and reporting in the final phase to 2021. The results focus for the final period of FGMC is set out in the Business Case addendum agreed with Ministers in October 2017 as well as in the country specific governance reforms agreed with national stakeholders and framed by VPA and their associated workplans.

FGMC takes an “adaptive” approach to monitoring with lesson-learning at its core. This involves active management of a rich network of actors who form a community of practice that mutually supports different initiatives across the world, through:
- strategic events where vision and understanding are developed. This includes an Annual Forum for FGMC partners to foster learning and coordination across the programme; an annual stakeholder meeting hosted by Chatham House and attended by over 250 participants from around the world, including high-level government officials; country level learning events to share lessons and coordinate action with national private sector, civil society and government services; regional level learning events focused on specific themes such as independent forest monitoring by CSO in Africa, and also in Asia; and working with SMEs in east Asia; and coordinating enforcement action between Asian and EU enforcement agencies;
- programme monitoring: Monitoring of FGMC progress is supported by an independent outsourced programme support team (PMST) engaging 5 full time experts. Feedback and evidence based on field visits, regular reviews and partner reports, is assembled by the PMST into quarterly and annual progress reports which form the basis for internal DFID reporting. Regular face to face meetings are held with Grantees, Suppliers and other partners to ensure that projects are on track and lessons are transferred across the programme and that activities are effectively coordinated. Based on the experience and challenges of monitoring and reporting the diversity and richness of the programme, as well as changes to DFID procedures, the PMST have developed a new reporting and feedback framework for all new grants and supplier contracts which will be deployed in the coming year;
- FGMC will again engage independent progress reviews to reflect particularly on the extent to which the programme outputs, with all its constituent parts, are advancing against the programme outcome to drive systemic governance and market reforms. These periodic reviews complement the insights gained from the European Forest Institute’s broader progress and results monitoring that inform national government, stakeholders and donors in the context of country specific change. A new supplier contract for this function is to be mobilised in 2018;
- Insights and intelligence from EFI’s VPA progress monitoring for each of 16 countries;
- ICF monitoring: FGMC contributes to the UK’s Climate Change objectives and contributes to:
- Transformational change: PMST has developed a unique approach to monitoring change, reflecting the focus of the programme on changing all aspects of forest sector governance – policy making, deliberation, voice, rights, transparency and the rule of law. This is tracked and reported by PMST through a Transformational Change Index (see output 1 above);
- Hectares indicator: A methodology for measuring “hectares of avoided deforestation”, developed by the commercial supplier Ecometrica, is being tested with a number of HMG programmes. In Ghana, the methodology is being integrated into the national monitoring system and is consistent with the Impact Monitoring developed for the VPA, discussions are on-going with a new project team in Indonesia to adapt this for their context;
- Forest dependent people: The PMST is working with the International Forest Research Institute on the indicator gauging the “number of forest dependent people benefitting” which is particularly challenging for FGMC a global programme with no fixed geographic scope. Identifying innovative approach to gauge progress will be developed in the coming year to better capture FGMC impacts.
Programme TCI Score (2013-18) Transformational Change Index
Given its focus on governance and policy change, FGMC has developed a Transformational Change Index (TCI) to assess governance results and the likelihood of their lasting impact across very different national contexts. The Programme Management Support Team (PMST) adapted the ICF’s methodology to the specific context, nature and objectives of the FGMC programme and determined baseline scores (2012-3) for comparison with subsequent years. At a country level the TCI gauges change that represent a shift from a) a state of ineffective forest governance to, b) a new state where the rules of the game have been legitimately agreed and are effectively implemented. It assesses the quality of policymaking process (inclusiveness, incentives, capacity, reasoning and evidence, mechanisms) as well as the enabling factors including sustainability, innovation and scale. The assessment draws from key experts engaged in country processes and from independent reports. It seeks to determine the extent to which conditions are present that will enable a transformational shift in institutions and markets.[7]
[7] For more detail see the FGMC Transformation Change Index: Assessment Report 2017/18 (PMST, 2018)
At the programme level, there has been a significant increase in the overall TCI score rising from 4.2 in 2012/13 to 5.9 in 2017/18 – an increase of 1.7 or 41%. The increase between 2016/17 – 2017/18 has been more modest reflecting varied progress at country level, with significant improvements in Indonesia, RoC and China and the remaining countries remaining steady in performance or slightly decreasing in the case with Burma. Overall it reflects improvements in the conditions necessary to transform global timber markets and national forest governance systems to a state where illegal timber is cut out of international exports and benefits accrue to poor and forest dependent people at the national level.
Economic Cost-Benefit Analysis Modelling: The economic model of the original FGMC business case mentioned in Section D needs to be updated (as recommended by the MTR). The model seeks to identify and value the intended impacts of far reaching governance and global markets reforms. It needs to be reworked to be more closely aligned to the FGMC programme theory of change. An independent consultant was engaged for this purpose and calculated a strongly positive rate of return for the programme, but independent review suggests that this needs further work before it can be used to track progress and impacts for the programme. The PMST will invest further in this analysis before analysing the programmes future economic impact monitoring.
Evidence used for this Annual Review includes:
1. External review of the 2nd phase of FGMC 2014-17 (July 2018 by Tom Blomley);
2. PMST Annual Progress Report April 2018;
3. Direct evidence from DFID and PMST visits to Liberia, Ghana, Rep of Congo and China;
4. Written evidence from PMST’s Quarterly reports which provide a synthesis of reports and material from FGMC partners, including the project completion reports of 20 grants;
5. Project completion reports from the Indonesia Multistakeholder forest programme; project completion report from the international trade and investment partnership with China;
6. Written reports from EFI outcome monitoring and documenting achievements database;
7. Review meetings with in-country Facilitators and Grantees by PMST and DFID;
8. Knowledge products developed by FGMC projects, particularly on Facilitation of FLEGT processes, Independent Forest Monitoring, and capacity building assessments in Liberia.
Learning
As indicated above this has been a year of transition bringing to a close many actions from the 2nd phase of the programme, drawing lessons and strategically positioning FGMC for its final phase. As such this year has featured extensive lesson learning between practitioners as well as in publications and project completion reports. Some of this has been shared widely across the community, some has informed the design of the last phase of the programme, new project proposals that have recently been agreed and new tools to inform future policy making. The 2018 Annual Programme Report provides a catalogue of the expansive learning this year that includes, for example:
- A series of case studies from the Congo Basin (Well Grounded) on building the capacity of civil society to engage effectively in national policy-making through innovative partnerships between African CSOs and International NGOs, in three languages.
- Guidance, best practice and lessons learnt in establishing clear standards to address land tenure issues including addressing historic grievances around land and forests in Corporate Social Responsibility policies (Rights Resources Initiative ‘Land Legacy Issues: Guidance on Corporate Responsibility’).
- From Ghana: lessons on gender mainstreaming in VPA processes and sector governance reforms aiming to inform future agreements and negotiation processes(Fern) ‘Analysis of gender impacts of the Ghana Voluntary Partnership Agreement with European Union’.
- From China: development on sustainable rubber guidelines for investments and operations in 3rd countries by the Chinese chamber of commerce has been shared with other commodity supply chain processes and may inform the development of an international rubber standard working together with international companies.
- In response to queries from the private sector, the UK Timber trade federation together with the Ghana trade associations commissioned a gap analysis between the Ghanaian VPA legality standards and the current PEFC private certification standards. The report highlights that the VPA standards are not restricted to legality (a common misconception in EU trade) and also address social, economic and environmental requirements (Certification vs VPA. Demonstrating the complementarity/equivalence of voluntary and regulatory market-based mechanisms for more efficient timber trade, UK Timber Trade Federation).

Learning from FGMC partners is also reflected in the proposals for future work or new policy dynamics. Some examples include:
- A study of market measures and experience of enforcement comparing emerging legislation in Japan, Korea, Malaysia, Indonesia, Vietnam and China and highlighting key similarities and differences in approaches to exclude illegal timber from their national markets. As a baseline, this study will allow Forest trends to monitor progress of adapting legal frameworks and enforcement practices in the region over the coming years to achieve greater coherence and level market.
- Fern’s in country partner conducted research in Republic of Congo to analyse the NDC development process and its ‘forest’ content. Interviews were held with government experts, donors, and civil society actors and the findings from the study will inform the future implementation of NDC in Republic of Congo and CSO driven governance reforms to be integrated to the future strategy.
- Chatham House hosted an experts meeting of impact monitoring experts to share lessons of monitoring the impacts of FLEGT and governance reforms so as to inform future monitoring. This learning has guided the refinements Chatham House propose to introduce for the new project that will continue to track indicators of change across 19 countries, but in a more interactive and expansive fashion to draw in additional analysis and expertise .
- EFIs contributions to the ‘Feasibility analysis of the incorporation of timber legality requirements into Chinese laws or regulations to promote trade in legal forest products’ provided insights from experience in other countries and will provide the basis from which Chinese stakeholders reflect on possible future legislation.

Recommendations (1/2 page)
The recommendations of the previous annual review have informed the design of this last phase of FGMC, the shape of the recent grant call for proposals and indeed some of the new Accountable Grant award decisions. Where appropriate they will be addressed in new Supplier Contracts or arrangements. In particular, this includes:
- More focus on financial investors encouraging them to eliminate illegal timber and other forest risk commodities from international trade.
- Greater attention to illegal forest conversion and the strategies adopted by different countries to control and manage forest clearance and contribute to national and international policy developments that tackle illegal deforestation.
- Focus on the challenges faced by small and medium-sized enterprises in VPA countries in meeting international market requirements.
- Support partner governments to secure the financial sustainability of institutional arrangements under VPAs[8], and of new or upgraded regulatory systems.
- Encouraging China to take a leadership role in tackling illegal logging in global trade and to support the reform efforts of developing countries.
1. The 2018 Annual Programme Report provides a catalogue of the expansive learning this year across the programme, there is a need to reflect how to make this more readily accessible, to better summarise and share lessons across HMG and into the wider FGMC community of practice. This could include a focus session at the Annual FGMC meeting on lesson learning. More broadly, FGMC should invest more in sharing lessons and experience across HMG, demonstrating the value of linking trade and market incentives to drive governance reforms, monitoring transformational change, and promoting inclusive policy-making processes.
2. The PMST should engage with EFI, FAO and Chatham House to reflect further on the need to better understand impacts of governance reforms on changes in business standards and practices, livelihoods, employment, forest status, environmental benefits and accountability.
3. The PMST should further revise the FGMC economic analysis, reflecting on the value of inclusive decision-making processes.