Type of Review: Project Completion Review

Project Title: DFID Kenya Humanitarian Programme 2010

Date started: Jan 2010	Date review undertaken: May 2012

Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
The UK provided £8.8million to the following agencies: / £2.0m United Nations Refugee Fund (UNHCR) - refugees multi-sectoral / £1.19m Save the Children– nutrition and health / £1.24m Action against Hunger (AAH) – nutrition and health / £825k Solidarités – Disaster Risk Reduction (DRR) / £600k Islamic Relief Kenya (IRK) – nutrition and health / £1.5m United Nations Childrens Fund (UNICEF) – nutrition and WASH / £1m United Nations Office for the Coordination of Humanitarian Affairs (OCHA) – Emergency Response Fund (ERF) / £150k OCHA – co-ordination / £37k Value for Money study

What were the expected results?
The expected outcome goal of the programme was: / To save lives, alleviate suffering and maintain dignity / The purpose of the programme was: / To address the most urgent and widespread human needs in Kenya / Amongst others, expected results included: / 40,000 starving children treated / 5,000 malnourished pregnant and breastfeeding mothers treated / 380,000 people provided with safe water, knowledge regarding safe treatment of water or improved sanitation / 20,000 refugees, IDPs and stateless persons reached with multi-sectoral support / 70% severely malnourished children in Arid lands have access to treatment / 64,000 people benefitting from asset protection activities / 9,000 households have access to at least 1 improved livelihood coping strategy / 5,000 people benefiting from efficient stove distribution and training

What was the context in which UK support was provided?
Recurrent drought, increasing commodity prices, resource related conflict and chronic poverty, marginalisation and underdevelopment has had a compounding effect on the livelihoods, food security, nutrition and health status of vulnerable populations in the Arid and Semi Arid Lands (ASALs) districts of northern and eastern Kenya. One good season of rains in 2009/2010 was not sufficient for recovery and rates of general acute malnutrition remained above emergency thresholds in many areas of the ASALs in 2010. In late 2010 and early 2011, the situation started to deteriorate again, especially following the short rains failure. The situation deteriorated again in mid 2011 due to poor long rains, high food prices and challenges in food aid delivery - with rates of acute malnutrition reaching double emergency thresholds in Turkana, Wajir and Mandera. / Kenya also continued to host a large and growing refugee population. In 2010 there were an estimated 412,000 registered refugees, including 338,000 of Somali origin. In late 2010 and 2011 the refugee caseload started to increase rapidly, causing the Dadaab refugee complex to be severely congested with many refugees living in the outskirts of the camps with limited access to services. Permission from the Government of Kenya (GoK) to open a new camp (Ifo II) which would improve conditions was delayed, but finally provided in mid 2011. / Outside of the ASALs, flooding affected 130,000 in 2010, causing dozens of casualties and mass temporary displacement. Cholera outbreaks were reported in many districts with 72 cholera deaths. Although the violent situation of 2008 was not repeated, the UN estimated 360,000 Internally Displaced Persons (IDPs) remained in Kenya, including 60,000 still displaced from the violence in 2008. / Despite some efforts by the Government of Kenya to respond to humanitarian needs, there was still a significant international response, coordinated by the UN. In 2010, the UN’s Emergency Humanitarian Response Plan sought funding of $586m and was 60% funded at the time of DFID’s intervention. The 2011 appeal initially sought $525m, but this was subsequently increased to $741m to take into account increasing needs. / DFID’s humanitarian programme supported activities over an eighteen month period, although the bulk of funds disbursement was completed by March 2011.

## Section A: Detailed Output Scoring

Output 1: Protection and life saving assistance to disaster and conflict affected populations, including refugees.
Output 1: final score and performance description: / Final score: A+. Moderately exceeded expectation: / Four of the output indicators were exceeded and two were slightly below expectation. On balance we judge that for the output as a whole the programme moderately exceeded expectations. In reality indicators 1, 3 and 4 were the most significant in terms of spend and impact. / Indicator Baseline Target Achieved / (DFID attributable) Output Description / No of starving children treated (SAM and MAM) 0 in Oct 2010 44,000 (16,000 – SAM; 28,000 – MAM) by Mar 2012 19,269 (SAM) and 57,081 (MAM) Exceeded expectation / No of malnourished pregnant and breastfeeding mothers treated 0 in Oct 2010 5,006 by Mar 2012 (this figure did not include a UNICEF anticipated figure) 1665 (although under reported from some partners) Moderately did not meet expectation / No of people provided with safe water, knowledge regarding safe treatment of water or improved sanitation 0 in Oct 2010 380,000 (increased from 100,000 following ERF allocations) 487,000 Exceeded expectation / No of refugees, IDPs and stateless persons reached with multi sectoral support 0 in Oct 2010 20,000 by Mar 2012 15,785 reached in 2010 Moderately did not meet expectations / No of people benefitting from asset protection activities 0 in Oct 2010 64,000 123,690 Exceeded expectation / % of severely malnourished children able to access treatment in Arid Lands 64% in Oct 2010 70% by Dec 2011 75% Exceeded expectation / Funded agency-specific results contributing to output (results attributable to DFID) / Indicator UNHCR Save the Children AAH Islamic Relief Kenya Solidarités UNICEF ERF / No of starving children treated / (SAM and MAM) 11,994 (women and children) / 16,611 (women and children) 4,000 / 13,734 6,970 (women and children) / 8,690 (women and children) Proposal was focused on coverage, not children treated, but subsequent additional reporting provides these results: / 19,269 (SAM) and 57,081 (MAM) children treated / No of malnourished pregnant and breastfeeding mothers treated 7,183 1665 2,107 / No data 50% / >50% / No of people provided with safe water, knowledge regarding safe treatment of water or improved sanitation 12,554 / No data 29,500 / 28,500 45,000 households (270,000 people) / 270,000 380,000 / 217,193 / No of refugees, IDPs and stateless persons reached with multi sectoral support 20,000 / 15,800 / No of people benefitting from asset protection activities 9,000 / 9,185 64,000 / 123,690 / % of severely malnourished children able to access treatment in Arid Lands 4,000 children / 13,734 75% / Proposed / Achieved
Final results: / Nutrition Indicators / The funding to nutrition partners in 2010 played a significant role in ensuring essential services and pipelines were in place for the deterioration in situation in early 2011 (with admissions seeming to peak in May before the actual scale up in relief response in July). / UNICEF reports that with support from DFID, the malnutrition recovery rates and death rates remained within the set SPHERE standards. The level of integration of nutrition services delivery improved greatly with an enhanced ownership of nutrition activities by the Ministry of Health. UNICEF helped scale up nutrition services through the provision of therapeutic food products, recruitment of field nutritionists and a constant engagement with nutrition focused NGOs. / UNICEF provides the commodities for NGOs to treat malnourished children and so to avoid double counting, UNICEF beneficiary figures are used as the overall total, rather than also adding to NGO figures, which increases risks of double counting beneficiaries. The output indicator regarding coverage is much higher than the target – this may be due to weaknesses in the assessment methodology used which overestimates coverage (and should be examined further in future programmes) / Save the Children’s project outputs were slightly below expectations (poor security in the area of operations is one factor), but at the time of the review (May 2012) the final project report had not been received. However February 2012 reporting shows more than the target number of women and children were reached through the nutrition programme. / Action Against Hunger cite an average cure rate of 90.8% for severe malnutrition and 88.6% for moderate malnutrition. Their final report shows that the number of children reached has been significantly exceeded – this is in part due to AHH’s expansion into Makueni District which has a higher population than Garbatullah. The fact that some indicators were far exceeded within the planned budget is not necessarily an indicator of poor budgeting. In Makueni, AAH’s level of engagement in treatment was relatively low (some training etc) and so cost per child much lower than the normal comparator (circa £54/child without supplies). / Islamic Relief Kenya report that about 62% of the targeted malnourished children under five and pregnant and lactating women were reached – this can be attributed to the mass screening of virtually all under fives and pregnant and breastfeeding women in the entire Wajir West and North districts. However no accumulative figures of actual population reached are reported. / The level of disaggregation of reporting by partners for nutrition has been disappointing and this will need to be flagged in future projects and programmes / WASH / Overall figures provided by UNICEF/ERF are used to measure whether indicators met (rather than adding NGO figures too) in order to reduce the risk of double counting given UNICEF, ERF and bilaterally funded NGOs may be working with same beneficiaries (with the same NGO implementing partners), but with different interventions or over different time periods. / IRK reports that despite training and health promotion messaging it was noted that behaviour change with regard to hygiene and sanitation has yet to be visible. / Asset protection / The UN managed Emergency Response Fund (ERF) was the main contribution to asset protection activities. DFID made a contribution of £1m in early 2011 following the anticipated failure of the short rains and early warning of poor long rains with the conditionality that it must be disbursed immediately for drought mitigation activities. Over the whole of 2011 the ERF committed $3,376,448 to projects. This included $1.19m for livestock and agriculture and $1.17m for WASH through various NGO partners. Key results included the destocking of 11,288 small ruminants; supplementary feeding of 2,970 breeding animals; provision of seeds to 1,000 households; cash transfers to 300 households; access to water for over 527,000 animals; and vaccinations for over 156,000 animals. The table below summarises ERF results at household level and DFID attributable share (total ERF spend of $3.75m, with a DFID contribution of £1m (approx $1.55m). DFID therefore has a 41% share of ERF expenditure and results in 2011). / Households Beneficiaries DFID share DFID beneficiaries / Livelihood support 59,875 359,250 41% 147,293 / Access to safe water 87,578 525,468 41% 217,193 / H/H food security 8816 52,896 41% 21,687 / Education 6274 6274 41% 2,572 / Refugees: / The 20,000 beneficiary figure target was calculated during programme design using approximate £/beneficiary costs for a refugee care and maintenance programme. However, DFID funding was allocated against UNHCR’s overall appeal, with utilization spread between the 2010 and 2011 appeal – up until the end of March 2011. UNHCR was not obliged to report specifically on the DFID contribution and the review has to rely on generic donor reporting. The 2010 appeal report is therefore taken as the basis for this review, with proportionate share of appeal results attributed to DFID according to proportionate share of funding available and spent by UNHCR in 2010 (e.g. £2m UK contribution equates to 3.3% of $97m UNHCR expenditure in 2010). In 2010, UNHCR reached 481,320 beneficiaries, with 3.3% (15,800) attributable to DFID support. / A number of factors prevented UNHCR from reaching the full number of refugees, IDPs and stateless persons (caseload 751,000), including funding shortfalls, security threats, camp congestion and lack of access to natural resources (firewood and shelter material) / Impact Weighting: 70% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 2: Improved effectiveness of overall humanitarian response
Output 2: final score and performance description: / Final Score: A. Met Expectation / Two of the output indicators met expectations and one did not. For output 4, we are missing key data, but anecdotal evidence is that the sector was relatively well funded in early 2011. On balance we judge that for the output as a whole the programme met expectations, given the ERF was only responsible for a relatively modest part of DFID’s spend and its impact on the overall system is limited. / Indicator Baseline Target Achieved Output Description / Evaluation of system-wide emergency nutrition response completed 0 1 by Dec 2011 (1 evaluation implemented) / (attributable to DFID) Met expectation / Numbers of nutrition surveys completed 0 8 by Dec 2011 (8 surveys completed) / (attributable to DFID) Met expectation / % of ERF grants disbursed within 1 month of call for proposals 0 100% by Mar 2012 (Hard data unavailable, but anecdotally was not achieved) / (not attributable to DFID alone) Not achieved / % of CAP needs met in nutrition cluster 60% in Sep 2010 > 60% by Mar 2011 No reporting now available / However, sector was relatively well funded given donor confidence in coordination system / (not attributable to DFID alone) Unknown / Final results: / UNICEF carried out an external evaluation of the system-wide emergency nutrition response in April 2011. It reported that the draft Food Security and Nutrition Strategy (2008) and related Food Security and Nutrition Policy (2009) are being reviewed prior to be being submitted to Parliament. Coordination within the Ministry of Public Health and Sanitation has been strengthened through the development of the Inter-sectoral Coordinating Committee for Nutrition. The Nutrition Technical Forum and its related working groups have expanded beyond an initial emergency focus to facilitate coordination and reach consensus on technical standards and targets. / Eight regional nutrition surveys were completed by December 2011. The Kenya CAP nutrition sector reports 345,000 people acutely malnourished with 290,000 of these being children and 55,000 women. However in April 2011, this figure was updated to 90,000 women. As the target figure fluctuates, it becomes extremely difficult to assess the percentage of CAP needs met in this sector. / ERF 2010 reporting does not include data on speed of grants disbursed, but anecdotally we assess the proposal screening and allocation of funds was slow. OCHA report awareness of the need to speed up processes whilst at the same time maintaining necessary screening procedures and the country team is reportedly working on this. Some critical ingredients to an effective ERF (e.g. sectoral coordination and UN leadership) cannot be fixed by the ERF itself. However, unless these issues are addressed the ERF is likely to remain of more limited effectiveness. / A cost extension was granted to the Save the Children nutrition programme to allow support to the Transparency International assessment of corruption risk in food assistance programmes. TI worked hard to ensure partner participation in the assessment process and have now secured funds for the phase II – follow up on implementing the recommendations. This report has the potential to play a catalytic role within the whole system in Kenya - and is not just specific to Save the Children. / Value for Money Study. A small proportion of funds from the DFID Kenya humanitarian programme 2010 were allocated towards an independent study to provide DFID with a useful framework for assessing value for money in humanitarian programming. The recommendations were rolled out with partners in 2011 and this approach is now being independently reviewed for its utility. / Summary / The humanitarian system in Kenya could still be more effective. Progress is uneven – with a strong nutrition sector (led by GoK, with support from UNICEF and NGO partners). Donors played a role in prompting OCHA and the Humanitarian Coordinator to accelerate the response to the 2011 drought (including by asking for, and supporting, an ERF allocation process). Significant efforts (funding and non funding engagement) were also made in the 2011/12 humanitarian programme to strengthen system coordination, but progress beyond nutrition remains slow.
Impact Weighting: 20% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Reduced disaster risk and increased resilience of disaster affected communities
Output 3: final score and performance description: / Final Score: A. Expectation Met / One of the output indicators moderately exceeded expectations and one was slightly below at the time of reporting. On balance we therefore judge that the overall output was met (especially as we were still awaiting additional reporting on output 2 at the time of the review). / Indicator Baseline Target Achieved Output Description / 60% of target households have access to at least 1 improved livelihood coping strategy 0 9,000 by Oct 2011 9,185 reached Moderately exceeded expectation / Number of people benefiting from efficient stove distribution and training 0 5,000 by Oct 2011 4,500 people Moderately did not meet expectation at time of reporting
Final results: / From an initial 27,000 proposed, Solidarités’ target population was increased to 29,500 and a total of 28,500 were reached by the end of the project period. / Acute lack of water in two locations hampered construction of improved stove in the two areas and only 4,500 people were reached at the time of reporting. Construction was agreed to re-start after the short rains when water would be available. Further reporting is necessary to provide feedback on whether the target was fully reached. / The consumption of firewood was reportedly reduced by at least 30% among half of the beneficiary group; livestock mortality was reduced by at least 10% in the targeted areas after the second de-worming campaign, and at least 60% of the beneficiary farmers increased their crop production by at least 30%. Less effective however, was the awareness campaign around the importance of protecting water sources and messages on hygiene promotion demonstrating changed behaviour and practices. / Impact Weighting: 10% / Revised since last Annual Review? N. / Risk: Medium / Revised since last Annual Review? N

Output 4: [insert output]
Output 4: final score and performance description:
Final results: / Impact Weighting (%): / Revised since last Annual Review? Y/N / Risk: Low/Medium/High / Revised since last Annual Review? Y/N

## If the project involved more than 4 Outputs please copy the box above and paste below.
## Section B: Results and Value for Money.

1. Achievement and Results

Has the logframe been changed since the last review? N / 1.2 Final Output score and description: / Final Score (Calculated by ARIES) / Broadly all projects funded under the umbrella humanitarian support package to Kenya in 2010 contributed to outputs being achieved. / Some parts of Northern Kenya and the ASAL regions of Kenya are inaccessible to DFID staff based in Nairobi, but field trips were undertaken to Wajir (IRK, SC, UNICEF), Marsabit (Solidarites, UNICEF), Turkana (UNICEF) and Dadaab (UNHCR). However, programme management by DFID staff was primarily undertaken remotely from Nairobi, with reliance on UN and NGO partners reporting. / DFID’s requirement for attributable beneficiary figures is sometimes challenging for those agencies where support is provided across agency reporting periods (e.g. UNICEF and UNHCR). DFID attempted to address this challenge in 2011/12 by insisting on DFID specific programme documents. / The independent review team did not undertake field visits, but relied on reporting agencies’ own reporting, in-depth interviews with a sample of partners and feedback from DFID staff that have monitored the portfolio during the course of the year.
Direct feedback from beneficiaries / The review did not include any direct feedback from beneficiaries, but field monitoring by DFID staff during the course of the project allowed some qualitative feedback plus efforts to see if partners had put systems in place to encourage participation of communities during the design and delivery of programmes. For example, monitoring confirmed that Solidarités has benefited from widespread acceptance and support from supported communities, with close participation of community leaders, CBO’s, schools and elders in decision making and site identifications. Solidarités encourages participation and community inputs during activity identification and prioritization and implementation of construction works. / The results of the Transparency International Study do flag opportunities to further strengthen beneficiary engagement and these should be followed up in future programmes.
Overall Outcome score and description: / Outcome goal Indicator Baseline Target Achieved Outcome Description / To address the most urgent and widespread human needs is Kenya Rates of GAM and SAM in Turkana, Mandera, Marsabit, Wajir and Samburu GAM / > 20% in June 2010 < 18% by Oct 2011 / < 15% by Mar 2012 2 out of five districts / met Oct 2011 target moderately did not meet expectation / Number of people provided with basic humanitarian assistance 0 115,000 / (n.b. was not updated correctly during year) 487,000 More than met expectation / Overall outcome score: / Nutritional surveys in the five named districts were carried out by UNICEF and partners.). / Results were as follows: / Turkana districts (Dec 2011) GAM: 9.7% - 16.9% / Mandera districts (Oct/Nov 2011) GAM: 15.6% - 25.3% / Marsabit (Nov 2011) GAM: 12.8% / Wajir districts (Nov 2011) GAM: 27.9 – 30.0% / Samburu (Nov/Dec 2011) GAM: 8.5% - 21.6% / Updated nutrition surveys should determine whether the outcome target indicator was met for March 2012. / The first indicator did not meet expectations. GAM rates in some districts did not reduce to desired targets – in fact the nutrition situation deteriorated due to high food prices and two failed or poor rainy seasons leading to rates of acute malnutrition spiking in some parts of Turkana of over 37%. It was beyond the scope of this programme alone to mitigate this risk, but it is a reasonable assumption to make that rates of acute malnutrition (and associated morbidity and mortality) would have been significantly higher without it. However, there is a question mark whether rates of acute malnutrition are an effective outcome indicator against which programme attribution and effectiveness can be measured. / The second indicator was met (Although should have been updated during the year to reflect additional WASH beneficiaries from UNICEF and ERF allocations). / Impact and Sustainability / Accurate mortality data over a short time frame in Kenya is difficult to obtain and estimates are too inexact to demonstrate conclusive evidence of significant change. Additionally, too many variables render it impossible to attribute mortality reductions directly to any given intervention. However anecdotal evidence from agency reporting and evidence of improvement in the overall humanitarian situation suggests some impact. More quantitatively, evolving evidence from nutrition sector is that 20% of all children treated for acute malnutrition would have died without treatment. Therefore we can calculate this programme saved the lives of at least 3,800 children. / AAH Life saving nutrition programme / Weak and suffering from malnutrition, 7 months old Abdullahi came to the health centre with his mother. The child was immediately admitted to inpatient care for management of severe acute malnutrition with medical complications. / “My name is Halima. I am 17 years old and a single mother of one. My seven month old child has been very sick for the last three weeks. The baby is coughing a lot and has been suffering from diarrhoea. I have taken the child to hospital and even traditional healers many times but with no improvement. This really made me worry a lot as he has been very weak, unlike the other children of his age. During this period, our village was informed that children below 5 years have to be taken to the hospital for screening so that their weight is assessed. I took my baby to the health centre where ACF staff together with MOH staff screened my child and informed me that his weight was low for his age. Abdullahi weighed 5.2kg. In addition, the child had high fever. The staff assured me that my baby will be healthy again if I adhere to their advice and treatment”. / “I was informed that my child will be in the ward for the next few days till he stabilizes. All the staff were very concerned and my child was given milk every three hours even throughout the night. By the end of the third day, the diarrhoea had subsided and my child looked bright unlike the admission day. On the fourth day, the staff started Abdullah on formula milk, which I was told will enable him to gain weight. The next morning the child weighed 5.5 kg and I was delighted. On the sixth day after admission, bright looking Abdullah even smiled as he became more interested with the environs. The staff introduced the child to Plumpynut as a preparation for exit to the out-patients therapeutic programme. “Luckily enough my child was taking Plumpynut, though in small amounts. The nurse told me to be patient as the child must get used to eating the new product which was said to be very nutritious”. / “The milk has done wonders to my child’s body. I never thought that my child would look that healthy especially after his grandmother invited a traditional healer who always comes and smears her saliva on to the child. All this happens because I wanted my child who has been sickly to get healed once and for all”. / On the eighth day, Abdullahi was discharged from the ward weighing 5.8 kgs. Immediate registration to outpatient therapeutic programme at the facility was done and the child was discharged from inpatients. Halima also gained the knowledge, skills and confidence needed to significantly improve her child’s health and nutritional well being through community health groups training conducted by ACF community health mobilizers. / Sustainability in humanitarian emergencies is rarely a high priority objective. However, nutrition interventions were targeted specifically to work within GoK policy guidance and structures wherever possible. It is too early to tell the impact of this approach, but it is clear that the alternative (of working outside GoK policy and setting up new structures) would contribute less to sustainability. Future DFID nutrition support will include specific indicators to measure whether sustainability ambitions are being reached. / DFID field visits of the Solidarites programme reinforced the view that effective disaster risk reduction interventions are less effective if reliant on short term annual funding – for example, by the time new staff were appointed to the project and understanding activities/ community relationships it was nearly time for the project to end. There was also little monitoring of project interventions funded under previous funding from donors. DFID should think carefully about funding such activities with short cycle funding.

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Y / Agencies completed proposed work within budget and expected costs. In some case DFID funding was a contribution towards a much higher overall programme cost and was allocated towards priority components. / 2.2 Key cost drivers / Key cost drivers for working in remote parts of Kenya are personnel and transport. Security has deteriorated in some parts of northern Kenya (e.g. Mandera and increasingly parts of Wajir and Dadaab refugee complex), which means that international staff may not routinely work or visit these areas. UN agencies and NGO partners are therefore reliant on good national staff. Agencies informed the review team that they have to compete to retain experienced and effective staff. Competition comes from other agencies who can offer increased staff incentives to recruit the best. The review team was also informed that transport companies can charge high rates for trucking goods to insecure and remote areas. Company owners know that agencies need to reach remote populations and fix minimum rates amongst themselves to avoid being undercut by each other. / 2.3 Was the project completed within the expected timescale: Y / DFID funding was provided for projects of up to eighteen month duration. Individual projects were completed within this timeframe. Funds given as a contribution towards an overall programme were spent within this timeframe. Funds given towards UNICEF, UNHCR and the Kenya ERF were disbursed or committed within the timeframe specified (March 2011).

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / Humanitarian partners routinely assessed the evidence around them to monitor the likely impact of their work and adapt programmes as necessary. Evidence relating to the humanitarian situation in northern Kenya and the ASAL region was closely followed and projects focused services on the evident need around them, until the end of the funding period. Some agencies, including Solidarités, found that their target population was greater than anticipated at proposal stage and had to adapt projects accordingly to cope with greater numbers in need. Islamic Relief Kenya adapted to take on additional beneficiaries under the DFID project when ECHO funding came to an end. / When funding is time-bound and of limited duration (eighteen months) agencies working in situations of acute on chronic need have no option but to cease operations at the end of the acute phase when funding ends. If there is little change in need and no secure funding beyond the project period, agencies know the impact they have made may be lost and a vulnerable population in chronic need may have to slip back into acute need before funding is made available again. / 3.2 Set out what plans are in place for an evaluation. / The Independent Commission for Aid Impact (ICAI) is currently investigating DFID’s emergency humanitarian response efforts in the Horn of Africa since October 2010. This will be a high level system evaluation focusing on maximising the effectiveness of the UK aid budget for intended beneficiaries and on delivering value for money for UK taxpayers. ICAI will publish a transparent, impartial and objective report to provide evidence and clear recommendations to support UK Government decision-making and to strengthen the accountability of the aid programme. The report will be accessible to a general readership. DFID had set aside funds for an independent evaluation, but is awaiting the results of this investigation before deciding whether evaluation gaps remain and further work should be commissioned. / In addition, a two person independent review team visited Nairobi in May 2012 to review agency reports and undertake interviews of a sample of funded programmes. The review team also interviewed DFID staff who had monitored the projects (through partner meetings and field visits) during the course of the project implementation. / DFID partners are encouraged to evaluate their own work or to commission independent evaluations in order to draw out lessons learned and recommendations to inform future practice. Under this programme, an external final evaluation has been received from Islamic Relief Kenya. DFID has also participated in the 2011 Interagency Standing Committee (IASC) Real Time Evaluation of the response in Kenya (which covers the period of some of the funded interventions). DFID also undertook an assurance audit of an NGO partner, which although flagging some controls which could be strengthened did not raise specific red flags

4. Risk
4.1 Risk Rating (overall project risk): Medium / Did the Risk Rating change over the life of the project? N / Specific risks and mitigation measures were considered to include: / Political violence, community resource-based conflict, banditry, kidnap risk, or terrorism could inhibit agencies’ and NGOs’ ability to operate and monitor activities and vulnerable populations’ ability to reach the assistance on offer. Chosen partners had to demonstrate a good track record of operating in difficult environments and have adequate security systems in place. / Risks from corruption are high as in all sectors and activities in Kenya. All partner agencies currently working with DFID funding are encouraged to be vigilant and to inform DFID where they have concerns. SC reported thefts and have co-operated in follow up action. The agencies have however been selected partly on the basis of their demonstrated commitment to principled humanitarian action. DFID has also undertaken an assurance audit of a partner and commissioned an assessment of corruption risk in the food assistance sector to facilitate mitigation efforts. / An overflow of conflict or armed groups from Somalia could increase the risk that NGOs and their staff receiving support from UK could be specifically targeted and at greater security risk. DFID was sensitive to concerns of NGOs and will discuss with them before embarking on any major communication efforts, and will retain a flexible approach to branding on the partner’s analysis of risks. / A specific risk of the Kenya ERF was that as UN humanitarian leadership was not strong, pooled ERF funds could be at risk of being allocated to non-highest priority activities. This risk was mitigated by DFID’s insistence that UK funds be allocated before the end of March 2010 thereby ensuring that funds are used for highest priority drought mitigation activities. DFID also insisted that FAO plays a strong role on the technical review board to ensure that activities are well co-ordinated with local level drought contingency plans over which FAO has a good understanding. / DFID and partners took measures to mitigate against these risks. Insecurity and flooding have caused some project delays, but generally this is to be expected and was therefore built into project timeframes and plans. / 4.2 Risk funds not used for purposes intended / See above / 4.3 Climate and Environment Impact / It has not been possible to measure climate and environment impact of this programme as no suitable indicators were included at the design phase or monitored by partners. This is an issue which is now being addressed in new DFID business cases.

5. Value for Money
5.1 Performance on VfM measures / Agencies were assessed broadly on cost effectiveness citing the generally accepted cost-effectiveness of certain types of activity (early response; co-ordination), or assessing in broad terms the cost per output or beneficiary against the planned intervention. / These output unit cost assessments were hampered by a lack of reliable data. DFID used as benchmarks standard metrics developed from past humanitarian operations. Due to the number and scale of the variables that determine a unit cost, whose effect can seen in the sometimes very wide ranges of actual costs, it was not clear to what extent the benchmarks used by DFID were in fact usefully comparable to agency’s budgeted costs in each case. This systematic weakness underlies the generally inconclusive nature of partner unit costs assessments, some of which flag particular confounding factors. DFID therefore initiated research both centrally and for the Kenya programme to provide recommendations and baseline data for future assessments (came into play in 2011). / 5.2 Commercial Improvement and Value for Money / No assessment of this has been undertaken / 5.3 Role of project partners / The following is a brief summary of the rather variable cost-effectiveness reasoning brought to bear on partner proposals by DFID. / UNHCR. Full support to a completely dependent population is estimated to cost in the region of 0.50c per person per day. Based on this assessment, the UNHCR proposal appeared expensive, with funding sufficient for an encamped population of 832,000 - well above the actual population being supported. However funding to UNHCR’s appeal was well below the appeal amount, indicating that UNHCR may indeed be operating more efficiently than might be expected from the project budget. / Save the Children UK aimed to provide emergency health and nutrition services at 63 sites across three districts. The expected approximate total cost for nutrition interventions (at standard intervention prices was taken to be around £74 per person. SCUK’s project costs amounted to £120 per person but includes an integrated basic health component so was judged to be reasonable. / Action Against Hunger’s nutrition component costs came to approximately £300 per person compared to a standard unit cost of £100 per person. Nevertheless the budget was agreed following an explanation from AAH that they may have under represented some of the planned health outputs, which had been included in the budget. / Islamic Relief Kenya appeared initially to have significantly under-budgeted for the number of malnourished children in their caseload. With an average SAM treatment cost at £140 per case and MAM treatment cost at £63 per case, Islamic Relief’s project caseload would be expected to require around £1.3m. However other donors had also been approached and the request to DFID of £600k was just a contribution. / The cost per beneficiary within UNICEF’s overall Kenya humanitarian appeal for 2010 were $18 per person for nutrition and $3 per person for WASH. These figures were not considered very illuminating given the wide range of activities included. For example, treatment of severe malnutrition costs between $200-230 per person, but costs of hygiene promotion activities are minimal with UNICEF estimating very high beneficiary numbers who they would expect to be reached. It was felt that further work was required to explore UNICEF actual costs and whether the agency can present information in a way that makes a true analysis of unit, output and even outcome costs, more possible. / OCHA centrally charges 3% for managing a country ERF but this does not provide any support to the in-country management and monitoring of the fund or its funded activities, an estimated cost to the Kenya office of $190,000. DFID CHASE is engaging at global level with OCHA to review the cost and support structure of pooled humanitarian funds including ERFs. / OCHA Co-ordination value for money is difficult to quantify. However it is reasonable to deduce that without effective co-ordination and prioritisation the risk of duplication and wastage would be much greater. OCHA’s co-ordination support funding requirements amounted to 0.5% of overall Emergency Humanitarian Action Plan costs. This was in the lower range of other country comparators. / Solidarités’ proposal allocated approximately £18 per beneficiary, however the spread of activities made assessment of cost effectiveness difficult. Provision of clean water in adequate quantities for 27,000 people as envisaged in the original proposal would be expected to cost in the region of $540,000 in a camp situation (at a unit cost of approximately $20 for a year). / 5.4 Did the project represent Value for Money : Y / DFID’s ability to comprehensively analyse cost effectiveness of humanitarian interventions in Northern Kenya and the ASAL region is extremely limited. A broad assessment of each agency’s ability to deliver effectively, economically and efficiently was made prior to funding recommendations. But an over emphasis on the economic unit cost metric of this assessment can give a misleading measure of value for money. / Whilst it may be possible to gain some measure of agencies’ efforts to keep costs down by looking at unit cost per output, there are a number of different ways to calculate this figure and no standardised methodology is available for partners to follow. A further limitation of this approach is that it can only be used to compare like with like; it cannot be used to compare across projects with different outputs and/or operating in different environments. If a standardised methodology is agreed and adopted it might be possible to develop a tool for assessing unit costs within an acceptable range for a given situation. This would form a useful part of looking at value for money performance. But it would still only give part of the picture of what defines value for money in a humanitarian intervention. / DFID defined Value for Money formally in July 2011 as ‘We maximise the impact of each pound spent to improve poor people’s lives’. To the extent that it is appropriate to apply an ex post facto definition to a 2010 programme, we can take the view that those agencies with a long-term presence in remote areas of Northern Kenya, a deep understanding of the context, and credibility with all the actors are best equipped to operate effectively and efficiently in this environment and hence are likely to represent the best value for money. / That being said, operating in remote and insecure regions of Kenya is always expensive. Essential operating costs (transport, security, personnel) are high and non negotiable (though some agencies pay more than others, for the general reason cited above). If agencies don’t budget enough for each output they risk not being able to deliver at all and risk their own safety in the region. Comparison of output costs with those from other programmes must recognise this. Efforts to develop networks of trust in order to operate effectively and safely take time and cost money. / DFID’s humanitarian programme in Kenya in 2010 can be said to have provided value for money in as much as awareness of the importance of these factors informed its funding decisions. DFID was aware of the difficulties of assessing value for money and was making efforts to sharpen its assessment of the economy, efficiency and effectiveness of programming.

6. Conditionality
6.1 Update on specific conditions / No conditionality was linked to this response

7. Conclusions
DFID’s 2010 humanitarian programme played an important contribution in meeting humanitarian needs in late 2010 and 2011 (especially timely given the spike in needs in 2011) but it did little to reduce the likelihood of future humanitarian needs. However there are some key learning points: / Although DFID responded swiftly and at scale to the crisis in 2010/2011 (the 2010 programme was particularly timely) more could be done to develop flexible funding mechanisms allowing partners to respond more rapidly to acute spikes in need. DFID could consider the improved value of multi year funding for agencies working in Kenya where acute humanitarian needs are likely to spike from time to time. Benefits would include: / Rent and transport costs fixed at a secure rate for a number of years rather than negotiated each year / No new start up costs / Good staff retained, reducing the need to retrain new staff each year / Gaps in programme averted – less likelihood of progress setbacks / Agency credibility with the local community increased / Security better for agencies staying longer term / The effectiveness of DFID funding DRR-type activities with short term funding is doubtful. It would be more effective to integrate DRR into longer term development programmes that can provide more predictable finance, but also more easily facilitate linkages and learning between field practice and evolving donor and Government policy. / Some of the outcome level indicators chosen for this programme (GAM rates) may not be most appropriate for short term emergency programmes. Lower level indicators may be needed at outcome level, which are more clearly within the control of the programme to influence. / Quality of results reporting and attribution to DFID has been uneven. Further work is required to encourage disaggregated data (gender and age) and clarify DFID attribution. / Efforts at promoting behaviour change on WASH seem to have limited impact in such short term programmes. Further analysis is needed regarding what actually works.

8. Review Process
In May 2012 DFID commissioned two consultants from Coffey International Development to review results of programmes and DFID’s approach to determining value for money in humanitarian programmes in Somalia and Kenya 2010 – 2012. The consultants spent 8 days in Nairobi (14 – 22 May) reviewing the project documentation of all agencies funded in 2010 and 2011 and interviewing a sample of programme managers across UN, NGO and Red Cross agencies. Interviews were also conducted with DFID and other donors - ECHO and OFDA (USAID). No field visits were undertaken. Evidence and data gathered from the review team plus agencies’ own reporting informed the review process. / DFID humanitarian advisors also provided significant input into the review and drafting process. / Whilst DFID advisors finalised this PCR (updating some of the results to reflect latest reporting and adding some additional qualitative assessment and reflections), the overall scoring has not changed compared to the original draft by the independent consultants.