Annual Review – post April 2018

Title: Annual Review 2017 – 2018 for the Strengthening Humanitarian Preparedness and Response (SHPR) Programme
Programme Value £ (full life): £175 million (spend so far is £68 million)		Review Date: 1 July 2017 – 31 March 2018
Programme Code: / 205268	Start Date: 1 June 2016	End Date: 31 March 2021

Summary of Programme Performance
Year	2016/17	2017/18
Programme Score	A	A
Risk Rating	Minor	Major

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5887625.odt
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/12772946.xlsx

A. Summary and Overview

Description of programme

Background

The Strengthening Humanitarian Preparedness and Response (SHPR) programme aims to improve Bangladesh’s disaster preparedness and assist affected populations with immediate support following extreme event that cause humanitarian emergencies. The programme also addresses the humanitarian needs of Rohingya refugees from Burma and vulnerable host communities in the south-east of Bangladesh. This review covers the 9 month period from July 2017 to March 2018 as the required information was not available to report for the period of April to July 2018 when the review was undertaken.

Responding to the Rohingya crisis

The SHPR was designed to provide predictable humanitarian relief and disaster risk reduction. However, the review period was a very challenging period for the SHPR Programme. It saw the influx of over 700,000 Rohingya refugees fleeing violence in Northern Rakhine in Burma. This created significant pressure on the programme team, our grant administrator and the partner organisations. The influx of the refugees also led to a shift in the implementation strategy as the programme had to focus on, and respond to the immediate needs of the Rohingya and host communities. This shifted the balance of programme implementation from pillar 1 and 2 to pillar 3 (see below further detail on these outputs). The programme had to rapidly ramp up to respond to the unprecedented crisis and additional funding was provided at scale, which led to two large cost extensions. The programme has therefore changed significantly since the last review.

Financial extensions

The SHPR Business Case was approved in 2016 with a budget of £35 million over five years. Since the programme’s last annual review, the business case has been amended three times (but only twice during this review period). The first amendment increased the overall spend by £25m (including £10m due to a high number of natural disasters and £15 million to respond to the start of the Rohingya crisis). The second two £25m (within this review period) and £20m respectively (after this review period) were undertaken to support the increased humanitarian needs of Rohingya refugees and host communities. Following this, another addendum has increased the programme spend by £70m (approved April 2017) to further respond to the Rohingya crisis to fund the underfunded Joint Response Plan. Hence, the total budget has increased from £35m in 2016 to £85m up to March 2018 and now £175m in August 2018.

The programme has three main areas of work:

- Pillar 1 – Preparedness. Up to £7.9 million over the life of the programme has been allocated to a joint United Nations (UN) and civil-society programme managed by the United Nations Office for Project Services (UNOPS). Combined these components will strengthen disaster preparedness and help to significantly reduce the cost of disaster response;
- Pillar 2 - Humanitarian response. £28 million, over the life of the programme up to £10 million has been allocated to a consortium of non-governmental organisations (NGOs), the Start Fund, to provide rapid and life-saving assistance to disaster affected communities; In addition, a pre-approved Emergency Response Fund of £18 million that enables DFID Bangladesh to respond fast and flexibly in the event of a major crisis in Bangladesh that exceeds national coping capacity.
- Pillar 3 - Rohingya refugee and host community support. Up to £165.8 million over the life of the programme has been allocated to UN agencies and NGOs to help address the urgent needs of Rohingya refugees and the vulnerable Bangladeshi communities that host them;
- Additionally, fund management costs including monitoring and evaluation of £3.8 million over the life of the programme.

Summary supporting narrative for the overall score in this review

The programme received an A rating during its annual review last year, which indicates that it fully met expectations. This year has been much more about direct delivery, which required revisions of the log frame. This has been an extraordinary year for Bangladesh and natural disasters and the Rohingya influx and impacted SHPR significantly. A number of fast paced, but appropriate, decisions have been made to achieve the outcomes outlined in the Theory of Change. Partners and the fund manager have had to be flexible to adapt to these frenetic changes.

This year, the SHPR scored an A again during the review period. Noting the major focus on Rohingya response and the effect this had on work, all components SHPR demonstrated satisfactory results as planned. The Rohingya refugee crisis has meant that the programme has delivered a different set of activities to deal with this unprecedented humanitarian crisis and several new indicators have been added. For these new indicators, some of the milestones are yet to be set since these need detailed discussions and agreement from implementing partners. However, where possible (which was in most cases) we have used partner’s work plans and proposals to draw milestones from.

There have been some exceptions in meeting expectations particularly in output 1; the National Resilience Programme has not taken off the ground mainly due to approval processes. Some challenges around setting up Humanitarian Staging Area have also been a barrier to output 1 fully meeting expectations. That is why Output 1 has scored B.

To note we have also reviewed the impact weighting since the last annual review based on major changes to context, namely the focus on output three (now 50% impact weighted) due to the Rohingya crisis and the sudden uplift in funding this caused. DFID and UNOPS agreed a new log frame as a reporting tool for this review to ensure that delivery of the Rohingya response (Pillar 3) could be incorporated into the report fully as it constitutes the biggest part of the programme.

Summary supporting narrative for the overall score in this review

We have scored the programme an A for this year, as it has fully met expectations during a challenging and frenetic time. It has responded to two floods, one landslide and one cyclone. The successful inception of Start Fund has also been a key achievement. For pillar three on the Rohingya specifically, we have reached targets, in line with the JRP, and provided consistent and coordinated support. For example, the UK has provided food assistance for up to 300,000 people, either through direct food items, e-voucher or cash transfers systems, and safe drinking water and emergency latrines for more than 280,000 people.

Pillar 1: Preparedness

The score for this output is justified by the fact that good progress has been made in increasing and catalysing humanitarian coordination mechanisms, including strong activity around strengthening the Inter Sector Coordination Group (for the Rohingya response) and Humanitarian Coordination Task Team (for national coordination). A number of assessments were also conducted as 2017 saw 2 major floods, a tropical storm, landslides and the Rohingya crisis. As per the Gender Equality Act, SHPR business case has built in specific indicators such as capacity building of female enumerators, inclusive design tools for assessments to capture gender desegregated needs. Under pillar 1, the National Resilience Programme has specific indicators to address women’s and children’s inclusion in disaster preparedness.

Two of the indicators (developing the National Resilience Programme and Humanitarian Staging Area) were not met in this output, however we feel that this remains at a B overall because both of these indicator’s delays are related to hold ups due to higher level decisions related to land allocation, inter-ministerial working arrangements and needs meticulous considerations for final decision. There are lessons here about considering risks around these processes more actively at the design phase. Additionally, going forwards further assessment may be needed to evaluate whether resource would be better spent elsewhere than on these two indicators.
Critical sector clusters (that we assessed in the Business Case as the most important) have been supported and invested in to a standard that the team feel met expectations, namely:
- Logistics cluster
- Food Security cluster
- Nutrition cluster
- WASH cluster

Pillar 2 - Humanitarian response

In terms of output 2, the Emergency Response START fund has responded to four disasters during the review period. This has exceeded the anticipated target for the year. ERRF was also activated thrice to support two floods and one cyclone and a tropical storm (Mora). The activities planned during the review period met expectations and thus Output 2 has scored A.

We assess that partners have met expectations on this output and in some cases have exceeded targets set in their proposals so have scored this an A. All emergency response narrative reports also reported gender and age disaggregated data. Gender specific targeting strategies have been developed by agencies in their emergency response funding proposals.

There is one indicator around beneficiary/ programme participant accountability in this output which we need to review. UNOPS are currently counting the number of complaints rather than assessing a more meaningful target like the timeliness for responses or the number or appropriate responses will this with them this year.

Pillar 3 - Rohingya refugee and host community support
This is the output is for the Rohingya crisis where a vast amount of the work on the delivery of this programme took place within the review period. We assess this is an A score as downstream partners met expectations by reaching most targets in their proposals and exceeding them in some areas. They also adapted quickly to the extraordinary circumstances of the crisis.
There is a question we need to explore with UNOPS on how objectively we can say that partners met expectations on some of these targets as some targets were set before the uplift in funding for the Rohingya crisis. Following these two uplifts in funding we are reviewing milestones and make them more challenging. We also need clarity in some areas as to whether the original targets were set for the review period specifically or for the four year programme.
Recommendations for the year ahead

Programme implementation changed focus to respond to the emerging needs and has adapted. At times, the overall monitoring process struggled to match the pace of the crisis (for the grant administrator UNOPS). UNOPS acknowledges that the slow adaptation of the logframe meant that the monitoring of the project did not adapt to the changing context as quickly as it could have, and will take this forward as a lesson and action for the coming year of the programme. Over the coming year DFID and UNOPS will invest in M&E, including by DFID investing in M&E support for the programme, and considering external evaluation. We will also work on the triangulation of methodologies of evaluation to determine and leverage programme quality at scale and across partners.

The fund management mechanism was not originally designed for rapid large scale emergency response, and the recent experience with Rohingya refugee response required us to revise and modify the modalities of grant management and monitoring to drive better value. This includes:

- Greater accountability of fund management.
- Revised respective roles and responsibilities of DFID and UNOPS for the Rohingya response.

DFID identified a need to take a more targeted and prioritised approach to partner management. DFID has now taken four partner agreements in house rather than use our delivery agent.

Partners had varying reporting periods which made it difficult to compile reports for a specific reference period. UNOPS and DFID will need to work on aligning the reporting periods this year for all its partners so that partner reports are for a similar reference period for easy compilation.

Data collection on disabilities has also been challenging. Partner reported that the Washington Group Principles are challenging for enumerators to use. UNOPS and START fund discussed the issue with DFID. DFID has planned to convene a special meeting with results adviser and partners to understand the challenge and develop strategy to address the issue by December 2018.

Partner reports did not have an adequate analysis of why certain achievements were over and achieved. This meant that UNOPS could not have an in-depth analysis of the variances. Challenges were encountered on getting feedback from partners on queries relating to the variances and in some cases no follow ups were made. UNOPS proposed an update to the reporting template to ensure that variance analysis is conducted for each indicator which DFID has accepted.

Moreover, DFID needs to increase coordination with other donors, look at longer term approaches with them and design a new business case to meet both the need to fund the underfunded JRP and the longer term strategy for supporting the Rohingya and host communities.

Some output specific lessons are included below.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Government of Bangladesh and humanitarian groups have increased understanding and capacity to prepare for disaster and climate change related events
Output number per LF		1	Output Score	B
Impact weighting (%):		30	Impact weighting % revised since last AR?	Y ↓

Indicator(s)	Partners involved	Milestone(s) for this review	Progress
Level of institutional / Knowledge of climate change issues as a result of ICF support. (ICF KPI 14)	NRP-UNDP	Not set (No milestone was set for 2017 as baseline figures had not been collected. The programme to collect baseline figures to estimate )current levels and set milestones	Achieved: 0 / Delays in getting Government of necessary approvals for the National Resilience Programme limited the achievement of this target.
1.2 Number of humanitarian coordination mechanism established and operational in accordance with IASC guidelines	UNRC	This is a new indicator in the log frame.	During the reporting period monthly HCTT meetings were held from Sept-Nov 2017. Rohingya crisis disrupted the regular meetings in Dec. However, inter-cluster meetings were arranged. It is noted that the frequency of meetings on the Rohingya crisis increased significantly from end Aug 2017 and onwards. The UNRC has helped facilitate the coordination structure for Rohingya-related interventions which has been endorsed by the GoB. The Resident Coordinator Office (RCO) participated in all Inter-Sectoral Coordination Group (ISCG) and the Strategic Executive Group (SEG) meetings were organized at during the review period, the ISCG coordination mechanism was also directly mechanisms were supported with DFID funding.
1.3 Number of cluster mechanisms established for disaster preparedness and response in accordance with IASC IASC guidelines (disaggregated by types of mechanisms (i.e. cluster meetings, support in advocacy and resources mobilization, effective coordination and information-sharing amongst the different sectoral groups)	UNICEF/WFP-JDPP, / UNRC-JDPP, / MAF, / CARE	This is a new indicator. The measurement of this indicator and milestones will be developed and agreed with implementing partners in 2018	The following clusters are being supported by DFID funding: / Logistics cluster / Food Security cluster / Nutrition cluster / WASH cluster
1.4 Number of gender sensitive disaster assessments accessible to humanitarian actors leading to timely response	CARE, / NRP-UN Women, / NRP- UNDP	2	Exceeded. 6 gender sensitive disaster assessments were completed for 4 major emergencies: Haor Flood, Cyclone Mora, Chittagong Hills Tract (CHT) Landslides and Monsoon flood. Although the partner had planned for 2 assessments, during the year there were 6 assessments for the 4 hazards that were encountered.
1.5 Number of people trained on coordination and assessment methodologies and equipped with gender sensitive tools (disaggregated by sex and humanitarian actors)	UNICEF/WFP, / CARE, / WFP FSC, / WFP LC, / UNICEF-WC, / UN ICEF-NC	60 (2 trainings identified in workplan	60 / 2 earthquake simulation exercises conducted by WFP for the MoDMR and the Department of Disaster Management (DDM) officials.
1.6 Emergency stocks prepositioned to high risk areas for a number of people	UNICEF WC (JDPP), / UNICEF NC (JDPP), / UNICEF CP	11,500 where this target came from)	Stock for 11,500 people has been prepositioned to high risk areas.
1.7 Progress towards establishment and operationalisation of Humanitarian Staging Area (HSA) in country	WFP	Not set. There was no milestone set for 2017; however during the first quarter of 2018, the partner has completed key activities that were part of their milestone for 2018.	There has been a delay in meeting this indicator due to delays in identifying land by GoB. This includes the finalization of land selection criteria, conceptualization of HSA and assessment of potential two lands, drafting of TOR for HSA steering committee and also have had high level meetings on the matter of land for HSA.
1.8 National Accountability Mechanism (NAM) established and operational for improving humanitarian architecture	SHPR	This is a new indicator	Achieved: The programme delivery responded to needs by shifting from covering accountability only of projects under SHPR to supporting the humanitarian architecture in establishing a national humanitarian accountability mechanism. Milestones and measurement of result will be agreed with partners in 2018.

Provide supporting narrative for the score

This output has scored B (which means that the programme has not fully fulfilled expectations). Performance on coordination mechanisms has been strong and helped with the Rohingya crisis and in creating strategic coordination across donors and agencies. Critical sector clusters that we assessed as the most important at the design phase have also been formed:

•	Logistics cluster
•	Food Security cluster
•	Nutrition cluster
•	WASH cluster

However, three indicators have not been met, five have been met during the programme and one was exceeded for gender sensitive needs assessments. Of the three indicators that were not met there were aspects of the delivery of these milestones that were beyond the control of the delivery partner in the large part.

For ICF, the partners are currently waiting for the correct approvals before the National Resilience Programme can be up and running. The Humanitarian Staging Area faced delays to approvals of land and internal challenges for the delivery partner. In addition, planned activities on ‘Beneficiary Accountability Mechanism (BAM)’ were also not possible to execute in the time frame, and a decision has been made to scope out a new appropriate accountability strategy.

The score for this output is justified by the fact that good progress has been made in most areas, and in particular in increasing and catalysing humanitarian coordination mechanisms.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lessons:

- SHPR’s existing contribution to strengthening the clusters and setting up the ISCG has provided a strong base to scale up emergency response in Cox’s Bazar after the influx in August 2017. All national level clusters immediately mobilised their staff to support the crisis by sending staff and sharing experiences.
- The existing ISCG coordinator (now ISCG secretariat manager) and team played a crucial role in bringing institutional knowledge and local context. In spite of ambiguity around proper coordination and leadership, the ISCG platform provided a space to continue and scale up emergency operations within a week.
- The Rohingya refugee influx in 2017 had a major impact in ongoing preparedness activities at national level. Cluster meeting attendance declined and participation at different coordination meetings was low. The reasons are mainly due to the heavy engagement on the Rohingya response and lack of staff/ resources within partner agencies to cover multiple humanitarian activities.
- National Resilience Programme’s approval process took longer than expected.

Recommendations:

- DFID to work with NRP partners to formulate a time bound plan to address the delay and develop a realistic target for rest of the programme duration.
- UNDP, UNWOMEN and UNOPS to follow up with DFID on a regular basis (preferably monthly) to update on possible start date for National Resilience Programme.
- DFID to follow up with WFP by August 2018 on the final decision of selecting location/ land for establishing HSA. In case of useful advocacy, DFID may flag the importance of HSA to different level with government if requested by agencies if useful to secure land/ facilities.
- DFID and UNOPS to work together to scope out the strategy for National Accountability Mechanism by October 2018.

Output Title	People affected by disasters have access to assets, basic services, livelihood and safety nets to help them absorb stresses and recover from shocks
Output number per LF		2	Output Score	A
Impact weighting (%):		20	Impact weighting % revised since last AR?	Y

Indicator(s)	Partners	Milestone(s) for this review	Progress
2.1 Number of people receiving humanitarian assistance-food aid, cash and voucher support	ACF / Caritas / BRAC / SCI / OXFAM / PLAN / Start Fund Bangladesh	Planned-ERRF: 259,776 / Planned-Start Fund: 93,150	Achieved-ERRF: 279,804 / ACF, BRAC, Caritas and SCI submitted change requests because they had made savings due to exchange rate gains and lower unit costs. (Reported till May 2018) / Achieved-Start Fund: 90,813
2.2 Number of disaster-affected people receiving other forms of support	FAO / ACF / SCI / BRAC / OXFAM / Plan / Start Fund Bangladesh	Planned-ERRF: 308,390 / Planned-Start Fund: 27,860	Achieved-ERRF: 324,165 Oxfam, BRAC and Plan submitted change requests with increased targets on WASH. (Reported till May 2018) / Achieved-Start Fund: 32,382
2.3 Number of beneficiary complaints/feedback received and effectively addressed.	Caritas / BRAC / SCI / OXFAM / PLAN	Planned: 90	Achieved: 90 (reported till April 2018)

Briefly describe the output and provide supporting narrative for the score

We assess that partners have met expectations on this output and in some cases have exceeded targets set in their proposals, so this output has scored as A. The Emergency Response START fund has responded to four disasters during the review period. This has exceeded the anticipated target for the year. ERRF was also activated thrice to support two floods and one cyclone and a tropical storm (Mora). Based on the decision to respond for all emergencies, all targets were achieved according to plan.

During the review period, the first amendment to the business case increased the ERRF funding pot by £10m given the unexpected number of natural disaster occurred in 2017. This output represents SHPR’s Pillar 2 focusing on timely response to small and medium size disasters. Based on the coordination and assessment activities (reflected under output 1), these mechanisms consistently responded to disasters to meet immediate and in the medium-term needs of effected populations.

Lessons identified this year, and recommendations for the year ahead linked to this output

- START Fund to develop a plan to address the learnings from lesson learnt workshop by August 2018.
- DFID and UNOPS to work together on ERRF structure and promote the mechanism as a credible emergency response and recovery mechanism to other donors.

Output Title	Rohingya refugees and host communities have access to assets, basic services, livelihood and safety nets to help them absorb stresses and recover from shocks
Output number per LF		3	Output Score	A
Impact weighting (%):		50	Impact weighting % revised since last AR?	Y ↑

Indicator(s)	Partners	Milestone(s) for this review	Progress
Number of affected Rohingya refugees and host communities reached with humanitarian assistance (food aid, cash and voucher transfers) through DFID support	ACF-CINGOs, / ACF Phase I, / ACF Phase II, / ACF Mora, / WFP Joint UN Rohingya, / WFP Phase I, / WFP Phase II, / Oxfam Phase II, / UNFPA Phase II	Planned: 1,157,149	Achieved: 1,166,541 (101%) This indicator was on track.
Number of affected Rohingya refugees and host communities with access to clean water and/or sanitation through DFID support	Oxfam Phase II, UNICEF Phase I, / SCI Phase II, / UNHCR Phase II, / ACI Phase I, / SI Phase II, / CA Phase III, / HelpAge Phase III, UNICEF Phase III	Planned: 852,680	Achieved: 1,098,984 (128.9%) / The programme improved access to water by installation of tube wells and provision of water. It also constructed and dislodged latrines, provided washing cubicles and hand washing points for the communities. Most of the partners achieved their targets and only Unicef and Oxfam overachieved. An analysis of the reports did not give full information on why there is a close to 29% overachievement. For future reports, SHPR will request variance analysis from all its partners so that over and under achievements could be satisfactorily covered.
Number of affected Rohingya refugees and host communities receiving NFI/shelter assistance	UNHCR Phase I, ACF Phase I, UNHCR Phase II, IOM Phase II, / SI Phase II, Handicap Phase III, Helpage Phase III	Planned: 698,605	Achieved: 693,325 (99.24%) / Rohingya refugees and host communities received shelter/NFI kits, which included core relief items and temporary shelter (tarpaulin). In addition, IOM provided disaster resilient shelter awareness training to Rohingya refugees and host communities. All agencies except Solidarites met their targets, during this period they only managed to conduct needs assessment but had not provided any support during this period.
Number of affected Rohingya refugees and host communities receiving nutrition services	WFP Joint UN Rohingya, / SCI Phase II, / ACF Phase I, UNICEF Phase II, UNHCR Phase II	Planned: 393,262	Achieved: 580,850 (147.5%) / As part of nutrition the programme provided food assistance, hot meals and therapeutic feeding. Nutrition support also included food assistance to 6-23 months old children from host community, pregnant and lactating women (PLWs). Acute malnutrition screening conducted for 0-6 month old infants on a monthly basis and admitted to community management of at risk mothers and infants service centres. WFP, ACF, UNICEF, overachieved on their set targets. ACF had targeted 18,560 people to receive hot meals per day but they reached 50,978 people due to the demand for hot meals in the camps. The continued influx of the Rohingya refugees created more demand for services.
Number of affected Rohingya refugees and host communities receiving emergency health care	IOM-Phase II, / ACF Phase III, / SCI Phase II, / CA Phase III, / HelpAge Phase III	Planned: 114,856	Achieved: 203,431 (177%) / Health package included antenatal care and post-natal care as well as sexual and reproductive health and mobile health services, screening and referral of older persons. The demand for health services due to the influx led to the overachievement of this indicator. The planned targets have been exceeded for health services funded under the Phase II allocation. SCI conducted 27879 consultations against the planned target of 13500. 342 pregnant women received comprehensive antenatal care visits against the planned target of 150. IOM reached the planned target of 25000 individuals reached with emergency health services and referrals supported.
Number of affected Rohingya refugees and host communities with access to safe community level infrastructure	IOM Phase II	Planned: 675,000	Achieved: 697,130 (103.2%) / The partners upgraded roads, rehabilitated drained, reinforcing steps, slope protection. This indicator's achievements were within the planned.
Number of affected Rohingya refugees and host communities children with continued access to education	UNICEF Joint UN Rohingya	Planned: 1,771	Achieved: 11,658 / UNICEF provided early learning and non-formal basic education. UNICEF achieved 658% of the target in providing access to education to the affected Rohingya refugees and host communities by introducing additional shift per classroom thereby increasing the capacity of learning centres.
Number of affected Rohingya refugees and host communities receiving GBV and SRH services	UNFPA Phase II, / UNFPA Phase III, / UNHCR Joint UN Rohingya, / CA Phase III	Planned: 163,950	Achieved: 206,287 (125.8%) / Services provided under this indicator were referrals, midwife care, survivor’s cases and healthcare and GBV care. UNFPA and UNHCR have achieved 125% of the target. UNFPA delivered services through clinics and women and girls received midwifery care and SRH services.
Number of affected Rohingya refugees and host communities receiving protection services	UNICEF UN Joint Rohingya, / UNHCR UN Joint Rohingya, / ACF Phase I, / UNICEF Phase I, / Oxfam Phase II, / SI Phase II, / UNHCR Phase II, / UNFPA Phase II, / UNFPA Phase III, / ACF Phase III, / CA Phase III, / HelpAge Phase III, / Handicap Phase III, / IOM Phase III, / Oxfam Phase III, / UNICEF (CP) Phase III	Planned: 366,629	Achieved: 492,946 (134.5%) / ACF and UNICEF provided psychosocial first aid to adults and adolescents, play sessions to ease stress and trauma for children<16y and established child friendly spaces (CFS) reaching 34,019 children. Through Phase II, UNICEF supported 20,523 children to learn and adapt protective behaviours in settlement environments, Solidarities International sensitized beneficiaries to protection risks. Through UNFPA, 18,135 refugee women and girls have accessed Women Friendly Spaces (WFS).UNHCR and UNICEF supported adolescents through life skill based education, establishment of community-based child protection centres and supported SGBV survivors with appropriate assistances. Adaptation of implementation strategy led to the overachievement of this indicator for example ACF had to use group rather than individual sessions to reach more children with art therapy.
Number of affected Rohingya refugees and host communities trained on community-leadership and decision making	UNHCR Joint UN Rohingya	Planned: 114	Achieved: 285 (250%) / The targets were set during the initial programming when the situation was stable but demand increased due to the influx of the refugees.
Number of affected Rohingya refugees and host communities with livelihoods assistance to help them cope with and recover from disasters	WFP Joint UN Rohingya, / UNHCR Joint UN Rohingya	Planned: 4,931	Achieved: 1,965 (39.9%) / There has been slow implementation of livelihoods activities especially during the emergency phase. Review of partner reports did not provide adequate information on this and UNOPS will follow up with partners on this issue.
Number of beneficiary complaints/feedback received and effectively addressed.	IOM Joint UN Rohingya, / WFP Phase I	Planned: 210	Achieved: 260 (123.8%) IOM and WFP set up a mechanism to receive complaints from the community. Systems put in place include complaints boxes. IOM received a total of 172 complaints and solved 103 of them satisfactorily while 60 of the respondents did not provide any feedback. The programme does not have overall control on the number of complaints provided but it uses this as a proxy to identify the communication channels between community and the programme.

Provide supporting narrative for the score

This output is for the Rohingya crisis where the funding allocation was rapidly scaled up from £5m (over four years) to £54 million to be spent within 12 months within the review period. The number of implementing partners also increased. We assess this output as scoring an A as downstream partners met expectations by reaching most targets in their proposals and exceeding them in some areas. They also adapted quickly to the extraordinary circumstances of the crisis. Due to the changing context, SHPR’s logframe was readjusted to include this output since the allocation spiked through this pillar (referred as Pillar 3 of SHPR) following the influx of Rohingya refugees in August 2017. SHPR business case was scaled up with cost extensions to provide urgent humanitarian assistance to Rohingya refugees and directly affected host communities in Bangladesh, enabling continuity of services as well as initial investments in more sustainable protracted crisis approaches.

The key sectors for support included food security, nutrition, health, shelter, water, sanitation and hygiene and protection. The support was aligned with the inter-agency Rohingya Crisis Joint Response Plan. The output indicators reflect the level of support provided to the sectors and the people reached. DFID provided support via UNOPS to the UN agencies (UNHCR, WFP, UNICEF, UNFPA) and International NGOs (ACF, Solidarities International, Oxfam, Save the Children) and contributions to the ICRC and IFRC appeal. DFID also provided in kind support of Shelter kits through IOM and support to the Diphtheria outbreak in the camps. Major factors in some indicators partially meeting targets have been delays in receiving approvals, staff recruitment. Under Phase 2, a number of agencies had requested time extensions to be able to achieve their targets. DFID also provided surge humanitarian advisory support, information management support, expertise in shelter, protection, preparedness and public health in emergencies. DFID also funded a number of experts deployed to the UN agencies via the standby partnership agreement.

Lessons identified this year, and recommendations for the year ahead linked to this output

There is a question we need to explore with UNOPS on how objectively we can say that partners met expectations on some of these targets as some targets were set before the uplift in funding for the Rohingya crisis. Following these two uplifts in funding we are reviewing milestones and make them more challenging.

We also need clarity in some areas as to whether the original targets were set for the review period specifically or for the four year programme. Going forwards for the new allocations we will take a much more targeted approach to M&E, including by commissioning an M&E adviser.

Moreover, we need to increase coordination with other donors, look at longer term approaches with them and design a new business case to meet both the need to fund the underfunded JRP and the longer term strategy for supporting the Rohingya and host communities.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

An existing protracted crisis component was originally designed to flex in support of up to 34,000 refugees and host communities in long term Rohingya affected areas of Bangladesh. Escalation of the conflict in Rakhine State, led to the rapid influx in August 2017 of an unprecedented 670,000 new Rohingya refugees. The existing SHPR facility provided an important funding mechanism and, existing partner network, to rapidly scale up in response to this new international humanitarian crisis. The original business case has increased from £35m to £105m and, is expected to increase by the end of July 2018. The logframe has been revised accordingly to reflect new results numbers.

The significant change in context requires the Theory of Change be revised. This process will identify the existing value of what people vulnerable to disasters are already doing to build their own resilience. It will also identify, reflect and build on the change aspirations that disaster prone social groups have for themselves.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

The programme has been on track in 1) strengthening national level disaster coordination 2) timely support to vulnerable populations and 3) disaster preparedness. The UK was one of the leading and timely responders to natural disasters and Rohingya crisis in 2017. Bangladesh exceptionally experienced multiple natural disasters including 2 major floods, 1 landslide and 1 cyclone. Both the Start Fund and ERRF allocated funds appropriately. The scale and urgency of the Rohingya response meant that support to education, livelihood and resilience were reduced.

There have been delays with progress of the NRP due to an unrealistic start date. Partners are confident that this can be addressed going forwards with a revised work plan and strategy. They will be requested to provide a strategy and monthly updates on this. WFP has 1) finalised concept design 2) land selection criteria 3) engaged its leadership to negotiate with government and 4) presented the plan at a high level ministry event.

Changes, Measures taken

2 addendums driven by new and additional Rohingya crisis response needs have been made in the reporting period. UNOPS as the original fund management and monitoring partner has been challenged by the rapid scale up. Based on partner consultation, DFID is playing a more direct complementary role, in monitoring and partnership management, for the Rohingya component.

Explain major changes to the logframe in the past year (1/2 page)

DFID worked with UNOPS to revise the logframe in view of 1) changes in context 2) revised DFID Guidelines on Logframes 3) greater coherence with the Theory of Change in the Business Case 4) Outcomes, Outputs and Indicators were further developed and revised in line with the last Annual Review recommendations. See further information on this at Annex A.

Describe any planned changes to the logframe as a result of this review (1/2 page)

DFID will further develop its medium and long term humanitarian funding strategy for the Rohingya and host population response. This may result in changes to the logframe and the current Business Case design.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

Key cost drivers and performance

UNOPS: The principal costs identified in the business case were administration fees, staff salaries, travel and overheads. While the exchange rate fluctuation was identified as the main cost driver in the business case, it has not yet had any major implication on the programme. Other costs have been the implementing partner’s costs which have included administration fees, staff salaries, travel and overheads as well as input related costs, e.g. the cost of procuring food commodities for Rohingya refugee interventions. DFID scrutinised all costs prior to agreeing to the proposal.

Start Fund Bangladesh: Principal costs were administration fees, staff salaries, travel and overheads for Start Network’s management of activities delivered by the fund’s members. Other costs include the grants for relief activities.

For responses delivered through ICRC and IFRC the key cost drivers have been the same as above and DFID provided support to their appeal. The key cost drivers for the diphtheria response has been staff, medical treatment and hospital set up costs. The key costs for the shelter kit deployment have been actual costs of the kits and transportation. Costs for surge staff have been fees, allowances and travel and accommodation.

Economy

During the review period, all budgets from delivery partners were scrutinised at two levels: first by UNOPS followed by DFID to ensure unit costs are reasonable and competitive based on market prices. Both teams have scrutinised detailed budget line to match with expected outcome. By contract, UN agencies/ NGOs must monitor downstream partners’ VfM. The existing DDA with implementing agencies ensured the capacity for doing so.

For all emergency response, humanitarian community follows standards agreed at Humanitarian Coordination Task Team (HCTT). DFID supported staffs at humanitarian clusters facilitate NGOs and UN to comply with the standards. However, for Rohingya response, the urgency for scale up and making most out of market availability and accessibility; standards were not harmonised until all sectors became active. DFID deployed experts based in Cox’s Bazar to regularly follow up on different costs with partner to emphasize on economical approach.

Shelter kits were deployed from the warehouse in Delhi (India) which led to lower transport and transfer costs than from Dubai or other further warehouse locations. For the emergency responses, the inputs were locally sourced where markets were functional.

In the Start Fund, particularly in the project selection phase of the alert process, vfm is ensured by utilising local experts within Bangladesh context to take decisions. The review process requires going through financial proposal analysis and rigorous comparison with similar proposals submitted by multiple parties. The selection process is recorded and publicly available to ensure transparency and credibility of the process.

Efficiency

During the review period all three pillars/ areas of SHPR’s activities showed efficiency in terms of quality programme delivery. Investment made through joint Disaster Preparedness Programme and SUBARNA deployed their experts immediately after the Rohingya influx. They have complimented DFID’s other investment through Joint Rohingya Programme for effective coordination (e.g. ISCG). Although the agencies deployed internationally experienced staffs to support the sector coordination at Cox’s Bazar; the initial support provided by national clusters (such as Food Security, Nutrition, Logistics and WASH) avoided starting coordination from scratch. SUBARNA colleagues, who works as secretariat of country’s joint needs assessment process shared whatever tools and capacity available at national level for assessment and analysis.

Partners have demonstrated capacity and experience of delivering support in the emergency refugee context. Rapid scale up and funding availability ensured immediate life-saving needs were met. Partners have made efforts to transform input into quality outputs by engaging trained staff and using local volunteers, increasing the involvement of communities for better delivery and adjusting to needs and the changing context of beneficiaries.

In a number of Rohingya refugee response projects, partners’ access, coordination ambiguity and delay in securing the FD7 permits by downstream partners impacted on efficiency in the delivery of services to beneficiaries. Certain inputs such as staffing may already be there but procurement of goods and actual delivery to beneficiaries had to be put on hold while waiting for government approvals. This was particularly true in the Rohingya response as well as ERRF responses of a number of INGOs. Joint effort between DFID, SHPR Fund Management Office and the INGO IPs is suggested to dialogue with the NGO Affairs Bureau to facilitate smooth and speedy review and action on FD7 requests. Most of the Rohingya response Phase II projects have sought time extension to be able to complete activities.

Although it was the first year for both START Fund Bangladesh and ERRF mechanism, both funding mechanism proven to be widely accepted processes by partners. Especially START responses to four disasters were highly appreciated as effective response mechanism in terms of transparency and speed during learning and sharing event.

Effectiveness

In the preparedness Pillar most of the outputs have been met except for the National Resilience Programme due to Government of Bangladesh approval delays and the set -up of the HSA due to the delay in allocating land. It is early to measure the effectiveness of the preparedness pillar as it is only a year since the activities started. For the Rohingya response and the ERRF projects the effectiveness of the projects is tangible as they are providing humanitarian response support and also addressing several Grand Bargain Commitments (e.g. Cash, Joints Needs Assessment etc.).

Cost-effectiveness

For Pillar 1 and the coordination aspects of Pillar 3 (IOM led ISCG coordination), the cost-effectiveness will be determined when we measure the impact and outcomes of SHPR as articulated in the logframe. Pillar 1 impact cannot yet be determined at this stage but Pillar 2 and 3 are already able to show some results in terms of providing life-saving support to people hit by disasters. The programme is currently in the process of computing the cost per beneficiary for ERRF. Through the UNICEF programme, it has been reported that the number of children targeted has been reached by the project and children receiving psychosocial support and adolescents following their targeted programme have demonstrated positive change. This has been possible by the introduction of additional shifts into learning centres; Education was able to reach twice the number of children without exceeding the initial budget limits.

As the programme significantly expanded through Rohingya Response, specific rationale was provided to seek HMT consent. Rationale for the Rohingya response allocations were:

- A multi-sector approach because people need all sectors to survive;
- Influence the wider system by having a stake in all sectors;
- Proportionately fund more protection to support women and girls in line with UK policy;
- Operate through a number of partners to spread the UK’s risk.

We have developed three levels to our approach to Value for Money in this context:

Strategic (Upstream) – Through the UN’S Joint Response Programme (JRP) and broader strategic engagement we continue to build a system of coordination. Alignment with the JRP and other donors offers more efficiency as we are able to quickly identify needs and gaps, duplications, and operational challenges and improve targeting. Without coordination centred on the JRP we risk overlap loss of sectoral synergy (e.g. in health services).

Operations (mid-stream) – We operate using DFID’s VFM policy throughout the funding operations of this allocation. Investment in operations is integral to achieving Value for Money and delivering focused and timely programmes. We are actively reviewing the operational delivery of the funding within this allocation. As part that we are identifying the trade-offs of plans to bringing some the grant administration in-house, removing significant grant administration costs. The larger the amounts we give to UN agencies, the more scope they have to create economies of scale (unit costs) through their pipeline. We are also proposing to give not-earmarked contributions to some agency when we have confidence in that agency and their ability to prioritise, which is also consistent with our humanitarian policy and our institutional assessments with those agencies.

Delivery (downstream) – Within this allocation we will uphold our commitments to The Grand Bargain which aims to enhance costs effectiveness though increased localisation and collaboration (e.g. more joint assessments and reporting). The response is applying principles of good practice that deliver both value and quality outcomes. Most NGO staff in Cox’s Bazar are Bangladeshi nationals and the vast majority of food, shelter material and non-food items are being procured from the local markets and latrines are locally constructed. Some items have to be imported where these are unavailable locally or not of sufficient quality.

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

Overall risk rating: Major

Overview of programme risk and actions for mitigation:

The risks identified in the last Annual review are included in the programme risk register and are reviewed monthly at partner meetings. Delivery Chain mapping of all implementing partners has been conducted, and risk and controls associated at each tier of delivery are mapped through the Delivery chain risk mapping exercise. This exercise enabled DFID to understand funds flow from DFID to the downstream project partners and risks associated with each level/tier or funds flow and controls mechanisms. The risks identified were:

- Poor performance by implementing partners: DFID has regular meetings with UNOPS and the Start Fund Bangladesh to discuss progress, challenges and manage any issues arising. DFID and UNOPS are reviewing what should be improved and to clarify on roles and expectations. KPIs are being developed for measuring partner performance.
- Number of emergencies requiring response drains the Start Fund Bangladesh and the ERRF: This risk will is closely monitored and action will be taken as appropriate. DFID has recently approved (outside the review period) additional funds to replenish the ERRF.
- Approvals for response interventions are not granted in time to undertake the work: DFID will liaise with concerned implementing partners and provide letters of support to expedite approvals.
- Grant mismanagement: DFID has communicated its zero tolerance to fraud, bribery and corruption to all partners in the programme. This is also included in the agreements with partners. DFID reserves the right to withdraw funding if the grant management clauses are not followed appropriately. DFID is also conducting due diligence assessments (DDAs) on UNOPS and UN partners; UNOPS is conducting DDAs on NGO partners.
- Other donors reduce their humanitarian funding: DFID continues to meet regularly with other donors to advocate for increased resources for critical humanitarian needs, as well as to build support for the resilience agenda. We will also endeavour to seek out strategic funding options like pooled funds.
- A major natural disaster or health outbreak impacts Bangladesh or the Rohingya crisis: As part of the planning process, DFID team in Bangladesh are in touch with colleagues in HQ in planning for a crisis simulation and medical teams and others have been deployed to respond to events like health outbreaks.
- Worsening security negatively impacts programme operations: We will work with the partners to understand the impact of such situations on the programme operations and adjust workplans accordingly.
- Safeguarding: DFID is working with experienced partners who have safeguarding policies in place, whistleblowing hotlines available to report issues and incidents, partners sensitised on safeguarding risks. DFID HQ has written to major partners setting out standards we expect and seeking statements of assurance on their safeguarding environment and policies, organisational culture, transparency and their handling of allegations and incidents. All forthcoming DDAs will include specific assessments of safeguarding. We will not fund organisations that have been identified as having insufficiently robust safeguarding policies.

Update on partnership

During the review period, govt. of Bangladesh has been one of the key responders to natural disasters and refugee crisis. DFID funded programmes closely coordinated with local government and complimented with flood response. Since the beginning of Rohingya crisis, govt. has mobilised their civil and armed forces to ensure access and basic needs. While Govt. of Bangladesh is seeking a political solution for the crisis, they are providing support to ensure humanitarian access for affected population.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial and financial issues

Delivery against planned timeframe

While the programme is on track against its planned timeframe for Pillar 1, the team needs to have discussions with the Joint UN Rohingya project partners and ACF on the future of their programme taking into account the changed context of the Rohingya response. UNOPS have been slightly delayed on their work plan due to the Rohingya response and will incorporate these into the new work plan. The monitoring and evaluation system, communications plans were delayed due to the diversion of staff capacity to respond to the Rohingya influx programme. The Start Fund is on track on its work plan though approval for FD6 for the host agency is expected to be received by October 2018. . During the reporting period, UNOPS signed 32 contracts with 16 partners for 3 ERRF projects and Rohingya phase 1 and 2.

Due to the new influx of Rohingya in August 2017, Pillar 3 grew exponentially as DFID allocated two funding rounds to respond to the emergency. While most projects required no costs extensions under Phase 2 of the Rohingya response, the Phase 1 were completed on time. Start Fund Bangladesh supported 3 responses in the last year with 13 partners. All the Start Fund responses were completed on time.

Performance of partnership (s)

Apart from START Fund component under pillar 2, rest of the programme’s delivery model was through UNOPS as the fund management agency. The key responsibilities of UNOPS included fund management, grant management and monitoring of downstream partners. START Fund operates through a secretariat currently hosted by Save the Children. Based on the governance system, START makes decisions on responding to disasters and allocates funds to INGOs.

Flexibility and ease of doing business: The Annual report was delayed due to the diversion of staff to the Rohingya response as well as delays in receiving reports from partners. The Start Fund has experienced delays (not response) in responding to requests for information due to the nature of the relationship between the host agency and Save the Children. Both agencies are working with DFID to improve the quality and timeliness of financial reporting and accuracy in forecasting.

Delivery and support: The deliverables by UNOPS were generally completed on time but sometimes there were delays, especially the launch of the online monitoring tool and the communications strategy. UNOPS fund management was relevant under the initial business case approach, but was not set up to respond to an L3 [1]type crisis such as the Rohingya response. The unexpected expansion of Pillar 3 resulted in delays in grant management. DFID is working together with UNOPS to identify lessons learned from the rapid expansion of UNOPS’ role, and to clarify roles and responsibilities of both parties to ensure more effective delivery of the ongoing Rohingya response. For the Start Fund, most of the deliverables are received on time.
[1] L3: An L3 emergency is the classification for the most severe, large-scale humanitarian crisis. An L3 declaration means that a system-wide mobilization is required to significantly scale up a humanitarian response and improve overall assistance.

Quality: Both UNOPS and Start Fund had a full complement of staff by the end of the reporting period. However, UNOPS capacity was challenged by the fast moving Rohingya response and high demand for real time data. DFID deployed consultants from HSOT during November to support quality delivery along with UNOPS. DFID also agreed to increase staffing for UNOPS to be able to respond to the Rohingya response. On adherence to budget, both organisations need to work more closely on forecasts with partners to improve the forecasting accuracy with DFID. This will be part of the finance improvement process mentioned above.

Partnership, Innovation and Improvement: Both partners actively capture lessons learnt and apply the actions to future work. The Start Fund conducts a lessons learnt workshop post each response and these are consolidated and fed into the planning of the next response. UNOPS conducts monitoring visits and provide feedback and lessons learnt to partners and DFID. Case studies have been collected and shared with DFID.

Risk and Compliance: UNOPS and Save the Children both work closely with the programme team on risk management and on compliance requests. These have been actively taken into consideration and reported on. The partners are able to provide data to support transparency requests. Risk Management plans are maintained and updated by both partners. Both partners have attended the Risk workshop conducted by DFID Bangladesh during the reporting period where issues on risk management, fraud reporting etc. have been conveyed. Fraud is also discussed at monthly meetings.

Asset monitoring and control

UNOPS and Save the Children maintained and updated the asset register. All assets procured under the noted in asset registers which are monitored and updated regularly. UNOPS maintains a register of all assets worth >£500 purchased and submits to DFID annually. On 29 March (UNOPS) and 7 March (Start Fund) DFID Bangladesh conducted asset spot checks.

Quality of financial management

During the review period, the programme was injected with more resources to support the Rohingya response. The total expenditure for the reporting period review period - July 2017 – Mar 2018 was £58.69m, of which the Rohingya response was £47.5m. The quality of financial management by partners’ needs improvement and DFID is already working with them to address this. The quality of financial reporting also needs to be improved and DFID has provided financial reporting templates to be used by both UNOPS and Start Fund. UNOPS could not forecast robustly due to the emergency nature of the Rohingya response where delays in partners’ abilities to start implementation which affected spend and subsequent forecasts. Start Fund has also struggled with forecasting due to management by different entities. The forecasting of the Grant component is recognised as being difficult as the expenditure is dependent on the occurrence of a disaster.

Recommendations in respect of UNOPS/Managing Agent

During the review period, DFID learnt a lot about using a managing agent for rapid response. Based on several discussions and technical reviews, the following recommendations were formulated to improve UNOPS’s fund management process:

- DFID should undertake a Commercial & Procurement Capability Review of UNOPS Bangladesh.
- DFID should ensure a clear statement of requirements (ToR) is included within any revised Agreement with UNOPS for Pillar 3. This should set out a clear governance & communications structure for the programme. It should also set out clear roles and responsibilities of DFID, UNOPS and partner organisations so they are transparent to all.
- DFID should identify management KPIs that will adequately identify and manage performance across the whole delivery chain but making UNOPS (and any partners moved from UNOPS downstream to direct delivery partners to DFID) responsible for managing this across their whole downstream delivery chain. This should include a good range of management KPIs (financial forecasting and management, quality of project team and team leader, responsiveness of team, ability to adapt and flex, innovation, etc). A full list is contained in the Strategic Relationship Management process for the Top 30 SRM suppliers and would be entirely appropriate for use on this programme with UNOPs (and other direct partners).
- DFID should provide/agree standard monitoring reporting templates and timings with Tier 1 supplier(s) to ensure that they can provide overall progress and performance. Tier 1s to manage with their downstream partners.

Date of last narrative financial report(s)	UNOPS: 25 June 2018 / Save the Children: 12 July 2018 / ICRC: 14 June 2018 / British Red Cross: Due in December 2018 / UKMED Interim report received – July 2018
Date of last audited annual statement (s)	UNOPS: N/A for Jan-Dec 2016 / Save the Children: 30 May 2018 / ICRC: 14 June 2018 / British Red Cross: Due in December 2018 / UKMED: Due in October 2018

G: MONITORING, EVIDENCE & LEARNING

Monitoring

UNOPS developed a monitoring plan for the overall programme and the emergency response component. This was modified to include the Rohingya response. UNOPS conducted an M&E Workshop with all partners in April 2017 to develop the initial SHPR Logframe. Two M&E Community of Practice meetings were also held in June and September 2017.

For the Start Fund and other emergency responses, DFID monitored the programme through 1) desk based review of progress reports 2) partner meeting 3) field visits and 4) discussion with beneficiaries. DFID HSOT Humanitarian Advisers based in Cox’s Bazar carried out Rohingya response programme monitoring.

One of the key tasks of the UNOPS was to develop the SHPR Beneficiary Accountability Mechanism (BAM). The main purpose of the BAM was to provide a platform for beneficiaries to communicate feedback, suggestions and concerns and/or, report perceived fraud or gaps in service.

DFID organised regular monthly meetings to discuss START Fund progress. Feedback was discussed with respective partners and relevant stakeholders through learning and action workshops.

As part of this Annual Review DFID met all SHPR partners and reviewed progress against the logframe and annual workplan. Partners participated in discussion to highlight achievements and challenges and, provided recommendations and lessons learnt which are captured in this review.

Evidence

No external evaluations were planned during the review period; however we want to change this for the coming year. Partner narrative reports, DFID Humanitarian Adviser’ monitoring reports, Start Fund monitoring reports and, regular meetings were used as evidence for determining partner performance and programme quality.

UNOPS provided an Annual Report prior to this review incorporating all updated results based on the logframe. START Fund Bangladesh has provided an Annual Activity Report.

IFRC and ICRC results were reported centrally as per usual practice.

Learning

Partners have multiple organisation specific mechanisms in place including hotlines, helplines, helpdesks, complaints boxes, community structures, community meetings, post distribution surveys etc. There is need for greater coherence and consolidation of a unified objective mechanism.

Proactive UNOPS relationship building with the relevant authorities to reduce delays in authorisation to start project implementation (FD6/FD7 Approvals) DFID should provide letters of support/intent to initiate the approvals process for INGOs.

Pre-alert discussions through established mechanisms like “Start Fund Bangladesh – alert discussion group” were found to be extremely useful in terms of information exchange, sharing of ideas and decision making.

High staff turnover in Cox’s Bazar and administrative delays have contributed to late implementation and lack of continuity/programme knowledge.

The Rohingya crisis led to reduced engagement of Start Fund member agencies with the fund. There is need to clarity of roles and responsibilities of members based on geographical presence and organisational mandate. A 4W (who, what, where, when) matrix would be useful during proposal reviewing.

This Annual Review was undertaken by the Humanitarian Advisor and Deputy Humanitarian and Protracted Crises Team Leader in consultation with partners and Quality Assured by the Senior Responsible Owner (SRO) and Head of Office.

Annex A. SHPR Logframe Revision, 23 May 2018
Summary of Changes

General Changes:
1. The SHPR Logframe was revised so that Outcomes, Outputs and the Indicators respond to the range of problem statements and proposed interventions outlined in the Business Case and Project proposals.
2. Coherence and inter-linkages of components were improved. Towards this, the locations of some indicators were adjusted to correspond to the level of results they were meant to measure.
3. To comply with DFID’s Revised Guidelines on Using the Log frame, Outcome statements were revised to identify what will change, and who will benefit.
4. Indicators were formulated in terms of how results were going to be measured. Previous indicators already included targets or milestones.
5. Outputs that related to M&E functions of the programme have been removed as they do not fit appropriately to the logical framework of programme.
6. The three Outcome statements now correspond to the three pillars of the SHPR Programme.

Result Statement	Old	Revision	Change
Impact	Improved Disaster Resilience (lives saved and financial losses reduced)	Improved Disaster Resilience in Bangladesh	No Change
Impact / Indicators	Improved preparedness and response mechanism among the humanitarian actors / Number of lives saved	No. of deaths, missing persons, attributed to disasters per 100,000 population / Direct economic loss in relation to global GDP, damage to critical infrastructure and number of disruptions to basic services, attributed to disasters / Number of people (affected by natural disasters and forced displacements) whose resilience have been improved	Indicators for measuring this impact have been adjusted to match this level of result. / As resilience is an SDG result, SDG indicators were adapted / ICF resilience indicator also used at this level instead of as an Output indicator
Outcome 1	Disaster preparedness strengthened	Strengthened capacity and accountability of the national humanitarian architecture/ structure and humanitarian actors in the country to cope with disasters and climate change	Outcome statement strengthened to capture what will change and who will benefit. Outcome 1 represents the Pillar 1 stream of work of the SHPR Programme
Outcome 1 Indicators	1.1 Level of Institutional knowledge of climate change issues as a result of ICF support	Percentage (%) of humanitarian actors expressing their satisfaction on the quality and effectiveness of humanitarian coordination in the country by DFID support / Percentage (%) of humanitarian actors expressing their satisfaction on the quality and effectiveness of clusters mechanism for national disaster preparedness and response in the country by DFID support / Percentage (%) of partners implementing effective and operational accountability mechanism in the country by DFID support	To strengthen the hierarchy of results and logical flow, the old outcome indicator has been moved as an output. / The new Outcome indicators provide better elaboration of how the Outcome will be measured.
Outcome 2	Urgent needs addressed via an improved response capacity	More predictable, effective and accountable support provided to disaster-affected communities	The old Output 1 statement was found to be more appropriate statement of Outcome and was elevated as Outcome 2. The new Outcome 2 represents the Pillar 2 stream of work of the SHPR Programme
Outcome 2 Indicators	Number of people supported by DFID Programmes to cope with the effects of climate change (disaggregated by sex and support type) / Number of people reached with humanitarian assistance (food aid, cash and voucher transfers) through DFID support	Number of people supported with humanitarian assistance with DFID funding (Disaggregated by sex, response type) / Number of people supported by DFID Programmes to cope with the effects of climate change (ICF KPI 01) / Number of days taken for support to reach beneficiaries (Disaggregated by support type)	Indicators for measuring this Outcome have been adjusted to match this level of result. / Indicator designed to report against DFID ICF reporting requirements. This will be made more generic once other donors contribute to the fund / Old Outcome 2 indicators relocated to Output 2 to have more logical progression of results / Timeliness of response indicator moved up to Outcome level to substantiate the Outcome statement / Outcome 2.1 is the aggregated measure of our emergency response output.
Outcome 3	Improved humanitarian outcomes for Rohingya refugees and host communities	More predictable, effective and accountable support provided to Forcefully Displaced Myanmar Nationals (FDMNs) and host communities	As Outcome 2 and 3 are both emergency response statements, they follow the same formulation but Outcome 3 is specific to FDMNs/Rohingya population. The new Outcome 3 represents the Pillar 3 stream of work of the SHPR Programme
Outcome 3 Indicators	3.1 Number of people reached with humanitarian assistance (food aid, cash and voucher transfers) through DFID support / 3.2 Number of people with sustainable access to clean water/sanitations through DFID support / 3.3 Number of people with sustainable access to clean drinking water sources through DFID support	3.1 Number of FDMNs and host communities supported with humanitarian assistance with DFID funding / 3.2 Number of FDMNs and host communities supported by DFID programmes to cope with the effects of climate change / 3.3 Number of FDMN supported to cope with the effects of non-climate related disasters / 3.4 Percentage (%) of humanitarian actors expressing their satisfaction on the quality and effectiveness of ISCG coordination in providing timely emergency response (Disaggregated by Org. type)	Indicators for measuring this Outcome have been adjusted to match this level of result. / Indicator designed to report against DFID ICF reporting requirements. This will be made more generic once other donors contribute to the fund. / Outcome 3.1 is the aggregated measure of our emergency response output. Further breakdown into sectoral outputs can be set up for donor reporting requirements. / Indicator added for non-climate induced disasters / Old indicators relocated to Output 3 to have more logical progression of results / Indicator 3.4 added to capture the ISCG coordination of response
Output 1	More predictable, timely and effective support provided to vulnerable communities	Humanitarian actors have increased understanding of and capacity to prepare for and respond to disaster and climate change related events (PILLAR 1)	Output 1 is restated to directly relate to Outcome 1 to which it contributes to. The new Output 1 is a consolidated statement of the old Output 1 and 2 statements.
Output 1 Indicators	Number of gender sensitive assessments conducted leading to timely response / Number of days taken for support to reach beneficiaries / Number of Rohingya refugees and host communities that have access to basic services / Number of people whose resilience has been improved as a result of project support	Level of institutional knowledge of climate change issues as a result of ICF support. (ICF KPI 14) / Number of humanitarian coordination mechanism established and operational in accordance with IASC guidelines / Number of cluster mechanisms for disaster preparedness and response in accordance with IASC guidelines (disaggregated by types of mechanisms / Number of gender sensitive disaster assessments accessible to humanitarian actors leading to timely response / Number of people trained on coordination and assessment methodologies and equipped with gender sensitive tools (disaggregated by sex and humanitarian actors) / Number of people receiving emergency stocks prepositioned to high risk areas / Progress towards establishment and operational of Humanitarian Staging Area (HSA) in country / National Accountability Mechanism (NAM) established and operational for improving humanitarian architecture	The old 1.1 has been retained as the new 1.4. The old 1.2 is seen more as an indicator to Outcome 2 and has been moved as a measure to that outcome. The old 1.3 has been relocated to Outcome 3 where it rightly belongs. The old 1.4 is seen as a higher level indicator and is now one of the Impact indicators. / Additional indicators have been added to adequately capture and respond to the problem statements/gaps identified in the business case and project proposals.
Output 2	Improved disaster preparedness for recurrent and major events	People affected by disasters have access to assets, basic services, livelihood and safety nets to help them absorb stresses and recover from shocks (PILLAR 2)	The old Output 2 has now been consolidated into the new Output 1 to strengthen and streamline the results links. (Please see comment above under Output 1)
Output 2 Indicators	Functioning supply chain and logistics mechanism for preparedness in place / Number of humanitarian actors equipped with trained personnel on gender sensitive tools / Robust mechanism in place to identify needs of vulnerable communities and communicate findings to humanitarian actors	Number of people receiving humanitarian assistance- food aid, cash and voucher support / Number of disaster-affected people receiving other forms of support / Number of beneficiary complaints/feedback received and effectively addressed.	Consistent with the consolidations of the old Output 1 and 2 into one output which is now Output 2, old Output 2 indicators have been moved to New Output 1 indicators / Output 2.3 is to measure accountability aspect of the emergency response (accountability being part of the Outcome 2 statement to which this Output aligns with)
Output 3	Better accountability, coordination and coherence of the institutional humanitarian system	FDMNs and host communities have access to assets, basic services, livelihood and safety nets to help them absorb stresses and recover from shocks (PILLAR 3)	The old Output 3 is now part of Outcome 1 and of Outcome 3 on the coordination aspects of Rohingya response. / The new Output 3 is entirely different and aligns with the Rohingya/FDMN Outcome 3
Output 3 / Indicators	Humanitarian coordination mechanism established and operational in accordance with IASC guideline / Effectiveness of existing cluster mechanisms improved in accordance with IASC guideline / Evidence-based information management system in place to be accessed by all humanitarian actors	3.1 Number of affected FDMNs and host communities reached with humanitarian assistance (food aid, cash and voucher transfers) through DFID support / 3.2 Number of affected FDMNs and host communities with access to clean water and/or sanitation through DFID support / 3.3 Number of affected FDMNs and host communities receiving NFI/shelter assistance / 3.4 Number of affected FDMNs and host communities receiving nutrition services / 3.5 Number of affected FDMNs and host communities receiving emergency health care / 3.6 Number of affected FDMNs and host communities with access to safe community level infrastructure / 3.7 Number of affected FDMNs and host communities’ children with continued access to education / 3.8 Number of affected FDMNs and host communities receiving GBV and SRH services / 3.9 Number of affected FDMNs and host communities receiving protection services / 3.10 Number of affected FDMNs and host communities trained on community-leadership and decision making / 3.11 Number of affected FDMNs and host communities with livelihoods assistance to help them cope with and recover from disasters / 3.12 Number of beneficiary complaints/feedback received and effectively addressed.	Output 3 indicators are totally different to the old Output 3 indicators because of the restructuring of Outputs from old logframe to this new one. / Old Output 3 indicators are now part of the Indicators of the new Output 1 except for 3.3 which is considered part of the monitoring function of the SHPR FMO and is therefore removed from this logframe. / While the output still measures results of the emergency interventions similar to the new Output 2, the indicators for Output 3 which is specific to the FDMN/Rohingya response is more detailed to reflect specific sectors with which SHPR plans to intervene. The breakdown of sectoral outputs will meet the requirements of the donor. Also, the breakdown reflects to capture the scale of the current response to the Rohingya crisis.
Output 4	Improved generation of evidence and synthesis of learning	None	Output 4 is deemed part of the monitoring, learning and knowledge management function of the SHPR FMO and does not fit appropriately with the results logic of the SHPR logframe. This indicator can be assessed as part of SHPR FMO performance against the approved technical proposal.
Output 4 / Indicators	4.1 Proactive functioning of a common platform to track and monitor results as per agreed project and programme logframes / 4.2 Number of programmatic changes reflected in the project and programme logframes based on share lessons (IPs and Beneficiaries) / 4.3 Improved inter and intra communication through an IP CoP	None	Please see comment on Output 4 above.

Annex B. List of Acronyms

BAM	Beneficiary Accountability Mechanism
CA	Christian Aid
CFS	Child Friendly Space
CHT	Chittagong Hill Tracts
DDA	Due Diligence Assessment
ERRF	Emergency Response and Recovery Fund
FDMN	Forcibly Displaced Myanmar Nationals
FMO	Fund Management Organisation
FSC	Food Security Cluster
HCTT	Humanitarian Coordination Task Team
HSA	Humanitarian Staging Area
HSOT	Humanitarian Support Operations Team
IASC	Inter-Agency Standing Committee
ICRC	International Committee for the Red Cross
IFRC	International Federation of Red Cross
IOM	International Organization for Migration
ISCG	Inter Sector Coordination Group
JDPP	Joint Disaster Preparedness Programme
JRP	Joint Response Plan
MAF	Mission Aviation Fellowship
MoDMR	Ministry of Disaster Management and Relief
NAM	National Accountability Mechanism
NC	Nutrition Cluster
NRP	National Resilience Programme
SCI	Save the Children International
SHPR	Strengthening Humanitarian Preparedness and Response
SI	Solidarities International
SRM	Strategic Relationship Management
UNDP	United Nations Development Programme
UNFPA	United Nations Population Fund
UNOPS	United Nations Office for Project Services
UNRC	United Nations Resident Coordinator
VfM	Value for Money
WC	Wash Cluster
WFP	World Food Programme
WFS	Women Friendly Space