Type of Review: Annual Review

Project Title:International Partnership for Microbicides (IPM)

Date started:Dec 2008	Date review undertaken:July 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet willcalculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meetexpectation C

## Introduction and Context
What support is the UK providing?
To prevent HIV transmission by accelerating the development, availability and adoption of safe and effective microbicides for use by women in developing countries, DFID will provide £20 million over five financial years 2008/9 – 2012/13 to fund the programme.

What are the expected results?
The development of safe, usable and effective microbicides that can be controlled by women to address HIV infection, and will have a major public health and financial impact worldwide. / The expected results of IPM’s work are: / a) Expedite the developmentof female controlled HIV prevention products; / b) Increased African capacity to plan and conduct clinical trials in high incidence countries; / c) Effective advocacy to promote and sustain favourable public policy and long term predictable funding. / The results from previous trials have helped this programme to focus on moving forward. The International Partnership for Microbicides (IPM) has gone through a difficult re-prioritising process along with other efforts to reduce costs, in order to ensure the ability to implement its dapivirine ring licensure programme. The global financial situation has presented significantchallenges to IPM and others working in microbicide development.

What is the context in which UK support is provided?
There are research gaps in essential technologies (such as microbicides, vaccines and medicines) to treat neglected diseases that affect the world’s poorest populations. For many of these diseasesthere are no current products or those that exist are either too expensive, difficult to access, difficult to use, no longer produced, have safety or tolerability concerns, or are ineffective. / HIV and AIDS is a major cause of mortality and morbidity throughout the world and particularly in Sub-Saharan Africa. HIV and AIDS has a higher impact on women, yet women often lack effective tools that they canuse to prevent infection. / The aimofthe programme is to reduce deaths and illness from HIV and AIDS, through preventing HIV transmission by accelerating the development, availability and adoption of safe and effective microbicides for use by women in developing countries. / This funding fits within the DFID research strategy to address the need for new or improved products to combat diseases of the poor. It is also consistent with the DFID approach to HIV and AIDS, with its focus on treatment and prevention. Development of new prevention technologies for HIV will help to achieve the Millennium Development Goals (MDGs), notably to combat diseases such as AIDS, reduce poverty and child mortality, improve maternal healthand promote gender equality and empower women.

## Section A: Detailed Output Scoring
Output 1:Accelerate microbicide product development
Output 1 score and performance description: A: Outputs met expectation
Progress againstexpected results / IPM has made good progress and focused its work on the dapivirine vaginal ring licensure programme. IPM also increased its operational efficiencies in order to respond to constrained funding through expanded partnership and collaboration andby implementing a new operating model which made a smaller staff profile feasible. IPM has partnered with other groups, such astheUSNational Institutes of Health (NIH), to advance a very limitedpipeline. IPM began work on a multipurpose prevention technology (MPT), avaginalring containing dapivirine along with one or more contraceptive hormones, with funding from the US Agency for International Development (USAID). / IPM’s ring licensure programmeincludestwo large-scale, long-term safety and efficacy studies: IPM 027 (The Ring Study).Initially, IPM planned to conduct two efficacy trials (in Malawi, Rwanda and South Africa) and had received approvals from Ethics Committees and Regulatory Agencies in South Africa and Rwanda. Plans changed when the Microbicide Trials Network (MTN) of the NIH became a partner with IPM to advance the ring in clinical studies. MTN-020 (ASPIRE), which is being conducted by the NIH-funded Microbicide Trials Network, with protocols for both studies aligned. The licensure program also includes studies to examine the ring’s safety in adolescents and peri- and post-menopausal women, condom compatibility and drug-drug interactions. / IPM has conducted a range of preclinical studies of dapivirine includingrepeat dose and reproductive toxicology, vaginal and penile irritation, investigations of drug tissue penetration, and multiple virology assays to support the drug’s safety and in vitro efficacy. The remaining required studies, including a two-yearcarcinogenicitystudy, are in progress. These studies along with additional preclinical evaluations of dapivirine in combination with maraviroc havesupporteddevelopment of a combination dapivirine‐maraviroc microbicide vaginal ring. / IPM has completed six safety studies of the dapivirinering and seven safety studies of dapivirine gel, including a male tolerance study conducted byMTN. MTN and IPM also initiated the first clinical trial of a combination microbicide, adapivirine‐maravirocvaginalring, also the first trial to evaluate maraviroc as a microbicide. / As part of the cost reduction programme, IPM closed its operations at the US-based Clinical Trial Materials facility and has now completed technology transfer and scale‐up ofthe dapivirine ringPhase IIImanufacturing process with its manufacturing partner, QPharma AB (Malmö, Sweden). QPharma is producing and testing dapivirine and placebo rings according to Good Manufacturing Practice (GMP) to supplyboth the IPM and MTN trials and smaller safety studies that comprise the dapivirine ring licensure programme. / Recommendations / IPM has communicated well with all its donors over a very difficult year, duringwhich financial constraints impacted on the work programme. The involvement of MTN in the trials of the dapivirine ring are welcome, at a time of significant organisational change. The work on the dual prevention microbicide-contraceptive ring is welcomed. / Impact Weighting (%):40% / Revised since last Annual Review?No / Risk: High / Revised since last Annual Review? No

Output 2:Increase clinical trial capacity in high HIV-incidence settings
Output 2 score and performance description: A: Outputs met expectation
Progress against expected results / In 2011, 13 research centres in Africa conducted IPM clinical or incidence studies. IPM conducted multiple training activities; supported improvements toinfrastructure and improving the skills up of research centre staff; completedparticipant visits for an HIV incidence study; and also held the annual Clinical Affairs meeting in Cape Town to coordinate and prepare all partners and stakeholders for the start of IPM dapivirine ring study. / IPM has established additional clinical trial sites and expanded capacity at existing sites so that staff are ready to undertake the IPM ring study which willenrol 1,650 healthy, HIV‐negative women at four sitesin South Africa andone in Rwanda.Through regular training, and the experience gained through conducting both HIV incidenceand clinical safety studies, the research centres have demonstrated a high level of Good ClinicalPractice (GCP) compliance. Each research centre has the capacity to conduct high‐quality clinical trials. / In addition, IPM provided its research centre partners with an array of communicationsmaterials (presentations, fact sheets, and brochures) with the aim of: / Increasing the ability of each research centre to recruit clinical trial participants. / Enhancing scientific research literacy among participants and the local communities wherethe studies are taking place. / Providing communication tools and techniques so that research centre partners cancommunicate information about the dapivirine licensure program to key stakeholdergroups. / Recommendations / None / Impact Weighting (%):40 / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

Output 3: Develop policy and advocacy programmes to support timely access to microbicides in selected countries
Output 3 score and performance description: A: Outputs met expectation
Progress against expected results / IPM completed a strategic plan for access in early 2011 that sets priorities to future efforts. This document is available on the IPM website www.ipmglobal.org. The strategy comprises five concepts: architecture (the network of organisations at the global, national, and local levels that support, connect and implement all access activities), availability, acceptability, affordability, and appropriate use (conducting medical education and awareness raising campaigns to ensure that microbicides are used properly). / In 2011 IPM started the “Microbicides: Giving Women New Hope and Choice in HIV Prevention” campaign toraise awareness of microbicides and to build support for product development and eventual access. / Along with WHO, UNAIDS and AVAC, IPM co‐hosted the forum, “Mind the Gap: Bridging from Trial Success toAccess,” at the International AIDS Society conference in Rome in July 2011. / IPM staff and consultants based in Africa, carried out an assessment of civil society organizations which led to two new civil society partnerships with the Southern African AIDS Trust’s (SAT) country offices in Malawi and Zimbabwe. IPM worked with representatives in both countries to develop theirmicrobicide advocacy program plan. In late 2011, SAT‐Malawi and SAT‐Zimbabwe began their advocacy activities by conducting HIV prevention research training for policymakers and journalists; monitoring and responding to media coverage of microbicide prevention research in national newspapers and radio programs;and holding community‐based awareness‐raising workshops on ARV‐based prevention technologies. / IPM also worked with the Kenya Medical Women’s Association. In 2011, KMWA strengthened its organisational capacity to educate and advocate for HIV prevention research by establishing a new HIV prevention working group within its membership. In addition, they embarked upon a continuing medical education program for physicians and healthcare workers throughout Kenya. / Recommendations / IPM should continue its work with the advocacy and scientificcommunity to improve the consistency of messaging to target audiences.It is important to improve understanding in the African media about HIV prevention research, in order to improve their reporting, which helps to shape public perceptions of clinical trials and new preventiontechnologies such as microbicides.In a resource‐constrained environment, donors and governments of countries where clinicaltrials are conducted need to understand the economic value and potential public health impactof investing in or supporting continued investment in microbicide research. / Impact Weighting (%):20 / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results

Has the logframe been updated since last review? No / Overall Output Score and Description:A: Outputs met expectation / 1.3 Direct feedback from beneficiaries / IPM works closely with local populations to raise awareness about HIV and HIV prevention and the need for prevention methods that can be controlled by women. / At their clinical trial sites they upgrade existing facilities – providing services, and infrastructure, equipping clinical labs and training health service personnel in good clinical practice and ethics, patient treatment and evaluation, accurate diagnosis and follow-up. / IPM establishes a community advisory group (CAG) at each research centre. The CAGs review draft versions of protocols, informed consent documents, and translations of data collection instruments and provide feedback on issues that may be of concern for, or confusing to, trial participants and community members. / IPM’s document, “Hope for tomorrow, benefits for today,” describes trial participant feedbackand is available on the IPM website.The document indicates that participation in trials improves awareness of HIV/AIDS, empowers women to seek health care and negotiate safer sex, and reduces stigma. / IPM’s current reporting structures could be strengthened to provide additional detail on beneficiary or trial participant feed-back.
1.4Summary of overall progress / IPM have made good progress during adifficult year. Partnering with other organizations for large safety and efficacy studies, such as IPM’s partnership with MTN on the dapivirine ring program, enhances efficiency and expertise and shares costs for the development of a novel pharmaceutical product. / There have been a number of advances in the field of antiretroviral (ARV) prevention, including trials of: a microbicide containing tenofovir gel; pre-exposure prophylaxis containing tenofovir or truvada; and treatment as prevention. The picture is not clear as there were also trials that showed no impact of certain ARV-based prevention methods. The trials being conducted by IPM and the MTN will make an important contribution to the evidence base over the next few years.
1.5 Key challenges / IPM has worked closely with development and implementation partners in order to minimise development risks. Key challenges will be to ensure that the parallel IPM and MTN trials are conducted to the highest standards and are able to recruit and retain participants at the anticipated rate during the next two-three years and that participants use the dapivirine ring consistently.Early and on‐going engagement with regulatory agencies has proved to be effective in an approach to safety and efficacy studies leading to rapid approval of a new pharmaceutical product such as a microbicide. The Parallel Scientific Advice procedure withEMA, FDA, WHO and African drug regulatory agencies was a timely and efficient way to learn the requirements for regulatory approval of a microbicide. / Funding has been a key challenge during the year and IPM and partners have successfully leveraged funding through the MTN for part of the work required by the regulatory agencies. IPM has been throughsignificant institutional and management restructuring to operate within constrained funding. The organisation is to be commended for its approach and the continued dedication of its staff.
1.6Annual Outcome Assessment / IPM's outcomes metexpectationsand we anticipate that they will continue to perform well through to the end of this funding period.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / 2.2 Key cost drivers / Product development is a very costly process, especially in the latter stages of development. As new products progress through the pipeline they enter into successively more costly phases of development. IPM has partnered with the MTN to leverage resources to ensure that there are funds available to test the dapivirine ring to regulatory standards. They have also received funds from USAID to begin the development of dual purpose (microbicide and contraceptive) technologies. / IPM works in partnership with public and private sector entities and has secured non‐exclusive, royalty‐free licenses for antiretroviral drugs (ARVs) from five pharmaceutical companies; developed new drug delivery formulations and analytical testing methods; developed and advanced a monthly dapivirine vaginal ring into Phase III testing; recognised the potential advantagesof combination ARVs and advanced a dapivirine‐maraviroc ring into clinical testing; initiated a contraceptive‐microbicide ring development programme; successfully manufactured and supplied GMP vaginal gels and rings for Phase I/II clinical trials, and scaled up ring manufacturing infrastructure and technology to support Phase III requirements. / 2.3 Is the project on-track against original timescale: Yes

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / N/A / 3.2 Where an evaluation is planned what progress has been made? / A number of evaluations were undertaken in 2010 (commissioned by the Bill and Melinda Gates Foundation). The review culminated in a discussion of the key issues between IPM, the Gates Foundation, IPM Board and other donors along with a detailed response developed by IPM management. / An independent financial analysis of IPM, conducted by KPMG, on behalf of the Gates Foundation, found no material problems.

4. Risk
4.1 Output Risk Rating: High / 4.2 Assessment of the risk level / New product development is high risk with the potential for new products to fail at any stage in the lengthy development process. The product development partnership model represents a mechanism to mitigate the risk associated with the development of new products for diseases where there is little likelihood of pharmaceutical companies recovering development costs. / In common with other PDPs, IPM and its partner organisations have robust mechanisms in place to manage their portfolios, drawing on global experts to identify milestones and stop/go decision points. / The main risk associated with new product development is that products developed are not rapidly approved for use or are not deployed to those people who need them due to supply chain constraints. IPM, working in partnership with others, has systems in place, including an access strategy, to work with the relevant authorities to minimise these risks.
Risk of funds not being used as intended / Low – DFID provide core funds to IPM to support the development of microbicides for HIV. / IPM have a strong governance structure and there is little or no risk of corruption. / 4.4Climate and Environment Risk / With the aim of registration and delivery of new products, IPM and its partners, like all pharmaceutical research and development, has to comply with a wide range of international regulations including Good Manufacturing Practice (GMP) which includes issues about environmental impact reduction. Compliance with these regulations, which include safe laboratory and disposal practices are essential to maintain registration status. No significant negative environmental impacts of the programme have been seen to date. / In disease-endemic countries, use of microbicides developed through the programme will eventually raise issues of packaging and distribution. The programme will ensure that packaging and distribution will be done to minimise environmental impact and ensure appropriate operations practices in logistics chains. IPM is exploring whether the current ring formulation would be effective for a longer duration; continuous use of one ring for 60 or 90 days will result in fewer rings used overall and less environmental impact. IPM is also assessing the use of a degradable polymer in developing a next-generation dapivirine ring, and has in its pipeline other microbicide formulations with low potential for environmental impact, such as vaginal films and tablets that do not require an applicator. / Drug volatility and stability under conventional distribution practices are carefully considered and formulations are developed to minimise the need for refrigeration or other storage requirements and continuously evaluated to support extension of product shelf life. / In the longer term the environmental impact of the programme should in fact be positive through the reduction of the need for HIV drugs, tests and consumable products. The diseases disproportionately affects poor populations, in particular women, who often live in remote rural areas.

5. Value for Money
5.1 Performance on VfM measures / Funding microbicide development through a PDP such as the IPM provides value for money through: / The use of a portfolio approach which allows funding to be redistributed if individual projects are stopped, when they do not meet their milestones; / The leveraging of contributions (resources, expertise, funding, access to products and other in-kind resources) from the private sector; / Support for the continued development of the most promising microbicide candidates / Facilitating opportunities to explore innovative partnership with private and public sector organisations to reduce costs / Strengthening medical research capacity in developing countries and benefiting clinical trial participants and their communities / 5.2 Commercial Improvement and Value for Money / Through its internal processes, identifying the most promising new microbicide candidates from different organisations across the world, IPM is able to provide a competitive environment for innovation and improved value for money. In addition, working with the pharmaceutical industry has also shown improved value for money, by leveraging in resources from other organisations, for microbicide discovery and development. / 5.3 Role of project partners / Ensuring value for money in developing microbicides for use in low income countries where there is no viable commercial market is central to the way PDPs work with partners from a range of different backgrounds, including pharmaceutical companies, other private sector organisations, academic researchers, advocacy organisations and local community groups. / DFID is one of a core group of donors supporting IPM’s work and we are involved in regular discussions both with the organisation directly and indirectly through such mechanisms as the PDP Funders Group. / 5.4 Does the project still represent Value for Money : Yes / 5.5 If not, what action will you take? / N/A

6. Conditionality
6.1 Update on specific conditions / No specific conditions attached to this funding.

7. Conclusions and actions
IPM has performed well during a difficult year. The next couple of years are also particularly important as IPM leads the overall dapivirine ring licensure program toward regulatory approval, while continuing to advance its microbicide pipeline.

8. Review Process
This review was conducted by members of the Human Development Research Team in DFID. / The review was done after 2 formal IPM Donor Meetings and three donor conference calls. In addition DFID staff have had a number of discussions with IPM staff, other donors, and independent members of the microbicide scientific community. DFID staff have had strong links and discussion on progress with funding colleagues from other Governments e.g. Ireland, Netherlands and USA together with members of the Bill and Melinda Gates Foundation and through the PDP Funders Group.