## Sheet1
PROGRAMME LOGFRAME: LAND TENURE SUPPORT PROGRAMME (LTSP) IN TANZANIA
TOTAL PROGRAMME INPUTS ($) | Total ($) | DIFID ($) | SIDA ($) |  | DANIDA ($) |  | GOV ($) | DIF HR (FTEs) %
Amount: | 15800000 | 6900000 | 5800000 |  | 3100000 |  | 0
Share in %: | 100% | 43.67% | 36.71% |  | 19.62% |  | 0%
Impact Weighting (%) |  |  |  |  | Risk rating |  | High
(H, M, L)
Impact (Final Outcome) | Impact Indicator 1 |  | Baseline | Milestone | Milestone | Milestone | Final Target achieved | Assumptions
|  |  | 2015/16 | Q4- 2016/17 | Q4- 2017/18 | Q4- 2018/19
Greater security of land tenure to land holders and users | % of men and women who perceive their land tenure is secure in pilot area. | Planned | (a) 38% | N/A | N/A | 42% | 42% | (i) Land registration increases security of tanure through reduction of land disputes. (ii) land registration process quaratees land rights to all comunity groups including the disadvataged groups (iii) community members and Authorities will respect land legal ownerships.
| (a) % of men |  | (b) 9% | N/A | N/A | 35% | 35%
(b) % of women
|  | Achieved | (a) | (a)
|  |  | (b) | (b)
|  | Sources | Perception survey conducted before and after the programme by the baseline/impact evaluation team
Outcome | Outcome Indicator 1 | [6 empty] | Assumptions
Improved transparency and land governance | Disposal rate of backlog of cases filed in the DLHTs before LTR Project. | Planned | 20% | Study on land disputes settlement mechanisms awarded | 60% | 70% | 70% | (i) Implementation of land regularization activities and facilitation of DLHT will reduce land disputes in the Programme area (ii) All MSG members especially those from non-Government institutions will be effectively participating in MSG meetings and decisions.
|  | Achieved |  | Consultant has been awarded. | 55%
|  | Source(s) | Annual inspection of DLHT records in project districts.
Outcome Indicator 2
| National scale programme to prepare VLUPs and issue CCROs designed for implementation | Planned | 0 | Draft ToR for national scale Programme | Draft plan prepared | Agreed plan and funding secured
|  | Achieved |  | ToR for national scale Programme prepared | Resolution has been made that, the annual review mission will review ToR for national scale Programme. The Governemnt will start preparation of National Scale Programme by October 2018.
|  | Source(s) | Programme documentation
Outcome Indicator 3
| % of stakeholders in the land sector agreeing that MSG effectively promotes greater transparency and improved land governance. | Planned | 0 | 20% | 50% | 75% | 75%
|  | Achieved |  |  | Collection of this data was planned to be done during national land stakeholders learning workshop in June 2018. The workshop was postponed to Mid September 2018.
|  | Source(s) | Interview with land stakeholders and land experts.
Output 1 | Output 1 Indicator 1 | [6 empty] | Assumptions
Improved land administration institutions at the district and village levels | Number of district land offices constructed. | Planned | 0 | District Land Office design approved by MLHHSD management | N/A | 3 | 3 DLOs constructed | Construction of District Land Offices will improve registry system of CCROs and will lead into improved land transaction sytem.
|  | Achieved |  | District Land Offices (DLO) design approved by MLHHSD management and contractor for construction of DLO identified. |  | Contractors for construction of 3 District Land Offices were awarded contracts and handover sites for construction.
|  | Source(s) | M&E reports, reports from district land offices and field inspection reports.
| Output 1 Indicator 2 | [6 empty] | No sub-division of villages during project implementation
| Number of renovated and equipped village land registries. | Planned | 11 | 61 | 53 | 49 | 163
|  | Achieved |  | 3 villages completed constraction of village land registries, 41 villages’ registries are at finishing stage, 11 have just started construction and 6 villages will start construction in the first quarter of 2017/2018. | 48 |  |  | Construction and equiping Village Land Offices will improve land records management for better land adnimistration.
|  | Source(s) | PIU Quarterly, Annually reports and field inspection reports.
Output 1 Indicator 3
| Number of demarcated and surveyed village boundaries | Planned | 113 | 47 surveyed | 71 resurveyed | 0 |  | Decentralisation policy fully implemented for LGA to support local administration institutions
|  | Achieved |  | 50 surveyed | 55 resurveyed |  | 121
|  | Source(s) | M&E reports and Director of Surveys and Mapping records.
Output 1 Indicator 4
| Number of Villages issued with Certificates of Village Land | Planned | 53 | 50 | 71 | N/A
|  | Achieved |  | 57 | 60 |  | 128
|  | Source(s) | PIU Quarterly and Annual reports.
Output 1 Indicator 5
| Number of VLUPs prepared for gazzettement. | Planned | 48 | 22 prepared | 47 prepared | 50 reviewed | 127 | Pastoralists and agro-pastrolists participates in VLUP meetings after receiving startegic public awareness and education in the process.
|  | Achieved |  | 30 prepared | 47 prepared
|  | Source(s) | quarterly and Annual reports, National Land Use Planning Commission records.
Output 1 Indicator 6
| Average cost of preparing VLUPs per village | Planned | 9000 | 8000 | 5000 | 4800 | 4800
|  | Achieved |  | 6200 | 3500
|  | Source(s) | The data will automatically be collected by the regular regularisation process and part of M&E reports, Records at Land District offices
Output 1 Indicator 7
| % of community members participating in awareness and education meetings for VLUP | Planned | A. 30% | 35% | 48% | 52% | 52%
|  |  | B.42% | 50% | 57% | 60% | 60%
|  | Achieved |  | A. 32% | A. 44%
| A. women |  |  | B.45% | B. 52%
| B. Men | Source(s) | PIU Quarterly, and Annual.
Output 1 Indicator 8
| % of total pastoralists residing in a village participating in Awareness and education meetings for VLUP | Planned | 20% | 30% | 40% | 60% | 60%
|  | Achieved |  | 25% | 32%
|  | Source(s) | PIU Quarterly, and Annually.
Impact Weighting (%) |  |  |  |  | Risk rating | (H, M, L) | Medium
Output 2 | Output 2 Indicator 1 | [6 empty] | Assumptions
CCROs issued in a participatory and cost-efficient manner in project districts | Number of demarcated and adjudicated land parcels | Planned | 3597 | 25000 | 110000 | 175000 | 310000 | VLUP process will not spark new disputes that will slow down the CCRO processes.
|  | Achieved |  | 16540 | 147550
|  | Source(s) | PIU reports, Village registries, District Offices and Ministry database |  |  |  |  | Stable village councils.
| Output 2 Indicator 2 | [6 empty] | No sub-division of villages during project implementation.
| Number of CCROs registered and issued to land holders | Planned | 3597 | 25000 | 82500 | 110625 | 218125
|  | Achieved |  | 9112 | 50163 |  |  | Legal framework allows for a low-cost approach to be developed. Public awareness and education will help men and women accept land right to all groups in the communty
|  | Source(s) | PIU Quarterly, Semi Annually and Annually and M&E reports.
Output 2 Indicator 3
| % of CCROs collected by landholders | Planned | 45% | 70% | 80% | 80% | 80%
|  | Achieved |  | 0% | 66%
|  | Source(s) | Village Land registries, PIU reports, District Offices, Ministry data base
Output 2 Indicator 4
| Average cost of issuing CCROs in Programme area | Planned | 24 | 20 | 14 | 9 | 9
|  | Achieved |  | 15 | 10
|  | Source(s) | PIU Quarter and Annual reports.
Costs of CCRO defined as cost for adjudication, tools, transport, printing, stationaries and public awarenes. The cost of programme management is excluded.
Output 2 Indicator 5
| % of CCROs registered to (i) women as individual (ii) men as individual (iii) co-ownership with women | Planned | (i) 9% | 9% | 26% | 26% | 26%
|  |  | (ii) 75% | 16% | 42% | 41% | 41%
|  |  | (iii)16% |  | 32% | 33% | 33%
|  | Achieved |  | (i) 25% | 24%
|  |  |  | (ii) 9% | 38%
|  |  |  | (iii) | 38%
|  | Source(s) | Village land Registries records.
Impact Weighting (%) |  |  |  |  | Risk rating | (H, M, L) | High
Output 3 | Output 3 Indicator 1 | [6 empty] | Assumptions
Policy and institutional framework strengthened | Position paper for review of 5 land laws and policy brief with 25 areas for review of laws prepared. | Planned | 0 | N/A | Position paper for review of 5 land laws are prepared | Policy brief with 25 areas for review prepared | Policy brief with 25 areas for review prepared
|  | Achieved | Policy, Legal and Institutional capacities Improved |  | Position paper for review of 5 land laws are prepared
Source(s)
Output 3 Indicator 2
| Number of Village Land Councils trained on land disputes mediation | Planned | 0 | N/A | 70 | 90
|  | Achieved |  | N/A | 39
|  | Source(s) | PIU Progress and performance report
Output 3 Indicator 3
| Number of Ward tribunals trained on land disputes mediation | Planned | 0 | N/A | 40 | 26 | 66
|  | Achieved |  | N/A | 48
|  | Source(s) | PIU Progress and performance report |  |  |  | 17.5
Output 3 Indicator 4
| District land and housing tribunals refurbished and equiped | Planned | 0 | N/A | 1 | 1 | 2
|  | Achieved |  |  | Asessment for renovation of DLHT building completed and BoQ prepared.
|  | Source(s) | PIU Progress and performance report
Output 3 Indicator 5
| Climate change issues incorporated into NLP, PLUM guidelines and piloted. | Planned | Climate change measures in land use are implicitly into Participatory Land Use Planning Guidelines | Climate change issues included in draft NLP. | PLUM Guideline reviewed to incorporate climate change issues in all six steps. | Reviewed PLUM Guideline piloted in the project area | Climate change in Land Use Planning incooperated into PLUM Guideline
|  | Achieved |  | (i) Climate change issues identified and integrated into draft NLP. (ii) Climate Change issues incorporated into PLUM Guidelines, those issues were mainstreamed in all 6 steps of Land Use Planning. | PLUM Guideline reviewed and incorporated climate change issues in all six steps.
|  | Source(s) | PIU report, Land Use Planning commission, Project District Offices, Revised VLUP Guidelines
Output 3 Indicator 6
| Guidelines on the roles and responsibilities of investors, Government and villagers prepared and approved | Planned | Existing guidelines lacks clarity | ToR for guideline in place | Final draft approved by MSG and stakeholders. | Guidelines on the roles and responsibilities of investors, Government and villagers disseminted. | Guidelines informing all land investments in Tanzania.
|  | Achieved |  | ToR prepared and approved by Multi Stakeholders Group for procurement of a consultant. | The procurement of consultant to formulate the Benefit Sharing Model on large scale investment in land is in contract award stage. This study is a prerequisite for preparation of guidelines.
|  | Source(s) | PIU reports, Land Investment Unit at Ministry of Lands, investment regulation, benefit sharing model document

## Compatibility Report
Compatibility Report for 20180814_Reviewed_Logframe_For Annual Review_FINAL.xls
Run on 8/14/2018 11:12
If the workbook is saved in an earlier file format or opened in an earlier version of Microsoft Excel, the listed features will not be available.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 30 | Excel 97-2003