Annual Review – post April 2018

Title: Mining Sector Reform Programme
Programme Value £ (full life): £1,319,560 (TCC component)		Review Date: August 2018
Programme Code: 105844	Start Date: 19/10/2011	End Date: 30/11/2018

Summary of Programme Performance
Year	2012	2013	2014	2015	2016	2017	2018
Programme Score	C	B	B	A	A+	A+	A+
Risk Rating	High	High	High	Low	Minor	Minor	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-105844/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-105844/documents

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

This is the final annual review on the programme and a project completion review will be conducted in three months. The original component of the programme with the World Bank (ProMines) was closed 4 years ago. The focus of this annual review is therefore assessing the progress of the remaining component with The Carter Centre (TCC) in the past one year. The external operating context has changed since the last annual review as follows:

- The Mining Code was revised in May 2018. A number of the mining companies expressed concerns over some of the provisions (related to taxes and a reduction of the stability period from 10years to 5 years).
- The near-suspension of the DRC from the Extractive Industries Transparency Initiative (EITI) due to the delayed publication of the 2015 report;
- A further postponement of the presidential elections that was due to take place in December 2016 now scheduled in December 2018;
- New conflicts in the Kasais, Ituri, North Kivu, South Kivu and Tanganyika
- Two new Ebola outbreaks that occurred in the Equateur province and Eastern DRC

Given the importance of the extractives sector in the DRC and the need for improved transparency and governance, in 2013, DFID reallocated funding to TCC’s extractives programme, “Advancing Transparency and Accountability in the Democratic Republic of Congo’s Extractive Industries”. TCC’s programme would be delivered through working with Congolese civil society organisations (CSOs) to advocate for fiscal reform, analyse revenue data, and improve the DRC’s EITI process and reporting. With CSOs empowered to substantively participate in this agenda, and with skills development they can influence reforms to improve accountability of mining sector revenues and ensure the sector better contributes to the DRC’s development.

DFID funded TCC through two Accountable Grants - the first grant from October 2013 to January 2015 and the second grant from September 2015 to November 2018. The TCC component has three outputs:

1. Congolese civil society better understands EITI implementation in the DRC, and is able produce contributions on EITI reporting and processes in the DRC.
2. Congolese civil society partner develops mining sector revenue analysis skills
3. Congolese civil society partners develop skills to use EITI data and other data for advocacy and produce interim deliverables for the implementation of evidence-based advocacy.

Summary supporting narrative for the overall score in this review (1/2 page)

TCC has made strong progress against the milestones and targets in the log-frame, in most cases exceeding expected targets. The main achievements of the TCC and their partners since the last Annual Review are as follows:

- Successfully influenced EITI to ensure social expenditure analysis was a key part of the EITI process – this included developing a social expenditure framework which has been adopted and approved by the EITI executive committee
- Worked with the Government of the DRC (GoDRC) to include a standardised measure of social expenditure contributions in the new Mining Code
- Undertook revenue analyses of two mining projects, Tenke Fungurume (TFM) and Alphamin Bisie
- Continued improvement of the capacity of CSOs in the DRC extractives sector
- Increased engagement of women on the programme through the inclusion of two women-led CSOs (DYFREN[1] and DYFEM[2]) as partners on the programme (with a key recommendation from DYFREN being taken forward by EITI)
  [1] Dynamique des Femmes des Mines
  [2] Dynamique des Femmes sur les Ressources Naturelles
- CSO partners and TCC have increased their profile as the ‘go-to’ organisations in their areas with respect to understanding the EITI process. They are increasingly invited to EITI workshops and meetings, including EITI executive committee meetings chaired by the Minister of Portfolio with the Minister of Mines as the Vice Chair). More notably at the May 2018 EITI executive committee meeting, TCC were invited to present their report on state-owned mining company, Gecamines – historically - it is understood that no other CSO/NGO has been invited to present at this forum before
- Some of the CSOs are now viewed as the ‘go-to’ organisations in their areas with respect to understanding the EITI process
- Enhanced their working relationships with EITI, GoDRC and mining companies
- Three recently appointed members of the EITI executive committee (announce at the July 2018 meeting) are from organisations that TCC had previously trained using DFID funding (under the previous phase)

All this is a testament to the level of influence and impact that TCC (and by extension the CSOs they have supported and trained) are beginning to have with GoDRC, the EITI and the mining companies.

Based on the above summary and detailed assessment of the progress against the last annual review (and log frame targets) as described in later sections, the review team judge that the overall outcome score of this programme is an “A+”.

Recommendations for the year ahead (1/2 page)

The programme will end in November 2018 with the majority of the activities planned to be completed by October 2018. It is not envisaged that TCC can take forward any recommendations made before the DFID programme ends, but they should consider the following to ensure the impact and progress made is maintained:

- TCC to leverage funding to maintain momentum and continue building CSO capacity
- TCC to work closer with the EITI-DRC to build their capacity and ensure long-term improvements in transparency and governance of extractives
- TCC to ensure public dissemination of the key findings from the revenue analysis work on TFM and Alphamin Bisie projects and to use the data for advocacy for economic reform

A recommendation for DFID DRC is to use evidence and the results achieved from this programme to inform wider policy and programming decisions with respect to the extractives / mining sector of the DRC.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Congolese civil society better understands EITI implementation in the DRC and is able produce contributions on EITI reporting and processes in the DRC.
Output number per LF		1.1	Output Score	A+
Impact weighting (%):		33%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress	Remarks
1.1a. Percentage of men and women of civil society organizations that have increased their knowledge on the EITI process and reporting by at least 20%.	72% (average)	85% (average)	Exceeded target
1.1b. Overall level of satisfaction among men and women of civil society organizations participating in TCC-led workshops held on monitoring and advocating for improvements to EITI-DRC processes and reporting.	87% (average)	86% (average)	Slightly below target
1.1c. Cumulative number of contributions by members of civil society developed for use in advocacy with key targets of the EITI-DRC process.	10	12	Exceeded target

Provide supporting narrative for the score

Two out of three targets (knowledge acquired & contributions made by CSOs) have been exceeded with one indicator (satisfaction levels of CSOs to TCC-led workshops), coming in just below the target by 1%.

TCC provided hands-on training to three CSO partners, (1) ADDH[3] in Kolwezi, (2) DYFEM in Goma, and (3) DYFREN in Lubumbashi to improve their ability to monitor and advocate for EITI improvements.
[3] Action pour la Défense des Droits Humains

The knowledge improvement was measured through pre-and post-training evaluations that TCC undertook to assess the level of knowledge gained on the subject. Through interviews held with ADDH and DYFREN, it was clear that they had considerably increased their knowledge and understanding of the EITI process, with ADDH indicating that they were seen as the ‘go to’ organisation for information on the EITI process in Kolwezi. Both organisations indicated that they were confident in having frank discussions with the mining companies with respect to EITI-related work.

Thus far, partners have provided 12 contributions to the EITI process, which exceeds the target of 10. These contributions included analyses and recommendations at each step of the EITI process, including:

- The 2015 EITI-DRC report
- The 2016 EITI scoping report
- The social expenditure framework
- The 2016 EITI contextual report
- EITI’s three-year work-plan
- The annual progress report

In addition, TCC advocated to EITI-DRC as well as to the International Secretariat for EITI to publish the 2016 contextual report in parts to enable CSOs and other stakeholders to feedback – the report was subsequently published in parts. As part of the annual review, the review team met with EITI, both in Lubumbashi and Kinshasa and they reinforced the value they placed on TCC and their CSO partners as they have made fundamental contributions to the EITI processes and quality of the EITI reports.

The average satisfaction levels with the workshops came in just below the target, mainly due to participants being unhappy with the delays experienced in publishing the 2015 EITI report and the tight schedules that were imposed by the EITI (workshops reduced from 3 to 2 days) in the last quarter.

Lessons identified this year, and recommendations for the year ahead linked to this output

The lessons learnt, and thus recommendations to be taken forward include:

- The need to be flexible and adaptive by maintaining a fluid timeline as well as supplementary activities / interventions to accommodate changes to EITI activities (e.g. the delayed publication of the 2015 EITI report had a direct impact on TCC’s ability to undertake activities on this component).
- Ensure sufficient planning beforehand to better manage and anticipate the release of EITI deliverables and the subsequent pressures on timeframes for CSO’s / TCC to complete their activities feedback.
- Review format of workshops to ensure key content can be covered in 2 days should time pressures necessitate changes.

Output Title	Congolese civil society partner develops mining sector revenue analysis skills.
Output number per LF		2.1	Output Score	A+
Impact weighting (%):		33%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1a. Percentage of men and women of civil society organization that have increased their knowledge on mining sector revenue analysis by at least 20%	66% (average)	76% (average)	Exceeded target
2.1b. Overall level of satisfaction with TCC-led workshops held on mining sector revenue analysis.	88% (average)	89% (average)	Exceeded target
2.1c. Cumulative number of interim deliverables completed toward the final revenues impact analysis case study.	16	18	Exceeded target

Provide supporting narrative for the score

All three targets under this output have been exceeded.

TCC provided hands-on training to two new CSO partners trained under output 1 (DYFEM and DYFREN) to increase their understanding of the extractives sector revenue flows and payments, and to apply that knowledge to the development of revenue analysis case studies of specific mining projects. The DYFEM team’s case study focuses on Alphamin’s Bisie Mine, while DYFREN is studying the Tenke Fungurume Mine (TFM). As women-led organisations, DYFREN and DYFEM have been key in delivering on the last annual review recommendation to ensure consideration of women and girls on the programme.

As in output 1, TCC measured the knowledge and satisfaction by conducting pre and post training evaluations that measured the level of knowledge and satisfaction with the quality of the training. Thus far, actual scores exceed final targets, with a substantial increase in knowledge gained being achieved. Interviews held with DYFREN in Lubumbashi during the review visit confirmed this finding as the DYFREN team felt their knowledge of fiscal-related subjects had significantly increased as a result of TCC’s capacity-building programme. Specifically, DYFREN mentioned that they valued the methodology and approach used by TCC and through the case study work they have an increase understanding of how mining companies operate and how their financial management and reporting is done.

To date, DYFEM has completed all eight revenue modules and associated deliverables and are working on their final case study report. DYFREN, who began the training at a lower technical capacity/level, has faced some challenges with understanding the highly technical concepts in the trainings. They have thus far successfully completed seven of the eight modules and associated deliverables. DYFREN did note that a key success for them thus far has been having one of their recommendations being taken forward by EITI and being acknowledged for that recommendation. DYFEM and DYFREN have produced a total of 18 deliverables above a target of 16. These deliverables, which include memos, recommendations, reports, analysis, etc., are continuously reviewed and scored by TCC, and have an average quality score of 73% above the target average of 68%. .

Lessons identified this year, and recommendations for the year ahead linked to this output

The lesson learnt, and thus recommendation to be taken forward is to:

Ensure the approach to training and capacity building is based on proactive engagement, an adaptive style and listening to the needs of individual partners rather than a ‘one-size-fits-all’ approach

Output Title	Congolese civil society partners develop skills to use EITI data and other data for advocacy and produce interim deliverables for the implementation of evidence-based advocacy.
Output number per LF		3.1	Output Score	A+
Impact weighting (%):		34%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1a. Percentage of men and women of civil society organizations that have increased their knowledge on data utilization and advocacy by at least 20%.	69% (average)	88% (average)	Exceeded target
3.1b. Overall level of satisfaction with TCC-led workshops held on data utilization and advocacy.	88% (average)	83% (average)	Below target
3.1c. Cumulative number of deliverables developed for using EITI-DRC data analysis in the implementation of the advocacy strategy.	12	15	Exceeded target

Provide supporting narrative for the score

Two out of three targets (knowledge acquired and number of deliverables by CSOs) have been exceeded with one indicator (satisfaction levels of CSOs to TCC-led workshops), coming in below target.

Under Output 3, TCC is supporting three CSO partners (1) OCEAN[4] in Kinshasa, (2) ACIDH[5] in Lubumbashi, and (3) IBDGH[6] in Kolwezi to use EITI data to advocate for improved compliance with transparency rules and governance reforms that promote accountability and good governance of the extractives sector. These partners have been trained in the analysis of EITI data and how to use this data for advocacy. In addition, the partners are receiving TCC support to develop advocacy strategies and engage in outreach activities related to provincial taxes and social expenditures.
[4] Organisation Congolaise des Ecologistes et Amis de la Nature
[5] Action Contre l'Impunité pour les Droits Humains
[6] Initiative Bonne Gouvernance et Droits Humains

As in Outputs 1 and 2, TCC measured the knowledge and satisfaction by conducting pre and post training evaluations that measured the level of knowledge and satisfaction with the quality of the training. In terms of knowledge gained, the actual scores achieved by partners exceed final targets, demonstrating a significant increase in knowledge. However, the level of satisfaction with the TCC-led workshops stands at 83%, 5% less than the expected target of 88%. This is due to an unusually low score in the first quarter of 2018, in which the scores reflected frustration with delays in execution of their sub-grant (80% actuals vs. 90% target) and a lower score in the second quarter of 2018, in which a particular participant’s assessment dragged down the overall satisfaction scores (85% actuals vs. 90% target).

In terms of deliverables, the cumulative number is 15, already exceeding the final target of 12. The annual review team met with OCEAN, ACIDH and IBDGH in Kinshasa, Lubumbashi and Kolwezi respectively and established that they all felt their skills and knowledge of the EITI process, reports and data had significantly improved. In addition to the previously-reported (in the last annual review) success where OCEAN developed a common definition of what constitutes ‘social expenditure’, OCEAN were particularly proud of their work related to social expenditure in mining. OCEAN developed a social expenditure framework which has since been adopted by EITI who are taking this forward as part of their work-plan. OCEAN also proposed to the Ministry of Mines, the standardisation of levels of social expenditure paid by companies, resulting in this recommendation being adopted under the revised Mining Code (0.3% of revenues to be spent on community development, etc.). Finally, in analysing the new Mining Code’s provisions on the social obligations of mining companies and sustainable development plans, OCEAN have developed a guidance note related to social expenditure and obligations which will be used to raise awareness amongst mining companies.

Lessons identified this year, and recommendations for the year ahead linked to this output

The lessons learnt, and thus recommendations to be taken forward include:

- Ensure proactive communication and engagement with partners. The lower-than-expected satisfaction scores from the partners under Output 3 indicate that better need to communication with the partners prior to workshops.
- Proactively communicate and agree the process of the sub-granting especially when working with new partners. The low satisfaction scores by some of the partners are a reflection of the intensive and time-consuming process undertaken. I line with the guidance the process required due diligence, risk assessment, detailed work plans and budgets reviewed at both the field and headquarter levels. Given low partner capacity, these documents often require several rounds of feedback and revisions before meeting acceptable standards.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

Whilst there was no theory of change in the original business case or subsequent addendum, the overarching goal of TCC’s programme is to improve governance of the DRC’s extractives sector by:

- Increasing data accessibility;
- Improving revenues management; and
- Supporting more responsible, sustainable, and equitable investment

In pursuit of this goal, the programme aims to support CSOs to contribute to EITI implementation; to effectively research and analyse revenue impacts and use this analysis for advocacy to improve fiscal governance; and to effectively utilise EITI data for advocacy. Should these improvements be delivered, and with increased advocacy from CSOs, it is envisaged that the CSOs could influence reforms which will improve accountability and expenditure of mining revenues which will result in development and growth being achieved in the DRC.

Whilst there have been no changes to the programme’s aims and objectives in the last year, the TCC component represents a considerable scale down (in terms of budget and results) of the original business case (which was based on ProMines). The original business case adopted a comprehensive approach that included transparency and access to information but also worked with the government to improve its capacity to manage the mining sector, and collection of taxes and royalties.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

The programme has achieved and generally exceeded expectations with respect to the indicators related to outcomes and impact.

There are two impact-level indicators on the programme - both have achieved the log frame targets as follows:

Impact: Governance of the DRC's extractive sector is improved (sector data is more accessible, governance of revenues improves, and investment is more responsible, sustainable and equitable)
Impact Indicator	Target	Achieved
A. The DRC is in compliance with the EITI.	Yes	Yes
B. Cumulative number of sector-wide changes to fiscal governance of the DRC extractives sector influenced by civil society advocacy	4	4

There are five outcome-level indicators on the programme – they have all been exceeded as below:

Outcome 1: Congolese civil society partners are able to effectively monitor, and advocate for improvements to, EITI-DRC processes and reporting
Outcome Indicator	Target	Achieved
1a. Number of partner civil society recommendations taken into account in final EITI-DRC reports and improved EITI-DRC process.	12	34
1b. Cumulative number of EITI contributions from civil society teams receiving TCC’s technical support that achieve a quality of at least 60%.	9	12

Outcome 2: Congolese civil society partners are able to effectively research and analyse revenue impacts and use their analysis to advocate for improved fiscal governance of key mining projects/companies
Outcome Indicator	Target	Achieved
2a. Quality of civil society team’s case study interim deliverables.	Average of 68%	Average of 73%

Outcome 3: Congolese civil society partners are able to effectively utilize EITI-DRC data and other sources for advocacy to address sector-wide fiscal governance challenges
Outcome Indicator	Target	Achieved
3a. Cumulative number of interim deliverables on using the data and associated advocacy from civil society teams receiving TCC’s technical support that achieve a quality of at least 60%.	6	10
3b. Number of meetings with targeted stakeholders.	8	15

There will be a review of the DRC’s EITI validation in October 2018 (after EITI-DRC requested a three-month extension of the validation from the EITI International Secretariat). EITI-DRC has made significant progress toward validation by submitting the 2015 final report, completing the 2016 scoping report, as well as submitting key pre-validation documents, including the 2016 contextual report, the 3-year work-plan and the annual progress report. The CSO partners have made substantial contributions to these deliverables. Specifically, the adoption of OCEAN’s framework on social expenditure reporting is an important milestone on the road to broader reforms on how extractive sector social expenditures are managed in the DRC. TCC and its partners will continue to engage and provide substantive and process-oriented support and recommendations to EITI-DRC to ensure it meets the 2016 EITI standards.
Explain major changes to the log-frame in the past year (1/2 page)

Based on recommendations in the previous annual review, and based on achievements made in the previous year, DFID challenged TCC to increase their level of ambition and to significantly increase targets for the extension phase of the project. As a result, TCC increased the majority of their stated targets resulting in a revised log-frame and targets being approved in May 2018. The following key changes were made to the log-frame indicators:

INDICATOR	ORIGINAL TARGET	FINAL TARGET
Outcome Indicator 1a	8	12
Outcome indicator 2a.	60%	68%
Output indicator 1.1a	60%	72%
Output indicator 1.1b	60%	87%
Output indicator 1.1c	9	10
Output indicator 2.1a	60%	66%

Describe any planned changes to the log-frame as a result of this review (1/2 page)

No further changes are expected to be made to the log-frame given the impending closure of the programme in November 2018.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

TCC continues to ensure value for money (VfM) by focusing, where practical, on the economy, efficiency, effectiveness, and equity of its interventions. TCC aim to apply a VfM ‘lens’ in all their activities through selection of least cost for key programme expenditure, combining meetings to reduce costs, monitoring of workshop days, reduction of training days and close monitoring of partners budget. TCC have trained 575 participants at a total training cost of approximately £145 per participant which is within acceptable norms.

The most significant cost drivers for the project are staff salaries, consultant fees, travel, meetings / trainings and sub-grants. TCC continuously review and assess mission costs, reducing costs where possible; regular oversight for civil society partners, particularly with regard to spending. They also use existing tools and skills to implement project activities, thus saving time and money, and aim to limit administrative overheads as much as possible. TCC spreads core cost coverage across donors and invests significant institutional funds to fill in any funding gaps. Whilst the staff salaries are a key cost driver, they are also the most significant driver of project performance, in addition to the enthusiasm of its partners, the skills and competencies of TCC staff and the technical support they have provided to the CSOs to be more effective.

In terms of achieving equity, TCC systematically involve women in project activities (as they did with DYFREN and DYFEM) and ensure effectiveness by working closely with partners and civil society more broadly, to develop the skills and environment necessary to ensure that the programme achieves its full impact and that the impact is sustainable. In particular:

- TCC staff regularly review mission costs (meetings and travel). This has led TCC to identify ways to save costs on travel (combining meetings, lengthening a single mission / field visit to avoid multiple missions, leveraging other donor funding, etc.) and to update its budget appropriately on a quarterly basis.
- TCC’s sub-grantee selection process included a rigorous assessment of organisations’ technical and organisational capacity, and TCC staff worked closely with selected partners to develop practical and efficient project budgets. In addition, one of the partners and some of the members of other partners have worked with TCC previously and thus had baseline knowledge of TCC’s sub-grant policies and procedures, limiting the time needed for onboarding.
- The TCC component relies largely on previously developed training modules (the Revenues Analysis Training Modules and advocacy training modules), which has resulted in staff time and resources saved.
- By using pre and post testing of participants’ knowledge, it is possible to ascertain (some) of the benefits of the programme and therefore, provide a basic benefits to cost ratio allowing TCC to continuously assess the net benefits of the programme.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

Whilst it is understood that the current programme is closing in November 2018, given the inroads that TCC and their partners have made in the transparency and accountability in the extractives sector, it is recommended that DFID continue to support TCC and/or their partner organisations to enable them to continue the positive work they are doing. There is considerable momentum that has been achieved by TCC in driving forward reform in the extractives sector of the DRC.

There are currently very few development partners who are working on transparency and governance in the extractives sector DRC. The support that DFID has been providing has thus far yielded some great results, but there is scope to do much more. The risk of not supporting TCC or similar organisations striving to achieve transparency and improved governance in the extractives sector is that the revenues secured from extractives activities will continue to benefit the few rather contribute to inclusive economic growth and poverty reduction.

The project continues to represent value for money. Whilst the most recent grant is relatively small in value (£539k), the impact that TCC’s work has had on the DRC’s mining sector is impressive and has already started to influence the approach of, and gained respect from the EITI, mining companies and the Government of DRC (at both provincial and national level). For example, through their advocacy and working with EITI, TCC have, amongst other achievements, (1) managed to improve and increase the level of contracts that are published (that hadn’t been published previously), (2) encouraged CSOs and other organisations to be more vocal and advocate for change to the extractives sector, (3) made history by being invited to the EITI executive committee to present their report on Gecamines – the result was the committee agreeing to the establishment of a sub-committee to probe further into the findings of the report, (4) built capacity of CSOs whose work has been incorporated into the EITI’s plan of work and the new Mining Code and (5) indirectly influenced, through IBDGH’s work on tax and fiscal issues, the Government of the Lualaba province’s decision to open an office of tax collection from mining activity, which has historically been in Kinshasa – this will facilitate receipt of provincial taxes from the mining companies in line with the new Mining Code.

Through the work they have been undertaking under the programme, TCC and their partners have cemented their place in the DRC extractives sector as organisations that can be invited to the ‘top table’ when discussing EITI-related issues. The effectiveness of the programme is therefore evident as noted above, but also as can be seen through progress against the log-frame targets, with impact and outcome target indicators being achieved already. TCC have reinforced the capacity of the various CSOs, and as a result increased their level of engagement on the EITI processes. Using tools developed from previous phases has helped TCC to be more efficient in their delivery and overall, their objectives have been met and in most cases, exceeded.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

With respect to the high-level risks identified by DFID, the following assessment is made, resulting in an overall risk rating of ‘Moderate’:

- External context – Major: The political economy of the extractives sector, the recent Ebola epidemic in the East, tension and violence around the elections all pose risks to the implementation of TCC and their partner’s work.
- Operational – Minor: TCC have not experienced a high staff turnover over the last year. The start of the programme was delayed due to the delay in the publication of the 2015 EITI report by the EITI, but this was mitigated by granting an extension to TCC to enable them to finalise their work.
- Reputational – Minor: The work of TCC and their partners has resulted in positive reactions from the community, and interestingly from the mining companies and the government. The role of CSOs in the extractives sector and the EITI process has increased and their contributions have been recognised across the sector.
- Delivery risk – Minor: the programme continues to perform well and exceed expectations. However, it is possible that as a result of increased focus on the upcoming December 2018 presidential elections in the DRC, this could have on TCC’s work as there will be more attention given to the elections than responding to TCC reports and advocacy for transparency and accountability. This may result in the momentum that has been gained over the year by TCC being lost as government focuses on pre and post-election activities. DFID will stay in close contact with the TCC team to monitor the impact and ensure this doesn’t affect delivery of TCC’s work
- Fiduciary risk – Minor: A due diligence assessment (DDA) was undertaken on TCC in June 2018 (the previous DDA was done in May 2015). No major issues were identified. TCC also undertakes DDAs of its downstream partners which ensures that there are financial controls at all levels. There have been no reported fraud cases on the programme in the last year.
- Safeguarding risk - Moderate: The nature of TCC’s work means that staff and partners risk being harassed and intimidated during the course of their work. In addition, with the elections due to take place in December 2018, and final presidential candidates likely to be announced in September 2018, there is a possibility that there may be some protests or similar in the run up to the election period, and once the final presidential candidate list is published. DFID and TCC have monthly catch up calls to discuss delivery progress and risks, and TCC maintain close contact with partners and their security advisor to ensure they are kept up to date with the latest developments and assessments of the security situation. Through close engagement, monitoring and communication, it is possible to mitigate and manage this risk.

TCC have also been providing risk registers to DFID as part of their quarterly reports and during monthly team progress meetings with DFID, TCC have been proactive in highlighting any risks that DFID should be aware of.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

Partner’s Performance:
Since the finalisation of the second accountable grant to TCC in August 2017, the implementation of the programme activities has been delayed due to the delay in the publication of the 2015 EITI report. Given the bulk of the activities are centred on scrutinising and analysing the EITI report and data, TCC and their partners were unable to start their work-plan as planned until the release of the EITI report, which occurred towards the end of December 2017. As a result of the delays experienced, TCC requested a no-cost extension to the agreement and a 4-month extension was subsequently granted, resulting in a revised end date of 30 November 2018 (from 31 July 2018). A DDA was therefore undertaken on TCC and no major concerns were noted. TCC also undertook DDAs on their partners prior to disbursements of the sub-grants and no major issues were observed.

Whilst there were concerns around the implications of the release of TCC’s report on Gecamines, the publication of the report did not adversely affect TCC’s performance in the delivery of the programme. TCC and their partners performed very well, in most cases exceeding their targets and managed to gain the respect of the EITI, mining companies and government. They have managed to influence content within the revised Mining Code, as well as EITI’s plan of work and approach with respect to social expenditures.

Some key observations related to TCC and partner performance is below:

- Despite the relatively small budget, TCC have delivered against the agreed targets and the programme has had a positive impact on the governance and transparency agenda in the DRC mining sector.
- Going beyond the log-frame targets, it would be beneficial to see the impact that the TCC work, especially related to mining revenues, has had on the DRC economy and local community development.
- An improvement in the technical skills and abilities of CSO partners has resulted in effective engagement with EITI and the mining companies.
- Partners appear to be very engaged in the EITI process and noted that they have gained significantly from the TCC support at both an organisational and personal level.
- TCC staff are currently invited to all EITI meetings due to their expertise and sector profile.
- Assessment of performance of the CSO partners is through a formal process using tests and evaluations before and after each training.
- Delays on the release of the EITI report affected TCC and partner activities during Q1 & Q2 of 2018.

TCC reporting has improved over the last year. At the start, there were numerous exchanges between DFID and TCC to ensure the format of the reports was in line with DFID’s expectations as DFID felt some key information was missing from their reports. Given the change in SRO for the programme, DFID used this as an opportunity to reiterate key messages to TCC on expected reporting standards and timelines. TCC have since addressed DFID’s requirements and tailored their reporting accordingly. TCC and DFID agreed to reporting timelines which have mostly been adhered to, with the exception to the most recent quarterly report, which was delayed by a couple of weeks.

Financial Performance:
There were a few issues experienced at the start of the year with respect to financial forecasting. DFID engaged with TCC to ensure future forecasting was accurate. The development of supplementary programme activities (options) that could kick off if originally planned activities were delayed due to broader policy changes or delays ( Eg EITI repot). This has since improved.

A summary of the forecast versus the actual is provided below. Overall, the expenditure is behind forecast due to delays experienced at the start of the grant.

Overall BUDGET	FORECAST spend from August 2017 to July 2018	ACTUAL spend from August 2017 to July 2018	Variance
£539,000	£446,426	£405,246	£41,180 (underspend)

Key financial dates are below:

Date of last narrative financial report(s)	13 August 2018
Date of last audited annual statement (s)	Due August 2018

There are no assets related to TCC’s accountable grant.

DFID’s Performance:
DFID’s engagement with EITI has also developed significantly over the last year, with DFID regularly being invited to, and attending the EITI executive committee meetings as well as the Extractives Sector Group Thematic Meetings chaired by the Minister of Mines. As an active member of the DRC Donor Group on Mining, DFID has regularly participated in donor meetings, including a meeting with the Minister of Mines where DFID had to explain and defend its support to TCC and the CSOs.

DFID introduced monthly progress calls with TCC, over the last year, to ensure that any issues that arose were dealt with quickly. This also facilitated better engagement between TCC and DFID given the core TCC team are based in Lubumbashi.

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

TCC uses their internal tools to monitor the performance of partners. Pre and post-evaluations for the training and workshops are conducted. The annual review interviews with the CSO partners confirmed that TCC engage regularly and conducts ‘check-in’ with its partners, through telephone conversations, face-to-face meetings and interactions at the workshops. On average, TCC were visiting partners every 2 months and in the words of one of the TCC partners, DYFREN, they indicated that ‘TCC has been with us all along the journey rather than just handing over the money and walking away’. This was the general sentiment from the other CSOs interviewed as well as EITI (the latter having no ‘ulterior motives’ to provide positive feedback on TCC given they do not receive any financial assistance from TCC/DFID). It was also noted, that the CSO partners also have an opportunity to evaluate TCC’s performance, so a 360 degree feedback process being applied on the programme. It is therefore of the view that TCC have been good at monitoring progress and performance of the partners.

DFID monitoring introduced, monthly progress calls in the last year to discuss monthly progress, key issues and risks, updates, finances and proposed activities for the upcoming month were agreed. This monthly call is attended by the DFID SRO and Programme Manager, TCC’s senior finance and administration team in Atlanta, USA, the TCC Country Director in Kinshasa and the lead Programme Manager in Lubumbashi. This regular forum has helped DFID to keep on top of progress on the programme. In addition to the monthly calls, adhoc meetings have taken place between DFID and TCC whenever the TCC team are visiting Kinshasa from Lubumbashi.

As part of the annual review, DFID SRO and Programme Manager had the following individual meetings:

Tuesday 31 July (Lubumbashi) –	TCC & ACIDH
Wednesday 1 August – (Kolwezi) -	ADDH & IBDGH
Friday 3 August (Lubumbashi) –	DYFREN & EITI Provincial team
Monday 13 August (Kinshasa) –	EITI National team
Tuesday 14 August (Kinshasa) -	OCEAN

The meetings with EITI were useful to get their independent views on TCC, their partners and the impact they have had on the extractives sector and community. The interviews with the CSOs consisted of a number of key questions covering a range of topics including the support received from TCC, level of interactions with the TCC team, lessons learnt, challenges faces, successes achieved and any negative or positive impacts observed.

Evidence (1/2 page)

The annual review process provides an opportunity to collate evidence of impact of the programme, as well as to independently validate information reported in TCC’s reports. Whilst there will be some tangible results and data that result from this annual review, other sources of evidence include interviews with the various CSO partners, EITI and TCC staff members, field monitoring visits to speak to other stakeholders and analysis of the number of reports and documentation delivered by TCC and their partners being discussed in extractives and other public forums. The biggest demonstration and evidence of impact of TCC’s work over the last year has been:

- The willingness of EITI to seek inputs from TCC and their partners during the process of developing their report and data, but more importantly, incorporating recommendations received into their work-plan.
- Participation of TCC and their partners at national-level EITI meetings.
- Incorporation of OCEAN’s proposal regarding the standardisation of social expenditure contributions from mining companies into the new Mining Code.
- An unprecedented invitation by the EITI executive committee for TCC to present their Gecamines report at the committee meeting which was attended by three government Ministers, including the Minister of Portfolio and the Minister of Mines and DFID.

Learning (1/2 page)

TCC, the CSO partners and DFID have learnt a number of lessons on the programme. A selection of the top lessons learnt includes:

- Being able to advocate for mining sector fiscal reform requires a detailed understanding of the DRC mining sector, including the operational models of mining companies, their reporting structure, fiscal regime of the sector and the EITI process and reporting
- Given the very high level of CSO-engagement in the DRC EITI process, in comparison to other countries who are part of the EITI, working with CSOs is key element to unlocking improvements in the governance the DRC mining sector, including improved transparency and accountability.
- EITI reports are large technical documents which need a considerable number of days to read through. As such, CSO partners, depending on their level of competence, need more time to go through the report as they are not technical experts.
- Budget constraints and increasing inflation leads to increased operational costs, such as increased costs for hosting workshops. This means careful selecting of attendees and target segment to workshops given the restrictions on the numbers.
- The EITI process and timescales are outside of TCC’s control. As such, any changes to EITI’s schedule with respect to releasing of their report could impact TCC and their partners’ activities if they do not adopt a flexible approach to the delivery of their programme. Given the likelihood of these external forces impacting on the delivery of TCC’s work, it is advisable that TCC and their partners build in flexibility into their planning process.
- TCC needed more time then expected to get new CSOs on board and to train them. This was not taken into the account in their work-plan. A key lesson is therefore to ensure that partners are categorised in terms of their level of experience and capabilities to enable TCC to better plan for the time needed with each partner, rather than apply a one-size-fits-all approach.
- The work with DYFREN and DYFEM is evidence that even on advocacy programmes in the extractives sector (which others may deem to be a male-dominated sector), it is possible to effectively engage women, there are a number of women who are interested and committed to improvements in the extractives / natural resources sector.
- The sensitiveness around tax-related matters makes research work challenging, especially when dealing with the provincial authorities, as they are normally reluctant to discuss revenues, etc. it is therefore important to gain their trust and confidence to ensure they are engaged in discussions around finances, tax, etc.
- There is a gap between provincial and national authorities regarding transparency on revenues. Both need to be train on the understanding of mining taxation.
- Relationships, organisational profile and visibility within the DRC extractives sector are key to gaining influence and buy-in from the government.

In addition to lessons learnt as highlighted above, TCC have gained an increased interest in continuing the work they have started in delivering reforms in the extractives sectors. Key areas of interest for possible future work include:

- Sub-contracting and local content-related interventions (how this impacts on the DRC’s economy)
- Social expenditure and its impact on local community development. This will include traceability of social expenditure funds (train the community to monitor how the extractives companies are contributing to local development)
- Deepen the governance and transparency work (advocacy activities around payment of provincial taxes needs to be continued)
- Mapping of cobalt sector (issues related to transparency and human rights in the cobalt sector)
- Working with other partners such as universities and administration authorities in addition to CSOs
- Assessment of the impact of the new Mining Code on mining activities in the DRC.
- Assess the impact of mining activities in agricultural and other economic sectors.

Progress on recommendations from previous reviews (1/2 page)

Progress made on addressing recommendations from last year’s annual review as outlined in the table overleaf:

2017 Annual Review Recommendation	Progress made
The short-term nature of the DFID support provided so far made it difficult for the Carter Centre to effectively measure and assess their impact (advocacy and influencing as well as capacity building beyond the evaluation of the specific training). The new extractives Business Case (BC) should consider this very carefully.	The Business Case for the new extractives programme has been drafted, but is currently on hold until finalisation of the office-wide strategy.
There is evidence of the diffusion of the skills learnt by the different CSOs. This is not formally measured or assessed under the current log frame but something that should be considered, along other measures for sustainability of the projects’ capacity building activities.	The current log frame formally measures and captures the ‘diffusion of skills’ learnt by the CSOs. For example, the log-frame includes an outcome indicator which measures the number of recommendations taken into account in final EITI-DRC reports
The new BC should also consider gender and women issues more carefully. The current project tried but did not fully succeed in securing long-term attendance of women in the training events. That said our focus should not be limited to inclusion of women in training. Under the extended grant (until July 2018) the Carter Centre will work with a women led CSO which will help address this issue. This also could be an opportunity to identify specific issues that affect women and girls in the mining sector that could be considered in the new Business Case.	The new extractives BC is on hold. However, under the current project, TCC have been working with two women-led CSOs, La Dynamique des Femmes des Mines (DYFEM) and La Dynamique des Femmes pour les Ressources Naturelles (DYFREN).
The revised log-frame, setting the right level of ambition for programme results in the next phase, should be finalised by December 2017	The log-frame was revised and the targets submitted by TCC were challenged and increased by DFID to ensure the targets were more ambitious.