Project Completion Review - Top Sheet

This Top Sheet captures the headlines on the programmes performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	January 2018

Title: Safety, Support and Solutions Programme for Refugees and Migrants in Europe and the Mediterranean region
Programme Code: / 300264	Start Date / 11 August 2016	End Date: / 11 December 2017
If programme was closed >1 month early please describe in a few words why.

Summary of Programme Performance

Year	2016/2017
Programme Score	A
Risk Rating	Moderate

Financial Position

Original Programme Value	£33.3 million
Extensions/ amendments	A three month no-cost extension was approved by the Head of Migration and Modern Slavery Department on 6th June 2017.
Log-frame revisions (with dates)	The first log frame was drafted on 11/07/2016 as part of the Business Case submission. This PCR uses the version of the log frame agreed on 25/07/2017.
Total programme spend	£32,369,720

Follow up actions required following closure

- All DFID funded assets will be disposed of following DFID guidelines, as part of the project closure process.
- Audited accounts submitted after the formal closure of the project will be reviewed by DFID, with identified issues followed up with partners as necessary.
- Catholic Relief Services (CRS) alerted DFID to a fire incident at a site in Krnjača, Serbia, on 25/08/2017. A police report, due 30 days from the incident, was not completed and on 8 January 2018 police gave permission to clear the damaged area, meaning the investigation is deemed complete. CRS are finalising a report of the losses incurred (damage to building that had recently been renovated), which are approximately £9,000. This will be submitted to DFID’s Finance and Control Department for write off.

List of Acronyms

BRC	British Red Cross
CMR	Central Mediterranean Route
CRS	Catholic Relief Services
CRIs	Core Relief Items
DRC	Danish Refugee Council
DTM	Displacement Tracking Matrix
EMR	Eastern Mediterranean Route
FEDI	Fund for Evidence Data and Information
NFIs	Non-Food Items (clothes, sleeping equipment, hygiene kits etc.)
IOM	International Organization for Migration
MERF	Migration Emergency Response Fund
MMP	Mixed Migration Platform
IRC	International Rescue Committee
SSS	Safety Support and Solutions (Programme)
UNHCR	The UN High Commissioner for Refugees
WGPF	Women and Girls Protection Fund

A. Introduction and Context

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/5722534.odt
DevTracker Link to Log frame:	Awaiting upload

Context

Throughout the programme period of 2016 to 2017, Italy, Greece, the Western Balkans and several African countries along the main migration routes towards Europe faced continued challenges posed by large movements of refugees and irregular migrants[1] .
[1] IOM defines a migrant as any person who is moving or has moved across an international border or within a State away from their place of residence. This report will use the term migrant, or irregular migrant, to depict persons whose movement takes place outside the regulatory norms of the sending, transit and receiving countries. A refugee is a person who, "owing to a well-founded fear of persecution for reasons of race, religion, nationality, membership of a particular social group or political opinions, is outside the country of his nationality and is unable or, owing to such fear, is unwilling to avail himself of the protection of that country.

Eastern Mediterranean Route (EMR[2])
[2] From Turkey to Greece and onwards through the Western Balkans to Northern Europe.

From early 2015 until March 2016 more than a million refugees and migrants travelled to Europe, most of them via the Eastern Mediterranean Route (EMR). This mass movement came to an abrupt halt as a result of multiple factors including the closure of borders along the route and the agreement of the EU-Turkey Statement in March 2016. This agreement effectively “fast-tracked” the processing of asylum claims on the Greek Islands, seeking to return those eligible for readmission back to Turkey. Migrants and asylum seekers who had wanted to move further along the route (to Germany, France, and other EU countries) were stranded predominantly in Greece and Serbia. Implementing partners in Europe thus dealt with a largely static situation while being prepared to respond to potential new spikes in need. They addressed critical gaps in the reception of vulnerable people, providing them with safe and dignified shelter, food and other basic services, as well as medical and psychosocial support.

2015-17 monthly migration arrivals by Mediterranean routes

Central Mediterranean Route (CMR)[3]
[3] Links West Africa (Nigeria, Guinea, Cote d’Ivoire, Gambia) Sudan and Eritrea to Niger, Egypt via Libya on to Italy.

While the situation was stabilising along the Eastern route, there remained a notable spike in deaths of those attempting to cross the Mediterranean Sea between Libya and Italy along Central Mediterranean Route (CMR). Since 2013 numbers of arrivals from the CRM to Italy have increased year on year. The rate was expected to continue rising from a record number of arrivals in 2016 (181,000). The first three months of 2017 saw arrivals up by 30% and growing increasingly deadly[4]. The number of fatalities along the CMR looked set to double in 2017 with at least 732 dead or missing migrants in the first three months compared to the previous period in 2016. Moreover 76% of arrivals to Italy in 2017 reported direct experience of at least one of the indicators of trafficking, exploitation or abuse (compared to 10% on the EMR) [5].
[4] For every 1,000 arrivals in Italy in 2016 and 2017, 25 people were reported dead or missing, an increase from 19 in the previous two years (2014 and 15). A similar proportion are thought to die while crossing the Saharan desert from Niger to Libya but data on this is hard to gather and verify.
[5] http://missingmigrants.iom.int/

From July 2017 onwards arrivals to Italy from the CMR also slowed, contributing to the overall reduction in migratory flows along both routes in 2017. In February 2017 a Memorandum of Understanding signed between Italy and the UN-backed Libyan Government of National Accord (GNA) set out plans for enhanced coordination between Italy and Libya on issues of security and irregular migration, with Italy committing financial support and technical assistance to help the Libyans manage their borders. This, coupled with poor weather, is thought to have resulted in the lowest total arrivals to Italy since 2013, at around 119,000 in 2017.

Outline of programme and what it has achieved

The package of interventions supported under the Safety, Support and Solutions (SSS) programme aimed to ‘save lives of refugees and migrants in the Mediterranean region, to protect them in situations of vulnerability, to enable host authorities to fulfil their obligations and to support durable solutions’. It did this by treating the situation not as a series of discreet crises, but as a dynamic response covering the entire migration route. It provided complementary forms of support, including life-saving assistance, protection, information, as well as access to integration support, humanitarian return and reintegration and access to asylum procedures where possible. Overall, the programme successfully adapted to meet the changing needs of the crisis, improving the quality of support for static populations along the EMR while responding rapidly to the worsening humanitarian crisis along the CMR.

This programme succeeded in filling critical humanitarian gaps such as the need for nutritional food, safe shelter and medical assistance for stranded and arriving migrants. It addressed long-term capacity issues, for example, by providing training and support to governments and civil society to better ensure the protection of existing and future migrants. It also succeeded in responding innovatively to emerging needs through the creation of the Migration Emergency Response Fund (MERF), which released small grants to NGOs within 72 hours of an emergency, enabling them to respond rapidly, for example, to provide life-saving assistance to people living outside in -20oC temperatures in Serbia in January 2017.

More specifically, the £33.5 million programme achieved:

- About 129,000 instances of emergency assistance, including food and non-food items (blankets, clothes, washing items, sanitary products) and medical assistance (including psychosocial support) to vulnerable migrants. This included 17,400 vulnerable people benefitting from cash support, who might otherwise have engaged in harmful coping strategies - such as survival sex or illegal labour - to purchase food and other necessities for their families.
- 38,000 people provided with rapid support that met their needs (food and medical assistance) through the development of a rapid response mechanism (MERF).
- 1,300 government officials, NGO staff and volunteers benefitted from training or capacity-building on protection, gender-based violence (GBV), asylum law and human rights to improve humanitarian and migration management responses.
- Nearly 13,800 people benefitting from improved reception services specially designed to cater for the needs of highly vulnerable people, such as women, girls, unaccompanied minors and victims of trafficking to protect them from abuse and facilitate their access to secondary support services (medical and psychosocial support, access to justice, rehabilitation etc.).
- Nearly 250,000 online views of data and evidence products developed to improve the targeting of the humanitarian response and inform states about migratory flows.
- Approx. 42,000 people accessing a combined migration data and policy portal (Mixed Migration Platform) on a monthly basis to inform policy and best practice on migration responses.
- Approx. 37,700 monitoring visits carried out in places of detention and in migrant communities to monitor human rights violations and target protection services towards the most vulnerable.
- Nearly 11,000 instances of support to help identify and register people in need of international protection and facilitate their access to fair asylum processes.

The SSS focused on assisting and protecting the most vulnerable. Our partners used criteria to assess the multiple factors contributing to a person’s vulnerability (age, disability, gender, pregnancy and maternity, race, religion or belief, sex and sexual orientation) and tailored their assistance to address these vulnerabilities. In particular, the SSS programme has been tailored to the specific needs of women and girls through mainstreaming gender-sensitive approaches and protection services and allocating £8m for the Women and Girls Protection Fund. This fund provided targeted services for women, girls and other vulnerable persons on the move, preventing and responding to the risks of sexual and gender based violence, trafficking and other forms of exploitation. This SSS programme fully complied with the International Development (Gender Equality) Act of 2014 and addresses other forms of discrimination, for example, by considering the needs of disabled persons and people of ethnic minorities.

## B: PERFORMANCE AND CONCLUSIONS

Overall Outcome Assessment

The intended impact of this programme was to save lives, manage protection risks, promote durable solutions and shorten suffering. It aimed to do this by promoting safety, support and solutions, with an emphasis on protection, particularly for the most vulnerable, including women and girls.

The programme achieved the following outcomes:

The international humanitarian system and governments are better coordinated and have the capability to meet the basic humanitarian needs of migrants and refugees inside, and in transit to, Europe.
2 year-long strategic secondments funded and 1,297 people trained (69% achieved)
Refugees and migrants receive adequate humanitarian assistance, information and protection.
290,568 instances of emergency humanitarian assistance (such as food, clothes and medical care) and protection services (psychosocial support and cash assistance) provided, in particular for those with specific vulnerabilities (96% achieved).
Better information on the movement and needs of people in Europe and transit countries available to humanitarian agencies and governments.
288,326 relevant stakeholders reached by new evidence products from data and information partners (111% achieved), for example on the numbers of dead or missing migrants along both routes.
Refugees and irregular migrants have better access to processes and systems that help them find durable solutions.
37,696 benefitting from protection monitoring, particularly of people in detention and 10,858 interactions with refugees and other migrants to facilitate their long-term protection (such as asylum and assisted voluntary return and reintegration – from which 363 persons benefitted) (115% achieved).
More lives saved as a result of flexible finance for timely humanitarian response to meet the needs of migrants and refugees inside, and in transit to, Europe.
34,726 beneficiaries received rapid support in times of crisis through the Migration Emergency Response Fund (MERF) (434% achieved)

The programme met expectations (overall score A), with 3 out of 5 outcomes exceeding, one meeting and one moderately not meeting expectations.

The regional, multi-partner programme provided a package of interventions that flexed well to respond to the dynamic situation on the ground, and made a significant contribution to international efforts to alleviate the suffering of refugees along Mediterranean routes. Overall, taking the total of the programme outputs (except for output 1.1 - secondments and 4 – data and information) the programme provided 375,145 instances of humanitarian assistance, protection (including training) or durable solutions.

Working with a range of partners allowed DFID to ensure programming was responsive to changing needs as our partners had the flexibility to shift resources to wherever the needs were greatest. The Migration Emergency Response Fund (MERF) reached vulnerable people quickly and provided a good degree of efficiency, through its agile, country-led allocation process and speed of response (disbursements to NGOs within 72 hours of an alert being raised). Other innovative elements, such as IOM’s study on innovative approaches for sustainable reintegration of returning migrants, will be piloted through a second phase of the programme.

The short timescales involved and pressure to support people in need amidst a continually evolving situation meant that some implementing partners focussed on achieving more immediate aims (provision of basic services, protection and assisted voluntary returns) over the more challenging, longer term structural changes needed to provide migrants and refugees with access to long-term protection and durable solutions, for example, supporting governments to establish fair and efficient asylum processes.

The business case set out the need to support multilateral appeals, such as the UNHCR Supplementary Budget - Refugee Emergency Response Appeal, to ensure agencies had the flexibility to allocate funding where it was most needed. While this represents good donor practice it makes it more difficult to identify disaggregated DFID results.  This review encountered challenges due to the non-disaggregation of some DFID-specific results.

Lessons from this PCR will be disseminated internally through DFID’s Programme Management Networks. Programme managers, advisors and management in the Migration and Modern Slavery Department will be made aware of the lessons from this PCR and will use it to inform future programme design. A second phase of this programme has chosen to work more closely with partners on the design of bilateral projects specifically targeted to DFID’s desired outcomes.

Output Score and Description

Output	Weighting	Score
1. Enhanced delivery and coordination capacity in multilateral agencies, as well as technical capacity in government bodies and NGOs.	20%	B / (68%)
2. Refugee and migrants benefit from specialised reception facilities, medical and protection services, and receive emergency assistance and/or cash support to enable them to meet their basic needs and avoid negative coping strategies, such as survival sex or forced labour.	20%	A+ / (113%)
3. Relevant stakeholders read data and research products produced by IOM, FEDI and the Mixed Migration Platform	20%	A / (96%)
4. Beneficiaries are aware of their options for durable solutions and those that are detained benefit from protection monitoring	20%	A+ / (117%)
5. Beneficiaries receive rapid context-specific support from the Migration Emergency Response Fund (MERF)	20%	A+ / (119%)
Overall score		A / (103%)

Lessons and how these have been shared

This programme’s experience has provided valuable lessons for ongoing and future responses, such as the need for flexible, conflict-sensitive interventions that can adapt quickly to changes in context and target beneficiaries in ways that meets their complex needs. Some of the key lessons from this PCR are:

Providing humanitarian support in contexts of mixed migration requires a range of tools and actors to be effective

A longer-term funding model (which was not feasible given the unpredictable flows and needs in 2017) is now required for some partners, particularly where they are working in difficult contexts consisting of new arrivals, recently displaced persons and permanent refugee caseloads, as well as seasonal workers using well-established labour routes. This should be paired with flexible funding mechanisms and approaches that allow programmes to adapt activities to respond most effectively to rapidly changing dynamics. This is a key lesson which has informed the design of a follow-on programme, the Safety Support and Solutions Programme - Phase 2.

Regular on-the-ground monitoring is vital

Wherever possible, information for this review was taken from written or verbal reports from DFID staff or contractors who were either on the ground or had conducted monitoring visits. A wide array of operational and contextual challenges had to be managed, such as local capacity variations and challenging relationships with governments. Drawing on this experience and best practice from across DFID, a full Monitoring, Evaluation and Learning Strategy has been developed in advance of the second phase of the SSS to inform a monitoring schedule as well as Terms of Reference for a third party monitoring supplier. This monitoring should include robust metrics to assess progress towards durable solutions (asylum and integration, resettlement etc.) not allowed for in the comparatively shorter time frame of this first phase of SSS.

The development of innovative mechanisms can be very effective in rapidly addressing emerging issues and plugging gaps in the response.

Both the Migration Emergency Response Fund (MERF) and the Women and Girls Protection Fund (WGPF) aimed to address specific needs. The MERF responded to the need for a flexible and adaptable mechanism to meet emerging needs in a volatile situation, while the WGPF aimed to ensure a focus on vulnerable women and girls who might otherwise be forgotten amidst the much larger group of men and boys travelling along these routes. The added value of each of these mechanisms will be addressed below, but overall this approach enabled DFID to prioritise particularly vulnerable people and ensure their needs were being adequately met.

Lessons from this PCR will be shared widely through DFID’s networks and used to inform wider DFID migration and modern slavery programme design.

## C: DETAILED OUTPUT SCORING

Output Title	Enhanced delivery and coordination capacity in multilateral agencies, as well as technical capacity in government bodies and NGOs
Output number per Log Frame	1	Output Score	(68%) B
Risk:	Moderate	Impact weighting (%):	20%
Risk revised since last AR?	N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Target	Achieved
1.1 # of secondments of expert staff into multilateral organisations	3	2 (67% achieved)
1.2 # of functionaries (law enforcement officials, coastguards, frontline staff, and other relevant officials) trained on psychological support and gender-sensitive protection (gender based violence (GBV), trafficking and protection of unaccompanied minors).	1887 / British Red Cross: / 670 frontline staff and volunteers in Italy, Egypt and Sudan trained to support women, girls and vulnerable migrants with psychosocial support, and information on trafficking and referral to appropriate services for further help. / Catholic Relief Services: / 527 frontline staff including local authorities and NGOs trained in gender-sensitive protection in the Balkans / UNHCR: / 760 officials and frontline staff trained in Tunisia and Libya to improve how refugees rescued at sea are taken care of and to support their reception in dedicated centres.	1297 (69% achieved) / British Red Cross: / 536 staff and volunteers received training: 444 in Italy, 19 in Sudan, and 73 in Egypt. / Catholic Relief Services: / 538 people received training, including 322 in Serbia and 136 in Albania. / UNHCR: / 223 people received training, including 102 in Tunisia, and 121 in Libya.

Key Points

1.1	Secondments and capacity support

As migrant numbers decreased overall in the Mediterranean in 2017 and the routes became more established, multilateral agencies were able to predict needs and concomitant staffing requirements more easily, reducing the need for and number of secondment requests. The SSS programme therefore funded just two rather than the targeted 3 secondments; namely a Child Protection Capacity Building specialist in Serbia and a Health Sector Coordinator in Libya. Both agencies felt the staff members made a substantial difference both in terms of capacity and coordination, such as in training 259 frontline individuals on child protection issues and contributing to capacity-building planning with Child Protection Working Group in Serbia. In Libya the coordinator organised primary health activities in remote underserved areas of Libya and developed sub-working groups to coordinate agencies around reproductive health.

1.2 _	Training on psychological support and gender-sensitive protection training

The training and capacity-building activities covered a wide range of actors and varied significantly in intensity and duration. The majority of training focused on local officials, NGO staff and local volunteers. This was a deliberate decision to ensure longer-term benefits beyond the end of the project. In addition to training officials, Red Cross and Red Crescent societies supported capacity building of their own staff and volunteers who remain present and active in their communities, thus further sustaining the impact of this programme.

Training benefited a wide cross-section of duty-bearers and service providers. For example CARITAS Albania, a downstream partner of Catholic Relief Services (CRS), trained state police, border and migration police, social services and education officials as well as civil society organisations (CSOs). CRS also reported that working regionally allowed them to transfer knowledge from one local partner to another, to share experience and expertise, and build an increased awareness at a regional level of protection best practice.

Capacity was also developed by supporting the establishment of cross and intra-governmental dialogues to improve understanding and acceptance among officials and local communities of the situation of refugees and undocumented migrants. For example, CRS convened a regional conference together with the Migration, Asylum and Refugees Regional Initiative (MARRI)[6], convening more than 80 government and civil society actors to discuss the risks of irregular migration and trafficking and how to protect individuals. Other examples of awareness raising activities include UNHCR’s workshops on international refugee law and refugee protection in situations of detention. These workshops involved government personnel, journalists, influential bloggers, NGOs and other frontline staff.
[6] MARRI is a regional initiative between South-eastern European to coordinate on issues of migration, asylum and refugees, and to better and more effectively manage migration flows in the region. Participating states are Albania, Bosnia and Herzegovina, Republic of Macedonia, Montenegro, Serbia and Kosovo.

Based purely on the output indicator scoring, this output did not meet expectations (68.7% achieved against planned targets). However, as a result of the flexibility of the funding mechanism used in this programme (contributions to pooled appeal funds with limited earmarking of funds to specific activities), UNHCR decided that instead of training 640 personnel in Tunisia as per the agreed log frame, beneficiary needs would best be met by training 102 people and procuring equipment for a number of schools and hospitals to increase the absorptive capacity of local institutions and improve the acceptance of refugees by local communities. These activities whilst important did not contribute directly to this programme’s outcomes. Moreover, the training and capacity-building log frame indicator does not capture all achievements under this programme as it was finalised before the full extent of training activities were known. For example, IRC conducted five training sessions in Niger with state and non-state actors on child protection, GBV and migration (155 participants, including 51 women), but IRC were not listed as a contributor to this indicator in the log frame.

Recommendations for future programmes

- Ensure widespread awareness of call-down facilities, such as standby partnership opportunities, by disseminating information about them through national humanitarian coordination mechanisms as well as at UN headquarters level to allow for more equal uptake by all eligible agencies.
- Some partners provided reports that captured levels of satisfaction with training or used pre- and post- testing to measure improved learning. It would have been useful, however, to identify more precisely what change is being sought with training and capacity building (e.g. number of border guards displaying an understanding of gender-sensitive protection techniques) and ask partners to provide more explicit measures of success. Immediate Action: Clearer success criteria for training will be designed under the new phase of the programme.
- Encourage partners to collect quantitative feedback on their capacity building programmes (using shared survey questions where possible to facilitate comparison). Partners should also annex to their reporting summaries of the responses to all questions, to avoid the risk that they cherry pick positive results.

Output Title	2. Refugee and migrants benefit from specialised reception facilities, medical and protection services, and receive emergency assistance and/or cash support to enable them to meet their basic needs and avoid negative coping strategies, such as survival sex or forced labour.
Output number per LF	2	Output Score	(113%) A
Risk:	Severe	Impact weighting (%):	20%
Risk revised since last AR?	N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Target	Achieved
2.1 # instances of emergency humanitarian support (food, water and non-food items (NFIs) in line with migrants' and refugees' needs.	Target: 156,120 / Greece / 5,700 migrants receive essential NFIs (ICRC) / Italy / 120,000 individuals receive hygiene kits on arrival (BRC) / Libya / 10,000 people receive core relief items (UNHCR) / 5,400 individuals receive NFIs, hygiene kits (IOM) / Serbia / 12,000 refugees receive food, NFIs (UNHCR) / 1,500 vulnerable teenage children receive NFIs (Save) / Tunisia / 1,520 individuals receive non-food items (hygiene kits, seasonally appropriate clothing) (UNHCR)	130,789 (84% achieved) / Greece / 5,140 migrants receive essential NFIs (ICRC) / Italy / 80,871 individuals receive hygiene kits on arrival (BRC) / Libya / 17,877 people receive core relief items (UNHCR) / 3,665 migrants receive NFIs, hygiene kits (IOM) / Serbia / 20,000 refugees receive food, NFIs (UNHCR) / 1,684 vulnerable children receive NFIs (Save) / Tunisia / 1,502 individuals receive core relief items or seasonal items (UNHCR)
2.2 # instances of medical assistance, including psychosocial support (PSS), first aid at points of arrival, and referrals to secondary healthcare.	Target: 135,207 / Algeria / 207 at-risk Unaccompanied Asylum Seeking Children (UASC) receive services (UNHCR / Egypt / 1,500 individuals access national primary health care (PHC) (UNHCR) / Italy / 120,000 people receive health screening at disembarkation (BRC) / Libya / 13,500 people access PHC from NGOs/faith-based organisations (UNHCR) / Serbia / 5,000 refugees receive psychosocial care. (UNHCR)	128,584 (95% achieved) / Algeria / 8 at-risk Unaccompanied Asylum Seeking Children (UASC) received services for specific needs. / Egypt / 1,270 individuals access national primary health care. / Italy / 104,569 people received health screening and 550 were referred to secondary healthcare / Libya / 22,737 medical consultations were delivered. / Target changed (not counted): Serbia / UNHCR report 7,800 individuals receiving NFIs.
2.3 # of persons benefiting from cash grants given to vulnerable individuals/ family members	Target: 7,963 / Egypt / 660 households (HH)/1,673 people receive multi-purpose cash grants (UNHCR) / Balkans/Europe / 5,480HH receive monthly multi-purpose cash grants (CRS) / Niger / 430 individuals receive one-time, multi-purpose cash grants (IRC) / Tunisia / 150HH/380 POCs receive cash grants (UNHCR)	17,400 (219% achieved) / Egypt / 5,000HH/7,800 people receive multi-purpose cash / Balkans/Europe / 8,671 unique individual beneficiaries (6,043 Serbia; 2,628 Bulgaria). / Niger / 430 individuals received one-time, multi-purpose cash. / Tunisia / 499HH receive temporary/regular cash.
2.4 # of vulnerable migrants (e.g. women, girls, pregnant or lactating women, victims of trafficking, unaccompanied minors, etc.) benefitting from specialised reception facilities	Target: 2,780 / Balkans/Europe / 1,230 women, girls, people at risk in improved shelters(CRS) / Greece / 900 people receive specialised reception assistance (UNHCR) / 200 places for UASC established (UNHCR) / Libya / 6 DCIM facilities rehabilitated and gender-sensitive benefitting 600 individuals / Sudan / 150 victims of trafficking and vulnerable people receive shelter and assistance (BRC) / Tunisia / 150 persons benefit from transitional and emergency shelter (UNHCR)	13,795 (496% achieved) / Balkans/Europe / 1,023 women, girls and people at risk had improved shelters / Greece / 4,000 people benefitted from dignified reception conditions. / 109 places for UASC were established and maintained. / Libya / 6 DCIM facilities rehabilitated benefitting 4,185 individuals, 1,339 of them women / Sudan / 360 victims of trafficking and vulnerable migrants received shelter and assistance. / Tunisia / 141 persons benefited from transitional and emergency shelter.

Key Points

Assistance under output 2 exceeded expectations in aggregate, exceeding expectations in the provision of cash grants and specialised reception facilities and moderately not meeting expectations in the provision of emergency relief items and medical assistance.

2.1	Instances of emergency food, water and non-food item and medical and psychosocial support (PSS).

This indicator was 84% achieved. In some cases this was for legitimate reasons. The Red Cross programme in Italy dealt with numbers of new arrivals that were significantly lower than anticipated. As a consequence, the Italian Red Cross were unable to distribute all of their items at disembarkation. The decision to re-orient these toward vulnerable undocumented migrants at safe points throughout Italy was timely and supported by DFID. In addition, the conflict in Sabratha in Libya, during which more than 15,000 migrants were moved to different areas of the country, required urgent adaptation to meet emerging needs through the provision of NFIs and other services. However, provision was hampered by delays in negotiating access permissions with the new detention centre managers and concerns that some of these new centres were under the control of militia groups. This illustrates the challenge with establishing meaningful targets in a fast moving situation, to which partners on the whole responded sensitively and flexibly.

2.2	Instances of medical assistance, including PSS, at points of arrival and transit

This indicator target was 95% achieved, with 128,584 instances of physiological, psychosocial and other forms of medical support provided.

There is a challenge with capturing results from Appeal funding as agencies are free to adapt targets if the response requires it. For this reason UNHCR did not report to DFID on the original agreed targets, which included psychosocial support. While the flexibility of appeal funding is preferred in fast-moving situations, it can cause challenges for reporting against logframe results. For this reason, we must look beyond the Logframe to understand the degree to which this programme provided psychological support to people in need. Results include 2074 individuals received psychosocial support in Egypt and 530 in Morocco, as well as 463 front-line workers trained in delivering psychosocial support in Italy and Sudan.

2.3	Cash grants given to vulnerable individuals / family members

Partners exceeded expectations in terms of cash assistance, reaching more than double the intended number of beneficiaries. Cash is often intended to meet different needs and achieve different objectives, so it is important that post-distribution monitoring captures whether the intended aim has been achieved. This was the case for CRS’s cash grants in Serbia where the beneficiaries stressed both material benefit and the dignity of choice. Post-spend analysis shows that they used these cards primarily to purchase more nutritional food supplies, clothes and phone credit for security and to stay in touch with family.

On the whole, cash interventions were well adapted to the protection needs of beneficiaries and many, like IRC’s programme in Niger or the CRS programme in Serbia, aimed to at least reduce the need for people to resort to negative coping strategies. However, the CRS survey conducted in May 2017, found that the assistance covered, on average, only 59% of the families’ revenue, with the remainder coming from either relatives or through their own labour (often non formal labour sectors). It is necessary to ensure the market analysis performed takes into account the minimum spending levels of beneficiaries and ensures cash is sufficient to meet their needs.

2.4	Vulnerable migrants benefitting from specialised reception facilities

Given the changing nature of the crisis, from one of transitory movement to more static conditions, this area of work focused on achieving adequate accommodation for large numbers of vulnerable people. The indicator target was exceeded fourfold which demonstrates the focus agencies gave to moving people out of camps and into safer more dignified accommodation. There was sometimes tension, particularly in Greece, between speed (rapidly moving people out of inadequate camp situations) and quality (achieving a better quality of living space). This was discussed on a number of occasions with partners and efforts were made to find a balance between the two.

The Red Cross and Red Crescent in Sudan surpassed expectations, flexing to respond to increases in need, as the number of victims of trafficking in need of accommodation significantly exceeded expectations. Field monitoring found that the programme would benefit from additional support from specialised international staff, but that, on the whole, the programme was effectively meeting an important needs.

Recommendations for future programmes
- Future programmes involving cash (especially for protection purposes) should examine the residual safeguard risk to beneficiaries to ensure the amount is sufficient (i.e. recipients of cash have sufficient means to provide for their basic needs without resorting to negative coping strategies, such as reducing food intake, forced or unregulated labour or survival sex.)
- Ensure cash distribution monitoring tracks how many individuals (as well as households) receive cash assistance and track the secondary benefits of households.
- DFID to make sure that partners are capturing all activities carried out which contribute to a particular log frame indicator to ensure results are fully representative of all activities.

Output Title	3. Relevant stakeholders read data and research products produced by IOM, Fund for Evidence Data and Information and the Mixed Migration Platform
Output number per LF		3	Output Score	(96%) A
Risk:		Minor	Impact weighting (%):	20%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Target	Achieved
3.1 # unique page impressions of migration evidence products produced by IOM.	195,000 hits, divided as follows: / 14,000 Libya Data Tracking Matrix / 153,000 Missing migrant / 8,000 Fatal Journeys / 20,000 Europe DTM	126% achieved: 246,350 hits, divided as follows: / 17,731 Libya DTM / 181,127 Missing migrant / 11,529 Fatal Journeys / 35,963 Europe DTM
3.2 # of people from target population[7] accessing materials distributed online by the Mixed Migration Platform (per month).	65,000	65% achieved: 41,976
[7] Target audience includes policy makers, UN agencies, INGOs including in country and front-line staff, civil society, governments, migrants, refugees and asylum seekers as well as host and home communities.

Key Points

Although the overall number of people moving towards Europe has reduced since the peak of 2015, there remains a strong need for robust data on migration flows, as well as information for migrants, refugees and their host and home communities. This is illustrated by the growing number of regional migration knowledge hubs involved in data collection, analysis and information products designed for service-providers, policy-makers and influencers as well as migrants themselves.

There has been considerable progress, partly due to this programme, in the quantity and quality of data and evidence on human migration through Africa and onward to Europe, but gaps still remain. Human movement is fluid, and routes and needs change rapidly. It is essential in this context to ensure information is not only being gathered, but also analysed and shared. Partners have worked hard to do this, using both quantitative and qualitative methods, and the resulting data is growing increasingly robust.

3.1	Collecting data and evidence about migration

A combination of tools established by different partners helped establish a more robust picture of human movement through the affected areas. This includes the International Organization for Migration (IOM)’s displacement tracking matrix (DTM), which continues to expand to new areas, allowing for a much better overall picture of how people move and how their needs change. During the programme period, IOM expanded the DTM in the five states of Darfur and in South and West Kordofan in Sudan, and conducted 10,666 surveys through 38 flow monitoring points (FMPs), which capture more detailed trends and characteristics of people on the move, in nine countries in Europe. Three additional FMPs were established in Eastern Sudan, and seven in West Africa. The DTM produced data not only on movement, but also on experiences, intentions and vulnerabilities. DTM data is widely used (113,796 website visits and 35,963 downloads) within the UK government (Home Office, Foreign and Commonwealth Office, National Crime Agency etc.) and additional analysis of migration trends commissioned, for example on trends from Nigeria and Bangladesh along the various routes, was used to position wider HMG policy and programming

The IOM Global Migration Data Analysis Centre (GMDAC) created and maintained a database of studies and publications, and provided information on a number of key issues. GMDAC also brought together 35 experts in a workshop on ‘Measuring Irregular Migration: Innovative Data Practices’ to help improve knowledge and practice in this area. Information from all the partners working in this area contributed to informing and influencing policy.

The IOM’s Missing Migrants Project averaged more than 16,466 views per month, and answered 74 requests for information from media, academic, humanitarian and government agencies. It reported significant policy influence, with use of its publications by national governments, the European Commission, Frontex the European Agency in charge of managing Europe’s External Borders, UN agencies and the European Commission, as well as non-governmental organisations and academics and was picked up in several media publications (AFP news agency, The Economist, The Guardian).

Despite these significant achievements, weaknesses remain in the way that data can be collected and managed. Placement of flow monitoring points, for example, is reliant on the agreement of governments. This is not always easy to obtain, as borders are often places of sensitivity for governments, particularly when security or anti-trafficking measures are being stepped-up, as is increasingly the case. In addition, mixed migration is, by its nature, opaque, as a considerable amount of movement is facilitated by smugglers and traffickers whose work is largely illegal.

3.2	Providing information to migrants

IOM’s work has been complemented by that of partners like the Mixed Migration Platform (MMP) and the Mixed Migration Monitoring Mechanism Initiative (4MI) both supported under the Fund for Evidence Data and Information (FEDI). Partners in these projects have carried out real-time monitoring, face-to-face meetings and mobile surveys to collect data about and from migrants. The results of over 25 data collection exercises have resulted in multiple policy briefs, information products and reports, including by the 4MI project on female migrants in Libya, a demographic group about which there has been very little information to date.

Importantly, partners not only communicated about refugees, asylum-seekers and migrants, but also to them. Through MMP an estimated 80% of migrants targeted in specific locations in Europe accessed information that could help keep them stay safe. While fewer than anticipated migrants accessed this information Europe, it is difficult to monitor how many migrants not targeted (eg. had not yet started their journey) were made aware of and could access this information, with potential secondary benefits. Information products included refugee information news bulletins, a weekly ‘Rumours and Answers’ bulletin, and the News that Moves website, updated daily. An online publication, ‘In the Loop’, also helped provide humanitarian organisations with information about the kind of questions, concerns and complaints of refugees and migrants. The Red Cross and Crescent “Virtual Volunteer”, which provides valuable information to migrants about how to stay safe, where to access assistance, and how the asylum process works in a number of countries, was developed and refined for the Italian context and was accessed more than 2,500 times by over 2,000 users in a relatively short project period.

Recommendations for future programmes
- Ensure continued oversight, including through spot-checks; to better understand the challenges of data collection in terms of access to migrants and partners’ ability to quality assure the data. Immediate Action: We will look to do this through our third party monitoring under the new phase of programming.
- Influence DFID’s data partners to work on harmonisation of different data sets and joint analysis to compare evidence from different countries about migratory flows, needs and protection risks. This would ensure a more comprehensive response that adapts to the changing needs and builds on best practice.
- A single online repository for migrants and refugees with information about their status, national and international laws and available services should be prioritised over multiple competing agency platforms. This should be user-friendly and accessible even with low connectivity, with information translated into key languages.

Output Title	4. Beneficiaries are aware of their options for durable solutions and those that are detained benefit from protection monitoring
Output number per LF		4	Output Score	(117%) A+
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Targets	Achieved
4.1 # detained migrants and asylum seekers benefitting from protection monitoring visits.	Total Target: 37,101 / Greece / 60 visits to places of detention carried out; protection risk assessments conducted (ICRC) / Libya / 10,000 individuals assisted through monitoring visits [improve sanitation, hygiene in 6 detention centres, 5 sea ports] (UNHCR) / 13,041 vulnerable female migrants receiving assistance in and outside of detention centres (DRC) / Europe / 14,000 persons in need of international protection registered (UNHCR)	37,696 (102% achieved) / Greece / 87 visits to places of detention carried out; protection risks assessments conducted / Libya / Target changed by partner but included as alternate indicator of durable solutions: 993 monitoring visits undertaken to 30 detention centres, resulting in release of 805 refugees and asylum seekers. / 29,711 vulnerable mixed migrant women receiving assistance in and outside of DCIM detention centres (DRC) / Europe / 6,905 persons in need of international protection registered (UNHCR)
4.2 # instances of support for improved asylum processes, including legal advice, educational grants, facilitated voluntary return, or resettlement.	Total target = 8,260[8] / Algeria / 2,500 persons of concern registered (UNHCR) / Egypt / 700 status determination decisions analysed (UNHCR) / 1,000 HH receiving education grants for 3,500 students / 1,375 refugee cases submitted for resettlement (UNHCR) / Tunisia / 185 applicants receive info on status determination procedures (UNHCR)	10,858 (131% achieved) / Algeria / 1,257 persons of concern registered (UNHCR) / Egypt / 7,168 status determination decisions analysed (UNHCR) / 830 HH receiving education grants for 2,474 students / 863 refugee cases submitted for resettlement (UNHCR) / Tunisia / 740 applicants receive info on status determination procedures (UNHCR)
[8] Note that the original logframe target was 9260, but had incorrectly double counted both the 1,000 households receiving education grants and the 3,500 individual grantees.

Key Points

4.1 number of detained migrants and asylum seekers benefitting from protection monitoring visits.
Achievement against this indicator exceeded expectations. Ensuring the release of 800 individuals from detention is an impressive result given the challenging environment. The protection monitoring component of this programme (reaching 37,696 individuals) was particularly valuable in monitoring migrants in extreme situations in Libya and advocating for their release and adequate protection. Ensuring a “do-no-harm” approach, HMG and partners advocated with Libyan authorities on detention conditions. Whilst not condoning the centres, partner activities focussed on providing life-saving assistance (food, water, hygiene items and medical assistance) both inside and out of detention, and engaging in advocacy on behalf of detained individuals for alternatives to arrest and detention. Partners also provided alternatives, such as assisted voluntary return and emergency accommodation with host families. These activities served to highlight the severity of the situation for migrants both in and outside of detention centres, and that there is a need for ongoing political attention on this issue.

4.2	Instances of support for improved asylum processes, including legal advice, educational grants, facilitated voluntary return, or resettlement.

It is hard to measure the long term improvements for migrants and refugees’ access to durable solutions given the timeline for the project was only 15 months. The indicator figures show substantial overachievement against some of the targets including status determination analysis; however, the reasons for these overachievements are not always clear due to the fact these activities came under Appeal contribution funding. In other cases the targets changed, as in UNHCR’s report on Libya, which aimed at assisting 10,000 individuals in detention with improved sanitation and hygiene, but reported on the number of monitoring visits that led to the release of refugees and asylum seekers (805). As this is a more relevant indicator for measuring durable solutions than improved sanitisation of detention centres, it has been included as a deliverable against this target. The original target number under 4.1, however, was not reduced down. Given the dire conditions, it is unsurprising that UNHCR focussed more on removing people from Libyan detention, sometimes evacuating them to third countries to continue their asylum procedures there. Part-way through the programme in response to the worsening humanitarian situation in Libya, IOM bid for an uplift to their budget to continue their emergency humanitarian return and reintegration (HRR) interventions in Libya. This was approved in May 2017 and an additional £500k granted. While there was not time to amend the log-frame as the change happened within six months from the end of the programme, this support enabled 363 people to access a durable solution: 121 people returned from Sudan to their countries of origin, with 63 receiving reintegration support, and 242 from Libya (75% from detention centres; 25% from urban areas) and contributed overall to outcome 4.

Other work in this programme also contributes in a meaningful way to durable solutions, notably the significant integration work undertaken by CRS including two events in Greece on dignified accommodation and integration, and several activities in Bulgaria, including support to help refugees find employment. The UK also made a contribution to the Emerging Resettlement Countries Mechanism (ERCM), which aims to help countries to increase the number of resettlement places they can offer to refugees. This is managed jointly by the IOM and UNHCR and UK funds are pooled with those of other donors (Sweden, USA and Portugal). Significant results were not expected within the first year of this three year programme, and were therefore not included in this programme’s Logframe. Nevertheless, progress against the three year targets has been slow (82 persons resettled during the programme period) and the political appetite to support resettlement places remains low. All donors and implementers remain committed to this mechanism, and are thinking through options to reinvigorate engagement with interested countries and expand the available support available to them under ERCM.

Finally, support was given to IOM to create an evidence product on sustainable reintegration which, at the time of writing, is still undergoing finalisation. Once published and the approach tested, this has the potential to help reframe the way governments and non-governmental organisations support returnees, ensuring individually-tailored schemes help migrants assume new roles in the community, provide individual and community support structures to ease their reintegration, and help them to find livelihoods that better meet their aspirations. This reintegration approach with be taken forwards through an initial pilot and potential roll in a number of locations under the new programme.

Recommendations for future programmes

Immediate Action review the new migration programme Theory of Change to better understand the assumptions underpinning access to durable solutions and be more specific about the interventions that are in scope of this programme to achieve improvement in this area.

Output Title	Beneficiaries receive rapid context-specific support from the Migration Emergency Response Fund (MERF)
Output number per LF		5	Output Score	(119%) A+
Risk:		Moderate	Impact weighting (%):	20%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Target	Achieved
5.1 % Migration Emergency Response Fund (MERF) allocations disbursed on average within 72 hours of an alert to respond to urgent needs on the ground.	100%	On average, time from alert to award was only 59 hours (100% achieved). / 93.3% of projects were started within an agreed target of seven days from the time of award.
5.2 # beneficiaries receiving context-specific support from rapid adaptive programmes, such as the Migration Emergency Response Fund (MERF)	8,000	34,726 achieved (430%)

Key Points

The MERF proved to be a versatile tool for responding to gaps and meeting emerging needs. The MERF reached 34,726 unique beneficiaries (approx. 25% female) through seven programmes in four countries (Serbia, Niger, Bulgaria, Morocco). The MERF provided blankets, sleeping mats and clothes for over 7,000 migrants and refugees sleeping in -20oC conditions in Serbia and Bulgaria in January 2017 while providing 3,200 people in camps with hot food supplies, including for children and pregnant mothers. It also mobilised to support over 3000 returnees in Niger with urgent medical assistance, providing them with food and hygiene items as well as medical escorts for those with severe needs back to their home regions where they could seek further help.

The single largest area of work addressed through the MERF was protection, with 25% of the activities implemented by partners falling under this sector. This was followed by non-food items (NFIs) and food security and livelihoods, each at 18%; nutrition at 14%; health at 11%; and cash and Water, Sanitation and Hygiene (WASH) each at 7%. The alert allocation process relied on humanitarian experts, including from DFID, taking part in an objective assessment of the needs and determining the required grant amount for each emergency. Approximately £2 million was allocated from a possible £2.5million, leaving an underspend against this component (see Section D financial performance).

Some of the key strengths of the MERF were:

- The majority of the work was developed and implemented locally (65.6% of funds were disbursed to local partners) and in consultation with beneficiaries. This fits well with the Grand Bargain commitment[9] to working with local and national responders, and ensures capacity-building within the region.
  [9] The Grand Bargain is a joint commitment between donors and the international humanitarian community to enhance innovation, collaboration and adaption by working together more efficiently and transparently and with new and existing partners, including the private sector, individuals and via non-traditional sources of funding.
- 86% of partners reported that the mechanism was transparent, and that information was shared in a timely manner though translation into more languages, making it easier for field teams to access information.

A learning event on the MERF highlighted some key challenges and adaptations:

The MERF initially had the same criteria for North Africa and Europe but this proved unworkable. Partners in Europe were already in place, whereas North African partners took longer to position themselves and the short implementation window was not adequate to the needs or complexity of the operating environment. As a result, the first half of the project saw the MERF being used exclusively to plug gaps in the response in the Western Balkans, with North African projects being funded only once the project duration was increased from three to five months. There were concerns that the short time frame was not necessarily compatible with programming in complex environments and when dealing with complex protection issues; and that the period of funding was not long enough to allow NGOs to identify and bid for further funding.

Recommendations for future programmes

In general, this has been a very successful component. It should continue to play to its strengths - speed, flexibility and a targeted response – and will need to resist the temptation to become all things to all people.
As it stands the mechanism is not necessarily adapted to longer-term needs. This is not the intention of the MERF, however, which was always designed to address rapid onset emergencies and spikes in needs. It is worth noting that the project duration was set deliberately short to ensure MERF funds are prioritised on only the most urgent and critical needs. Anecdotally, it has been noted that this short time frame can add stress to agencies that must rapidly prove their effectiveness on the ground whilst also searching for future funding if needs continue; as such, a new phase of the MERF under SSS Phase 2 is likely to involve slightly longer project times (up to six months) and will have a higher ceiling amount taking on the lessons of NGOs experience using the MERF in the North Africa.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and cost per beneficiary performance

### Due to the blended nature of appeal and project funding it is difficult to identify individual cost drivers for this programme. A large proportion of spend went on staffing for medical and protection services, including individual monitoring visits to detention centres, psychosocial support and medical assistance. This relied on highly trained personnel and one-to-one sessions with beneficiaries to administer support. These specialised forms of assistance, often involving follow up sessions and referrals.
### Agencies committed in their proposals to make savings throughout the project period. Some interventions, for example, renting and renovating apartments for migrants to live in, took advantage of low rents and economies of scale in purchasing building materials to obtain savings (circa. $40,000 or £29,000). These funds were reinvested with DFID’s agreement over a two month period, to reach a further 500 people with improved reception facilities.
### There is a higher cost per beneficiary for professional services than unique provision of, say, a non-food item. Therefore, in a response where populations become more static or in contexts such as Libya, where severe protection risks require closer attention by expert staff, the costs of supporting a single beneficiary are much higher. We should therefore assume a higher cost per beneficiary than in the original Mediterranean migration crisis emergency response (205141) since this was more focussed on rapid forms of assistance (non-food items, water and food) to people on the move.

While we can count the instances when refugees and migrants benefitted from humanitarian support it is not possible to measure the total number of unique beneficiaries reached through the programme due to the risk of double counting because people were often reached with a number of interventions, such as access to food, psychosocial support, advice etc. Where the unique number of beneficiaries is known, for example those reached via the MERF mechanism, the average cost per beneficiary (cpb) was £56. This compares favorably with that of the Start-funded European Refugee Response (ERR 2) which ran from April 2016 to August 2016, where in a similar context the average cpb was £75 per beneficiary[10]. However, the costs of MERF interventions varied greatly depending on the project and types of services delivered. For example, food security projects where three substantial meals were distributed a day for the course of the project intervention was £113.62 over 3 months or £1.20 a day, while providing fewer items aimed at supplementing main meals cost £19.70 per beneficiary over a similar project duration.
[10] Programme Completion Review of the European Refugee Response: PCR completed 30 December 2017 in process of being uploaded on https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300228/documents

There were no major changes in costs during implementation, with the exception of the liquidity crisis in Libya, which had the positive impact of enabling teams to procure more medical items due to the favourable exchange rate.

Value for Money (VfM performance compared to the original VfM proposition in the business case

The Safety, Support and Solutions business case stated that funding multiple partners constituted good value for money because it allowed DFID to benefit from a wide range of specialist skills to meet the needs of refugees and irregular migrants over a broad geographical area. It has in fact, proven to be a better option than working with a single partner over multiple years, despite the significantly lower administrative costs that the latter model might have offered. This is because the programme allowed for more significant coverage of needs by bringing together partners with particular mandates (refugees, migrants) and specific expertise (detention, gender-based violence, cash). No single partner that DFID works with is present in all of the countries of operation or has the ability both to work with affected populations and governments.

The Business Case argued that the political context remained too complex for multi-year funding. This has proven to be true, given how recently borders had been closed and agreements made between governments. It is worth revisiting this, and the future phase of the programme will be on a longer timeframe. Multi-year investment should allow partners to improve the quality of their work and engage more effectively with governments in a way that maximises the potential for capacity-building. Finally, DFID’s choice to provide funding to appeals like those of UNHCR and ICRC helped ensure low transaction costs due to a higher predictability of aid and the potential to benefit from economies of scale in procurements. It also gave partners flexibility to ensure that they met the most urgent needs.

Assessment of whether the programme represented value for money

Evidence of how partners drive VfM in their programming was assessed against DFID’s standard framework (i.e. economy, efficiency and effectiveness and equity). Some of the key findings are highlighted below.

Economy
- All agencies used their standard procurement processes to ensure equal opportunity, open competition and transparency.
- Cash components were both efficient and economical as it is converted directly into commodities and services that are needed by beneficiaries, therefore reducing waste and the higher transport costs associated with gifts in kind.
- The programme developed and refined existing data platforms rather than creating new ones (e.g. Red Cross/Red Crescent’s PROTECT e-module and Virtual Volunteer; IOM’s DTM and other data-gathering tools). This allowed DFID to both extend the reach of effective data platforms and improve their quality for a relatively small investment.

Efficiency
- Organisations working in consortia and in collaboration with one another allowed for a cross -fertilisation of knowledge and skills. (E.g. CRS’s downstream partner Philanthropy shared best practice on cash distributions with partners in Sofia).
- MERF was able to accomplish a lot through quick, short-term interventions to meet clear needs, through partners already present on the ground at each location.
- Many partners demonstrated where long-term and ongoing collaboration with governments and other partners resulted in efficiencies, such as free use of facilities for accommodation or conferences.
- NFIs and other service provisions not only provided essential items to people who needed them, but facilitated access to people in need of protection, e.g. in Libyan detention centres.

Effectiveness:
- Use of cash has additional benefits on top of its face value, such as enhanced feelings of dignity and choice, as supported by CRS’ and DRC’s beneficiary feedback as well as meaning people do not need to resort to negative coping strategies.
- Feedback from cash programmes found in Bulgaria that 91% of people were very satisfied with the voucher system. NFIs distributed in Libya by the DRC consortium received an 88% satisfaction rate, suggesting this is an intervention that migrants and refugees used and relied on.
- Effectiveness of data and evidence is maximised as partners share information and learn from one another. Where data might be incomplete, e.g. some of the 4MI data or flow monitoring/DTM of IOM, it is reinforced by information provided by others, creating overall a much more effective use of data and evidence.

Equity:
- The project addressed specific needs and vulnerabilities, by using vulnerability criteria and addressing protection concerns specific to minors, women and girls, disabled persons, people of ethnic minorities and trafficked persons etc. Humanitarian principles of non-discrimination ensured people in need, including from host communities, could access available support.
- The MERF interventions reached vulnerable people quickly where other partners may have taken longer to mobilise, thereby ensuring an equitable level of support regardless of the individuals’ location, or the availability of existing donor support.
- Whilst partners were asked to disaggregate their results by age and sex, more could have been done to ensure key characteristics of beneficiaries were recorded and analysed to ensure programming targeted those most in need and left no one behind. This will be taken account of in the next phase of the programme.

Quality of financial management during programme

Partners have showed good financial management, providing mostly accurate financial reports on a quarterly basis, with minor inaccuracies later resolved. Partners also effectively used savings to reallocate funding to meet emerging needs, such as CRS’s decision to use savings from the shelter construction in Greece to support the rehabilitation of shelters in Presevo camp in Serbia and a special women’s centre for women who had recently or were due to give birth.

The funds remaining at the end of the project period represented 3% of the total programme budget, at £930,280. The largest areas of underspend were on the Migration Emergency Response Fund (£337,914) and the IRC Niger component of the Women and Girls Protection Fund (£165,231), which was also the shortest project with 9 months for implementation. The final area of underspend came from the lower number of secondments that were funded, with underspends of £165,118. As described above and due to the changing nature of the crisis requiring longer-term planned responses, the need for temporary seconded experts reduced or became unjustifiable against our criteria. We reviewed the programme and reallocated underspends mid-way through the programme to provide an uplift of £500,000 to support the IOM to provide emergency voluntary returns of migrants from Libya to their home countries.

While no partner activities will be paid for outside the project period, a small amount of money remains for DFID to conduct closure exercises (reviews, final meetings with partners, etc.) and will be spent before the financial end date of the project.

Date of last narrative financial report	Multiple financial reports received from all programme partners by 30th January 2018. No major issues identified, with some minor inaccuracies resolved.
Date of last audited annual statement	Audited statements will be received within six months of project completion, as required by DFID procedures.

E: RISK

Quality of risk management over the life of the programme

A number of risks explored in the Business Case for this programme did not transpire, notably the breakdown in the EU-Turkey agreement which would have led to a resumption of large-scale movement in Europe. Other risks, such as those associated with rapidly changing needs and challenges in working with local partners or government, were adequately mitigated by the programme design itself. For example, the MERF was able to meet emerging gaps on a number of occasions, and the established relationships of partners with local organisations helped facilitate effective programming.

Ongoing dialogue with partners and regular monitoring meant that there was a willingness to discuss issues with DFID staff as soon as they arose, resulting in adequate oversight and challenge on risk management. In Libya, for example, DFID regularly held discussions with all partners about the challenges of working in detention centres, where the pros and cons of interventions required carefully consideration.

Libya risk landscape and how it changed: the instability in Sabratha, liquidity crisis and shifting power dynamics made it difficult for partners in Libya to establish themselves and get the necessary government approvals in all areas. Moreover, as fewer boats departed from Libya and certain regions became unstable, this impacted on the wider dynamics, leaving detention capacity overwhelmed resulting in worsening conditions and increased vulnerabilities of migrants as smugglers took greater risks to continue transporting them. Given the context, the results achieved in Libya are impressive, and risk was mitigated well with only a minor incident reported of some non-food items being taken from a truck by local militia (total value approximately $25 USD in total).

Despite all partners of the programme providing risk frameworks, these showed variability in terms of which types of risks (e.g. contextual, operational) were assessed and how. Most partners identified risks relating to security and political issues that were, at least to a large extent, outside of their control. However, in most complex situations, access was a challenge and implementing partners were not always present in country, relying on downstream delivery partners in some instances. This meant they only had a partial view of the risk picture. There was a need, therefore, for DFID to work more closely with partners to ensure that their risk management was being conducted more effectively.

Fiduciary and Safeguarding Risks

There was one case of fraud (total loss $25 worth of supplies stolen from a truck), as well as one unsubstantiated allegation against an agency, the individual against which these were made was not directly connected to the programme. These were dealt with promptly and in a manner compliant with DFID rules. We can be confident due to our financial controls and the degree to which partners did report on minor instances, that no major instances of fraud, corruption or misuse of funds arose under this programme. Moving forwards, we will ensure third party monitoring independently verifies partner activities where high amounts of funds are involved (e.g. in terms of purchasing stock or delivering cash transfers). We also intend to complete a full systems review of our new programme partners, to ensure fiduciary risk is being managed in line with risk appetites, and our partners have robust systems in place to monitor the movement of funds all the way through the delivery chains.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

The programme was ambitious involving a large number of different partners (listed in Annex B). Delays in the initial signing of some agreements due to the need to conduct full due diligence meant that some projects only started in spring of 2017. No Cost Extensions (NCEs) were granted to the following partners up to 30th November 2017.

1.	British Red Cross
2.	Catholic Relief Services
3.	Danish Refugee Council (FEDI)
4.	Danish Refugee Council (WGPF)
5.	UNHCR
6.	International Rescue Committee (Niger)
7.	International Organization for Migration

These extensions enabled all partners to programme against a more realistic timeframe to achieve optimum results. The majority of IOM projects were completed within the original timeframe but a delay to one project necessitated an extension to the whole DFID-IOM agreement up to 30 November 2017.

Performance of partnership(s)

Partnerships between DFID and partners worked overall well. DFID and partners held regular meetings remotely and in person to discuss progress and performance. Partners have for the most part delivered against their planned targets and communication between DFID and partners has been strong throughout the duration of the programme. An example of close engagement between DFID and the partner was on the MERF, where DFID was involved fully in the selection process and helped shaped the mechanism itself.

Where communication DFID encountered challenges, including in terms of responsiveness to donor requests, we raised these with relevant partners in different ways, for example, through DFID institutional leads and through annual strategic dialogues. We have learnt lessons in terms of how we work with partners to ensure accountability, responsiveness to DFID requests and robust oversight of our programmes.

Asset disposal and value obtained by DFID

DFID has monitored partners’ asset management through partner financial reports and regular progress meetings. All DFID funded assets will be disposed of following DFID guidelines, as part of the project closure process. An asset register has been kept for all partners under this programme. Assets procured under this programme include medical equipment and supplies (bought in bulk to achieve better economy), vehicles to allow professional staff to access beneficiaries and transport them e.g. to hospitals. Over the course of the project closure period we will review partner requests for permission to transfer these assets or continue using any currently in stock in line with DFID’s assets policy to ensure their maximum value and developmental use.

H: MONITORING & EVALUATION

Evidence and evaluation

The data and evidence forms an important component of this programme. This is not by chance. Early in the crisis DFID identified important gaps in available evidence, and invested substantial amounts of funding into helping to build the evidence base. This has not included formal evaluations of this programme, but has included the development of new tools, mechanisms and approaches to the collection, analysis and dissemination of knowledge and evidence.

More programme-specific tools have also been produced as a result of this programme that serve not only to improve the work of individual agencies, but can also act as reference tools for the wider community as they tackle some of the challenges inherent in mixed migration. Specific examples include the MEASURE report produced by IOM on reintegration, the adaptation of the Red Cross/Red Crescent’s e-module on trafficking, and the conference report produced by the CRS programme from the regional workshop of the Migration, Asylum and Refugees Regional Initiative (MARRI) on irregular migration and trafficking in human beings.

Monitoring progress throughout the programme

The programme had an overarching log frame underpinned by individual partner indicator milestones. Most partners had some form of monitoring to assess the effectiveness of their programming, including post-distribution monitoring for cash, satisfaction surveys and third-party monitoring, among others. In general, many involved a component measuring beneficiary satisfaction. Regular reporting from all partners showed where many had made course corrections in their work, for example, and the Red Cross/Red Crescent’s shifting of resources to provide for existing undocumented migrants located elsewhere in Italy, when there were fewer new arrivals.

Partners’ log frames established clear baselines, milestones and targets, but the extent to which these were reliably reported on varied. Some partners reported precisely against the criteria, providing explanatory information when there was divergence. Some identified early when they would be unable to complete planned activities and requested changes. Others, however, provided less information during the course of delivery despite requests for timely reports. This was a particularly an issue with un-earmarked appeal funding.

DFID requested quarterly reporting from NGO partners, whilst UN agencies were required to submit interim and final reports. A series of visits was conducted by DFID’s programme staff and humanitarian advisers to ensure the programme was achieving against targets. A Humanitarian Advisor was based in Tunis, to act as a lynchpin between headquarters and country implementation teams, and carry out regular visits to projects. The HMG Libya Office based in Tunis also carried out spot checks to visit detention centres to see the work of partners to review their progress.

Despite the very wide range of activities in a broad spectrum of countries, DFID has been able to remain on top of changes in the operating environment thanks to HMG-wide experience in the affected countries, knowledge of and familiarity with the partners and, in some countries, ongoing presence and understanding of the country context (e.g. Sudan). The next programme, however, would benefit from a monitoring plan that ensured more consistent presence on the ground, particularly in places where DFID has a limited presence, such as North Africa, e.g. through third party monitoring.

Annex A

The outputs of this programme have been scored using a calculation as per DFID’s PCR Scoring Guidance.

DFID project performance scoring definitions

A++	138%	Outputs substantially exceeded expectation
A+	113%	Outputs moderately exceeded expectation
A	88%	Outputs met expectation
B	63%	Outputs moderately did not meet expectations
C	50%	Outputs substantially did not meet expectations

­­Results over 138% have been moderated down so as not to skew the average.

Annex B – List of Partners funded under the SSS and budgets

Organisation	Budget (£)
International Committee of the Red Cross (ICRC)	2,000,000
International Organization for Migration (IOM)	5,533,862
United Nations High Commissioner for Refugees (UNHCR)	9,800,000
Women & Girls Protection Fund (WGPF)	7,557,780
 British Red Cross	1,500,000
 Catholic Relief Services	4,000,000
 Danish Refugee Council	1,457,780
 International Rescue Committee	600,000
Migration Emergency Response Fund (MERF)	2,500,000
Fund for Evidence, Data and Information (FEDI)	2,249,798
Technical Assistance-Fund	400,000
Emerging Resettlement Countries Joint Support Mechanism	2,500,000
Non Food Items	400,000
Secondments	416,340
Total	33,357,780