Type of Review: Annual Review

Project Title: World Bank Trust Fund – International Comparison Programme – 2011 Round

Date started:	August 2010	Date review undertaken: August 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
DFID will provide a contribution of £4 million over a 6 year period from August 2010 to July 2016 in support of the International Comparison Program (ICP) which is a worldwide statistical initiative. / The programme is required to estimate Purchasing Power Parities (PPPs) to be used as currency converters to enable comparison of the size of economies around the world. The indicator for the Millennium Development Goal (MDG) on poverty reduction explicitly uses PPP data to set a poverty line of $1.25 per person per day measured in constant purchasing power parities. / DFID support will help ICP produce internationally comparable price and volume measures for gross domestic product (GDP) and its component expenditures. The measures are based on purchasing power parities (PPPs). To calculate the PPPs, the ICP conducts surveys every six years to collect price and expenditure data for the goods and services that comprise GDP including consumer goods and services, government services and capital goods. / The GDP volumes facilitate comparisons of the economic size of countries and, when put on a per capita basis, the economic welfare of their populations. They can also be used to compare the overall productivity and investment potential of countries. Other uses include monitoring the incidence of poverty and tracking progress towards the Millennium Development goals.

What are the expected results?
The intended impact of this project is that data informs policies of donor agencies, government and civil society institutions. / The intended outcome of the project is timely and reliable statistical data on purchasing power parities for GDP and its main sub-aggregates for all major countries and regions are compiled and published. / The outputs attributable to DFIDs support are: / New methodological preparation developed for various components of the program / Accurate and timely collection of price survey data. / Improvements in statistical capacity in IDA countries. / This round of the ICP support is leveraging on the successful implementation of the 2005 round and its scope is being further extended. It will be designed to enhance the robustness of PPP estimates through greater adherence to the System of National Accounts (SNA), the improvement of price survey methodologies, and to perform additional methodological research.

What is the context in which UK support is provided?
There is a clear need for countries to have good quality statistics. They are essential not only to inform policy, but also to enhance the credibility of policies by enabling citizens to hold governments to account. Particularly crucial for the international community is reliable data on MDG indicators. These play a key role in: / holding the international community to account; / encouraging sustained public support and funding for development; / ensuring effective allocation of aid, and; / comparing progress across countries. / The results framework of the Global Statistics Partnership (GSP) team’s operational plan identifies areas of our work that contribute to delivering the following Structural Reform Plan pillars and DFID strategic priorities: / Improve quality and availability of statistics to enable more transparent results reporting. / Improve the quality and comparability of MDG data to inform policies, and to allow robust monitoring of MDG progress. / The international system provides more coordinated and effective support to statistics. / Increase the quality and availability of gender specific and sex disaggregated data to inform policies, and to measure the progress of DFIDs efforts to improve the lives of girls and women. / DFIDs support for the ICP will contribute towards delivering these priorities.

## Section A: Detailed Output Scoring

Output 1: New methodological preparation developed for various components of the program.
Output 1 score and performance description: / B. Outputs moderately did not meet expectation
Progress against expected results: / Progress against the expected result has been as follows: / As of August 2012, 12 components have had methodological improvements approved by TAG (technical advisory groups) against an October 2011 target of 14. The research on PPP-based poverty and Sub-national PPPs are still underway. For the latter, pilot exercises are being conducted in the Philippines and South Africa. The pilot in Philippines was conducted in 2011 and is being updated in 2012, while the pilot in South Africa was just launched in August 2012. The research on PPP-based poverty will conclude by June 2014.Africa. / Recommendations: / No action required. / Impact Weighting (%): 15% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 2: Accurate and timely collection of price survey data.
Output 2 score and performance description: / A. Outputs met expectation
Progress against expected results: / Progress has been good against the expected results: / 199 countries/economies are participating in ICP 2011 round as of August 2012. Surveys were conducted in 157 countries in 2011 and are underway in 42 counties in 2012 (Pacific Islands and Caribbean Islands), as planned. Preliminary 2011 average price data were submitted by all regions, except the Caribbean and the Pacific, in August 2012. / Number of countries collecting price data relating to other price surveys: / To date, 47/47 countries from OECD/Eurostat, 23/23 countries from Asia Pacific, 9/9 from Commonwealth of Independent States (CIS), 17/17 from Latin American & Caribbean (LAC) and 12/12 from Western Asia conducted surveys for education, health, equipment and construction, except 4 countries out of 17 in LAC that have not conducted the equipment survey yet. Data are being validated at the regional level. Africa re-scheduled their survey: so far, 16 countries have started surveys related to education, 15 for equipment, and 14 for construction, whereas all the other countries in the region are expected to conduct their surveys and submit their data by the end of 2012. Health survey is incorporated in their Household Consumption survey, and was conducted in 2011. / As of August 2012, all participating countries from OECD/Eurostat, Asia Pacific, CIS, LAC, and Western Asia conducted the survey for compensation of government employees. Data is being validated at the regional level. 19 countries had started their survey in Africa and all the other countries in the region are expected to conduct their survey and submit their data by the end of 2012 / Recommendations: / No action required. / Impact Weighting (%): 60% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Improvements in statistical capacity in IDA countries.
Output 3 score and performance description: / B. Outputs moderately did not meet expectation
Progress against expected results: / Progress against the expected result has been as follows: / Comparing 2012 with 2011, 38% of IDA countries with a population more than 1 million have increased their statistical capacity indicator score. The target was 66%. It should be noted however that the many of the factors which influence the score are outside the scope of this program. / Recommendations: / No action required. / Impact Weighting (%): 25% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? / Y – the logframe was revised as a result of the last review. In particular the Impact statement was revised and changes were made to indicators under outputs 1 and 3. / 1.2 Overall Output Score and Description: / A. Outputs met expectation / 1.3 Direct feedback from beneficiaries / The main beneficiaries of the volume and price measures generated by the ICP are international organisations and regional agencies. There is a growing demand for PPPs from a variety of users at the national level including government agencies, research institutes, private firms and public enterprises. Countries on low Gross National Income will also benefit as PPP data collation and analysis targets the poor and will help to identify and compare the spending power in the 175 participating countries. An independent, external evaluation of ICP will be conducted in year 5 of the program and is expected to commence when the results are published in December 2013.
1.4 Summary of overall progress / The project is progressing well and remains on schedule and on budget. / The ICP Global Office at the World Bank received 4 quarters price data, national annual averages, expenditure data and metadata from all regions by August 2012, and launched the data validation process. In 2011/2012, the Global Office prepared operational and outreach material, and planned the meetings of the Executive Board, Regional Coordinators, the Technical Advisory Group, and other working groups. / At the regional level, since most of the participating countries completed the 2011 main household consumption survey, the Regional Coordinators and National Coordinators devoted more time and effort to iterative validation activities, which culminated in regional workshops in the first half of 2012. / Data collection and submission are broadly on schedule, despite some initial delays faced.
1.5 Key challenges / The main challenges will continue to be that: / National Statistics offices are committed to carrying out data collection and have the capacity to do so. / Regional agencies have the capacity to provide guidance and coordinate data collection and data validation / The international community remain interested in regional and global results
1.6 Annual Outcome Assessment / The outcome of the program is to produce timely and reliable statistical data on purchasing power parities for GDP and its main sub-aggregates for all major countries and regions. Given the progress to date we expect to achieve the project outcome.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y / 2.2 Key cost drivers / The key cost drivers related to the delivery of the ICP programme continue to be Staff/Consultant costs and grants to support regional programmes. / 2.3 Is the project on-track against original timescale: Y

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / The need for timely and reliable statistical data on purchasing power parities for country and regional GDPs, which inform policies of donor agencies and government, is still the rational behind the design of this project. Therefore no modifications to the design or theory of change are recommended for this project. / 3.2 Where an evaluation is planned what progress has been made? / An independent, external evaluation of ICP will be conducted in year 5 of the program and is expected to commence when the results are published in December 2013. It will review data quality and other aspects of the program and will make recommendations for financing it on an ongoing basis. As was the case for the 2005 round, it is anticipated that this review will be carried out by the United nations Statistics Commission Friends of the Chair working group. The evaluation would use the responses of Countries, Regional Implementing Agencies, and the Global Office to the ICP Quality Assurance Framework checklists.

4. Risk
4.1 Output Risk Rating: Low / 4.2 Assessment of the risk level / The overall risk level for this project is judged as medium. The ICP report to donors dated March 2012 highlighted the following categories of risk associated with the programme delivery: / Political Risks - The socio-political tension heightened with the Arab Spring remained in several countries in Africa and Western Asia in early 2011 which caused various levels of disruption to data collection. The situation was closely monitored by the Global Office and regional co-ordinators with mitigating measures applied on a case by case basis. / Data Quality Risks – A review of the status of survey implementation reveals that some countries collecting prices differs from one month to another and some are not complying with their initial survey frames. To mitigate this, some regions have decided to extend their main household consumption survey into additional quarters which will increase the number of data points in each country and improve the quality of average prices and resulting PPPs. / Funding Risks – In 2011, some African countries faced funding problems because of delayed justification of earlier disbursements but these were resolved. Fund raising efforts are intensifying in some regions to raise more funds for the 2011 Round of the ICP. Mitigation actions have been identified in the event of insufficient funding.
Risk of funds not being used as intended / There are no indications that misuse of funds is a major risk or concern. DFID funding will be covered by a formal arrangement with the World Bank in the form of a multi donor trust fund. Under this commonly used mechanism, DFID’s contribution will be administered in accordance with the World Banks standard and applicable policies and procedures, including its framework to prevent and combat fraud and corruption. / 4.4 Climate and Environment Risk / The environmental risks are negligible since this is a project to improve statistical reporting. ICP is a worldwide initiative that compares the size of economies around the world and the information gathered will be useful in a wide range of policy development and decision making. Any environmental and carbon footprints that arise during the conduct of the work will be minimised by the project.

5. Value for Money
5.1 Performance on VfM measures / DFID’s financial support for this program will result in many benefits including improvement in the quality of the data produced, improvement in the methodology used and a greater number of countries being included in the program. / The 2011 Round introduced improvements in ICP methodologies, a Quality Assurance Framework, a software tool to facilitate data collection, validation, and analysis, and a Global Core list of items that can be used for data collection in subsequent years and rounds. These improvements and innovations will reduce the cost of the program in future years. The program will also lead to improved price collection capacity in poor countries which reduces the costs of future ICP rounds and contributes to the sustainability of the program. / 5.2 Commercial Improvement and Value for Money / A strong governance structure is in place for the management and Implementation of the ICP which informs value for money. This comprises of an ICP Executive Board, a Global Office led by a Global manager appointed through an international, transparent and competitive selection process, a Technical Advisory Group and Regional Implemental agencies. The World Bank hosts the Global Office. The framework defines the role of each governance body and their mandate to coordinate international regional and national efforts to produce PPPs. / The World bank continues to mange any Procurement activities under this project in accordance with their internal standard guidelines and procedures covering expenditures allocated to goods and services. / 5.3 Role of project partners / No specific indicators have been developed to measure the World Banks performance in the delivery of value for money. The Bank, however, have already introduced processes (see 5.1 above) to the programme that bring cost-effective savings. / 5.4 Does the project still represent Value for Money : Y / Yes, we are satisfied that the project is delivering results and representing value for money / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
Despite experiencing some delays, the project is progressing well and remains on schedule and on budget. Results are generally being achieved as planned. There are no changes required to the milestones, targets or indicators in the logframe. The overall risk of the project is low.

8. Review Process
The review process was conducted by Kenny Bambrick (Statistics advisor in the Global Statistics Partnership team) in August 2012. / Consultation during this process was conducted with the following people: / Robert Morrison (Deputy Program Manager in DFID) / Michel Mouyelo-Katoula (World Bank) / Nada Hamadeh (World Bank) / This Annual Review was informed by: / Annual Review of ICP activities produced by World Bank and sent to DFID in March 2012. / Interim progress report (as of June 30, 2011), which was submitted to the ICP Executive Board. / Meetings conducted between DFID and the World Bank during the year. Since March 2012 there have been regular (6-8 weekly) VC meetings to discuss DFID-funded projects, of which this is one. Progress was also discussed at the annual meeting in Washington in November 2011.