Project Completion Review – post April 2018

Title: Security and Risk Management in Hostile Environments
Programme Value £1,819,617	Review Date: June 2018
Programme Code: 203978	Start Date: July 2013	Final End Date: March 2018

Summary of Programme Performance

Year	2015	2016	2017	2018
Programme Score	A	A	A	A
Risk Rating	Minor	Minor	Moderate	Moderate

DevTracker Link to Business Case:	Here

A. Summary and Overview

The Security and Risk Management in Hostile Environments programme promotes improved safety and security in humanitarian contexts by strengthening NGO’s security and risk management practices, essential for delivery humanitarian assistance to those people in need. It does this through three complementary programme and partners: RedR UK, the European Interagency Security Forum (EISF); and the International NGO Safety Organisation (INSO). A small amount of funding was also provided to the Overseas Development Institute (ODI) in support of a memorial for humanitarian aid workers. Key outcomes include:

(i) Accessible and effective training: A NGO-led partnership between RedR and Digital Training Solutions (DTS) has developed an innovative approach to humanitarian security training using interactive gaming software designed to improve knowledge retention through immersive learning. It complements existing face-to-face training, but as an e-learning package, is able to reach more users at lower cost. It helps teach key skills, such as raising the awareness of personal security, preparedness and planning, direct and remote security management, personal risk assessments, and travel security. CHASE jointly supported the project with OFDA (US government), providing £270,000 to support the design and build phase of the training programme.

(ii) Improved NGO security management and awareness: The European Interagency Security Forum (EISF) is a network of European NGO security focal points. It leads best practice in humanitarian security management, enhancing the safety and security of aid workers and allowing increased and sustainable access to populations in need. The impact of EISF’s work has been the professionalisation of NGO approaches to security management. EISF has also enabled smaller international and national organisations – often with limited resources for security – to meet acceptable standards of care. CHASE provided £250,000 to EISF between 2013 – 2018.

(iii) Building global capacity in humanitarian safety: The International NGO Safety Organisation (INSO): INSO was established in 2011 to support the humanitarian community with information, analysis and advice. INSO has established a comprehensive network of field level safety platforms that provide daily support to more than 800 national and international NGOs in 12 high risk and Level 3 countries including Syria, Iraq, the Central African Republic, DRC, Somalia and Afghanistan. By improving NGOs’ contextual awareness and strengthening their capacity to respond, INSO plays a vital role in protecting aid workers and ensuring safe humanitarian access. CHASE provided £594,000 core support to INSO in 2014/15, and a further £364,658 for 2017/18.

1. Red R – Mission Ready

With DFID funding, RedR and Digital Training Solutions (DTS) have designed, developed and delivered 2 new online courses: Field Security Management (FSM) and Remote Security Management (RSM). RedR report it has become the go to platform for online security training and has received positive feedback from the humanitarian community. Target output indicators have either been met or partially exceeded.

The training modules are composed of 10 interactive scenarios, with FSM management set in an East African context and available in Arabic, French, Spanish and English, and RSM set in a Middle Eastern context available in English and Arabic. The courses are also able to be downloaded and accessed offline which is useful in areas where there is poor internet connectivity.

The training has been accessed by 59 organisations, from people of 85 different nationalities, operating in 90 countries, demonstrating its global reach. Feedback from users has been an average 4.1 out of 5 for the courses and 4.3 out of 5 for accompanying course material. Surveys conducted pre and post training show that an average 77% of users who completed the courses stated their knowledge had improved after doing the courses.

Three years after its launch, the current number of individual licences sold to access the Mission Ready training stands at 1,668 (June 2018), exceeding the (reduced[1]) logframe target of 1,600. Outreach, marketing and communications activities by RedR have helped achieved the good licence sales numbers.
[1] The logframe target was reduced from 1,800 to 1,600 following the decision to bring forward the end date of the grant to March 2018 from September 2018.
Total numbers of users completing the training has however been lower than hoped. Course completion rates lag behind licence purchases, and by the end of March 503 users had completed the course, with 784 active users. Learners are also taking longer than expected to complete the course than expected, perhaps using it as learning platform, or returning to it as part of a monthly study plan. This is apparently not uncommon for e-learning courses. RedR plan to undertake a user experience survey of Mission Ready to investigate completion rates and better understand how participants are engaging with the platform.

2. European Interagency Security Forum

EISF has played an important role over the duration of the project to improve security risk management practice across the humanitarian sector. It has done this by building relationships and trust between partners, training and sharing of information and best practice, commissioning research and blogs, and utilising social media. Target output indicators have mostly been exceeded.

EISF membership has steadily increased reflecting the continuing demand for its services and networking opportunities. This is also reflected in the fact that 86% of members utilise its services, and over 70% of its members attended at least one of its forum events in the past year. EISF has continued to be able to attract high quality external sector experts to present at its forums, workshops and other events.

EISF has continued to develop its website, with healthy use and access figures. In the six months between October 2017 - March 2018 there were nearly 16,000 new visitors to the website and nearly 9,500 documents downloaded. EISF are planning to commission an analysis of its website usage to provide a more comprehensive understanding of how members interact with it. EISF have launched new services via its website including EISF_Chat which allows members to share information and questions directly between themselves, with almost 75% of member organisations signing up to use it.
EISF’s use of social media has continued to increase, using it to raise awareness of events and issues, including a greater use of Twitter. It has also launched a podcast series “EISF in Conversation”, which is partly aimed at non-traditional EISF audience, covering issues such as humanitarian access and humanitarian principles.

Demand for EISF guidelines and toolkits has been sustained, with publications such as Security to Go and Security Risk Management: a basic guide for smaller NGOs still receiving many downloads, providing practical information to NGOs to help them improve security and risk practices. In addition to these publications EISF has continued to facilitate workshops to promote learning and knowledge sharing about security risk management in humanitarian contexts with other NGOs across Europe. It has also commissioned articles and blogs on live issues likely to be faced by security focal points and aid workers in the field.

EISF has been working with a consultant to develop a funding strategy to supplement traditional donor support with funding from the corporate sector. A 3 tier strategy was agreed in the spring, offering organisations different levels of engagement and access to EISF depending on their interest and commitment. It will be important to monitor how successful this new approach will be.

3. International NGO Safety Organisation

INSO is currently providing services for 12 conflicts, and has a presence in 16 countries, with more potentially coming online (Niger and Yemen). INSO are present in 70% of severe humanitarian crises, and 60% of humanitarian crises, and serve almost 800 partners including the Red Cross and MSF. 20% - 25% of their partners are national NGOs, and over 100 NGOs from UK. The services they provide are free to other NGOs. DFID funds under this grant have been used in Gaza, Cameroon (covering the Lake Chad response), South Sudan and Yemen.

Target output indicators have mostly been met, with the exception of the Conflict and Humanitarian Data Centre (CHDC) which requires further time and work to finalise properly. INSO has made satisfactory progress against its organisational development milestones, enabling it to provide a good level of information, analysis and advice to NGO’s working in humanitarian situations. All senior level positions in the office in Dubai are now filled, progress is being made against its organisational developmental plan, and the risk register has been regularly analysed and reviewed. Headquarters staffing does however remain relatively light compared to the size of the organisation, which has grown significantly over the lifetime of the project.

INSO have broken new ground with publications such as the Security & Access Review, which for the first time is aimed to inform decision making by security staff at headquarters. It is hoped this product will help increase INSO’s profile visibility amongst partners, growing the demand for its products and services. In addition, the donor meeting in Berlin, hosted by the German MFA, was the first meeting of INSO’s core donors, and is likely to be replicated in the future with wider participation.
INSO received an initial grant under this project for one year in 2014, and a recommendation following that was that it should aim to secure wider support from DFID Country Offices and other donors which it successfully did, securing support from DFID Iraq and Syria, as well as OFDA and ECHO. A follow on CHASE grant in 2017/18 has helped further build and support INSO’s capacity as an organisation as well as invest the Conflict and Humanitarian Data Centre, a potentially powerful resource for INSO, its partner organisations and security focal points. Although the CHDC was not complete by the end of this project INSO are confident it can be completed in-house at no extra cost by the end of 2018.

At the end of the project INSO conducted a partner survey in an attempt to measure the impact of its services. Positively, an aggregate of the responses received showed that 94% of NGO’s believed INSO’s services help them operate more safely. INSO recognise the need for a more sophisticated measurement of their impact and are actively thinking about how to do this. In addition, INSO needs to continue to diversify its funding base and should develop a sustainability strategy if it is to continue to offer products and services to others for free and it if is to continue to expand its geographical presence.

4. Memorial for Humanitarian Aid Workers

Through this project DFID provided a small amount of funding to ODI to support the establishment a permanent humanitarian memorial in central London. This has now been erected in the Coin Street Neighbourhood Centre following a successful fundraising campaign. DFID Ministers and other senior officials have also regularly represented the Department at the annual memorial service held at Westminster Abbey in remberance of those who have lost their lives delivering humanitarian assistance.

## B: DETAILED OUTPUT SCORING

1. MISSION READY: INNOVATION IN HUMANITARIAN SECURITY TRAINING

Output Title	An innovative, online security training system is available to the humanitarian sector through 6 interactive film-based scenarios
Output number per LF		1	Output Score	A
Impact weighting (%)?		15%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (Target)	Progress
Number of scenarios made available to the humanitarian sector	Online system available and fully functioning. / Downloadable PC application of training available. / Available in 4 languages: English, Arabic, French, Spanish / 10 interactive scenarios in two separate courses	Mission Ready is a fully functioning online platform that provides security training globally to humanitarian NGOs and INGOs; available in 4 languages and 10 interactive scenarios, through 2 separate courses
Participant feedback on relevance of online scenarios	Average satisfaction score from all users in terms of relevance for interactive scenarios is 4/5 (600 + participants, 3yrs after launch)	Participant feedback for Field Security Management and Remote Security Management both scored 4.1 / 5, based on 784 users

Output Title	A series of high quality programmes to support the scenarios is available to the humanitarian sector including documentaries, expert interviews and written content
Output number per LF		2	Output Score	A+
Impact weighting (%)?		15%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (Target)	Progress
Percent of proposed programme of learning tools made available to the humanitarian sector	11 expert interviews; 1 course introduction documentary; 1 impact report; 9 downloadable pdf resources; 2 audio lessons in incident reporting; 10 audio recaps. FSM - available in 4 languages: English, Arabic, French & Spanish. RSM - available in English & Arabic. 1 group study guide for FSM (PDF download). 1 individual study book for RSM (PDF download)	Achieved: All products have been delivered, with additional background reading and security information on the platform as well
Participant feedback on overall quality and relevance of all learning tools	Average participant score from all users for quality and relevance is 4/5 (600+ participants, 3yrs after launch)	503 users have completed the course. Average feedback for FSM is 4.3 / 5 for quality and 4.3 for relevance. For RSM participant feedback is 4.4 / 5 for quality and 4.3 / 5 for relevance

RedR have made good progress, either meeting or exceeding the milestones. Two courses have now been developed: Mission Ready Field Security Management (FSM) and Remote Security Management (RSM). Both are online, available, and fully functional. A downloadable PC version has also now been made. The target for the learning tools to support the online training courses has been met, even exceeded, with the provision of extra materials and information from security experts. These will be stored on the online platform and will be available to participants to use.

The Field Security Management course is set in an East African context, and is available in 4 languages: English, Arabic, Spanish and French. The Remote Security Management (RSM) course is set in a Middle Eastern context, and is available in English and Arabic. Launch events were held in London (twice), Kenya, Pakistan and Jordan. By the end of the project a total of 1668, licences (for both courses) had been distributed to people in 90 different countries.

Between November 2016 and January 2017 qualitative feedback on FSM was gathered through interviews with course commissioners and users. Users liked the option of being able to obtain online training as it offered flexibility and that it could be done around other work commitments. It also allowed staff in remote locations, often at the front line of humanitarian responses, to receive training. Participants also liked the interactive nature of the training which made it accessible and engaging.

Once the training is complete a survey is automatically conducted to gauge the impact of the course. An Impact Assessment of the Field Security Management training conducted in April 2017 found that:

- 83% of users rated the course good or excellent, and 87% of users rated it relevant or highly relevant.
- 93% of users said they would recommend the course to others.
- 60% of users have worked or were working in hostile environments since taking the course.
- 78% of users agreed or strongly agreed the course had positively changed their behaviour and the behaviour of other staff within their organisation.

Average participant feedback measured at the end of the project for both of the courses was 4.1 out of 5, based on 784 active users. Participant feedback on the overall quality and relevance of the associated learning tools was 4.3 out of 5.

The total number of users completing the training was lower than had been hoped, with course completion rate lagging behind licence purchase rates. By the end of March 2018, 503 users had completed the course. RedR introduced a progress tracker bar so that learners could see how much of the course they had done to incentivise completion, with regular email reminders sent as well. RedR and DTS continue to consider how to further incentive course completion and are considering conducting a user experience survey to investigate completion rates and better understand how users are engaging with the platform.

2. EUROPEAN INTERAGENCY SECURITY FORUM

Output Title	Members actively engage with each other and the EISF Secretariat and the relationships amongst security risk management stakeholders is expanded and strengthened
Output number per LF		1	Output Score	A+
Impact weighting (%)?		10%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (Target)	Progress
1.1 % of EISF members who positively engage with EISF	60% attendance at EISF forums is maintained, with members scoring 3 out of 4 for quality and relevance, and 55% of members in at least one additional event per year	London Forum October 2017 50% attendance, rated 3.4 / 4; Utrecht Forum March 2018 56% attendance, rated 3.3 / 4. Overall, 71% attendance with average score of 3.35 out of 4
1.2 Number of country coordination events supported per year	At least four country coordination events attended and supported per year	8 country coordination meetings
1.3 Number of stakeholders and external experts who support EISF research projects	At least one sector expert included in EISF research working groups	6 sector experts supporting Managing the Security of Aid Workers with Diverse Profile and 2 supporting Managing Sexual Violence Against Aid Workers

The EISF Forum held in London in October 2017 was attended by 45 of 90 EISF’s member organisations (50%), with an overall satisfaction rating of 3.4 out of 4. Sessions held included Managing Sexual Violence and Legal Responsibilities in High Risk Environments. The Forum in Utrecht in March 2018 was attended by 53 out of 95 member organisations (56%), with an overall feedback rating of 3.3 out of 4. This included sessions on Safeguarding and Fraud and Corruption. Overall, 71% of EISF members attended at least one Forum last year, with feedback scoring an average of 3.3 out of 4, demonstrating a good level of engagement and satisfaction. Over half of the members also attended one of the five workshops held between April 2017 - March 2018.

During the reporting period EISF attended or supported 8 meetings to increase the knowledge base within the Secretariat and expand sharing amongst organisations in the same geographical regions. This included: Spanish NGOs; the Dutch Security Network; the Danish NGO Security Coordination Forum; the UK Security Focal Point Group; German and French NGO Security Coordination Groups; CINFO (Forum for Swiss NGOs); and the MENA & West Africa Regional Security Fora. These groups have a broad membership that includes many smaller, development focussed NGO’s who are not members of EISF, but are able access EISF resources, updates, reports and events.

EISF currently have two live research project supported by external stakeholders. Managing the Security of Aid Workers with Diverse Profiles is being supported by 6 sector experts, and the Managing Sexual Violence Against Aid Workers project is being support by 2 sector experts.

Output Title	Members actively share information and respond to requests, EISF website and social media is an up to date resource for humanitarian security issues, and EISF ensure the global debate on humanitarian security issues considers the needs of EISF members
Output number per LF		2	Output Score	A+
Impact weighting (%)?		10%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (Target)	Progress
2.1 Number of member updates circulated per year	24 EISF updates circulated, including questions and responses from members	42 updates (25 this reporting period and 17 last reporting period)
2.2 Number of external vacancies and training events added to the EISF website per month	Security-related vacancies and training opportunities uploaded to the EISF website each month, both from requests and pro-active search for appropriate postings	At end of March 144 external notifications live on website, including 8 vacancies, 133 trainings and 2 upcoming events. Average of 32 notifications per month.
2.3 Number of original papers and translations produced per year	EISF produces 1 paper, 2 short research reports, and at least 1 translation per year	Research paper Security of Aid Workers with Diverse Profiles and Duty of Care for humanitarian and development organisations. Contributed to Security Incident Information Management Handbook and translated Security to Go guide into Spanish and French.
2.4 Number of EISF blogs produced per month	An average of 3 blogs and service updates produced each month	73 over the year - an average of 6 per month
2.5 Number of external events and working groups that EISF participate in	EISF Secretariat actively participate in 2 sector working groups and 8 external events per year	10 external events and 5 cross sector working groups

Over the last reporting period a total of 25 updates were shared by the Executive Director, Project and Membership Officer and the Research Team. This was in addition to the 17 updates circulated last period. The number of updates has been reducing since the introduction of EISF_Chat in October 2017, with many questions and responses now handled directly through this service.

At the end of March there were 144 external notifications live on the EISF website, including 8 vacancies, 133 trainings and two upcoming events. Over the reporting period this averaged 32 notifications per month.

Work has continued with the Managing the Security of Aid Workers with Diverse Profiles research paper. Its findings were presented at the Borderless conference in March 2018 and it is expected to be completed by the middle of 2018. EISF has also been working with CINFO (forum for Swiss NGO’s) to better understand the Duty of Care obligations of aid organisations towards their staff. EISF has also worked alongside RedR and Insecurity Insight on the ECHO-funded Security Incident Information Management Handbook. The Security to Go guide has been translated into Spanish and French.

EISF has produced 73 blogs and service updates over the year, which is an average of 6 per month. This included 13 blogs on topics such as: Improving relations between programme staff and security advisors (Oct 17); Five guidelines for security risk management personnel: how to address sexual violence (Jan 18); Investing at the sharp end of risk (Feb 18); and duty of care and sexual violence in the humanitarian community (March 18), amongst others.

EISF participated in a total of 10 external events during the year, including four during the last reporting period, including: ICoCA Annual Conference (Oct 17); AidEx Brussels (Nov 17); Humanitarian Human Resources Conference, Bangkok (Nov 17) and SAR Consultancy – Risk Management in Action (Irish Security Series) (March 2018), amongst others. EISF also participated in the CSARN Physical Security Workshop and regular events at the ODI, the Frontline Club and Chatham House.

EISF continued to be actively engaged in 5 cross-sector working groups, including (i) the SLT Oversight Committee; (ii) IASC Reference Group for Principled Humanitarian Action; (iii) UK civil military coordination group; (iv) BOND counter-terrorism group; and (v) ATHA / ACF community of practice for protection of humanitarian action.

Output Title	Capacity of members for security risk management is improved and horizons broadened, EISF Secretariat identifies skills gaps in security risk management and develops means to address them, and practical tools and guides produced to fill skills gaps in humanitarian security
Output number per LF		3	Output Score	A+
Impact weighting (%)?		10%	Impact weighting % revised since last AR?	Y/N (if Yes, indicate if ↑or ↓)

Indicator(s)	Milestones	Progress
3.1 Number of external stakeholders participating in EISF forums	At least three non-NGO perspectives represented at each Forum meeting	15 external speakers at the October 2017 Forum and 4 at the March 2018 Forum
3.2 Number of capacity building events facilitated by EISF	3 capacity building events for improving security risk management of humanitarian response participated in and / or organised per year	4 conferences or workshops and 3 workshops
3.3 Number of guides and tools produced by EISF	At least 2 guides or translations produced per year	3 guides and 1 translation

At the October Forum in London there were 15 external speakers, and at the March Forum in Utrecht there were 4 external speakers, representing a cross section of organisations from NGO’s, policy and private sectors.

EISF facilitated 4 capacity building events during the reporting period: (i) The Borderless Conference (March 2018); (ii) Crisis Management Awareness Workshop, London for the UK Security Focal Point Group and the Muslim Charities Forum (Jan 2018); (iii) HHR Conference in Bangkok (Nov 17); and the MCF Risk Management Workshop in Birmingham (Nov 17). In addition EISF facilitated 3 workshops on Family Support, in Paris (Nov 17) and two workshops in Amman, Jordan on Crisis Management from an In-Country Perspective (Dec 17).

EISF has also launched a podcast series during the reporting period, with the first two covering access and security issues from outside the usual NGO perspective. Four more podcasts have also been released which have received positive feedback and are helping EISF reach a wider audience.

EISF recently published its Abduction and Kidnap Risk Management guide for NGO’s. Due to the sensitive nature of the document it was available only on the member’s area of the website, but has also been shared with other interested organisations upon request. The Security Risk Management guide for smaller NGO’s was launched in 2017, aiming to be a simple and easy to use resource for smaller NGO’s. The Security To Go guide has also been translated into Spanish, with the French version currently being finalised. A new guide designed to provide practical assistance to NGO’s on how to prevent staff from experiencing sexual abuse and how to deal with incidents is due to be published later this year.

3. INTERNATIONAL NGO SAFETY ORGANISATION

Output Title	INSO is able to govern, operate and upgrade its existing project portfolio
Output number per LF		1	Output Score	A
Impact weighting (%)?		20%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (Target)	Progress
1.1 The number of identified key staff positions filled	85%	86% HR Director recruited 2 vacancies for Section Officers.
1.2 The % of Organisational Development Plan (ODP) projects completed	40%	39% of ODP projects completed.
1.3 The % of measurable indicators of the Organisational Risk Register completed	50%	45% completed

The HR Director has now been recruited meaning all key positions in Dubai are filled. This position is considered critical, particularly as the organisation has increased rapidly both in size and complexity over the lifetime of the project. Key tasks to be taken forward by them will include strengthening the policy framework for national staff, improving recruitment processes, reinforcing legal and ethical standards of behaviour, and improving information management processes. INSO HQ does however report it remains under capacity for an organisation of its size; vacancies still remain with the Section Officers, with only one in three positions filled.

39% of Organisational Development Plan projects have been completed. INSO are on track to complete all of them by the end of 2019. Most recent developments include:

- Launch of INSO Safety & Access Review (SAR), its first global analysis product. This represents the first service the organisation has delivered beyond country-level advice. The SAR synthesizes country level quarterly reports into a graphical report and is aimed at regional and global security staff at headquarters. It was released to 60 NGO’s initially, and an additional 30 NGO’s have requested to receive the next issue.
- The Monthly NGO Bulletin report, providing insights on violence against NGO’s.
- Guidelines completed setting out the procedures for selecting, developing and implementing projects.
- Operating rules for Advisory Boards, updated to include issues such as selection, regional programmes, and the addition of a framework for the International Advisory Board.

The Risk Register has undergone two major revisions by INSO’s Board over the project period, originally reducing the number of indicators to 34, and then increasing them to 40. By the end of 2017, 40% of the measurable indicators had been completed, and this had increased to 45% by the end of the project, just missing the target of 50%.

Good progress has been made on raising awareness of INSO at HQ levels through publication of the Security and Access Review and in March 2018 INSO held its first core donor meeting in Berlin. This was hosted by the German Ministry of Foreign Affairs (MFA), with participation from DFID and the Dutch Ministry of Foreign Affairs. The meeting featured presentations and discussions on INSO’s achievements and plans for the future. The Dutch and German MFA’s confirmed ongoing core funding shortly after the conference.

Output Title	INSO develops new platforms, data analysis and research tools that improve support at both the country and international level
Output number per LF		2	Output Score	A
Impact weighting (%)?		20%	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones (Target)	Progress
2.1 The number of humanitarian crises benefiting from Direct Project Support (DPS)	2	3 Cameroon (Lake Chad Basin), South Sudan, Kenya
2.2 The number of NGO’s benefiting from INSO direct project support activities per country	30 NGOs per country where started	14 in Cameroon (77 in wider region); 80 in South Sudan; 103 in Kenya
2.3 Conflict and Humanitarian Data Centre (CHDC): the development of a centralised incident database and user interface	User interface final and CHDC final operational draft	Delayed, however it is hoped a version of the CHDC will be in operation by the end of 2018, with no requirement for extra funding

Over the lifetime of the project Direct Project Support (DPS) grants have supported INSO activities in Gaza, Cameroon, South Sudan, Yemen and Kenya. By the end of the project support to Gaza had ceased, and it was agreed in March 2018 that an underspend could be redirected to support start-up activities in South Sudan.

- Cameroon: INSO have been supporting the Lake Chad Basin response, co-funded by ECHO, from Cameroon. DPS funds have supported staff and local logistics to provide basic alerts and analysis. The normal full set of INSO services has been hampered due to a lack of formal registration and several requests to pay bribes from high level officials. The unexpected termination of the local Safety Adviser who had been leading the application process also disrupted the process further. INSO are supporting 14 NGOs working in northern Cameroon, and a total of 77 NGO’s in the wider Lake Chad Basin region.
- South Sudan: INSO successfully registered with the authorities in South Sudan at the end of November 2017 following calls by local NGOs for their presence there. A start up team was sent to set up an office, sort out logistical matters, and begin the recruitment of the first round of employees. INSO will take over the from the NGO Forum that has previously been present in the country, expanding upon the services they offered, including having dedicated teams in the west, east and central areas of the country. Services will start with training on NGO Security Management and First Aid. Despite only opening partner registration at the end of March 2018, INSO are already providing support to 80 NGOs, including 26 local NGOs and 12 UK NGOs (Oxfam, Save the Children, The British Council, Mines Advisory Council (MAG) and Islamic Relief).
- Kenya: The full INSO platform in Kenya has now been wound down and replaced with the new INSO Monitoring concept. This aims to provide reduced services in medium risk or transitional contexts to support preparedness and response activities. In Kenya INSO is providing support to 103 registered members.
- Yemen: An unexpected opportunity arose for INSO to operate in Yemen at the start of the year following lengthy but discreet scoping since mid-2017. Although a project still remains a distant prospect, INSO’s presence could potentially add value in this context. No partners are registered in Yemen yet.

The development of the Conflict and Humanitarian Data Centre (CHDC) has proved more complex and time-consuming than originally anticipated, meaning the target for a final operating version of the software by the end of the project was missed. This was due to several reasons, but a lengthy procurement process and the dismissal of the lead developer were contributing factors. INSO’s lack of experience developing such a hi-tech application was also a reason. Good progress has however been made and the database can now be completed in-house and without the need for additional funds. A beta version of it was demonstrated to donors in Berlin.

Progress over the past year includes:

- Completion of the Data Entry Application which will be used by INSO personnel to enter verified security incidents on to the database;
- Completion of the final design draft of the Analysis Application. This is the customer facing side of the CHDC and will allow users to interrogate the database and generate charts and maps according to need, giving users their own personal dashboard;
- Application Programming Interfaces, allowing applications such as the INSO Partners Portal to communicate with other parts of the CHDC.
- Recruitment of an in-house IT Development Officer, taking over from the external developer, who will complete the CHDC without the need for any further external support.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES

MISSION READY: INNOVATION IN HUMANITARIAN SECURITY TRAINING

Outcome
Indicator(s)	Milestones	Progress
1. Number of active users of Mission Ready (completed courses or currently using a course)	1,600 (3 years after launch)	1,668 licences sold
2. Evident change in knowledge of Mission Ready users	Analysis component of tool indicates increase in knowledge for 80% of users who completed the course (+600 participants 3 years after launch)	Overall increase in knowledge for 77% of users who completed the course, with 784 active users

The Mission Ready platform is a well-researched and executed product. RedR report it has become the go to platform for online security training and has received positive feedback from the humanitarian community with sales continuing to be made.

RedR and DTS have designed, developed and delivered 2 courses comprising 10 interactive scenarios, in 4 languages, with offline functionality. It has achieved an average feedback rating of 4.3 / 5 by users who have completed it. The training has been accessed by 59 organisations, from people of 85 different nationalities, operating in 90 countries, demonstrating its global reach. 43% of users were female.
Field Security Management was released in Arabic, French, Spanish and English in 2015, and an offline PC application was made available in 2016. The second Mission Ready course Remote Security Management (RSM) was released in English in 2016, and translated into Arabic in 2017.

Three years after its launch, the current number of licences sold for Mission Ready users stands at 1,668 (June 2018), just exceeding the logframe target of 1,600. The logframe target was revised down from 1,800 at the request of DFID as the end date of the project was brought forward to March 2018 (from September 2018), to align with the end date of other projects supported under the Security & Risk programme. The healthy uptake of licences is in part attributable to outreach and communication activities by RedR, such as articles in newspapers, via Facebook and Twitter, at conferences and workshops, and through email campaigns.

The Mission Ready Learning Management System (LMS) was used measure users pre and post-training scores for both courses. On average 77% of users who completed the courses stated their knowledge had improved between the pre and post trainings surveys. This is just below the target of 80%. Interestingly, the feedback for the Field Security Management course on its own was 85%.

Geographical Distribution of Mission Ready Users

Region	% of Total
MENA	10%
Europe	35%
Asia	5%
North America	19%
Africa	27%
Oceania	1%
Latin America & Caribbean	1%
No Info	2%

Of the 784 current active users, to date, 503 have completed the course. RedR report that learners are taking longer to complete the course than expected, and this may indicate it is being used as a learning platform that users return to as part of a monthly study plan, or that users dip into certain topic areas when they feel the need or context arises. Apparently this is not uncommon for e-learning modules with self-paced learning.

RedR have added a progress bar which they hope will make it easier for the learner to understand how much of the course is still to be completed, incentivising completion. RedR also plan to undertake a user experience survey of Mission Ready to investigate completion rates and better understand how participants are engaging with the platform. Ongoing licence sales and support for the platform suggest a continued need and interest for the training, supported by the user surveys that demonstrate its impact and quality.

EUROPEAN INTERAGENCY SECURITY FORUM

Outcome	Security risk management improved across the humanitarian sector through stronger relationships and greater trust
Indicator(s)	Milestones	Progress
1 % of members who utilise EISF services	80% of members utilise EISF services with a 5% growth in membership per year	86% of members utilised EISF services with a 9% growth in membership over the year.
2 Number of stakeholders and external experts who facilitate EISF events	Broad range of external experts facilitate EISF events	11 external speakers: 4 at the Forum in Utrecht and further 7 at workshops in Annam and Paris
Outcome	Knowledge and experience on humanitarian security risk management is shared using the EISF platform
Indicator(s)	Milestones	Progress
3. % of EISF members who use the EISF website	70% of members utilise the EISF website with 5% growth in membership per year	81% of member utilise the website (based on anecdotal information) with 9% growth
4. Number of visits to the EISF website and the number of documents that are downloaded per month	EISF website is accessed by a wide variety of countries and a broad range of materials is downloaded	619 page views and 495 unique page views. 15,753 new users and 9,433 documents downloaded
Outcome	Integrated security risk management skills and knowledge improved
Indicator(s)	Milestones	Progress
5. Number of workshop / learning events organised by EISF per year	At least four workshops / learning events organised by the Secretariat per year	3 workshops (Paris, Amman x2), plus 3 other learning events. 5 workshops over the year, 6 podcasts, 2 webinars.
6. Number of articles tackling gaps in SRM implementation produced by EISF per year	Two articles tackling practical gaps in SRM implementation produced by EISF	1 article published, 3 currently being worked on

EISF has made solid progress towards its outcome of improving security risk management across the humanitarian sector through stronger relationships and building greater trust. 5 new members joined over the last reporting period, and over the last year the number of EISF members has increased from 87 to 95, representing a 9% growth in membership. This reflects the ongoing demand for EISF services and networking opportunities.

The value of the EISF to the NGO security sector is demonstrated by 86% of its members utilising its services, either through attendance at events such as the Forum, workshops and country level meetings,
engaging through the new EISF_Chat facility, or asking questions of the Secretariat.

The EISF Chat facility allows members to share information and questions directly between themselves. There is also a public channel available where external experts can share their knowledge and respond to member queries. EISF­­_Chat also allows the Secretariat to share updates and useful links with members. Almost three-quarters of member organisations have signed up to the Chat facility, with 42% of them using the public area of the platform over the last 6 months.

The value of EISF is also reflected in its continued ability to attract external experts to speak at its forums and other events. Over the past year over 25 external speakers have addressed EISF’s forums and workshops, with 11 over the recent reporting period, including representatives from IRIN News, Chatham House, BRAC and UNICEF.

Over the last six months the EISF website has received 619 page views and 495 unique page views. EISF report that based on anecdotal evidence that most members use the website, particularly for the library of resources it offers, as well as the links to training events and for advertising vacancies. Looking ahead, EISF plan to supplement analysis of website usage with data collected from membership surveys to provide a more comprehensive picture of how members interact with it.

Between October 2017 and March 2018 there were 15,753 new users of the website with a total of 9,433 documents downloaded. EISF has continued to lead on best practice with Security Risk Management: a basic guide for smaller NGO’s and Security to Go: a risk management toolkit for humanitarian aid agencies as the most downloaded documents, both providing practical information to NGO’s to help them improve their security risk practices.

EISF has continued to increase its usage of social media, using specific events to raise awareness around the agreed messages in its communications plan. Newsletter subscribers have increased by 85 to over 1,000, and the blog on Five Guidelines for Addressing Sexual Violence in Humanitarian Security Risk Management by Megan Nobert achieved its highest number of monthly Twitter impressions with over 36,400.

At the end of the last reporting period EISF launched “EISF in Conversation”, a series of podcasts looking at access and security risk management using a series of speakers to attract non-security audiences, as well as EISF’s usual customers. To date the podcasts have received 721 views and 860 downloads, and have covered issues such as humanitarian access; humanitarian principles, the role of the global security advisor; and working in the field.

EISF has promoted learning and knowledge sharing by running three workshops in Paris and Amman (2) over the recent reporting period, as well as contributing learning at other forums and security networks. In November 2017 a Family Support workshop was held in Paris in collaboration with Hostage UK to promote good practice and support for families during abduction of a staff member from an NGO. In December 2017, two workshops were held in Amman on Crisis Management from the In-Country Perspective, aimed to bridge the gap between headquarters and country-based teams in the management and response to abduction and kidnap.

EISF has been actively working on 4 articles over the year. In December 2017 EISF and Mala Kumar, a technology and international development professional, published an article discussing the digital risks faced by LGBTQI aid workers working in hostile environments. The article has received positive feedback from the United Nations and USAID, as well as the LGBTQI network within GIZ. Other articles currently being drafted include: managing security related information; managing the security of aid workers with diverse profiles; and security considerations that aid organisations should take into account when engaging in sea search and rescue activities.

INTERNATIONAL NGO SAFETY ORGANISATION

Outcome	NGOs have access to high quality safety information, analysis and coordination services that help them operate and deliver aid more safely
Indicator(s)	Milestones	Progress
The percentage of registered NGOs indicating that INSO services improve their ability to operate and deliver more safely	To be assessed at end of project	94% of NGO’s registered with INSO believe their services help them operate more safely

INSO has made satisfactory progress against the organisational development milestones that will enable it to continue to provide a high level of information, analysis and coordination services for NGOs. The organisation is now in a much better place with a new HR Director meaning all key positions in Dubai are now filled. INSO does however report its HQ remains under capacity for an organisation of its size.

Progress against INSO’s organisation development plan is currently on track and it reports all outstanding issues will have been completed by the end of 2019. The risk register has undergone two major revisions over the project lifetime, initially reducing the number of indicators then increasing them. Currently 45% of indicators had been completed, narrowly missing the milestone target of 50%.

Significant organisational milestones have been achieved with the first publication of Security and Access Review aimed at HQ organisations, and the first INSO core donor meeting, held in Berlin and hosted by the German Ministry of Foreign Affairs, and with participation from DFID and MINBUZA, the Dutch Ministry of Foreign Affairs, who both confirmed follow on funding.

Direct Project Support (DPS) funds have been utilised in Gaza, Cameroon, South Sudan, Yemen and Kenya over the life of the project. INSO has recently successfully registered with the authorities in South Sudan and a start-up team has been sent out to the country that will begin providing initial services to 80 local NGO’s. INSO have continued to support the Lake Chad Basin response from Cameroon, but a full set of services has been hampered by the lack of formal registration and the termination of the local Safety Adviser. Following initial scoping during 2017, an opportunity in Yemen arose recently that may potentially open the way to INSO working there in the future. In Kenya, INSO has wound down its full platform but is still providing some preparedness and response services to over 100 members.

Progress developing the CHDC has been more challenging and time-consuming than INSO originally anticipated meaning the final operating version of the software was not finished by the end of the project. Delays were caused by a number of factors, including drawn out procurement processes and the sacking of the lead developer. INSO gave donors a demonstration at the donor conference in Berlin and it looks potentially very powerful. INSO are confident it can be completed in-house without the need for additional funds.

To measure the impact of INSO’s services on its members at the end of the project it conducted an online feedback survey in each country office. The survey sought to measure the impact of INSO services on NGO’s as basic measure of its performance and as a way to identify any areas of concern that its partners may have. The feedback will also be used to inform future project development, the addition of new services, or changes to geographical operating areas. An aggregate of the responses received showed that 94% of NGO’s believed INSO’s services help them operate more safely. A full summary of the questions asked and NGO’s responses can be found at Annex A.

Summarise the programme’s theory of change and major changes to it in the past year

The aim of the Business Case when it was originally drafted was to improve the safety of aid workers, and in particular the exponential increase in kidnap cases. These events were having the knock-on effect of making it difficult to recruit aid workers, meaning NGOs were less able to operate in hostile environments. The activities supported by the project were research, forums, training and information sharing, with NGOs, primarily through EISF, so that staff had a greater awareness of security issues and were equipped to avoid danger. The outcome of project was to enable staff to be able continue to work in such environments, allowing NGO’s to continue to provide humanitarian assistance.

The Theory of Change still remains valid at the end of the project, although has evolved somewhat. The focus on kidnapping specifically has expanded to encompass broader security and risk management practices by NGOs. This has been through the interactive online video training through RedR and DTS, and the frontline security information provided to local NGOs by INSO. The interventions supported by the programme have undoubtedly contributed to this end.

- The Mission Ready online training is specifically focussed on local and national aid workers unable to access formal security training programmes, and although completion rates are lower than hoped for, there remains an interested and need for the training.
- INSO are working at the frontline of some of the world’s most pressing humanitarian emergencies, providing information and advice to hundreds of local NGO’s, facilitating humanitarian access and promoting staff safety.
- EISF has continued to share best practice in security risk management through its forums, workshops, research, publications and blogs, with a steady growth in its membership and demand for its products and services.

Collectively all three organisations have contributed the project’s goal: “to save lives, alleviate suffering and maintain dignity.” Investment in security risk management of NGO partners remains as important today as when the Business Case was first drafted, and is likely to remain important in the future with DFID’s focus in fragile and conflict affected countries.

Explain major changes to the logframe in the past year

Major changes to the logframe over the past year were:

- Reductions to the target milestones for the Mission Ready logframe to reflect the fact the programme was ending 6 months early, to align with the end date of other projects supported under the Security and Risk programme;
- Amendment to the INSO logframe to reflect the agreement to channel a forecasted underspend to start up activities in South Sudan.
- For EISF some of the logframe wording was amended to reflect changes to the target milestones following the IT challenges capturing information about the use of its website. Some of the specific targets were also amended to “an average per month”, rather than a specific figure.

## D: VALUE FOR MONEY

The three projects supported under the Security and Risk programme represent an effective and cost efficient way for DFID to support improved risk and security management of our NGO partners. It has facilitated them to reach those people most in need, whilst also minimising the risks to themselves when delivering humanitarian assistance. With attacks on humanitarian aid workers remaining high this relatively small investment by DFID facilitates humanitarian access and assists delivery of larger scale humanitarian support, overall giving DFID good value for money.

Economy: RedR’s Mission Ready online training is substantially cheaper than face-to-face training when compared with other similar courses – typically costing one tenth of the price of traditional course. The price has been kept low to keep it attractive for its primary target audience – national staff working in humanitarian response. The average cost of a licence is $8 for individuals and $48 for organisations. These costs can be further reduced when licences are bought as a bundle. Proceeds from the sale of the licences have been reinvested back in the platform.

EISF members are required to pay a membership fee, which goes some way to reduce its reliance on donor funding. EISF has been working with a funding consultant to develop a strategy to bring in alternative corporate funding. A 3 tier strategy was agreed in March 2018 by the EISF membership offering organisations different levels of engagement and access to EISF depending on interest and commitment. The next step is to develop guidelines that ensure corporate partners adhere to EISF and members’ values. The strategy also includes a component to raise awareness amongst humanitarian sector sponsors and generally promote the importance of good security risk management for staff care and programme sustainability.

Efficiency: RedR achieved cost savings by sharing resources with RedR Kenya during filming, negotiating discounts for accommodation and facilities, securing documentary interviews for free, obtaining multiple quotes to get the best price for translations, and using in-house resources to assist with subtitling all Spanish translations. EISF have managed to get some technical input for their papers for free, and the German Development Agency GIZ hosted and covered all expenses for the forum in September 2016 in Eschborn, and a security provider sponsored the September 2017 forum in London.

Effectiveness: Mission Ready online security training, is an effective method of reaching a wide audience, in particular national staff who may find it difficult to receive face-to-face training due to travel, visa or geographical restrictions. Statistics gathered during the reporting period show that people of 85 different nationalities, operating in 90 countries, used the training, demonstrating its global reach.

EISF membership continues to grow, with 86% of its member organisations actively engaged with it, and over nearly 16,000 new users of its website, demonstrating its relevance and usefulness to the sector.

INSO has established a comprehensive network of field level safety platforms that provide daily support to more than 800 national and international NGOs in 11 high risk and Level 3 countries, and this is set to expand as the South Sudan platform becomes established. In addition the CHDC will be a resource available to all INSO members when it is finished.

E: RISK

Overall risk rating: Moderate

Overview of programme risk: The risk rating for the project is currently judged to be moderate, increased from minor in 2016. This primarily due to the funding being channelled to INSO which is working in some challenging and dangerous countries. It also reflects RedR’s lower than anticipated completion figures.

The challenge and main programme risk for RedR is ensuring the courses they have developed reach as many users as possible, and in particular those aid workers in the field that cannot access traditional security training. As already stated, despite the target for number of licence sales being met (1,600), course completion rates lag behind (506), with currently 784 active users. The user experience survey proposed by RedR will be an important process to better understand and incentivise completion rates.

Most of EISF’s activities are considered low risk, given they operate mostly in Europe. EISF does however recognise the need to diversify its funding base further. The work being done with the funding consultant will be important to help EISF expand its donor base and secure funding from new corporate sources. EISF will however have to proceed carefully to ensure corporate sponsorship does not compromise its core values or neutrality.

INSO is operating in some risky and difficult countries and is facing challenges establishing new platforms in Cameroon and South Sudan and potentially Yemen. Now the new HR Director is in post some of the work streams that had previously been on hold can be taken forward, which is positive. The donor meeting held in Berlin was also a positive step forward for the organisation to secure on-going core support, but it does need to consider its longer term sustainability strategy and further diversifying its funding base.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Delivery against timeframes

All three partner organisations have provided good quality narrative progress and financial reports on time. As indicated earlier, the end date for Mission Ready was brought forward from 30 September to 31 March 2018 to align with the end date of the other projects supported under this Security & Risk programme, with logframe milestones changed accordingly. RedR and EISF have spent funds in line with original budget estimates; INSO requested some funds were reallocated from a potential underspend to support start up activities in South Sudan which was approved. All three projects have spent in full.

A Delivery Chain mapping exercise was carried out for all partners in December 2017 when this became mandatory. Similarly all partners were required to provide information and statements of assurance on safeguarding following the enhanced Due Diligence standards put into place by the Secretary of State in March 2018. INSO in particular has been proactive at updating and sharing its Risk Register regularly.

Performance of Partnerships

RedR has developed a successful partnership with DTS throughout the lifetime of the project to develop the training and set up systems to manage ongoing project activities effectively, improve the platforms and resolve problems. INSO experienced problems with its external developer for the CHDC, and in hindsight should have brought this in house sooner. DFID’s engagement on the project has suffered due to the departure of the HSOT Security & Risk adviser in November 2017 resulting in reduced direct engagement with partners towards the end of the project.

G: MONITORING, EVIDENCE & LEARNING

Monitoring

The programme has been regularly monitored throughout its lifetime, with 3 Annual Reviews conducted by DFID since 2015. EISF and RedR have provided progress reports on a 6 monthly basis, and INSO on a quarterly basis for its last grant. DFID and the three partners have met on a regular basis, with attendance at EISF’s forums and INSO donor meetings. The former CHASE OT Security Adviser was also on the Mission Ready Steering Committee.

RedR have undertaken their own monitoring of the Mission Ready platforms through user feedback surveys, and are planning to conduct a user experience survey to understand better how people are interacting with the platform. INSO also undertook a feedback survey of its members at the end of the project to measure the impact of its services. They do however recognise that their impact measurement can be improved and are currently using a Harvard University intern to assess its existing evaluations tools and make recommendations for a set of analytical indicators and tools for monitoring and evaluating impact. EISF regularly obtain feedback on the quality and relevance of their forums from members.

This PCR has been drafted by the Programme Manager based on self-reporting from the partners, review of previous Annual Reviews and the original Business Case and Intervention Summary. It has been shared with HRG’s Humanitarian Response Manager and HSOT Security Adviser for comment and input, approved by the Head of HRG and shared with the Deputy Head of CHASE.

Lessons learned and recommendations

RedR
1. RedR should continue to develop its marketing and promotion of Mission Ready to ensure maximum sales of licences and up take of the training.
2. Whilst RedR have met the target for licence sales, further investigation is needed to better understand and incentivise course completion rates. In hindsight, perhaps the logframe indicator should have been number of courses completed, rather than number of licences sold.
3. Now DFID’s grant to RedR has finished it needs to consider how the platform will be maintained and how the training will be kept current so it does not become quickly out of date.
EISF
4. Future DFID support for EISF should shift away from process / activity indicators and give a better sense of impact measurement of the organisations’ work. This should include contributions towards meeting DFID’s Grand Bargain commitments such as localisation, and other priorities such as safeguarding.
5. EISF should continue to attempt to expand its donor base and secure funding from other European donors. EISF are in the process of developing a strategy to raise funds from the corporate sector, but it is not known if European donors are to be targeted. ECHO would be an obvious potential donor for EISF.
INSO
6. INSO held a core donor meeting in March 2018 which was a positive step forward. Building on its success to date it needs to develop a sustainability strategy for the future, further expanding is funding base, and reducing its reliance on a small number of donors, particularly if it is to continue to expand.
7. INSO recognises it needs to further refine how it measures the impact of its services and how it communicates these successes to its partners and donors.
8. INSO recognises its staffing compliment at headquarters remains light, and there is limited ability to cover when senior members of staff move on. INSO need to think about how to make HQ staffing more resilient with sufficient capacity to allow work to continue whilst carrying short term gaps.
9. Both RedR and INSO have undertaken software development projects under this grant. A common lesson is that development of these applications can be more complex and time-consuming than originally anticipated. Furthermore it can be difficult to predict potential demand and uptake at the outset of the project.
DFID
10. Aid workers continue to work in dangerous and fragile countries at the frontline of aid delivery. These are usually from local or national NGOs. The need for DFID’s continued investment in this sector is required, and it offers potentially good value for money if it opens up humanitarian access and space for other relief agencies to operate.
11. The safety and security of DFID’s NGO partners working in humanitarian contexts remains important to DFID and it should consider continuing to provide core support to organisations such INSO and EISF. The newly approved Humanitarian Global Services Business Case includes provision to support improved security risk management practices for NGOs, building on previous investment in this sector.
12. DFID should consider allocating part of the HSOT Security Adviser’s time to advise on future support to EISF, INSO, as well as broader NGO security and risk management related matters.

Annex A: INSO Summary User Survey Results:

Country	Q no. & Form of question	% of NGO respondents saying yes or giving a positive rating	Date of survey close	Response rates
AFG	Q5 - How would you evaluate the usefulness and relevance of INSO services in terms of assisting you in managing your security policies, protocols and staff safety?	85% (Very good + Good)	20-Feb-18	244 respondents
CAR	Q2 - How satisfied are you with INSO services	98% (Very satisfied + Satisfied)	20-Mar-18	62 respondents
DRC	Q4 - How would you evaluate the usefulness and relevance of INSO services in terms of assisting you in managing your security policies, protocols and staff safety?	86% (Very good + Good)	10-Dec-17	76 respondents
MALI	Q11 - Do INSO services correspond to your needs in helping you improve your security management practices and understand your operating environment?	99% (Strongly agree + Agree)	08-Jan-18	162 respondents
KEN	Q1 - How much do you agree with the following statement? "INSO KENYA services are relevant and useful to improve my NGO's understanding of the environment and our security management practices"?	96% (Strongly Agree + Agree)	08-Dec-17	78 respondents
SOM	Q1- How much do you agree with the following statement?: “the services provided by INSO improve my organization’s understanding of the environment and our security management practices.”	100% (Strongly Agree + Agree)	31-Dec-17	69 respondents
NGA	Q1 - How much do you agree with the following statement ? "INSO Nigeria services are relevant and useful and improve my NGO's understanding of the security environment ?"	92% (Strongly Agree + Agree)	27-Apr-17	37 respondents
UKR	Q3 - In general terms, are you happy with the standard of service provided by INSO Ukraine?	100% (Yes)	30-Oct-17	35 respondents
SYR	Q3 - Do you agree with the following statement: "The services currently provided by INSO Syria support my organisation to operate more safely"?	92% (Strongly Agree/Agree)	19/01/2018	102 respondents
IRAQ	Q4 - In general terms, are you happy with the standard of service provided by INSO Iraq?	98% (Strongly agree + Agree)	12-Nov-17	102 respondents