Annual Review

Title: Sustainable Urban Economic Development (SUED) Programme
Programme Value: £60m		Review Date: September 2018
Programme Code: 204338	Start Date: September 2016	End Date: September 2022

Summary of Programme Performance
Year	2017	2018
Programme Score	C	B
Risk Rating	Major	Major

DevTracker Link to Business Case:	The Business Case had been excluded from publishing due to procurement. It will be published at the next publishing round in September 2018.
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204338/documents

A. Summary and Overview

DFID Kenya’s Sustainable Urban Economic Development (SUED) programme (2017 – 2022) aims to support up to 10 fast growing towns in Kenya to develop sustainable urban economic plans, improve the business environment and attract investment for climate-resilient[1] infrastructure and value chain projects.
[1] Refers to assets located, designed, built and operated with consideration to current and future climate change.

Kenya is urbanising rapidly. By 2030, almost half the population is expected to live in urban centres. Although the three major cities of Nairobi, Mombasa and Kisumu along the Northern Corridor[2] contain half of Kenya’s urban population, towns situated on secondary economic growth corridors are seeing the fastest population growth estimated at 7.3% a year. Poorly planned urbanisation often results in informal settlements that depict stark socio-economic inequalities, extreme poverty, inadequate and unaffordable housing, high unemployment and vulnerability to environmental shocks. Creating the right conditions now for inclusive and sustainable urbanisation in smaller, fast growing and marginalised towns, presents an excellent opportunity to achieve more balanced economic growth, reduce rural-urban poverty and create climate resilient livelihoods for future generations.
[2] The busiest and most prominent transport corridor in East and Central Africa, providing a gateway through Kenya to the landlocked economies of Uganda, Rwanda, Burundi, Eastern DRC and South Sudan.

Through supporting urban economic development, the UK is directly responding to the Government of Kenya (GoK) ‘Big Four’ priorities[3] while strengthening the UK’s partnership with Kenya in line with the new UK Africa Strategy and DFID’s Strategic Directions initiative.
[3] These are: Manufacturing, Universal Healthcare, Affordable Housing and Food Security - President Kenyatta’s legacy projects that he has committed to have in place by the time he exits office in 2022.

SUED implementation is through:
- A Private Sector Consortium led by a Managing Agent - Coffey International Development Ltd. The Managing Agent provides overall programme management, technical oversight and coordinates the consortium of subcontractors comprising of urban economic planners, investment climate advisers, technical experts and capacity building specialists. The Private Sector Consortium contract was signed in August 2018, with a 12 month inception phase starting in September 2018.
- A complementary strategic partner – the International Finance Corporation (IFC), member of the World Bank Group (WBG). A Memorandum of Understanding (MoU) between DFID and IFC was signed in November 2017 to support the IFC’s Kenya Competitiveness Enhancement Programme carry out national and sub-national investment climate reforms and sector-specific reforms including the development of Special Economic Zones (SEZs) and Public-Private Partnerships (PPPs).
- An independent Monitoring and Evaluation (M&E) firm – Procurement is ongoing, to be completed by October 2018. This firm will carry out rigorous M&E, supporting programme learning and adaptation to demonstrate that the project is (or is not) achieving its intended outcomes and impact.
Summary supporting narrative for the overall score in this review

This is the second annual review of the SUED programme. The first annual review completed in August 2017 assessed that the programme’s slow mobilisation was off-track and performance substantially did not meet expectations. During this reporting period, timely mobilisation of partners and implementation of activities, though prioritised, has remained challenging. This has been primarily due to:
- Delays in procurement of the Private Sector Consortium due to changes in the regulatory environment, internal procedures and incomplete procurement information from bidders. The contract was signed in August 2018, with a 12 month inception phase starting in September 2018.
- Unprecedented political uncertainty: In 2017 Kenya held two elections (August 2017 and October 2017) which resulted in changes within the national and county governments. This hindered IFC’s engagement with counties and government Ministries, Departments and Agencies (MDAs) as new governors were elected and new political appointments were made in key MDAs in early 2018. As a result, substantive engagement only resumed in March 2018.

In spite of this, progress has been made on a number of key areas as follows:
- Establishment of a strategic partnership between DFID and WBG: In November 2017, DFID Kenya and the IFC signed a MoU to support investment climate reforms and sector-specific reforms including the development of SEZs and promotion of PPP’s; through structuring priority projects, market engagement and institutional capacity building at the country level.
- High-level stakeholder engagement: The DFID Kenya team discussed the programme with the Principal Secretary for Housing and Urban development and the WBG Task Team Leader for the $300m Kenya Urban Support Programme.[4] The discussion outlined priority areas of support and opportunities for collaboration.
  [4] SUED was designed before the World Banks’ Urban Support Programme. This makes the World Bank a key stakeholder to be engaged before and during SUED’s implementation
- Procurement of implementing partners: Procurement of the Private Sector Consortium was completed in August 2018, with a 12 month inception phase starting in September 2018. Procurement of the M&E firm is to be completed by October 2018.
- Prioritised counties and sectors for business environment reforms: The IFC has engaged selected county governments, completed a scoping exercise to identify key constraints to doing business both at national and sub-national levels and developed work plans for interventions. Institutional engagement has been positive and demonstrated high appetite and commitment for reforms, indicating a timely opportunity for SUED’s implementation. For example, through SUED support, the IFC is working with the GoK to develop an affordable housing PPP prototype in Nakuru County. Both the National Treasury and State Department of Housing and Urban Planning have formally communicated support to Nakuru County and intent to scale up the Naivasha prototype to other counties, as part of the GoK ‘Big Four’ priorities to develop 500,000 affordable houses by 2022.

Overall output score and description

SUED’s cross-cutting portfolio is central to delivery of DFID Kenya’s Sub-National strategy, HMG Prosperity Strategy and the Africa Strategy. Although the protracted mobilisation phase for the Private Sector Consortium has been challenging, progress has been made in a number of key areas, working with selected counties. The overall output score of this programme is B - Moderately did not meet expectation. Output 1 has scored a C and Output 2 has scored a B. Progress by IFC is considered on track; therefore Output 3 has scored an A. The impact weighting for each output was adjusted to reflect the level of input required to achieve the milestones that could be measured during this reporting period. As Output 4 was not being marked in this annual review, the impact weighting for Output 4 (15%) was equally distributed between Outputs 1 – 3 (5% added to each of the outputs).

Output	Impact weighting	Score
1. Improved capacity of selected secondary towns to plan and deliver market-driven urban economic planning	30%	C
2. Facilitation of public-private financing of climate resilient infrastructure and value chain development projects	45%	B
3. County level business environment reform interventions are undertaken	25%	A
4. Increased knowledge and information on sustainable urban development	0%	N/A

The programme’s risk remains ‘major’ as per the approved business case, due to potential changes in the political economy during the life of the programme, as well as risks of fraud, bribery and corruption on high-value infrastructure and value-chain investments.

Key Lessons
Managing change in DFID’s procurement processes effectively. Programme implementation has experienced delays due to important changes in DFID’s procurement process. Lessons from SUED have been shared and incorporated to refine these processes.

Making better use of short-term, call down facilities available. To manage unexpected delays in future, the DFID Kenya team will consider utilising technical assistance call-down facilities available through DFID Centrally Managed Programmes (CMPs), such as the DFID Infrastructure and Cities for Economic Development (ICED) programme, to deliver on specific, short-term milestones.

Recommendations for the year ahead

Detailed recommendations for the next year have been provided against each of the outputs. High-level recommendations are summarised in the table below:

Outputs 1 – 4 Recommendations	Rationale	Timeframe
Rec 1: The DFID Kenya team to exercise careful and diligent management through monthly meetings with the supplier to ensure key milestones are met and provide quarterly updates to the Head of Office.	To get performance back on track	Ongoing, as per contractual timelines
Rec 2: The DFID Kenya team to ensure the final town selection criteria is transparent, objective, inclusive and meets the objectives of the programme	To mitigate reputational risks linked to perceived lack of transparency	Before the end of inception
Rec 3: The DFID Kenya team to revise Output Indicator 1.2	To accurately reflect private sector input	By the end of the inception
Rec 4: The DFID Kenya team to disaggregate milestone indicators for each implementing partner	To accurately capture partners performance	By the end of the inception
Rec 5: IFC to include tangible measures to assess and the long-term improvements from institutional capacity building and/or technical assistance in the monitoring and reporting framework to DFID	To ensure key functions can be delivered by institutions over time	Ongoing, according to action plan
Rec 6: The DFID Kenya team to create an action plan that ensures strong collaboration between IFC and the Private Sector Consortium	To ensure synergies in implementation	Ongoing, according to action plan
Theory of Change & VFM Recommendations	Rationale	Timeframe
The DFID Kenya team to apply for no-cost extension to adjust the time for implementation	To get performance back on track and ensure VfM	To be determined during inception
The DFID Kenya team to request for HMT’s approval early in order to proceed into implementation on schedule	To get performance back on track and ensure VfM	To be determined during inception
DFID Kenya team with implementing partners to test the validity of the ToC in relation to the logframe and make improvements as required	Due to political and contextual changes in Kenya	By the end of the inception phase

## B: DETAILED OUTPUT SCORING

Output Title	Improved capacity of selected secondary towns to plan and deliver market-driven urban economic planning
Output number per LF		1	Output Score	C
Impact weighting (%):		30%	Impact weighting % revised since last AR?	Yes(↑)

Indicators	Milestones for this review	Progress
1.1 No. of high quality urban development plans supported in selected secondary towns	Stakeholder engagement plan and county selection strategy finalised	C - Substantially did not meet expectation. These milestones were contingent upon the Private Sector Consortium being in place and the inception phase being underway.
1.2 Effective roll-out of urban development plans in selected towns	Mapping of County Integrated Development Plans and key stakeholder plans
1.3 Increased private sector consultation in urban planning	To be defined at inception phase.	N/A for this annual review.

SUED is implemented through a Private Sector Consortium managed by Coffey International Development Ltd, and the IFC. Output 1 milestones (supporting the creation and rolling-out of urban economic plans and involving the private sector in planning processes) are the responsibility of the Private Sector Consortium. However, that consortium has been under procurement for over the review period and so these milestones have not been achieved.

Reasons for delays in procurement of the Private Sector Consortium were as set out above. However, the contract was signed in August 2018, with a 12 month inception phase starting in September 2018. The protracted mobilisation phase for the Private Sector Consortium has been particularly challenging. To get programme performance back on track, the DFID Kenya team will need to exercise careful and diligent management to ensure project milestones are completed on time and take corrective actions promptly as required. As specified in the contract, monthly performance monitoring meetings will be carried out with Coffey International Development Ltd, to ensure that key inception milestones are met over the next 12 months. These include: 1) three towns selected for the first phase; 2) urban economic plans developed for the selected towns, and 3) sub-contractors procured as required. The DFID Kenya Head of Office will be provided with quarterly progress updates throughout the coming year.

A lesson learned is that DFID Kenya should consider utilising technical assistance call-down facilities through DFID CMPs such as ICED to deliver against short-term programme milestones if facing protracted procurement processes.

In the review period, the DFID Kenya team has proceeded to pave the way for the Private Sector Consortium inception phase through engaging high-level stakeholders including (i) the Principal Secretary for Housing and Urban development and the World Bank Task Team Leader for the $300m Kenya Urban Programme; discussing opportunities for collaboration including having representatives of DFID, the World Bank and Government on each of the respective Steering Committees; and (ii) the Private Infrastructure Development Group (PIDG) companies, such as GuarantCo, on potential sources of financing for climate-resilient infrastructure and value chain projects identified . The DFID Kenya team has further refined the draft county selection criteria which will be finalised by the Private Sector Consortium through further consultations with key stakeholders.

Lessons identified this year, and recommendations for the year ahead linked to this output

- Rec 1: The DFID Kenya team to exercise careful and diligent management to ensure project milestones are completed on time, through monthly performance meetings with the lead supplier to ensure key inception milestones are met and providing quarterly updates to the Head of Office.
- Rec 2: The DFID Kenya team to ensure the final town selection criteria is transparent, objective, inclusive and meets the objectives of the programme.
- Rec 3: Output Indicator 1.2 to be revised to more accurately reflect private sector engagement.

Output Title	Facilitation of public-private financing of climate resilient infrastructure and value chain development projects
Output number per LF		2	Output Score	B
Impact weighting (%):		45%	Impact weighting % revised since last AR?	Yes (↑)

Indicators	Milestones for this review	Progress
2.1 Strengthened technical capacity of counties to originate, screen and prioritise PPPs	Both Private Sector Consortium and independent M&E firm procured by DFID; SUED governance structure finalised and KPI's established; ToR for PPP consultancy firm finalised	B - Moderately did not meet expectation. Procurement by DFID (on-track); SUED governance and KPI's established (off-track); ToR for PPP firm finalised (on-track)
2.2 Volume of i) public, ii) private and iii) public-private finance mobilised for climate resilient infrastructure and value chain development projects (ICF KPI 11 & 12)	To be defined once the Private Sector Consortium is in place.	N/A for this annual review. / The sequencing of SUED interventions means that Outputs 2.2, 2.3 and 2.4 will only yield results in the implementation phase of the programme (after inception phase), once the urban economic development plans have been developed and key infrastructure projects identified for which financing is required. As such, no milestone targets were assigned for this reporting period.
2.3 Leverage ratio for projects brought to bankability
2.4 Number of climate resilient infrastructure and value chain development projects in implementation with sustainable financing models as a result of SUED support

Progress was made against Output 2.1, though Outputs 2.2, 2.3 and 2.4 were to be defined once the Private Sector Consortium (main implementation partner) was in place and so are not applicable for this annual review.

Summary of progress against Output 2.1 is as follows:
- Procurement of implementing partners: Procurement of the Private Sector Consortium was fully achieved. The contract was signed in August 2018 with inception activities due to commence in September 2018. Procurement of an independent Monitoring and Evaluation (M&E) firm was partially achieved. DFID Ministers approved the £2.5 million contract with the preferred supplier in July 2018 and the process for signing a contract with the firm is underway.
- SUED governance: This milestone was partially achieved. The programme governance structure comprises a Steering Committee (for strategic oversight) and a Programme Management Unit (for programme coordination) to be established by the Private Sector Consortium. The DFID Kenya team developed a draft Terms of Reference (ToR) for the Steering Committee outlining the composition, roles and responsibilities of members. The draft ToR and nomination of Steering Committee members comprising of at least 40% women, will be finalised by the Private Sector Consortium during the inception phase.
- Key Performance Indicators (KPIs). This milestone was not achieved. The Private Sector Consortium and M&E contracts specify KPIs. The programme’s overarching KPI’s are as set out in the programme logframe and will be finalised during the inception phase.
- ToR for PPP consultancy firm. This milestone was fully achieved. This task was led by IFC to deliver PPP capacity building for counties, through a consultancy firm. The ToR was finalised and training was undertaken on PPP project identification, screening and prioritisation. Key lessons from this task showed that standard one-off capacity building involving theoretical workshop/ classroom based styles delivered by short-term consultants, do not effectively transfer or retain institutional knowledge. Moving forward, institutional capacity strengthening will be embedded into each transaction supported by SUED to ensure key functions can be delivered by institutions over time, with the goal of creating a cohort of PPP reform champions at the county level who can transfer their knowledge to other colleagues. It is recommended that tangible measures to track, monitor and assess and the long-term improvements as a result of institutional capacity building and/or technical assistance activities are included in IFC’s monitoring and reporting framework to DFID.

Lessons identified this year, and recommendations for the year ahead linked to this output

- Rec 4: The DFID Kenya team to disaggregate milestone indicators for activities undertaken by each implementing partner, for ease of reporting in subsequent annual reviews.
- Rec 5: IFC to include tangible measures to tack, monitor and assess and the long-term improvements as a result of institutional capacity building activities in the monitoring and reporting framework to DFID.

Output Title	County level business environment reform interventions are undertaken
Output number per LF		3	Output Score	A
Impact weighting (%):		25%	Impact weighting % revised since last AR?	Yes (↑)

Indicators	Milestones for this review	Progress
3.1 Mechanisms/ institutions for hosting public-private dialogue identified	Strategic partnership in place between DFID and the IFC, and performance on-track delivering complementary business environment reforms	A - Outputs met expectation. Strategic partnership in place between DFID and the IFC delivering reforms (on-track)
3.2 No. of targeted investment promotion strategies supported in conjunction with county government and private sector stakeholders	To be defined once the Private Sector Consortium is in place.	N/A for this annual review
3.3 No. of targeted investment promotion strategies supported in conjunction with national government and private sector stakeholders	Project stakeholders mapped and engaged on reform activities, in particular close working collaboration with the Ministry of Transport, Infrastructure, Housing and Urban Development and with the World Bank’s urban programme (credit to GoK)	A - Outputs met expectation. Project stakeholders mapped and engaged (on-track)
3.4 No. of business environment reforms enacted by County government	To be defined once the private sector consortium is in place.	N/A for this annual review

The IFC is responsible for delivering milestones under Output 3.

Output 3.1 Mechanisms/institutions established for public-private dialogue:
Progress against this milestone is summarised as follows:
Strategic partnership in place between DFID and IFC. This milestone was fully achieved. In November 2017, DFID Kenya and the IFC signed an £8.5 million Memorandum of Understanding (MoU) and set up a Single Donor Trust Fund for DFID to support the IFC’s Kenya Competitiveness Enhancement Programme (KCEP) to carry out:
  1. Economy-wide investment climate reforms to address market failures impacting the broader business environment at national and county levels.
  2. Sector-specific reforms targeting key constraints to the economy (e.g. SEZ’s, agri-business, and manufacturing).
  3. PPP capacity building for counties.

Performance on-track delivering complementary business environment reforms. This milestone is on-track, after experiencing initial delays. During 2017, Kenya held an unprecedented two presidential elections, in August and October, with an extended period of political uncertainty resulting in changes within both national and sub-national governments. This period hindered IFC’s engagement with both counties and national government as new governors were elected and new political appointments were made in key MDAs over the course of a number of months. For example, the current Principal Secretary for Housing and Urban Development was appointed in February 2018 and election petitions against the governors of key counties were not dismissed until early 2018. As a result, substantive engagement by the IFC with Government only resumed in March 2018.

Nonetheless, since then progress has been good and is considered on-track. During this reporting period the IFC has:
  1. At national level: Prioritised technical assistance to develop ease of doing business action plans in collaboration with Government of Kenya’s (GoK) Ministries and unlocking private investments in three sectors aligned with the GoK ‘Big Four’ priorities[5] (Agribusiness, Manufacturing and Affordable Housing).
    [5] These are: Manufacturing, Universal Healthcare, Affordable Housing and Food Security - President Kenyatta’s legacy projects that he has committed to have in place by the time he exits office in 2022.
  2. At sub-national level: Prioritised technical assistance to counties with strong appetite for reform pilots (e.g. Kisumu, Nyeri and Mombasa) to enhance/streamline existing automated licensing systems/portals and business interfaces. IFC is providing demand-led business case analysis to support the development of well-structured and bankable PPP projects in sectors identified by selected counties (Affordable Housing, Livestock and Transport).
  3. On Affordable Housing, IFC is working with the GoK to develop an affordable housing PPP prototype in Naivasha (Nakuru County). Both the GoK National Treasury and State Department of Housing and Urban Planning have formally communicated support to Nakuru County and intent to scale up the Naivasha prototype to other counties, as part of the GoK ‘Big Four’ priorities to develop 500,000 affordable houses by 2022. A formal request has also been submitted by Laikipia County for IFC support on affordable housing. A second site has been identified and IFC is currently engaging a consortium of technical, financial, legal and social and environmental experts to support the refinement of the Naivasha prototype for Laikipia County, and create a framework for scaling up the scheme across the country. Procurement of the team of experts will be concluded by October 2018.
  4. On Livestock, IFC engaged a technical expert in July 2018 to carry out a pre-feasibility assessment on the potential for PPP/private sector participation (with some level of partnership with the GoK) in establishing the “Integrated Feedlot Scheme” in Laikipia County. The scheme seeks to consolidate the full red meat value chain i.e. feedlot, abattoir, meat processing and export with clear value addition (job creation and retaining wealth within the community), to increase the county’s competitiveness via improved genetics and disease control.

This positive engagement has demonstrated high appetite and commitment from selected counties for reforms, indicating a timely opportunity for SUED implementation and collaboration between IFC and the Private Sector Consortium. Initial lessons from IFC’s activities highlight the need to strengthen capacity building (see Output 2.1) and the political importance of having a transparent county selection strategy. Once the Private Sector Consortium inception phase kicks-off, it will be important to draw on/leverage off IFC’s experience in working with counties and ensure synergies in county selection, technical assistance in national level reforms and development of sub-national bankable PPP projects.

Output 3.3 No. of targeted investment promotion strategies supported. This milestone is on-track. Progress for each component is summarised below.
Mapping/engagement of project stakeholders. To prioritise the above three sectors (Affordable Housing, Livestock and Transport) and counties for potential bankable PPP projects, IFC has engaged a wide range of institutional and private sector stakeholders shown in the table:

Public sector institutions	Private sector institutions
Office of the President / National Treasury / Ministry of Industry Trade and Cooperatives / Ministry of Agriculture / Office of the Attorney General / SEZ Authority / Nairobi County / Mombasa County / Kisumu County / Nyeri County / Kericho County / Uasin Gishu County / Narok County	Kenya Private Sector Alliance / Kenya Association of Manufacturers / Kenya National Chamber of Commerce / East African Grain Council

Key project stakeholders engaged by DFID Kenya:
  1. At national level: The DFID Kenya team has directly engaged the Principal Secretary for Housing and Urban development and the World Bank Task Team Leader for the $300m Kenya Urban Programme, to discuss priority areas of support for the GoK and potential areas of collaboration.
  2. At sub-national level: The DFID Kenya team has also engaged a few counties (Wajir, Isiolo, Kisumu and Laikipia) to discuss their broad development plans. However, it was deemed necessary to first refine the county selection strategy and agree on priority counties with the main implementing supplier, before any deeper programme-specific engagement.

The sequencing of SUED interventions means that Outputs 3.2 and 3.4 will only yield results once the Private Sector Consortium is in place and urban economic development plans developed and key infrastructure projects identified for which financing is required. As such, no milestone targets were assigned for this reporting period.

Lessons identified this year, and recommendations for the year ahead linked to this output

Rec 5: The DFID Kenya team to create an action plan that ensures strong collaboration between IFC and the Private Sector Consortium in county selection, technical assistance in business reforms and development of bankable PPP projects.

Output Title	Increased knowledge and information on sustainable urban development
Output number per LF		4	Output Score	N/A
Impact weighting (%):		0%	Impact weighting % revised since last AR?	Yes (↓)

Indicators	Milestones for this review	Progress
4.1 No. of quality knowledge products produced and disseminated to strategic stakeholders	To be defined once the private sector consortium is in place.	N/A for this annual review
4.2 Level of stakeholder engagement and institutional knowledge of sustainable urban development and climate change issues as a result of SUED support (ICF KPI 14)
4.3 Evidence of replication of SUED initiatives by other actors and HMG-supported activities are creating the incentives for others to act on climate change i) in SUED targeted counties, and ii) in non-SUED targeted counties (ICF KPI 15)

The independent M&E firm is responsible for delivering Output 4 milestones which are contingent upon the Private Sector Consortium first being in place. As such, no milestone targets were assigned for this reporting period.

Lessons identified this year, and recommendations for the year ahead linked to this output
N/A.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

During the review period there were no changes in the programme’s Theory of Change (ToC). As per the business case, the ToC assumes that through better urban planning, a reformed business environment and strengthened institutional capacity, selected towns in Kenya will be able to attract private sector financing to build priority climate-resilient infrastructure and value chain projects. The outcomes are expected to increase investment in selected value chains, create employment and demonstrate a replicable model for rapidly urbanising towns to plan for, deliver and sustain climate-resilient economic growth. The impact of the programme aims to achieve more balanced economic growth, reduce rural-urban poverty and create climate resilient livelihoods for future generations.

A series of assumptions underpin the effective delivery of results, and the M&E team will review progress against the log frame indicators on a bi-annual basis to assess the strength of the transmission channels within the ToC, highlight any weaknesses and address key evidence gaps identified. This process will proactively respond to evidence gaps and foster a culture of adaptive programming through use of feedback loops.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead

Following the mobilisation phase, procurement of the Private Sector Consortium contract was signed in August 2018, with a 12 month inception phase starting in September 2018. Delays in contracting the Private Sector Consortium have had implications on overall programme delivery which is off-track. To get programme performance back on track the DFID Kenya team will need to exercise careful and diligent management to ensure work plans are followed and take corrective actions promptly as required. As this is a large, high-risk, programme, the DFID Kenya Head of Office will be provided with quarterly progress updates throughout the coming year.

It is too early in programme implementation to assess the performance in relation to expected outcomes and impact. Once procured, the M&E firm will set up an overall M&E framework including finalising of the logframe, and adopt a rigorous approach to support learning and adaptation to assess whether the programme is on track to lead to the expected outcomes and impact or not.

Explain major changes to the logframe in the past year

The logframe was revised in May 2018 for the three main reasons:
Revision 1: As the performance of the programme was off-track in the last annual review, some milestones for 2017 were not met. The logframe changes moved and added these milestones to 2018 (this reporting period), without changes to the content. The milestones are:
  1. Output 1, indicator 1.1 - Both managing agent consortium and independent M&E firm procured by DFID
  2. Output 1, indicator 1.2 – Advance review of a range of County Integrated Development Plans and key stakeholder plans
  3. Output 3, indicator 3.1 - Strategic partnership in place between DFID and the World Bank to undertake complementary business environment reforms
Revision 2: The 2017 logframe milestones were largely ‘to be defined during the inception phase’ with the Private Sector Consortium and M&E firm. Due to the procurement delays, two new process indicators listed below were added, for this review period.
  1. To measure IFC’s preparatory work and stakeholder engagement in county selection, designing interventions for reforms, capacity building and developing bankable PPP projects, one new indicator was added Output 2 ‘Indicator 2.1- Strengthened technical capacity of counties to originate, screen and prioritise PPPs’. Consequently, a new 2018 milestone was also introduced – ‘ToR for PPP consultancy (capacity-building) firm finalised.’
  2. To reflect the work that will be undertaken with national government over the life of the programme, in addition to the existing indicator that measures sub-national work, one new indicator was added to Output 3 ‘Indicator 3.3. - No. of targeted investment promotion strategies supported in conjunction with National government and private sector stakeholders ‘.Consequently, a new 2018 milestone was also introduced - ‘Project stakeholders mapped and engaged on reform activities, in particular close working collaboration with the Ministry of Transport, Infrastructure, Housing and Urban Development and with the World Bank’s urban programme.’
Revision 3: Outputs 2 and 3 were largely the same, which was likely to present measurement and reporting challenges in future reviews (though not an issue for this review). To minimise repetition and confusion going forward, the two outputs were consolidated into one and the logframe weightings adjusted accordingly.

Details of the changes are shown in Annex A.

The impact weighting for each output was adjusted to reflect the level of input required to achieve the milestones that could be measured during this reporting period. As Output 4 was not being marked in this annual review, the impact weighting for Output 4 (15%) was equally distributed between Outputs 1 – 3 (5% added to each of the outputs).

Describe any planned changes to the logframe as a result of this review

A key deliverable of the M&E firm is to set up an overall M&E framework for the programme, including finalising of the logframe. The M&E firm will lead the revisions of the logframe to take into account the recommendations of this annual review, the proposed no cost extension and agreed workplans of all the implementing partners. Given the political and contextual changes in Kenya since the programme was designed, the DFID Kenya team, with implementing partners, will test the validity of the ToC in relation to the logframe expected outcomes and impact and make improvements as required.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

The protracted mobilisation phase has implications on the programmes VfM proposition. SUED was designed as a five year programme and potential suppliers submitted – and DFID accepted – commercial and technical proposals on this basis. However, due to procurement delays, only four years now remains and so to ensure good VfM and in order to align programme and contract end-dates, the DFID Kenya team would need to apply for a one year no-cost extension to the programme.

Key cost drivers

During the reporting period, the key cost driver was personnel fees for advisory services by the IFC, which cost £400,000 out of the £645,000 spent by July 2018, that is, about 63% of spend during the reporting period. DFID ensures VfM on advisory services by the IFC through agreeing, at an institutional level, rules and standards around operating IFC Trust Funds.

For both the Private Sector Consortium and M&E firm contracts, VfM has been ensured through output-based payment structures with capped daily fee rates and, for the M&E firm, benefiting from discounted day rates through using DFID’s Global Evaluation framework Agreement. Both suppliers will deliver detailed VfM frameworks grounded in each of ‘Economy, Efficiency, Effectiveness and Equity’. This will include: detailed mechanisms for ensuring VFM; actions required to deliver VfM; and proposed VfM indicators (such as those set out in the table below).

Level	Proposed VFM indicators
Economy	Different implementing partners in SUED will be monitored in terms of cost and quality information to ensure VfM in procurement of goods and services and operating expenses
Efficiency	Cost of technical assistance per programme town intervention / Management costs for each delivery mechanism/fund as a proportion of invested funds will be included.
Effectiveness	Unit costs of delivering different types of infrastructure; / Evidence to demonstrate whether DFID and other leveraged funds are altering investment behaviour amongst private financial institutions who are partners under SUED – measured by replication of SUED activities beyond the targeted counties / The proposed ratio of costs spent on developing vs. implementing the law/regulation/policy/strategy / Time savings (e.g. weeks, days, hours) due to improvements in service delivery / Reduction in number of days for PPP project to go through the full project cycle
Equity	Ratio of marginal benefits disaggregated by poverty threshold, gender and rural/urban location

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

It is too early to assess VfM for the programme. There is a clear need for emerging towns in Kenya to put in place sustainable urban economic plans; improve their investment climate and draw in investment for priority climate-resilient infrastructure and value chain projects. Given the slow mobilisation phase of SUED on top of a range of other political/contextual risks, there are major risks for the programme not achieving high VfM and this will need to be carefully monitored in the coming year.

There are compelling reasons to continue SUED, based on high external and internal demand for the programme. Through IFC, SUED’s work with countries on affordable housing is formally supported by GoK National Treasury and State Department of Housing and Urban Planning and is directly contributing to the GoK ‘Big Four’ priorities to develop 500,000 affordable houses by 2022. Other donors have also expressed interest to potentially invest in similar SUED projects going forward, which shows strong external confidence in the sectors identified by IFC and SUED’s early ability to leverage even further investment and achieve greater impact.

Internally, SUED is an important programme for UK priorities in Kenya and in our national interest. SUED’s cross-cutting portfolio working at both national and sub-national levels is central to delivery of DFID Kenya’s Sub-National strategy, HMG Prosperity Strategy and the Africa Strategy.

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

The programme’s risk remains ‘major’, as per the approved business case and a fraud risk assessment completed in July 2018. The overall risk rating is linked to potential changes in the political economy during the life of the programme, as well as risks of fraud, bribery and corruption on high-value infrastructure and value-chain investments. DFID has embedded rigorous political economy analysis into the private sector consortium’s key performance indicators, and will work closely with them to forecast where political shifts may threaten the delivery of sustainable results.

Key programme risks and mitigation measures in place are highlighted in the table below:

Risk	Mitigating measures in place
Lack of complementarity within the programme on the counties/towns to be supported	DFID will ensure close collaboration between IFC and the Private Sector Consortium on a county selection criteria and support to offered to selected counties by each implementation partner
Lack of complementarity with other sector stakeholders on support to counties	The context has significantly changed since SUED’s original design, with new initiatives underway e.g. World Bank Urban credit to GoK. The programme should conduct a thorough stakeholder mapping which is one of the Private Sector Consortium’s KPI’s for the first quarter.
Reputational risk linked to perceived lack of transparency in the selection of towns to be supported	DFID and the Private Sector Consortium should agree on a final town selection criteria is transparent, objective, inclusive and meets the objectives of the programme
Potential for corruption and poor governance of high-value infrastructure and value chain projects	The programme team will work closely with DFID Kenya’s governance programme, as well as other infrastructure and value-chain programmes to learn lessons and incorporate them into the programme’s implementation.
Lack of interest from the private sector to invest in infrastructure and value chains at the county level	DFID will ensure that firms with the appropriate expertise are procured by the Private Sector Consortium to develop bankable projects that attract private sector interest. SUED will also learn lessons from similar DFID programmes in other countries.
Delays in securing further HMT approval and/or no-cost programme extension (referred to in section D above)	DFID should start the process of seeking HMT approval and a no-cost programme extension early to prevent a gap in and/or disruption to implementation.

Update on partnership principles

The partnership principles do not apply in the management and monitoring of SUED. With both contracted suppliers, no funds will pass through government systems.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

During this reporting period, there has been progress in procuring a Private Sector Consortium. An OJEU two-stage procurement process was chosen as the preferred route to the market. At stage one, potential suppliers were invited to express interest in submitting a tender. All potential tenderers were issued with a Standard Selection Questionnaire that established their initial suitability. At stage two, shortlisted tenderers who met the selection criteria were then invited to submit detailed technical and commercial proposals. This resulted in the selection of the preferred bidder, and DFID’s Secretary of State approved the contract award for the Private Sector Consortium in May 2018. There have been a few delays in signing the contract, as the draft contract needed re-drafting to comply with the General Data Protection Regulations that were introduced in May 2018. The contract between DFID and the Private Sector Consortium[6] was signed in August 2018.
[6] Details of the managing agent remain commercially sensitive until a contract is signed, and will therefore not be disclosed in this annual review report

There has also been progress in procuring the M&E firm. A preferred supplier was selected through a mini-competition under the Global Evaluation Framework Agreement (GEFA). This procurement route was chosen as the framework has pre-selected, technically capable suppliers which meet the requirements detailed in the ToR and provide good value for money. The procurement opportunity was notified to suppliers on the GEFA in January 2018, in compliance with Public Procurement Regulations 2015. A preferred bidder was selected following a technical and commercial tender evaluation process. DFID Ministers approved the £2.5 million contract in July 2018 and contracting is due to be completed by October 2018.

An administrative arrangement was signed with the IFC in November 2017. However, in an unprecedented year, Kenya held two elections in August and October 2017. Despite initial delays due to the two Kenya elections and extended period of political uncertainty, since March 2018 progress has been good and is considered on-track.

The programme is forecast to spend £1.5m within the current financial year based on projected milestone based payments to the Managing Agent and M&E firm, and to the IFC. The DFID Kenya team should exercise careful and diligent management to ensure that contracts are signed on time and projected milestones are completed on time. A disbursement of £2.5m has been made to IFC; £1m upon signing of the administrative arrangement in November 2017 to facilitate project start-up and scoping, and £1.5m in June 2018 for implementation. By the end of DFID 2017/18 financial year in March 2018, IFC had spent only £300,000 of the disbursement of £1m; this is mainly because of the aforementioned election-related implementation delays. To date, spend has been slow, at 25% of disbursements. DFID and IFC will work together to ensure accuracy of spend versus forecasts in the next reporting year.

During the inception phase for the Private Sector Consortium, the DFID Kenya team will need to prioritise the following within the next 6 months for effective programme and contract management and compliance with DFID’s requirements as follows:
- Agree on quality and timeliness of progress and financial reporting and audited financial statements with all three implementers; agree with IFC on reporting standards to ensure that upto-date information on programme progress and on finances by the IFC is available to DFID.
- Set up arrangements for proactive dialogue on risks and updating of delivery chain maps;
- Agree on high standards of financial management e.g. accuracy of forecasting; monitoring of assets.
- Ensure that overarching contract KPIs and Terms and Conditions are agreed and enforced as per the newly-introduced contract management plan
- Compliance with the Supply Partner Code, where applicable, drawing on advice from DFID’s procurement and commercial department.
- Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting)
- Completion of the Supplier Review Management scorecard assessment for each supplier, where necessary.
- Prioritise all the actions necessary for full compliance with the smart rules.

Date of last narrative financial report	April 2018
Date of last audited annual statement	N/A – next audited statement due in December 2018

G: MONITORING, EVIDENCE & LEARNING

Monitoring

To date, the programme has been monitored through regular engagement with the IFC to agree workplans and a Theory of Change for each component. While progress reports have been submitted, there is a 3-month time lag in submission due to IFC’s internal reporting processes. DFID is seeking to address this, as much as is feasible, in the next reporting period.

The programme will adopt a rigorous approach to M&E to support learning and adaptation and to determine whether the programme is successful or not. The M&E firm will be required to develop and implement a M&E framework (aligned with International Climate Funds (ICF) reporting standards) which includes establishing baselines, defining definitions, setting up robust data collection systems which augment existing data collection efforts, designing beneficiary/participatory mechanisms and identifying any relevant case studies.
This component will be led by an independent M&E firm. Procurement of the independent M&E firm is ongoing and is considered on-track. DFID Ministers approved the £2.5 million contract in July 2018 and contracting is due to be completed by October 2018.

Evidence

There is some existing, fragmented, secondary evidence available, such as data contained within Kenya County Integrated Development Plans (CIDPs) as well as from the World Bank, UN Habitat and AfDB, though a significant amount of primary data collection will be needed.
1. Evaluation: The M&E firm will use the OECD-DAC evaluation criteria as a guiding framework to assess the relevance, effectiveness, efficiency sustainability and impact of the programme.
2. Learning: The M&E firm will develop knowledge/research products which address the evaluation questions and summarise monitoring findings that are underpinned by rigorous and systematic analytical approaches, and develop and implement a dissemination strategy.

Learning

The M&E firm will be responsible for generating and sharing knowledge on what works and doesn’t work for influencing key stakeholders. However, during the reporting period the DFID Kenya team has focused on enhancing knowledge and understanding of context-specific issues with stakeholders through:
1. DFID centrally managed programmes: Comprehensive mapping of DFID programmes operating in different sectors in Kenya that can contribute to and gain from SUED, and engaging key stakeholders (e.g. (PIDG[7] companies). During the inception phase sessions will include lessons learning from DFID programmes on relevant thematic areas such as urban, developing bankable projects, PPP investment, jobs and working with counties; as well as learning from external partners’ experiences working on urbanisation (e.g. World Bank and UN-Habitat).
  [7] Private Infrastructure Development Group
2. DFID research programmes: Affordable housing is emerging as a priority at both national and sub-national levels, alignment with the ‘GoK Big Four’ priorities. DFID’s East Africa Research Hub (EARH) has undertaken comprehensive mapping of research in Kenya on this thematic area, which the DFID Kenya team are engaged in and will continue to learn from as the programme develops.

Progress on recommendations from previous reviews

Recommendation	Action
The DFID Kenya team should put in place concrete, weekly/monthly, procurement milestones between September 2017 and January 2018 and report to the Head of Office on progress in November 2017 and January 2018.	Achieved – the DFID Kenya team put in place and monitored procurement milestones with regular updates to the Head of Office including identifying when and explaining why certain procurement milestones were not achieved.
By end-October 2017, the DFID Kenya team and PCD counterparts should organize an after action review and share lessons with other programme teams on how best to prepare for, and avoid pitfalls of, the new procurement steps and processes.	Achieved – this was completed in December 2017.
As the SUED Private Sector Consortium won’t be in place until January 2018 but as current CIDPs end in December 2017, the DFID Kenya team should engage priority counties after the August 2017 elections and prior to December 2017 to explore how best to input into development of the next 5-year county development plans.	Partially achieved – DFID Kenya has engaged a few counties (Wajir, Isiolo, Kisumu and Laikipia) to discuss their broad development plans. However, it was deemed necessary to first refine the county selection strategy and agree on priority counties with the main implementing supplier, before any deeper programme-specific engagement.
In the SUED inception and implementation phases, working effectively alongside other new/evolving donor initiatives (such as the World Bank $300m urban planning credit to government and TradeMark East Africa’s Phase 2 support to ‘growth hubs’) should be prioritized and overseen early on through early establishment of the SUED Steering Committee.	Achieved – DFID Kenya has engaged the World Bank’s representative for the $300m Kenya Urban Support Programme. DFID Kenya has developed draft terms of reference for the Steering Committee outlining the composition, roles and responsibilities of members who include key stakeholders in urban development. The draft terms of reference and nomination of Steering Committee members will be finalised by the Private Sector Consortium during the inception phase. / There is also an opportunity for SUED to collaborate on the TMEA trade and logistics clusters (growth hubs) project in areas where both will work both on programming and on knowledge sharing. SUED MA should explore this partnership during the inception phase.
In the SUED inception and implementation phases, DFID Kenya priorities of youth employment and a focus on Northern/ASAL counties in Kenya should be sufficiently integrated into SUED and opportunities to learn from and collaborate with ICED and DFID’s EARH team regularly assessed and pursued as appropriate.	Achieved – In preparation for the first kick-off workshop with the Private Sector Consortium, DFID Kenya has prepared a workshop schedule, which includes a discussion of current DFID priorities, particularly issues of youths and jobs and the focus on Northern/ASAL counties. A focus on jobs has already been included as a logframe milestone.

The annual review process

This annual review was completed by Yolanda Chakava (Infrastructure Adviser, DFID Kenya) and Beverly Migani (Senior Programme Officer, DFID Kenya), with inputs from other members of the Sustainable Economic Development Team. The report has been quality assured by DFID Kenya’s Accountability and Results Team.

Annex A: Table of detailed changes to the logframe

Output	Indicator	Milestone	Original	Revision
Output 1 - Improved capacity of selected secondary towns to plan and deliver market-driven urban economic planning	Indicator 1.1 - No. of high quality strategic economic development plans supported in selected secondary towns	Milestone 1 (2017)	Both managing agent consortium and independent M&E firm procured by DFID.	This was not achieved in 2017, therefore moved to 2018 (output 2, milestone 1) / The milestone for this indicator was set as: Stakeholder engagement plan and country selection strategy finalised.
		Milestone 2 (2018)	3 secondary towns selected for programme support through a competitive bidding process; 3 detailed urban economic development plans developed.	This was deleted as preceding milestones had not been achieved. / To be defined during the inception phase.
	Indicator 1.2 - Effective roll-out of urban economic development plans in selected towns	Milestone 1 (2017)	Advance review of a range of County Integrated Development Plans and key stakeholder plans	This was not achieved in 2017, was therefore moved to 2018.
		Milestone 2 (2018)	None.	Changed to: Mapping of County Integrated Development Plans and key stakeholder plans
Output 2 - Facilitation of public-private financing of climate resilient infrastructure and value chain development projects	Output 2 and 3 were initially exactly the same: / Output 2 - Facilitation of public-private financing of climate resilient infrastructure and / Output 3 - Facilitation of value chain development projects, connecting to economic growth corridors. / This would likely present measurement and reporting challenges later as some projects would qualify as both infrastructure and value-chain development projects. Output 2 and 3 were therefore merged into output 2, and one new indicator added: / Indicator 2.1 - Strengthened technical capacity of counties to originate, screen and prioritise PPPs			Milestone 2 (2018) / ToR for PPP consultancy firm finalised
Output 3 - County level business environment reform interventions are undertaken	Indicator 3.1 - Mechanisms/institutions for hosting public-private dialogue (PPD) identified (Y1); number of regular PPD forums held (Y2-6); good stakeholder feedback on utility and uptake of PPD forums (Y2-6)	Milestone 1 (2017)	Strategic partnership in place between DFID and the World Bank to undertake complementary business environment reforms	Deleted and moved to 2018 as it was not achieved in 2017.
		Milestone 2 (2018)	To be defined at inception phase	Strategic partnership in place between DFID and the World Bank to undertake complementary business environment reforms
	Indicator 3.3. - No. of targeted investment promotion strategies supported in conjunction with National government and private sector stakeholders (New indicator introduced to reflect the work that will be undertaken with national government during the life of the programme, in addition to the existing indicator that measures county-level work)	Milestone 2 (2018)	N/A	Project stakeholders mapped and engaged on reform activities, in particular close working collaboration with the Ministry of Transport, Infrastructure, Housing and Urban Development and with the World Bank’s urban programme

Weightings of output indicators were also amended as below:

	Output	Original weighting	Revised weighting	Final weighting
First, individual output weightings were revised for all outputs in light of the merging of output 2 and 3 / Second, as Output 4 was not being marked in this annual review, the impact weighting for Output 4 was proportionally distributed between Outputs 1 - 3	Output 1	25%	25%	30%
	Output 2	20%	40%	45%
	Output 3	20%	20%	25%
	Output 4	20%	15%	0
	Output 5	15%	N/A	N/A
	Total	100%	100%	100%