Type of Review: Project Completion Review (Multilateral Organisation Core funding)

Title of funding stream: Support to the CGIAR 2008-13

Date started: March 2008	Date review undertaken: June 2012

Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
DFID approved an allocation of up to £130m to the CGIAR over the period 2008-13. In the 2011-12 financial year £45m was provided, completing this phase of UK support. UK support contributed around 8-9%[1] of total CGIAR funding which is funded by over 20 donors. UK support is provided as core financing, channelled through the CGIAR Fund, a multi-donor trust fund administered by the World Bank in Washington. UK funding is not restricted to any specific CGIAR research programme; it is allocated to the CGIAR Fund, a recipient managed trust fund held by the World Bank. Progress is monitored using a single harmonised financial and technical reporting system. DFID holds a seat on the Fund Council, the executive body which controls the release of money by the Fund, and has one of 4 seats allocated to European donor
[1] Overall funding to the CGIAR will rise to $910m in 2012. Changes in the contribution by other donors mean that the UK percentage varies from year to year.

What were the expected results?
The overall goal of DFID’s support to the CGIAR is: / Greater contribution of agriculture and natural resources to food security, inclusive growth, poverty reduction, and environmental sustainability / The purpose is: / Increased relevance and impact of international agriculture and natural resources research. / The expected results, as set out in DFID’s log frame for this intervention are: / Consortium Research Programmes are generating high quality research outputs contributing to at least one of the system level results areas. / Climate change challenges addressed across all CGIAR research with specific CC research targeted by CRPs delivering relevant adaptation strategies and solutions. / Effective mechanisms for CGIAR system-wide support in gender and capacity building. / Governance and structural reforms required to transform the CGIAR into a more effective research for development body are implemented speedily and effectively. / This Annual Review measures performance against these 4 results areas. These are set in the context of the CGIAR Strategy and Results Framework (SRF), which sets out the main deliverables of the system as a whole as four System Level Objectives: / Reducing rural poverty: Improved productivity and better developed markets will deliver agriculture growth / Improved food security: Increasing supplies of key staples will buffer communities against the impacts of price rises and volatility, making food affordable for millions of poor people. / Improved nutrition and health: Improved crop varieties and more diverse farming systems will improve the diet of millions of poor people, particularly women and children / Sustainable management of natural resources: Maintaining healthy ecosystems and high levels of agriculture productivity in the face of climate change.

What was the context in which UK support was provided?
There has been modest progress in reducing the proportion of people in hunger over the past 20 years, down from 16% in 1991 to 13% today. Between 2008 and 2009, the number of hungry increased by 105 million, to 1.02 billion people, due to rises in the price of food and the financial crisis. Although this number fell back as food prices declined, the best estimate by FAO is that in 2010 there were still 925m hungry people, more than in 1990. / The UK Foresight Study - The Future of Food and Farming - predicts that pressures coming from increased demand, climate variability and a growing scarcity of resources will increasingly lead to imbalances in supply and demand, volatility in food prices and possibly to longer term price increases. The poor are most likely to be affected by higher food prices; they already spend 75% of their income on food and are least able to respond to short-term price volatility without making significant changes to the quality and quantity of food they consume 8. A sustained increase in food prices is likely to exacerbate pressures to expand agriculture into forest areas and new land and to over-extract water resources, leading to further loss of forests, biodiversity and ecosystem services with impacts on GHG emissions. / Significant investment will be required just to maintain current productivity levels – to combat new pests and diseases and to ensure resilience of crops to drought or flooding and to reduce the use of increasing scarce resources. In the longer term sustainable global food supply will come from addressing the future threats to existing productivity and sustainable intensification of agriculture; increasing productivity at a rate significantly greater than has been achieved in the past two decades using progressively fewer resources. / The CGIAR has a unique track record of development research which has deliver long-term sustained development impacts. Technology developed by the CGIAR was at the heart of the green revolution, tripling yields in Europe and North America, as well as Asia, and lifting millions out of poverty and hunger. Over 60% of modern plant varieties grown in developing countries have CGIAR ancestry and 30% of yield growth between 1965 and 1998 in developing countries can be attributed to plant genetic improvement by the CGIAR. A meta-analysis of the overall investment in the CGIAR over the past 40 years estimated Benefit: Cost Ratios in the range of 1.9-17.3 depending on impact scenario however the authors concluded that actual BCRs were even higher[2]. For every $1 invested in CGIAR at least an additional $9 worth of additional food is produced in developing countries[3]. In the 1980s and 1990s improved plant varieties developed by the CGIAR were responsible for 50% of the yield increases in global crop agriculture. / Continued and expanded support to the CGIAR is essential if the triple threats outlined above are to be met. The UK has historically been one of the five largest donors to the CGIAR.
[2] Raizer and Kelley, 2008
[3] Raizer, 2003.

## Section A: Detailed Output Scoring

Output 1: Consortium Research Programmes are generating high quality research outputs contributing to at least one of the system level results areas.
Output 1: final score and performance description: / A+: Moderately exceeded expectations / Progress against expected results: / The CGIAR centres have been developing 15 research programmes for the past three years. These are multi-year programmes each involving a consortium of CGIAR centres and external research partners and intended to run for a period of up to 10 years. The development of the CRPs has been supported by ex-ante impact modelling by IFPRI. The 15 CRPs cover a wide range of important themes and topics relevant to developing country agriculture. They encompass agriculture systems focusing on the development of more productive and resilient systems, specifically targeting those systems most important to the poor, drylands, the humid tropics and aquatic systems. Crop commodity programmes intended to develop new crop varieties and commodity based farming systems able to respond to the challenges developing country agriculture will face over the next 20 years. The research portfolio also includes programmes supporting stronger agriculture policies, markets and institutions, a better understanding of value chains, improving the response of developing country agriculture to climate change of agriculture, the links between agriculture, nutrition and health and improved natural resource management. The total investment in the CGIAR research programmes, if each is fully funded for 10 years, will be in excess of $7bn. However funding for each CRP has been approved for three years and future funding will be provisional on the delivery of results.. / Funding for all 15 CRPs has now been approved by the Fund Council (see table 1 below) though in some cases this is provisional on further revisions. In all cases the CRP research proposals were subjected to independent peer review by the ISPC involving ISPC members and external reviewers. Three proposals were rejected by the FC outright and were subsequently redesigned and resubmitted for approval. Nine CRPs were provisionally approved pending revision. These were then redrafted in response the recommendations of the Fund Council and ISPC and resubmitted to the ISPC to ensure they had fully responded to the recommendations. Three CRPs were approved outright. / Current Status of Project Approval / Project Title Lead Centre Status Budget($) / CRP 1.1 Dryland Systems: Integrated Agricultural Production Systems for the Poor and Vulnerable in Dry Areas ICARDA Unconditional approval of inception phase & conditional approval of overall program & budget on 9-Nov-11 122.7 / CRP 1.2 Humidtropics: Integrated Systems for the Humid Tropics IITA CAT II / Approved on / 8-Mar-12 144.4 / CRP 1.3 Harnessing the Development Potential of Aquatic Agricultural Systems for the Poor and Vulnerable WorldFish CAT I / Approved on / 8-Jul-11 59.5 / CRP 2 Policies, Institutions, and Markets to Strengthen Food Security and Incomes for the Rural Poor IFPRI CAT I / Approved on / 19-Dec-2011 265.6 / CRP 3.1 WHEAT – Global Alliance for Improving Food Security and the Livelihoods of the Resource-poor in the Developing World CIMMYT CAT I / Approved on / 14-Oct-11 227.5 / CRP 3.2 MAIZE – Global Alliance for Improving Food Security and the Livelihoods of the Resource-poor in the Developing World CIMMYT CAT I / Approved on / 6-Apr-11 238 / CRP 3.3 GRiSP – A Global Rice Science Partnership IRRI CAT I / Approved on / 1-Nov-10 593.4 / CRP 3.4 Roots, Tubers and Bananas for Food Security and Income CIP CAT I / Approved on / 15-Nov-11 182.8 / CRP 3.5 Grain Legumes: Leveraging Legumes to Combat Poverty, Hunger, Malnutrition and Environmental Degradation ICRISAT CAT II / Approved on / 8-Mar-12 139.1 / CRP 3.6 Dryland Cereals: A Global Alliance for Improving Food Security, Nutrition and Economic Growth for the World’s Most Vulnerable Poor ICRISAT CAT II / Approved on / 8-Mar-12 84.3 / CRP 3.7 More Meat, Milk and Fish by and for the Poor ILRI CAT I / Approved on / 8-Jul-11 99.6 / CRP 4 Agriculture for Improved Nutrition and Health IFPRI CAT I / Approved on / 19-Dec-2011 191.4 / CRP 5 Water, Land and Ecosystems IWMI CAT I / Approved on / 9-Nov-11 246.3 / CRP 6 Forests, Trees and Agroforestry: Livelihoods, Landscapes and Governance CIFOR CAT I / Approved on / 6-Apr-11 232.9 / CRP 7 Climate Change, Agriculture and Food Security (CCAFS) CIAT CAT I / Approved on / 2-Nov-10 392.6 / The CGIAR will now begin the complex task of transitioning from the current mix of funding allocated by numerous donors to specific centres and projects to a system of funds channelled through the CG Fund to the CRPs. The aim of this is to ensure that on-going research is not affected and there is a gradual re-alignment of research with the CRPs. Overall funding available to the CGIAR has risen significantly over the project period from $560m to $800m in 2011 and despite the difficult economic circumstances is expected to reach over $900m in 2012. / In Nov 2011 the Fund Council approved a five-year plan, co-funded by the Global Crop Diversity Trust (GCDT), to provide support and management of CGIAR genebanks. This includes seeking solutions for funding in perpetuity the genebanks through the GCDT endowment. / The Council also approved a harmonized reporting system for 2012 for CGIAR Research Programs (CRPs) and Centres, as well as the CGIAR Policy and Principles on Intellectual Assets (IA) management for a trial period of two years. By adopting its first ever system-wide policy for the management of IA, the CGIAR will enable a wide range of new partnerships with the private sector, ensuring that the outcomes of its research reach those who need them most, particularly smallholder farmers, while safeguarding its assets. / Templates for CRP reporting were approved for adoption on a trial basis during 2012.
Final results: / All CRP budgets have been approved and funding is flowing to eight of the 15 CRP, with funding going to all of the CRPs by the end of 2012. In 2010 the CGIAR produced 2600 per reviewed publications, exceeding the target. It is still too early to assess the outputs of the CRPs since these were approved only in 2011. The first two CRPs to be approved, the Climate Change, Agriculture and Food Security Programme (CCAFS) and the Global Rice Science Partnership (GRiSP) will be evaluated in 2015, in line with the CGIAR evaluation policy. At this stage it will be possible to assess the extent to which research outputs are contributing towards CRP Outcomes. Determining the impact of the CRPs on the system level objectives will take many years to assess. Nevertheless the benefit cost ratios of CGIAR research have been extensively researched and there is an impressive body of evidence linking CGIAR research to agriculture productivity gains, and poverty reduction over the past 20 years. The evidence which links research outputs to other higher level impacts (nutrition, hunger and NR management) is as yet underdeveloped and will be a major focus of on-going reforms. Nevertheless the CGIAR continues to deliver a stream of high quality research products. There have been numerous highlights of CGIAR research over the past 4 years. These include: / The development by the International Rice Research Institute of SCUBA rice, flood tolerant high yield rice able to withstand up to two week submersion. The Sub gene which provides this protection has now been incorporated into Asian rice mega varieties and is being grown by 10m farmers living in flood prone areas. This research won the UK Government Climate Week Award for the best technological innovation in 2011. / Research to incorporate of fodder trees into maize farming systems by the World AgroForestry Centre. The trees shed nitrogen rich leaves in the dry season which have tripled maize yields in Zambia and provide fodder and timber. Growing the right tree in the right farming system can increase incomes and crop yields as well as mitigating climate change and increasing resilience. / The development and testing of biofortified crops rich in micronutrients by the Harvest Plus Programme. Field trials of orange fleshed sweet potato in Uganda and Mozambique have demonstrated the impact this crop can have on the nutrition of women and children. Research is underway to develop 9 new biofortified crops, test their effectiveness and to get these into widespread use in target countries. / The development of drought tolerant maize by the International Wheat and Maize Centre (CIMMYT). In collaboration with the private sector CIMMYT has developed 84 varieties of drought tolerant maize. More than 2 million smallholder farmers in sub-Saharan Africa are growing the new varieties. Between 2007 and 2016, the project aims to reach 30-40 million people in sub-Saharan Africa, adding grain worth an annual average of USD 160-200 million in drought-affected areas. This research won the UK Government Climate Week Award in 2012. / The International Water Research Institute (IWMI) has been awarded the prestigious 2012 Stockholm Water Prize by the Stockholm Institute for their research. / Impact Weighting (%): 35% / Revised since last Annual Review? Y/N No / Risk: Low/Medium/High. Low / Revised since last Annual Review? Y/N No

Output 2: Climate change challenges addressed across all CGIAR research with specific CC research targeted by CRPs delivering relevant adaptation strategies and solutions.
Output 2: final score and performance description: / A+ Moderately exceeded expectations.
Final results: / The Climate Change, Agriculture and Food Security Programme (CCAFS) transitioned successfully from a Challenge Programme to the new CRP structure in 2010. It is a well-managed research programme that is delivering well and is exceeding expectations The full CRP was presented to the Fund Council for approval in November 2010, ahead of schedule. It was approved by the Fund Council and the first tranche of funds was passed to the programme in 2011. / The programme is led by two partners, the International Centre for Tropical Agriculture (CIAT) and the Earth System Sciences Partnership (ESSP). All fifteen CGIAR centres are in partnership with the CCAFS along with 5 Universities, the University of Leeds and Oxford in the UK, the University of Copenhagen and the University of Vermont and Columbia University in the USA. The programme has successfully established a wide range of partnerships within the scientific establishment and with Governments globally. / The programme has produced 4 policy briefs, 6 joint policy briefs, 4 technical reports, 8 scientific papers, 15 working papers since June 2011. This greatly exceeds the target for this period set in the CGIAR log-frame. At this stage of the programme it is difficult to assess the number of centres using the research coming from CCAFS, however the extensive partnerships established by the programme across the CG as whole indicates the effectiveness of the programme in establishing the basis for getting its research outputs into use. Overall CCAFS has made very good progress on its technical research objectives in such a short period of time. / Impact Weighting (%): 15% / Revised since last Annual Review? Y/N No / Risk: Low/Medium/High: Low / Revised since last Annual Review? Y/N No

Output 3: Effective mechanisms for CGIAR system-wide support in gender and capacity building.
Output 3: final score and performance description: / A: Outputs met expectations / Progress against expected results: / The CGIAR has made reasonable progress in establishing mechanisms and processes to ensure gender is effectively addressed through the CRPs. The CGIAR Consortium Office has worked to establish gender strategies within each of the CRPs. Progress reported by the Consortium in March 2011. / i. The CGIAR Gender and Agriculture Research Network has been established - all 15 CRPs participate in a facilitated network to support implementation of gender research; / ii. Mainstreaming of gender issues into CRPs: CRP Lead Centers have appointed lead scientists to coordinate centres’ work on gender for 13 over the existing 15 CRPs; / iii. Preparation of gender strategy for each of the CRPs underway: five drafts of Gender Strategies have been received and three reviewed; / iv. Eleven CRPs are actively communicating with the gender advisor about preparation of the gender strategy and/or network participation; / v. One third of CRPs (5) will produce their gender strategies by June 2012 and in all, two- thirds are expected to be completed by December 2012 / Two specific concerns remain over the commitment by the CRPs to implementing these strategies.1) The lead gender scientists are relatively junior women. They may not have sufficient influence on the CRP management to ensure gender is embedded in the research 2) The budget allocations to support gender research may to not be adequate. / The number of training fellowships awarded to female researchers greatly exceeds the indicator target. The AWARD programme will have supported 230 female researchers both within and outside the CGIAR by mid-2012. / Although there is no specific indicator set for the establishment of mechanisms to support capacity building by the CGIAR, progress to develop a consistent approach has been slow. The Consortium has been overloaded by the pressure to roll out the CRPs quickly and establish a range of cross-system management and coordination mechanisms. The intention to establish a capacity building platform across the centres and CRPs has been shelved until the Consortium can take this work on. This will be a priority for the CGIAR over the next 12 months. Under the circumstances this is a realistic and pragmatic response to a complex and fast evolving situation.
Final results: / Overall the CGIAR has taken a number of concrete actions to strengthen system-wide support to gender research. While these efforts have yet to result in any clear impact, they are nonetheless an impressive response to the challenge of integrating gender into the CRPs. The impact and influence of the gender network and the gender strategies on the research funded by the CGIAR is as yet not clear. It is still early in the process of developing and implementing the 15 CRPs, however all major targets have been met or exceeded during the development and design phase. The AWARD programme has made considerable progress in providing training and mentoring support to women researchers across the CGIAR, has exceeded its targets and attracted significant new funding from other donors. / Impact Weighting (%): 15% / Revised since last Annual Review? Y/N. No / Risk: Low/Medium/High: Medium / Revised since last Annual Review? Y/N. No

Output 4: Governance and structural reforms required to transform the CGIAR into a more effective research for development body are implemented speedily and effectively.
Output 4: final score and performance description: / A+: Moderately exceeded expectations / Progress against expected results: / The reform of the CGIAR governance bodies, management structures and funding mechanisms has been a huge undertaking lasting several years. The primary decision-making body, the Executive Committee (ExCo) has been disbanded and replaced by a Fund Council, with membership representing donors, developing countries, private foundation, farmers groups and the private sector. Agreeing the membership of the FC was a huge task in itself. The CGIAR Secretariat has been replaced by a Fund Office, based in Washington which will manage the CGIAR Fund. Funds will no longer be allocated directly to the 15 CGIAR research centres but will go to the research programmes (the CRPs). A new CGIAR Consortium has been set up which will provide a single management body for the CG research portfolio, which will assess performance of the CRPs, and liaise with the Fund Office over the release of funds. The Consortium Office is led by a CEO and is overseen by an independent Board. Although this process has proceeded relatively smoothly there are concerns over the capacity of the Consortium Office to take on its role. Its function has also been hindered by the dismissal of its first CEO in 2011. Nevertheless it has made impressive progress and has appointed a new CEO. A single set of harmonised management procedures have been developed in a Common Operating Framework developed jointly by the CO and FO. / The annual general meetings of the CGIAR have been terminated and replaced by biennial Global Conferences (GCARD) which will set the agenda for international agriculture research. / Donors have stressed the need for effective and independent peer review processes for CGIAR science. The Independent Science and Partnership Council (the ISPC) has effectively fulfilled this role over the past year. They have conducted independent peer reviews of all 15 CRPs, providing high quality assessment of their scientific quality and development relevance. / These changes represent a significant change in the way that the CGIAR is governed and managed and have not been without their opponents. The fact that they have been successfully implemented in a way which has minimised disruption to the on-going research is a major success for the CGIAR as a whole. / The proportion of overall CGIAR funding being channelled through the CGIAR Fund is a key measure of success and of donor confidence in the new management arrangements. Without a substantial proportion of overall funds being channelled through the fund, then the objective of reform, having a simplified and unified system, would have not been met. In 2011 the proportion of overall CGIAR funds allocated to fund was 55% of overall funding substantially above the target of 40%. The remaining 45% were largely tied up in legacy projects; projects which were initiated before or during reform. As these projects come to an end the percentage of funds passing through the CGIAR Fund will rise. However the policy and management rules will mean that some donors will not use the fund. The majority (67%) of the money received by the CGIAR fund was unrestricted, not allocated to any specific CRP. The remaining 33% was restricted to some extent. / Overall system costs have been limited to 2% of the money passing through the CG Fund. System costs are used to fund the Consortium Office, the Fund Office, the ISPC and the Independent Evaluation Arrangement. This effectively reduces research funding by 2% is a source of friction between the Fund Office the Consortium and the Research Centres The Fund Council has taken a firm line on the 2% ceiling for system cost and this will continue to pressure the budgets. Of the FO, CO, ISPC and IEA. The FO has significantly reduced its budget over the past two years, however the CO in particular has struggled to develop the capacity it needs to fulfil its role within the 2% ceiling., / The M and E policy has been developed and approved. A director for the Independent Evaluation Arrangement has been appointed and is expected to take up their post in July 2012. This is the final element of reform. The decision to base the IEA in FAO has slowed recruitment up, the time taken to do anything within the FAO, particularly during the appointment of the new D-G. led to considerable delays, however this is off-set by the benefits of independence.
Final results: / The CGIAR has substantially completed the reform of its management and governance envisaged in the reforms and has done so in a way that has largely avoided substantial disruption to the on-going research. / Impact Weighting (%):35% / Revised since last Annual Review? Y/N. No / Risk: Low/Medium/High. Low / Revised since last Annual Review? Y/N. No

## If the funding stream involved more than 4 Outputs please copy the box above and paste below.
## Section B: Results and Value for Money.

1. Achievement and Results

Has the logframe been changed since the last review? Y/N: No / 1.3 Final Output score and description: / A+: Moderately exceeded expectations. / Substantial progress has been made by the CGIAR in delivering all four outputs and in three cases exceeding the targets set in the CGIAR LogFrame. There are two specific areas where progress has been slower, the establishment of the IEA, where changes within FAO meant recruitment could not move ahead in a timely manner. The Evaluation policy was agreed on schedule, however the establishment of the entity to actually roll out the policy across the CRPs has been delayed. Secondly the development of a cross-system offer on capacity building. Although this function should be mainstreamed across the CRPs, this has been very slow to develop.
1.4 Overall Outcome score and description: / A+: Moderately exceeded expectations. / Increased relevance and impact of international agriculture and natural resources research.
Over the past three years there has been a transformation in the way that research is identified, commissioned, designed review and managed. These changes, which respond to the recommendations set out in the 2008 independent review of the system, will ensure that the CGIAR will deliver research which is more relevant to developing countries and will have more impact. There are 7 stand-out reforms: / The setting of a global research agenda: The annual CGIAR AGM was a process dominated by research organisation in which the users of research had limited involvement. This has been replaced by a biennial Global Conference for Agriculture Research for Development (GCARD) in which research users will work with the CGIAR, farmers groups, the private sector and civil society, to establish a global roadmap for research, setting out clear deliverables. / The replacement of the ExCO which was dominated by research organisations and donors, with a Fund Council equally representing the global north and south and including donors, southern states, famers groups, the UN, CSOs, foundations and the private sector, The FC acting on the advice of the ISPC, approves the release of funds to the research programmes. / The CGIAR Strategy and Results Framework (SRF) provides the basis linking CGIAR research to four system level objectives; poverty reduction, food and nutrition and sustainable NR management. Although the SRF is being further developed, it provides a basis for future ex-post and ex-ante assessment of the impacts of research. Increasingly it will provide the basis for future research prioritisation. Work on the SRF includes improved foresight capability with a global foresight hub being developed.in Rome. / Improved Management of Research, breaking out of the centre led silos. The CGIAR has established fifteen long-term research programmes designed to address key agriculture systems and commodity constraints which cut across the systems and a whole and draw in a wide range of external research partners. The CRPs are managed by a single CGIAR Consortium based in Montpellier with a single reporting system. Each CRP has a performance management framework setting out milestones and targets against which performance will be managed. The development of robust and effective management of the CRPs will ensure that research is progressively directed toward priority areas of research with the greatest impact of developing countries / Evaluation and Impact Assessment: The oversight of research has been improved with the establishment of the ISPC and IEA, and the expansion of ex-post impact assessment by SPIA. / Funding has been harmonised through the establishment of a single fund. Previously over 60 donors channelled resources to 15 centres through a wide range of mechanisms, all of which had huge transaction costs. Over 70% of CGIAR funds are channelled through a single fund, managed by a Fund Office and linked directly to the SRF. / The mainstreaming of gender across the research programmes, with the development of a gender strategy and the allocation of specific earmarked resources to support inclusion of gender within the research programmes / These reforms collectively represent a major shift in the relations between the research centres and the major donors, linking funding to a global research agenda. Although it is too early to assess the impacts of the reforms to the system, they nevertheless represent a significant shift in management. / In the past 4 years the CGIAR has published over 8000 papers in peer reviewed journals. / In order to strengthen the evidence linking CGIAR research to long term impacts, the Standing Panel for Impact Assessment (SPIA) has commissioned a series analyses and meta-analyses / 1.5 Impact: / Typically the time taken for research to deliver widespread impact is considerable, often decades. The main thrust of this project has been to support the restructuring of research through the reform process and it is too early to assess the impact of these reforms on the achievement of the system level objectives. Assessing the impact of the CGIAR over the duration of this project is therefore based on the long –term impact assessment completed by the Standing Panel for Impact assessment (SPIA) and evidence of new technology developed over the past four years. The accumulated impact of CGIAR research is set out in Byerlee and Renkow (2010) ACIAR (2011) and a number of other meta-evaluations highlight the very large returns to CGIAR investment. The evidence of impact of germplasm improvement of staple crops is strong. For every $1 invested in CGIAR at least an additional $9 worth of additional food is produced in developing countries. In the 1980s and 1990s improved plant varieties developed by the CGIAR were responsible for 50% of the yield increases in developing country crop production. Without these yield gains : / world food production would have been 4-5% lower; / world grain prices would have been 18-21% higher; / the area planted to food crops would have been 11 – 13 million hectares greater at the expense of primary forests, fragile lands and biodiversity; / per capita food consumption in developing countries would have been 5% lower overall and up to 7% lower in the poorest regions; and / 13 – 15 million additional children would have been malnourished, predominantly in South Asia. / The evidence of the impact of CGIAR research on other objectives, particularly hunger and nutrition is less strong. Developing better evidence of the impact of CGIAR research on hunger and nutrition will be a priority for the CRPs and SPIA in the next three years.

2. Spending profile and timescale
2.1 Was the spend profile detailed in the Business Case followed: Y/N. No / Payment was made ahead of the profile set out in the in the Project Memorandum. This was in response to requests from DFID for RED to pick-up additional spending. An assessment of the options for additional spending by RED to high priority programmes identified the CGIAR. The research conducted by the CGIAR was assessed as providing excellent value for money and long-term development impact. The project spending was competed at the end of the 2011-12 FY as opposed to 2012-13. / 2.2 Were any additional payments linked to good performance triggered: Y/N/Not Applicable. Not applicable

3. Evidence and Evaluation
3.1 Assess any changes in evidence / It is important to record all major evidence relating to the multilateral organisation’s performance that has emerged since the Business Case was completed and since the MAR was published. Performance includes both operational (on the ground) performance and organisational (systems) performance. Evidence could include, for example, DFID country level data, publications from other donors, and work conducted by the multilateral organisation itself. / The CGIAR was not included in the MAR. The MAR focused on the large multi-lateral organisations, and the MAR team decided that the CGIAR was not large enough to warrant inclusion. / The performance of the CGIAR was independently reviewed by an international team in 2008, the review analysed system funding, management and performance. The report established the case for the governance and management reforms which were concluded in 2012 and which are set out in detail above. The key recommendations of the review included the establishment of independent peer review and evaluation of research, the need for a single coherent strategy and results framework linking all CGIAR research and the need to consolidate both donor support through a single fund and research centres through a single consortium. All of these recommendations have been implemented. Details of this review can be found at: / http://www.cgiar.org/www-archive/www.cgiar.org/pdf/agm08/agm08_CGIAR-technical-report.pdf. / 3.2 Set out what plans are in place for an evaluation. / There are no immediate plans for a comprehensive evaluation of the system. The changes to the governance and management of the system have yet to translate into substantially improved research performance. However the reforms have included significant changes to the way in which research performance is evaluated with the establishment of an independent office in FAO and an evaluation policy covering all research programmes. The main task of the independent Evaluation Arrangement will be to ensure that high quality evaluations are mainstreamed across the CGIAR research programmes. The results of these evaluations will be apparent in 2015 once the first round is complete.

4. Risk
4.1 Overall Risk Rating: Low/Medium/High - Low / Did the Risk Rating change over the life of the project? No / 4.2 Risk funds not used for purposes intended. Low / Annual financial statements were provided by each of the Centres and Challenge Programmes that benefitted from DFID funding. These statements were checked each year to confirm that our contributions were fully recorded in the relevant year, the organisation was solvent and not carrying excessive surpluses or losses, the audit had been carried out by qualified auditors and whether the audit opinion was qualified or unqualified. There was no evidence to suggest that DFID funds had been used for purposes other than those provided. / In July 2012 evidence was brought to our attention of large scale fraud involving DFID funds in one of the CGIAR centres. This fraud related to investments made by IITA and approved by the IITA Board in 2008 and is currently being investigated in the US by the Federal Authorities. As an immediate response we have requested that no further releases of funds are made to the CGIAR centre. We are planning further action in conjunction with other Fund Council donors. / 4.3 Climate and Environment Impact / If the Business Case identified improvements within the multilateral organisation’s approach to climate change and the environment as a priority, provide details of progress against the identified weaknesses. Otherwise leave this section blank.

5. Value for Money
5.1 Performance on VfM measures / This project commenced in 2008 before the introduction of the Business Case. So, no specific value for money measures have been put in place against which we can review performance through Annual Reviews and this Project Completion Review. However, the Progress Against Expected Results sets out some of the highlights of the CGIAR over the period of this project. / A key objective of the CGIAR Reform Process is to integrate the work of the Centres and their partners thereby avoiding fragmentation and duplication of effort. The first detailed report on the financial performance in 2011 of the CGIAR Centres was produced based on the Centre’s own annual audited financial statements. This shows that the indirect cost ratio indicator, i.e. the ratio of indirect costs to direct costs, is an average of 16%. This is two percentage points lower than in 2010. Overall system costs have been limited to 2% of the funds that pass through the CGIAR Fund. / There are administrative savings to DFID as a result of the Reform Process. We now make our contributions through the CGIAR Multi-Donor Trust Fund. This involves setting up two Grant Agreements each year, as opposed to the 18 MOUs signed each year with the 15 Centres and 3 Challenges Programmes. Similarly, we receive a consolidated financial report that replaces the 18 individual financial reports prepared by each Centre and Challenge Programme. / Under the newly approved funding, we will assess value for money by: / Measuring the overall management and administration costs of the CGIAR and ensuring these are controlled. / Measuring the delivery of the priority research programme outputs against milestones, getting a robust evaluation mechanism in place and conducting a series of ex-post impact assessments. / Simplifying DFID’s administrative and management inputs by contributing funds through the CGIAR fund. / 5.2 Commercial Improvement and Value for Money / Each of the CGIAR Research Programmes has a lead research centre which receives the funds from the Fund Office and manages the overall programme, allocating funds to CGIAR and non-CGIAR research partners. The Centres are autonomous entities with their own governance and management systems, under the oversight of an independent Board of Trustees. They have in place financial management and procurement systems which have been reviewed by numerous donors which contribute earmarked funds to the CGIAR and have been subject to periodical External Performance and Management Reviews by the CGIAR itself. / 5.3 Did the funding represent Value for Money: Y/N Yes. / The CGIAR has continued to produce high quality research outputs, as evidenced in the report, whilst at the same time as developing, agreeing and starting to implement a comprehensive reform process. This reform process is integrating the work of the Centres and is starting to deliver administrative savings.

7. Conclusions
The CGIAR has conducted a comprehensive reform process in response to the recommendations set out in 2008 independent review. Although it is too early to assess the impacts of these reforms on the overall performance of the CGIAR, they nevertheless represent a significant achievement. They have substantially reformed all of the main governance and management structures. The CGIAR track record of conducting long-term high impact research has been maintained over this transition period. The impact of these reforms will form a key element of future support.

8. Review Process
The review was conducted by DFID staff closely involved with the CGIAR reform process. The review drew on a wide range of published material setting out the progress in restructuring and reforming the CGIAR, the development, review and approval of the research programmes and the establishment of the new funding governance and management structures and processes.