Type of Review: Annual Review

Project Title: Support to Civil Society in Tanzania: Foundation for	Civil Society Programme

Date started:	Jan 2011 Date review undertaken: June 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK is providing £8m to support Civil Society Organizations (CSOs) in Tanzania through the Foundation for Civil Society (FCS) to ensure that by March 2015 more citizens (especially the poor and marginalized) are empowered to influence and monitor policies that meet their needs and participate in the budgeting processes for improvement of service delivery in Tanzania. This support is an extension of programme started in 2009. / This intervention seeks to deliver the following outputs: a) Citizens are more aware of their civic rights and responsibilities; b) Ability of CSOs and citizens to participate and influence policies and budgeting processes is strengthened; c) Increased CSOs involvement in promoting rights of women, persons with disabilities and other vulnerable groups e.g. pastoralists; d) Strengthened CSOs organizational capacity and effectiveness; and e) Foundation for Civil Society delivers high quality services and is efficiently and effectively managed and governed. / Total FCS budget over a five year period is about USD 56 million. Donors that support FCS include Swiss, Denmark, Sweden, Canada, and Netherlands. Others are Norway, Comic Relief and American Jewish World Service (AJWS). During 2011, the total FCS spends was USD 10.7 million. UK support accounted for 30% of this spend.

What are the expected results?
Two million men and women enabled by DFID to access quality and user friendly information on services, entitlements and rights / 150 new CSOs have strengthened their organizational and institutional capacity, especially in the areas of: resource mobilization, report writing, strategic planning, financial management and M&E / 200 CSOs trained to demand greater accountability and transparency from governments with 75 CSOs effectively monitoring budgets and decision-making processes at national and district levels / 200 CSOs trained to mainstream gender equality in their organizations and interventions and at least 50% showing evidence of the impact of their work on promoting gender equality. / 100 Disabled People’s Organizations (DPOs) receive grants and capacity building support to better promote rights of their members / Annual CSO Forum bringing together CSO representatives to promote learning, networking and sharing of lessons / Annual CSO Exhibition at the National Assembly (Dodoma) and House of Representatives (Zanzibar) to facilitate consultations between civil society representatives and Members of Parliament – a platform for mutual learning, exchange and advocacy / Strengthened capacity of the Foundation for Civil Society to professionally manage and deliver small grants to civil society organizations and showing evidence of improvements in the area of results monitoring and reporting.

What is the context in which UK support is provided?
The results of the 2010 general elections in Tanzania demonstrate increased political competition. By-elections are hotly contested and there is jostling for position in advance of the 2015 Presidential elections. Some MPs from both ruling party and opposition are increasingly outspoken, making use of watch-dog parliamentary committees and Auditor General report to challenge the Executive. / The power of the media has continued to be strong. Radio remains the main source of information for especially rural Tanzania while the print media has built a reputation for setting an agenda of challenging the Executive. Examples of corrupt practice are regularly headlined in Tanzania, as well as the frustration with services, for example Tanesco. Live broadcast of Parliament sessions provide citizens with access to valuable information about GoT and their MPs performance. / Pressure for revisions to the Constitution has grown, to the extent that a major Review process has been put in place, potentially creating major opportunities for citizens to secure their rights. Citizens have become increasingly vocal and active outside dialogue processes, for example doctors are now in a 2nd strike within six months. The first doctors’ strike received good support from a number of civil society activists. / The increased reach of the Tanzanian state has led to some notable successes, such as increases in Primary School enrolment yet these have not always been accompanied by increases in the quality of service provision. Increasing engagement beyond the state, in accountability processes, will be essential to delivering improvements in the efficiency and efficacy of key services. / Civil society in Tanzania continues to proliferate in terms of numbers of organisations but their effectiveness and efficiency as drivers of change still does not fulfil its potential. Through FCS support, many CSOs are increasing their organizational capacity to mobilize their constituents, advocate for rights and ensure transparency over resources that reaches lower levels of government. FCS Programme is actively playing this catalytic role as it remains the only grant making organization that is able to reach smaller CSOs in rural Tanzania.

## Section A: Detailed Output Scoring

Output 1: More citizens are more aware of their civic rights and responsibilities;
Output 1 score and performance description: / Score A / Indicator / - # and quality of new CSOs supported to promote civic rights (A) / - # of citizens enabled to access information on services, rights (A) / - # of new CSOs supported to increase citizens involvement in local government planning and budgeting exercises (A) Milestone / 15 / 1m / 15 Achieved / 13 / 936,000 / 26
Progress against expected results: / During the year, FCS directly reached a total of 3.123 million beneficiaries with different types of information on their rights, roles and responsibilities. 936,000 citizens are directly attributable to DFID as UK’s support to FCS during 2011 was equivalent to 30% of its total budget. The number of citizens reached through FCS support is directly contributing towards DFIDT’s corporate headline indicator reporting. Directly reached beneficiaries by FCS can further be broken down as follow: / 813,474 people (of them 489,867 women) were reached through grantees that aimed at sensitizing communities to increase awareness on key policies such as: the National Agricultural Policy (2004); National Child Development Policy (1996), the National Disability Policy (2004); the National Environmental Policy (1997); and the Zanzibar Environmental Policy (1992). Others were the National HIV/Aids Policy (2001); the National Land Policy (1995); the Women and Gender Development Policy (2000); and the National Youth Development Policy (1996); / 2,037,152 people (of which 972,066 were women) were reached with projects aimed at building transparency, improving accountability and securing citizens’ rights; / Additional 273,100 people, including 164,825 women were reached through FCS grantees that benefitted from capacity building grants; / Further analysis of activities carried by FCS and directly supports indicators for outputs 1 reveal the following results: / 45 CSOs (13 attributable to DFID) were supported to promote civic rights roles and responsibilities including support that were provided to ensure effective citizen participation in the monitoring of the Igunga By-election in September 2011. Other CSOs in this category were supported to increase citizen’s knowledge and understanding on current Constitution with a view to prepare and increase their engagement on the exercise to participate in the constitution review bill in 2011; / 85 CSOs (26 attributable to DFID)- district CSO networks were provided with skills and implemented activities to mobilize citizen to engage with Local Government Authorities (LGAs); / To supplement grantees activities, FCS through its Communications Departments carried a number of activities to increase citizens’ civic competence and rights. These includes the following: / Airing a total of six television programmes focusing on citizens’ dialogues on ‘the New Constitution and Tanzania We Want’. These programmes were aired on ITV and provided general public, members of the academic community, CSOs and political party representatives with opportunity to participate in these dialogues; / FCS facilitated dialogue between CSOs and Members of the House of Representatives Zanzibar which were aired on Zanzibar Television; / Publishing of the CSO Analysis of Constitutional Review Bill 2011 in local newspapers -reached approximately 300,000 readers; / Facilitating a live video streaming of the Public Hearing on the Constitutional Review Bill 2011 – of which 200 people viewed Public Hearing held in Dodoma via internet; / Through the use of mass media, FCS communication efforts are estimated to have reached over 3 million citizens above those directly reached through grantees. / The following few examples illustrate the type, nature and outcome of supported grantees to increase civic competency of citizens in Tanzania: / Tanga Youth Development Association (TAYODEA) was supported by FCS to empower and enable youths in all seven districts and 161 wards of Tanga Region to participate in planning and monitoring of development activities. TAYODEA has established Youth Parliaments in every ward in Tanga Region to provide a platform and mechanisms through which youth can learn, share experience and strategize to engage with planning and budgeting processes at the local level. Each Youth Parliament at a ward level has 30 members (50% females) and through different outreach and sensitization programmes more than 25,000 youths in Tanga region has been reached. Through TAYODEA youths have gained skills on planning, budgeting and development interventions that are meant to address youth concerns and aspirations. TAYODEA programmes have also contributed in inspiring more youths to actively take up leadership positions in their communities. / FCS supported 17 CSOs under the auspices of Tanzania Civil Society Consortium for Election Observation (TACCEO) to mobilize and deploy 245 local monitors to observe and provide an independent monitoring report of the conduction of the Igunga By-election in September 2011. Through FCS support, local monitors were able to cover 57% of all the polling stations of Igunga constituency and observe all aspects of conduction of elections covering such areas as: civic and voter education; registration of voters; nomination of candidates; campaign and election day administration. TACCEO produced a detailed report outlining major findings and specific recommendations for GoT, Electoral Commission, Media, Political Parties and Registrar of Political Parties. / Through FCS support to the Legal and Human Rights Centre, the Tanzania Human Rights Report for 2010 was produced and launched in June 2011. The report details information on the status of human rights in Tanzania and Zanzibar over the course. It is also an advocacy tool that has been widely used by civil society actors and activists as evidence to engage MPs and decision makers. For instance, during the June 2011 Parliamentary Session two legislators used the information in the report to question the government on steps taken against the police officers who allegedly killed people in mining areas. / CSOs were supported by FCS to organised public dialogues in 28 districts in which 7,046 people (1,894 women) participated. Citizens, their representatives, public officials and development stakeholders held frank discussions on the Constitution, leadership, good governance and accountability. The dialogues enabled citizens to query their local leaders and assert their expectations of their leaders. / Recommendations: / FCS to develop a short strategy paper by September 2012 outlining how it seeks to increase its support to CSOs to engage and mobilize citizens in the unfolding constitutional review process. This paper will inform FCS’s 2013 annual implementation plan. / Impact Weighting 25% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 2: Increased CSOs role in contributing to improved transparency at a local level i.e. how LGAs/GoT allocate and utilize public resources;
Output 2 score and performance description: / Score: A+ / Indicator / - # of new CSOs supported to implement PETS (A) / - # of new CSOs supported to implement SAM (C) Milestone / 9 / 5 Achieved / 10 / 12
Progress against expected results: / Through FCS support, Public Expenditure Tracking Surveys (PETS) – discrete follow the money initiatives - were conducted by 32 CSOs (10 attributable to DFID) in over 50 communities across the country. These surveys are done in a small scale, at a local level and largely seek to mobilize citizen and increase their ability to understand and query use of public resources at e.g. a health facility level. / Examples of results and findings from PETS supported by FCS during 2011 includes: / The Pugu Poverty Alleviation and Development Agency (PPADA) – CSO based in Ilala District DSM, was supported to mobilize and increase citizens’ participation in scrutinizing the use of public resources and delivery of services such as education, health and infrastructure. Over 100 community volunteers were trained on PETS and in turn these were able to indirectly reached over 8,000 community members in 13 streets in Ilala District with information about how public resources are utilized in the 18 dispensaries and other development projects in their areas. Some of the findings from PETS activities by PPADA includes the following: / Out of TSh 209 million allocated to 18 dispensaries in Ilala during 2010/11, only Tsh 152 million was received; / Several incidents of potential fraud/misuse of public funds were observed. E.g. at Mvuti dispensary while Tsh14.42m was collected from cost sharing payments, TSh 6.88m was used to buy medicines while Tsh1.77m went missing. There were also no supporting documents for expenditures of Tsh 12 million collected from cost-sharing funds / Lindi Region Association of NGOs formed and trained Six PETS committees to conduct PETS focusing on the infrastructure sector in the region. A number of questionable expenditures were unearthed. For example in Ruangwa District an irrigation project was allocated a budget of Tsh340 million but on the ground only TSH 5 million had been used. The rest of the funds were unaccounted for and the water channels were never built. Nangulukulu village had a budget for building cattle dip and although the money was spent, the cattle dip was nowhere to be seen. And while Tsh 9 million was allocated for the construction of a road from Ngongo to Tulieni within Lindi Municipal Council, there was no evidence of such a road and the money was transferred from the community’s account without the community’s knowledge. / Testimonies from CSOs participating in these PETS activities indicate that there is good local level evidence of increased transparency over how the public resources are utilized. In the long-term, these are likely to contribute to reduced incidents of corruption and increase responsiveness as officials now realized that ‘they are being watched’. / Through FCS, 12 CSOs received support to carry out Social Accountability Monitoring (SAM) interventions in 12 different districts in Tanzania. SAM is a step by step process that enables citizens to monitor Local Government and service providers in five key areas of a) resource allocation; b) public fund expenditure; c) performance management, d) integrity and e) oversight function. / Examples of results and findings from SAM interventions supported by FCS during 2011 includes: / Tandale Market Grain Association and Investment (TAMAGRASAI) achieved a better sanitation at the market as well as access to budgetary information for their ward. Ilala Municipal Council finally constructed a public toilet that had been delayed and handed it to Ferry traders after a SAM training championed by TAMAGRASAI. TAMAGRASAI monitoring has caused the municipality to start building an area for fruit traders at Tandale market; / After a SAM training in Monduli by a Network of Farmers Groups in Tanzania (Mtandao wa Vikundi Vya Wakulima Tanzania); farmers are now participating in the district input voucher committee and in the ward development committee. In addition, the District Agricultural and Livestock Development Office started providing information on agricultural programmes meant to benefit the farmers. / Recommendations: / FCS needs to strengthen its monitoring and information capture system and find better ways to aggregate results under different outputs and themes e.g. PETS, SAM etc to clearly articulate overall achievements and results. Current information provided is only limited to grantee level achievement; / Impact Weighting 20% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 3: increased CSO involvement on empowering women, addressing gender inequities and issues affecting other vulnerable groups;
Output 3 score and performance description: / Score: A+ / Indicator / - # and quality of new CSOs supported to sensitize women on their rights (C) / - % of women enabled to take up leadership positions in CSO/communities (C) / - # and quality of CSOs supported to address issues affecting people with disability, pastoralists and other minority groups (A) Milestone / 36 / 35% / 20 Achieved / 38 / 36% / 25
Progress against expected results: / A total of 38 CSOs were supported to sensitize and provide women with information on their rights to own family assets and resources especially land resources. Through FCS support, community groups were sensitised on the following policies and law that has a bearing on women rights and access to resources: the National Land Policy (1995); the Women and Gender Development Policy (2000); Islamic laws of Inheritance, the Law of Sexual Offenses, and the Marriage Act of 1971. / Examples of progress from supported FCS grantees include the following: / GBV: During the 2011, FCS supported AFNET - a CSO based in Dodoma to empower communities in Iringa and Dodoma to change attitude towards GBV including addressing issues related to female genital mutilation. The project focused in mobilizing community members to increase their awareness on GBV and willingness to report such cases to the authorities. Some of the reported achievements by AFNET during 2011 includes: 50 community based facilitators on GBV were identified, trained and involved in carrying out sensitization activities to different groups in the communities ; 92,744 people in Iringa and Dodoma were reached of which 74,128 were reached through GBV focused interventions while 18,616 were reached through FGM focused interventions; 18,000 copies of print materials (including newsletters, leaflets and posters) were printed and disseminated; over 100 community leaders - ward executive officers, village executive officers, police officers and magistrates were trained on GBV and FGM issues; 33 journalists were trained and empowered on GBV and FGM issues. Training of journalists has led into increase in reporting of FGM and GBV issues The project has also been able to put in place a data bank on media reporting on GBV and FGM issues as well as ensuring that the victims of GBV/FGM who need legal aid are linked to the legal aid organizations. Leaders from faith-based organizations were also sensitized. As a result of this project, six GBV cases were reported to the police and primary courts and hearing is in progress; two cases were resolved by ward tribunals; one case was resolved by the ward executive officer and one case was resolved by the district education officer. / Land Rights: / After taking its Land rights message to 9,250 women out of a population of 260,525 (in-direct beneficiaries) in Mvomero district, the Morogoro Paralegal Centre saw 680 women get their own title deeds by October 2011. MPC has trained 100 paralegals who provided legal aid to at least 1,000 disadvantaged citizens in a year; / Action for Justice in Society (AJISO) printed and disseminated 5,000 booklets on land and gender policies, 500 booklets on inheritance and will writing and 200 paralegal manuals. The organisation also aired six radio programmes through Moshi FM educating the community on different issues pertaining to children and women’s rights. Through the use of Mosh FM, AJISO has been able to reach over 35,000 people while through a network of over 100 paralegals another 30,000 citizens mostly women in all the 60 villages of the Rombo District have been reached; / Through Haki Ardhi (Land Rights CSOs), 3,345 people (of them, 1,225 women) in Korogwe and Kilindi districts were sensitised on land rights and governance; / Women Wake Up Organization (WOWAP) trained women in Dodoma on their legal and human rights to own family assets including land. Increased awareness on these rights contributed to an increase in the number of women who are went on to apply for land certificates. In Chamwino district, 1,500 women applied for village land certificates; / After an awareness campaign by Songea Women Movement on Development in Ruvuma region that reached 12,300 people (4,210 women and 8,090 men) members of village land councils were educated on their roles and responsibilities and started to reclaim all areas that were sold to community members without following proper procedures. Some women in Liweta village, for instance, were able to acquire land and many community members have started processing title deeds; / Women and Leadership: through FCS support a new approach was initiated/promoted to ensure that more women are enabled to take leadership position in community groups and organizations supported by FCS. As of Dec 2011, 36% (23% in 2009) of leadership positions in supported CSOs were held by women;. / Persons with Disability (PWD): During 2011, FCS provided support to over 27 CSOs (8 attributable to DFID) that implemented interventions to address issues affecting persons with disability. These ranged from supporting the deaf to increase their engagement in community affairs through provision of sign language to advocacy campaign that for example led to enabling 25 persons with disability get sponsorship to attend vocation training in Dodoma and Iringa. Examples of good success in this sub-area includes the following: / In Uyui district, as a result of a campaign by FCS grantee Chama cha Walemavu Tanzania promoting the rights of PWDs and the National Disability Policy, the Uyui district council established a committee charged with ensuring that the rights of the PWDs were protected and that PWDs participated in development meetings at ward and village level; / Zanzibar Association of the Disabled was able to reach over 5,075 people altogether in Zanzibar and achieved the following successes: a) Provided information to at least 120 PWDs through awareness trainings on Community-Based Rehabilitation (CBR), the UN Convention on Rights of People with Disabilities and the Zanzibar Disability Act; b) Supported training on community based rehabilitation and early detection of disabilities for CBR volunteers, health workers, traditional birth attendants and traditional healers and Madrassa teachers; c) Supported 8 outreach programmes to initiate community-based rehabilitation for 240 children with disabilities; and d) Provided socialisation and recreation for 360 children with disabilities through the formation of eight playgrounds; / Tanzania National Institute of the Blind’s (TNIB) - conducted searches to identify people with disabilities who were being hidden from the public by their families. Families were counselled and encouraged to send affected children to school. In Ifakara, for instance, the community mobilisers came across a family with four blind people; two were young children of school-going age but were not in school. The family had no idea there were schools for the blind and were advised where to enrol the two children. They are now attending a special school in Kilosa; / Six information centres were established by the TNIB in Tabora Municipal, Uyui, Nzega, Igunga, Urambo, and Sikonge Districts, to continuously provide information on the rights and interests of people with visual impairment in Tabora. As of June 2011, there were 2,909 (1,250 men and 1,659 women) accessing information from these centres. The centres are supplied with relevant information including policies, government strategies and constitutions, most of these printed in Braille. / Most Vulnerable Children (MVCs): FCS supported 19 CSOs (6 attributable to DFID) that implemented activities to address issues affecting MVCs in Tanzania to support re-integrate vulnerable children and increase awareness on the rights of the child. Examples of initiatives supported during 2011 includes the following: / In Kimnyaki and Muriet wards in Arumeru district, 12 committees were established to champion the rights of children living in most vulnerable environment. These committees consist of 379 people out of whom, 255 are women. As a result of the project, 195 orphans received school uniforms and books from community members, six children who had failed to join formal secondary school were enrolled for vocational education. / Enabled 327 children, including 35 girls, to access transitional housing, health services and psychosocial support as well as basic or complimentary education. FCS support also facilitated the reunification of these children with their families. This project was implemented through Mkombozi Centre for Street Children in Kilimanjaro. / After the activities of FCS grantee, the Kigoma Development Centre (KIWODE), children’s social welfare funds were established in 20 wards of Kigoma rural district with the close supervision of KIWODE. The purpose of the funds is to promote and protect children rights. / The Women Children Legal Aid Trust conducted training on the rights of the child and reached 110 people from 9 wards in Makambako district. They sensitised communities on child labour, the rights of MVCs and promoting children’s access to health and education services. / Training was conducted by CHAVITA in Iringa region on the rights of deaf children. Participants included government leaders, parents and guardians of deaf children in the districts of Iringa Urban, Kilolo, Mufindi and Iringa Rural. As a result of the training, 50 deaf children were enrolled in school, and deaf people aged 18 to 45 of aged have been mobilised to join adult-education programmes. / The African Peace Ambassadors implemented a project on forging community based efforts to curb child labour in the orange fields, business centres and truck loading areas in four wards of Mkuzi, Kilulu, Mtindiro and Majengo in Muheza district, Tanga. As a result of these efforts, child labour intervention committees consisting of a total of 49 members (31 women) were formed in five wards to protect children in those wards against child labour. As a result three children were rescued from orange plantations in Mtindiro and Mkuzi and were taken back to school / In addition, a total of 36 CSOs (11 attributable to DFID) were supported to implement activities focusing on addressing issues affecting people living with HIV/AIDS and elderly. / Recommendations: / Since FCS has a target that seeks to enable 250,000 women to effectively take up leadership position in the communities (CBOs, CSOs and LGAs) by 2014, FCS needs to start capturing information on the status of this target. Currently, information is provided as % and is not possible to assess the actual number of women enabled. / FCS needs to strengthen its monitoring and information capture system and find better ways aggregate results under different themes e.g. MCV, GBV etc to clearly articulate overall achievements and results. Current information provided is only limited to grantee level achievement; / . / Impact Weighting 20% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 4: Strengthened CSOs organizational capacity and policy engagement effectiveness;
Output 3 score and performance description: / Score: B / Indicator / - Number and quality of new CSOs supported on institutional and organizational capacity (A) / - % increase of policy dialogues with active participation of CSOs (C) - Proportion of FCS supported CSOs with improved overall impact capability(C) Milestone / 90 / 60% / 60% Achieved / 171 / 30% / 61%
NB: While milestones have been overachieved, a B score is given as limited evidence is available to indicate how FCS grantees were able to effectively engage in policy dialogues. / Progress against expected results: / Capacity Development Services: Through a systematic approach towards strengthening the capacity of supported grantees, a total of representatives from 571 CSOs (171 attributable to DFID) were involved in various institutional and capacity building interventions to address identified organizational capacity gaps as follows: / Manage Your Grant trainings: a compulsory training for each CSO receiving grants from FCS. A total of 776 participants representing 388 CSOs were trained; / Tailor made trainings: a total of 22 sessions of tailor made trainings session were conducted for 672 representatives from 571 CSOs. Topics covered in these sessions included: project design and management, M & E, financial management, strategic planning, documentation, participatory planning approaches, and fundraising techniques; / And in order to foster dynamic and vibrant CSO networks, during 2011 FCS trained 120 representatives from 69 CSO networks on the following modules: organizational management, financial management, governance and leadership, project management, strategic planning, proposal writing, monitoring and evaluation, lobbying, advocacy and fundraising. / Dialogues with MPs: In efforts to build a stronger, more focused sector, FCS nurtured effective partnerships by organising platforms for dialogues between government officials, Members of House of Representatives Zanzibar and CSO representative on local government reforms. FCS organised a CSO exhibition during the House of Representatives sessions in Zanzibar in order to enhance the legislators’ understanding of the work of civil society. Through the Foundation’s support, CSOs developed a draft position paper on the local government structure in Zanzibar. The paper was presented to senior officials of the Ministries responsible for developing Local government policy for Zanzibar. / Capacity Strengthening Grants: FCS supported 197 CSOs with capacity strengthening grants to contribute to its mission over the need for a strong civil society that will contribute to its overall goal of citizens becoming a strong force for change in improving the democratic governance of Tanzania, fighting poverty and in achieving a better quality of life. Though this grant, CSOs were supported to improve internal organisation systems/structures; improving planning and financial management; and improvement of organizational governance and accountability; as well as increasing the usage of ICT. / CSO Organizational Capacity Improvements: During 2011, FCS administered the organisational self-capacity assessment (OCSAT) to 29 out of planned 31 organizations which capacity was assessed in 2007. The aim was to see how assessed CSOs used feedback on finding from Organizational Capacity Assessment (OCA) to improve performance of their organizations. The assessment shows that there has been improvement in all capacity variables including overall capacity growth from 2.9 in 2007 to 3.7 in 2011 for the assessed CSOs. / FCS also carried out a detailed organizational capacity assessment for 101 organizations. Findings from this assessment reveals that: a) 60% of the assessed CSOs shows relatively functioning governance process in their organizations; b) 45% of the assessed CSOs show improvements in the area of project management and fund raising; and c) there were good improvements in the areas of stakeholder relationship by 80% of assessed CSOs. Average overall assessment on these three areas is 61%. Gaps were however noted in the areas of human resource development (which scored 3.1) and financial management which scored 3.3 / Capacity analysis reveals that majority of grantees assessed got a score of between 3.3 and 3.8 above a cut-off point of 3.0. These scores suggests that there is need for more work to be done by grantees to sustain performance since the analysis shows that assessed grantees are functioning at acceptable level, but there is no guarantee that good performance could be sustained in a long time. / Recommendations: / FCS needs to put much emphasis on strengthening grantees organization sustainability, human resource development and financial management. / FCS also needs to ensure every supported grantee continue to pay greater attention on the issues of governance and oversight, putting mechanisms that ensure funds are properly utilized and grantees are vigorously fighting all forms of fraud and misuse of funds. / Impact Weighting 20% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 5: Foundation for Civil Society is delivering high quality services and is efficiently and effectively managed and governed;
Output 3 score and performance description: / Score: A / Indicator / - % of CSOs supported and implement projects in the rural areas(C) / - number of monitoring visits to grantees (C) / - number of applications received and processed on time (C) Milestone / 50% / 180 / 1,500 Achieved / 59% / 168 / 2,152
Progress against expected results: / FCS has made good progress in ensuring that the organization and services provided are of high quality and are efficiently and effectively managed and governed. Results attained under this output includes the following: / Audited Financial Statement produced by independent auditors and available on time to DPs as stipulated on MoU. FCS got clean opinion and management letter show few and minor queries raised by external auditors. All queries were adequately responded for by FCS management / Two FCS – DPs meetings were organized and implemented as per MoU. Documents were provided on time and proper agenda and minutes clearly indicate implementation of agreed key action points; / Two joint FCS – DPs Monitoring visits were organized and conducted as per MoU. The first visit was conducted in Kilimanjaro and Arusha Regions while the second visit was conducted in Lake Zone (Mwanza and Shinyanga); / Pre-award visits to 680 grants applicants (10 strategic grants, 248 medium grants, 404 rolling small grants and18 rolling development grants). This is 156.32 per cent of the target of 435 grants applicants. Of the applicants visited, 394 were approved for funding. The exercise aimed at ascertaining how genuine the applying organisations were as well as assessing their capacity to implement the submitted projects; / As part of the monitoring of implementation of projects, 168 grantees – or 94 per cent of the target – were visited; / Percentage of CSOs supported by FCS that implemented projects in the rural areas reached 59% against annual milestone of 50%; / By December 2011, a total of 2,152 grants applications were received and process, surpassing the annual target by 43%. / Recommendations: / Impact Weighting 15% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? Yes. To correctly capture milestones to differentiate FCS milestones vs. those attributable to DFID based on % of fund. Few indicators have also been changed especially on output 5. / 1.2 Overall Output Score and Description: A / The programme has performed well across all of the outputs. Key achievements include / During the year, FCS directly reached a total of 3.123 million beneficiaries with different types of information on their rights, roles and responsibilities. As DFID support to FCS during 2011 was equivalent to 30% of its total budget, total number of citizens directly reached through DFID support was 936,000; / Three million additional citizens were indirectly reached through FCS communication/mass media interventions; / By December 2011, a total of 2,152 grants applications were received and process, surpassing the annual target by 43%. 472 new CSOs were screed and approved to receive grants under the following grant types: a) 218 medium grants; b) 244 small grants; c) 8 large grants; and d) 7 registration grant. / As noted in previous sections above, FCS interventions delivered good results in the areas of: civic rights, land rights, GBV, empowering persons with disability and addressing the plight of MVCs in Tanzania. Notable results were also recorded in the areas of promoting transparency over resource utilization and CSO capacity building. / 1.3 Direct feedback from beneficiaries / FCS has good mechanisms to ensure beneficiaries provide direct feedback on the implementation of supported projects. Some of these mechanisms include: / Opinion Forms: During 2011, FCS distributed 246 opinion forms to its grantees to invite their views and feedback on FCS’s interventions and services. Once filled out, these forms are analysed and informs FCS internal planning and strategy; / Joint Monitoring visits: each year FCS organizes two joint monitoring visits providing opportunities to funding partners to meet and interact directly with grantees and beneficiaries; / Annual pre-award visits and regular monitoring visits to grantee through the FCS Monitoring Unit is another mechanism through which grantees and beneficiaries provide their feedback to the services provided by the FCS. In 2011 for example, a total of 168 monitoring visits and 680 pre-award visits were conducted; / Information sessions – during 2011, FCS conducted 25 information sessions throughout the country to insure that CSOs and community beneficiaries are more aware of activities funded and implemented by the FCS. These sessions serves as a good platform for FCS to receive direct feedback from beneficiaries.
Summary of overall progress / Overall progress is covered in section 1.2 above.
1.5 Key challenges / FCS supports very many small CSOs across Tanzania. During 2011, 472new CSOs were supported. This brought the total number of on-going projects by end of December 2011 to 733. Due to the sheer volume of grantees supported and diversity over issues covered under the broad themes of governance and accountability it is quite a challenging task for FCS to find better ways of aggregating results beyond the headcount aspect. Most of the supported grantees have a strong grassroots focus and implements projects at a very small scale.
1.6 Annual Outcome Assessment / The outcome of the programme is “more citizens are more empowered to participate, influence and monitor pro-poor policies and budgeting processes for improvement of services in Tanzania by 2015.” Results generated through this annual review indicate that the programme is delivering results that contribute to the achievement of the outcome. / Examples of the outcomes achieved includes the following: a) during the year, FCS directly reached a total of 3.123 million beneficiaries with different types of information on their rights, roles and responsibilities; b) vulnerable groups notably women, girls, persons with disability and children were positively impacted by the interventions supported. e.g. over 680 women got own land title deeds as a result of FCS grantee interventions in Morogoro. This is a more direct means of empowerment as status and livelihood of these women is more secure. / There is currently no updated information to measure status of the outcome level indicators. Views of the People and Afrobarometer Survey are planned during 2012. Next FCS AR will include updated details on these two indicators.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / 2.2 Key cost drivers: Recurrent/operational costs for the delivery and implementation of the programme on behalf of DFID are the key cost drivers. During 2011, these costs were at 14.6% of the total annual spending. This is consistent with the projection made in the approved business case. / 2.3 Is the project on-track against original timescale: Yes.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / FCS’s Theory of Change remains relevant. Results during 2011 confirms that support being provided to civil society organisations is contributing to increased respect for rights and improvements in the utilization of public resources. This will contribute to improvement in the service delivery. The provision of small grants and capacity building to a diverse range of civil society groups has contributed into increasing quality and quantity of information to citizens about rights, resources and policy. Results during 2011 further indicate that some CSOs have directly engaged elected representatives. There are good examples in this review which indicates how supported CSOs have contributed towards directly monitoring and defending citizens’ rights through legal aid and election observation. This ensures that individual citizens’ rights are respected and creates precedents, ensuring the rights of others are also respected. / Grantees have worked with communities to develop solutions to local problems such as gender based violence. This has been achieved through community meetings and other awareness raising campaigns. By empowering work outside of the state in this way, DFID strengthens Tanzania’s, already active, ‘Big Society’. Related to this, by investing in civil society organisations, DFID ensures Tanzania civil society continues to be strengthened. / 3.2 Where an evaluation is planned what progress has been made? / An external mid-term evaluation was carried out in 2011. A local research organization was awarded a tender to carry out this midterm evaluation by FCS. Report from this evaluation has not been published by FCS as it contained a number of technical shortcomings especially around the methodology employed. / FCS is currently seeking a technical advice on ways to address those shortcomings.

4. Risk
4.1 Output Risk Rating: Low / Assessment of the risk level / Overall, the risks of this project not achieving its outputs should be seen as low. This is largely due to the nature of specific interventions and the current operating environment in Tanzania where at local and national levels – CSOs are allowed to operate without state or political interference. The on-going constitutional review process is another key milestone. CSOs and citizens have sufficient space to mobilize and engage in the constitutional review process.
Risk of funds not being used as intended / FCS implements a small grant scheme where applicants are supposed to provide a detailed activity based budgeting. / To ensure funds are properly utilized, every approved grantee must attend Manage Your Grant (MYG) training course. This training is designed to enhance the capacity of selected CSOs that qualified for FCS grants. The training is focused on the basics of project design and management, financial management and M&E. This is a deliberate process by FCS to orient grantees with basic skills that promote effective grant management and ultimately ensure funds are properly utilized. / To complement the training, each year FCS undertakes auditing of a sample of grantee to ensure compliance and proper utilization of approved grants. During 2011, FCS appointed two external auditors to work with its internal audit unit to audit 184 grantees (20% higher than the annual target of 153 grantees and an increase of 21% from 2010). Auditing focuses on all key aspects including: bank reconciliation, expenditure management, proper coding, supporting documents, record keeping and cash book maintenance. Other areas include: adherence to financial management regulations, procurement procedures and how the accounting system operates including segregation of duties, payment vouchers etc. / Through this system, FCS is able to pick up key auditing queries that each audited grantee will require to act before next disbursement is made. / FCS has anti-corruption policy which states that: The Foundation for Civil operates a Zero Tolerance policy on all forms of corruption, both within the Foundation and its services, and externally with all whom the Foundation may have any association. Any member of the Foundation found guilty, following a full in depth investigation of inappropriate corrupt practice will be severely dealt with under the Foundation’s disciplinary procedures. / Where any member of the public has any cause of concern with regards to any individual associated with the Foundation, he should contact the Executive Director, in full confidence, and inform him of the issue as early as possible, in writing if possible, or any other means available, providing as much evidence to support his/her claim immediately after being alerted or directly approached. The Executive Director will ensure that the matter is investigated confidentially and sensitively within the Foundation’s complaints procedure and guarantees the anonymity of the complainant, so as not to place the complainant in a position of vulnerability. The complainant will not be discriminated in any way as a result of making a genuine complaint. / There is some evidence that demonstrate how FCS is applying its anti-corruption policy: / During 2011, services of one member of staff were terminated after it was confirmed that she submitted forged document to the Foundation. Another member of staff resigned herself after receiving a warning that FCS Management has doubt on her integrity; / During 2011, funding to four (out of 184) audited grantees was permanently suspended after the audit suspected higher possibilities for fraudulent expenditures totalling about £7,000 (or 0.4% of total audited value) in their organizations. These four grantees have been permanently sanctioned and follow up actions are done during the year 2012 to recover the funds. / 4.4 Climate and Environment Risk / FCS intervention is rated as category C: No / Low risk but medium opportunity. Most of expected outputs will also have a positive impact on i) delivery of environmental services ii) management and use of natural resources, and iii) the collection and use of revenues collected. During 2011, FCS supported about 15 CSOs whose interventions had a direct contribution towards enabling more citizens to have access to information about natural resource management, environmental policy and water services.

5. Value for Money
5.1 Performance on VfM measures / VfM measures identified during the BC submission of FCS includes the following: / Economy: During 2011, programme management costs were at 14.6% of the total annual spending. This is consistent with the projection made in the approved business case; / Efficiency & Effectiveness measures: / Cost per CSO capacity supported to promote rights. During 2011, FCS carried out the following types of capacity building interventions: i) Manage Your Grant training to 776 participants from 388 CSOs; ii) 22 tailor made trainings (on M&E, financial management, strategic planning, participatory planning etc to 672 representatives from 571 CSOs supported. All these trainings were done at a cost of £453,451.00. / Further analysis of the unit costs reveals the following conclusions: / S/No Category Number of Sessions Number of Participants Total Cost (£) Average Cost/Session (£) Cost/Participant (£) / Tailor made training 22 672 209,109 9,504 311 / Manage Your Grant Training 20 776 244,342 12,217 315 / Note: Total cost involves: a) Consultancy Fee (average of £4,485 per a five days session), b) Accommodation £14 per person per day for 5 days, c) training materials, and living expenses to participants amounting to £19 per person per night for 6 nights. A training session had an average of 30 and 40 participants for Tailor Made and Manage Your Grant Training respectively. Exchange rate used 1£ = 2418 TSh. / Through these trainings participating CSOs have gained multiple benefits including: a) paying increased focus to ensure funds are well managed and results are clearly communicated to beneficiaries and funders – this is consistent with DFID focus on results and anti-corruption; b) strengthened governance and organizational effectiveness; and c) gaining skills to working collaboratively with communities to develop solutions to local problems such as gender based violence and effective ways to promote transparency and follow public money. These benefits represent good value for money, although further analysis is needed. / DFID will consider a possibility of using FCS programme as a test case to probe further the VfM aspects related to training and capacity building of CSOs. To avoid the danger of only focusing on cost aspects, it was suggested that a detailed analysis of benefits of trainings and capacity building to CSOs be carried out as initial step. / Cost per person with improved access to information: During 2011, through FCS interventions, about 3.123 million beneficiaries were directly reached. Total FCS spend during this period was £6.9 million. This represents a unit cost of £2.20 per every person directly reached. Given the fact that FCS interventions were implemented across all the districts of Mainland Tanzania and Zanzibar, this represents a reasonable cost. NB: This does not include an estimated 3 million other citizens that were reached with/through FCS interventions indirectly. / Deepening VfM approach / In efforts to ensure that FCS pay an increased attention to the Value for Money agenda, DFID has successfully advised FCS of the need to carry out a detailed VfM assessment of its non-grants interventions. During 2011, total spend by FCS on non-grants interventions (trainings, policy dialogues, outreach sessions etc) amounted to 20% of its total spend. According to FCS, these spending levels are consistent with previous years and in line with five year strategic plan and annual implementation plan. / Paying an increasing focus on VfM approach will enable FCS to develop a better understanding (and better articulation) of costs and results (benefits) that are being achieved so that can make more informed, evidence-based choices. This is an important step as it would enable DFID and other DPs currently supporting FCS to have documented evidence on how different aspects of FCS interventions are delivering good value for money. / FCS will engage an independent and reputable auditing firm to carry out a detailed VfM assessment of its key non-grants interventions. They includes: a) trainings to grantees; b) regional and districts policy dialogues; c) annual CSO forum; d) annual CSO Excellency award; e) regional outreach and information sessions; and f) publishing and printing of materials. This analysis will be commissioned by FCS by October 2012. DFID and other DPs will provide comments on the ToR and ensure a quality and reputable audit firm is selected. Findings from this assessment will help validate the benefits (or impact) and value of a number of non-grants interventions carried out by FCS and shade light on ones which are of less value. FCS is keen to own this process and uses its findings to inform its implementation plan and strategy from 2013 going forward. / Recruitment of Results Advisor: as part of strengthening its results and value for money approach, FCS had plans to recruit a Results Advisor by June 1012. FCS followed up with VSO for possibility to get an experienced results advisor from VSO global network. VSO is still working on this proposal and there is expectation that this post will be filled by Dec 2012. / 5.2 Commercial Improvement and Value for Money / The nature of the Foundation’s work means that it does not undertake large procurement exercises. As a grant giving institutions, selection of grantees, disbursement and monitoring of grants are the core business of the Foundation. Based on the 2010 SIDA’s systems-based audit and DFID monitoring, Foundation’s grants making processes and procedures continues to be a) transparent; b) follow pre-determined assessment criteria; c) analyses grantees organizational, financial and management capacity. FCS is taking measures to improve internal cost management e.g. it is considering to relocate from current office premise due to costs consideration. / A procurement assessment of FCS was done by DFID in 2011, (as part of DFID’s extension of support to FCS) and confirmed that FCS has an adequate system for procurement for goods and services The planned vfm assessment of non-grants interventions will help identify ways through which FCS can further strengthen its procurement system. / Role of project partners / Majority of FCS grantees are smaller CBOs. They all contribute to the vfm agenda through ensuring that their project proposals are adequately focused in terms of outputs to be achieved. Detailed budget to activity level is also required. Through FCS capacity building interventions, grantees are regularly trained on financial management, m & e and reporting requirements. All these aspects are meant to promote vfm. FCS has recruited an internal audit function to strengthen internal controls and ensure compliance with all standards. This is a commendable move and key aspect that will increase value on efficient running of the organization. / 5.4 Does the project still represent Value for Money : Y/N / Yes / FCS programme continue to offer a good vfm. Results achieved and input costs (especially management costs) are in line with those outlined in the business case. Providing over 3 million citizens with information on their rights or entitlement, as well as recording cases of incidents where officials at national and or local levels have made specific decisions or taken action as a result of citizen engagement is a notable achievement of the FCS programme. / The outcome of the programme is “more citizens are more empowered to participate, influence and monitor pro-poor policies and budgeting processes for improvement of services in Tanzania by 2015.” Results generated through this annual review indicate that the programme is delivering results that contribute to the achievement of the outcome e.g. through FCS grantee over 680 women in Morogoro got their own land title deeds for a first. This is a more direct means of empowerment as status and livelihood of these women is more secure. These kinds of example confirm that FCS programme is generating benefits that are worth buying. / . / 5.5 If not, what action will you take? / 5.6 VfM lesson learnt / Through this annual review, initial good attempt has been made to capture and compare different unit costs. This has contributed towards clearly mapping out economy aspects of vfm. Challengesd remain in identifying vfm metrics for measuring effectiveness and efficiency for this type of programme. The suggestion to spend more time to map out benefits associated with training and capacity building of CSOs is a first step towards addressing this gap. FCS plan to commission audit firm to carry out vfm analysis of non-grant spending is also a positive movement. Both these exercises will generate important lessons that will keep informing future DFID assessment of vfm of its programmes.

6. Conditionality
6.1 Update on specific conditions / N/A

7. Conclusions and actions
The programme is performing well, meeting the majority of output milestones. The following are main conclusions and actions: / FCS to develop a short strategy paper by September 2012 outlining how it seeks to increase its support to CSOs to engage and mobilize citizens in the unfolding constitutional review process. This paper will inform FCS’s 2013 annual implementation plan; / FCS needs to strengthen its monitoring and information capture system and find better ways to aggregate results under different outputs and themes e.g. PETS, SAM, MCV, GBV etc to clearly articulate overall achievements and results. Current information provided is only limited to grantee level achievement; / Since FCS has a target that seeks to enable 250,000 to effectively take up leadership position in the communities (CBOs, CSOs and LGAs) by 2014, FCS needs to start capturing information on the status of this target. Currently, information is provided as % and is not possible to assess the actual number of women enabled; / FCS needs to put much emphasis on strengthening grantees organization sustainability, human resource development and financial management; / FCS also needs to ensure every supported grantee continue to pay greater attention on the issues of governance and oversight, putting mechanisms that ensure funds are properly utilized and grantees are vigorously fighting all forms of fraud and misuse of funds; / FCS to seek technical advice on ways to address methodological shortcomings from its recent Mid Term Evaluation; / FCS to engage an independent reputable auditing firm to carry out a detailed VfM assessment of its key non-grants interventions. They includes: a) trainings to grantees; b) regional and districts policy dialogues; c) annual CSO forum; d) annual CSO Excellency award; e) regional outreach and information sessions; and f) publishing and printing of materials; / FCS to finalize the recruitment of Results Advisor by Dec 2012 / DFID to consider a possibility of using FCS programme as a test case to probe further the VfM aspects related to training and capacity building of CSOs. To avoid the danger of only focusing on cost aspects, it was suggested that a detailed analysis of benefits of trainings and capacity building to CSOs be carried out as initial step.

8. Review Process
This review was drafted by DFID staff based on FCS Annual Report (2011).