Type of Review: Annual Review

Project Title: Bihar Governance & Administrative Reforms Programme

Date started: September 2008	Date review undertaken: Aug 23-24, 2012

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
DFID is providing £13 million in financial aid to the Government of Bihar to design and implement governance and administrative reforms in two phases of three years each (2008-2014), and £5 million in technical cooperation to procure Technical Assistance to support reforms prioritised by the Government of Bihar.

What are the expected results?
As a result of the programme interventions, the quality of governance will improve in Bihar. This will be reflected in the improved capacity of the government to deliver public services, mobilise more revenue and build institutional capacity. This assessment will be based on independent citizen feedback and other independent sources. / The main programme outputs are: / Improve human resource management by streamlining the recruitment process, training of personnel and their performance appraisal / Enhance the quality of public service delivery by selected departments such as commercial taxes, registration, education, home etc. / Improve service delivery at the frontline level by leveraging information technology and streamlining systems and processes

What is the context in which UK support is provided?
Bihar is one of the poorest states in India, accounting for over 13% of the country’s poor. In 2005, it ranked at the bottom of Indian States for a range of governance indicators including law and order, corruption, legal structure and security of property rights, revenue collection, and investment climate. There are systemic weaknesses such as out-dated administrative functions, poorly managed, demotivated and low skilled workforce with large number of unfilled posts; and weak accountability at all levels. Since 2006, the government of Bihar has demonstrated a real intent to improve governance and there have been significant improvement in law and order, financial management, accountability of public institutions, and delivery of public services. Through this programme, DFID support the Bihar Government to undertake governance reforms for improving its capability to deliver better quality services to all its citizens, particularly the poorest and most excluded. / DFID is providing financial assistance to the Government of Bihar through a dedicated Mission set up for undertaking administrative reforms in the state. This will enable the government to improve its human resource management, develop stronger institutional capacity and enhance quality of public service delivery, particularly at the frontline level. / The technical cooperation funds will be used to contract a technical support team that will provide technical assistance to the Government of Bihar on prioritised reform areas.

## Section A: Detailed Output Scoring

Output 1: Quality of human resource management viz. recruitment, training, performance management is more efficient and effective.
Output 1 score and performance description: A
Progress against expected results: / Indicator: Proportion of vacancies against currently sanctioned strength for Bihar Administrative Service (BAS), Bihar Financial Service (BFS) and Bihar Registration Service (BRS) cadres / Milestone: Less than 40% (Baseline ~ 50%) / For the BAS cadre, GoB lowered the entry level position for BAS officers resulting in 570 surplus filled positions. For BFS & BRS cadres, vacancies have gone up as the sanctioned strength has increased by 20% while recruitment is yet to be undertaken. / Sanctioned Strength Posts Filled Vacancies % vacancy / BAS 851 1370 - Nil / BRS 164 104 60 36% / BFS 524 331 193 36% / 1539 1705 - Nil / Indicator: Training of BAS, BFS and BRS Officers / Milestone: Development of Comprehensive Training Policy / GoB approved a comprehensive training policy, the key features of which are (a) Mandatory training for all about 6 lakh employees of GoB linked to promotion (b) 1.5% of salary expenses to be earmarked as training expense for all departments (c) Training to be linked with Performance Appraisal, Promotions and increments. / In-service training plan for Bihar Secretariat Service (BSS) officers was also approved, which envisages at least 10 weeks of training for 3500 employees during their service period. / Induction Training of 48-52nd Batch of Bihar Administrative Service (BAS) officers (160 Nos) was also completed in this year. / The Bihar Institute of Public Administration and Rural Development (BIPARD) has been restructured based on recommendations from GTAST. The streamlined structure and faculty positions for which non-government professionals can also compete have been approved by the BIPARD Governing Council. Operationalization of training has been facilitated through the development of a Training Manual. / Indicator: Proportion of appraisal reports for BAS officers which are initiated and accepted every year / Milestone: 75% of the officers complete self-appraisal using the new PAR form / Based on actual BAS strength, 57% (779/1370) of the officers have completed self-appraisal using the new PAR form. This is expected to improve significantly when the appraisals are due by April 2013. / Indicator: Establishment of a Centre for Good Governance (CGG) / Milestone: CGG Staffed & Operationalised / As envisaged, GoB has formally established the Centre for Good Governance in Bihar in August 2012. Through the programme, technical assistance was provided for drafting of MoA, byelaws, preparation of Vision/Mission, HR Plan, procurement & operation manual for CGG. CGG will be headed by the outgoing Chief Secretary who has been appointed as the Director-General. It is expected that over the next six months, the institution will be staffed and start functioning. / The programme is also supporting development of an Administrative Reforms Framework (ARF) which will be an overarching framework for enabling single point delivery of all services to citizens. / Recommendations: / There needs to be sustained focus on completion and use of PAR formats so that it can be effectively institutionalised. / The development of the proposed administrative reforms framework needs to be accelerated by the government. / The agenda and role for the Centre for Good Governance requires more clarity, including its engagement with the BPSM. / Impact Weighting (%): 30% / Revised since last Annual Review? Y / Risk: Low / Revised since last Annual Review? Y/N

Output 2: Performance of focal Departments is made more effective, efficient and accountable.
Output 2 score and performance description: A+
Progress against expected results: / Indicator: Improved systems for revenue mobilisation (Commercial Taxes & Registration Departments) / Milestone: No. of dealers registered; 50% of registration records digitised / No. of registered dealers increased to 256043 in FY12 as compared to 180,123 in FY 11. Revenue from commercial taxes has increased by 27% in the last three years and by 6% in the last year. / A range of new initiatives have been taken up in Commercial Taxes. This includes Harmonised System of Nomenclature (HSN) based Commodity Classification, Sample Analysis of VAT Input Tax Credit Claim, VAT Commodity Analysis- comparison of tax rates with other states. / The HSN code based classification can potentially tap an additional Rs.1,000 crore (£120m) of tax revenue, which is currently being evaded. / Digitization of old records (1995-2005) in Registration Department is continuing in all 38 districts and more than 60% of old records numbering 12 million have been digitized. / Indicator: Development of monitoring systems in social sector departments / Milestone: (a) Adult Literacy Monitoring systems in Human Resources Dept. / The programme supported the development of an IT application for managing data for “Mahapariksha” (Examination) to assess literacy levels of the adult population under Saakshar Bharat. As per a recent media report, Bihar ranks first on neo-literates with 53 lakh people from appearing for assessments since 2009, of which 81% were women, and 43 lakh cleared the test. / Technical assistance to the Education department has also enabled development of an MIS for Kasturba Gandhi Balika Vidyalaya (KGBVs) – there are 35000 girls currently enrolled there in 391 KGBVs. GTAST is developing a web based MIS for monitoring the implementation of the scheme in Bihar viz. enrolment, dropout rate, allocation and utilization of funds, physical infrastructure etc. / The programme has also commenced support to agriculture department. A Functional Review in on-going as well as development of an MIS for monitoring Central and State schemes. / Indicator: Institutional strengthening & capacity building of police / Milestone: (a) Training programme on citizen-centric policing designed and commenced (b) Prison Manual revised and approved by GoB / The training programme on citizen-centric policing has been developed and initiated in Nalanda District in August 2012. With the support of the Chandragupta Institute of Management Patna (CIMP), a cadre of 120 master trainers have been developed for roll out of the training programme. Over a 3 year period, the programme will train 50,000 sub-inspectors and constables on citizen-centric and responsive policing. / The Prison Manual has been revised through technical assistance provided under the programme. The revised manual was presented to the Chief Minister in July 2012 and subsequently revised with his suggestions. / The Human Rights Case Management System was completed and operationalized last year. This enables the Home Department to effectively handle all pending human rights cases filed against the state. / The programme also supported the Energy Department by undertaking a Renewable Energy Potential Assessment and developing a Renewable Energy Action Plan for Bihar. The report was quite enthusiastically received by the energy department and based on a study recommendation, the energy department launched a solar pumps scheme in the state. / Recommendations: / There is need to consolidate and intensify engagement with the partner departments, as discussed during the annual review. / In Home / Police, apart from the existing interventions, an action plan for implementation of the Prison Manual needs to be developed and supported. / Home Department should develop key performance indicators to measure improvements in service delivery and should link it to BPSM support. / In Commercial Taxes Department, the programme will support the overhaul of the entire tax return process, which can significantly help generate additional revenue through lower tax evasion. / Impact Weighting (%): 30% / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? Y/N

Output 3: Strengthened district level administration and service delivery.
Output 3 score and performance description: A+
Progress against expected results: / Indicator: Quality of service delivery at district & sub-district level and its effective monitoring / Milestone: Effective implementation of Right to Public Services Act (RtPS) and its monitoring; First round of Citizen Report Card (CRC) completed / The Right to Public Services (RtPS) Act has been successfully rolled out with more than 20 million applications made in the first year of its operation. Of about 1.7 crore applications received till June-end 2012, about 94% have already been disposed. Among the disposed applications, 89% was within the timelines. A breakdown of the applications by services is given below: / Certificates (Income, caste, domicile) – 64% / Registration – 11% / Land related – 11% / Pensions – 7% / Others – 7% / Item Unit Applications received Disposed Applications Disposed Applications / Disposed Pending – Beyond timelines Pending - Within timelines Services delivered Services denied Within timeline After timeline / Total for Bihar (All Services) Number 16,181,682 312,706 630,818 15,315,609 866,073 13,645,971 1,669,638 / % 94% 2% 4% 95% 5% 89% 11% / In 5% cases services were denied. The denial of service was higher for the following services – Pensions (21%), Land mutations (17%), issue of new ration cards (81%), determination of urban land holding (19%). / DfID’s support through GTAST has enabled Bihar to continuously improving implementation of RtPS. Suggestions accepted and implemented by Government of Bihar include SMS alerts, use of Common Service Centres and reduction of stipulated time limits. State governments of Rajasthan and Karnataka sought GoB’s inputs before legislating themselves, and the Government of Nepal showed keen interest in RTPS. / The citizen report card (CRC) exercise in under way. Findings from the Citizen Survey on quality of delivery of public services will be available by October 2012. Some interim findings (part sample 22000 respondents) are given in the table below: / Experience with RtPS – Quality of service delivery Better than before 64% / Same as before 22% / Worse than before 14% / Services Improvement in service over last 3-4 years (% of users) % of users satisfied / (% of users) Among those satisfied / Improved to a great extent Improved to some extent Satisfied completely Satisfied partial / Functioning of Ration Shops 7 65 75 78 22 / Services provided by Anganwadis 7 64 73 76 24 / Government primary & middle schools 10 67 73 78 22 / Government health care facilities 15 69 86 81 19 / NREGS 6 53 62 76 24 / Pension services 13 64 80 81 19 / Issuance of certificates 15 62 80 80 80 / Grievance Redressal 4 29 45 71 29 / A large proportion of respondents say that most services have improved to some extent, while 7%-15% respondents say services have improved to a great extent. However, citizens by and large seem to be quite satisfied with the improved quality of service delivery. / Incidence of corruption as reported by users is very low in case of ration shops (1.5%), Anganwadis (0.4%), government schools (1.3%), government healthcare facilities (2.6%), NREGS (1.7%). It is higher for pension services (28%) and certificates (9%). / Indicator: Redressal of public grievances / Milestone: Citizen information helpline institutionalised; Typology of grievances undertaken / The centralised citizen information helpline ‘Jigyasa’ that was operationalised in August 2010, continues to provide single-point information services to citizens. In two years, the call centre has received more than 65,000 calls. The chart below provides a breakdown of calls received during Aug 10 – Feb 12 (53000 Nos). / Typology determination of grievances was undertaken to evolve a uniform set of facts for investigating each such type of complaint and enable a standardization of the process involved in addressing and disposal of the grievance. This activity has been completed for 6 out of the 12 identified departments. / Indicator: Implementation of Reform Strategy for Collectorate Modernisation / Milestone: Reforms implemented in identified District administrations & Block offices / The programme has helped build significant capacity at district & sub-district levels. BPSM supports each district with an IT manager, an Executive Assistant and Public Grievance Officers. At the block level, each block has been provided with a block IT Assistant for collating information and reporting. / In Nalanda District, through programmatic support, a centralised call centre is now operational that enables citizens to connect to district & block officials across 14 service sectors. / Online service delivery for identified RtPS services was also piloted in Nalanda. This has also enabled delivery of RtPS services through common service centres (CSCs) or Vasudha Kendras. That this has benefitted citizens immensely was evident during the field visit undertaken by the review mission team. / Recommendations: / Undertake an audit to understand the reasons for higher denial in some services as well as review the back-end processes to improve quality of service delivery. It is also necessary to understand why the incidence of appeal to appellate authorities for denial of service is very low. / An Information Dashboard is being developed to enable decision-makers to review the findings from the study and take suitable measures. Support and high level ownership in GoB will be required to institutionalise the dashboard at departmental and district level. / GoB needs to strengthen reforms at district and block levels. A pilot should be undertaken in a selected district to analyse institutional constraints in delivering RTPS and other services leading to implementation of a comprehensive reform action plan for the district/block administration. / Impact Weighting (%): 40% / Revised since last Annual Review? Y / Risk: Medium / Revised since last Annual Review? Y/N

## Section B: Results and Value for Money.

1. Progress and results

1.1 Has the logframe been updated since last review? No / No logframe changes were made for goal, purpose and output indicators during 2011-12. / 1.2 Overall Output Score and Description: A+ / Outputs moderately exceeded expectation. Out of three outputs, two outputs score A+ and one output scores A. / 1.3 Direct feedback from beneficiaries / A large scale citizen survey was undertaken to assess citizen feedback on quality of service delivery for a range of services. This survey is under way and it will cover 32,000 households across all 534 blocks in rural Bihar. Interim findings suggest significant improvement in quality of service delivery. / Direct feedback from citizens was also obtained during the annual review field visit. Separately, feedback was also obtained from beneficiaries by the technical assistance team which undertook a study to assess implementation of RtPS.
1.4 Summary of overall progress / The programme has successfully completed four years and has achieved significant results. It has been able to deliver effectively on all the three outputs. / On the first output that pertains to civil service reforms, the programme has enabled restructuring of the core state cadres, streamlined the recruitment process, revamping of the performance appraisal system and overhaul of the training policy and delivery. / Under the second output, the initial limited support to partner departments has strengthened considerably. In the process, more departments have benefitted from the programme. This includes departments of Registration, Transport, Commercial Taxes, Home / Police, Education and Energy. / District & block level reforms were more difficult to initiate. However, since last year, with the enactment of the Right to Public Services Act, the opportunity to engage at the frontline level has increased significantly, with positive results. The citizen report card delivered at scale promises to be another important instrument for reforms. / At the institutional level, the programme has enabled the Bihar Prashasnik Sudhar Mission (BPSM) to emerge as the nodal agency for governance reforms in Bihar. Other institutions which have been strengthened include Bihar Public Service Commission (BPSC), Bihar Institute of Public Administration & Rural Development (BIPARD). The establishment of a Centre for Good Governance (CGG) provides further opportunity for institutional development. / The programme has also supported policy development in critical areas. This includes the Right to Public Services, Rationalisation of Transport-related Taxes, Revised training policy and performance appraisal system, Renewable Energy Action Plan.
1.5 Key challenges / The first and foremost challenge is the need to build ownership within GoB to evolve and implement an action plan for reforms at the district and block level. This will also be a key issue when the findings from the citizen report card need dissemination. / Managing the widening departmental portfolio will also be a key challenge, given that an additional growth component will also bring into the programme fold three more departments – Agriculture, Industries & Tourism. / The third key challenge pertains to the regular transfers of key officials in partner departments, which often results in changing priorities. Stronger and direct engagement with partner departments/officials will be necessary to maintain consistency in reform priorities as well as to create demand for wider reforms. / Strengthening the capacity of the nodal agency, BPSM, to manage the wide portfolio of interventions is also a challenge. The programme is currently providing financial accounting and auditing expertise to BPSM.
1.6 Annual Outcome Assessment / BGARP is well on track to achieving its goal and purpose. As per the State of States Report (November 2011), Bihar shows marked improvements in governance but is hampered by economic factors. / It performs well on both purpose indicators: / (a) There has been a significant improvement in service delivery. The citizen report card exercise highlights that a majority of beneficiaries believe that delivery of services have improved (70%-80%) and there is a high level of satisfaction with most services (70%-80%). / (b) There has been significant growth in revenue generated from commercial taxes, which have grown at an annual average of 24% between 2008-09 and 2011-12. Own tax to GSDP ratio is estimated to be 5.3 as compared to 4.8 in 2008-09.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / The programme has successfully completed 4 years in 2011. In the reporting year (2011-12) the programme fully spent the forecast expenditure of FA £3.4 million and TA £1.09 million. / 2.2 Key cost drivers / The Governance and Administration Department (GAD), Government of Bihar (GoB) is the key cost driver of the programme. The Governing Council, chaired by the Chief Secretary, along with representation by DFID and other spending departments approves all expenditure at the beginning of the financial year and disburse allocation to various departments. DFID’s contribution is reimbursed on submission of expenditure statement and claim bi-annually. / TC funds are spent directly by DFID. These funds are used to procure staff/consultants, provision of training and contribute to running costs of the GTAST and RSUs. DFID reimburses GTAST expenditure following the submission of quarterly invoices using standard agreed procedures / 2.3 Is the project on-track against original timescale: Yes / The programme is in the 5th year of DFID support and has achieved significant results. GoB has submitted request to GoI for cost and time extension of the programme to continue on-going reforms in partner departments as well as to implement a growth component covering agriculture, tourism and industries. GoB and DFID will work together and submit DPR for project expansion till 2016.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / There are 3 areas where we see emerging evidence which could have significant implications for the programme. / For the first time, a robust large scale beneficiary survey provides evidence on quality of service delivery in Bihar. Using the novel lot quality assurance sampling (LQAS), the survey will be able to report on key performance indicators at not only district level (38 Nos), but also at the sub-division (101) and block level (538 Nos), thereby enabling decision-makers to evaluate service delivery at the frontline level. This survey will also serve as a baseline for future service delivery assessments. Uptake of the survey at the political and administrative level can raise the profile of the programme significantly. / With the RtPS completing one year, there is now a robust database available on the reliability and timeliness of delivery of services. The evidence, while indicating improved responsiveness and timely delivery, also highlights denial of service for certain services like issue of ration cards, pensions, land mutations etc. There is need to ascertain the reasons for the relatively less efficient delivery for these services. In addition, there is also need to understand the reasons why applicants do not avail of their right to appeal in case service is denied. / The programme has supported many important training initiatives and anecdotal evidence suggests significant positive results emanating from them. There is need to capture evidence in a more systematic and robust manner such that results can be quantified and held up to scrutiny. At this stage, two training initiatives need concurrent evaluation – (a) the induction training of BAS probationers and (b) the citizen-centric policing training for frontline police personnel. / 3.2 Where an evaluation is planned what progress has been made? / A large scale citizen survey was planned to obtain beneficiary feedback on quality of service delivery for a range of services. This was initially delayed since the approval from the Governing Council took more time than expected. The CRC commenced in February 2012 and the fieldwork will be completed in September 2012. The findings from the survey will be shared with the government in October 2012.

4. Risk
4.1 Output Risk Rating: Low/Medium/High / The programme is judged to be of low to medium risk with the potential of high return. / 4.2 Assessment of the risk level / There are two key risks. / The first area of risk is the limited financial management capacity of BPSM. The programme has enabled BPSM strengthen its capacity to undertake financial accounting and facilitate independent audit. A robust accounting software has been implemented this year and all accounts have been updated. Independent audit has been completed for years 2009-10, 2010-11 and audit for 2011-12 is ongoing. The audit report is expected in October 2012. / The second area of risk is the possible use of financial assistance in non-core areas such as office modernisation and procurement of IT equipment. DFID has proactively raised this issue with GoB. As a result, GoB has agreed that DFID funds will be used in areas which present the potential for higher returns.
Risk of funds not being used as intended / The risk of funds not being used as intended is low. Approval for each spending proposal is given by the Governing Council, which is chaired by the Chief Secretary and its members include Principal Secretaries of all partner departments. DFID is a special invitee at the Governing Council meetings and is party to approval of each spending proposal. / DFID financial assistance is provided to BPSM on a reimbursable basis. Departments and districts submit utilisation certificates before the release of next tranche of funds. Audit of project funds has been initiated and the final audit report is expected in October 2012. / 4.4 Climate and Environment Risk / The climate & environmental risk is judged to be low for the programme.

5. Value for Money
5.1 Performance on VfM measures / RtPS: A cost-benefit analysis of RtPS was done by GTAST. The benefits that were monetised include (a) time & labour savings for beneficiaries (b) travel & other expenses saved by beneficiaries. The costs that were taken into account include (a) HR costs for staff deployed in districts & blocks and (b) publicity & media costs. Savings from reduced corruption could not be monetised due to lack of data availability. / Two different calculations were done – (a) costs & benefits for the last year and (b) potential benefits of delivery through Vasudha Kendras. / Last year: Against a cost of Rs. 40 crore, actual benefits are monetised to be Rs. 761 crore. (without corruption savings) / Vasudha Kendra Potential: Once the issuance of certificates is rolled out through Vasudha Kendras (village level common service centres), the benefits could potentially be Rs. 843 crores every year, assuming the same number of certificates being issued every year. / There have also been significant efficiency improvements in the service delivery process. These include: / Simplification and standardisation of all application forms to make it simpler, convenient and citizen-friendly. / Introduction of single window for applications manned by non-official executive assistants - Reduced dependence on intermediaries/ middlemen and lesser avenues for rent-seeking activity by corrupt officials/staffs / Provision of mandatory acknowledgment receipt which is a proof of submission of applications. The unique no. in the receipt can be used to track the application status through SMS, internet and helpline number / Removal of uncertainty in service delivery (about timelines of service delivery, official responsible for service delivery, counters for submitting applications and receiving services etc.) through prominently displayed notice boards in the offices / Introduction of online facility for certain services (caste, income and residential certificates) which account for about 70% of the applications means that applicants are required to go to block/circle office only to receive the certificates. The applicants are also sent automated reply once the services are ready to be delivered. This is perhaps the most important facility under RTPS for services that are in most demand. / Registration: The digitisation of registration records will not only help the citizens in availing the service in significantly lesser time but also reduce the time spent by the Department officials in searching and retrieving the required documents. So far 60% of the records have been digitised. / The digitisation of registration records involved a total cost of Rs. 15 crores, out of which DFID contributed Rs. 3 crores. / The Department would be able to save about 6 man days of this staff member leading to savings of Rs. 108 crore per year. / Estimated savings of citizens (one visit less at a minimum) will be Rs. 9 crore per year. / There will also be significant benefits due to lower incidence of corruption – this has however not been monetised due to non-availability of relevant data. / The efficiency of the department will also improve significantly. Time for issuance of non- encumbrances certificates will be reduced to 1 hour from 7 days – to benefit 9 lakh citizens every year. / Commercial Taxes: A single initiative undertaken for the commercial taxes department will deliver significant amount of additional revenue. The harmonised system of nomenclature involved a total cost of Rs. 14 lakhs. This has the potential to generate additional revenue of Rs. 1000 crores per year to the state exchequer. / General Administration: A range of interventions undertaken to improve human resource management has led to efficiency gains such as: / Faster career progression amongst the state cadre officers / Improved induction and in-service training leading to a more professional cadre / Streamlined examination processes resulting in smooth conduct of examinations leading to timely recruitment / 5.2 Commercial Improvement and Value for Money / Commercial improvement and value for money are ensured for both direct and indirect procurement. For better value for money, DFID directly procured the GTAST through OJEU process. GTAST contract was initially for 3 years (2008-09- 2011-12), which ended on 30 September 2011. PrG team renegotiated the GTAST contract and a cost extension for 16 months was issued in October 2011. CVs and past 3 years performance of existing consultants were reviewed at the time of renegotiation and replaced a few consultants with new professionals to match the changing demands of GoB. All third party contracts are managed by GTAST, strictly following the procurement guidelines jointly agreed by GoB and DFID. DFID project team review and approve all technical and commercial bids received before contract is issued. During the year 2011-12 we have made a saving of £85,000 from the sub-contracting budget. A proper inventory is maintained for all the items procured from DFID funds. DFID PrG team conducted a post procurement review of all sub-contracts let by GTAST and have acknowledged the best practices followed in the procurement processes and have made recommendations for further improvements. / Procurement under Financial Aid is managed by BPSM adhering to the standard GoB procurement standards. Payment for procurement of services and major equipment are made by the Directorate on behalf of the partner departments. The fund flow and accounting arrangements for funds utilised are agreed during the quarterly General Council Meeting Chaired by the MD, BPSM. All expenditures are subject to audit by an external agency recommended by CAG. The annual review conducted by DFID will assess the performance of expenditure against allocation for each intervention. / 5.3 Role of project partners / DFID is the sole donor for the BGARP intervention. Principal partners are the Mission Directorate for coordination and leading government-wide reform, the Department for Personnel and Administrative Reforms (DPAR), and line Departments identified for service delivery improvements. The Mission Directorate (MD), led by the Principal Secretary, DPAR, is responsible for implementation of the programme and eventually oversees other governance reforms to ensure coherence and co-ordination. Reform Support Units (RSUs), led by senior government staff, in partner departments oversee Department-level service delivery improvements. / The Technical Support Agency (GTAST) provides consultancy support to the MD and RSUs and help identify and procure specific expertise needed to achieve outputs and goals / 5.4 Does the project still represent Value for Money : Y/N / Yes. / 5.5 If not, what action will you take?

6. Conditionality
6.1 Update on specific conditions / DFID’s support is based on a shared commitment to three objectives of reducing poverty, respecting human rights and strengthening financial management and accountability. GoB continues to show strong commitment to poverty reduction, human rights and financial accountability issues.

7. Conclusions and actions
BGARP is well on track to achieving its goal and purpose. The programme has contributed significantly to the positive governance agenda of the State Government. It has delivered effectively on all the three outputs – improving human resource management, strengthening systems and service delivery in partner departments and improving delivery of services at the frontline level. / The key action points emerging from the annual review are: / GoB has submitted request to GoI for cost & time expansion of the programme to implement a growth component to the existing programme. GoB & DFID to work together and submit DPR for project expansion. / Right to Public Services (RtPS) Act has been successfully rolled out with more than 20 million beneficiaries in the first year of its operation. Audit of back-end processes need to be initiated to improve service delivery, particularly for services with higher rejection rates. (By Dec 2012). In addition, a study to be undertaken which will enable implementation of a comprehensive reform action plan for the district/block administration. / In GAD, further support will be provided to institutionalise the Performance Appraisal Report (PAR), for evaluation of induction training for BAS probationers, for developing a comprehensive administrative reforms framework and for strengthening of training delivery in BIPARD. / In Home / Police, the `Citizen-centric police’ training of frontline police personnel was appreciated. This will be rolled out in a phased manner with ongoing evaluation (By June 2013). Action plan for Jail manual to be developed and implemented initiated. / In Commercial Taxes Department, DFID support on HSN Code based Commodity Classification will help GoB raise significantly more tax revenue. Further support will be provided to overhaul the entire tax return process. / Findings from the Citizen Survey on quality of delivery of public services will be available by October 2012. DFID will help GoB develop an Information Dashboard which will provide key analytics from the survey to all decision-makers. / Financial Audit of BPSM is underway and will be completed by September 2012. The accounts of BPSM have been streamlined through accounting software (years 2009-10, 2010-11 and 2011-12).

8. Review Process
The Annual Review of BGARP was undertaken during 23-24 August 2012. The DFID team took a field visit in Nalanda district of Bihar to review progress of various interventions under this programme and met with key GoB officials responsible for the implementation and monitoring of the programme. The findings of the review and recommendations were discussed with the Chief Secretary, and Mission Director, BPSM.