Annual Review – post April 2018

Title: Improving Public Financial Management and Accountability in Nepal (PFMA)
Programme Value £ (full life): GBP 5 million		Review Date: August 2018
Programme Code: 30006	Start Date: / September 2016	End Date: / March 2021

Summary of Programme Performance
Year	2017	2018
Programme Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300006/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-GOV-1-300006/documents

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

The Improving Public Financial Management and Accountability Programme (PFMA2) will contribute to the increased effectiveness of Nepal’s public financial management and revenue systems and reduce opportunities for corruption. PFMA2 is a £5 million, five-year programme and was approved in August 2016 (Vault ID 6032817). It is made up of three components:

Component One: Technical assistance to assess fiduciary and corruption risks in key sectors; design fiduciary safeguards to address these risks; and support the government’s medium term reform efforts to improve public financial management and accountability.

Component Two: Demand-led technical assistance and capacity building support in response to requests by the government. This will likely include design of financial management systems for the new local governments; sector-specific financial management reform plans; design and roll out of standardised internal financial controls; and support to improved external audit in social sectors.

Component Three: A reserve fund for significant institutional reform opportunities. This fund will enable scale-up on specific, stand-alone reforms that stem from sector or revenue assignments supported under Components One and Two, or that may arise as a result of Nepal’s transition to federalism.

This programme has been designed in concurrence with a multi donor trust fund (MDTF) for PFM reforms. The MDTF is the leading PFM reform mechanism directly aligned to the Government’s PFM Reform Plan and is jointly designed and funded by DFID, Government of Norway, Australia (DFAT), USAID, the European Union, and Government of the Swiss Confederation. The MDTF is managed by the World Bank and is run as a more traditional, large-scale technical assistance. The flexible, iterative approach built into PFMA2 will balance ongoing responsiveness to the government needs with a proactive mechanism to identify and exploit opportunities for small strategic interventions. It will play a critical role in supporting Nepal’s transition to a federal system of government.

By designing two complementary programmes in concurrence, DFID Nepal expects to achieve complementary programme objectives with greater overall control and programme accountability. The PEFA Secretariat is the government body charged with coordination of PFM activities across government and, along with the Ministry of Finance, is the principal government partner for the both the PFM programmes.

Summary of progress since the Business Case

The focus of this programme since the beginning has been on delivery and rollout of a flagship subnational (municipal and provincial) financial management system. As of last annual review, DFID had been able to rapidly respond to an urgent request by the Government for technical assistance to design a basic budget and accounting system for the 753 new local governments. The federal government was planning US$2.25 billion fiscal transfers to these newly established autonomous governments, but had no system for accounting and reporting.

The flexible fund for institutional support under the third component was used to support the development of the municipal level financial management system. Due to delay in procurement of supplier for PFMA2, DFID’s Expert Advisory Call Down Service (EACDS) was used for hiring a private contractor from June-September 2017 to provide technical and financial support to the Government of Nepal for identification, preparation and commissioning of an interim PFM system for the recently formed local governments. The system has been developed, tested and is being used in more than 200 out of 753 municipalities.

After a competitive procurement exercise, Crown Agents was awarded a contract in October 2017 to implement Components One and Two of the programme. The support for the municipal financial management system was taken over by Crown Agents. The third component has been retained as a flexible fund to enable DFID to contribute to government’s emerging needs in transition to federalism. The inception phase for Components One and Two finished at the end of January 2018. The focus of this programme until now has also been on supporting the municipal level system and developing a new system for the Provincial level. All the seven provinces have produced their respective budgets for fiscal year 2018/19 using the software developed by the programme, and more than 200 municipalities are using the system for budgeting, accounting and reporting till date. The municipal system in combination with provincial is known as Subnational Treasury Regulatory Application (SuTRA) (www.sutra.gov.np).

The DFID-funded system will deliver the following benefits to the various tiers of government: (i) enables federal government to prepare consolidated financial statements, (ii) supports federal government in providing fiscal transfers to the subnational governments (iii) enables subnational governments to prepare their budget and prioritize resources, (iv) allows subnational governments to directly access information on conditional transfers as the data is directly fed into the system from federal government, (v) enables subnational government keep track of expenses and produce financial reports in templates prescribed by Office of the Auditor General (OAG). Additionally, the system has incorporated GFSM 2014 already and the federal government is also updating its Chart of Accounts to the same standard. This ensures consistency across governments for preparing consolidated financial statements and will also allow accrual based accounting when the government is ready. Furthermore, this will be available to the subnational governments at no cost, and the system updates and maintenance will also be done by the federal government. Overall, the system is expected to fill a major gap in the subnational public financial management system, reduce opportunities for corruption and help minimise the disruption to services. It has also positioned DFID to positively engage with and influence future reforms.

The PEFA Steering Committee, the decision making authority for PFM reforms in the country has instructed the Financial Comptroller General’s Office (FCGO) under Ministry of Finance to enhance the system as necessary, and implement it in all provinces and local level. Although there is a clear steer from the committee, a strategy for implementation of SuTRA has still not been finalized due to absence of a clearly shared approach between various stakeholders in and out of the government.

Besides the system development, the programme is exploring opportunities to support (i) the Office of the Auditor General to develop and refine an institutional framework for long-term IT auditing and (ii) the Ministry of Finance’s Revenue Department on analysis of non-tax revenue and tax exemptions. The programme has also provided demand driven cross office support on assessments of fiduciary risks or other financial analysis for sector programmes. Additionally, a national level fiduciary risk assessment (FRA) has been produced to inform DFID’s engagement at the federal level, and a municipal level FRA has been scheduled for September 2018.

DFID is continuing to identify and consider other innovative, demand driven ideas which could potentially be implemented through Component Three of the programme to help the federal transition on governance and PFM. For example, after successful discussions with political and administrative levels in Province Two, the Forum of Federations has submitted a proposal seeking to provide the Ministry of Federal Affairs and General Administration (MoFAGA), province and local level leaders with comparative experiences in federal/devolved transition management. The aim of the work would be to bridge the gap between politics and administration, and strengthen intergovernmental coordination.

Summary supporting narrative for the overall score in this review (1/2 page)

The overall score of this programme is ‘A’. The programme has been quick to recognise and respond to gaps in the public financial management system through Component 2 and 3. However Component 1 has underachieved; the procurement process was slow with suppliers’ contracting delayed.

Firstly, the SuTRA system has been endorsed by the Financial Comptroller General’s Office (FCGO), Ministry of Finance (MoF) and Office of the Auditor General (OAG) as the system of choice for use at the subnational level. The government is currently working on long term strategy for the institutionalization of subnational financial management. It already incorporates Chart of Accounts and reporting templates approved by the OAG and the FCGO. In less than a year since its design, the budgeting, accounting and reporting modules have been used by more than 200 municipalities, and the seven Provinces have used it this fiscal year to produce their annual budget. The total cost of system development and Training of Trainers (TOT) (for both municipal and provincial level) has only been around £385k, which is excellent value for money. The SuTRA system would represent quite good value for money as a transitional system for subnational governments and extremely good value for money if it ultimately comes to provide a sustainable solution.

Second, the programme has been an excellent example of thinking and working politically. The programme has actively established and managed relationship with both government counterparts and donors, without which the progress on SuTRA would not have been possible. In addition to protecting current initiatives, the programme has positioned itself to deliver key assistance to other PFM institutions: building IT audit capacity of the OAG in partnership with the National Audit Office (NAO) - UK, and recommending policy reforms on non-tax revenues and tax exemptions. The programme has also prepared a report on baseline political economy analysis of public finance in Nepal, which will be updated semi-annually.

Third, the programme has already supported some sector programmes to analyse, monitor or manage fiduciary risk at various levels. PFMA2 has also developed and shared with the DFID office a systematic approach to preparing a pipeline of opportunities for working with sector programmes, something that had been lacking till date. The national FRA has been completed and municipal FRA has been scheduled for this month, both which will inform DFIDN’s engagement strategy and financial aid portfolio going forward.

Recommendations for the year ahead (1/2 page)

The logframe should be revised in order to bring clarity to, and avoid duplication in outputs. These revisions are not intended to significantly affect the theory of change which remains relevant. They include: revising logframe to set annual targets in alignment with Annual review date; updating it for upcoming support to the government (eg. OAG and MOF); merging outputs 2.1 and 2.2 and impact weighting increased to 40%.

The value for money indicators should be revised: This includes moving the vfm indicator on the cost of FRA to economy from efficiency and including at least one indicator for measuring effectiveness of the programme.

A systematic approach and stronger engagement across DFIDN office is needed on Component One to identify fiduciary risk review and mitigation opportunities: The Annual Review notes that in the past six months of implementation, the programme has not been able to build a pipeline of opportunities of supporting sector programmes, and the service has been ad hoc. Although an approach has been developed and shared with the office, the programme needs stronger engagement across office to implement it effectively in future. As an example of such cross office support, PFMA2 could facilitate a session on identifying mitigation measures for safeguarding and fraud risk for DFIDN programmes during the Strategic Portfolio Review (SPR) week. Internal Audit Department had recommended DFIDN to conduct a comprehensive assessment of fraud and safeguarding risk and to develop a proactive approach for mitigation in the 2018 Assurance Report.

Ensure gender balance in consultant recruitment: One of the equity vfm indicator “Provision of non-management Component 1 and 2 technical input days (%) disaggregated by gender (Male and Female)” has not been met. The programme is recommended to make an active effort to secure more female technical experts.

Clarify roles of partners in consortium: While value to the programme from two lead suppliers is evident, contribution from other partners is not clear. The programme is recommended to revisit and clarify roles of partners in the consortium, considering VfM and interest in building a sustainable approach. .

Develop a clear strategy for implementation of IAD’s recommendation for review of FRAs: The IAD has also recommended external evaluation of the FRAs conducted by the programme and a mid-term review of progress made against FRA recommendations. The programme should develop a clear strategy for implementation of these agreed actions.

Develop a coordinated approach for Subnational PFM system across DPs: There is clearly an absence of a shared approach amongst stakeholders including government and DPs. While influencing the government is challenging, the programme needs to try building consensus and a coordinated approach amongst the DPs.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Delivery of high quality analysis of fiduciary and corruption risks in key sectors in Nepal
Output number per LF		1-1	Output Score	B
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 1.1.1 / Number of Fiduciary Risk Assessments (FRAs) or Annual Statements of Progress (ASP)s produced [original plus revised methodology]	3	1 / Partially achieved
Output indicator 1.1.2 / Number of non-traditional PFM-related assessments (e.g., due diligence, asset management, etc)	2	2 / Achieved

Briefly describe the output and provide supporting narrative for the score

The DFID’s How to Note - June 2011 on FRA states that… (FRA is) mandatory for all projects over £10 million where the funds are managed by a PFM system significantly different from the national PFM system. The most likely example is support to sub-national governments in a federal state in which sub-national governments have largely autonomous financial management systems and may be subject to their own financial management laws. As Nepal has moved to a federal system with three tiers of government – Federal, Provincial and Local, an FRA for each tier of government is required. The first indicator targeted to complete two of the three FRAs (National and Local) and at least one annual statement of progress (ASP) for sectoral FRAs conducted by the predecessor programme. There has been a gap in conducting FRAs and ASPs for DFIDN sectoral programmes (with financial aid component) since the predecessor programme ended in March 2017.

DFID defines fiduciary risk as the risk that: a) funds are not used for the intended purposes; b) do not achieve value for money; and/or c) are not properly accounted for. The traditional approach has been limited to assessing fiduciary risk only on financial aid, even though fiduciary risk could arise from any funding modality or implementation partner. Therefore, PFMA2 has planned to take a risk based approach to assessing fiduciary risk instead, regardless of the aid modality. The second indicator targets these non-traditional fiduciary risk elements in programmes.

It is important to note that these milestones were set in the end of inception period (January 2018) and the planned implementation period was eight months starting February 2018 to September 2018. At the time of drafting of this annual review, the programme is only six months into implementation. While the target for the second indicator has already been met, the target for the first indicator is in progress. The National FRA has been completed and the Local Governments FRA is scheduled for September 2018. In some areas, DFIDN has either stopped or paused financial aid because of lack of clarity in functional assignments and reporting framework after devolution, one of the reasons why sectoral ASPs were not conducted. However, the programme also lacked a systematic approach of engaging with SROs in a way that develops a pipeline of important work. Considering these facts, the output has been rated as ‘Outputs moderately did not meet expectation (B)’

Output indicator 1.1.1
Number of Fiduciary Risk Assessments (FRAs) or Annual Statements of Progress (ASP)s produced [original plus revised methodology]

The programme has completed one FRA at the national level and will be starting another FRA at the local government level in late August. The provincial level FRA has been planned for mid-2019 to allow one full year of budget implementation cycle for provinces before assessment. The provinces had received recurrent expenditures only of one billion rupees (approximately $10m) fiscal transfers in the last fiscal year (2016-17). This fiscal year (starting July 2018) is the first time provincial assemblies have approved their first full budget of both capital and recurrent spend.

When the logframe was being drafted ASPs were considered for other sectoral programmes that have received financial aid through government systems. However, as federalism is unfolding in the country and as responsibilities are being rationalised across three tiers of government, the sectoral division that existed in the unitary system is starting to be less significant. Additionally, DFID Nepal has paused, postponed or cancelled financial aid from many earlier programmes and thus conducting ASPs in this scenario is less relevant. This milestone has been partially achieved.

Output indicator 1.1.2
Number of non-traditional PFM-related assessments (e.g., due diligence, asset management, etc)

A limited scope risk assessment for DFID’s support to the National Climate Change Support Programme 1 Transition (NCCSP-1T) has been conducted to assess capacity of the designated partner to manage the programme. Similarly, the PFMA2 has carried out a review of the Financial Monitoring Reports of Environment Friendly Local Governance (EFLG) as the programme was coming to an end. The primary objective of this review was to provide sufficient basis for DFID to conclude whether the financial and supporting statements validate the figures included in the Financial Management Reports submitted to DFID; and to help the team ascertain the amount of unspent funds at the end of programme period and therefore due for return to DFID. This milestone has been achieved.

Lessons identified this year, and recommendations for the year ahead linked to this output

The assessment of the targets for this output would have been easier had the implementation period been aligned with Annual Review date (August 2018). However, this annual review gives an opportunity to reassess and reset the logframe. Additionally, as the sectoral division that existed in the past is less significant after federalism, and as DFID Nepal had made decisions to stall financial aid for this fiscal year due to lack of clarity, the need and opportunity for conducting sectoral ASPs was reduced. That should be factored into the updated logframe.

Recommendations:
- Revise the current logframe to set annual targets in alignment with Annual review date.
- Ensure that there is stronger engagement strategy across office to identify fiduciary risk review and mitigation opportunities. The new approach for conducting alternative fiduciary risk review has recently been communicated to the DFID Nepal office.

Output Title	Development and implementation of tailored FMIPs and activities, including advice on short term safeguards and measures to remedy and mitigate identified weaknesses
Output number per LF		1-2	Output Score	C
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 1.2.1 / Number of developed or updated Financial Management Implementation Plans (FMIPs) incorporating FRA/ASP findings	1	Not achieved
Output indicator 1.2.2 / Number of capacity building activities linked to risk assurance frameworks	1	Not achieved

Briefly describe the output and provide supporting narrative for the score

This output aims to support government entities to develop action plans to mitigate risks identified by FRA/ASPs and provide support to enhance their capacity to take recommended action. The predecessor programme PFMA-1 had supported seven institutions in the Government to develop Financial Management Implementation Plans (FMIPs) to address issues raised by FRA assessments. Due to the transition to federalism and changes in the government structures and functional assignments, DFIDN has made decisions to either pause or stop financial aid in many programmes and thus, the FMIPs were not given priority during this period. The output has been scored ‘Outputs substantially did not meet expectation (C)’

Output indicator 1.2.1
Number of developed or updated FMIPs (incorporating FRA/ASP findings)
The first indicator aimed to update at least one FMIP to ensure proper ownership within new federalised structures. No progress has been made as this activity was linked to recommendations made in sectoral FRAs conducted by the predecessor PFMA programme. As DFIDN has made decisions to either pause or stop financial aid in the current context, this output was not given priority.

Output indicator 1.2.2
Number of capacity building activities linked to risk assurance frameworks
This activity is linked to the previous indicator and the milestone has not been achieved.

Lessons identified this year, and recommendations for the year ahead linked to this output

- The programme should engage more closely with DFIDN SROs and Federalism Task Force (FTF) to understand changing context for sector programmes.
- The sectoral FRAs and FMIPs should be revised or updated for federal context when and if the SROs confirm it is appropriate to engage with particular sector/ministry. This could also help DFIDN understand and prepare mitigation actions for financial aid in the new context.

Output Title	Identification, design and implementation of specific PFM assignments.
Output number per LF		2-1	Output Score	A++
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 2.1.1 / Number of Political Economy Analysis (PEAs) reports/updated stakeholder analysis produced.	1	1 / Achieved
Output indicator 2.1.2 / Number of demand-led analytical assessments completed to inform and improve DFID programmes.	3	4 / Exceeds Expectations
Output indicator 2.1.3 / Implementation of reform projects in PFM and revenue systems (specific indicators from approved projects will be added below)
Output indicator 2.1.3.1 / Rollout of Subnational Treasury Regulatory Application (SUTRA) at provincial ministries, (e.g., software installed and personnel trained)	Delivery/design and pilot / Testing	Exceeds Expectations / All seven provinces produced their budgets using SuTRA.

Provide supporting narrative for the score

PFMA2 being a flexible and adaptive programme, the aim of this output is to i) identify potential emerging windows of opportunity and ‘orphan’ needs not addressed by other PFM programmes, and ii) support the strengthening of Government PFM systems. The Output indicator 2.1.3 has been kept open ended to accommodate any emerging opportunities as the programme progresses. Through output indicator 2.1.2, PFMA2 has supported other sectoral programmes in carrying out assessments of partner government systems, and the progress made has exceeded the set milestone. The assessments have also assisted the individual sectoral programmes to make informed decisions.

A key intervention that has already been delivered by the programme is SuTRA system at the municipal and provincial level. The government requested DFID to provide a provincial level budgeting system as an enhancement after DFID successfully delivered budgeting, accounting and reporting modules for the municipal governments. While the programme aimed to only design and pilot the system during this period, it has successfully rolled out and provided training for the budgeting module. Furthermore, all seven provinces produced their budget using SuTRA this fiscal year, which speaks volumes about the demand for quality support to the government. This output has been scored as Outputs substantially exceeded expectation (A++)

Output indicator 2.1.1
Number of Political Economy Analysis (PEAs) reports/updated stakeholder analysis produced.
The programme’s approach to understanding political economy is through a combination of stakeholder engagement, utilising a national cadre of experts and supply partners; and a specific review carried out by Overseas Development Institute (ODI). The report has captured the recent changes to the political and macro fiscal scenario, intergovernmental relationships between federal PFM institutions, impact of federalism and entry points of reform going forward. The report will be updated on a semi-annual basis. This milestone has been achieved.

Output indicator 2.1.2
Number of demand-led analytical assessments completed to inform and improve DFID programmes.
PFMA2 has completed four analytical assessments for DFIDN programmes. The programme has done a preliminary analysis of the Investment Board Nepal’s (IBN) budget and financial statements. Further engagement with the entity has been planned to provide recommendations on planning and increasing capital expenditure. Similarly, an analysis has been provided on possible funding arrangements for the new National Climate Change Support Programme (NCCSP) programme. The programme has provided advice and analysis on the funds flow for housing reconstruction for DFID funds channelled through the World Bank. The programme has also provided support to the Nepal Safer School Programme in relation to funds disbursement and fiduciary assurance at the local level. This milestone has been achieved and has moderately exceeded expectations.

Output category 2.1.3
Implementation of reform projects in PFM and revenue systems
Specific indicators from approved projects will be added to this indicator as the programme identifies further areas for intervention. Progress on one sub-indicator is identified below.

Output indicator 2.1.3.1
Rollout of SUTRA at provincial ministries, (e.g. software installed and personnel trained)
All seven Provinces have published their budgets from SuTRA. This is a significant achievement as this involved rapid development of the software, training at the province levels and constant support during the data entry process. The milestone for this output was to design the system and pilot test, considering the challenges on implementation. The delivery of this output has significantly exceeded expectations.

Lessons identified this year, and recommendations for the year ahead linked to this output

SuTRA’s success confirms that a simple but timely response to governments demand has better chances of succeeding than a complex, off the shelf best practice solutions.

PFMA2 should update the logframe to incorporate upcoming support to two key PFM institutions – Office of the Auditor General (OAG) and Ministry of Finance, Revenue department. PFMA2 has been scoping support to the Ministry of Finance on analysis of non-tax revenue and tax exemptions. Ad hoc tax exemptions distort markets and reduce government revenue resulting in reliance on regressive taxes such as VAT. Potentially, the assignment will involve assessing the present scenario of non-tax revenues, and tax exemptions; opportunities for increasing their contribution into total revenue systems and having integrated framework for both revenue sources. In addition, a scoping exercise with the Office of the Auditor General to develop and refine an institutional framework for long-term IT auditing and its sustainability is underway. This support will help the OAG prioritise audits based on risk and materiality, and will strengthen oversight of DFID programmes. It will be necessary to identify key indicators and update the logframe.

Output Title	Capacity building in financial management and revenue administration reforms (Government of Nepal).
Output number per LF		2-2	Output Score	A++
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 2.2.1 / Number of capacity building events intended to support PFM initiatives	2	Achieved and exceeded expectations. / 7 (SuTRA orientation on budgeting process provided to all seven Provinces) + ongoing helpdesk support.

Provide supporting narrative for the score
The output aims to build capacity in various government entities that are responsible for financial management and revenue administration. One of the methods of capacity building is by conducting events or trainings, and the programme has exceeded planned milestones by delivering seven orientations across provinces. As a result, the Provinces have produced their budget for FY2018/19 through SuTRA. The output has been scored Outputs substantially exceeded expectation (A++).

Output indicator 2.2.1
Number of capacity building events intended to support PFM initiatives
PFMA2 consultants carried out orientation events on budgeting process to all seven Provinces coupled with backstopping support during the budgeting period. As a result, the provinces were able to produce their budget through the SuTRA system.

Additionally, PFMA2 has been providing embedded support to the PEFA Secretariat. The PEFA Secretariat has the responsibility of coordinating PFM activities across the government and, along with the Ministry of Finance, is the principal government partner for PFMA2 and PFM Multi-Donor Trust Fund. There is no permanent staff in the Secretariat: a Joint secretary and an Undersecretary from the Finance Comptroller General’s Office (FCGO) are deputed as Coordinator and Member secretary. Both the positions have dual responsibility – to FCGO and to PEFA, and thus need additional resource to carry out their important function. The PFMA2 embedded support prepared the implementation strategy for the PFM MDTF programme and supported the preparation of PFM policy reform in the federal context.

Lessons identified this year, and recommendations for the year ahead linked to this output

In retrospect, this output is not significantly different from Output 2.1 above. The two outputs should be merged and the impact weighting increased to 40%, given its significance as technical support to the government.

Output Title	Thematic emphasis in key areas of inclusion
Output number per LF		2-3	Output Score	B
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 2.3.1 / Number of recommendations or implementation actions that address digital, financial, social and gender inclusion and financial transparency	2	1 / Partially Achieved

Provide supporting narrative for the score
The way that governments raise, allocate and spend money has the potential to reduce or amplify existing gender based inequality. In Nepal, such decisions – whether at federal, provincial or local – continue to be made nearly exclusively by men. This is particularly critical in sector PFM decision making where choices that are made based on financial management considerations without the inputs of women and girls can have very real impacts on the services and support available to them. The main objective of this output is to ensure that disaggregated budget data is available for gender (and some other key thematic areas such as digital reforms, financial reforms, social inclusion and financial transparency), so that at least a benchmark data is available to aim for higher targets. SuTRA requires disaggregated budget data on four areas of inclusion at both municipal and provincial level. This will help the subnational governments link their policy to budget and monitor progress. In future, the programme should systematically engage with DFIDN SROs to contribute more to this output.

Output indicator 2.3.1
Number of recommendations or implementation actions that address digital, financial, social and gender inclusion and financial transparency

SuTRA requires budget to be disaggregated for gender, social inclusion, environment and poverty. This is a useful tool that enables civil society and academia to hold the governments to account on inclusion. The social inclusion related budget code further disaggregates budget set aside for Janajati, Dalits, and traditionally excluded groups.

Lessons identified this year, and recommendations for the year ahead linked to this output

Enabling data availability on gender and social budget is definitely a positive step, but the programme should systematically engage with DFIDN SROs to identify opportunities to mainstream inclusion in public financial management.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

The PFMA-2 Theory of Change is based on a number of inputs and key assumptions which aim to tackle weaknesses in public financial management and accountability practices in Nepal.

The inputs include time and human and financial resources which make up the economy dimension of VfM. These inputs will be used to carry out a number of activities including: strategic management and coordination, provision of technical assistance and embedded hands on support, fiduciary risk and corruption assessment, political economy analysis, preparation of financial management improvement plans, annual statements of progress, capacity building measures (training, exposure visits, workshops), procurement of software and hardware to support reform, among others.

These activities will produce high quality reports on fiduciary and corruption risk as well as political economy analyses. Tailored PFM reform plans will also be developed and implemented, and specific PFM assignments will be identified, designed and implemented. Reforms in sector financial management and revenue administration will be enhanced due to the capacity building measures.

The outputs will contribute to reforms in government policies, processes and activities that will in turn contribute to improved accountability and functioning of Nepal’s PFM system and revenue. In addition, the outputs will contribute to mitigating risk in DFID’s programming on public financial management and Nepal’s social sector PFM and revenue systems. The outcomes will contribute to increased accountability and effectiveness in Nepal’s PFM and revenue systems, more resources for services and to reduced opportunities for corruption.

The Theory of Change was established after an inception phase in January 2018. It remains relevant, except for some outputs in the logframe based on recommendations from this Annual Review.

Figure 1.1: PFMA2 Theory of Change

Increased accountability and effectiveness in Nepal’s PFM and revenue systems, reduced opportunities for fraud and corruption and improved PEFA scores

IMPACT

Reforms in government policies, processes and activities that contribute to improved accountability and effective functioning of Nepal’s PFM systems and revenue
Mitigation of risk in DFID portfolio and Nepal’s social PFM systems and revenue
Increased awareness and visibility of DFID’s work on PFM reform

OUTCOMES

Thematic emphasis in key areas of social inclusion
Delivery of high quality analysis of fiduciary and corruption risks in key sectors in Nepal
Capacity building in financial management and revenue administration reforms
Development and implementation of tailored FMIPs and activities, including advice on short term safeguards and measures to remedy and mitigate identified weaknesses
Identification, design and implementation of specific PFM assignments

OUTPUTS

TA, training, exposure visits, workshops, strategic management and coordination
TA, training, workshops, strategic management and coordination
TA, fiduciary and corruption risk analysis, political economy analysis, strategic management and coordination
TA, preparation of FMIPs, preparation of annual statements of progress, strategic management and coordination

TA and embedded hands on support, strategic management and coordination

ACTIVITIES

Time, human and financial resources

INPUTS
Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

PFMA2 aims to contribute to “Increased accountability and effectiveness in Nepal’s PFM and revenue systems, reduced opportunities for fraud and corruption and improved PEFA scores”. The programme is only six months into implementation, so it is too early to assess the programme against its impact statement.

However, the programme is well on track to accomplish its outcomes. The programme aims for three outcomes: (i) Mitigation of fiduciary risk in DFID portfolio (social sectors, governance and infrastructure) and Nepal's PFM systems and revenue, (ii) Reforms in government policies, processes and activities that contribute to improved accountability and effective functioning of Nepal's PFM systems and revenue, and (iii) Increased awareness and visibility of DFID's work on PFM reform.

Contributing to the first outcome, PFMA2 has conducted a National level FRA and is in the process of conducting the Municipal FRA in September. These two assessments and the recommendations on risk mitigations are critical for DFIDN’s decision on the way forward for financial aid. Additionally, the programme has further expanded the scope of fiduciary risk beyond financial aid and has already completed two assessments for a climate and a governance programme (NCCSP and EFLGP as described for Output 1.1). Similarly, assessments conducted on IBN, reconstruction and safer schools programme all contribute to this outcome.

Development of the SuTRA system, both at the municipality and provincial levels have contributed towards the second and third outcomes. Currently all seven provinces are using the budgeting module of the system, and more than 200 municipalities are using the system for budgeting, accounting and reporting. If the system is institutionalized as planned, it will help the federal government produce consolidated annual financial statements, which would otherwise not currently be possible. The use of the system at the sub-national level will also contribute towards transparent and accessible information on budget and expenditure to local citizens. DFID is also recognized, both by development partners and the government for thinking ahead and contributing to this key reform agenda.
Other reform initiatives with Office of the Auditor General and the Ministry of Finance - Revenue division that are currently under deliberation should further contribute towards these outcomes.

Explain major changes to the logframe in the past year (1/2 page)

During the first annual review, the programme was not under implementation due to a delay in the procurement of the supplier. One output corresponding to each component of the programme had been sketched out; with the idea of developing a full results framework during inception. The three outputs were (i) Strengthened fiduciary risk management at the sectoral and sub-national level, (ii) Institutional reform resulting from strengthened public financial management and accountability, and (iii) Program identifies and responds to opportunities to support reforms enabling significant improvements in Public Financial Management system. The previous outputs broadly correspond to the outputs in the current logframe, except for some change in the language and some additional outputs.

Broadly, Outputs 1.1 and 1.2 target mitigation of fiduciary risk in DFID portfolio and Outputs 2.1 to 2.3 aim to bring reforms in government policies and processes that contribute to improved accountability and effective functioning of Nepal's PFM systems and revenue. A flexible component – output indicator 2.3.1 has been added to accommodate any emerging opportunities as the programme progresses. The new opportunities will be evaluated based on methodology agreed between DFID and the suppliers in the inception report for ‘Intervention evaluation criteria for component two’. The methodology includes (i) an analysis of consideration for government’s ownership, leadership and support for the idea; (ii) ensuring from DFID’s perspective that the intervention does not duplicate existing interventions by other DPs, benefits of interventions can be identified and measured, and that it supports the country’s transition to federalism; and lastly, (iii) ensuring that the programme has resources and skillsets necessary for quality delivery of the intervention.

Describe any planned changes to the logframe as a result of this review (1/2 page)

The recommended changes to the current logframe are an attempt to clarify concepts and avoid duplication rather than suggesting any fundamental changes to the Theory of Change.

Output 1.2: Development and implementation of tailored FMIPs and activities, including advice on short term safeguards and measures to remedy and mitigate identified weaknesses

The ‘FMIP’ in this output refers to recommendations that have emerged from FRAs conducted by the predecessor programmes. The title should be reframed to accommodate any recommendations made to a government entity to mitigate its risks.

Output 2.1: Identification, design and implementation of specific PFM assignments

There are three indicators associated with this output. While the first and third are relevant to this output, the second indicator Number of demand-led analytical assessments completed to inform and improve DFID programmes duplicates output 1.1 to some extent, and is recommended to be removed.

Output 2.2: Capacity building in financial management and revenue administration reforms (Government of Nepal)

The only indicator for this output relates to conducting capacity building events, which is very limited in scope. Other mechanisms of capacity building of the government entity, such as embedded support, training, peer learning opportunities need to be included. However, it is also important to distinguish these activities from activities relating to indicator 2.1.2 (Implementation of reform projects in PFM and revenue systems) and indicator 1.2.2 (Number of capacity building activities linked to risk assurance frameworks). Thus, it is recommended that this output is to merged with 2.1.2 and the impact weighting increased to 40% given its significance as a technical support to the government.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

For the last annual review, the service providers’ proposal was taken as a proxy, which was broadly in line with the assumptions in the business case. The suppliers have established a VfM framework and indicators for the programme during the inception. The progress against each element (Economy, Efficiency, Effectiveness and Equity) is presented below.

Economy:

- Average flight cost from the UK and Ireland to Nepal: The flight cost from the UK to Kathmandu has averaged at £850 approx against 2018 target of £1,000.
- Number and % of inputs (days) provided by national consultants vis-à-vis international consultants (excludes programme and admin staffs): The split between input days of national and international consultants is 84% and 16% respectively. The target set for 2018 was 60%. The programme has made excellent use of national consultants through its longstanding partnership with Team consult, especially on Component Two.

Additionally, the total cost of system development and rollout till date has been roughly £500k, which is excellent value for money. The total cost of SuTRA till date, including USAIDs cost in conducting trainings in municipalities is given below:

Expense head	Cost[1]
Municipal system design and TOT (DFID)	£123 k
Provincial system design and TOT (DFID)	£ 251 k
Rollout of municipal system to municipalities and setting up helpdesk in PEFA secretariat (USAID)[2]	£143 k
Total	£517 k
[1] Cost to DFID and USAID includes programme management and indirect costs.
[2] The cost to USAID includes per diems provided to government staffs, accommodation and travel cost

Efficiency:

% of follow-on assignments which use the same personnel as the first assignment, building trust with Government of Nepal and knowledge: In terms of using consultants with previous relevant experience, PFMA2 has mobilized repeat consultants that had experience with the entity and assignment from the predecessor programme. In terms of support to the OAG, PFMA2 will be partnering with NAO and is planning to deploy the same resources that were used by the predecessor programme and appreciated by the government.
For upcoming assignments that have to be delivered in the federal context, such as the work on revenue and the municipal level FRA that are in the pipeline, the programme plans to deploy relevant skillsets, a mixture of previous experience but also new expertise as appropriate. This year, the programme has been able to deploy 100% repeat consultants with previous experience of the entity against target set at 33%.

New average cost of FRA and ASP produced (Given impact of federalism and sampling): The national FRA was completed at a cost of £25,225. The municipal and provincial FRAs together with federal will give an idea of a new average for comparison against future years. However, this is more suitable as an economic vfm indicator rather than efficiency indicator and is recommended to be moved under economy.

Additionally, the municipal and provincial systems have been developed and are already being implemented in more than 200 municipalities and seven provinces in less than a year since the development started. All three modules of municipal system was complete and rolled out in five months (August – December 2017) and the provincial budgeting module was completed and rolled out in six months (December 2017 – June 2018).

Effectiveness

Although this was not included in the inception logframe, it is important to note that the programme has done particularly well in this area. The fact that all seven Provincial governments used SuTRA for preparing their annual budget provides good evidence that the initiative has been effective.

Equity

% of PFMA-2 technical budget allocated to analytical work in hard-to-reach areas or to support federalism (e.g., SUTRA, Natural Resource Commission - budgetary allocations, cost index)
The entire technical budget has been dedicated to assignments which take into account and support federalism and its implications. This is particularly noteworthy of SuTRA.

Provision of non-management Component 1 and 2 technical input days (%) disaggregated by gender (Male and Female).: Positions in the team that are undertaken by females include Programme Director, MEL lead and Programme Administrator: However, the programme has been unsuccessful in resourcing female consultants to undertake technical assignments. One reason behind this has been utilisation of consultants with previous experience – which have been all male. However, the programme needs to make an active effort to secure more female technical experts.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

This £5m programme provides crucial assessments of fiduciary risk to the wider portfolio in DFIDN informing mitigation for significant parts of its roughly £85m annual portfolio. The fiduciary risk assessments at federal, provincial and municipal level will also help DFID understand risks and develop mitigation measures if it decides to channel financial aid at sub-national levels.
PFMA2 is a flexible and adaptive programme that has been proactive and politically savvy in identifying and delivering technical assistance to the government in order to support the implementation of federalism. As an example, the SuTRA system that is being developed through this programme is the only mechanism for the federal government to collect financial data from sub-national governments in order to prepare consolidated financial statements. Additionally, this system is crucial for development partners including DFID to get financial reports on local or provincial levels in case financial aid is channelled at those levels.

The system has also been developed locally, and the total cost of the local and provincial systems and conducting the training of trainers has only been £385k. Investment of £385k in the SuTRA system is expected to enable tracking of around USD 3.08 billion[3] in fiscal transfers to subnational governments, which is great value for money.
[3] Total fiscal transfers to provincial and local government for FY 2018/19

Besides being of economic value, the efficiency with which this has been delivered (less than one year in total) and implemented, and its effectiveness (used by about 200 plus municipalities and seven provinces) has also been impressive.

Other reforms in the pipeline are: Support to the Office of the Auditor General’s long term IT strategy to help the entity conduct risk based audit and carry out its expanded mandate; engagement on non-tax revenue and tax exemptions with Ministry of Finance; helping the Revenue Department rationalise and expand its revenue source in order to mitigate the budget deficit.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

The risk rating of the programme overall is moderate. The main delivery risks of this programme and their mitigation measures are highlighted below.

Absence of clearly shared approach on subnational PFM system: The implementation of Federalism and establishment of its institutions have led to significant change in mandates and personnel in the federal government during the first year of PFMA-2. The number of line ministries were rationalised and many civil servants were posted to Provincial governments throughout the country. In a context where institutional ownership is driven by personal choices, change in personnel in key client agencies has affected project delivery – mainly SuTRA. Although PEFA Steering committee has clearly made decision to adopt SuTRA as the subnational financial system, there seems to be an absence of a clearly shared approach amongst various stakeholders. PFMA-2 is trying to mitigate this through establishing and maintaining institutional relationships within the government and with relevant development partners to build a consensus on way forward.

Limited government capacity or incentives to implement identified reform plans: As an example, there is a risk that some local governments will reject the idea of using SuTRA, or that they may have limited capacity or personnel to use it properly.

This risk will be addressed by understanding the underlying constraints to reform and testing new incentives to trigger reform as well as providing tailored capacity building support.

Lack of coordination or unhealthy competition between development partners (DPs) for Public Financial Management reform programmes (central, local, sectoral): There could be competition even between development partners to carry out reform activities. For example, SuTRA has been a successful reform till date, other development partners or their suppliers are also interested in taking this forward, risking a decrease in the quality of implementation. This risk is mitigated through strong formal and informal engagement to ensure alignment.

Operational knowledge of donor activity and priorities is often communicated to PFMA-2 via DFID formally during liaison meeting and informally also. This helps to ensure alignment with needs and avoidance of duplication. DFID SRO will use PFM Multi-Donor Trust Fund as a forum for discussion with other DPs.

Sub-standard technical assistance to the government: This risk is high if national or international consultants with limited technical experience or limited contextual knowledge are used. This has also been a concern often expressed by the government.

However, the suppliers use high quality consultants that have previously delivered similar assignments. In addition, for Component 2 delivery, the suppliers share CVs and agree on the technical assistance personnel with DFID and the relevant government entity.

Compromised safeguarding and ethics: Project policies and practice to mitigate risk include independent “Delivery Reviews” by Crown Agents HQ, by members of staff not involved in the programme, renewal of compliance agreements in line with Crown Agents Ethical Code for partners, whistleblowing avenues are also in place and details shared.

Update on partnership principles (1/2 page)

Although PFMA2 is not providing any direct financial aid, this programme provides analysis and mitigation measures for fiduciary risks relevant to other financial aid programmes in DFID Nepal. The national level FRA rating conducted by the programme remains the same as the previous assessment in 2016, with fiduciary risk rated as substantial with a stable trajectory and the corruption risk rated as high with a stable trajectory.

With the implementation of federalism in progress, there has been significant change in partner Governments Public Financial Management systems. DFIDN sector programmes have either paused or stopped financial aid for this fiscal year in the current context. A DFIDN federalism task force has been formed to help strategise and adapt its portfolio for the new context. The PFMA2 programme will be carrying out municipal and provincial level FRAs in future that will inform wider office about fiduciary risk and mitigation measures for future decisions on financial aid.

DFID has two PFM centered programmes that are aligned to government’s PFM reform plan. A World Bank-managed Multi Donor Trust Fund (MDTF) on PFM is the platform to introduce systemic core PFM reforms; whereas this PFMA2 programme endeavours to provide more focused, high impact and quick support to the government to fill the gap that a more traditional programme like MDTF would not be flexible to deliver. DFID co-chairs the PFM technical working group, a donor coordination mechanism on PFM where donors meet on a quarterly basis to discuss emerging issues and risks, and escalate any significant concerns to the government. Additionally, DFID is also a member of federalism working group, another donor coordination mechanism which endeavours to discuss the broader federalism implementation agenda in order to support and help Governments plans.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial and financial issues (1-2 pages)

The main consortium partners for delivery of this programme are Crown Agents (as the lead), Team Consult (lead country partner), ODI and The Governance Group. The DFID programme team provided feedback to PCD on Strategic Relationship Management (SRM) scorecard on Crown Agents in July 2018. The suppliers’ performance on PFMA2 was rated as ‘Good performance’ – with a caveat that score is based on limited information as the programme is in early stages of implementation.

The majority of the programmes’ focus has been on development and institutionalization of SuTRA, delivery of which has exceeded expectations. Other deliverables have also been generally completed in line with agreed plan but there have been instances of delay, such as the PEA report and Component 1 methodology. However, Crown Agents communicate effectively and provide further information or explanation when and as needed. While the Crown Agents and Team Consult have been working with DFID closely and delivered effectively, DFID is keen to develop a clearer understanding of the value add of ODI and The Governance Group to the consortia. Specifically, ODI is expected to provide proactive political economic analysis (PEA) to inform the programme about risks and to identify opportunities for politically smart reforms. There is a risk that the lack of a locally stationed team to provide in-depth insight necessary at a regular basis may limit ODI’s ability to carry out this role. We believe it would be useful for the programme to revisit and clarify roles of partners in the consortium, considering VfM and interest in building a sustainable approach. .

Financial management of Crown Agents has been satisfactory. Monthly invoices are submitted every third week of the month except on some rare occasions when the supplier had to be chased. Invoices are generally accurate with few and minor alterations required. DFID has suggested including cumulative and balance days of consultants measured against resource plan in the inception report in the monthly invoices going forward for effective tracking of resource utilization. Forecasting has been good so far with variance below 10%. After the inception period, updated forecast was provided for legitimate programme changes. It is important to note that Crown Agents are amongst the first few suppliers who agreed on transparency of budget and provided their profit margin. Moreover, VfM indicator has been developed during the inception report and Crown Agents report the status on quarterly basis.

At the time of review, only 12% of the budget has been spent. Out of £5m of the total budget, £1.8m has been allocated as reserve fund for significant institutional reform opportunities under Component Three.

The table below shows cumulative spend under the PFMA components.

Component	Budget	Spent to date	Balance
Technical Assistance to support Public Financial Management and Accountability / (Component One and Two)	£3.03m	£0.49m	£2.6m
Institutional support on public financial management and accountability / (Component Three)	£1.9m	£131k	£1.8m
Total	£5m	£628K	£4.4m

The main cost driver for the programme is consultant fees which makes up 91% of the total spent to date.

Crown Agents is compliant with DFID terms and conditions and also understands DFID Aid Diversion Standards. They have provided their Ethical code for Business partners in response to our Aid diversion letter dated (Vault: 35369892). There is no change on the existing Delivery Chain mapping which was submitted in Jan 2018. Crown Agents submit updated assets list every six months. Audit report will be submitted after October 2018.

Date of last narrative financial report(s)	22/05/2018
Date of last audited annual statement (s)	NA

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

As the programme is only six months into implementation, a light touch review has been carried out by the SRO of the programme. The programme had been covered by the A2L Programme Manager for Governance and Service Delivery Team under supervision of the Deputy Team Leader during SROs maternity leave since January to June 2018. They have also been consulted during preparation of this Annual Review. The B2 Programme Manager for this programme provided administrative and financial inputs.

The programme is monitored continuously against deliverables by DFID SRO and Programme Manager. On a weekly basis, the suppliers send email listing activities conducted in the week and plans for next week. The Team Leader and SRO have monthly meetings scheduled to review progress and evaluate risks. Quarterly reports are submitted to DFID which include financial reports that track key
financial information such as expenditure incurred to date, amounts invoiced, comparison against
profiled budget and revised profile budget for next quarter, and value for money analysis. This is followed by quarterly review meetings with DFID. The Programme Manager and Director of the suppliers are also responsive as and when needed.

A set of evaluation criteria has been developed to aide decisions regarding use of Component Two for a new assignment. Every new assignment is evaluated against these criteria collectively by DFID and suppliers team to come to a decision. Broadly, this exercise includes evaluating if the proposed idea is of strategic value to DFID and to the government, and whether the programme has available resource and skillset to deliver quality service or product.

Semi-annually, all DFIDN programmes have an update meeting with the Head of Office which involves discussing key risks, opportunities and strategy going forward. Additionally, the SRO also has regular meetings with government counterparts to check quality of service delivery of the technical assistance provided. The SRO also seeks feedback with sector teams after assignments are completed by the suppliers.

Evidence (1/2 page)

The development of SuTRA software was the biggest single activity of PFMA-2 in year one of the project. This system is basic, low cost and has been progressively built one module at a time to allow phased testing and rollout. This methodology agrees with evidence[4] on critical success factors for implementing Integrated Financial Management Information System (IFMIS) in developing countries -“Incremental and iterative approaches that phase in IFMIS work best”. This is also a lesson learnt from DFID’s attempt to introduce a municipal administration and revenue system (MARS) through the predecessor programme. The component of the programme managed by ADB invested in the system that was piloted in Kathmandu municipality. Although locally made, the system included upto nine modules and was too advanced even for Kathmandu municipality. The project failed to think about capacity and constraints beyond Kathmandu and did not include a plan to expand the pilot further.
[4] https://www.gov.uk/dfid-research-outputs/implementing-integrated-financial-management-information-systems-gsdrc-helpdesk-research-report-1229

The ‘rapid development’ approach to SuTRA and the immediacy of imperatives (such as statutory deadlines) to implement created an environment where learning evidence could best be obtained at high output levels. The programme has completed and handed over users’ manual for municipal module to the government, based on which training have been conducted. The programme has maintained a register of users of SuTRA (200+ Municipalities and all seven Provinces) and judged success by the extent to which statutory functions (primarily accounting and budgeting) were fulfilled using SuTRA. Perhaps the clearest evidence of learning was that all seven Provinces used SuTRA to create the annexes to their budget speeches and publish their annual appropriations. The programme had submitted a handover booklet to the government that for municipal system in January 2018 and the handover document for the provincial system is scheduled to be completed by September 2018..

Learning (1/2 page)

The programmes approach to Component One that provides fiduciary risk coverage to DFIDN portfolio has not been systematic. The assignments have been conducted on an ad hoc basis until now. However, the SRO has recently circulated an email to all staff at DFIDN advertising service available from Component One and sharing a systematic approach for accessing the service.

The learning has been more explicit on SuTRA development. Major lessons are as follows:

Firstly, the lesson has been that as for any reform, understanding the political positions and incentives of decision-makers and users is essential to get buy-in and identify opportunities to advance system development. This includes internal institutional dynamics between ministries, financial incentives and access to power of competing systems, and competition between development partners for successful reform initiatives amongst others.

Second, rapid system development is possible given clear ownership and need of the government. DFID identified early on that an IT system was needed to bridge the gap between federal and subnational governments to capture fiscal transfers and their reporting – ultimately contributing to consolidated financial statement. Even when there have been competing interests, the government has pushed forward this initiative because it serves their fundamental need. Also, it is equally necessary to identify ‘champions’ within the government that are willing to invest their time and protect and defend the system when necessary.

Third, institutionalization should go hand in hand with system development. This includes a sustainable plan beyond just few days training introducing the system to the users – also evident from the failure of VDC Accounting Software also initiated by the predecessor programme.

Progress on recommendations from previous reviews (1/2 page)

DFID and its service providers need to be flexible and adaptive, based on evolving political dynamics of the country to ensure the programme remains responsive, relevant and manages risks.
  1. PFMA2 has continued to be flexible and adaptive, and has very well responded to emerging areas of reform. The programme is well abreast with political dynamics affecting its projects and

DFID to finalise the overarching PFMA logframe and Value for Money matrix by the end of the inception phase, by December 2017.

  1. This was completed, but the inception phase was extended to January 2018 due to bereavement in supplier’s side. Logframe now needs revision based on this annual review.

Continue strong coordination and communication with other development partners (DPs), DFID programmes and other stakeholders at the national and provincial level to ensure coherence, avoid duplication and support the effective transition of functions to the local level.

The PFMA2 suppliers as well as the SRO continue to coordinate with other development partners on different forums. The SRO is also a member of the federal task force within the DFID office that helps in coordination with other programmes.

Smart Guide

The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.

The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided