Type of Review: Project Completion Review (Multilateral Organisation Core funding)

Title of funding stream: Commonwealth of Learning Three Year Plan, 2009-2012

Date started: 1 January 2009	Date review undertaken: September 2012
Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
The Commonwealth of Learning (CoL) is an intergovernmental organisation created by Commonwealth Heads of Government that has been operational since 1989. It is financially supported by Commonwealth governments on a voluntary basis[1]. DFID provided £1.1 million annually to support the programmes set out in its three year plan, Learning for Development, which ran from July 2009 to June 2012.
[1] Although it receives additional contributions from international agencies, foundations and national governments for specific projects and services.

What were the expected results?
Impact / At the impact level, DFID expected CoL to be able to show progress against its mission - “To help governments and Institutions expand the scope, scale and quality of learning by using new approaches and technologies, especially those subsumed under the general term of open and distance learning”. More specifically, we expected to see: / target countries improving the accessibility and quality of their formal education systems at all levels through the use of Open and Distance Learning (ODL) tools and strategies. / the income, livelihoods, and quality of life of communities and their members improving through new knowledge, skills and economic opportunities gained by the use of ODL tools and strategies / Outcome / DFID’s support was expected to help Commonwealth developing countries to expand their access to quality education and training by harnessing appropriate technologies – and to achieve the following more specific outcomes corresponding to CoL’s eight programme areas: / Open Schooling[2] - Countries plan and implement open schooling as a means of increasing access to learning opportunities at the secondary level; / Teacher Education - More teacher education and training institutions use ODL methodologies to train and upgrade larger numbers of teachers; / Higher Education - Higher education institutions have policies, systems and staff competencies that support the use of ODL to increase learner access and completion rates while enhancing curricular content; / Virtual University for Small States of the Commonwealth - VUSSC partners produce and deliver relevant courses using e-learning strategies that are scalable and sustainable; / Skills development - Training institutions and civil society organisations have the policy frameworks and increased capacity needed to develop and deliver ODI materials for strengthening knowledge and skills in both formal and non-formal learning environments; / Learning for Farmers – Resource-poor farming communities, in collaboration with CoL and partner institutions, use ODL to increase their knowledge and skills to access new information, training and finance that improves their livelihoods through various economic activities; / Healthy Communities – Community organisations, NGOs and local public institutions have increased their capacity to create and use ODL materials to improve the health and well-being of their communities; / E-learning – Institutions and communities use digital technologies to design and develop learning materials and models that are made available, where possible, as open educational resources[3] and to provide effective and appropriate skills training. / In all these outcomes there was expected to be strong evidence of quality, gender equality, and the use of appropriate technologies.
[2] Open Schooling is defined by two elements (i) the physical separation of the school-level learner from the teacher, and (ii) the use of unconventional teaching methodologies and information and communications technologies (ICTs) to bridge the separation and provide the education and training.
[3] Open Educational Resources (OER) are digital materials that can be re-used for teaching, learning, research and more, made available free through open licenses, which allow uses of the materials that would not be easily permitted under copyright alone

What was the context in which UK support was provided?
The Commonwealth is a voluntary association of independent sovereign states, which provide support to each other, and work together toward international goals. It brings together some 1.7 billion people from over 50 countries, most of which were originally connected by the British Empire. Building on the use of English as a common language and other cultural and educational links, they work together to: / Promote partnership and co-operation among its members. / Promote understanding and tolerance among its citizens. / Reduce prejudice, ignorance, disease and poverty. / Promote democracy and good governance, sustainable economic and social development, respect for human rights and the rule of law, gender equality and protection of the environment. / The Coalition Agreement has a stated aim “to strengthen the Commonwealth as a focus for promoting democratic values and development” and DFID is committed to supporting both the role of Commonwealth institutions in development and Commonwealth developing countries themselves. DFID’s support for CoL is part of a multi-faceted portfolio of DFID support to Commonwealth development programmes. This aims to complement assistance provided through the bilateral aid programme and through other multilateral channels; and to build on the Commonwealth’s strengths as set out above. It encompasses: / Intergovernmental cooperation through the Commonwealth Fund for Technical Cooperation and the Commonwealth Youth Programme; / Local government capacity building through the Commonwealth Local Government Forum; / Civil society strengthening through the Commonwealth Foundation; / The promotion of open and distance learning through the Commonwealth of Learning; / Scholarships and fellowships to academics and professionals through the Commonwealth Scholarships Commission. / The CoL is an intergovernmental agency created by the Commonwealth Heads of Government to encourage the development and sharing of open learning and distance education, knowledge, resources and technologies. It operates on the premise that knowledge is the key to individual freedom and to cultural, social and economic development. / The CoL is the only intergovernmental agency focused on Open and Distance Learning (ODL). Countries have long sought help with expanding teacher education and more recently they are looking into improving the provision of secondary education to cope with the success of Universal Primary Education. More recently, the CoL has broadened its activities into modes of learning that are vital for achieving development goals in poverty reduction and health, for example: / Fighting hunger and improving prosperity by engaging farmers and other rural people in livelihood-related learning. / Improving the health of mothers and children and arresting the spread of disease through the use of participatory community media. / Education is fundamental to everything DFID does. It is key to beating poverty and transforms countries and societies, as educated people are able to take better care of their families and find greater employment opportunities. Access to usable knowledge enables people in developing countries to take rapid advantage of favourable changes and distance learning enables teachers to upgrade their skills. CoL’s outcomes are consistent with DFID’s education work, and in DFID focus countries, support the achievement of DFID results, in particular: / The number of children in primary school; / The number of children in secondary school (with a focus on girls) / Training teachers and improving the quality of education and children’s’ learning.

## Section A: Detailed Output Scoring

Output 1: Open Schooling: countries plan and implement open schooling as a means of increasing access to learning at a secondary level
Output 1: final score and performance description: A – Outputs met expectation / Expectation: New schools opened in 2 countries and 10 existing schools significantly extended. / Final results: Exceeded. Open schools were established in five countries (Ghana, Kiribati, Tonga, Papua New Guinea and India (Assam). The evaluation of the CoL 2009-2012 Plan[4] recognises that this was an ambitious target and the fact that it was exceeded is impressive. Since July 2009, open schooling has taken root in the Pacific, reached out to the Caribbean and made further progress in Africa. Ten open schools have been ‘extended’, in so far as the CoL has clearly supported institutional development in a number of existing schools. / Expectation: Open Schools in 6 countries offer new high quality courses in 20 subjects. / Final results: Partially achieved. Courses in 18 subjects have been developed in six countries (Botswana, Lesotho, Namibia, Seychelles, Trinidad and Tobago and Zambia). The two subjects outstanding are at an advanced stage and will be completed this year. A review of the materials and a sample survey of teachers concluded that while the materials do not as yet constitute high quality, a very firm base has been established on which to make the final recommended revisions[5]. There may still be work to do before the materials are in the shape envisaged by the project objectives, but good progress has been made. / Expectation: 10 Secondary schools adopt open education resources (OER) as a central part of their learning strategy / Final results: Partially achieved. OER has been adopted in six open schools in the six countries taking part in the Hewlett funded project[6] (Botswana, Lesotho, Namibia, Trinidad and Tobago, Seychelles and Zambia). CoL informed us that progress has been made for adoption in more than 10 countries. This is turning out to be a slower process than CoL expected.
Impact Weighting (15%): / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? Y - risk not specified in the logframe
[4] Patrick Spaven, Evaluation of the Commonwealth of Learning 2009-2012 Plan, Report 13 December 2011
[5] SAIDE (South Africa Institute for Distance Education)
[6] CoL’s largest open schooling project in OERs with US$750,000 from the William and Flora Hewlett Foundation (WFHF)

Output 2: More teacher education and training institutions use ODL methodologies to train and upgrade a larger number of teachers
Output 2: final score and performance description: A+ Outputs moderately exceeded expectation / Expectation: Number of trained new and existing teachers is significantly increased in 4 major institutions and across 3 Commonwealth regions using ODL / Final results: Largely achieved. Four major institutions in Africa and Asia use ODL to train/ upgrade new and existing teachers. However, in terms of regional spread, only two regions were reached. / Expectation: Teacher education institutions in 4 countries offer significantly improved curriculum content through the development and use of OER. / Final results: Exceeded. 10 teacher education institutions in six countries (Sierra Leone, Nigeria, Zambia, South Africa, Uganda and India) have significantly enhanced the content of their curriculum through the use of OERs. . Multilingual OERs have been developed through CoL’s partnership with the Teacher Education in sub-Saharan Africa (TESSA), as well as resources for English Language Teaching (ORELT). / Expectation: Institutions in 6 countries adopt the Child Friendly Schools (CFS) approach
Final results: Exceeded. Nigeria, Botswana, Swaziland, Lesotho, South Africa, Sri Lanka and Zambia have adopted the CFS approach. The December 2011 evaluation remarks that the project was well designed, there appear to be high levels of satisfaction with the project in four evaluated countries and meeting this target represents a solid achievement for the project. / Impact Weighting (15%): / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? Y - risk not specified in the logframe

Output 3: HEIs have policies, systems and staff competencies that support the use of ODL to increase learner access and completion rates whilst enhancing curricular content
Output 3: final score and performance description: A – Outputs met expectation / Expectation: 4 major institutions in at least two Commonwealth regions begin or increase numbers educated through ODL. / Final results: Achieved. Twelve higher education institutions (HEIs) in four regions adopted ODL or increased numbers educated in this way. Three institutions started offering ODL courses[7]; and nine partner institutions enhanced the number of learners enrolled in the Commonwealth Executive Masters of Business/ Public Administration (CEMBA/PA) ODL programmes, with graduate figures more than doubling from 2031 in 2006-09 to 5396 in 2009-12. / Expectation: New or improved curriculum content is in use in HEIs in 4 countries / Final results: Partially achieved. The revision has taken longer than anticipated, but the initiative is nearing completion. 8 courses were ready for dispatch to 4 institutions by June 2012, and 4 new case studies are being used by 4 partner institutions. / Expectation: Quality Assurance mechanisms are adopted by 4 tertiary institutions. / Final results: Exceeded. The Higher Education Review and Improvement Model (COL RIM) was implemented in six HEIs[8] Implementation of COL RIM in 5 other HEIs is expected to be completed in 2012. The December 2011 evaluation commented that COL RIM was an area of work that attracted most positive comments and appears to be a well-crafted instrument that is addressing a clear and substantial demand.
Impact Weighting (10%): / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? Y - risk not specified in the logframe
[7] Mico University College (Caribbean), USP (South Pacific) and National Law University (India)
[8] UTech Jamaica; University of Calabar, Nigeria; OUSL; Dominica State College, Caribbean; NIHSS, Seychelles; and SIM Seyschelles.

Output 4: Virtual University for Small States of the Commonwealth (VUSSC) partner institutions produce and deliver relevant courses using eLearning strategies that are scalable and sustainable
Output 4: final score and performance description: A – Outputs met expectation / Expectation: 8 new courses are developed and 2 institutions in 3 Commonwealth regions offer a total of 6 VUSSC courses. / Final results: Exceeded. Ten courses and four programmes have been developed, ranging from certificate to master’s degree levels. Six institutions in 4 regions are using VUSSC developed content and offering courses. / Expectation: Agreements are in place committing 10 member states to take responsibility for the on-going management of VUSSC. / Final results: Partially achieved. To date there are 33 member states participating in the VUSSC consortium. As at November 2011[9], a VUSSC Management Committee representing all regions of the Commonwealth had been set up, but was still heavily dependent on CoL (e.g. CoL provides or attracts most of the funding, convenes the interlocutor meetings and organises the inter-state workshops). There seemed to be little inter-state networking and the CoL is still the driver of the VUSSC. / Expectation: NQAs in 6 VUSSC member states will ensure the implementation of the Transnational Qualifications Framework (TQF). / Final results: Achieved. The CoL report that the six members of the TQF management committee (representing all regions of the Commonwealth) have taken the responsibility to ensure the successful implementation of the TQF. / Impact Weighting (10%): / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? Y - risk not specified in the logframe
Output 5: Training institutions and CSOs have the policy frameworks and capacity needed to develop and deliver ODL materials for formal and non-formal learning and environments
Output 5: final score and performance description: A – Outputs met expectation / Expectation: 6 institutions in at least 2 Commonwealth regions begin technical vocational education or significantly increase the number educated, through ODL. / Final results: Exceeded. CoL reports that seven African institutions are offering new, flexible courses and have increased enrolment in existing ODL courses. In the Pacific, 7 countries participated in writing a new ODL course in vocational literacy. Fifteen institutions piloted the course. / Expectation: New or improved curriculum content in technical vocational education is in use in institutions in 4 countries / Final results: Achieved. CoL reports that in Kenya, Nigeria, Zambia and Tanzania, Technical Teacher Vocational Training (TVET) Principals and teachers reported the use of new teaching approaches and media enhanced curriculum content. Additionally in Fiji a Community Education and Training Centre is using newly developed distance learning resources to improve its programme. / Expectation: 3 new skills development courses (in addition to VUSSC courses) are available as OERs and used by institutions in 4 countries
Final results: Partially achieved. CoL reports a new OER course in vocational literacy has been developed and used in 6 Pacific countries. Three courses in TVET teacher training were developed in Trinidad and Tobago and are available as OER. Support provided to the Nursing Council of Kenya (NCK) did not yield the promised degree level nurse education course, as NCK are disinclined to make them available as OER. / Impact Weighting (15%): / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? Y - risk not specified in the logframe
[9] Patrick Spaven, 13 December 2011 Evaluation

Output 6: Resource-poor farming communities collaborate with COL and others to use ODL to increase skills, knowledge, and gain access to information, training and financing that improves their livelihoods through economic activities.
Output 6: final score and performance description: A+ - Outputs moderately exceeded expectation / Expectation: Members of farming communities in 6 countries in 4 Commonwealth regions have significantly improved economic circumstances through ODL / Final results: Partially Achieved. CoL reported that members of farming communities in 4 countries in two commonwealth regions (India, Sri Lanka, Kenya and Uganda) have significantly improved their income and food security through ODL. In India, credit and income worth $6m were generated among 6,000 women. This has attracted the attention of 40,000 farmers and 8 banks that have joined the Lifelong Learning for Farmers (L3F) movement. The December 2011 evaluation is of the opinion that this is a longer-term outcome and the innovativeness of L3F means that it needs time to produce stronger results. / Expectation: 4 government or international organisations adopt Lifelong Learning for Farmers (L3F) models in 2 Commonwealth regions / Final results: Achieved. CoL reported that 5 government and international organisations in 3 Commonwealth regions have adopted L3F models. However, in their progress report only 4 examples are given. The L3F approach is being taken up by the Ministry of Cooperatives in Kenya, Ministry of Agriculture in Uganda, national Institute of Bank Management in India and Department of Export Agriculture, Sri Lanka. / Expectation: 20 organisations in 3 Commonwealth regions strengthen their capacity in ODL to address farmers’ learning needs. / Final results: Exceeded. CoL reported that 26 organisations in 4 Commonwealth regions have built their capacity in ODL to address farmer’s learning needs
Impact Weighting (10%): / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? Y – risk not specified in the logframe

Output 7: Community Organisations, NGOs, and local public institutions have increased their capacity to create and use ODL materials to improve the health and wellbeing of their communities
Output 7: final score and performance description: A+ - output moderately exceeded / Expectation: 40 community organisations, NGOs, and local public institutions in at least 20 countries in 4 Commonwealth regions begin to use, or significantly enhance or extend their use of, ODL / Final results: Exceeded. CoL reported that 61 local organisations – including community-based organisations, NGOs and local health offices – are actively engaged in the design and delivery of community based ODL programmes in all regions of the Commonwealth. / Ten national/ regional organisations across the Commonwealth are actively engaged in using, promoting and/ or training local-level groups in community-based ODL. / Coverage extends to 16 countries in 4 regions. / Expectation : 16 new health-related ODL programmes are used by communities in 4 regions of the Commonwealth
Final results: Largely achieved. Seventeen programme series have been used by 16 local communities in 10 countries in three regions. Topics include maternal health, HIV and AIDS, non-communicable disease and environmental health. / Impact Weighting (10%): / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? Y - risk not specified in the logframe

Output 8: Institutions and communities use digital technologies to design and develop learning materials and models that are Open Education Resources where possible, and provide effective skills training
Output 8: final score and performance description: A – Output met expectations / Expectation: 10 major institutions in at least 2 Commonwealth regions use OER for their curricula. / Final results: Largely achieved. CoL report that eight institutions in three regions are using OER for their curricula. Three institutions in Guyana developed teacher training materials for the use of ICT in their curriculum and it has been adapted for seven Caribbean and Pacific Institutions. Through the East African Health Alliance, five institutions in Rwanda, Uganda, Tanzania and Kenya are developing and using OER in Public Health. / Expectation: Additional low-cost ICT training models are in use in 8 institutions in 4 Commonwealth regions / Final results: Largely achieved. The Commonwealth Certificate for Teacher Integration (CCTI) distance education-mentor based model has been in use in 10 institutions in two Commonwealth regions (mainly in the Caribbean, where 224 mentors and over 1,300 teachers were trained in this way). The mobile (m)Learning model for support in formal schooling has been developed and deployed in three institutions/countries, including Tanzania and Kenya.
Impact Weighting (15%): / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? Y - risk not specified in the logframe

## Section B: Results and Value for Money.

1. Achievement and Results

1.1 Has the logframe been changed since the last review? N / 1.2 Final Output score and description: A – Outputs met expectation
1.4 Overall Outcome score and description: A – Outcome met expectation / Outcome – To help developing Commonwealth countries to expand access to quality education and training by harnessing appropriate technologies. / Indicator (i) – CoL interventions have led to high quality ODL design and delivery. / Indicator (ii) - The use of technology advocated by CoL has been relevant to the outcomes sought / Both these indicators are taken from CoL’s Logic Model for their 2009-12 Three Year Plan. They were intended to assess progress against two of the three cross-cutting themes of CoL’s work (the third being gender). The target in both cases was that 80% of independent evaluations of CoL activities and 80% of stakeholders in the triennial survey concur with the statements. / CoL’s reporting does not explicitly address progress against these targets. However the Progress Report to the June 2012 Board of Governors meeting asserts on relevance that: / The 2009-12 three year plan was developed after consulting widely in the Commonwealth, and focused specifically on the expressed needs of Member States; / CoL has a very wide range of stakeholders, and is responding to the needs of this large constituency through appropriate strategies; / CoL has developed Country Action Plans based on discussions with country Focal Points and partners; / CoL’s work is focused on meeting the challenges of relevant MDGs and Education for All goals. / The December 2011 evaluation notes that CoL has not actively monitored these two cross-cutting dimensions during the triennium – but states “there is no evidence however that [CoL] has failed to promote quality and appropriate technology in any aspect of its work”. / Among its general conclusions, the 2011 evaluation states: / “…CoL looks and feels like a different organisation from the one encountered in 2005. In all the teams, there is a palpable striving to be relevant and to create deep and long-term effects.” / “…CoL has not lost its disposition and ability to be needs-driven and to listen to what this means for particular clients.” / “Probably the clearest manifestation of CoL’s transition to more outcomes-oriented approaches is its concentration on the development and application of innovative models for ODL.” / The general picture which emerges from the 2011 evaluation, and which is corroborated by both the progress reporting against CoL’s eight initiatives and DFID staff’s interaction with CoL and its staff, is of an organisation fulfilling its mission, meeting its targets and performing well.
1.5 Impact – Governments and Institutions expand the scope, scale and quality of learning by using new approaches and technologies, especially those subsumed under the general term ODL. / Indicator (i) – Target countries improve the accessibility and quality of their formal education system at all levels through the use of ODL tools and strategies. / This indicator is intended to assess the impact of CoL’s education initiatives, ie Outputs 1 to 4 above. No baseline or target specific to this indicator has been identified. / CoL’s report to the June 2012 Board states that its education sector work is making progress towards impact as more institutions adopt ODL and expand the coverage and quality of their programmes so that more Commonwealth citizens acquire relevant knowledge and skills that will enable them to lead healthy and productive lives – this is borne out by the progress against outputs reported above. However the Board report also notes that there is a need for concrete data to shed more light on the extent to which CoL’s initiatives in education have made a difference to student outcomes. / The 2011 evaluation was intended to assess the impact of CoL’s work since the 2003-06 triennium. However the evaluation report notes that this proved extremely difficult because: / Few of CoL’s areas of work had continuity back to the 2003-06 period, and; / With one exception (not in the education sector), the external evaluations conducted on specific CoL programmes were not designed as impact assessments. / Given these limitations, the evaluation does not reach any explicit conclusions on impact. But its analysis of the individual education initiatives suggests that they have not had the impact which was anticipated. One of the evaluation’s conclusions was that, to fully realise the potential of its work, CoL needs to: / “…build intensive outcome monitoring and evaluation as standard into its planning for interventions with models.” / “…put more time into researching, discussing, designing and implementing strategies for replication and upscaling.” / Indicator (ii) – The income, livelihoods and quality of life of communities and their members are improved through new knowledge, skills and economic opportunities gained by means of ODL tools and strategies. / This indicator is intended to assess the impact of CoL’s livelihood and health sector initiatives, i.e. Outputs 5 to 8 above. No baseline or target specific to this indicator has been identified. / CoL’s report to the June 2012 Board states that Governments and development agencies have become increasingly aware of the scope of ODL in adding value to the development process. Studies of individual initiatives show that ODL can effect changes in health-seeking behaviours, empowerment and income. There is clear evidence in the CoL progress report of ODL tools being used to reach large numbers of people – for example: / 50,000 women and men learning daily through mobile phones to enhance livelihoods in Asia and Africa and / 8,000 active learners and an estimated 100,000 listeners in 10 countries have new opportunities to learn about Mother and Child Health, HIV and AIDS, non-communicable diseases and environmental health. / However the Board report also states that further evidence is needed to determine the extent of CoL’s impact in the field. And, as noted above, the 2011 evaluation report assessed that it was very difficult to reach any conclusions on impact. That said, the evaluation does cite some cases where ODL tools have been shown to have a positive impact – it states for example that the Learning for Farmers initiative “…can - in certain circumstances - make a significant difference to people’s livelihoods.” In a review of the L3F, a World Bank report concludes that ‘the use of ICT such as mobile phones for learning influenced development outcomes because the learning experience was tailored to women’s cognitive social capital and reinforced by links with commercial banks.’ (ICT in Agriculture Sourcebook: Connecting Smallholders to Knowledge, Networks and Institutions, The World Bank, 2011). According to World Watch Institute, ‘Because L3F Uganda adapts its educational tools to fit farmers’ lifestyles and technological capacities, rather than imposing costly or time-intensive educational programmes on farmers, the project can make real advances in empowering farmers and improving their livelihoods’ (Mobile Phone Technology Improves Farmers’ Fortunes in Uganda, World Watch Institute, 2012). / As with the education initiatives, the evaluation concludes that the initiatives need to be validated, refined and scaled up to achieve the anticipated impact.

2. Spending profile and timescale
2.1 Was the spend profile detailed in the Business Case followed: Y / 2.2 Were any additional payments linked to good performance triggered: Not Applicable

3. Evidence and Evaluation
3.1 Assess any changes in evidence / The CoL evolved from the 1987 Vancouver Commonwealth Heads of Government meeting, in the belief that (i) the use of distance education can deliver cost effective quality education in developing commonwealth countries and (ii) rapidly developing communications technologies should be harnessed to assist with people’s education. No evidence has emerged to contradict this assertion. / At the level of the individual initiatives, 10 independent evaluations (“longitudinal studies”) have been conducted to assess the effectiveness of specific projects or activities. The findings of some of these studies and other evidence gained from on-going experience have influenced programme design. Examples cited by CoL staff include: / The SADC Centre of Excellence - realisation that this was not performing as anticipated led CoL to review the initiative, reduce the budget and identify alternative fund-raising mechanisms; / The Commonwealth Executive MBA – the emergence of private funding for this initiative led CoL to change their funding model and strategy; / Child-friendly Schools – the programme was supposed to be entirely done by distance learning. But on review it became clear this was not possible in the timescale envisaged, so face-to-face training was introduced in some places. / However as noted above, the 2011 Evaluation identified a need for CoL to do more to capture and use evidence to validate, refine, upscale and diversify its activities. / 3.2 Set out what plans are in place for an evaluation. / CoL commissioned an independent evaluation of its work under the 2009-12 Three Year Plan to inform plans for the Three Year Plan for 2012-15. This was carried out by consultant Patrick Spaven in December 2011. The 4 key questions which the evaluation tried to answer were: / To what extent has CoL made a difference in the life of its current TYP? / What lessons can CoL, its Board of Governors and partners, take from the operation of the plan into the next TYP? / How appropriate are the two strategic sectors, Education and Livelihoods and Health, in realising the aims of the current TYP? / What has been the impact of CoL’s work since the 2003-06 TYP? / The evaluation can be found on CoL’s website at http://www.col.org/resources/publications/Pages/detail.aspx?PID=390. / It contains detailed conclusions and recommendations on each of CoL’s programmes, its cross-cutting themes (gender, quality and appropriate technology), knowledge management and results-based management. Some of the key conclusions and recommendations not referred to elsewhere in this PCR include: / “…CoL understands the need to build sustainability into its interventions.” / “CoL has made good progress with its results-based management so far” / “CoL should focus even more on a small number of substantial medium to long-term interventions.” / “A focus on 4-6 major interventions suggests that CoL should reduce the number of Initiatives.” / “CoL should not shy away from external funding opportunities, particularly where it is ready to take a model to a bigger stage.” / “CoL should develop short strategic plans for each Initiative. They should be built around a logic model or theory of change that links key actions and outputs for each “Activity” to the Initiative outcome.” / “CoL should institutionalise monitoring and evaluation planning with the implementation of the new TYP”.

4. Risk
4.1 Overall Risk Rating: Medium / Did the Risk Rating change over the life of the project? Y – risk not specified in the logframe / 4.2 Risk funds not used for purposes intended / The risk is assessed as low. CoL has a transparent accounting and budgeting system. Audited accounts are presented by the external auditors to the Audit Committee and the Board for scrutiny – DFID is represented on both bodies. The accounts have been unqualified in recent years, and no cases of suspected or actual fraud have been reported. About 30% of COL’s budget is spent on CoL salaries with the largest proportion going directly to programme costs,. / 4.3 Climate and Environment Impact / If the Business Case identified improvements within the multilateral organisation’s approach to climate change and the environment as a priority, provide details of progress against the identified weaknesses. Otherwise leave this section blank. / CoL has a programme with the Commonwealth Foundation to integrate climate and environment considerations into its projects. It has developed a strategy and has initiated action in some programmes such as Lifelong Learning for Farmers and the VUSSC.

5. Value for Money
5.1 Performance on VfM measures / No VfM measures were identified at the time of project approval or during the period under review. / 5.2 Commercial Improvement and Value for Money / CoL report that they have reduced expenditure on travel from 14% to 9% of total budget, without an adverse effect on results, by making greater use of IT e.g. Skype conferences and on-line training. They have leveraged in-kind contributions, e.g. from the Government of Singapore for meeting costs, to reduce their own expenditure. / CoL has an established contract management system with clear procedures for letting contracts. Staff have to justify recruitment of consultants – all proposals are vetted by the Director (Finance, Administration and Human Resources). CoL operates a fees schedule for jobs – the rates are modest. National or regional consultants are engaged wherever possible to save on air fares etc. CoL are trying to diversify their consultant base though the scope is limited due to the specialised nature of their work. / Value for Money considerations are applied to decisions on programme development. For example investment in an education initiative in Sri Lanka was stopped when it emerged that introduction of ODL had not improved graduate output. / 5.3 Did the funding represent Value for Money: Y / CoL appears to be providing a well-targeted range of results-oriented programmes, which meet real demand from members and do not duplicate the activities of other organisations. They operate efficiently and effectively on a relatively modest budget in a niche market. However there is only limited evidence of impact on broader development outcomes to date.

7. Conclusions
CoL is a small but important and valued partner that helps developing Commonwealth countries expand the scope, scale and quality of learning through innovative use of open educational resources and modern technology. On the face of it, CoL has made good progress and no output is underperforming. However there are question marks over its ability (and perhaps desire) to focus more on those activities which have greatest development impact, and to work with its partners to replicate and scale up these activities. CoL is currently an innovative niche operator – with encouragement it should be able to play a more significant role in development. There seems a good case for continuing DFID support. / But DFID needs to ensure that it can better measure success for future support. Baselines and targets should be included in the project logframe for the next business case and a more thorough risk assessment will be needed, particularly on oversight of DFID funds. The next DFID business case needs to be clear about what we would like the CoL to deliver and the theory of change that will bring it about. We also need to be able to demonstrate more clearly how CoL delivers value for money. These will be the points on which to improve, when drafting the business case for a future phase of support. / There is very little focus on how gender has been addressed (other than saying it’s a cross cutting issue) and what progress has been made. This is important across all outputs, but particularly open schooling as it is linked with DFID’s results focus on girls, especially transition to secondary. CoL should provide data and evidence against its gender indicators for future projects. / There should be a stronger link between any future CoL programme and DFID’s education programme. In education these include: number of children in primary school supported; number of children in secondary school supported (especially girls); and number of teachers trained. There may be other relevant results outside of education. Greater evidence of impact in these areas (and others) is important going forward.

8. Review Process
The review was conducted by the Deputy Programme Manager for CoL, and quality assured by the Senior Responsible Officer within United Nations and Commonwealth Department, DFID, with inputs from the head of DFID’s Education Policy team (who is also the UK representative on CoL’s Board). It covers the period 01/01/2009 to 30/06/2012.